R PHY_CCAP_WRB_RPHY Bundled Solution V3_44119 | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-04-15 | 2020-08-31 |  | Active | Log | Upd | SN-0263 | Schedule Change | Approved | 2020-02-21 16:27 | Requesting Santa Barabara and Warner Robins to be accelerated into Q2 due to the following reasons Santa Barbara - To move the nodes from existing 10Ks to RPHY to alleviate the node conjestion Warner Robins - This is to get the site RPHY Ready for the
R PHY_CCAP_WRB_RPHY Bundled Solution V3_44119 | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-07-10 | 2020-10-30 | 2020-10-30 | Active | Log | Upd | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_WRB_RPHY Bundled Solution V3_44119 | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-07-10 | 2020-07-31 | 2020-07-31 | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_WRB_RPHY Bundled Solution V3_44119 | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-07-10 | 2020-08-31 | 2020-08-31 | Active | Log | Upd | SN-0742 | Schedule Change | Approved | 2020-07-10 10:13 | RPHY CCAP POR Update for Warner Robins and South Pecue facilites
R PHY_CCAP_WRB_RPHY Bundled Solution V3_44119 | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-07-10 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0811 | Schedule Change | Approved | 2020-08-07 09:40 | This is to update RPHY CCAP POR for CLR WRB SAB and PNS sites
R PHY_CCAP_BAR_RPHY Bundled Solution V3_44119 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_BAR_RPHY Bundled Solution V3_44119 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_BAR_RPHY Bundled Solution V3_44119 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
RPHY MRTR-New2-PAV-CIN-RPA-5110 | CA | ORG | PAV | R PHY | R PHY CA ORG PAV RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Deleted | EP
RPHY MRTR-New2-PAV-CIN-RPA-5110 | CA | ORG | PAV | R PHY | R PHY CA ORG PAV RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Deleted | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New2-PAV-CIN-RPA-5110 | CA | ORG | PAV | R PHY | R PHY CA ORG PAV RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | Log | Del | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-Growth2-DWN-CIN-RPA-5110 | CA | SAN | DWN | R PHY | R PHY CA SAN DWN RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Deleted | EP
RPHY MRTR-Growth2-DWN-CIN-RPA-5110 | CA | SAN | DWN | R PHY | R PHY CA SAN DWN RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Deleted | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth2-DWN-CIN-RPA-5110 | CA | SAN | DWN | R PHY | R PHY CA SAN DWN RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | Log | Del | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-SAB-CIN MGMT-2K | CA | SAB | SAB | R PHY | R PHY CA SAB SAB RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 12 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-SAB-CIN MGMT-2K | CA | SAB | SAB | R PHY | R PHY CA SAB SAB RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-04-01 | 2020-06-15 | 2020-06-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-SAB-CIN MGMT-2K | CA | SAB | SAB | R PHY | R PHY CA SAB SAB RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-07-05 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-SAB-CIN MGMT-2K | CA | SAB | SAB | R PHY | R PHY CA SAB SAB RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-04-05 | 2020-06-01 | 2020-06-01 | Active | Log | Upd | SN-0270 | Schedule Change | Approved | 2020-02-21 16:29 | 1 Pulling in Warner Rbins and Santa Barbara into Q2 2 OCML in Warner Robins is not covered in the current budget, adding that to the plan 3 New OCML request to be raised seperate 4 Total Pull IN of 520K
RPHY MRTR-New-SAB-CIN MGMT-2K | CA | SAB | SAB | R PHY | R PHY CA SAB SAB RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 12 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-SAB-CIN-DPA-5200 (100G DPIC) | CA | SAB | SAB | R PHY | R PHY CA SAB SAB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-SAB-CIN-DPA-5200 (100G DPIC) | CA | SAB | SAB | R PHY | R PHY CA SAB SAB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 4 | 2020-04-01 | 2020-06-15 | 2020-06-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-SAB-CIN-DPA-5200 (100G DPIC) | CA | SAB | SAB | R PHY | R PHY CA SAB SAB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 4 | 2020-07-05 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-SAB-CIN-DPA-5200 (100G DPIC) | CA | SAB | SAB | R PHY | R PHY CA SAB SAB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 4 | 2020-04-05 | 2020-06-01 | 2020-06-01 | Active | Log | Upd | SN-0270 | Schedule Change | Approved | 2020-02-21 16:29 | 1 Pulling in Warner Rbins and Santa Barbara into Q2 2 OCML in Warner Robins is not covered in the current budget, adding that to the plan 3 New OCML request to be raised seperate 4 Total Pull IN of 520K
RPHY MRTR-New-SAB-CIN-DPA-5200 (100G DPIC) | CA | SAB | SAB | R PHY | R PHY CA SAB SAB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-SAB-CIN-RPA-5110 | CA | SAB | SAB | R PHY | R PHY CA SAB SAB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 24 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-SAB-CIN-RPA-5110 | CA | SAB | SAB | R PHY | R PHY CA SAB SAB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 11 | 2020-04-01 | 2020-06-15 | 2020-06-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-SAB-CIN-RPA-5110 | CA | SAB | SAB | R PHY | R PHY CA SAB SAB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 11 | 2020-07-05 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-SAB-CIN-RPA-5110 | CA | SAB | SAB | R PHY | R PHY CA SAB SAB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 11 | 2020-04-05 | 2020-06-01 | 2020-06-01 | Active | Log | Upd | SN-0270 | Schedule Change | Approved | 2020-02-21 16:29 | 1 Pulling in Warner Rbins and Santa Barbara into Q2 2 OCML in Warner Robins is not covered in the current budget, adding that to the plan 3 New OCML request to be raised seperate 4 Total Pull IN of 520K
RPHY MRTR-New-SAB-CIN-RPA-5110 | CA | SAB | SAB | R PHY | R PHY CA SAB SAB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 24 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-Growth-BVL-CIN-RPA-5110 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-Growth-BVL-CIN-RPA-5110 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-04-01 | 2020-06-15 | 2020-06-15 | Deleted | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth-BVL-CIN-RPA-5110 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-04-01 03:01 | 2020-06-30 | 2020-09-30 | Deleted | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-Growth-BVL-CIN-RPA-5110 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | Log | Del | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-Growth-FTS-CIN MGMT-2K | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-04-01 | 2020-11-20 | 2020-09-30 | Active | EP
RPHY MRTR-Growth-FTS-CIN MGMT-2K | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-09-01 | 2020-11-15 | 2020-12-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth-FTS-CIN MGMT-2K | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-Growth-FTS-CIN MGMT-2K | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-Growth-FTS-CIN MGMT-2K | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-04-01 | 2020-11-20 | 2020-09-30 | Active | Log | Upd | SN-0900 | Schedule Change | Approved | 2020-09-11 09:33 | RPHY Metro: POR Update to activation date for 2 sites Abbeville sue to resource constraints and the site was low priority Adjusting date for Forst SMith as well
RPHY MRTR-New-FTS-CIN-DPA-5200 (100G DPIC) | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-11-20 | 2020-09-30 | Active | EP
RPHY MRTR-New-FTS-CIN-DPA-5200 (100G DPIC) | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-09-01 | 2020-11-15 | 2020-12-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-FTS-CIN-DPA-5200 (100G DPIC) | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-FTS-CIN-DPA-5200 (100G DPIC) | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Active | Log | Del | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-FTS-CIN-DPA-5200 (100G DPIC) | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-07-15 | 2020-08-31 | Active | Log | Undel | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-FTS-CIN-DPA-5200 (100G DPIC) | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-FTS-CIN-DPA-5200 (100G DPIC) | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-11-20 | 2020-09-30 | Active | Log | Upd | SN-0900 | Schedule Change | Approved | 2020-09-11 09:33 | RPHY Metro: POR Update to activation date for 2 sites Abbeville sue to resource constraints and the site was low priority Adjusting date for Forst SMith as well
RPHY MRTR-New-FTS-CIN-RPA-5110 | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-11-20 | 2020-09-30 | Active | EP
RPHY MRTR-New-FTS-CIN-RPA-5110 | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-09-01 | 2020-11-15 | 2020-12-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-FTS-CIN-RPA-5110 | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-FTS-CIN-RPA-5110 | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-08-30 | Active | Log | Upd | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-FTS-CIN-RPA-5110 | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-30 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-FTS-CIN-RPA-5110 | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-FTS-CIN-RPA-5110 | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-11-20 | 2020-09-30 | Active | Log | Upd | SN-0900 | Schedule Change | Approved | 2020-09-11 09:33 | RPHY Metro: POR Update to activation date for 2 sites Abbeville sue to resource constraints and the site was low priority Adjusting date for Forst SMith as well
RPHY MRTR-Growth-WIC-CIN MGMT-2K | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-04-01 | 2020-10-31 | 2020-10-31 | Active | EP
RPHY MRTR-Growth-WIC-CIN MGMT-2K | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-09-01 | 2020-11-15 | 2020-12-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth-WIC-CIN MGMT-2K | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-Growth-WIC-CIN MGMT-2K | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-04-01 | 2020-10-31 | 2020-10-31 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-WIC-CIN-DPA-5200 (100G DPIC) | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-07-15 | 2020-08-31 | Active | EP
RPHY MRTR-New-WIC-CIN-DPA-5200 (100G DPIC) | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-09-01 | 2020-11-15 | 2020-12-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-WIC-CIN-DPA-5200 (100G DPIC) | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-WIC-CIN-DPA-5200 (100G DPIC) | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Active | Log | Del | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-WIC-CIN-DPA-5200 (100G DPIC) | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-07-15 | 2020-08-31 | Active | Log | Undel | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-WIC-CIN-DPA-5200 (100G DPIC) | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-07-15 | 2020-08-31 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-WIC-CIN-RPA-5110 | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 5 | 2020-05-15 | 2020-07-31 | 2020-09-30 | Active | EP
RPHY MRTR-New-WIC-CIN-RPA-5110 | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 3 | 2020-09-01 | 2020-11-15 | 2020-12-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-WIC-CIN-RPA-5110 | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 3 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-WIC-CIN-RPA-5110 | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-WIC-CIN-RPA-5110 | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 5 | 2020-05-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-WIC-CIN-RPA-5110 | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 5 | 2020-05-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-Growth-BAR-CIN-RPA-5110 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 3 | 2020-01-01 | 2020-08-31 | 2020-08-31 | Active | EP
RPHY MRTR-Growth-BAR-CIN-RPA-5110 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 3 | 2020-04-01 | 2020-06-15 | 2020-06-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth-BAR-CIN-RPA-5110 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 3 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-Growth-BAR-CIN-RPA-5110 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 3 | 2020-01-01 | 2020-08-31 | 2020-08-31 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-Growth-GAR-CIN MGMT-2K | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-05-15 | 2020-11-30 | 2020-11-30 | Active | EP
RPHY MRTR-Growth-GAR-CIN MGMT-2K | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-09-01 | 2020-11-15 | 2020-12-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth-GAR-CIN MGMT-2K | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2021-01-31 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-Growth-GAR-CIN MGMT-2K | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-Growth-GAR-CIN MGMT-2K | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-05-15 | 2020-11-30 | 2020-11-30 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-GAR-CIN-DPA-5200 (100G DPIC) | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-11-30 | 2020-11-30 | Active | EP
RPHY MRTR-New-GAR-CIN-DPA-5200 (100G DPIC) | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-09-01 | 2020-11-15 | 2020-12-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-GAR-CIN-DPA-5200 (100G DPIC) | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2021-01-31 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-GAR-CIN-DPA-5200 (100G DPIC) | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-GAR-CIN-DPA-5200 (100G DPIC) | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-11-30 | 2020-11-30 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-GAR-CIN-RPA-5110 | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-11-30 | 2020-11-30 | Active | EP
RPHY MRTR-New-GAR-CIN-RPA-5110 | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-09-01 | 2020-11-15 | 2020-12-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-GAR-CIN-RPA-5110 | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2021-01-31 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-GAR-CIN-RPA-5110 | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-GAR-CIN-RPA-5110 | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-GAR-CIN-RPA-5110 | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-11-30 | 2020-11-30 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-Growth-MWC-CIN MGMT-2K | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-04-01 | 2020-11-30 | 2020-11-30 | Active | EP
RPHY MRTR-Growth-MWC-CIN MGMT-2K | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-09-01 | 2020-11-15 | 2020-12-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth-MWC-CIN MGMT-2K | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-Growth-MWC-CIN MGMT-2K | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-04-01 | 2020-11-30 | 2020-11-30 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-MWC-CIN-DPA-5200 (100G DPIC) | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-11-30 | 2020-11-30 | Active | EP
RPHY MRTR-New-MWC-CIN-DPA-5200 (100G DPIC) | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-09-01 | 2020-11-15 | 2020-12-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-MWC-CIN-DPA-5200 (100G DPIC) | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-MWC-CIN-DPA-5200 (100G DPIC) | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Active | Log | Del | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-MWC-CIN-DPA-5200 (100G DPIC) | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-07-15 | 2020-08-31 | Active | Log | Undel | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-MWC-CIN-DPA-5200 (100G DPIC) | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-11-30 | 2020-11-30 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-MWC-CIN-RPA-5110 | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-05-15 | 2020-11-30 | 2020-11-30 | Active | EP
RPHY MRTR-New-MWC-CIN-RPA-5110 | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-09-01 | 2020-11-15 | 2020-12-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-MWC-CIN-RPA-5110 | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-MWC-CIN-RPA-5110 | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-MWC-CIN-RPA-5110 | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-05-15 | 2020-11-30 | 2020-11-30 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-Growth-NEH-CIN MGMT-2K | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-12-31 | 2020-12-31 | Active | EP
RPHY MRTR-Growth-NEH-CIN MGMT-2K | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-09-01 | 2020-11-15 | 2020-12-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth-NEH-CIN MGMT-2K | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-09-05 | 2020-11-30 | 2021-02-28 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-Growth-NEH-CIN MGMT-2K | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-Growth-NEH-CIN MGMT-2K | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-12-31 | 2020-12-31 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-NEH-CIN-DPA-5200 (100G DPIC) | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-12-31 | 2020-12-31 | Active | EP
RPHY MRTR-New-NEH-CIN-DPA-5200 (100G DPIC) | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-09-01 | 2020-11-15 | 2020-12-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-NEH-CIN-DPA-5200 (100G DPIC) | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-09-05 | 2020-11-30 | 2021-02-28 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-NEH-CIN-DPA-5200 (100G DPIC) | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Active | Log | Del | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-NEH-CIN-DPA-5200 (100G DPIC) | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-07-15 | 2020-08-31 | Active | Log | Undel | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-NEH-CIN-DPA-5200 (100G DPIC) | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-12-31 | 2020-12-31 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-NEH-CIN-RPA-5110 | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-12-31 | 2020-12-31 | Active | EP
RPHY MRTR-New-NEH-CIN-RPA-5110 | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-09-01 | 2020-11-15 | 2020-12-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-NEH-CIN-RPA-5110 | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-09-05 | 2020-11-30 | 2021-02-28 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-NEH-CIN-RPA-5110 | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-NEH-CIN-RPA-5110 | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-12-31 | 2020-12-31 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-Growth-WLK-CIN-RPA-5110 | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-Growth-WLK-CIN-RPA-5110 | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-09-01 | 2020-11-15 | 2020-12-15 | Deleted | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth-WLK-CIN-RPA-5110 | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-09-05 | 2020-11-30 | 2021-02-28 | Deleted | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-Growth-WLK-CIN-RPA-5110 | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-Growth-WEH-CIN MGMT-2K | CE | OKC | WEH | R PHY | R PHY CE OKC WEH RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-Growth-WEH-CIN MGMT-2K | CE | OKC | WEH | R PHY | R PHY CE OKC WEH RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-09-01 | 2020-11-15 | 2020-12-15 | Deleted | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth-WEH-CIN MGMT-2K | CE | OKC | WEH | R PHY | R PHY CE OKC WEH RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-09-05 | 2020-11-30 | 2021-02-28 | Deleted | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-Growth-WEH-CIN MGMT-2K | CE | OKC | WEH | R PHY | R PHY CE OKC WEH RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-WEH-CIN-DPA-5200 (100G DPIC) | CE | OKC | WEH | R PHY | R PHY CE OKC WEH RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-New-WEH-CIN-DPA-5200 (100G DPIC) | CE | OKC | WEH | R PHY | R PHY CE OKC WEH RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-09-01 | 2020-11-15 | 2020-12-15 | Deleted | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-WEH-CIN-DPA-5200 (100G DPIC) | CE | OKC | WEH | R PHY | R PHY CE OKC WEH RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-09-05 | 2020-11-30 | 2021-02-28 | Deleted | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-WEH-CIN-DPA-5200 (100G DPIC) | CE | OKC | WEH | R PHY | R PHY CE OKC WEH RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-WEH-CIN-RPA-5110 | CE | OKC | WEH | R PHY | R PHY CE OKC WEH RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-New-WEH-CIN-RPA-5110 | CE | OKC | WEH | R PHY | R PHY CE OKC WEH RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-09-01 | 2020-11-15 | 2020-12-15 | Deleted | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-WEH-CIN-RPA-5110 | CE | OKC | WEH | R PHY | R PHY CE OKC WEH RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-09-05 | 2020-11-30 | 2021-02-28 | Deleted | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-WEH-CIN-RPA-5110 | CE | OKC | WEH | R PHY | R PHY CE OKC WEH RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-Growth-BLV-CIN MGMT-2K | CE | OMA | BLV | R PHY | R PHY CE OMA BLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-10-31 | 2020-10-31 | Active | EP
RPHY MRTR-Growth-BLV-CIN MGMT-2K | CE | OMA | BLV | R PHY | R PHY CE OMA BLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-09-01 | 2020-11-15 | 2020-12-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth-BLV-CIN MGMT-2K | CE | OMA | BLV | R PHY | R PHY CE OMA BLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-Growth-BLV-CIN MGMT-2K | CE | OMA | BLV | R PHY | R PHY CE OMA BLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-Growth-BLV-CIN MGMT-2K | CE | OMA | BLV | R PHY | R PHY CE OMA BLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-10-31 | 2020-10-31 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-BLV-CIN-DPA-5200 (100G DPIC) | CE | OMA | BLV | R PHY | R PHY CE OMA BLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-10-31 | 2020-10-31 | Active | EP
RPHY MRTR-New-BLV-CIN-DPA-5200 (100G DPIC) | CE | OMA | BLV | R PHY | R PHY CE OMA BLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-10-01 | 2020-12-15 | 2020-12-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-BLV-CIN-DPA-5200 (100G DPIC) | CE | OMA | BLV | R PHY | R PHY CE OMA BLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-BLV-CIN-DPA-5200 (100G DPIC) | CE | OMA | BLV | R PHY | R PHY CE OMA BLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Active | Log | Del | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-BLV-CIN-DPA-5200 (100G DPIC) | CE | OMA | BLV | R PHY | R PHY CE OMA BLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-07-15 | 2020-08-31 | Active | Log | Undel | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-BLV-CIN-DPA-5200 (100G DPIC) | CE | OMA | BLV | R PHY | R PHY CE OMA BLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-10-31 | 2020-10-31 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-BLV-CIN-RPA-5110 | CE | OMA | BLV | R PHY | R PHY CE OMA BLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-04-01 | 2020-10-31 | 2020-10-31 | Active | EP
RPHY MRTR-New-BLV-CIN-RPA-5110 | CE | OMA | BLV | R PHY | R PHY CE OMA BLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-09-01 | 2020-11-15 | 2020-12-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-BLV-CIN-RPA-5110 | CE | OMA | BLV | R PHY | R PHY CE OMA BLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-BLV-CIN-RPA-5110 | CE | OMA | BLV | R PHY | R PHY CE OMA BLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-04-01 | 2020-08-31 | 2020-09-30 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-BLV-CIN-RPA-5110 | CE | OMA | BLV | R PHY | R PHY CE OMA BLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-04-01 | 2020-10-31 | 2020-10-31 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-Growth-ONA-CIN MGMT-2K | CE | OMA | ONA | R PHY | R PHY CE OMA ONA RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-Growth-ONA-CIN MGMT-2K | CE | OMA | ONA | R PHY | R PHY CE OMA ONA RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-09-01 | 2020-11-15 | 2020-12-15 | Deleted | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth-ONA-CIN MGMT-2K | CE | OMA | ONA | R PHY | R PHY CE OMA ONA RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-08-01 | 2020-10-31 | 2021-01-31 | Deleted | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-Growth-ONA-CIN MGMT-2K | CE | OMA | ONA | R PHY | R PHY CE OMA ONA RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Deleted | Log | Del | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-ONA-CIN-DPA-5200 (100G DPIC) | CE | OMA | ONA | R PHY | R PHY CE OMA ONA RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-New-ONA-CIN-DPA-5200 (100G DPIC) | CE | OMA | ONA | R PHY | R PHY CE OMA ONA RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-09-01 | 2020-11-15 | 2020-12-15 | Deleted | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-ONA-CIN-DPA-5200 (100G DPIC) | CE | OMA | ONA | R PHY | R PHY CE OMA ONA RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-08-01 | 2020-10-31 | 2021-01-31 | Deleted | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-ONA-CIN-DPA-5200 (100G DPIC) | CE | OMA | ONA | R PHY | R PHY CE OMA ONA RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Deleted | Log | Del | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-ONA-CIN-DPA-5200 (100G DPIC) | CE | OMA | ONA | R PHY | R PHY CE OMA ONA RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2021-03-31 |  | Deleted | Log | Undel | SN-1036 | Schedule Change | Draft | 2020-10-29 10:06 | RPHY Metro: POR Update CR
RPHY MRTR-New-ONA-CIN-RPA-5110 | CE | OMA | ONA | R PHY | R PHY CE OMA ONA RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-New-ONA-CIN-RPA-5110 | CE | OMA | ONA | R PHY | R PHY CE OMA ONA RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-09-01 | 2020-11-15 | 2020-12-15 | Deleted | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-ONA-CIN-RPA-5110 | CE | OMA | ONA | R PHY | R PHY CE OMA ONA RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-08-01 | 2020-10-31 | 2021-01-31 | Deleted | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-ONA-CIN-RPA-5110 | CE | OMA | ONA | R PHY | R PHY CE OMA ONA RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | Log | Del | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-Growth-WES-CIN MGMT-2K | CE | OMA | WES | R PHY | R PHY CE OMA WES RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-Growth-WES-CIN MGMT-2K | CE | OMA | WES | R PHY | R PHY CE OMA WES RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-09-01 | 2020-11-15 | 2020-12-15 | Deleted | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth-WES-CIN MGMT-2K | CE | OMA | WES | R PHY | R PHY CE OMA WES RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-09-05 | 2020-11-30 | 2021-02-28 | Deleted | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-Growth-WES-CIN MGMT-2K | CE | OMA | WES | R PHY | R PHY CE OMA WES RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Deleted | Log | Del | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-WES-CIN-DPA-5200 (100G DPIC) | CE | OMA | WES | R PHY | R PHY CE OMA WES RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-New-WES-CIN-DPA-5200 (100G DPIC) | CE | OMA | WES | R PHY | R PHY CE OMA WES RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-10-01 | 2020-12-15 | 2020-12-15 | Deleted | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-WES-CIN-DPA-5200 (100G DPIC) | CE | OMA | WES | R PHY | R PHY CE OMA WES RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-09-05 | 2020-11-30 | 2021-02-28 | Deleted | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-WES-CIN-DPA-5200 (100G DPIC) | CE | OMA | WES | R PHY | R PHY CE OMA WES RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Deleted | Log | Del | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-WES-CIN-DPA-5200 (100G DPIC) | CE | OMA | WES | R PHY | R PHY CE OMA WES RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-31 | 2021-03-31 |  | Deleted | Log | Undel | SN-1036 | Schedule Change | Draft | 2020-10-29 10:06 | RPHY Metro: POR Update CR
RPHY MRTR-New-WES-CIN-RPA-5110 | CE | OMA | WES | R PHY | R PHY CE OMA WES RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-New-WES-CIN-RPA-5110 | CE | OMA | WES | R PHY | R PHY CE OMA WES RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-09-01 | 2020-11-15 | 2020-12-15 | Deleted | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-WES-CIN-RPA-5110 | CE | OMA | WES | R PHY | R PHY CE OMA WES RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-09-05 | 2020-11-30 | 2021-02-28 | Deleted | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-WES-CIN-RPA-5110 | CE | OMA | WES | R PHY | R PHY CE OMA WES RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | Log | Del | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-Growth-CLV-CIN MGMT-2K | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 16 | 2020-08-01 | 2020-12-31 | 2020-12-31 | Active | EP
RPHY MRTR-Growth-CLV-CIN MGMT-2K | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-10-01 | 2020-12-15 | 2020-12-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth-CLV-CIN MGMT-2K | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-Growth-CLV-CIN MGMT-2K | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 16 | 2020-08-01 | 2020-12-31 | 2020-12-31 | Active | Log | Upd | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
RPHY MRTR-New-CLV-CIN-DPA-5200 (100G DPIC) | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 4 | 2020-08-01 | 2020-12-31 | 2020-12-31 | Active | EP
RPHY MRTR-New-CLV-CIN-DPA-5200 (100G DPIC) | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-10-01 | 2020-12-15 | 2020-12-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-CLV-CIN-DPA-5200 (100G DPIC) | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-CLV-CIN-DPA-5200 (100G DPIC) | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 4 | 2020-08-01 | 2020-12-31 | 2020-12-31 | Active | Log | Upd | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
RPHY MRTR-New-CLV-CIN-RPA-5110 | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 32 | 2020-08-01 | 2020-12-31 | 2020-12-31 | Active | EP
RPHY MRTR-New-CLV-CIN-RPA-5110 | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-10-01 | 2020-12-15 | 2020-12-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-CLV-CIN-RPA-5110 | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-CLV-CIN-RPA-5110 | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 32 | 2020-08-01 | 2020-12-31 | 2020-12-31 | Active | Log | Upd | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
RPHY MRTR-Growth-CLR-CIN MGMT-2K | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-01-15 | 2020-08-31 | 2020-06-30 | Active | EP
RPHY MRTR-Growth-CLR-CIN MGMT-2K | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-10-01 | 2020-12-15 | 2020-12-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth-CLR-CIN MGMT-2K | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-01-05 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-Growth-CLR-CIN MGMT-2K | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-01-15 | 2020-04-30 |  | Active | Log | Upd | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-Growth-CLR-CIN MGMT-2K | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-01-15 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-Growth-CLR-CIN MGMT-2K | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-01-15 | 2020-07-31 | 2020-06-30 | Active | Log | Upd | SN-0741 | Schedule Change | Approved | 2020-07-10 10:12 | RPHY Metro: Updates to POR based on Field inputs
RPHY MRTR-Growth-CLR-CIN MGMT-2K | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-01-15 | 2020-08-31 | 2020-06-30 | Active | Log | Upd | SN-0810 | Schedule Change | Approved | 2020-08-07 09:41 | 1 Warner Robins and Clear View needs to be moved to August as Alrm Testing was not completed
RPHY MRTR-New-CLR-CIN-DPA-5200 (100G DPIC) | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-01-15 | 2020-08-31 | 2020-06-30 | Active | EP
RPHY MRTR-New-CLR-CIN-DPA-5200 (100G DPIC) | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-10-01 | 2020-12-15 | 2020-12-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-CLR-CIN-DPA-5200 (100G DPIC) | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-01-05 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-CLR-CIN-DPA-5200 (100G DPIC) | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-01-15 | 2020-04-30 |  | Active | Log | Upd | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-CLR-CIN-DPA-5200 (100G DPIC) | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-01-15 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-CLR-CIN-DPA-5200 (100G DPIC) | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-01-15 | 2020-07-31 | 2020-06-30 | Active | Log | Upd | SN-0741 | Schedule Change | Approved | 2020-07-10 10:12 | RPHY Metro: Updates to POR based on Field inputs
RPHY MRTR-New-CLR-CIN-DPA-5200 (100G DPIC) | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-01-15 | 2020-08-31 | 2020-06-30 | Active | Log | Upd | SN-0810 | Schedule Change | Approved | 2020-08-07 09:41 | 1 Warner Robins and Clear View needs to be moved to August as Alrm Testing was not completed
RPHY MRTR-New-CLR-CIN-RPA-5110 | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-01-15 | 2020-08-31 | 2020-06-30 | Active | EP
RPHY MRTR-New-CLR-CIN-RPA-5110 | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 5 | 2020-10-01 | 2020-12-15 | 2020-12-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-CLR-CIN-RPA-5110 | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 5 | 2020-01-05 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-CLR-CIN-RPA-5110 | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 5 | 2020-01-15 | 2020-04-30 |  | Active | Log | Upd | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-CLR-CIN-RPA-5110 | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-01-15 | 2020-04-30 | 2020-06-30 | Active | Log | Upd | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-CLR-CIN-RPA-5110 | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-01-15 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-CLR-CIN-RPA-5110 | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-01-15 | 2020-07-31 | 2020-06-30 | Active | Log | Upd | SN-0741 | Schedule Change | Approved | 2020-07-10 10:12 | RPHY Metro: Updates to POR based on Field inputs
RPHY MRTR-New-CLR-CIN-RPA-5110 | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-01-15 | 2020-08-31 | 2020-06-30 | Active | Log | Upd | SN-0810 | Schedule Change | Approved | 2020-08-07 09:41 | 1 Warner Robins and Clear View needs to be moved to August as Alrm Testing was not completed
RPHY MRTR-New-ELM-CIN MGMT-2K | SE | NOR | ELM | R PHY | R PHY SE NOR ELM RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-New-ELM-CIN MGMT-2K | SE | NOR | ELM | R PHY | R PHY SE NOR ELM RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-07-01 | 2020-09-20 | 2020-09-20 | Deleted | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-ELM-CIN MGMT-2K | SE | NOR | ELM | R PHY | R PHY SE NOR ELM RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-04-01 | 2020-07-20 | 2020-07-20 | Deleted | Log | Upd | SN-0152 | Schedule Change | Approved | 2020-02-06 11:12 | 1 There are changes to the NBD for Nexus 2248 and RPA, DPA in South East 2 This is based on the OSPC Node Split Plan 3 Ffew activation dates have been updated based on feedback from Field 4 Aligning material and labor accordingly
RPHY MRTR-New-ELM-CIN MGMT-2K | SE | NOR | ELM | R PHY | R PHY SE NOR ELM RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Deleted | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-ELM-CIN MGMT-2K | SE | NOR | ELM | R PHY | R PHY SE NOR ELM RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-04-01 | 2020-07-20 | 2020-07-20 | Deleted | Log | Upd | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-ELM-CIN MGMT-2K | SE | NOR | ELM | R PHY | R PHY SE NOR ELM RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Deleted | Log | Del | SN-0601 | Schedule Change | Approved | 2020-05-22 17:32 | 1 Lapalco Kenner and Elmwood were part of 16 7 node action plan 2 These sites are not in 18 14 plan but still continutes to be on the list 3 Deleting those occurences
RPHY MRTR-New-ELM-CIN-DPA-5200 (100G DPIC) | SE | NOR | ELM | R PHY | R PHY SE NOR ELM RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-New-ELM-CIN-DPA-5200 (100G DPIC) | SE | NOR | ELM | R PHY | R PHY SE NOR ELM RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-04-15 | 2020-07-01 | 2020-07-01 | Deleted | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-ELM-CIN-DPA-5200 (100G DPIC) | SE | NOR | ELM | R PHY | R PHY SE NOR ELM RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Deleted | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-ELM-CIN-DPA-5200 (100G DPIC) | SE | NOR | ELM | R PHY | R PHY SE NOR ELM RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-04-15 | 2020-07-01 | 2020-07-01 | Deleted | Log | Upd | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-ELM-CIN-DPA-5200 (100G DPIC) | SE | NOR | ELM | R PHY | R PHY SE NOR ELM RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Deleted | Log | Del | SN-0601 | Schedule Change | Approved | 2020-05-22 17:32 | 1 Lapalco Kenner and Elmwood were part of 16 7 node action plan 2 These sites are not in 18 14 plan but still continutes to be on the list 3 Deleting those occurences
RPHY MRTR-New-ELM-CIN-RPA-5110 | SE | NOR | ELM | R PHY | R PHY SE NOR ELM RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-New-ELM-CIN-RPA-5110 | SE | NOR | ELM | R PHY | R PHY SE NOR ELM RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 3 | 2020-04-15 | 2020-07-01 | 2020-07-01 | Deleted | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-ELM-CIN-RPA-5110 | SE | NOR | ELM | R PHY | R PHY SE NOR ELM RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 3 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Deleted | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-ELM-CIN-RPA-5110 | SE | NOR | ELM | R PHY | R PHY SE NOR ELM RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 3 | 2020-04-15 | 2020-07-01 | 2020-07-01 | Deleted | Log | Upd | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-ELM-CIN-RPA-5110 | SE | NOR | ELM | R PHY | R PHY SE NOR ELM RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | Log | Del | SN-0601 | Schedule Change | Approved | 2020-05-22 17:32 | 1 Lapalco Kenner and Elmwood were part of 16 7 node action plan 2 These sites are not in 18 14 plan but still continutes to be on the list 3 Deleting those occurences
RPHY MRTR-Growth-KNN-CIN MGMT-2K | SE | NOR | KNN | R PHY | R PHY SE NOR KNN RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-Growth-KNN-CIN MGMT-2K | SE | NOR | KNN | R PHY | R PHY SE NOR KNN RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-07-01 | 2020-09-20 | 2020-09-20 | Deleted | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth-KNN-CIN MGMT-2K | SE | NOR | KNN | R PHY | R PHY SE NOR KNN RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-04-01 | 2020-07-31 | 2020-07-31 | Deleted | Log | Upd | SN-0152 | Schedule Change | Approved | 2020-02-06 11:12 | 1 There are changes to the NBD for Nexus 2248 and RPA, DPA in South East 2 This is based on the OSPC Node Split Plan 3 Ffew activation dates have been updated based on feedback from Field 4 Aligning material and labor accordingly
RPHY MRTR-Growth-KNN-CIN MGMT-2K | SE | NOR | KNN | R PHY | R PHY SE NOR KNN RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Deleted | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-Growth-KNN-CIN MGMT-2K | SE | NOR | KNN | R PHY | R PHY SE NOR KNN RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Deleted | Log | Del | SN-0601 | Schedule Change | Approved | 2020-05-22 17:32 | 1 Lapalco Kenner and Elmwood were part of 16 7 node action plan 2 These sites are not in 18 14 plan but still continutes to be on the list 3 Deleting those occurences
RPHY MRTR-New-KNN-CIN-DPA-5200 (100G DPIC) | SE | NOR | KNN | R PHY | R PHY SE NOR KNN RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-New-KNN-CIN-DPA-5200 (100G DPIC) | SE | NOR | KNN | R PHY | R PHY SE NOR KNN RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-04-15 | 2020-07-01 | 2020-07-01 | Deleted | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-KNN-CIN-DPA-5200 (100G DPIC) | SE | NOR | KNN | R PHY | R PHY SE NOR KNN RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Deleted | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-KNN-CIN-DPA-5200 (100G DPIC) | SE | NOR | KNN | R PHY | R PHY SE NOR KNN RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Deleted | Log | Del | SN-0601 | Schedule Change | Approved | 2020-05-22 17:32 | 1 Lapalco Kenner and Elmwood were part of 16 7 node action plan 2 These sites are not in 18 14 plan but still continutes to be on the list 3 Deleting those occurences
RPHY MRTR-New-KNN-CIN-RPA-5110 | SE | NOR | KNN | R PHY | R PHY SE NOR KNN RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-New-KNN-CIN-RPA-5110 | SE | NOR | KNN | R PHY | R PHY SE NOR KNN RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-04-15 | 2020-07-01 | 2020-07-01 | Deleted | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-KNN-CIN-RPA-5110 | SE | NOR | KNN | R PHY | R PHY SE NOR KNN RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Deleted | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-KNN-CIN-RPA-5110 | SE | NOR | KNN | R PHY | R PHY SE NOR KNN RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | Log | Del | SN-0601 | Schedule Change | Approved | 2020-05-22 17:32 | 1 Lapalco Kenner and Elmwood were part of 16 7 node action plan 2 These sites are not in 18 14 plan but still continutes to be on the list 3 Deleting those occurences
RPHY MRTR-Growth-LPL-CIN MGMT-2K | SE | NOR | LPL | R PHY | R PHY SE NOR LPL RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-09-01 | 2020-12-15 | 2020-12-15 | Deleted | EP
RPHY MRTR-Growth-LPL-CIN MGMT-2K | SE | NOR | LPL | R PHY | R PHY SE NOR LPL RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-10-01 | 2020-12-15 | 2020-12-15 | Deleted | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth-LPL-CIN MGMT-2K | SE | NOR | LPL | R PHY | R PHY SE NOR LPL RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-09-01 | 2020-12-15 | 2020-12-15 | Deleted | Log | Upd | SN-0152 | Schedule Change | Approved | 2020-02-06 11:12 | 1 There are changes to the NBD for Nexus 2248 and RPA, DPA in South East 2 This is based on the OSPC Node Split Plan 3 Ffew activation dates have been updated based on feedback from Field 4 Aligning material and labor accordingly
RPHY MRTR-Growth-LPL-CIN MGMT-2K | SE | NOR | LPL | R PHY | R PHY SE NOR LPL RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Deleted | Log | Del | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-LPL-CIN-DPA-5200 (100G DPIC) | SE | NOR | LPL | R PHY | R PHY SE NOR LPL RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-New-LPL-CIN-DPA-5200 (100G DPIC) | SE | NOR | LPL | R PHY | R PHY SE NOR LPL RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-10-01 | 2020-12-15 | 2020-12-15 | Deleted | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-LPL-CIN-DPA-5200 (100G DPIC) | SE | NOR | LPL | R PHY | R PHY SE NOR LPL RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-09-01 | 2020-12-15 | 2020-12-15 | Deleted | Log | Upd | SN-0152 | Schedule Change | Approved | 2020-02-06 11:12 | 1 There are changes to the NBD for Nexus 2248 and RPA, DPA in South East 2 This is based on the OSPC Node Split Plan 3 Ffew activation dates have been updated based on feedback from Field 4 Aligning material and labor accordingly
RPHY MRTR-New-LPL-CIN-DPA-5200 (100G DPIC) | SE | NOR | LPL | R PHY | R PHY SE NOR LPL RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-07-05 | 2020-09-30 | 2020-12-31 | Deleted | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-LPL-CIN-DPA-5200 (100G DPIC) | SE | NOR | LPL | R PHY | R PHY SE NOR LPL RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Deleted | Log | Del | SN-0601 | Schedule Change | Approved | 2020-05-22 17:32 | 1 Lapalco Kenner and Elmwood were part of 16 7 node action plan 2 These sites are not in 18 14 plan but still continutes to be on the list 3 Deleting those occurences
RPHY MRTR-New-LPL-CIN-RPA-5110 | SE | NOR | LPL | R PHY | R PHY SE NOR LPL RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-09-01 | 2020-12-15 | 2020-12-15 | Deleted | EP
RPHY MRTR-New-LPL-CIN-RPA-5110 | SE | NOR | LPL | R PHY | R PHY SE NOR LPL RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-10-01 | 2020-12-15 | 2020-12-15 | Deleted | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-LPL-CIN-RPA-5110 | SE | NOR | LPL | R PHY | R PHY SE NOR LPL RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-09-01 | 2020-12-15 | 2020-12-15 | Deleted | Log | Upd | SN-0152 | Schedule Change | Approved | 2020-02-06 11:12 | 1 There are changes to the NBD for Nexus 2248 and RPA, DPA in South East 2 This is based on the OSPC Node Split Plan 3 Ffew activation dates have been updated based on feedback from Field 4 Aligning material and labor accordingly
RPHY MRTR-New-LPL-CIN-RPA-5110 | SE | NOR | LPL | R PHY | R PHY SE NOR LPL RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | Log | Del | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-Growth-SPC-CIN MGMT-2K | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-02-15 | 2020-07-31 | 2020-06-30 | Active | EP
RPHY MRTR-Growth-SPC-CIN MGMT-2K | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-10-01 | 2020-12-15 | 2020-12-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth-SPC-CIN MGMT-2K | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-02-15 | 2020-04-15 | 2020-04-30 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-Growth-SPC-CIN MGMT-2K | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-02-15 | 2020-04-30 |  | Active | Log | Upd | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-Growth-SPC-CIN MGMT-2K | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-02-15 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-Growth-SPC-CIN MGMT-2K | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-02-15 | 2020-07-31 | 2020-06-30 | Active | Log | Upd | SN-0741 | Schedule Change | Approved | 2020-07-10 10:12 | RPHY Metro: Updates to POR based on Field inputs
RPHY MRTR-New-SPC-CIN-DPA-5200 (100G DPIC) | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-02-15 | 2020-07-31 | 2020-06-30 | Active | EP
RPHY MRTR-New-SPC-CIN-DPA-5200 (100G DPIC) | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-07-01 | 2020-09-15 | 2020-09-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-SPC-CIN-DPA-5200 (100G DPIC) | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-02-15 | 2020-04-15 | 2020-04-30 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-SPC-CIN-DPA-5200 (100G DPIC) | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-02-15 | 2020-04-30 |  | Active | Log | Upd | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-SPC-CIN-DPA-5200 (100G DPIC) | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-02-15 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-SPC-CIN-DPA-5200 (100G DPIC) | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-02-15 | 2020-07-31 | 2020-06-30 | Active | Log | Upd | SN-0741 | Schedule Change | Approved | 2020-07-10 10:12 | RPHY Metro: Updates to POR based on Field inputs
RPHY MRTR-New-SPC-CIN-RPA-5110 | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-06-30 | Active | EP
RPHY MRTR-New-SPC-CIN-RPA-5110 | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-07-01 | 2020-09-15 | 2020-09-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-SPC-CIN-RPA-5110 | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-02-15 | 2020-04-15 | 2020-04-30 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-SPC-CIN-RPA-5110 | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-02-15 | 2020-04-30 |  | Active | Log | Upd | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-SPC-CIN-RPA-5110 | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-SPC-CIN-RPA-5110 | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-SPC-CIN-RPA-5110 | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-SPC-CIN-RPA-5110 | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-06-30 | Active | Log | Upd | SN-0741 | Schedule Change | Approved | 2020-07-10 10:12 | RPHY Metro: Updates to POR based on Field inputs
RPHY MRTR-Growth-PNS-CIN MGMT-2K | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-01-01 | 2020-09-30 | 2020-07-31 | Active | EP
RPHY MRTR-Growth-PNS-CIN MGMT-2K | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth-PNS-CIN MGMT-2K | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-01-01 | 2020-05-31 | 2020-05-31 | Active | Log | Upd | SN-0152 | Schedule Change | Approved | 2020-02-06 11:12 | 1 There are changes to the NBD for Nexus 2248 and RPA, DPA in South East 2 This is based on the OSPC Node Split Plan 3 Ffew activation dates have been updated based on feedback from Field 4 Aligning material and labor accordingly
RPHY MRTR-Growth-PNS-CIN MGMT-2K | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-Growth-PNS-CIN MGMT-2K | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-01-01 | 2020-05-31 |  | Active | Log | Upd | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-Growth-PNS-CIN MGMT-2K | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-01-01 | 2020-07-31 | 2020-07-31 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-Growth-PNS-CIN MGMT-2K | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-01-01 | 2020-08-31 | 2020-07-31 | Active | Log | Upd | SN-0786 | Schedule Change | Approved | 2020-07-27 09:30 | 1 SE OSNAP for Metairie was approved last week in CR 726 2 This POR adds that EPS project created into the POR 3 Also updating OCML Chassis count for Omaha North as to align with the BOM
RPHY MRTR-Growth-PNS-CIN MGMT-2K | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-01-01 | 2020-09-30 | 2020-07-31 | Active | Log | Upd | SN-0881 | Schedule Change | Approved | 2020-08-28 10:07 | 1 Moving Pensacola Activation Date from August to September because of Firewall issues 2 Moving BTR dates from August to September because of Resource constraints in with BTR NF team
RPHY MRTR-New-PNS-CIN-DPA-5200 (100G DPIC) | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-01-05 | 2020-09-30 |  | Active | EP
RPHY MRTR-New-PNS-CIN-DPA-5200 (100G DPIC) | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-07-01 | 2020-09-15 | 2020-09-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-PNS-CIN-DPA-5200 (100G DPIC) | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-01-05 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-PNS-CIN-DPA-5200 (100G DPIC) | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-01-05 | 2020-05-31 |  | Active | Log | Upd | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-PNS-CIN-DPA-5200 (100G DPIC) | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-01-05 | 2020-08-31 |  | Active | Log | Upd | SN-0786 | Schedule Change | Approved | 2020-07-27 09:30 | 1 SE OSNAP for Metairie was approved last week in CR 726 2 This POR adds that EPS project created into the POR 3 Also updating OCML Chassis count for Omaha North as to align with the BOM
RPHY MRTR-New-PNS-CIN-DPA-5200 (100G DPIC) | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-01-05 | 2020-09-30 |  | Active | Log | Upd | SN-0881 | Schedule Change | Approved | 2020-08-28 10:07 | 1 Moving Pensacola Activation Date from August to September because of Firewall issues 2 Moving BTR dates from August to September because of Resource constraints in with BTR NF team
RPHY MRTR-New-PNS-CIN-RPA-5110 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-01-05 | 2020-09-30 | 2020-07-31 | Active | EP
RPHY MRTR-New-PNS-CIN-RPA-5110 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-07-01 | 2020-09-15 | 2020-09-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-PNS-CIN-RPA-5110 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-01-05 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-PNS-CIN-RPA-5110 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-01-05 | 2020-05-31 |  | Active | Log | Upd | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-PNS-CIN-RPA-5110 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-01-05 | 2020-05-31 | 2020-06-30 | Active | Log | Upd | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-PNS-CIN-RPA-5110 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-01-05 | 2020-07-31 | 2020-07-31 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-PNS-CIN-RPA-5110 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-01-05 | 2020-08-31 | 2020-07-31 | Active | Log | Upd | SN-0786 | Schedule Change | Approved | 2020-07-27 09:30 | 1 SE OSNAP for Metairie was approved last week in CR 726 2 This POR adds that EPS project created into the POR 3 Also updating OCML Chassis count for Omaha North as to align with the BOM
RPHY MRTR-New-PNS-CIN-RPA-5110 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-01-05 | 2020-09-30 | 2020-07-31 | Active | Log | Upd | SN-0881 | Schedule Change | Approved | 2020-08-28 10:07 | 1 Moving Pensacola Activation Date from August to September because of Firewall issues 2 Moving BTR dates from August to September because of Resource constraints in with BTR NF team
RPHY MRTR-New-WRB-CIN MGMT-2K | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-04-01 | 2020-09-30 | 2020-07-31 | Active | EP
RPHY MRTR-New-WRB-CIN MGMT-2K | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-07-01 | 2020-09-15 | 2020-09-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-WRB-CIN MGMT-2K | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-07-01 | 2020-09-15 | 2020-09-15 | Active | Log | Upd | SN-0152 | Schedule Change | Approved | 2020-02-06 11:12 | 1 There are changes to the NBD for Nexus 2248 and RPA, DPA in South East 2 This is based on the OSPC Node Split Plan 3 Ffew activation dates have been updated based on feedback from Field 4 Aligning material and labor accordingly
RPHY MRTR-New-WRB-CIN MGMT-2K | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-WRB-CIN MGMT-2K | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-04-01 | 2020-08-30 |  | Active | Log | Upd | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-WRB-CIN MGMT-2K | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-04-01 | 2020-07-31 | 2020-07-31 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-WRB-CIN MGMT-2K | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-04-01 | 2020-08-31 | 2020-07-31 | Active | Log | Upd | SN-0741 | Schedule Change | Approved | 2020-07-10 10:12 | RPHY Metro: Updates to POR based on Field inputs
RPHY MRTR-New-WRB-CIN MGMT-2K | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-04-01 | 2020-09-30 | 2020-07-31 | Active | Log | Upd | SN-0810 | Schedule Change | Approved | 2020-08-07 09:41 | 1 Warner Robins and Clear View needs to be moved to August as Alrm Testing was not completed
RPHY MRTR-New-WRB-CIN-DPA-5200 (100G DPIC) | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-04-01 | 2020-09-30 | 2020-07-31 | Active | EP
RPHY MRTR-New-WRB-CIN-DPA-5200 (100G DPIC) | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-07-01 | 2020-09-15 | 2020-09-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-WRB-CIN-DPA-5200 (100G DPIC) | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-WRB-CIN-DPA-5200 (100G DPIC) | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-04-01 | 2020-08-30 |  | Active | Log | Upd | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-WRB-CIN-DPA-5200 (100G DPIC) | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-04-01 | 2020-07-31 | 2020-07-31 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-WRB-CIN-DPA-5200 (100G DPIC) | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-04-01 | 2020-08-31 | 2020-07-31 | Active | Log | Upd | SN-0741 | Schedule Change | Approved | 2020-07-10 10:12 | RPHY Metro: Updates to POR based on Field inputs
RPHY MRTR-New-WRB-CIN-DPA-5200 (100G DPIC) | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-04-01 | 2020-09-30 | 2020-07-31 | Active | Log | Upd | SN-0810 | Schedule Change | Approved | 2020-08-07 09:41 | 1 Warner Robins and Clear View needs to be moved to August as Alrm Testing was not completed
RPHY MRTR-New-WRB-CIN-RPA-5110 | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-04-01 | 2020-09-30 | 2020-07-31 | Active | EP
RPHY MRTR-New-WRB-CIN-RPA-5110 | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-07-01 | 2020-09-15 | 2020-09-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-WRB-CIN-RPA-5110 | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-WRB-CIN-RPA-5110 | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-04-01 | 2020-08-30 |  | Active | Log | Upd | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-WRB-CIN-RPA-5110 | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-04-01 | 2020-07-31 | 2020-07-31 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-WRB-CIN-RPA-5110 | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-04-01 | 2020-08-31 | 2020-07-31 | Active | Log | Upd | SN-0741 | Schedule Change | Approved | 2020-07-10 10:12 | RPHY Metro: Updates to POR based on Field inputs
RPHY MRTR-New-WRB-CIN-RPA-5110 | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-04-01 | 2020-09-30 | 2020-07-31 | Active | Log | Upd | SN-0810 | Schedule Change | Approved | 2020-08-07 09:41 | 1 Warner Robins and Clear View needs to be moved to August as Alrm Testing was not completed
RPHY MRTR-New-VSA-CIN MGMT-2K | SW | ARZ | VSA | R PHY | R PHY SW ARZ VSA RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-New-VSA-CIN MGMT-2K | SW | ARZ | VSA | R PHY | R PHY SW ARZ VSA RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Deleted | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-VSA-CIN MGMT-2K | SW | ARZ | VSA | R PHY | R PHY SW ARZ VSA RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Deleted | Log | Del | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-VSA-CIN MGMT-2K | SW | ARZ | VSA | R PHY | R PHY SW ARZ VSA RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Deleted | Log | Del | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-VSA-CIN-DPA-5200 | SW | ARZ | VSA | R PHY | R PHY SW ARZ VSA RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-New-VSA-CIN-DPA-5200 | SW | ARZ | VSA | R PHY | R PHY SW ARZ VSA RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Deleted | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-VSA-CIN-DPA-5200 | SW | ARZ | VSA | R PHY | R PHY SW ARZ VSA RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Deleted | Log | Del | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-VSA-CIN-DPA-5200 | SW | ARZ | VSA | R PHY | R PHY SW ARZ VSA RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Deleted | Log | Del | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-VSA-CIN-RPA-5110 | SW | ARZ | VSA | R PHY | R PHY SW ARZ VSA RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-New-VSA-CIN-RPA-5110 | SW | ARZ | VSA | R PHY | R PHY SW ARZ VSA RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Deleted | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-VSA-CIN-RPA-5110 | SW | ARZ | VSA | R PHY | R PHY SW ARZ VSA RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | Log | Del | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-VSA-CIN-RPA-5110 | SW | ARZ | VSA | R PHY | R PHY SW ARZ VSA RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | Log | Del | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSB-CIN MGMT-2K | SW | LAS | OSB | R PHY | R PHY SW LAS OSB RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-02-05 | 2020-08-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-OSB-CIN MGMT-2K | SW | LAS | OSB | R PHY | R PHY SW LAS OSB RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-02-12 | 2020-03-15 | 2020-03-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-OSB-CIN MGMT-2K | SW | LAS | OSB | R PHY | R PHY SW LAS OSB RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-02-05 | 2020-04-30 | 2020-07-31 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-OSB-CIN MGMT-2K | SW | LAS | OSB | R PHY | R PHY SW LAS OSB RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-02-05 | 2020-08-31 | 2020-08-31 | Active | Log | Upd | SN-0640 | Schedule Change | Approved | 2020-06-06 12:36 | RPHY Metro : POR CHanges based on Field Inputs
RPHY MRTR-New-OSB-CIN-DPA-5200 (100G DPIC) | SW | LAS | OSB | R PHY | R PHY SW LAS OSB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-02-05 | 2020-08-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-OSB-CIN-DPA-5200 (100G DPIC) | SW | LAS | OSB | R PHY | R PHY SW LAS OSB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-02-12 | 2020-03-15 | 2020-03-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-OSB-CIN-DPA-5200 (100G DPIC) | SW | LAS | OSB | R PHY | R PHY SW LAS OSB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-02-05 | 2020-04-30 | 2020-07-31 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-OSB-CIN-DPA-5200 (100G DPIC) | SW | LAS | OSB | R PHY | R PHY SW LAS OSB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-02-05 | 2020-08-31 | 2020-08-31 | Active | Log | Upd | SN-0640 | Schedule Change | Approved | 2020-06-06 12:36 | RPHY Metro : POR CHanges based on Field Inputs
RPHY MRTR-New-OSB-CIN-RPA-5110 | SW | LAS | OSB | R PHY | R PHY SW LAS OSB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-02-05 | 2020-08-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-OSB-CIN-RPA-5110 | SW | LAS | OSB | R PHY | R PHY SW LAS OSB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 5 | 2020-02-12 | 2020-03-15 | 2020-03-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-OSB-CIN-RPA-5110 | SW | LAS | OSB | R PHY | R PHY SW LAS OSB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 5 | 2020-02-05 | 2020-04-30 | 2020-07-31 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-OSB-CIN-RPA-5110 | SW | LAS | OSB | R PHY | R PHY SW LAS OSB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-02-05 | 2020-04-30 | 2020-07-31 | Active | Log | Upd | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSB-CIN-RPA-5110 | SW | LAS | OSB | R PHY | R PHY SW LAS OSB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-02-05 | 2020-08-31 | 2020-08-31 | Active | Log | Upd | SN-0640 | Schedule Change | Approved | 2020-06-06 12:36 | RPHY Metro : POR CHanges based on Field Inputs
RPHY MRTR-New-TEN-CIN-RPA-5110 | SW | LAS | TEN | R PHY | R PHY SW LAS TEN R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 15 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-TEN-CIN-RPA-5110 | SW | LAS | TEN | R PHY | R PHY SW LAS TEN R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 22 | 2020-09-01 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-TEN-CIN-RPA-5110 | SW | LAS | TEN | R PHY | R PHY SW LAS TEN R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 22 | 2020-09-05 | 2020-11-30 | 2021-02-28 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-TEN-CIN-RPA-5110 | SW | LAS | TEN | R PHY | R PHY SW LAS TEN R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 11 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-TEN-CIN-RPA-5110 | SW | LAS | TEN | R PHY | R PHY SW LAS TEN R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 15 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-Growth-CHS-CIN-RPA-5110 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
RPHY MRTR-Growth-CHS-CIN-RPA-5110 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-04-01 | 2020-06-15 | 2020-06-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth-CHS-CIN-RPA-5110 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-Growth-LTF-CIN MGMT-2K | VA | HRD | LTF | R PHY | R PHY VA HRD LTF RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-Growth-LTF-CIN MGMT-2K | VA | HRD | LTF | R PHY | R PHY VA HRD LTF RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-08-15 | 2020-11-01 | 2020-12-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth-LTF-CIN MGMT-2K | VA | HRD | LTF | R PHY | R PHY VA HRD LTF RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-LTF-CIN-DPA-5200 (100G DPIC) | VA | HRD | LTF | R PHY | R PHY VA HRD LTF RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-07-15 | 2020-08-31 | Active | EP
RPHY MRTR-New-LTF-CIN-DPA-5200 (100G DPIC) | VA | HRD | LTF | R PHY | R PHY VA HRD LTF RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-08-15 | 2020-11-01 | 2020-12-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-LTF-CIN-DPA-5200 (100G DPIC) | VA | HRD | LTF | R PHY | R PHY VA HRD LTF RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Active | Log | Del | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-LTF-CIN-DPA-5200 (100G DPIC) | VA | HRD | LTF | R PHY | R PHY VA HRD LTF RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-07-15 | 2020-08-31 | Active | Log | Undel | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-LTF-CIN-RPA-5110 | VA | HRD | LTF | R PHY | R PHY VA HRD LTF RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-LTF-CIN-RPA-5110 | VA | HRD | LTF | R PHY | R PHY VA HRD LTF RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-08-15 | 2020-11-01 | 2020-12-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-LTF-CIN-RPA-5110 | VA | HRD | LTF | R PHY | R PHY VA HRD LTF RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-08-15 | 2020-10-31 | 2021-01-31 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-LTF-CIN-RPA-5110 | VA | HRD | LTF | R PHY | R PHY VA HRD LTF RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-Growth-OCN-CIN-RPA-5110 | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
RPHY MRTR-Growth-OCN-CIN-RPA-5110 | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-04-01 | 2020-06-15 | 2020-06-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth-OCN-CIN-RPA-5110 | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-Growth-PRA-CIN-RPA-5110 | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
RPHY MRTR-Growth-PRA-CIN-RPA-5110 | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth-PRA-CIN-RPA-5110 | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-Growth-PRA-CIN-RPA-5110 | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-Growth-FBG-CIN MGMT-2K | VA | NVA | FBG | R PHY | R PHY VA NVA FBG RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-Growth-FBG-CIN MGMT-2K | VA | NVA | FBG | R PHY | R PHY VA NVA FBG RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-07-01 | 2020-09-15 | 2020-09-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth-FBG-CIN MGMT-2K | VA | NVA | FBG | R PHY | R PHY VA NVA FBG RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-FBG-CIN-DPA-5200 (100G DPIC) | VA | NVA | FBG | R PHY | R PHY VA NVA FBG RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-07-15 | 2020-08-31 | Active | EP
RPHY MRTR-New-FBG-CIN-DPA-5200 (100G DPIC) | VA | NVA | FBG | R PHY | R PHY VA NVA FBG RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-07-01 | 2020-09-15 | 2020-09-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-FBG-CIN-DPA-5200 (100G DPIC) | VA | NVA | FBG | R PHY | R PHY VA NVA FBG RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Active | Log | Del | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-FBG-CIN-DPA-5200 (100G DPIC) | VA | NVA | FBG | R PHY | R PHY VA NVA FBG RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-07-15 | 2020-08-31 | Active | Log | Undel | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-FBG-CIN-RPA-5110 | VA | NVA | FBG | R PHY | R PHY VA NVA FBG RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-FBG-CIN-RPA-5110 | VA | NVA | FBG | R PHY | R PHY VA NVA FBG RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-07-01 | 2020-09-15 | 2020-09-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-FBG-CIN-RPA-5110 | VA | NVA | FBG | R PHY | R PHY VA NVA FBG RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-FBG-CIN-RPA-5110 | VA | NVA | FBG | R PHY | R PHY VA NVA FBG RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
R PHY_CCAP_BVL_RPHY Unbundled Solution V2_43940 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY CCAP Augment POR20 | License | License Activation | 138 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_BVL_RPHY Unbundled Solution V2_43940 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY CCAP Augment POR20 | License | License Activation | 2 | 2020-04-19 | 2020-05-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_BVL_RPHY Unbundled Solution V2_43940 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY CCAP Augment POR20 | License | License Activation | 138 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_BVL_RPHY Unbundled Solution V2_44027 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_BVL_RPHY Unbundled Solution V2_44027 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY CCAP Augment POR20 | License | License Activation | 2558 | 2020-07-15 | 2020-08-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_BVL_RPHY Unbundled Solution V2_44027 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_BVL_RPHY Unbundled Solution V2_44119 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_BVL_RPHY Unbundled Solution V2_44119 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY CCAP Augment POR20 | License | License Activation | 402 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_BVL_RPHY Unbundled Solution V2_44119 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_FAY_RPHY Unbundled Solution V2_43941 | CE | NWA | FAY | R PHY | R PHY CE NWA FAY RPHY CCAP Augment POR20 | License | License Activation | 69 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_FAY_RPHY Unbundled Solution V2_43941 | CE | NWA | FAY | R PHY | R PHY CE NWA FAY RPHY CCAP Augment POR20 | License | License Activation | 1 | 2020-04-20 | 2020-05-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_FAY_RPHY Unbundled Solution V2_43941 | CE | NWA | FAY | R PHY | R PHY CE NWA FAY RPHY CCAP Augment POR20 | License | License Activation | 69 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_FAY_RPHY Unbundled Solution V2_44027 | CE | NWA | FAY | R PHY | R PHY CE NWA FAY RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_FAY_RPHY Unbundled Solution V2_44027 | CE | NWA | FAY | R PHY | R PHY CE NWA FAY RPHY CCAP Augment POR20 | License | License Activation | 44 | 2020-07-15 | 2020-08-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_FAY_RPHY Unbundled Solution V2_44027 | CE | NWA | FAY | R PHY | R PHY CE NWA FAY RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_FAY_RPHY Unbundled Solution V2_44119 | CE | NWA | FAY | R PHY | R PHY CE NWA FAY RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_FAY_RPHY Unbundled Solution V2_44119 | CE | NWA | FAY | R PHY | R PHY CE NWA FAY RPHY CCAP Augment POR20 | License | License Activation | 176 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_FAY_RPHY Unbundled Solution V2_44119 | CE | NWA | FAY | R PHY | R PHY CE NWA FAY RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_BAR_RPHY Unbundled Solution V2_43944 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY CCAP Deployment POR20 | License | License Activation | 276 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_BAR_RPHY Unbundled Solution V2_43944 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY CCAP Deployment POR20 | License | License Activation | 3 | 2020-04-23 | 2020-05-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_BAR_RPHY Unbundled Solution V2_43944 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY CCAP Deployment POR20 | License | License Activation | 276 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_BAR_RPHY Unbundled Solution V2_44027 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_BAR_RPHY Unbundled Solution V2_44027 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY CCAP Deployment POR20 | License | License Activation | 2426 | 2020-07-15 | 2020-08-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_BAR_RPHY Unbundled Solution V2_44027 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_OKC_RPHY Unbundled Solution V2_43942 | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY CCAP Augment POR20 | License | License Activation | 69 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_OKC_RPHY Unbundled Solution V2_43942 | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY CCAP Augment POR20 | License | License Activation | 1 | 2020-04-21 | 2020-05-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_OKC_RPHY Unbundled Solution V2_43942 | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY CCAP Augment POR20 | License | License Activation | 69 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_OKC_RPHY Unbundled Solution V2_44027 | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_OKC_RPHY Unbundled Solution V2_44027 | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY CCAP Augment POR20 | License | License Activation | 2 | 2020-07-15 | 2020-08-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_OKC_RPHY Unbundled Solution V2_44027 | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_OKC_RPHY Unbundled Solution V2_44119 | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_OKC_RPHY Unbundled Solution V2_44119 | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY CCAP Augment POR20 | License | License Activation | 1 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_OKC_RPHY Unbundled Solution V2_44119 | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_OWA_RPHY Unbundled Solution V2_44027 | CE | TUL | OWA | R PHY | R PHY CE TUL OWA RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_OWA_RPHY Unbundled Solution V2_44027 | CE | TUL | OWA | R PHY | R PHY CE TUL OWA RPHY CCAP Augment POR20 | License | License Activation | 89 | 2020-07-15 | 2020-08-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_OWA_RPHY Unbundled Solution V2_44027 | CE | TUL | OWA | R PHY | R PHY CE TUL OWA RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_QNC_RPHY Unbundled Solution V2_44119 | CE | TUL | QNC | R PHY | R PHY CE TUL QNC RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_QNC_RPHY Unbundled Solution V2_44119 | CE | TUL | QNC | R PHY | R PHY CE TUL QNC RPHY CCAP Augment POR20 | License | License Activation | 89 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_QNC_RPHY Unbundled Solution V2_44119 | CE | TUL | QNC | R PHY | R PHY CE TUL QNC RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_WLK_RPHY Unbundled Solution V2_44119 | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_WLK_RPHY Unbundled Solution V2_44119 | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY CCAP Augment POR20 | License | License Activation | 90 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_WLK_RPHY Unbundled Solution V2_44119 | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_YAL_RPHY Unbundled Solution V2_44027 | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY CCAP Augment POR20 | License | License Activation | 69 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_YAL_RPHY Unbundled Solution V2_44027 | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY CCAP Augment POR20 | License | License Activation | 89 | 2020-07-15 | 2020-08-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_YAL_RPHY Unbundled Solution V2_44027 | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY CCAP Augment POR20 | License | License Activation | 69 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_YAL_RPHY Unbundled Solution V2_44119 | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_YAL_RPHY Unbundled Solution V2_44119 | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY CCAP Augment POR20 | License | License Activation | 44 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_YAL_RPHY Unbundled Solution V2_44119 | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_ELK_RPHY Unbundled Solution V2_43943 | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY CCAP Augment POR20 | License | License Activation | 138 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_ELK_RPHY Unbundled Solution V2_43943 | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY CCAP Augment POR20 | License | License Activation | 2 | 2020-04-22 | 2020-05-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_ELK_RPHY Unbundled Solution V2_43943 | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY CCAP Augment POR20 | License | License Activation | 138 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_ELK_RPHY Unbundled Solution V2_44027 | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_ELK_RPHY Unbundled Solution V2_44027 | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY CCAP Augment POR20 | License | License Activation | 4 | 2020-07-15 | 2020-08-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_ELK_RPHY Unbundled Solution V2_44027 | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_ELK_RPHY Unbundled Solution V2_44119 | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_ELK_RPHY Unbundled Solution V2_44119 | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY CCAP Augment POR20 | License | License Activation | 398 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_ELK_RPHY Unbundled Solution V2_44119 | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_SOU_RPHY Unbundled Solution V2_44027 | CE | OMA | SOU | R PHY | R PHY CE OMA SOU RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_SOU_RPHY Unbundled Solution V2_44027 | CE | OMA | SOU | R PHY | R PHY CE OMA SOU RPHY CCAP Augment POR20 | License | License Activation | 4 | 2020-07-15 | 2020-08-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_SOU_RPHY Unbundled Solution V2_44027 | CE | OMA | SOU | R PHY | R PHY CE OMA SOU RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_SOU_RPHY Unbundled Solution V2_44119 | CE | OMA | SOU | R PHY | R PHY CE OMA SOU RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_SOU_RPHY Unbundled Solution V2_44119 | CE | OMA | SOU | R PHY | R PHY CE OMA SOU RPHY CCAP Augment POR20 | License | License Activation | 178 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_SOU_RPHY Unbundled Solution V2_44119 | CE | OMA | SOU | R PHY | R PHY CE OMA SOU RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_BTR_RPHY Unbundled Solution V2_43947 | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY CCAP Augment POR20 | License | License Activation | 1 | 2020-03-01 | 2020-09-30 |  | Active | EP
R PHY_CCAP_BTR_RPHY Unbundled Solution V2_43947 | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY CCAP Augment POR20 | License | License Activation | 1 | 2020-03-01 | 2020-04-01 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_BTR_RPHY Unbundled Solution V2_43947 | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY CCAP Augment POR20 | License | License Activation | 1 | 2020-03-01 | 2020-08-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_BTR_RPHY Unbundled Solution V2_43947 | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY CCAP Augment POR20 | License | License Activation | 1 | 2020-03-01 | 2020-09-30 |  | Active | Log | Upd | SN-0879 | Schedule Change | Approved | 2020-08-28 10:07 | RPHY CCAP POR Update for Roanoke Baton Rouge and Pensacola
R PHY_CCAP_BTR_RPHY Unbundled Solution V2_44027 | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_BTR_RPHY Unbundled Solution V2_44027 | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY CCAP Augment POR20 | License | License Activation | 44 | 2020-07-15 | 2020-08-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_BTR_RPHY Unbundled Solution V2_44027 | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_BTR_RPHY Unbundled Solution V2_44119 | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_BTR_RPHY Unbundled Solution V2_44119 | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY CCAP Augment POR20 | License | License Activation | 224 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_BTR_RPHY Unbundled Solution V2_44119 | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_LFY_RPHY Unbundled Solution V2_43948 | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY CCAP Augment POR20 | License | License Activation | 3 | 2020-03-01 | 2020-05-31 |  | Active | EP
R PHY_CCAP_LFY_RPHY Unbundled Solution V2_43948 | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY CCAP Augment POR20 | License | License Activation | 3 | 2020-03-01 | 2020-04-01 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_LFY_RPHY Unbundled Solution V2_43948 | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY CCAP Augment POR20 | License | License Activation | 3 | 2020-03-01 | 2020-05-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_LFY_RPHY Unbundled Solution V2_44027 | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY CCAP Augment POR20 | License | License Activation | 207 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_LFY_RPHY Unbundled Solution V2_44027 | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY CCAP Augment POR20 | License | License Activation | 44 | 2020-07-15 | 2020-08-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_LFY_RPHY Unbundled Solution V2_44027 | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY CCAP Augment POR20 | License | License Activation | 207 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_LFY_RPHY Unbundled Solution V2_44119 | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_LFY_RPHY Unbundled Solution V2_44119 | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY CCAP Augment POR20 | License | License Activation | 355 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_LFY_RPHY Unbundled Solution V2_44119 | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_LUL_RPHY Unbundled Solution V2_44119 | SE | NOR | LUL | R PHY | R PHY SE NOR LUL RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_LUL_RPHY Unbundled Solution V2_44119 | SE | NOR | LUL | R PHY | R PHY SE NOR LUL RPHY CCAP Augment POR20 | License | License Activation | 45 | 2020-09-01 | 2020-10-01 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_LUL_RPHY Unbundled Solution V2_44119 | SE | NOR | LUL | R PHY | R PHY SE NOR LUL RPHY CCAP Augment POR20 | License | License Activation | 45 | 2020-10-05 | 2020-11-15 |  | Deleted | Log | Upd | SN-0149 | Schedule Change | Approved | 2020-02-06 11:10 | 1 SE RPHY CCAP Plan Change request per field to meet the node action plan 2 Lapalco CBR8 request date changed from July to Sept 3 PNS, LFY, ABV and Luling migration date changes
R PHY_CCAP_LUL_RPHY Unbundled Solution V2_44119 | SE | NOR | LUL | R PHY | R PHY SE NOR LUL RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_MCY_RPHY Unbundled Solution V2_43949 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY CCAP Augment POR20 | License | License Activation | 8 | 2020-03-01 | 2020-04-01 |  | Active | EP
R PHY_CCAP_MCY_RPHY Unbundled Solution V2_43949 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY CCAP Augment POR20 | License | License Activation | 8 | 2020-03-01 | 2020-04-01 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_MCY_RPHY Unbundled Solution V2_44027 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY CCAP Augment POR20 | License | License Activation | 483 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_MCY_RPHY Unbundled Solution V2_44027 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY CCAP Augment POR20 | License | License Activation | 4 | 2020-07-15 | 2020-08-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_MCY_RPHY Unbundled Solution V2_44027 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY CCAP Augment POR20 | License | License Activation | 483 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_MCY_RPHY Unbundled Solution V2_44119 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_MCY_RPHY Unbundled Solution V2_44119 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY CCAP Augment POR20 | License | License Activation | 183 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_MCY_RPHY Unbundled Solution V2_44119 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_CHS_RPHY Unbundled Solution V2_44027 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY CCAP Augment POR20 | License | License Activation | 276 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_CHS_RPHY Unbundled Solution V2_44027 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY CCAP Augment POR20 | License | License Activation | 220 | 2020-07-15 | 2020-08-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_CHS_RPHY Unbundled Solution V2_44027 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY CCAP Augment POR20 | License | License Activation | 276 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_CHS_RPHY Unbundled Solution V2_44119 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_CHS_RPHY Unbundled Solution V2_44119 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY CCAP Augment POR20 | License | License Activation | 352 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_CHS_RPHY Unbundled Solution V2_44119 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_NRF_RPHY Unbundled Solution V2_44027 | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY CCAP Augment POR20 | License | License Activation | 483 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_NRF_RPHY Unbundled Solution V2_44027 | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY CCAP Augment POR20 | License | License Activation | 704 | 2020-07-15 | 2020-08-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_NRF_RPHY Unbundled Solution V2_44027 | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY CCAP Augment POR20 | License | License Activation | 483 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_NRF_RPHY Unbundled Solution V2_44119 | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_NRF_RPHY Unbundled Solution V2_44119 | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY CCAP Augment POR20 | License | License Activation | 837 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_NRF_RPHY Unbundled Solution V2_44119 | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_OCN_RPHY Unbundled Solution V2_44027 | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY CCAP Augment POR20 | License | License Activation | 207 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_OCN_RPHY Unbundled Solution V2_44027 | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY CCAP Augment POR20 | License | License Activation | 44 | 2020-07-15 | 2020-08-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_OCN_RPHY Unbundled Solution V2_44027 | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY CCAP Augment POR20 | License | License Activation | 207 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_OCN_RPHY Unbundled Solution V2_44119 | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_OCN_RPHY Unbundled Solution V2_44119 | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY CCAP Augment POR20 | License | License Activation | 324 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_OCN_RPHY Unbundled Solution V2_44119 | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PTM_RPHY Unbundled Solution V2_43946 | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY CCAP Augment POR20 | License | License Activation | 69 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_PTM_RPHY Unbundled Solution V2_43946 | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY CCAP Augment POR20 | License | License Activation | 1 | 2020-04-25 | 2020-05-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_PTM_RPHY Unbundled Solution V2_43946 | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY CCAP Augment POR20 | License | License Activation | 69 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_PTM_RPHY Unbundled Solution V2_44027 | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_PTM_RPHY Unbundled Solution V2_44027 | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY CCAP Augment POR20 | License | License Activation | 488 | 2020-07-15 | 2020-08-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_PTM_RPHY Unbundled Solution V2_44027 | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PTM_RPHY Unbundled Solution V2_44119 | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_PTM_RPHY Unbundled Solution V2_44119 | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY CCAP Augment POR20 | License | License Activation | 667 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_PTM_RPHY Unbundled Solution V2_44119 | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PRA_RPHY Unbundled Solution V2_44027 | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY CCAP Augment POR20 | License | License Activation | 69 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_PRA_RPHY Unbundled Solution V2_44027 | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY CCAP Augment POR20 | License | License Activation | 528 | 2020-07-15 | 2020-08-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_PRA_RPHY Unbundled Solution V2_44027 | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY CCAP Augment POR20 | License | License Activation | 69 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_PRA_RPHY Unbundled Solution V2_44119 | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_PRA_RPHY Unbundled Solution V2_44119 | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY CCAP Augment POR20 | License | License Activation | 1857 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_PRA_RPHY Unbundled Solution V2_44119 | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_VBC_RPHY Unbundled Solution V2_44027 | VA | HRD | VBC | R PHY | R PHY VA HRD VBC RPHY CCAP Augment POR20 | License | License Activation | 207 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_VBC_RPHY Unbundled Solution V2_44027 | VA | HRD | VBC | R PHY | R PHY VA HRD VBC RPHY CCAP Augment POR20 | License | License Activation | 308 | 2020-07-15 | 2020-08-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_VBC_RPHY Unbundled Solution V2_44027 | VA | HRD | VBC | R PHY | R PHY VA HRD VBC RPHY CCAP Augment POR20 | License | License Activation | 207 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_VBC_RPHY Unbundled Solution V2_44119 | VA | HRD | VBC | R PHY | R PHY VA HRD VBC RPHY CCAP Augment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | EP
R PHY_CCAP_VBC_RPHY Unbundled Solution V2_44119 | VA | HRD | VBC | R PHY | R PHY VA HRD VBC RPHY CCAP Augment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 3 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_VBC_RPHY Unbundled Solution V2_44119 | VA | HRD | VBC | R PHY | R PHY VA HRD VBC RPHY CCAP Augment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_RON_RPHY Unbundled Solution V2_44027 | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_RON_RPHY Unbundled Solution V2_44027 | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY CCAP Augment POR20 | License | License Activation | 265 | 2020-07-15 | 2020-08-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_RON_RPHY Unbundled Solution V2_44027 | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_RON_RPHY Unbundled Solution V2_44119 | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_RON_RPHY Unbundled Solution V2_44119 | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY CCAP Augment POR20 | License | License Activation | 577 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_RON_RPHY Unbundled Solution V2_44119 | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_SRH_Boundary_Clocks_44119 | CE | OKC | SRH | R PHY | R PHY CE OKC SRH RPHY CCAP Augment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_SRH_Boundary_Clocks_44119 | CE | OKC | SRH | R PHY | R PHY CE OKC SRH RPHY CCAP Augment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-10-15 | 2020-11-01 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_SRH_Boundary_Clocks_44119 | CE | OKC | SRH | R PHY | R PHY CE OKC SRH RPHY CCAP Augment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis |  |  |  |  | Deleted | Log | Del | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_SRH_D9485_44119 | CE | OKC | SRH | R PHY | R PHY CE OKC SRH RPHY CCAP Augment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_SRH_D9485_44119 | CE | OKC | SRH | R PHY | R PHY CE OKC SRH RPHY CCAP Augment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-10-15 | 2020-11-01 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_SRH_D9485_44119 | CE | OKC | SRH | R PHY | R PHY CE OKC SRH RPHY CCAP Augment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_SRH_RPHY Bundled Solution V3_44119 | CE | OKC | SRH | R PHY | R PHY CE OKC SRH RPHY CCAP Augment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_SRH_RPHY Bundled Solution V3_44119 | CE | OKC | SRH | R PHY | R PHY CE OKC SRH RPHY CCAP Augment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-10-15 | 2020-11-01 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_SRH_RPHY Bundled Solution V3_44119 | CE | OKC | SRH | R PHY | R PHY CE OKC SRH RPHY CCAP Augment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_TUL_RPHY Bundled Solution V3_43945 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL R PHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-05-26 | 2020-10-30 | 2020-10-30 | Active | EP
R PHY_CCAP_TUL_RPHY Bundled Solution V3_43945 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL R PHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-04-24 | 2020-05-01 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_TUL_RPHY Bundled Solution V3_43945 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL R PHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-12-01 | 2020-12-31 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_TUL_RPHY Bundled Solution V3_43945 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL R PHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-05-26 | 2020-08-30 | 2020-08-30 | Active | Log | Upd | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_TUL_RPHY Bundled Solution V3_43945 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL R PHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-05-26 | 2020-10-30 | 2020-10-30 | Active | Log | Upd | SN-0613 | Schedule Change | Approved | 2020-05-29 16:19 | RPHY CCAP POR Update
R PHY_CCAP_TUL_RPHY Unbundled Solution V2_44027 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL R PHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | EP
R PHY_CCAP_TUL_RPHY Unbundled Solution V2_44027 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL R PHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 3 | 2020-07-15 | 2020-08-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_TUL_RPHY Unbundled Solution V2_44027 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL R PHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_TUL_RPHY Unbundled Solution V2_44119 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL R PHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | EP
R PHY_CCAP_TUL_RPHY Unbundled Solution V2_44119 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL R PHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_TUL_RPHY Unbundled Solution V2_44119 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL R PHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
RPHY MRTR-New-SSC-CIN-Nokia-OCML | SW | ARZ | SSC | R PHY | R PHY SW ARZ SSC RPHY Metro Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-New-SSC-CIN-Nokia-OCML | SW | ARZ | SSC | R PHY | R PHY SW ARZ SSC RPHY Metro Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Deleted | Log | Undel | SN-0147 | Scope Change | Approved | 2020-02-06 11:08 | 1 The OCML and 10G Tunable BOM s are submitted for Q1 2 The OCML Q2 is available and Q3-Q4 Volume has been created 3 Total 3 6M will be hitting RPHY Metro Budget which was not built into the plan 4 Asking for this fund from Risk
RPHY MRTR-New-SSC-CIN-Nokia-OCML | SW | ARZ | SSC | R PHY | R PHY SW ARZ SSC RPHY Metro Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-ERN-CIN-Nokia-OCML | SW | LAS | ERN | R PHY | R PHY SW LAS ERN RPHY Metro Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-New-ERN-CIN-Nokia-OCML | SW | LAS | ERN | R PHY | R PHY SW LAS ERN RPHY Metro Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Deleted | Log | New | SN-0147 | Scope Change | Approved | 2020-02-06 11:08 | 1 The OCML and 10G Tunable BOM s are submitted for Q1 2 The OCML Q2 is available and Q3-Q4 Volume has been created 3 Total 3 6M will be hitting RPHY Metro Budget which was not built into the plan 4 Asking for this fund from Risk
RPHY MRTR-New-ERN-CIN-Nokia-OCML | SW | LAS | ERN | R PHY | R PHY SW LAS ERN RPHY Metro Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-TUC-CIN-Nokia-OCML | SW | ARZ | TUC | R PHY | R PHY SW ARZ TUC RPHY Metro Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-New-TUC-CIN-Nokia-OCML | SW | ARZ | TUC | R PHY | R PHY SW ARZ TUC RPHY Metro Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Deleted | Log | New | SN-0147 | Scope Change | Approved | 2020-02-06 11:08 | 1 The OCML and 10G Tunable BOM s are submitted for Q1 2 The OCML Q2 is available and Q3-Q4 Volume has been created 3 Total 3 6M will be hitting RPHY Metro Budget which was not built into the plan 4 Asking for this fund from Risk
RPHY MRTR-New-TUC-CIN-Nokia-OCML | SW | ARZ | TUC | R PHY | R PHY SW ARZ TUC RPHY Metro Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-VLY-CIN-Nokia-OCML | SW | LAS | VLY | R PHY | R PHY SW LAS VLY RPHY Metro Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-New-VLY-CIN-Nokia-OCML | SW | LAS | VLY | R PHY | R PHY SW LAS VLY RPHY Metro Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Deleted | Log | New | SN-0147 | Scope Change | Approved | 2020-02-06 11:08 | 1 The OCML and 10G Tunable BOM s are submitted for Q1 2 The OCML Q2 is available and Q3-Q4 Volume has been created 3 Total 3 6M will be hitting RPHY Metro Budget which was not built into the plan 4 Asking for this fund from Risk
RPHY MRTR-New-VLY-CIN-Nokia-OCML | SW | LAS | VLY | R PHY | R PHY SW LAS VLY RPHY Metro Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-PNL-CIN-Nokia-OCML | SW | ARZ | PNL | R PHY | R PHY SW ARZ PNL RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | EP
RPHY MRTR-New-PNL-CIN-Nokia-OCML | SW | ARZ | PNL | R PHY | R PHY SW ARZ PNL RPHY Metro Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | New | SN-0147 | Scope Change | Approved | 2020-02-06 11:08 | 1 The OCML and 10G Tunable BOM s are submitted for Q1 2 The OCML Q2 is available and Q3-Q4 Volume has been created 3 Total 3 6M will be hitting RPHY Metro Budget which was not built into the plan 4 Asking for this fund from Risk
RPHY MRTR-New-PNL-CIN-Nokia-OCML | SW | ARZ | PNL | R PHY | R PHY SW ARZ PNL RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | Upd | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-NSC-CIN-Nokia-OCML | SW | ARZ | NSC | R PHY | R PHY SW ARZ NSC RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2020-01-01 | 2020-03-15 | 2020-06-15 | Active | EP
RPHY MRTR-New-NSC-CIN-Nokia-OCML | SW | ARZ | NSC | R PHY | R PHY SW ARZ NSC RPHY Metro Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | New | SN-0147 | Scope Change | Approved | 2020-02-06 11:08 | 1 The OCML and 10G Tunable BOM s are submitted for Q1 2 The OCML Q2 is available and Q3-Q4 Volume has been created 3 Total 3 6M will be hitting RPHY Metro Budget which was not built into the plan 4 Asking for this fund from Risk
RPHY MRTR-New-NSC-CIN-Nokia-OCML | SW | ARZ | NSC | R PHY | R PHY SW ARZ NSC RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2020-01-01 | 2020-03-15 | 2020-06-15 | Active | Log | Upd | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-MCD-CIN-Nokia-OCML | SW | ARZ | MCD | R PHY | R PHY SW ARZ MCD RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | EP
RPHY MRTR-New-MCD-CIN-Nokia-OCML | SW | ARZ | MCD | R PHY | R PHY SW ARZ MCD RPHY Metro Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | New | SN-0147 | Scope Change | Approved | 2020-02-06 11:08 | 1 The OCML and 10G Tunable BOM s are submitted for Q1 2 The OCML Q2 is available and Q3-Q4 Volume has been created 3 Total 3 6M will be hitting RPHY Metro Budget which was not built into the plan 4 Asking for this fund from Risk
RPHY MRTR-New-MCD-CIN-Nokia-OCML | SW | ARZ | MCD | R PHY | R PHY SW ARZ MCD RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | Upd | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-FWL-CIN-Nokia-OCML | SW | ARZ | FWL | R PHY | R PHY SW ARZ FWL RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | EP
RPHY MRTR-New-FWL-CIN-Nokia-OCML | SW | ARZ | FWL | R PHY | R PHY SW ARZ FWL RPHY Metro Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | New | SN-0147 | Scope Change | Approved | 2020-02-06 11:08 | 1 The OCML and 10G Tunable BOM s are submitted for Q1 2 The OCML Q2 is available and Q3-Q4 Volume has been created 3 Total 3 6M will be hitting RPHY Metro Budget which was not built into the plan 4 Asking for this fund from Risk
RPHY MRTR-New-FWL-CIN-Nokia-OCML | SW | ARZ | FWL | R PHY | R PHY SW ARZ FWL RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | Upd | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-CHD-CIN-Nokia-OCML | SW | ARZ | CHD | R PHY | R PHY SW ARZ CHD RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | EP
RPHY MRTR-New-CHD-CIN-Nokia-OCML | SW | ARZ | CHD | R PHY | R PHY SW ARZ CHD RPHY Metro Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | New | SN-0147 | Scope Change | Approved | 2020-02-06 11:08 | 1 The OCML and 10G Tunable BOM s are submitted for Q1 2 The OCML Q2 is available and Q3-Q4 Volume has been created 3 Total 3 6M will be hitting RPHY Metro Budget which was not built into the plan 4 Asking for this fund from Risk
RPHY MRTR-New-CHD-CIN-Nokia-OCML | SW | ARZ | CHD | R PHY | R PHY SW ARZ CHD RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | Upd | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-BUK-CIN-Nokia-OCML | SW | ARZ | BUK | R PHY | R PHY SW ARZ BUK RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | EP
RPHY MRTR-New-BUK-CIN-Nokia-OCML | SW | ARZ | BUK | R PHY | R PHY SW ARZ BUK RPHY Metro Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | New | SN-0147 | Scope Change | Approved | 2020-02-06 11:08 | 1 The OCML and 10G Tunable BOM s are submitted for Q1 2 The OCML Q2 is available and Q3-Q4 Volume has been created 3 Total 3 6M will be hitting RPHY Metro Budget which was not built into the plan 4 Asking for this fund from Risk
RPHY MRTR-New-BUK-CIN-Nokia-OCML | SW | ARZ | BUK | R PHY | R PHY SW ARZ BUK RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | Upd | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-PWY-CIN-Nokia-OCML | CA | SAN | PWY | R PHY | R PHY CA SAN PWY RPHY Metro Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-New-PWY-CIN-Nokia-OCML | CA | SAN | PWY | R PHY | R PHY CA SAN PWY RPHY Metro Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Deleted | Log | New | SN-0147 | Scope Change | Approved | 2020-02-06 11:08 | 1 The OCML and 10G Tunable BOM s are submitted for Q1 2 The OCML Q2 is available and Q3-Q4 Volume has been created 3 Total 3 6M will be hitting RPHY Metro Budget which was not built into the plan 4 Asking for this fund from Risk
RPHY MRTR-New-PWY-CIN-Nokia-OCML | CA | SAN | PWY | R PHY | R PHY CA SAN PWY RPHY Metro Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OCE-CIN-Nokia-OCML | CA | SAN | OCE | R PHY | R PHY CA SAN OCE RPHY Metro Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-New-OCE-CIN-Nokia-OCML | CA | SAN | OCE | R PHY | R PHY CA SAN OCE RPHY Metro Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Deleted | Log | New | SN-0147 | Scope Change | Approved | 2020-02-06 11:08 | 1 The OCML and 10G Tunable BOM s are submitted for Q1 2 The OCML Q2 is available and Q3-Q4 Volume has been created 3 Total 3 6M will be hitting RPHY Metro Budget which was not built into the plan 4 Asking for this fund from Risk
RPHY MRTR-New-OCE-CIN-Nokia-OCML | CA | SAN | OCE | R PHY | R PHY CA SAN OCE RPHY Metro Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-FED-CIN-Nokia-OCML | CA | SAN | FED | R PHY | R PHY CA SAN FED RPHY Metro Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-New-FED-CIN-Nokia-OCML | CA | SAN | FED | R PHY | R PHY CA SAN FED RPHY Metro Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Deleted | Log | New | SN-0147 | Scope Change | Approved | 2020-02-06 11:08 | 1 The OCML and 10G Tunable BOM s are submitted for Q1 2 The OCML Q2 is available and Q3-Q4 Volume has been created 3 Total 3 6M will be hitting RPHY Metro Budget which was not built into the plan 4 Asking for this fund from Risk
RPHY MRTR-New-FED-CIN-Nokia-OCML | CA | SAN | FED | R PHY | R PHY CA SAN FED RPHY Metro Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-DNP-CIN-Nokia-OCML | CA | ORG | DNP | R PHY | R PHY CA ORG DNP RPHY Metro Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-New-DNP-CIN-Nokia-OCML | CA | ORG | DNP | R PHY | R PHY CA ORG DNP RPHY Metro Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Deleted | Log | New | SN-0147 | Scope Change | Approved | 2020-02-06 11:08 | 1 The OCML and 10G Tunable BOM s are submitted for Q1 2 The OCML Q2 is available and Q3-Q4 Volume has been created 3 Total 3 6M will be hitting RPHY Metro Budget which was not built into the plan 4 Asking for this fund from Risk
RPHY MRTR-New-DNP-CIN-Nokia-OCML | CA | ORG | DNP | R PHY | R PHY CA ORG DNP RPHY Metro Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-IND-CIN-Nokia-OCML | CE | TUL | IND | R PHY | R PHY CE TUL IND RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-IND-CIN-Nokia-OCML | CE | TUL | IND | R PHY | R PHY CE TUL IND RPHY Metro Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Deleted | Log | New | SN-0147 | Scope Change | Approved | 2020-02-06 11:08 | 1 The OCML and 10G Tunable BOM s are submitted for Q1 2 The OCML Q2 is available and Q3-Q4 Volume has been created 3 Total 3 6M will be hitting RPHY Metro Budget which was not built into the plan 4 Asking for this fund from Risk
RPHY MRTR-New-IND-CIN-Nokia-OCML | CE | TUL | IND | R PHY | R PHY CE TUL IND RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-30 | Deleted | Log | Upd | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-IND-CIN-Nokia-OCML | CE | TUL | IND | R PHY | R PHY CE TUL IND RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-WIC2-CIN-RPA-5110 | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-New-WIC2-CIN-RPA-5110 | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Deleted | Log | New | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-WIC2-CIN-RPA-5110 | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | Log | Del | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
R PHY_CCAP_BVL_CBR8-1 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAP_BVL_CBR8-1 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_FAY_CBR8-1 | CE | NWA | FAY | R PHY | R PHY CE NWA FAY RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAP_FAY_CBR8-1 | CE | NWA | FAY | R PHY | R PHY CE NWA FAY RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_NWA_GMC1 | CE | NWA | NWA | R PHY | R PHY CE NWA NWA RPHY CCAP Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAP_NWA_GMC1 | CE | NWA | NWA | R PHY | R PHY CE NWA NWA RPHY CCAP Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_CL_CBR8-1 | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAP_CL_CBR8-1 | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_OKC_CBR8-1 | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAP_OKC_CBR8-1 | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_WLK_CBR8-1 | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAP_WLK_CBR8-1 | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_ELK_CBR8-1 | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAP_ELK_CBR8-1 | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_OMM_GMC1 | CE | OMA | OMM | R PHY | R PHY CE OMA OMM RPHY CCAP Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAP_OMM_GMC1 | CE | OMA | OMM | R PHY | R PHY CE OMA OMM RPHY CCAP Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_SOU_CBR8-1 | CE | OMA | SOU | R PHY | R PHY CE OMA SOU RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAP_SOU_CBR8-1 | CE | OMA | SOU | R PHY | R PHY CE OMA SOU RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_BAR_CBR8-1 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAP_BAR_CBR8-1 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAPOWA_CBR8-1 | CE | TUL | OWA | R PHY | R PHY CE TUL OWA R PHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAPOWA_CBR8-1 | CE | TUL | OWA | R PHY | R PHY CE TUL OWA R PHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_QNC_CBR8-1 | CE | TUL | QNC | R PHY | R PHY CE TUL QNC RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAP_QNC_CBR8-1 | CE | TUL | QNC | R PHY | R PHY CE TUL QNC RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_TUL_CBR8-1 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAP_TUL_CBR8-1 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_YAL_CBR8-1 | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-12-20 | 2020-12-20 | Active | EP
R PHY_CCAP_YAL_CBR8-1 | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_YAL_CBR8-1 | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-12-20 | 2020-12-20 | Active | Log | Upd | SN-0637 | Schedule Change | Approved | 2020-06-05 14:50 | RPHY CCAP POR Update
R PHY_CCAP_PRV_GMC1 | NE | RHD | PRV | R PHY | R PHY NE RHD PRV RPHY CCAP Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-11-01 |  | Active | EP
R PHY_CCAP_PRV_GMC1 | NE | RHD | PRV | R PHY | R PHY NE RHD PRV RPHY CCAP Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_PRV_GMC1 | NE | RHD | PRV | R PHY | R PHY NE RHD PRV RPHY CCAP Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | Upd | SN-0865 | Schedule Change | Approved | 2020-08-21 11:34 | This is to update the RPHY Activation dae for Providence facility
R PHY_CCAP_PRV_GMC1 | NE | RHD | PRV | R PHY | R PHY NE RHD PRV RPHY CCAP Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-11-01 |  | Active | Log | Upd | SN-0958 | Schedule Change | Approved | 2020-09-25 09:32 | This is to update Providence RPHY activation date
R PHY_CCAP_PTH_CBR8-1 | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-04-21 |  | Active | EP
R PHY_CCAP_PTH_CBR8-1 | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_PTH_CBR8-1 | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-11-01 |  | Active | Log | Upd | SN-0865 | Schedule Change | Approved | 2020-08-21 11:34 | This is to update the RPHY Activation dae for Providence facility
R PHY_CCAP_PTH_CBR8-1 | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-04-21 |  | Active | Log | Upd | SN-0958 | Schedule Change | Approved | 2020-09-25 09:32 | This is to update Providence RPHY activation date
R PHY_CCAP_BTR_CBR8-1 | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-09-30 |  | Active | EP
R PHY_CCAP_BTR_CBR8-1 | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-08-15 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_BTR_CBR8-1 | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-09-30 |  | Active | Log | Upd | SN-0879 | Schedule Change | Approved | 2020-08-28 10:07 | RPHY CCAP POR Update for Roanoke Baton Rouge and Pensacola
R PHY_CCAP_ABV_CBR8-1 | SE | LFY | ABV | R PHY | R PHY SE LFY ABV RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-10-31 |  | Active | EP
R PHY_CCAP_ABV_CBR8-1 | SE | LFY | ABV | R PHY | R PHY SE LFY ABV RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-11-15 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_ABV_CBR8-1 | SE | LFY | ABV | R PHY | R PHY SE LFY ABV RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-09-30 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_ABV_CBR8-1 | SE | LFY | ABV | R PHY | R PHY SE LFY ABV RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-10-31 |  | Active | Log | Upd | SN-0899 | Schedule Change | Approved | 2020-09-11 09:34 | RPHY CCAP actiation date updates for Fort Smith and Abbeville sites Material delivery date update for CLV FTS RSM BLU and HEN facilites
R PHY_CCAP_LFY_CBR8-1 | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-05-31 |  | Active | EP
R PHY_CCAP_LFY_CBR8-1 | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-05-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_ELM_GMC1 | SE | NOR | ELM | R PHY | R PHY SE NOR ELM RPHY CCAP Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAP_ELM_GMC1 | SE | NOR | ELM | R PHY | R PHY SE NOR ELM RPHY CCAP Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_LUL_CBR8-1 | SE | NOR | LUL | R PHY | R PHY SE NOR LUL RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-10-30 |  | Active | EP
R PHY_CCAP_LUL_CBR8-1 | SE | NOR | LUL | R PHY | R PHY SE NOR LUL RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-11-30 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_LUL_CBR8-1 | SE | NOR | LUL | R PHY | R PHY SE NOR LUL RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-10-30 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_MCY_CBR8-1 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAP_MCY_CBR8-1 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_CHS_CBR8-1 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAP_CHS_CBR8-1 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_NRF_CBR8-1 | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAP_NRF_CBR8-1 | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_OCN_CBR8-1 | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-04-30 |  | Active | EP
R PHY_CCAP_OCN_CBR8-1 | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-04-30 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_PRA_CBR8-1 | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-05-31 |  | Active | EP
R PHY_CCAP_PRA_CBR8-1 | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-05-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_PTM_CBR8-1 | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-05-31 |  | Active | EP
R PHY_CCAP_PTM_CBR8-1 | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-05-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_RON_CBR8-1 | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-10-31 |  | Active | EP
R PHY_CCAP_RON_CBR8-1 | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-06-30 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_RON_CBR8-1 | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-10-31 |  | Active | Log | Upd | SN-0879 | Schedule Change | Approved | 2020-08-28 10:07 | RPHY CCAP POR Update for Roanoke Baton Rouge and Pensacola
R PHY_CCAP_BVL_Boundary_Clocks-1 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAP_BVL_Boundary_Clocks-1 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_BVL_Boundary_Clocks-1 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_FAY_Boundary_Clocks-1 | CE | NWA | FAY | R PHY | R PHY CE NWA FAY RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAP_FAY_Boundary_Clocks-1 | CE | NWA | FAY | R PHY | R PHY CE NWA FAY RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_FAY_Boundary_Clocks-1 | CE | NWA | FAY | R PHY | R PHY CE NWA FAY RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_OKC_Boundary_Clocks-1 | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAP_OKC_Boundary_Clocks-1 | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_OKC_Boundary_Clocks-1 | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_OKC_GMC1 | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAP_OKC_GMC1 | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_CL_Boundary_Clocks-1 | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAP_CL_Boundary_Clocks-1 | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_CL_Boundary_Clocks-1 | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_WLK_Boundary_Clocks-1 | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAP_WLK_Boundary_Clocks-1 | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_WLK_Boundary_Clocks-1 | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_OKC_QPSK-1 | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAP_OKC_QPSK-1 | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_CL_QPSK-1 | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAP_CL_QPSK-1 | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_WLK_QPSK-1 | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAP_WLK_QPSK-1 | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_ELK_Boundary_Clocks-1 | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAP_ELK_Boundary_Clocks-1 | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_ELK_Boundary_Clocks-1 | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_SOU_Boundary_Clocks-1 | CE | OMA | SOU | R PHY | R PHY CE OMA SOU RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAP_SOU_Boundary_Clocks-1 | CE | OMA | SOU | R PHY | R PHY CE OMA SOU RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_SOU_Boundary_Clocks-1 | CE | OMA | SOU | R PHY | R PHY CE OMA SOU RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_BAR_Boundary_Clocks-1 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAP_BAR_Boundary_Clocks-1 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_BAR_Boundary_Clocks-1 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_TUL_Boundary_Clocks-1 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAP_TUL_Boundary_Clocks-1 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_TUL_Boundary_Clocks-1 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_TUL_GMC1 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAP_TUL_GMC1 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAPOWA_Boundary_Clocks-1 | CE | TUL | OWA | R PHY | R PHY CE TUL OWA R PHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAPOWA_Boundary_Clocks-1 | CE | TUL | OWA | R PHY | R PHY CE TUL OWA R PHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAPOWA_Boundary_Clocks-1 | CE | TUL | OWA | R PHY | R PHY CE TUL OWA R PHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_QNC_Boundary_Clocks-1 | CE | TUL | QNC | R PHY | R PHY CE TUL QNC RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAP_QNC_Boundary_Clocks-1 | CE | TUL | QNC | R PHY | R PHY CE TUL QNC RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_QNC_Boundary_Clocks-1 | CE | TUL | QNC | R PHY | R PHY CE TUL QNC RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_YAL_Boundary_Clocks-1 | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-12-20 | 2020-12-20 | Active | EP
R PHY_CCAP_YAL_Boundary_Clocks-1 | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_YAL_Boundary_Clocks-1 | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_YAL_Boundary_Clocks-1 | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-12-20 | 2020-12-20 | Active | Log | Upd | SN-0637 | Schedule Change | Approved | 2020-06-05 14:50 | RPHY CCAP POR Update
R PHY_CCAP_PTH_Boundary_Clocks-1 | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-04-21 |  | Active | EP
R PHY_CCAP_PTH_Boundary_Clocks-1 | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_PTH_Boundary_Clocks-1 | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_PTH_Boundary_Clocks-1 | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-11-01 |  | Active | Log | Upd | SN-0865 | Schedule Change | Approved | 2020-08-21 11:34 | This is to update the RPHY Activation dae for Providence facility
R PHY_CCAP_PTH_Boundary_Clocks-1 | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-04-21 |  | Active | Log | Upd | SN-0958 | Schedule Change | Approved | 2020-09-25 09:32 | This is to update Providence RPHY activation date
R PHY_CCAP_BTR_Boundary_Clocks-1 | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-09-30 |  | Active | EP
R PHY_CCAP_BTR_Boundary_Clocks-1 | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-08-15 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_BTR_Boundary_Clocks-1 | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-08-15 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_BTR_Boundary_Clocks-1 | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-09-30 |  | Active | Log | Upd | SN-0879 | Schedule Change | Approved | 2020-08-28 10:07 | RPHY CCAP POR Update for Roanoke Baton Rouge and Pensacola
R PHY_CCAP_ABV_Boundary_Clocks-1 | SE | LFY | ABV | R PHY | R PHY SE LFY ABV RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-10-31 |  | Active | EP
R PHY_CCAP_ABV_Boundary_Clocks-1 | SE | LFY | ABV | R PHY | R PHY SE LFY ABV RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-11-15 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_ABV_Boundary_Clocks-1 | SE | LFY | ABV | R PHY | R PHY SE LFY ABV RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-09-30 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_ABV_Boundary_Clocks-1 | SE | LFY | ABV | R PHY | R PHY SE LFY ABV RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-10-31 |  | Active | Log | Upd | SN-0899 | Schedule Change | Approved | 2020-09-11 09:34 | RPHY CCAP actiation date updates for Fort Smith and Abbeville sites Material delivery date update for CLV FTS RSM BLU and HEN facilites
R PHY_CCAP_LFY_Boundary_Clocks-1 | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-05-31 |  | Active | EP
R PHY_CCAP_LFY_Boundary_Clocks-1 | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-05-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_LFY_Boundary_Clocks-1 | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-05-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_LFY_Boundary_Clocks-1 | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-05-31 |  | Active | Log | Upd | SN-0613 | Schedule Change | Approved | 2020-05-29 16:19 | RPHY CCAP POR Update
R PHY_CCAP_LUL_Boundary_Clocks-1 | SE | NOR | LUL | R PHY | R PHY SE NOR LUL RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-10-30 |  | Active | EP
R PHY_CCAP_LUL_Boundary_Clocks-1 | SE | NOR | LUL | R PHY | R PHY SE NOR LUL RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-11-30 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_LUL_Boundary_Clocks-1 | SE | NOR | LUL | R PHY | R PHY SE NOR LUL RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-10-30 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_MCY_Boundary_Clocks-1 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAP_MCY_Boundary_Clocks-1 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_MCY_Boundary_Clocks-1 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_CHS_Boundary_Clocks-1 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAP_CHS_Boundary_Clocks-1 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_CHS_Boundary_Clocks-1 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_NRF_Boundary_Clocks-1 | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
R PHY_CCAP_NRF_Boundary_Clocks-1 | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_NRF_Boundary_Clocks-1 | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_OCN_Boundary_Clocks-1 | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-04-30 |  | Active | EP
R PHY_CCAP_OCN_Boundary_Clocks-1 | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-04-30 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_OCN_Boundary_Clocks-1 | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-04-30 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_PRA_Boundary_Clocks-1 | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-05-31 |  | Active | EP
R PHY_CCAP_PRA_Boundary_Clocks-1 | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-05-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_PRA_Boundary_Clocks-1 | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-05-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_PTM_Boundary_Clocks-1 | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-05-31 |  | Active | EP
R PHY_CCAP_PTM_Boundary_Clocks-1 | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-05-31 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_PTM_Boundary_Clocks-1 | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-05-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_RON_Boundary_Clocks-1 | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-10-31 |  | Active | EP
R PHY_CCAP_RON_Boundary_Clocks-1 | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-06-30 |  | Active | Log | New | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_RON_Boundary_Clocks-1 | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-06-30 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_RON_Boundary_Clocks-1 | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-10-31 |  | Active | Log | Upd | SN-0879 | Schedule Change | Approved | 2020-08-28 10:07 | RPHY CCAP POR Update for Roanoke Baton Rouge and Pensacola
RPHY MRTR-New-CHS-CIN-Nokia-OCML | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY Metro Initial Deployment POR19 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-CHS-CIN-Nokia-OCML | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY Metro Initial Deployment POR19 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-NRF-CIN-Nokia-OCML | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-NRF-CIN-Nokia-OCML | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY Metro Initial Deployment POR19 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2019-11-15 | 2020-03-31 |  | Deleted | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-NRF-CIN-Nokia-OCML | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-OCN-CIN-Nokia-OCML | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-OCN-CIN-Nokia-OCML | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY Metro Initial Deployment POR19 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2019-11-15 | 2020-04-30 |  | Deleted | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-OCN-CIN-Nokia-OCML | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-PRA-CIN-RPA-5110 | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-05-31 |  | Active | EP
RPHY MRTR-New-PRA-CIN-RPA-5110 | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-05-31 |  | Active | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-PRA-CIN-DPA-5200 | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-05-31 |  | Active | EP
RPHY MRTR-New-PRA-CIN-DPA-5200 | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-05-31 |  | Active | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-PRA-CIN MGMT-2K | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-05-31 |  | Active | EP
RPHY MRTR-New-PRA-CIN MGMT-2K | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-05-31 |  | Active | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-PRA-CIN-Nokia-OCML | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-PRA-CIN-Nokia-OCML | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY Metro Initial Deployment POR19 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2019-11-15 | 2020-05-31 |  | Deleted | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-PRA-CIN-Nokia-OCML | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-PTM-CIN-Nokia-OCML | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-PTM-CIN-Nokia-OCML | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY Metro Initial Deployment POR19 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2019-11-15 | 2020-05-31 |  | Deleted | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-PTM-CIN-Nokia-OCML | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-RON-CIN-RPA-5110 | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-09-30 | 2020-09-30 | Active | EP
RPHY MRTR-New-RON-CIN-RPA-5110 | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-06-30 |  | Active | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-RON-CIN-RPA-5110 | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0640 | Schedule Change | Approved | 2020-06-06 12:36 | RPHY Metro : POR CHanges based on Field Inputs
RPHY MRTR-New-RON-CIN-DPA-5200 | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-06-30 |  | Active | EP
RPHY MRTR-New-RON-CIN-DPA-5200 | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-06-30 |  | Active | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-RON-CIN MGMT-2K | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-06-30 |  | Active | EP
RPHY MRTR-New-RON-CIN MGMT-2K | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-06-30 |  | Active | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-RON-CIN-Nokia-OCML | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-RON-CIN-Nokia-OCML | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY Metro Initial Deployment POR19 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2019-11-15 | 2020-06-30 |  | Deleted | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-RON-CIN-Nokia-OCML | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-BVL-CIN-Nokia-OCML | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-BVL-CIN-Nokia-OCML | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY Metro Initial Deployment POR19 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2019-11-15 | 2020-03-31 |  | Deleted | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-BVL-CIN-Nokia-OCML | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-FAY-CIN-Nokia-OCML | CE | NWA | FAY | R PHY | R PHY CE NWA FAY RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-FAY-CIN-Nokia-OCML | CE | NWA | FAY | R PHY | R PHY CE NWA FAY RPHY Metro Initial Deployment POR19 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2019-11-15 | 2020-03-31 |  | Deleted | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-FAY-CIN-Nokia-OCML | CE | NWA | FAY | R PHY | R PHY CE NWA FAY RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-CLH-CIN-RPA-5110 | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-CLH-CIN-RPA-5110 | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-CLH-CIN-DPA-5200 | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-CLH-CIN-DPA-5200 | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-CLH-CIN MGMT-2K | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-CLH-CIN MGMT-2K | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-CLH-CIN-Nokia-OCML | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-CLH-CIN-Nokia-OCML | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY Metro Initial Deployment POR19 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2019-11-15 | 2020-03-31 |  | Deleted | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-CLH-CIN-Nokia-OCML | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-OKC-CIN-Nokia-OCML | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-OKC-CIN-Nokia-OCML | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY Metro Initial Deployment POR19 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2019-11-15 | 2020-03-31 |  | Deleted | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-OKC-CIN-Nokia-OCML | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-WLK-CIN-Nokia-OCML | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-WLK-CIN-Nokia-OCML | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY Metro Initial Deployment POR19 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2019-11-15 | 2020-03-31 |  | Deleted | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-WLK-CIN-Nokia-OCML | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-ELK-CIN-Nokia-OCML | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-ELK-CIN-Nokia-OCML | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY Metro Initial Deployment POR19 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2019-11-15 | 2020-03-31 |  | Deleted | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-ELK-CIN-Nokia-OCML | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-SOU-CIN-RPA-5110 | CE | OMA | SOU | R PHY | R PHY CE OMA SOU RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-SOU-CIN-RPA-5110 | CE | OMA | SOU | R PHY | R PHY CE OMA SOU RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-SOU-CIN-DPA-5200 | CE | OMA | SOU | R PHY | R PHY CE OMA SOU RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-SOU-CIN-DPA-5200 | CE | OMA | SOU | R PHY | R PHY CE OMA SOU RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-SOU-CIN MGMT-2K | CE | OMA | SOU | R PHY | R PHY CE OMA SOU RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-SOU-CIN MGMT-2K | CE | OMA | SOU | R PHY | R PHY CE OMA SOU RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-SOU-CIN-Nokia-OCML | CE | OMA | SOU | R PHY | R PHY CE OMA SOU RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-SOU-CIN-Nokia-OCML | CE | OMA | SOU | R PHY | R PHY CE OMA SOU RPHY Metro Initial Deployment POR19 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2019-11-15 | 2020-03-31 |  | Deleted | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-SOU-CIN-Nokia-OCML | CE | OMA | SOU | R PHY | R PHY CE OMA SOU RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-BAR-CIN-Nokia-OCML | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-BAR-CIN-Nokia-OCML | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY Metro Initial Deployment POR19 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2019-11-15 | 2020-03-31 |  | Deleted | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-BAR-CIN-Nokia-OCML | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-OWA-CIN-Nokia-OCML | CE | TUL | OWA | R PHY | R PHY CE TUL OWA RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-OWA-CIN-Nokia-OCML | CE | TUL | OWA | R PHY | R PHY CE TUL OWA RPHY Metro Initial Deployment POR19 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2019-11-15 | 2020-03-31 |  | Deleted | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-OWA-CIN-Nokia-OCML | CE | TUL | OWA | R PHY | R PHY CE TUL OWA RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-QNC-CIN-Nokia-OCML | CE | TUL | QNC | R PHY | R PHY CE TUL QNC RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-QNC-CIN-Nokia-OCML | CE | TUL | QNC | R PHY | R PHY CE TUL QNC RPHY Metro Initial Deployment POR19 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2019-11-15 | 2020-03-31 |  | Deleted | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-QNC-CIN-Nokia-OCML | CE | TUL | QNC | R PHY | R PHY CE TUL QNC RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-TUL-CIN-Nokia-OCML | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-TUL-CIN-Nokia-OCML | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY Metro Initial Deployment POR19 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2019-11-15 | 2020-03-31 |  | Deleted | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-TUL-CIN-Nokia-OCML | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-YAL-CIN-Nokia-OCML | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-YAL-CIN-Nokia-OCML | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY Metro Initial Deployment POR19 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2019-11-15 | 2020-03-31 |  | Deleted | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-YAL-CIN-Nokia-OCML | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-BTR-CIN-Nokia-OCML | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-BTR-CIN-Nokia-OCML | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY Metro Initial Deployment POR19 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2019-11-15 | 2020-08-31 |  | Deleted | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-BTR-CIN-Nokia-OCML | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-ABV-CIN-Nokia-OCML | SE | LFY | ABV | R PHY | R PHY SE LFY ABV RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-ABV-CIN-Nokia-OCML | SE | LFY | ABV | R PHY | R PHY SE LFY ABV RPHY Metro Initial Deployment POR19 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2019-11-15 | 2020-11-30 |  | Deleted | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-ABV-CIN-Nokia-OCML | SE | LFY | ABV | R PHY | R PHY SE LFY ABV RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-LFY-CIN-Nokia-OCML | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-LFY-CIN-Nokia-OCML | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY Metro Initial Deployment POR19 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2019-11-15 | 2020-05-31 |  | Deleted | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-LFY-CIN-Nokia-OCML | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-LUL-CIN-Nokia-OCML | SE | NOR | LUL | R PHY | R PHY SE NOR LUL RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-LUL-CIN-Nokia-OCML | SE | NOR | LUL | R PHY | R PHY SE NOR LUL RPHY Metro Initial Deployment POR19 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2019-11-15 | 2020-11-30 |  | Deleted | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-LUL-CIN-Nokia-OCML | SE | NOR | LUL | R PHY | R PHY SE NOR LUL RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-MCY-CIN-Nokia-OCML | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-MCY-CIN-Nokia-OCML | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY Metro Initial Deployment POR19 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2019-11-15 | 2020-03-31 |  | Deleted | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-MCY-CIN-Nokia-OCML | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-PTH-CIN-RPA-5110 | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-PTH-CIN-RPA-5110 | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-PTH-CIN-DPA-5200 | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-PTH-CIN-DPA-5200 | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-PTH-CIN MGMT-2K | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-PTH-CIN MGMT-2K | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-PTH-CIN-Nokia-OCML | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-PTH-CIN-Nokia-OCML | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY Metro Initial Deployment POR19 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2019-11-15 | 2020-03-31 |  | Deleted | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-PTH-CIN-Nokia-OCML | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
CCAP Licenses | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | License | License Activation | 138 | 2020-04-15 | 2020-09-30 |  | Active | EP
CCAP Licenses | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | License | License Activation | 138 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
CCAP Licenses | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | License | License Activation | 138 | 2020-04-15 | 2020-07-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
CCAP Licenses | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | License | License Activation | 138 | 2020-04-15 | 2020-08-31 |  | Active | Log | Upd | SN-0811 | Schedule Change | Approved | 2020-08-07 09:40 | This is to update RPHY CCAP POR for CLR WRB SAB and PNS sites
CCAP Licenses | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | License | License Activation | 138 | 2020-04-15 | 2020-09-30 |  | Active | Log | Upd | SN-0879 | Schedule Change | Approved | 2020-08-28 10:07 | RPHY CCAP POR Update for Roanoke Baton Rouge and Pensacola
RPHY MRTR-New-NWA-CIN-Nokia-OCML | CE | NWA | NWA | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-NWA-CIN-Nokia-OCML | CE | NWA | NWA | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-15 | 2020-03-31 | 2020-03-31 | Deleted | Log | Undel | SN-0232 | Scope Change | Approved | 2020-02-06 09:32 | 1 There appears to be more OCML PON Overlay projects outside of the NT2 0 plan in the pipeline 2 Johnson for example would need OCML which is not part of 2020 POR and is 2021 acceleration 3 Adding a risk CR to denote the activity that would be in comin
RPHY MRTR-New-NWA-CIN-Nokia-OCML | CE | NWA | NWA | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-WRB-CIN-Nokia-OCML | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-New-WRB-CIN-Nokia-OCML | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 50 | 2020-04-05 | 2020-06-01 | 2020-06-30 | Deleted | Log | New | SN-0270 | Schedule Change | Approved | 2020-02-21 16:29 | 1 Pulling in Warner Rbins and Santa Barbara into Q2 2 OCML in Warner Robins is not covered in the current budget, adding that to the plan 3 New OCML request to be raised seperate 4 Total Pull IN of 520K
RPHY MRTR-New-WRB-CIN-Nokia-OCML | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-PWY-CIN-Nokia-OCML2 | CA | SAN | PWY | R PHY | R PHY CA SAN PWY RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2020-01-01 | 2020-03-15 | 2020-06-30 | Active | EP
RPHY MRTR-New-PWY-CIN-Nokia-OCML2 | CA | SAN | PWY | R PHY | R PHY CA SAN PWY RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2020-01-01 | 2020-03-15 | 2020-06-30 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-PWY-CIN-RPA-5110 | CA | SAN | PWY | R PHY | R PHY CA SAN PWY RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-New-PWY-CIN-RPA-5110 | CA | SAN | PWY | R PHY | R PHY CA SAN PWY RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OCE-CIN-ATX-OCML | CA | SAN | OCE | R PHY | R PHY CA SAN OCE RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2020-01-01 | 2020-03-15 | 2020-06-30 | Active | EP
RPHY MRTR-New-OCE-CIN-ATX-OCML | CA | SAN | OCE | R PHY | R PHY CA SAN OCE RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2020-01-01 | 2020-03-15 | 2020-06-30 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OCE-CIN-ATX-OCML2 | CA | SAN | OCE | R PHY | R PHY CA SAN OCE RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-New-OCE-CIN-ATX-OCML2 | CA | SAN | OCE | R PHY | R PHY CA SAN OCE RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OCE-RPA-5110 | CA | SAN | OCE | R PHY | R PHY CA SAN OCE RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 6 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-New-OCE-RPA-5110 | CA | SAN | OCE | R PHY | R PHY CA SAN OCE RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 6 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-FED-CIN-ATX-OCML | CA | SAN | FED | R PHY | R PHY CA SAN FED RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-30 | Active | EP
RPHY MRTR-New-FED-CIN-ATX-OCML | CA | SAN | FED | R PHY | R PHY CA SAN FED RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-30 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-FED-CIN-ATX-OCML2 | CA | SAN | FED | R PHY | R PHY CA SAN FED RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-New-FED-CIN-ATX-OCML2 | CA | SAN | FED | R PHY | R PHY CA SAN FED RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 20 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-FED-CIN-ATX-OCML2 | CA | SAN | FED | R PHY | R PHY CA SAN FED RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-FED-CIN-RPA-5110 | CA | SAN | FED | R PHY | R PHY CA SAN FED RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 14 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-New-FED-CIN-RPA-5110 | CA | SAN | FED | R PHY | R PHY CA SAN FED RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 16 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-FED-CIN-RPA-5110 | CA | SAN | FED | R PHY | R PHY CA SAN FED RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 14 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-FED-CIN-DPA-5200 | CA | SAN | FED | R PHY | R PHY CA SAN FED RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-New-FED-CIN-DPA-5200 | CA | SAN | FED | R PHY | R PHY CA SAN FED RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-FED-CIN MGMT-2K | CA | SAN | FED | R PHY | R PHY CA SAN FED RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-New-FED-CIN MGMT-2K | CA | SAN | FED | R PHY | R PHY CA SAN FED RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-ELC-CIN-ATX-OCML | CA | SAN | ELC | R PHY | R PHY CA SAN ELC RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-30 | Active | EP
RPHY MRTR-New-ELC-CIN-ATX-OCML | CA | SAN | ELC | R PHY | R PHY CA SAN ELC RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-30 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-ELC-CIN-ATX-OCML2 | CA | SAN | ELC | R PHY | R PHY CA SAN ELC RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-New-ELC-CIN-ATX-OCML2 | CA | SAN | ELC | R PHY | R PHY CA SAN ELC RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 20 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-ELC-CIN-ATX-OCML2 | CA | SAN | ELC | R PHY | R PHY CA SAN ELC RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-ELC-CIN-DPA-5200 | CA | SAN | ELC | R PHY | R PHY CA SAN ELC RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 6 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-New-ELC-CIN-DPA-5200 | CA | SAN | ELC | R PHY | R PHY CA SAN ELC RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 6 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-ELC-CIN MGMT-2K | CA | SAN | ELC | R PHY | R PHY CA SAN ELC RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-New-ELC-CIN MGMT-2K | CA | SAN | ELC | R PHY | R PHY CA SAN ELC RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-DWN-CIN-ATX-OCML | CA | SAN | DWN | R PHY | R PHY CA SAN DWN R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-30 | Active | EP
RPHY MRTR-New-DWN-CIN-ATX-OCML | CA | SAN | DWN | R PHY | R PHY CA SAN DWN R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-30 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-DWN-CIN-RPA-5110 | CA | SAN | DWN | R PHY | R PHY CA SAN DWN R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 9 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-New-DWN-CIN-RPA-5110 | CA | SAN | DWN | R PHY | R PHY CA SAN DWN R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 11 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-DWN-CIN-RPA-5110 | CA | SAN | DWN | R PHY | R PHY CA SAN DWN R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 9 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-DWN-CIN-ATX-OCML2 | CA | SAN | DWN | R PHY | R PHY CA SAN DWN R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-New-DWN-CIN-ATX-OCML2 | CA | SAN | DWN | R PHY | R PHY CA SAN DWN R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 20 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-DWN-CIN-ATX-OCML2 | CA | SAN | DWN | R PHY | R PHY CA SAN DWN R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-DWN-CIN MGMT-2K | CA | SAN | DWN | R PHY | R PHY CA SAN DWN R PHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-New-DWN-CIN MGMT-2K | CA | SAN | DWN | R PHY | R PHY CA SAN DWN R PHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-CHU-CIN-ATX-OCML | CA | SAN | CHU | R PHY | R PHY CA SAN CHU RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-06-15 | 2020-06-30 | Active | EP
RPHY MRTR-New-CHU-CIN-ATX-OCML | CA | SAN | CHU | R PHY | R PHY CA SAN CHU RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-06-15 | 2020-06-30 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-Growth-CHU-CIN-RPA2-5110 | CA | SAN | CHU | R PHY | R PHY CA SAN CHU RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 9 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-Growth-CHU-CIN-RPA2-5110 | CA | SAN | CHU | R PHY | R PHY CA SAN CHU RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 11 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-Growth-CHU-CIN-RPA2-5110 | CA | SAN | CHU | R PHY | R PHY CA SAN CHU RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 9 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-CHU-CIN-ATX-OCML2 | CA | SAN | CHU | R PHY | R PHY CA SAN CHU RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-New-CHU-CIN-ATX-OCML2 | CA | SAN | CHU | R PHY | R PHY CA SAN CHU RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 20 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-CHU-CIN-ATX-OCML2 | CA | SAN | CHU | R PHY | R PHY CA SAN CHU RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-CHU-CIN MGMT-2K | CA | SAN | CHU | R PHY | R PHY CA SAN CHU RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-New-CHU-CIN MGMT-2K | CA | SAN | CHU | R PHY | R PHY CA SAN CHU RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-RSM-CIN-ATX-OCML | CA | ORG | RSM | R PHY | R PHY CA ORG RSM RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-06-15 | 2020-06-15 | Active | EP
RPHY MRTR-New-RSM-CIN-ATX-OCML | CA | ORG | RSM | R PHY | R PHY CA ORG RSM RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-06-15 | 2020-06-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-Growth-RSM-CIN-RPA-5110 | CA | ORG | RSM | R PHY | R PHY CA ORG RSM RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 6 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-Growth-RSM-CIN-RPA-5110 | CA | ORG | RSM | R PHY | R PHY CA ORG RSM RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-Growth-RSM-CIN-RPA-5110 | CA | ORG | RSM | R PHY | R PHY CA ORG RSM RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 6 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-Growth-RSM-CIN-DPA-5200 | CA | ORG | RSM | R PHY | R PHY CA ORG RSM RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-Growth-RSM-CIN-DPA-5200 | CA | ORG | RSM | R PHY | R PHY CA ORG RSM RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-PAV-CIN-ATX-OCML | CA | ORG | PAV | R PHY | R PHY CA ORG PAV R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2020-01-01 | 2020-03-15 | 2020-06-30 | Active | EP
RPHY MRTR-New-PAV-CIN-ATX-OCML | CA | ORG | PAV | R PHY | R PHY CA ORG PAV R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2020-01-01 | 2020-03-15 | 2020-06-30 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-PAV2-CIN-RPA-5110 | CA | ORG | PAV | R PHY | R PHY CA ORG PAV R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 5 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-New-PAV2-CIN-RPA-5110 | CA | ORG | PAV | R PHY | R PHY CA ORG PAV R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 5 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-PAV-CIN-ATX-OCML2 | CA | ORG | PAV | R PHY | R PHY CA ORG PAV R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-New-PAV-CIN-ATX-OCML2 | CA | ORG | PAV | R PHY | R PHY CA ORG PAV R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-PAV-CIN MGMT-2K | CA | ORG | PAV | R PHY | R PHY CA ORG PAV R PHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-New-PAV-CIN MGMT-2K | CA | ORG | PAV | R PHY | R PHY CA ORG PAV R PHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-ORG-CIN-ATX-OCML | CA | ORG | ORG | R PHY | R PHY CA ORG ORG RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-30 | Active | EP
RPHY MRTR-New-ORG-CIN-ATX-OCML | CA | ORG | ORG | R PHY | R PHY CA ORG ORG RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-30 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-IRV-CIN-ATX-OCML | CA | ORG | IRV | R PHY | R PHY CA ORG IRV RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-30 | Active | EP
RPHY MRTR-New-IRV-CIN-ATX-OCML | CA | ORG | IRV | R PHY | R PHY CA ORG IRV RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-30 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-IRV-CIN-RPA2-5110 | CA | ORG | IRV | R PHY | R PHY CA ORG IRV RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 6 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-New-IRV-CIN-RPA2-5110 | CA | ORG | IRV | R PHY | R PHY CA ORG IRV RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 6 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-DNP-CIN-ATX-OCML | CA | ORG | DNP | R PHY | R PHY CA ORG DNP RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-30 | Active | EP
RPHY MRTR-New-DNP-CIN-ATX-OCML | CA | ORG | DNP | R PHY | R PHY CA ORG DNP RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-30 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-DNP-CIN-RPA-5110 | CA | ORG | DNP | R PHY | R PHY CA ORG DNP RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 6 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-New-DNP-CIN-RPA-5110 | CA | ORG | DNP | R PHY | R PHY CA ORG DNP RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 6 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-AVJ-CIN-ATX-OCML | CA | ORG | AVJ | R PHY | R PHY CA ORG AVJ RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-30 | Active | EP
RPHY MRTR-New-AVJ-CIN-ATX-OCML | CA | ORG | AVJ | R PHY | R PHY CA ORG AVJ RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-30 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-AVJ-CIN-RPA2-5110 | CA | ORG | AVJ | R PHY | R PHY CA ORG AVJ RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 16 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-New-AVJ-CIN-RPA2-5110 | CA | ORG | AVJ | R PHY | R PHY CA ORG AVJ RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 14 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-AVJ-CIN-RPA2-5110 | CA | ORG | AVJ | R PHY | R PHY CA ORG AVJ RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 16 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-AVJ-CIN-ATX-OCML2 | CA | ORG | AVJ | R PHY | R PHY CA ORG AVJ RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-New-AVJ-CIN-ATX-OCML2 | CA | ORG | AVJ | R PHY | R PHY CA ORG AVJ RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-AVJ-CIN MGMT-2K | CA | ORG | RSM | R PHY | R PHY CA ORG RSM RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-New-AVJ-CIN MGMT-2K | CA | ORG | AVJ | R PHY | R PHY CA ORG AVJ RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-AVJ-CIN MGMT-2K | CA | ORG | RSM | R PHY | R PHY CA ORG RSM RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-SAB-CIN-ATX-OCML | CA | SAB | SAB | R PHY | R PHY CA SAB SAB RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 100 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-New-SAB-CIN-ATX-OCML | CA | SAB | SAB | R PHY | R PHY CA SAB SAB RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 120 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-SAB-CIN-ATX-OCML | CA | SAB | SAB | R PHY | R PHY CA SAB SAB RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 100 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-ESC-CIN-RPA-5110 | CA | SAN | ESC | R PHY | R PHY CA SAN ESC RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-New-ESC-CIN-RPA-5110 | CA | SAN | ESC | R PHY | R PHY CA SAN ESC RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-ESC-CIN-RPA-5110 | CA | SAN | ESC | R PHY | R PHY CA SAN ESC RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-ESC-CIN-ATX-OCML | CA | SAN | ESC | R PHY | R PHY CA SAN ESC RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 20 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-New-ESC-CIN-ATX-OCML | CA | SAN | ESC | R PHY | R PHY CA SAN ESC RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 20 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-ESC-CIN MGMT-2K | CA | SAN | ESC | R PHY | R PHY CA SAN ESC RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-New-ESC-CIN MGMT-2K | CA | SAN | ESC | R PHY | R PHY CA SAN ESC RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-VST-CIN-ATX-OCML | CA | SAN | VST | R PHY | R PHY CA SAN VST RPHY Metro Augment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-30 | Active | EP
RPHY MRTR-New-VST-CIN-ATX-OCML | CA | SAN | VST | R PHY | R PHY CA SAN VST RPHY Metro Augment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-30 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-VST-CIN-RPA-5110 | CA | SAN | VST | R PHY | R PHY CA SAN VST RPHY Metro Augment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 8 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-New-VST-CIN-RPA-5110 | CA | SAN | VST | R PHY | R PHY CA SAN VST RPHY Metro Augment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 10 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-VST-CIN-RPA-5110 | CA | SAN | VST | R PHY | R PHY CA SAN VST RPHY Metro Augment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 8 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-VST-CIN-ATX-OCML2 | CA | SAN | VST | R PHY | R PHY CA SAN VST RPHY Metro Augment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-New-VST-CIN-ATX-OCML2 | CA | SAN | VST | R PHY | R PHY CA SAN VST RPHY Metro Augment POR20 | Chassis | OCML - ATX OCML RACK KIT | 20 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-VST-CIN-ATX-OCML2 | CA | SAN | VST | R PHY | R PHY CA SAN VST RPHY Metro Augment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-VST-CIN MGMT-2K | CA | SAN | VST | R PHY | R PHY CA SAN VST RPHY Metro Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-New-VST-CIN MGMT-2K | CA | SAN | VST | R PHY | R PHY CA SAN VST RPHY Metro Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-BLV-CIN-Nokia-OCML | CE | OMA | BLV | R PHY | R PHY CE OMA BLV RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-05-15 | 2020-10-31 | 2020-10-31 | Active | EP
RPHY MRTR-New-BLV-CIN-Nokia-OCML | CE | OMA | BLV | R PHY | R PHY CE OMA BLV RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-BLV-CIN-Nokia-OCML | CE | OMA | BLV | R PHY | R PHY CE OMA BLV RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 3 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-BLV-CIN-Nokia-OCML | CE | OMA | BLV | R PHY | R PHY CE OMA BLV RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-05-15 | 2020-10-31 | 2020-10-31 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-MWC-CIN-Nokia-OCML | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 20 | 2020-05-15 | 2020-11-30 | 2020-11-30 | Active | EP
RPHY MRTR-New-MWC-CIN-Nokia-OCML | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 20 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-MWC-CIN-Nokia-OCML | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 20 | 2020-05-15 | 2020-11-30 | 2020-11-30 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-WIC-CIN-NOKIA-OCML | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 20 | 2020-05-15 | 2020-07-31 | 2020-09-30 | Active | EP
RPHY MRTR-New-WIC-CIN-NOKIA-OCML | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 20 | 2020-05-15 | 2020-07-31 | 2020-09-30 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-WIC-CIN-NOKIA-OCML | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 20 | 2020-05-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-TUL-CIN-RPA2-5110 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 10 | 2020-05-15 | 2020-10-31 | 2020-10-31 | Active | EP
RPHY MRTR-New-TUL-CIN-RPA2-5110 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 18 | 2020-05-15 | 2020-07-31 | 2020-08-30 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-TUL-CIN-RPA2-5110 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 10 | 2020-05-15 | 2020-07-31 | 2020-08-30 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-TUL-CIN-RPA2-5110 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 10 | 2020-05-15 | 2020-10-31 | 2020-10-31 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-TUL-CIN-Nokia-OCML2 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 50 | 2020-05-15 | 2020-10-31 | 2020-10-31 | Active | EP
RPHY MRTR-New-TUL-CIN-Nokia-OCML2 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 90 | 2020-05-15 | 2020-07-31 | 2020-08-30 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-TUL-CIN-Nokia-OCML2 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 50 | 2020-05-15 | 2020-07-31 | 2020-08-30 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-TUL-CIN-Nokia-OCML2 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 50 | 2020-05-15 | 2020-10-31 | 2020-10-31 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-TUL-CIN MGMT2-2K | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 3 | 2020-05-15 | 2020-10-31 | 2020-10-31 | Active | EP
RPHY MRTR-New-TUL-CIN MGMT2-2K | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 9 | 2020-05-15 | 2020-07-31 | 2020-08-30 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-TUL-CIN MGMT2-2K | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 3 | 2020-05-15 | 2020-07-31 | 2020-08-30 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-TUL-CIN MGMT2-2K | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 3 | 2020-05-15 | 2020-10-31 | 2020-10-31 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-ONA-CIN-NOKIA-OCML | CE | OMA | ONA | R PHY | R PHY CE OMA ONA RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2021-03-31 | Active | EP
RPHY MRTR-New-ONA-CIN-NOKIA-OCML | CE | OMA | ONA | R PHY | R PHY CE OMA ONA RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 20 | 2020-05-15 | 2020-07-31 | 2021-03-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-ONA-CIN-NOKIA-OCML | CE | OMA | ONA | R PHY | R PHY CE OMA ONA RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 20 | 2020-05-15 | 2020-07-31 | 2021-03-31 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-ONA-CIN-NOKIA-OCML | CE | OMA | ONA | R PHY | R PHY CE OMA ONA RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2021-03-31 | Active | Log | Upd | SN-0786 | Schedule Change | Approved | 2020-07-27 09:30 | 1 SE OSNAP for Metairie was approved last week in CR 726 2 This POR adds that EPS project created into the POR 3 Also updating OCML Chassis count for Omaha North as to align with the BOM
RPHY MRTR-New-FTS-CIN-Nokia-OCML | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-05-15 | 2020-11-20 | 2020-09-30 | Active | EP
RPHY MRTR-New-FTS-CIN-Nokia-OCML | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 20 | 2020-05-15 | 2020-07-31 | 2020-08-30 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-FTS-CIN-Nokia-OCML | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 20 | 2020-05-15 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-FTS-CIN-Nokia-OCML | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-05-15 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0710 | Schedule Change | Approved | 2020-06-26 09:58 | Updates to Optical Switch in Central Region and OCML Chassis count in Fort Smith and Garnett
RPHY MRTR-New-FTS-CIN-Nokia-OCML | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-05-15 | 2020-11-20 | 2020-09-30 | Active | Log | Upd | SN-0900 | Schedule Change | Approved | 2020-09-11 09:33 | RPHY Metro: POR Update to activation date for 2 sites Abbeville sue to resource constraints and the site was low priority Adjusting date for Forst SMith as well
RPHY MRTR-New-GAR-CIN-NOKIA-OCML | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-05-15 | 2020-09-30 | 2020-09-30 | Active | EP
RPHY MRTR-New-GAR-CIN-NOKIA-OCML | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 20 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-GAR-CIN-NOKIA-OCML | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 20 | 2020-05-15 | 2020-11-30 | 2020-11-30 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-GAR-CIN-NOKIA-OCML | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-05-15 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0710 | Schedule Change | Approved | 2020-06-26 09:58 | Updates to Optical Switch in Central Region and OCML Chassis count in Fort Smith and Garnett
RPHY MRTR-New-WES-CIN-NOKIA-OCML | CE | OMA | WES | R PHY | R PHY CE OMA WES RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2021-03-31 | Active | EP
RPHY MRTR-New-WES-CIN-NOKIA-OCML | CE | OMA | WES | R PHY | R PHY CE OMA WES RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2021-03-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-NEH-CIN-NOKIA-OCML | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-05-15 | 2020-12-31 | 2020-12-31 | Active | EP
RPHY MRTR-New-NEH-CIN-NOKIA-OCML | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-NEH-CIN-NOKIA-OCML | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-05-15 | 2020-12-31 | 2020-12-31 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-PNS-CIN-RPA2-5110 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-New-PNS-CIN-RPA2-5110 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Deleted | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-PNS-CIN-RPA2-5110 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-PNS-CIN-ATX-OCML | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-09-30 | 2020-07-31 | Active | EP
RPHY MRTR-New-PNS-CIN-ATX-OCML | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 20 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-PNS-CIN-ATX-OCML | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-PNS-CIN-ATX-OCML | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-07-31 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-PNS-CIN-ATX-OCML | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-08-31 | 2020-07-31 | Active | Log | Upd | SN-0786 | Schedule Change | Approved | 2020-07-27 09:30 | 1 SE OSNAP for Metairie was approved last week in CR 726 2 This POR adds that EPS project created into the POR 3 Also updating OCML Chassis count for Omaha North as to align with the BOM
RPHY MRTR-New-PNS-CIN-ATX-OCML | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-09-30 | 2020-07-31 | Active | Log | Upd | SN-0881 | Schedule Change | Approved | 2020-08-28 10:07 | 1 Moving Pensacola Activation Date from August to September because of Firewall issues 2 Moving BTR dates from August to September because of Resource constraints in with BTR NF team
RPHY MRTR-Growth-PNS-CIN MGMT2-2K | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-Growth-PNS-CIN MGMT2-2K | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Deleted | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-Growth-PNS-CIN MGMT2-2K | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-SPC-CIN-Nokia-OCML | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-SPC-CIN-Nokia-OCML | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Deleted | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-SPC-CIN-Nokia-OCML | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-SPC-CIN-ATX-OCML | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-SPC-CIN-ATX-OCML | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 20 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-SPC-CIN-ATX-OCML | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-SPC-CIN-ATX-OCML | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0741 | Schedule Change | Approved | 2020-07-10 10:12 | RPHY Metro: Updates to POR based on Field inputs
RPHY MRTR-New-VLY-CIN-Nokia-OCML1 | SW | LAS | VLY | R PHY | R PHY SW LAS VLY RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-VLY-CIN-Nokia-OCML1 | SW | LAS | VLY | R PHY | R PHY SW LAS VLY RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-15 | Deleted | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-VLY-CIN-Nokia-OCML1 | SW | LAS | VLY | R PHY | R PHY SW LAS VLY RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-VLY-CIN-RPA-5110 | SW | LAS | VLY | R PHY | R PHY SW LAS VLY RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-VLY-CIN-RPA-5110 | SW | LAS | VLY | R PHY | R PHY SW LAS VLY RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-TEN-CIN-Nokia-OCML2 | SW | LAS | TEN | R PHY | R PHY SW LAS TEN R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-TEN-CIN-Nokia-OCML2 | SW | LAS | TEN | R PHY | R PHY SW LAS TEN R PHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 24 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Deleted | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-TEN-CIN-Nokia-OCML2 | SW | LAS | TEN | R PHY | R PHY SW LAS TEN R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-TEN-CIN-ATX-OCML | SW | LAS | TEN | R PHY | R PHY SW LAS TEN R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-TEN-CIN-ATX-OCML | SW | LAS | TEN | R PHY | R PHY SW LAS TEN R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-TEN-CIN MGMT-2K | SW | LAS | TEN | R PHY | R PHY SW LAS TEN R PHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 3 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-TEN-CIN MGMT-2K | SW | LAS | TEN | R PHY | R PHY SW LAS TEN R PHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-TEN-CIN MGMT-2K | SW | LAS | TEN | R PHY | R PHY SW LAS TEN R PHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 3 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-HEN-CIN-ATX-OCML | SW | LAS | HEN | R PHY | R PHY SW LAS HEN R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 36 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
RPHY MRTR-New-HEN-CIN-ATX-OCML | SW | LAS | HEN | R PHY | R PHY SW LAS HEN R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 36 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-HEN-CIN-RPA2-5110 | SW | LAS | HEN | R PHY | R PHY SW LAS HEN R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 9 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-HEN-CIN-RPA2-5110 | SW | LAS | HEN | R PHY | R PHY SW LAS HEN R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 3 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-HEN-CIN-RPA2-5110 | SW | LAS | HEN | R PHY | R PHY SW LAS HEN R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 9 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-HEN-CIN-ATX-OCML2 | SW | LAS | HEN | R PHY | R PHY SW LAS HEN R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-HEN-CIN-ATX-OCML2 | SW | LAS | HEN | R PHY | R PHY SW LAS HEN R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-HEN-CIN-DPA-5110 | SW | LAS | HEN | R PHY | R PHY SW LAS HEN R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-HEN-CIN-DPA-5110 | SW | LAS | HEN | R PHY | R PHY SW LAS HEN R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-HEN-CIN MGMT-2K | SW | LAS | HEN | R PHY | R PHY SW LAS HEN R PHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-HEN-CIN MGMT-2K | SW | LAS | HEN | R PHY | R PHY SW LAS HEN R PHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-HEN-CIN MGMT-2K | SW | LAS | HEN | R PHY | R PHY SW LAS HEN R PHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-ERN-CIN-Nokia-OCML2 | SW | LAS | ERN | R PHY | R PHY SW LAS ERN RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-ERN-CIN-Nokia-OCML2 | SW | LAS | ERN | R PHY | R PHY SW LAS ERN RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-15 | Deleted | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-ERN-CIN-Nokia-OCML2 | SW | LAS | ERN | R PHY | R PHY SW LAS ERN RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-ALI-CIN-Nokia-OCML | SW | LAS | ALI | R PHY | R PHY SW LAS ALI RPHY Metro Augment POR20 | Chassis | OCML - ATX OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-ALI-CIN-Nokia-OCML | SW | LAS | ALI | R PHY | R PHY SW ARZ VSA RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 24 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Deleted | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-ALI-CIN-Nokia-OCML | SW | LAS | ALI | R PHY | R PHY SW LAS ALI RPHY Metro Augment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 24 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Deleted | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-ALI-CIN-Nokia-OCML | SW | LAS | ALI | R PHY | R PHY SW LAS ALI RPHY Metro Augment POR20 | Chassis | OCML - ATX OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-ALI-CIN-RPA-5110 | SW | LAS | ALI | R PHY | R PHY SW LAS ALI RPHY Metro Augment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 5 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-ALI-CIN-RPA-5110 | SW | LAS | ALI | R PHY | R PHY SW ARZ VSA RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 5 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-ALI-CIN-RPA-5110 | SW | LAS | ALI | R PHY | R PHY SW LAS ALI RPHY Metro Augment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 5 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-VSA-CIN-RPA2-5110 | SW | ARZ | VSA | R PHY | R PHY SW ARZ VSA RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 3 | 2020-05-15 | 2020-07-31 | 2020-07-31 | Active | EP
RPHY MRTR-New-VSA-CIN-RPA2-5110 | SW | ARZ | VSA | R PHY | R PHY SW ARZ VSA RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 3 | 2020-05-15 | 2020-07-31 | 2020-07-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-TUC-CIN-Nokia2-OCML | SW | ARZ | TUC | R PHY | R PHY SW ARZ TUC RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-15 | Active | EP
RPHY MRTR-New-TUC-CIN-Nokia2-OCML | SW | ARZ | TUC | R PHY | R PHY SW ARZ TUC RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-TUC-CIN-RPA-5110 | SW | ARZ | TUC | R PHY | R PHY SW ARZ TUC RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 9 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-TUC-CIN-RPA-5110 | SW | ARZ | TUC | R PHY | R PHY SW ARZ TUC RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-TUC-CIN-RPA-5110 | SW | ARZ | TUC | R PHY | R PHY SW ARZ TUC RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 9 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-TUC-CIN-DPA-5200 | SW | ARZ | TUC | R PHY | R PHY SW ARZ TUC RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-TUC-CIN-DPA-5200 | SW | ARZ | TUC | R PHY | R PHY SW ARZ TUC RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 6 |  | 2020-07-15 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-TUC-CIN-DPA-5200 | SW | ARZ | TUC | R PHY | R PHY SW ARZ TUC RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-SSC-CIN-Nokia2-OCML | SW | ARZ | SSC | R PHY | R PHY SW ARZ SSC RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-30 | Active | EP
RPHY MRTR-New-SSC-CIN-Nokia2-OCML | SW | ARZ | SSC | R PHY | R PHY SW ARZ SSC RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-30 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-SSC-CIN-RPA-5110 | SW | ARZ | SSC | R PHY | R PHY SW ARZ SSC RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 8 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-SSC-CIN-RPA-5110 | SW | ARZ | SSC | R PHY | R PHY SW ARZ SSC RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 8 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-PNL-CIN-RPA-5110 | SW | ARZ | PNL | R PHY | R PHY SW ARZ PNL RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-PNL-CIN-RPA-5110 | SW | ARZ | PNL | R PHY | R PHY SW ARZ PNL RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-PEO-CIN-Nokia-OCML | SW | ARZ | PEO | R PHY | R PHY SW ARZ PEO R PHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 24 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
RPHY MRTR-New-PEO-CIN-Nokia-OCML | SW | ARZ | PEO | R PHY | R PHY SW ARZ PEO R PHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 24 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-PEO-CIN-RPA2-5110 | SW | ARZ | PEO | R PHY | R PHY SW ARZ PEO R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 8 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-PEO-CIN-RPA2-5110 | SW | ARZ | PEO | R PHY | R PHY SW ARZ PEO R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 10 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-PEO-CIN-RPA2-5110 | SW | ARZ | PEO | R PHY | R PHY SW ARZ PEO R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 8 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-PEO-CIN-Nokia2-OCML | SW | ARZ | PEO | R PHY | R PHY SW ARZ PEO R PHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 20 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-PEO-CIN-Nokia2-OCML | SW | ARZ | PEO | R PHY | R PHY SW ARZ PEO R PHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 20 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-PEO-CIN MGMT-2K | SW | ARZ | PEO | R PHY | R PHY SW ARZ PEO R PHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-PEO-CIN MGMT-2K | SW | ARZ | PEO | R PHY | R PHY SW ARZ PEO R PHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-PEO-CIN MGMT-2K | SW | ARZ | PEO | R PHY | R PHY SW ARZ PEO R PHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-NSC-CIN-RPA-5110 | SW | ARZ | NSC | R PHY | R PHY SW ARZ NSC RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-NSC-CIN-RPA-5110 | SW | ARZ | NSC | R PHY | R PHY SW ARZ NSC RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-Growth-MSA-CIN-Nokia-OCML | SW | ARZ | MSA | R PHY | R PHY SW ARZ MSA RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 36 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-Growth-MSA-CIN-Nokia-OCML | SW | ARZ | MSA | R PHY | R PHY SW ARZ MSA RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 36 | 2020-05-15 | 2020-03-15 | 2020-05-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-Growth-MSA-CIN-Nokia-OCML | SW | ARZ | MSA | R PHY | R PHY SW ARZ MSA RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 36 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0601 | Schedule Change | Approved | 2020-05-22 17:32 | 1 Lapalco Kenner and Elmwood were part of 16 7 node action plan 2 These sites are not in 18 14 plan but still continutes to be on the list 3 Deleting those occurences
RPHY MRTR-Growth-MSA-CIN-RPA2-5110 | SW | ARZ | MSA | R PHY | R PHY SW ARZ MSA RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 15 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-Growth-MSA-CIN-RPA2-5110 | SW | ARZ | MSA | R PHY | R PHY SW ARZ MSA RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 25 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-Growth-MSA-CIN-RPA2-5110 | SW | ARZ | MSA | R PHY | R PHY SW ARZ MSA RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 15 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-Growth-MSA-CIN-Nokia2-OCML | SW | ARZ | MSA | R PHY | R PHY SW ARZ MSA RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 50 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-Growth-MSA-CIN-Nokia2-OCML | SW | ARZ | MSA | R PHY | R PHY SW ARZ MSA RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 100 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-Growth-MSA-CIN-Nokia2-OCML | SW | ARZ | MSA | R PHY | R PHY SW ARZ MSA RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 50 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0608 | Schedule Change | Approved | 2020-05-23 14:32 | Metro Routers: POR update Adding Aliante Valley and North Scottsdale Nexus 2K s
RPHY MRTR-New-MSA-CIN MGMT-2K | SW | ARZ | MSA | R PHY | R PHY SW ARZ MSA RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 5 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-MSA-CIN MGMT-2K | SW | ARZ | MSA | R PHY | R PHY SW ARZ MSA RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 10 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-MSA-CIN MGMT-2K | SW | ARZ | MSA | R PHY | R PHY SW ARZ MSA RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 5 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-MCD-CIN-RPA-5110 | SW | ARZ | MCD | R PHY | R PHY SW ARZ MCD RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-MCD-CIN-RPA-5110 | SW | ARZ | MCD | R PHY | R PHY SW ARZ MCD RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-FWL-CIN-RPA-5110 | SW | ARZ | FWL | R PHY | R PHY SW ARZ FWL RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 8 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-FWL-CIN-RPA-5110 | SW | ARZ | FWL | R PHY | R PHY SW ARZ FWL RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 10 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-FWL-CIN-RPA-5110 | SW | ARZ | FWL | R PHY | R PHY SW ARZ FWL RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 8 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-FWL-CIN-Nokia-OCML2 | SW | ARZ | FWL | R PHY | R PHY SW ARZ FWL RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 20 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-FWL-CIN-Nokia-OCML2 | SW | ARZ | FWL | R PHY | R PHY SW ARZ FWL RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 20 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-FWL-CIN MGMT-2K | SW | ARZ | FWL | R PHY | R PHY SW ARZ FWL RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-FWL-CIN MGMT-2K | SW | ARZ | FWL | R PHY | R PHY SW ARZ FWL RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-FWL-CIN MGMT-2K | SW | ARZ | FWL | R PHY | R PHY SW ARZ FWL RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-CHD-CIN-RPA-5110 | SW | ARZ | CHD | R PHY | R PHY SW ARZ CHD RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 8 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-CHD-CIN-RPA-5110 | SW | ARZ | CHD | R PHY | R PHY SW ARZ CHD RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 12 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-CHD-CIN-RPA-5110 | SW | ARZ | CHD | R PHY | R PHY SW ARZ CHD RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 8 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-CHD-CIN-Nokia-OCML2 | SW | ARZ | CHD | R PHY | R PHY SW ARZ CHD RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 40 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-CHD-CIN-Nokia-OCML2 | SW | ARZ | CHD | R PHY | R PHY SW ARZ CHD RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 40 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-CHD-CIN-DPA-5200 | SW | ARZ | CHD | R PHY | R PHY SW ARZ CHD RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-CHD-CIN-DPA-5200 | SW | ARZ | CHD | R PHY | R PHY SW ARZ CHD RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-CHD-CIN MGMT-2K | SW | ARZ | CHD | R PHY | R PHY SW ARZ CHD RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-CHD-CIN MGMT-2K | SW | ARZ | CHD | R PHY | R PHY SW ARZ CHD RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-CHD-CIN MGMT-2K | SW | ARZ | CHD | R PHY | R PHY SW ARZ CHD RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-BUK-CIN-RPA-5110 | SW | ARZ | BUK | R PHY | R PHY SW ARZ BUK RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 5 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-BUK-CIN-RPA-5110 | SW | ARZ | BUK | R PHY | R PHY SW ARZ BUK RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 5 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-BEL-CIN Nokia-OCML | SW | ARZ | BEL | R PHY | R PHY SW ARZ BEL RPHY Metro Augment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 36 | 2020-01-01 | 2020-12-31 | 2020-12-31 | Active | EP
RPHY MRTR-New-BEL-CIN Nokia-OCML | SW | ARZ | BEL | R PHY | R PHY SW ARZ BEL RPHY Metro Augment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 36 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-BEL-CIN Nokia-OCML | SW | ARZ | BEL | R PHY | R PHY SW ARZ BEL RPHY Metro Augment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 36 | 2020-01-01 | 2020-12-31 | 2020-12-31 | Active | Log | Upd | SN-0640 | Schedule Change | Approved | 2020-06-06 12:36 | RPHY Metro : POR CHanges based on Field Inputs
RPHY MRTR-New-BEL-CIN Nokia-OCML2 | SW | ARZ | BEL | R PHY | R PHY SW ARZ BEL RPHY Metro Augment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 20 | 2020-05-15 | 2020-12-31 | 2020-12-31 | Active | EP
RPHY MRTR-New-BEL-CIN Nokia-OCML2 | SW | ARZ | BEL | R PHY | R PHY SW ARZ BEL RPHY Metro Augment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 20 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-BEL-CIN Nokia-OCML2 | SW | ARZ | BEL | R PHY | R PHY SW ARZ BEL RPHY Metro Augment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 20 | 2020-05-15 | 2020-12-31 | 2020-12-31 | Active | Log | Upd | SN-0640 | Schedule Change | Approved | 2020-06-06 12:36 | RPHY Metro : POR CHanges based on Field Inputs
RPHY MRTR-New-BEL-CIN-RPA-5110 | SW | ARZ | BEL | R PHY | R PHY SW ARZ BEL RPHY Metro Augment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 8 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-BEL-CIN-RPA-5110 | SW | ARZ | BEL | R PHY | R PHY SW ARZ BEL RPHY Metro Augment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 10 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-BEL-CIN-RPA-5110 | SW | ARZ | BEL | R PHY | R PHY SW ARZ BEL RPHY Metro Augment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 8 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-BEL-CIN MGMT-2K | SW | ARZ | BEL | R PHY | R PHY SW ARZ BEL RPHY Metro Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-BEL-CIN MGMT-2K | SW | ARZ | BEL | R PHY | R PHY SW ARZ BEL RPHY Metro Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-BEL-CIN MGMT-2K | SW | ARZ | BEL | R PHY | R PHY SW ARZ BEL RPHY Metro Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-OSB-CIN-RPA2-5110 | SW | LAS | OSB | R PHY | R PHY SW LAS OSB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 14 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-OSB-CIN-RPA2-5110 | SW | LAS | OSB | R PHY | R PHY SW LAS OSB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 14 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSB-CIN-NOKIA-OCML | SW | LAS | OSB | R PHY | R PHY SW LAS OSB RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-OSB-CIN-NOKIA-OCML | SW | LAS | OSB | R PHY | R PHY SW LAS OSB RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 70 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Deleted | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSB-CIN-NOKIA-OCML | SW | LAS | OSB | R PHY | R PHY SW LAS OSB RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-OSB-CIN MGMT2-2K | SW | LAS | OSB | R PHY | R PHY SW LAS OSB RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 6 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-OSB-CIN MGMT2-2K | SW | LAS | OSB | R PHY | R PHY SW LAS OSB RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 7 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSB-CIN MGMT2-2K | SW | LAS | OSB | R PHY | R PHY SW LAS OSB RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 6 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-BLU-CIN-Nokia-OCML | SW | LAS | BLU | R PHY | R PHY SW LAS BLU R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-BLU-CIN-Nokia-OCML | SW | LAS | BLU | R PHY | R PHY SW LAS BLU R PHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 24 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Deleted | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-BLU-CIN-Nokia-OCML | SW | LAS | BLU | R PHY | R PHY SW LAS BLU R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-BLU-CIN-RPA2-5110 | SW | LAS | BLU | R PHY | R PHY SW LAS BLU R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 8 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-BLU-CIN-RPA2-5110 | SW | LAS | BLU | R PHY | R PHY SW LAS BLU R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 6 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-BLU-CIN-RPA2-5110 | SW | LAS | BLU | R PHY | R PHY SW LAS BLU R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 8 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-BLU-CIN-Nokia-OCML2 | SW | LAS | BLU | R PHY | R PHY SW LAS BLU R PHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-BLU-CIN-Nokia-OCML2 | SW | LAS | BLU | R PHY | R PHY SW LAS BLU R PHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 30 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Deleted | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-BLU-CIN-Nokia-OCML2 | SW | LAS | BLU | R PHY | R PHY SW LAS BLU R PHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-AVJ-CIN MGMT2-2K | SW | LAS | BLU | R PHY | R PHY SW LAS BLU R PHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-AVJ-CIN MGMT2-2K | SW | LAS | BLU | R PHY | R PHY SW LAS BLU R PHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 3 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-AVJ-CIN MGMT2-2K | SW | LAS | BLU | R PHY | R PHY SW LAS BLU R PHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-FBG-CIN-Nokia-OCML | VA | NVA | FBG | R PHY | R PHY VA NVA FBG RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-FBG-CIN-Nokia-OCML | VA | NVA | FBG | R PHY | R PHY VA NVA FBG RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Deleted | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-FBG-CIN-Nokia-OCML | VA | NVA | FBG | R PHY | R PHY VA NVA FBG RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-LTF-CIN-Nokia-OCML | VA | HRD | LTF | R PHY | R PHY VA HRD LTF RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | EP
RPHY MRTR-New-LTF-CIN-Nokia-OCML | VA | HRD | LTF | R PHY | R PHY VA HRD LTF RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Deleted | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-LTF-CIN-Nokia-OCML | VA | HRD | LTF | R PHY | R PHY VA HRD LTF RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT |  |  |  |  | Deleted | Log | Del | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-VBC-CIN-ATX-OCML | VA | HRD | VBC | R PHY | R PHY VA HRD VBC R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-VBC-CIN-ATX-OCML | VA | HRD | VBC | R PHY | R PHY VA HRD VBC R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-NWP-CIN-RPA-5110 | VA | HRD | NWP | R PHY | R PHY VA HRD NWP RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-08-15 | 2020-08-31 | Active | EP
RPHY MRTR-New-NWP-CIN-RPA-5110 | VA | HRD | NWP | R PHY | R PHY VA HRD NWP RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-NWP-CIN-RPA-5110 | VA | HRD | NWP | R PHY | R PHY VA HRD NWP RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-08-15 | 2020-08-31 | Active | Log | Upd | SN-0741 | Schedule Change | Approved | 2020-07-10 10:12 | RPHY Metro: Updates to POR based on Field inputs
RPHY MRTR-New-NWP-CIN-ATX-OCML | VA | HRD | NWP | R PHY | R PHY VA HRD NWP RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-08-15 | 2020-08-31 | Active | EP
RPHY MRTR-New-NWP-CIN-ATX-OCML | VA | HRD | NWP | R PHY | R PHY VA HRD NWP RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 20 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-NWP-CIN-ATX-OCML | VA | HRD | NWP | R PHY | R PHY VA HRD NWP RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-08-15 | 2020-08-31 | Active | Log | Upd | SN-0741 | Schedule Change | Approved | 2020-07-10 10:12 | RPHY Metro: Updates to POR based on Field inputs
RPHY MRTR-New-NWP-CIN MGMT-2K | VA | HRD | NWP | R PHY | R PHY VA HRD NWP RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-08-15 | 2020-08-31 | Active | EP
RPHY MRTR-New-NWP-CIN MGMT-2K | VA | HRD | NWP | R PHY | R PHY VA HRD NWP RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-NWP-CIN MGMT-2K | VA | HRD | NWP | R PHY | R PHY VA HRD NWP RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-08-15 | 2020-08-31 | Active | Log | Upd | SN-0741 | Schedule Change | Approved | 2020-07-10 10:12 | RPHY Metro: Updates to POR based on Field inputs
RPHY MRTR-New-PRV-CIN-RPA-5110 | NE | RHD | PRV | R PHY | R PHY NE RHD PRV RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-11-01 | 2020-08-31 | Active | EP
RPHY MRTR-New-PRV-CIN-RPA-5110 | NE | RHD | PRV | R PHY | R PHY NE RHD PRV RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-PRV-CIN-RPA-5110 | NE | RHD | PRV | R PHY | R PHY NE RHD PRV RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-PRV-CIN-RPA-5110 | NE | RHD | PRV | R PHY | R PHY NE RHD PRV RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-11-01 | 2020-08-31 | Active | Log | Upd | SN-0842 | Schedule Change | Approved | 2020-08-14 15:08 | Providence Activation date change from 10 16 to 11 1
RPHY MRTR-New-PRV-CIN MGMT-2K | NE | RHD | PRV | R PHY | R PHY NE RHD PRV RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-11-01 | 2020-08-31 | Active | EP
RPHY MRTR-New-PRV-CIN MGMT-2K | NE | RHD | PRV | R PHY | R PHY NE RHD PRV RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-PRV-CIN MGMT-2K | NE | RHD | PRV | R PHY | R PHY NE RHD PRV RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-11-01 | 2020-08-31 | Active | Log | Upd | SN-0842 | Schedule Change | Approved | 2020-08-14 15:08 | Providence Activation date change from 10 16 to 11 1
RPHY MRTR-New-PRV-CIN-ATX-OCML | NE | RHD | PRV | R PHY | R PHY NE RHD PRV RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-09-30 | 2020-10-31 | Active | EP
RPHY MRTR-New-PRV-CIN-ATX-OCML | NE | RHD | PRV | R PHY | R PHY NE RHD PRV RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-PRV-CIN-ATX-OCML | NE | RHD | PRV | R PHY | R PHY NE RHD PRV RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-09-30 | 2020-10-31 | Active | Log | Upd | SN-0640 | Schedule Change | Approved | 2020-06-06 12:36 | RPHY Metro : POR CHanges based on Field Inputs
RPHY MRTR-New-CLH-CIN-RPA2-5110 | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2021-03-31 | 2021-03-31 | Active | EP
RPHY MRTR-New-CLH-CIN-RPA2-5110 | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-07-15 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-CLH-CIN-RPA2-5110 | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2021-03-31 | 2021-03-31 | Active | Log | Upd | SN-0640 | Schedule Change | Approved | 2020-06-06 12:36 | RPHY Metro : POR CHanges based on Field Inputs
RPHY MRTR-New-CLH-CIN-Nokia-OCML2 | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-05-15 | 2020-07-15 | 2020-08-31 | Active | EP
RPHY MRTR-New-CLH-CIN-Nokia-OCML2 | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-05-15 | 2020-07-15 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-CLH-CIN MGMT2-2K | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-15 | 2020-08-31 | Active | EP
RPHY MRTR-New-CLH-CIN MGMT2-2K | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-15 | 2020-08-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSNAP-BLU | SW | LAS | BLU | R PHY | R PHY SW LAS BLU Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
RPHY MRTR-New-OSNAP-BLU | SW | LAS | BLU | R PHY | R PHY SW LAS BLU Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSNAP-ALI | SW | LAS | ALI | R PHY | R PHY SW LAS ALI Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
RPHY MRTR-New-OSNAP-ALI | SW | LAS | ALI | R PHY | R PHY SW LAS ALI Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSNAP-VLY | SW | LAS | VLY | R PHY | R PHY SW LAS VLY Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
RPHY MRTR-New-OSNAP-VLY | SW | LAS | VLY | R PHY | R PHY SW LAS VLY Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSNAP-TEN | SW | LAS | TEN | R PHY | R PHY SW LAS TEN Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
RPHY MRTR-New-OSNAP-TEN | SW | LAS | TEN | R PHY | R PHY SW LAS TEN Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSNAP-HEN | SW | LAS | HEN | R PHY | R PHY SW LAS HEN Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
RPHY MRTR-New-OSNAP-HEN | SW | LAS | HEN | R PHY | R PHY SW LAS HEN Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSNAP-PNL | SW | ARZ | PNL | R PHY | R PHY SW ARZ PNL Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
RPHY MRTR-New-OSNAP-PNL | SW | ARZ | PNL | R PHY | R PHY SW ARZ PNL Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSNAP-TUC | SW | ARZ | TUC | R PHY | R PHY SW ARZ TUC Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
RPHY MRTR-New-OSNAP-TUC | SW | ARZ | TUC | R PHY | R PHY SW ARZ TUC Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSNAP-MSA | SW | ARZ | MSA | R PHY | R PHY SW ARZ MSA Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
RPHY MRTR-New-OSNAP-MSA | SW | ARZ | MSA | R PHY | R PHY SW ARZ MSA Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSNAP-CHD | SW | ARZ | CHD | R PHY | R PHY SW ARZ CHD Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
RPHY MRTR-New-OSNAP-CHD | SW | ARZ | CHD | R PHY | R PHY SW ARZ CHD Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSNAP-BEL | SW | ARZ | BEL | R PHY | R PHY SW ARZ BEL Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
RPHY MRTR-New-OSNAP-BEL | SW | ARZ | BEL | R PHY | R PHY SW ARZ BEL Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSNAP-SSC | SW | ARZ | SSC | R PHY | R PHY SW ARZ SSC Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
RPHY MRTR-New-OSNAP-SSC | SW | ARZ | SSC | R PHY | R PHY SW ARZ SSC Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSNAP-MCD | SW | ARZ | MCD | R PHY | R PHY SW ARZ MCD Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
RPHY MRTR-New-OSNAP-MCD | SW | ARZ | MCD | R PHY | R PHY SW ARZ MCD Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSNAP-PEO | SW | ARZ | PEO | R PHY | R PHY SW ARZ PEO Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
RPHY MRTR-New-OSNAP-PEO | SW | ARZ | PEO | R PHY | R PHY SW ARZ PEO Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSNAP-NSC | SW | ARZ | NSC | R PHY | R PHY SW ARZ NSC Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
RPHY MRTR-New-OSNAP-NSC | SW | ARZ | NSC | R PHY | R PHY SW ARZ NSC Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSNAP-BUK | SW | ARZ | BUK | R PHY | R PHY SW ARZ BUK Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
RPHY MRTR-New-OSNAP-BUK | SW | ARZ | BUK | R PHY | R PHY SW ARZ BUK Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSNAP-FWL | SW | ARZ | FWL | R PHY | R PHY SW ARZ FWL Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
RPHY MRTR-New-OSNAP-FWL | SW | ARZ | FWL | R PHY | R PHY SW ARZ FWL Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSNAP-OSB | SW | LAS | OSB | R PHY | R PHY SW LAS OSB Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
RPHY MRTR-New-OSNAP-OSB | SW | LAS | OSB | R PHY | R PHY SW LAS OSB Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSNAP-ERN | SW | LAS | ERN | R PHY | R PHY SW LAS ERN Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
RPHY MRTR-New-OSNAP-ERN | SW | LAS | ERN | R PHY | R PHY SW LAS ERN Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSNAP-VST | CA | SAN | VST | R PHY | R PHY CA SAN VST Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
RPHY MRTR-New-OSNAP-VST | CA | SAN | VST | R PHY | R PHY CA SAN VST Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSNAP-PWY | CA | SAN | PWY | R PHY | R PHY CA SAN PWY Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
RPHY MRTR-New-OSNAP-PWY | CA | SAN | PWY | R PHY | R PHY CA SAN PWY Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSNAP-OCE | CA | SAN | OCE | R PHY | R PHY CA SAN OCE Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
RPHY MRTR-New-OSNAP-OCE | CA | SAN | OCE | R PHY | R PHY CA SAN OCE Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSNAP-FED | CA | SAN | FED | R PHY | R PHY CA SAN FED Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
RPHY MRTR-New-OSNAP-FED | CA | SAN | FED | R PHY | R PHY CA SAN FED Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSNAP-ESC | CA | SAN | ESC | R PHY | R PHY CA SAN ESC Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
RPHY MRTR-New-OSNAP-ESC | CA | SAN | ESC | R PHY | R PHY CA SAN ESC Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSNAP-ELC | CA | SAN | ELC | R PHY | R PHY CA SAN ELC Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
RPHY MRTR-New-OSNAP-ELC | CA | SAN | ELC | R PHY | R PHY CA SAN ELC Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSNAP-DWN | CA | SAN | DWN | R PHY | R PHY CA SAN DWN Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
RPHY MRTR-New-OSNAP-DWN | CA | SAN | DWN | R PHY | R PHY CA SAN DWN Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSNAP-CHU | CA | SAN | CHU | R PHY | R PHY CA SAN CHU Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
RPHY MRTR-New-OSNAP-CHU | CA | SAN | CHU | R PHY | R PHY CA SAN CHU Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSNAP-RSM | CA | ORG | RSM | R PHY | R PHY CA ORG RSM Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
RPHY MRTR-New-OSNAP-RSM | CA | ORG | RSM | R PHY | R PHY CA ORG RSM Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSNAP-PAV | CA | ORG | PAV | R PHY | R PHY CA ORG PAV Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
RPHY MRTR-New-OSNAP-PAV | CA | ORG | PAV | R PHY | R PHY CA ORG PAV Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSNAP-ORG | CA | ORG | ORG | R PHY | R PHY CA ORG ORG Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
RPHY MRTR-New-OSNAP-ORG | CA | ORG | ORG | R PHY | R PHY CA ORG ORG Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSNAP-IRV | CA | ORG | IRV | R PHY | R PHY CA ORG IRV Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
RPHY MRTR-New-OSNAP-IRV | CA | ORG | IRV | R PHY | R PHY CA ORG IRV Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSNAP-DNP | CA | ORG | DNP | R PHY | R PHY CA ORG DNP Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
RPHY MRTR-New-OSNAP-DNP | CA | ORG | DNP | R PHY | R PHY CA ORG DNP Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-OSNAP-AVJ | CA | ORG | AVJ | R PHY | R PHY CA ORG AVJ Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
RPHY MRTR-New-OSNAP-AVJ | CA | ORG | AVJ | R PHY | R PHY CA ORG AVJ Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
R PHY_CCAP_NWP_CBR8 Line Card_1 | VA | HRD | NWP | R PHY | R PHY VA HRD NWP RPHY CCAP Augment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 3 | 2020-07-15 | 2020-10-15 | 2020-10-15 | Active | EP
R PHY_CCAP_NWP_CBR8 Line Card_1 | VA | HRD | NWP | R PHY | R PHY VA HRD NWP RPHY CCAP Augment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 3 | 2020-07-15 | 2020-10-15 | 2020-10-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_FAY_RPHY CCAP Licenses_1 | CE | NWA | FAY | R PHY | R PHY CE NWA FAY RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_FAY_RPHY CCAP Licenses_1 | CE | NWA | FAY | R PHY | R PHY CE NWA FAY RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_OKC_RPHY CCAP Licenses_1 | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY CCAP Augment POR20 | License | CCAP license | 26 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_OKC_RPHY CCAP Licenses_1 | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY CCAP Augment POR20 | License | CCAP license | 26 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_BAR_RPHY CCAP Licenses_1 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY CCAP Deployment POR20 | License | CCAP license | 78 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_BAR_RPHY CCAP Licenses_1 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY CCAP Deployment POR20 | License | CCAP license | 78 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_OWA_RPHY CCAP Licenses_1 | CE | TUL | OWA | R PHY | R PHY CE TUL OWA RPHY CCAP Augment POR20 | License | CCAP license | 26 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_OWA_RPHY CCAP Licenses_1 | CE | TUL | OWA | R PHY | R PHY CE TUL OWA RPHY CCAP Augment POR20 | License | CCAP license | 26 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_TUL_RPHY CCAP Licenses_1 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY CCAP Deployment POR20 | License | CCAP license | 2165 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_TUL_RPHY CCAP Licenses_1 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY CCAP Deployment POR20 | License | CCAP license | 2165 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_YAL_RPHY CCAP Licenses_1 | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY CCAP Augment POR20 | License | CCAP license | 207 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_YAL_RPHY CCAP Licenses_1 | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY CCAP Augment POR20 | License | CCAP license | 207 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PTH_RPHY CCAP Licenses | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY CCAP Initial Deployment POR19 | License | CCAP license | 207 | 2020-07-15 | 2020-04-21 | 2020-04-21 | Active | EP
R PHY_CCAP_PTH_RPHY CCAP Licenses | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY CCAP Initial Deployment POR19 | License | CCAP license | 207 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PTH_RPHY CCAP Licenses | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY CCAP Initial Deployment POR19 | License | CCAP license | 207 | 2020-07-15 | 2020-11-01 | 2020-11-01 | Active | Log | Upd | SN-0865 | Schedule Change | Approved | 2020-08-21 11:34 | This is to update the RPHY Activation dae for Providence facility
R PHY_CCAP_PTH_RPHY CCAP Licenses | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY CCAP Initial Deployment POR19 | License | CCAP license | 207 | 2020-07-15 | 2020-04-21 | 2020-04-21 | Active | Log | Upd | SN-0958 | Schedule Change | Approved | 2020-09-25 09:32 | This is to update Providence RPHY activation date
R PHY_CCAP_CLR_RPHY CCAP Licenses_1 | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY - CCAP Initial Deployment POR20 | License | CCAP license | 1014 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_CLR_RPHY CCAP Licenses_1 | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY - CCAP Initial Deployment POR20 | License | CCAP license | 1014 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_MCY_RPHY CCAP Licenses_1 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY CCAP Augment POR20 | License | CCAP license | 26 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_MCY_RPHY CCAP Licenses_1 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY CCAP Augment POR20 | License | CCAP license | 26 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_SPC_RPHY CCAP Licenses_1 | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY - CCAP Initial Deployment POR20 | License | CCAP license | 69 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_SPC_RPHY CCAP Licenses_1 | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY - CCAP Initial Deployment POR20 | License | CCAP license | 69 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PNS_RPHY CCAP Licenses_1 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | License | CCAP license | 69 | 2020-07-15 | 2020-09-30 | 2020-09-30 | Active | EP
R PHY_CCAP_PNS_RPHY CCAP Licenses_1 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | License | CCAP license | 69 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PNS_RPHY CCAP Licenses_1 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | License | CCAP license | 69 | 2020-07-15 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0879 | Schedule Change | Approved | 2020-08-28 10:07 | RPHY CCAP POR Update for Roanoke Baton Rouge and Pensacola
R PHY_CCAP_CHS_RPHY CCAP Licenses-1 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY CCAP Augment POR20 | License | CCAP license | 121 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_CHS_RPHY CCAP Licenses-1 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY CCAP Augment POR20 | License | CCAP license | 121 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_NRF_RPHY CCAP Licenses-1 | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY CCAP Augment POR20 | License | CCAP license | 52 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_NRF_RPHY CCAP Licenses-1 | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY CCAP Augment POR20 | License | CCAP license | 52 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PTM_RPHY CCAP Licenses-1 | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY CCAP Augment POR20 | License | CCAP license | 173 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_PTM_RPHY CCAP Licenses-1 | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY CCAP Augment POR20 | License | CCAP license | 173 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PRA_RPHY CCAP Licenses-1 | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY CCAP Augment POR20 | License | CCAP license | 52 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_PRA_RPHY CCAP Licenses-1 | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY CCAP Augment POR20 | License | CCAP license | 52 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_VBC_RPHY CCAP Licenses-1 | VA | HRD | VBC | R PHY | R PHY VA HRD VBC RPHY CCAP Augment POR20 | License | CCAP license | 458 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_VBC_RPHY CCAP Licenses-1 | VA | HRD | VBC | R PHY | R PHY VA HRD VBC RPHY CCAP Augment POR20 | License | CCAP license | 458 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_RON_RPHY CCAP Licenses-1 | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY CCAP Augment POR20 | License | CCAP license | 621 | 2020-07-15 | 2020-10-31 | 2020-10-31 | Active | EP
R PHY_CCAP_RON_RPHY CCAP Licenses-1 | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY CCAP Augment POR20 | License | CCAP license | 621 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_RON_RPHY CCAP Licenses-1 | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY CCAP Augment POR20 | License | CCAP license | 621 | 2020-07-15 | 2020-10-31 | 2020-10-31 | Active | Log | Upd | SN-0879 | Schedule Change | Approved | 2020-08-28 10:07 | RPHY CCAP POR Update for Roanoke Baton Rouge and Pensacola
R PHY_CCAP_NEH_CBR8_1 | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | EP
R PHY_CCAP_NEH_CBR8_1 | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_CLR_CBR8_1 | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | EP
R PHY_CCAP_CLR_CBR8_1 | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_NWP_CBR8_1 | VA | HRD | NWP | R PHY | R PHY VA HRD NWP RPHY CCAP Augment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 2 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | EP
R PHY_CCAP_NWP_CBR8_1 | VA | HRD | NWP | R PHY | R PHY VA HRD NWP RPHY CCAP Augment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 2 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_VBC_CBR8_1 | VA | HRD | VBC | R PHY | R PHY VA HRD VBC RPHY CCAP Augment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | EP
R PHY_CCAP_VBC_CBR8_1 | VA | HRD | VBC | R PHY | R PHY VA HRD VBC RPHY CCAP Augment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_BTR_RPHY CCAP Licenses-2 | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | EP
R PHY_CCAP_BTR_RPHY CCAP Licenses-2 | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_BTR_RPHY CCAP Licenses-2 | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | Upd | SN-0879 | Schedule Change | Approved | 2020-08-28 10:07 | RPHY CCAP POR Update for Roanoke Baton Rouge and Pensacola
R PHY_CCAP_BVL_RPHY CCAP Licenses-1 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY CCAP Augment POR20 | License | CCAP license | 416 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | EP
R PHY_CCAP_BVL_RPHY CCAP Licenses-1 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY CCAP Augment POR20 | License | CCAP license | 416 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_BAR_RPHY CCAP Licenses-2 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY CCAP Deployment POR20 | License | CCAP license | 182 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | EP
R PHY_CCAP_BAR_RPHY CCAP Licenses-2 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY CCAP Deployment POR20 | License | CCAP license | 182 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_CHS_RPHY CCAP Licenses-2 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY CCAP Augment POR20 | License | CCAP license | 78 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | EP
R PHY_CCAP_CHS_RPHY CCAP Licenses-2 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY CCAP Augment POR20 | License | CCAP license | 78 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_CLH_RPHY CCAP Licenses-1 | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY CCAP Augment POR20 | License | CCAP license | 52 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | EP
R PHY_CCAP_CLH_RPHY CCAP Licenses-1 | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY CCAP Augment POR20 | License | CCAP license | 52 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_ELK_RPHY CCAP Licenses-1 | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY CCAP Augment POR20 | License | CCAP license | 414 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | EP
R PHY_CCAP_ELK_RPHY CCAP Licenses-1 | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY CCAP Augment POR20 | License | CCAP license | 414 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_GAR_RPHY CCAP Licenses-1 | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY - CCAP Initial Deployment POR20 | License | CCAP license | 26 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | EP
R PHY_CCAP_GAR_RPHY CCAP Licenses-1 | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY - CCAP Initial Deployment POR20 | License | CCAP license | 26 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_LFY_RPHY CCAP Licenses-1 | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY CCAP Augment POR20 | License | CCAP license | 138 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | EP
R PHY_CCAP_LFY_RPHY CCAP Licenses-1 | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY CCAP Augment POR20 | License | CCAP license | 138 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_NRF_RPHY CCAP Licenses-2 | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY CCAP Augment POR20 | License | CCAP license | 416 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | EP
R PHY_CCAP_NRF_RPHY CCAP Licenses-2 | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY CCAP Augment POR20 | License | CCAP license | 416 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_OCN_RPHY CCAP Licenses-1 | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY CCAP Augment POR20 | License | CCAP license | 78 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | EP
R PHY_CCAP_OCN_RPHY CCAP Licenses-1 | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY CCAP Augment POR20 | License | CCAP license | 78 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_OKC_RPHY CCAP Licenses-1 | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY CCAP Augment POR20 | License | CCAP license | 286 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | EP
R PHY_CCAP_OKC_RPHY CCAP Licenses-1 | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY CCAP Augment POR20 | License | CCAP license | 286 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_OWA_RPHY CCAP Licenses-1 | CE | TUL | OWA | R PHY | R PHY CE TUL OWA RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | EP
R PHY_CCAP_OWA_RPHY CCAP Licenses-1 | CE | TUL | OWA | R PHY | R PHY CE TUL OWA RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PTH_RPHY CCAP Licenses-1 | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY CCAP Augment POR20 | License | CCAP license | 345 | 2020-10-15 | 2020-04-21 | 2020-04-21 | Active | EP
R PHY_CCAP_PTH_RPHY CCAP Licenses-1 | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY CCAP Augment POR20 | License | CCAP license | 345 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PTH_RPHY CCAP Licenses-1 | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY CCAP Augment POR20 | License | CCAP license | 345 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | Upd | SN-0865 | Schedule Change | Approved | 2020-08-21 11:34 | This is to update the RPHY Activation dae for Providence facility
R PHY_CCAP_PTH_RPHY CCAP Licenses-1 | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY CCAP Augment POR20 | License | CCAP license | 345 | 2020-10-15 | 2020-04-21 | 2020-04-21 | Active | Log | Upd | SN-0958 | Schedule Change | Approved | 2020-09-25 09:32 | This is to update Providence RPHY activation date
R PHY_CCAP_PTM_RPHY CCAP Licenses-2 | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY CCAP Augment POR20 | License | CCAP license | 52 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | EP
R PHY_CCAP_PTM_RPHY CCAP Licenses-2 | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY CCAP Augment POR20 | License | CCAP license | 52 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PRA_RPHY CCAP Licenses-2 | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY CCAP Augment POR20 | License | CCAP license | 78 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | EP
R PHY_CCAP_PRA_RPHY CCAP Licenses-2 | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY CCAP Augment POR20 | License | CCAP license | 78 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_QNC_RPHY CCAP Licenses-1 | CE | TUL | QNC | R PHY | R PHY CE TUL QNC RPHY CCAP Augment POR20 | License | CCAP license | 242 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | EP
R PHY_CCAP_QNC_RPHY CCAP Licenses-1 | CE | TUL | QNC | R PHY | R PHY CE TUL QNC RPHY CCAP Augment POR20 | License | CCAP license | 242 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_RON_RPHY CCAP Licenses-2 | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY CCAP Augment POR20 | License | CCAP license | 552 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | EP
R PHY_CCAP_RON_RPHY CCAP Licenses-2 | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY CCAP Augment POR20 | License | CCAP license | 552 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_SOU_RPHY CCAP Licenses-1 | CE | OMA | SOU | R PHY | R PHY CE OMA SOU RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | EP
R PHY_CCAP_SOU_RPHY CCAP Licenses-1 | CE | OMA | SOU | R PHY | R PHY CE OMA SOU RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_TUL_RPHY CCAP Licenses-1 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL R PHY CCAP Deployment POR20 | License | CCAP license | 2319 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | EP
R PHY_CCAP_TUL_RPHY CCAP Licenses-1 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL R PHY CCAP Deployment POR20 | License | CCAP license | 2319 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_WLK_RPHY CCAP Licenses-1 | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY CCAP Augment POR20 | License | CCAP license | 26 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | EP
R PHY_CCAP_WLK_RPHY CCAP Licenses-1 | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY CCAP Augment POR20 | License | CCAP license | 26 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_YAL_RPHY CCAP Licenses-1 | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY CCAP Augment POR20 | License | CCAP license | 190 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | EP
R PHY_CCAP_YAL_RPHY CCAP Licenses-1 | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY CCAP Augment POR20 | License | CCAP license | 190 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_BTR_RPHY CCAP Licenses_1 | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-07-15 | 2020-09-30 | 2020-09-30 | Active | EP
R PHY_CCAP_BTR_RPHY CCAP Licenses_1 | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_BTR_RPHY CCAP Licenses_1 | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-07-15 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0879 | Schedule Change | Approved | 2020-08-28 10:07 | RPHY CCAP POR Update for Roanoke Baton Rouge and Pensacola
R PHY_CCAP_PRV_CBR8_1 | NE | RHD | PRV | R PHY | R PHY NE RHD PRV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-04-28 | 2020-11-01 | 2020-11-01 | Active | EP
R PHY_CCAP_PRV_CBR8_1 | NE | RHD | PRV | R PHY | R PHY NE RHD PRV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-04-28 | 2020-07-28 | 2020-07-28 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PRV_CBR8_1 | NE | RHD | PRV | R PHY | R PHY NE RHD PRV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-04-28 | 2020-11-01 | 2020-11-01 | Active | Log | Upd | SN-0958 | Schedule Change | Approved | 2020-09-25 09:32 | This is to update Providence RPHY activation date
R PHY_CCAP_BVL_RPHY CCAP Licenses_Q2_18.17 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY CCAP Augment POR20 | License | CCAP license | 138 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_BAR_RPHY CCAP Licenses_Q2_18.18 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY CCAP Deployment POR20 | License | CCAP license | 207 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_CHS_RPHY CCAP Licenses_Q2_18.21 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY CCAP Augment POR20 | License | CCAP license | 276 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_ELK_RPHY CCAP Licenses_Q2_18.27 | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_LFY_RPHY CCAP Licenses_Q2_18.33 | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY CCAP Augment POR20 | License | CCAP license | 207 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_MCY_RPHY CCAP Licenses_Q2_18.35 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY CCAP Augment POR20 | License | CCAP license | 828 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_NWP_RPHY CCAP Licenses_Q2_18.36 | VA | HRD | NWP | R PHY | R PHY VA HRD NWP RPHY CCAP Augment POR20 | License | CCAP license | 2208 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_NRF_RPHY CCAP Licenses_Q2_18.37 | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY CCAP Augment POR20 | License | CCAP license | 483 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_OCN_RPHY CCAP Licenses_Q2_18.39 | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY CCAP Augment POR20 | License | CCAP license | 138 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_PTM_RPHY CCAP Licenses_Q2_18.44 | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_PRA_RPHY CCAP Licenses_Q2_18.46 | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_VBC_RPHY CCAP Licenses_Q2_18.52 | VA | HRD | VBC | R PHY | R PHY VA HRD VBC RPHY CCAP Augment POR20 | License | CCAP license | 414 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_VST_RPHY CCAP Licenses_Q2_18.53 | CA | SAN | VST | R PHY | R PHY CA SAN VST R PHY CCAP Deployment POR20 | License | CCAP license | 552 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_WLK_RPHY CCAP Licenses_Q2_18.54 | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_YAL_RPHY CCAP Licenses_Q2_18.55 | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_BVL_RPHY CCAP Licenses_Q2_18.14 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY CCAP Augment POR20 | License | CCAP license | 138 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_BVL_RPHY CCAP Licenses_Q2_18.14 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY CCAP Augment POR20 | License | CCAP license | 138 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_BAR_RPHY CCAP Licenses_Q2_18.14 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY CCAP Deployment POR20 | License | CCAP license | 207 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_BAR_RPHY CCAP Licenses_Q2_18.14 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY CCAP Deployment POR20 | License | CCAP license | 207 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_CHS_RPHY CCAP Licenses_Q2_18.14 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY CCAP Augment POR20 | License | CCAP license | 276 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_CHS_RPHY CCAP Licenses_Q2_18.14 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY CCAP Augment POR20 | License | CCAP license | 276 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_ELK_RPHY CCAP Licenses_Q2_18.14 | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_ELK_RPHY CCAP Licenses_Q2_18.14 | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_LFY_RPHY CCAP Licenses_Q2_18.14 | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY CCAP Augment POR20 | License | CCAP license | 207 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_LFY_RPHY CCAP Licenses_Q2_18.14 | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY CCAP Augment POR20 | License | CCAP license | 207 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_MCY_RPHY CCAP Licenses_Q2_18.14 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY CCAP Augment POR20 | License | CCAP license | 828 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_MCY_RPHY CCAP Licenses_Q2_18.14 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY CCAP Augment POR20 | License | CCAP license | 828 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_NWP_RPHY CCAP Licenses_Q2_18.14 | VA | HRD | NWP | R PHY | R PHY VA HRD NWP RPHY CCAP Augment POR20 | License | CCAP license | 2208 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_NWP_RPHY CCAP Licenses_Q2_18.14 | VA | HRD | NWP | R PHY | R PHY VA HRD NWP RPHY CCAP Augment POR20 | License | CCAP license | 2208 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_NRF_RPHY CCAP Licenses_Q2_18.14 | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY CCAP Augment POR20 | License | CCAP license | 483 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_NRF_RPHY CCAP Licenses_Q2_18.14 | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY CCAP Augment POR20 | License | CCAP license | 483 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_OCN_RPHY CCAP Licenses_Q2_18.14 | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY CCAP Augment POR20 | License | CCAP license | 138 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_OCN_RPHY CCAP Licenses_Q2_18.14 | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY CCAP Augment POR20 | License | CCAP license | 138 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PTM_RPHY CCAP Licenses_Q2_18.14 | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_PTM_RPHY CCAP Licenses_Q2_18.14 | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PRA_RPHY CCAP Licenses_Q2_18.14 | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_PRA_RPHY CCAP Licenses_Q2_18.14 | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_VBC_RPHY CCAP Licenses_Q2_18.14 | VA | HRD | VBC | R PHY | R PHY VA HRD VBC RPHY CCAP Augment POR20 | License | CCAP license | 414 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_VBC_RPHY CCAP Licenses_Q2_18.14 | VA | HRD | VBC | R PHY | R PHY VA HRD VBC RPHY CCAP Augment POR20 | License | CCAP license | 414 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_VST_RPHY CCAP Licenses_Q2_18.14 | CA | SAN | VST | R PHY | R PHY CA SAN VST R PHY CCAP Deployment POR20 | License | CCAP license | 552 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_VST_RPHY CCAP Licenses_Q2_18.14 | CA | SAN | VST | R PHY | R PHY CA SAN VST R PHY CCAP Deployment POR20 | License | CCAP license | 552 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_WLK_RPHY CCAP Licenses_Q2_18.14 | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_WLK_RPHY CCAP Licenses_Q2_18.14 | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_YAL_RPHY CCAP Licenses_Q2_18.14 | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_YAL_RPHY CCAP Licenses_Q2_18.14 | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_ABV_RPHY CCAP Licenses_Q2 NC Video | SE | LFY | ABV | R PHY | R PHY SE LFY ABV RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-10-31 | 2020-10-31 | Active | EP
R PHY_CCAP_ABV_RPHY CCAP Licenses_Q2 NC Video | SE | LFY | ABV | R PHY | R PHY SE LFY ABV RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_ABV_RPHY CCAP Licenses_Q2 NC Video | SE | LFY | ABV | R PHY | R PHY SE LFY ABV RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_ABV_RPHY CCAP Licenses_Q2 NC Video | SE | LFY | ABV | R PHY | R PHY SE LFY ABV RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-10-31 | 2020-10-31 | Active | Log | Upd | SN-0899 | Schedule Change | Approved | 2020-09-11 09:34 | RPHY CCAP actiation date updates for Fort Smith and Abbeville sites Material delivery date update for CLV FTS RSM BLU and HEN facilites
R PHY_CCAP_BTR_RPHY CCAP Licenses_Q2 NC Video | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-09-30 | 2020-09-30 | Active | EP
R PHY_CCAP_BTR_RPHY CCAP Licenses_Q2 NC Video | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_BTR_RPHY CCAP Licenses_Q2 NC Video | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-08-31 | 2020-08-31 | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_BTR_RPHY CCAP Licenses_Q2 NC Video | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0879 | Schedule Change | Approved | 2020-08-28 10:07 | RPHY CCAP POR Update for Roanoke Baton Rouge and Pensacola
R PHY_CCAP_BVL_RPHY CCAP Licenses_Q2 NC Video | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_BVL_RPHY CCAP Licenses_Q2 NC Video | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_BAR_RPHY CCAP Licenses_Q2 NC Video | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY CCAP Deployment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_BAR_RPHY CCAP Licenses_Q2 NC Video | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY CCAP Deployment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_CHS_RPHY CCAP Licenses_Q2 NC Video | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_CHS_RPHY CCAP Licenses_Q2 NC Video | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_CLH_RPHY CCAP Licenses_Q2 NC Video | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_CLH_RPHY CCAP Licenses_Q2 NC Video | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_ELK_RPHY CCAP Licenses_Q2 NC Video | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_ELK_RPHY CCAP Licenses_Q2 NC Video | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_FAY_RPHY CCAP Licenses_Q2 NC Video | CE | NWA | FAY | R PHY | R PHY CE NWA FAY RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_FAY_RPHY CCAP Licenses_Q2 NC Video | CE | NWA | FAY | R PHY | R PHY CE NWA FAY RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_LFY_RPHY CCAP Licenses_Q2 NC Video | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_LFY_RPHY CCAP Licenses_Q2 NC Video | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_LUL_RPHY CCAP Licenses_Q2 NC Video | SE | NOR | LUL | R PHY | R PHY SE NOR LUL RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-10-31 | 2020-10-31 | Active | EP
R PHY_CCAP_LUL_RPHY CCAP Licenses_Q2 NC Video | SE | NOR | LUL | R PHY | R PHY SE NOR LUL RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_LUL_RPHY CCAP Licenses_Q2 NC Video | SE | NOR | LUL | R PHY | R PHY SE NOR LUL RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-10-31 | 2020-10-31 | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_CLR_RPHY CCAP Licenses_Q2 NC Video | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY - CCAP Initial Deployment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-08-31 | 2020-07-31 | Active | EP
R PHY_CCAP_CLR_RPHY CCAP Licenses_Q2 NC Video | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY - CCAP Initial Deployment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_CLR_RPHY CCAP Licenses_Q2 NC Video | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY - CCAP Initial Deployment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-07-31 | 2020-07-31 | Active | Log | Upd | SN-0742 | Schedule Change | Approved | 2020-07-10 10:13 | RPHY CCAP POR Update for Warner Robins and South Pecue facilites
R PHY_CCAP_CLR_RPHY CCAP Licenses_Q2 NC Video | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY - CCAP Initial Deployment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-08-31 | 2020-07-31 | Active | Log | Upd | SN-0811 | Schedule Change | Approved | 2020-08-07 09:40 | This is to update RPHY CCAP POR for CLR WRB SAB and PNS sites
R PHY_CCAP_MCY_RPHY CCAP Licenses_Q2 NC Video | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_MCY_RPHY CCAP Licenses_Q2 NC Video | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_NWP_RPHY CCAP Licenses_Q2 NC Video | VA | HRD | NWP | R PHY | R PHY VA HRD NWP RPHY CCAP Augment POR20 | License | CCAP license | 2040 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_NWP_RPHY CCAP Licenses_Q2 NC Video | VA | HRD | NWP | R PHY | R PHY VA HRD NWP RPHY CCAP Augment POR20 | License | CCAP license | 2040 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_NRF_RPHY CCAP Licenses_Q2 NC Video | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_NRF_RPHY CCAP Licenses_Q2 NC Video | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_OCN_RPHY CCAP Licenses_Q2 NC Video | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_OCN_RPHY CCAP Licenses_Q2 NC Video | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_OKC_RPHY CCAP Licenses_Q2 NC Video | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_OKC_RPHY CCAP Licenses_Q2 NC Video | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_OWA_RPHY CCAP Licenses_Q2 NC Video | CE | TUL | OWA | R PHY | R PHY CE TUL OWA RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_OWA_RPHY CCAP Licenses_Q2 NC Video | CE | TUL | OWA | R PHY | R PHY CE TUL OWA RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_SPC_RPHY CCAP Licenses_Q2 NC Video | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY - CCAP Initial Deployment POR20 | License | CCAP license | 136 | 2020-03-30 | 2020-07-31 | 2020-07-31 | Active | EP
R PHY_CCAP_SPC_RPHY CCAP Licenses_Q2 NC Video | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY - CCAP Initial Deployment POR20 | License | CCAP license | 136 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_SPC_RPHY CCAP Licenses_Q2 NC Video | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY - CCAP Initial Deployment POR20 | License | CCAP license | 136 | 2020-03-30 | 2020-07-31 | 2020-07-31 | Active | Log | Upd | SN-0742 | Schedule Change | Approved | 2020-07-10 10:13 | RPHY CCAP POR Update for Warner Robins and South Pecue facilites
R PHY_CCAP_PNS_RPHY CCAP Licenses_Q2 NC Video | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | License | CCAP license | 136 | 2020-03-30 | 2020-09-30 | 2020-09-30 | Active | EP
R PHY_CCAP_PNS_RPHY CCAP Licenses_Q2 NC Video | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | License | CCAP license | 136 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PNS_RPHY CCAP Licenses_Q2 NC Video | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | License | CCAP license | 136 | 2020-03-30 | 2020-07-31 | 2020-07-31 | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_PNS_RPHY CCAP Licenses_Q2 NC Video | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | License | CCAP license | 136 | 2020-03-30 | 2020-08-31 | 2020-08-31 | Active | Log | Upd | SN-0811 | Schedule Change | Approved | 2020-08-07 09:40 | This is to update RPHY CCAP POR for CLR WRB SAB and PNS sites
R PHY_CCAP_PNS_RPHY CCAP Licenses_Q2 NC Video | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | License | CCAP license | 136 | 2020-03-30 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0879 | Schedule Change | Approved | 2020-08-28 10:07 | RPHY CCAP POR Update for Roanoke Baton Rouge and Pensacola
R PHY_CCAP_PTH_RPHY CCAP Licenses_Q2 NC Video | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-04-21 | 2020-04-21 | Active | EP
R PHY_CCAP_PTH_RPHY CCAP Licenses_Q2 NC Video | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PTH_RPHY CCAP Licenses_Q2 NC Video | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-11-01 | 2020-11-01 | Active | Log | Upd | SN-0865 | Schedule Change | Approved | 2020-08-21 11:34 | This is to update the RPHY Activation dae for Providence facility
R PHY_CCAP_PTH_RPHY CCAP Licenses_Q2 NC Video | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-04-21 | 2020-04-21 | Active | Log | Upd | SN-0958 | Schedule Change | Approved | 2020-09-25 09:32 | This is to update Providence RPHY activation date
R PHY_CCAP_PTM_RPHY CCAP Licenses_Q2 NC Video | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_PTM_RPHY CCAP Licenses_Q2 NC Video | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PRA_RPHY CCAP Licenses_Q2 NC Video | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_PRA_RPHY CCAP Licenses_Q2 NC Video | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_QNC_RPHY CCAP Licenses_Q2 NC Video | CE | TUL | QNC | R PHY | R PHY CE TUL QNC RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_QNC_RPHY CCAP Licenses_Q2 NC Video | CE | TUL | QNC | R PHY | R PHY CE TUL QNC RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_RON_RPHY CCAP Licenses_Q2 NC Video | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-10-31 | 2020-10-31 | Active | EP
R PHY_CCAP_RON_RPHY CCAP Licenses_Q2 NC Video | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_RON_RPHY CCAP Licenses_Q2 NC Video | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-10-31 | 2020-10-31 | Active | Log | Upd | SN-0879 | Schedule Change | Approved | 2020-08-28 10:07 | RPHY CCAP POR Update for Roanoke Baton Rouge and Pensacola
R PHY_CCAP_SOU_RPHY CCAP Licenses_Q2 NC Video | CE | OMA | SOU | R PHY | R PHY CE OMA SOU RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_SOU_RPHY CCAP Licenses_Q2 NC Video | CE | OMA | SOU | R PHY | R PHY CE OMA SOU RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_TUL_RPHY CCAP Licenses_Q2 NC Video | CE | TUL | TUL | R PHY | R PHY CE TUL TUL R PHY CCAP Deployment POR20 | License | CCAP license | 1496 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_TUL_RPHY CCAP Licenses_Q2 NC Video | CE | TUL | TUL | R PHY | R PHY CE TUL TUL R PHY CCAP Deployment POR20 | License | CCAP license | 1496 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_VBC_RPHY CCAP Licenses_Q2 NC Video | VA | HRD | VBC | R PHY | R PHY VA HRD VBC RPHY CCAP Augment POR20 | License | CCAP license | 544 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_VBC_RPHY CCAP Licenses_Q2 NC Video | VA | HRD | VBC | R PHY | R PHY VA HRD VBC RPHY CCAP Augment POR20 | License | CCAP license | 544 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_VST_RPHY CCAP Licenses_Q2 NC Video | CA | SAN | VST | R PHY | R PHY CA SAN VST R PHY CCAP Deployment POR20 | License | CCAP license | 476 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_VST_RPHY CCAP Licenses_Q2 NC Video | CA | SAN | VST | R PHY | R PHY CA SAN VST R PHY CCAP Deployment POR20 | License | CCAP license | 476 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_WLK_RPHY CCAP Licenses_Q2 NC Video | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_WLK_RPHY CCAP Licenses_Q2 NC Video | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_YAL_RPHY CCAP Licenses_Q2 NC Video | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_YAL_RPHY CCAP Licenses_Q2 NC Video | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
RPHY MRTR-New-OCE-CIN-RPA-5110 | CA | SAN | OCE | R PHY | R PHY CA SAN OCE RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 6 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-New-OCE-CIN-RPA-5110 | CA | SAN | OCE | R PHY | R PHY CA SAN OCE RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 6 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-CLR-CIN-RPA2-5110 | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 8 | 2020-05-15 | 2020-08-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-CLR-CIN-RPA2-5110 | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 8 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-CLR-CIN-RPA2-5110 | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 8 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0741 | Schedule Change | Approved | 2020-07-10 10:12 | RPHY Metro: Updates to POR based on Field inputs
RPHY MRTR-New-CLR-CIN-RPA2-5110 | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 8 | 2020-05-15 | 2020-08-31 | 2020-08-31 | Active | Log | Upd | SN-0810 | Schedule Change | Approved | 2020-08-07 09:41 | 1 Warner Robins and Clear View needs to be moved to August as Alrm Testing was not completed
RPHY MRTR-New-OCE-CIN MGMT-2K | CA | SAN | OCE | R PHY | R PHY CA SAN OCE RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-New-OCE-CIN MGMT-2K | CA | SAN | OCE | R PHY | R PHY CA SAN OCE RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-WRB-CIN-ATX-OCML | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-04-05 | 2020-09-30 | 2020-07-31 | Active | EP
RPHY MRTR-New-WRB-CIN-ATX-OCML | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 50 | 2020-04-05 | 2020-07-31 | 2020-07-31 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-WRB-CIN-ATX-OCML | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-04-05 | 2020-07-31 | 2020-07-31 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-WRB-CIN-ATX-OCML | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-04-05 | 2020-08-31 | 2020-07-31 | Active | Log | Upd | SN-0741 | Schedule Change | Approved | 2020-07-10 10:12 | RPHY Metro: Updates to POR based on Field inputs
RPHY MRTR-New-WRB-CIN-ATX-OCML | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-04-05 | 2020-09-30 | 2020-07-31 | Active | Log | Upd | SN-0810 | Schedule Change | Approved | 2020-08-07 09:41 | 1 Warner Robins and Clear View needs to be moved to August as Alrm Testing was not completed
RPHY MRTR-New-CHS-CIN-ATX-OCML | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY Metro Initial Deployment POR19 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-New-CHS-CIN-ATX-OCML | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-CHS-CIN-ATX-OCML | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY Metro Initial Deployment POR19 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-NRF-CIN-ATX-OCML | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-NRF-CIN-ATX-OCML | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-OCN-CIN-ATX-OCML | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-04-30 |  | Active | EP
RPHY MRTR-New-OCN-CIN-ATX-OCML | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-04-30 |  | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-PRA-CIN-ATX-OCML | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-05-31 |  | Active | EP
RPHY MRTR-New-PRA-CIN-ATX-OCML | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-05-31 |  | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-PTM-CIN-ATX-OCML | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-05-31 |  | Active | EP
RPHY MRTR-New-PTM-CIN-ATX-OCML | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-05-31 |  | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-RON-CIN-ATX-OCML | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-06-30 |  | Active | EP
RPHY MRTR-New-RON-CIN-ATX-OCML | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-06-30 |  | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-BTR-CIN-ATX-OCML | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-09-30 |  | Active | EP
RPHY MRTR-New-BTR-CIN-ATX-OCML | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-08-31 |  | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-BTR-CIN-ATX-OCML | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-09-30 |  | Active | Log | Upd | SN-0881 | Schedule Change | Approved | 2020-08-28 10:07 | 1 Moving Pensacola Activation Date from August to September because of Firewall issues 2 Moving BTR dates from August to September because of Resource constraints in with BTR NF team
RPHY MRTR-New-ABV-CIN-ATX-OCML | SE | LFY | ABV | R PHY | R PHY SE LFY ABV RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-10-31 | 2020-09-30 | Active | EP
RPHY MRTR-New-ABV-CIN-ATX-OCML | SE | LFY | ABV | R PHY | R PHY SE LFY ABV RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-11-30 |  | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-ABV-CIN-ATX-OCML | SE | LFY | ABV | R PHY | R PHY SE LFY ABV RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-ABV-CIN-ATX-OCML | SE | LFY | ABV | R PHY | R PHY SE LFY ABV RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-10-31 | 2020-09-30 | Active | Log | Upd | SN-0900 | Schedule Change | Approved | 2020-09-11 09:33 | RPHY Metro: POR Update to activation date for 2 sites Abbeville sue to resource constraints and the site was low priority Adjusting date for Forst SMith as well
RPHY MRTR-New-LFY-CIN-ATX-OCML | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-05-31 |  | Active | EP
RPHY MRTR-New-LFY-CIN-ATX-OCML | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-05-31 |  | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-LUL-CIN-ATX-OCML | SE | NOR | LUL | R PHY | R PHY SE NOR LUL RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-10-31 | 2020-10-31 | Active | EP
RPHY MRTR-New-LUL-CIN-ATX-OCML | SE | NOR | LUL | R PHY | R PHY SE NOR LUL RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-11-30 |  | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-LUL-CIN-ATX-OCML | SE | NOR | LUL | R PHY | R PHY SE NOR LUL RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-10-31 | 2020-10-31 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-MCY-CIN-ATX-OCML | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-MCY-CIN-ATX-OCML | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-PTH-CIN-ATX-OCML | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-PTH-CIN-ATX-OCML | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-BVL-CIN-Nokia2-OCML | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-BVL-CIN-Nokia2-OCML | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-FAY-CIN-Nokia2-OCML | CE | NWA | FAY | R PHY | R PHY CE NWA FAY RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-FAY-CIN-Nokia2-OCML | CE | NWA | FAY | R PHY | R PHY CE NWA FAY RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-CLH-CIN-Nokia2-OCML | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-CLH-CIN-Nokia2-OCML | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-OKC-CIN-Nokia2-OCML | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-OKC-CIN-Nokia2-OCML | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-WLK-CIN-Nokia2-OCML | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-WLK-CIN-Nokia2-OCML | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-ELK-CIN-Nokia2-OCML | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-ELK-CIN-Nokia2-OCML | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-SOU-CIN-Nokia2-OCML | CE | OMA | SOU | R PHY | R PHY CE OMA SOU RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-SOU-CIN-Nokia2-OCML | CE | OMA | SOU | R PHY | R PHY CE OMA SOU RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-BAR-CIN-Nokia2-OCML | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-BAR-CIN-Nokia2-OCML | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-OWA-CIN-Nokia2-OCML | CE | TUL | OWA | R PHY | R PHY CE TUL OWA RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-OWA-CIN-Nokia2-OCML | CE | TUL | OWA | R PHY | R PHY CE TUL OWA RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-QNC-CIN-Nokia2-OCML | CE | TUL | QNC | R PHY | R PHY CE TUL QNC RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-QNC-CIN-Nokia2-OCML | CE | TUL | QNC | R PHY | R PHY CE TUL QNC RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-TUL-CIN-Nokia2-OCML | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-TUL-CIN-Nokia2-OCML | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-YAL-CIN-Nokia2-OCML | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-YAL-CIN-Nokia2-OCML | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
R PHY_CCAP_CLV_CBR8_3 | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 4 | 2020-10-09 | 2020-12-31 |  | Active | EP
R PHY_CCAP_CLV_CBR8_3 | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 3 | 2020-07-15 | 2020-10-15 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_CLV_CBR8_3 | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 4 | 2020-07-15 | 2020-10-15 |  | Active | Log | Upd | SN-0637 | Schedule Change | Approved | 2020-06-05 14:50 | RPHY CCAP POR Update
R PHY_CCAP_CLV_CBR8_3 | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 4 | 2020-07-15 | 2020-12-31 |  | Active | Log | Upd | SN-0843 | Schedule Change | Approved | 2020-08-15 10:44 | This is to update Activation date for Cleveland
R PHY_CCAP_CLV_CBR8_3 | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 4 | 2020-09-25 | 2020-12-31 |  | Active | Log | Upd | SN-0899 | Schedule Change | Approved | 2020-09-11 09:34 | RPHY CCAP actiation date updates for Fort Smith and Abbeville sites Material delivery date update for CLV FTS RSM BLU and HEN facilites
R PHY_CCAP_CLV_CBR8_3 | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 4 | 2020-10-09 | 2020-12-31 |  | Active | Log | Upd | SN-0959 | Schedule Change | Approved | 2020-09-25 14:13 | 4 X CBR8s planned for Clevelandand in September are delayed into Octobe One CBR8 for Bluediamond is scheduled to arrive at the month end and has a risk of gettting the order closed and the amount hit the books before month end Total amount at risk is 888K
RPHY MRTR-New-ERN-CIN-MGMT-2K | SW | LAS | ERN | R PHY | R PHY SW LAS ERN RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 3 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-ERN-CIN-MGMT-2K | SW | LAS | ERN | R PHY | R PHY SW LAS ERN RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 3 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-BLU-CIN-ATX-OCML2 | SW | LAS | BLU | R PHY | R PHY SW LAS BLU R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 40 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-BLU-CIN-ATX-OCML2 | SW | LAS | BLU | R PHY | R PHY SW LAS BLU R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 40 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-OSB-CIN-ATX-OCML | SW | LAS | OSB | R PHY | R PHY SW LAS OSB RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 60 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-OSB-CIN-ATX-OCML | SW | LAS | OSB | R PHY | R PHY SW LAS OSB RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 60 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
R PHY_CCAP_PRV_Boundary Clock_2 | NE | RHD | PRV | R PHY | R PHY NE RHD PRV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-05-30 | 2020-11-01 |  | Active | EP
R PHY_CCAP_PRV_Boundary Clock_2 | NE | RHD | PRV | R PHY | R PHY NE RHD PRV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-05-30 | 2020-07-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_PRV_Boundary Clock_2 | NE | RHD | PRV | R PHY | R PHY NE RHD PRV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-05-30 | 2020-11-01 |  | Active | Log | Upd | SN-0958 | Schedule Change | Approved | 2020-09-25 09:32 | This is to update Providence RPHY activation date
R PHY_CCAP_BVL_OTDR_1 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_BVL_OTDR_1 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_BAR_OTDR_1 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_BAR_OTDR_1 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_CHS_OTDR_1 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_CHS_OTDR_1 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_ELK_OTDR_1 | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_ELK_OTDR_1 | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_FAY_OTDR_1 | CE | NWA | FAY | R PHY | R PHY CE NWA FAY RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_FAY_OTDR_1 | CE | NWA | FAY | R PHY | R PHY CE NWA FAY RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_FTS_OTDR_1 | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-09-30 |  | Active | EP
R PHY_CCAP_FTS_OTDR_1 | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_FTS_OTDR_1 | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-09-30 |  | Active | Log | Upd | SN-0613 | Schedule Change | Approved | 2020-05-29 16:19 | RPHY CCAP POR Update
R PHY_CCAP_FTS_OTDR_1 | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-09-30 |  | Active | Log | Upd | SN-0899 | Schedule Change | Approved | 2020-09-11 09:34 | RPHY CCAP actiation date updates for Fort Smith and Abbeville sites Material delivery date update for CLV FTS RSM BLU and HEN facilites
R PHY_CCAP_FBG_OTDR_1 | VA | NVA | FBG | R PHY | R PHY VA NVA FBG RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_FBG_OTDR_1 | VA | NVA | FBG | R PHY | R PHY VA NVA FBG RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_LFY_OTDR_1 | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_LFY_OTDR_1 | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_LTF_OTDR_1 | VA | HRD | LTF | R PHY | R PHY VA HRD LTF RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_LTF_OTDR_1 | VA | HRD | LTF | R PHY | R PHY VA HRD LTF RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_MCY_OTDR_1 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_MCY_OTDR_1 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_NWP_OTDR_1 | VA | HRD | NWP | R PHY | R PHY VA HRD NWP RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_NWP_OTDR_1 | VA | HRD | NWP | R PHY | R PHY VA HRD NWP RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_NRF_OTDR_1 | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_NRF_OTDR_1 | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_ONA_OTDR_1 | CE | OMA | ONA | R PHY | R PHY CE OMA ONA RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_ONA_OTDR_1 | CE | OMA | ONA | R PHY | R PHY CE OMA ONA RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_OCN_OTDR_1 | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_OCN_OTDR_1 | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_OKC_OTDR_1 | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_OKC_OTDR_1 | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_OWA_OTDR_1 | CE | TUL | OWA | R PHY | R PHY CE TUL OWA RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_OWA_OTDR_1 | CE | TUL | OWA | R PHY | R PHY CE TUL OWA RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_SPC_OTDR_1 | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-07-31 |  | Active | EP
R PHY_CCAP_SPC_OTDR_1 | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_SPC_OTDR_1 | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-07-31 |  | Active | Log | Upd | SN-0742 | Schedule Change | Approved | 2020-07-10 10:13 | RPHY CCAP POR Update for Warner Robins and South Pecue facilites
R PHY_CCAP_PNS_OTDR_1 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-09-30 |  | Active | EP
R PHY_CCAP_PNS_OTDR_1 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_PNS_OTDR_1 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-09-30 |  | Active | Log | Upd | SN-0879 | Schedule Change | Approved | 2020-08-28 10:07 | RPHY CCAP POR Update for Roanoke Baton Rouge and Pensacola
R PHY_CCAP_PTH_OTDR_1 | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-12-31 |  | Active | EP
R PHY_CCAP_PTH_OTDR_1 | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_PTH_OTDR_1 | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-11-01 |  | Active | Log | Upd | SN-0865 | Schedule Change | Approved | 2020-08-21 11:34 | This is to update the RPHY Activation dae for Providence facility
R PHY_CCAP_PTH_OTDR_1 | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-12-31 |  | Active | Log | Upd | SN-0958 | Schedule Change | Approved | 2020-09-25 09:32 | This is to update Providence RPHY activation date
R PHY_CCAP_PTM_OTDR_1 | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_PTM_OTDR_1 | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_PRA_OTDR_1 | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_PRA_OTDR_1 | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_PRV_OTDR_1 | NE | RHD | PRV | R PHY | R PHY NE RHD PRV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-11-01 |  | Active | EP
R PHY_CCAP_PRV_OTDR_1 | NE | RHD | PRV | R PHY | R PHY NE RHD PRV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_PRV_OTDR_1 | NE | RHD | PRV | R PHY | R PHY NE RHD PRV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-11-01 |  | Active | Log | Upd | SN-0958 | Schedule Change | Approved | 2020-09-25 09:32 | This is to update Providence RPHY activation date
R PHY_CCAP_QNC_OTDR_1 | CE | TUL | QNC | R PHY | R PHY CE TUL QNC RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_QNC_OTDR_1 | CE | TUL | QNC | R PHY | R PHY CE TUL QNC RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_RON_OTDR_1 | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-10-31 |  | Active | EP
R PHY_CCAP_RON_OTDR_1 | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_RON_OTDR_1 | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-10-31 |  | Active | Log | Upd | SN-0879 | Schedule Change | Approved | 2020-08-28 10:07 | RPHY CCAP POR Update for Roanoke Baton Rouge and Pensacola
R PHY_CCAP_SOU_OTDR_1 | CE | OMA | SOU | R PHY | R PHY CE OMA SOU RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_SOU_OTDR_1 | CE | OMA | SOU | R PHY | R PHY CE OMA SOU RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_TUL_OTDR_1 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL R PHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-10-30 |  | Active | EP
R PHY_CCAP_TUL_OTDR_1 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL R PHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_TUL_OTDR_1 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL R PHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-10-30 |  | Active | Log | Upd | SN-0613 | Schedule Change | Approved | 2020-05-29 16:19 | RPHY CCAP POR Update
R PHY_CCAP_VBC_OTDR_1 | VA | HRD | VBC | R PHY | R PHY VA HRD VBC RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_VBC_OTDR_1 | VA | HRD | VBC | R PHY | R PHY VA HRD VBC RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_WLK_OTDR_1 | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_WLK_OTDR_1 | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_YAL_OTDR_1 | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_YAL_OTDR_1 | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_CLH_OTDR_1 | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_CLH_OTDR_1 | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
RPHY MRTR-New-OCE-CIN Exfo-Switch | CA | SAN | OCE | R PHY | R PHY CA SAN OCE RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 4 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-OCE-CIN Exfo-Switch | CA | SAN | OCE | R PHY | R PHY CA SAN OCE RPHY Metro Deployment POR20 |  |  | 4 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-PAV-CIN Exfo-Switch | CA | ORG | PAV | R PHY | R PHY CA ORG PAV RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 4 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-PAV-CIN Exfo-Switch | CA | ORG | PAV | R PHY | R PHY CA ORG PAV RPHY Metro Deployment POR20 |  |  | 4 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-AVJ-CIN Exfo-Switch | CA | ORG | AVJ | R PHY | R PHY CA ORG AVJ R PHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 13 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-AVJ-CIN Exfo-Switch | CA | ORG | AVJ | R PHY | R PHY CA ORG AVJ R PHY Metro Deployment POR20 |  |  | 13 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-SAB-CIN Exfo-Switch | CA | SAB | SAB | R PHY | R PHY CA SAB SAB RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 10 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-SAB-CIN Exfo-Switch | CA | SAB | SAB | R PHY | R PHY CA SAB SAB RPHY Metro Initial Deployment POR20 |  |  | 10 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-VST-CIN Exfo-Switch | CA | SAN | VST | R PHY | R PHY CA SAN VST RPHY Metro Augment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 6 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-VST-CIN Exfo-Switch | CA | SAN | VST | R PHY | R PHY CA SAN VST RPHY Metro Augment POR20 |  |  | 6 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-FED-CIN Exfo-Switch | CA | SAN | FED | R PHY | R PHY CA SAN FED RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 9 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-FED-CIN Exfo-Switch | CA | SAN | FED | R PHY | R PHY CA SAN FED RPHY Metro Deployment POR20 |  |  | 9 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-ESC-CIN Exfo-Switch | CA | SAN | ESC | R PHY | R PHY CA SAN ESC RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 3 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-ESC-CIN Exfo-Switch | CA | SAN | ESC | R PHY | R PHY CA SAN ESC RPHY Metro Deployment POR20 |  |  | 3 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-ELC-CIN Exfo-Switch | CA | SAN | ELC | R PHY | R PHY CA SAN ELC RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 5 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-ELC-CIN Exfo-Switch | CA | SAN | ELC | R PHY | R PHY CA SAN ELC RPHY Metro Deployment POR20 |  |  | 5 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-DWN-CIN Exfo-Switch | CA | SAN | DWN | R PHY | R PHY CA SAN DWN RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 6 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-DWN-CIN Exfo-Switch | CA | SAN | DWN | R PHY | R PHY CA SAN DWN RPHY Metro Deployment POR20 |  |  | 6 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-ORG-CIN Exfo-Switch | CA | ORG | ORG | R PHY | R PHY CA ORG ORG RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 5 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-ORG-CIN Exfo-Switch | CA | ORG | ORG | R PHY | R PHY CA ORG ORG RPHY Metro Deployment POR20 |  |  | 5 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-IRV-CIN Exfo-Switch | CA | ORG | IRV | R PHY | R PHY CA ORG IRV R PHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 7 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-IRV-CIN Exfo-Switch | CA | ORG | IRV | R PHY | R PHY CA ORG IRV R PHY Metro Deployment POR20 |  |  | 7 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-CHU-CIN Exfo-Switch | CA | SAN | CHU | R PHY | R PHY CA SAN CHU RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 7 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-CHU-CIN Exfo-Switch | CA | SAN | CHU | R PHY | R PHY CA SAN CHU RPHY Metro Deployment POR20 |  |  | 7 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-DNP-CIN Exfo-Switch | CA | ORG | DNP | R PHY | R PHY CA ORG DNP RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 5 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-DNP-CIN Exfo-Switch | CA | ORG | DNP | R PHY | R PHY CA ORG DNP RPHY Metro Deployment POR20 |  |  | 5 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-RSM-CIN Exfo-Switch | CA | ORG | RSM | R PHY | R PHY CA ORG RSM RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 5 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-RSM-CIN Exfo-Switch | CA | ORG | RSM | R PHY | R PHY CA ORG RSM RPHY Metro Deployment POR20 |  |  | 5 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-PWY-CIN Exfo-Switch | CA | SAN | PWY | R PHY | R PHY CA SAN PWY RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 3 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-PWY-CIN Exfo-Switch | CA | SAN | PWY | R PHY | R PHY CA SAN PWY RPHY Metro Deployment POR20 |  |  | 3 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-BLV-CIN Exfo-Switch | CE | OMA | BLV | R PHY | R PHY CE OMA BLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-10-31 | 2020-10-31 | Active | EP
RPHY MRTR-New-BLV-CIN Exfo-Switch | CE | OMA | BLV | R PHY | R PHY CE OMA BLV RPHY Metro Initial Deployment POR20 |  |  | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-BLV-CIN Exfo-Switch | CE | OMA | BLV | R PHY | R PHY CE OMA BLV RPHY Metro Initial Deployment POR20 |  |  | 1 | 2020-05-31 | 2020-10-31 | 2020-10-31 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-MWC-CIN Exfo-Switch | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 2 | 2020-05-31 | 2020-11-30 | 2020-11-30 | Active | EP
RPHY MRTR-New-MWC-CIN Exfo-Switch | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY Metro Initial Deployment POR20 |  |  | 2 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-MWC-CIN Exfo-Switch | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY Metro Initial Deployment POR20 |  |  | 2 | 2020-05-31 | 2020-11-30 | 2020-11-30 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-WIC-CIN Exfo-Switch | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 2 | 2020-05-15 | 2020-10-31 | 2020-10-31 | Active | EP
RPHY MRTR-New-WIC-CIN Exfo-Switch | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 |  |  | 2 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-WIC-CIN Exfo-Switch | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 |  |  | 2 | 2020-05-15 | 2020-10-31 | 2020-10-31 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-TUL-CIN Exfo-Switch | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 6 | 2020-05-31 | 2020-10-31 | 2020-10-31 | Active | EP
RPHY MRTR-New-TUL-CIN Exfo-Switch | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY Metro Deployment POR20 |  |  | 10 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-TUL-CIN Exfo-Switch | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY Metro Deployment POR20 |  |  | 10 | 2020-05-31 | 2020-10-31 | 2020-10-31 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-TUL-CIN Exfo-Switch | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY Metro Deployment POR20 |  |  | 6 | 2020-05-31 | 2020-10-31 | 2020-10-31 | Active | Log | Upd | SN-0710 | Schedule Change | Approved | 2020-06-26 09:58 | Updates to Optical Switch in Central Region and OCML Chassis count in Fort Smith and Garnett
RPHY MRTR-New-YAL-CIN Exfo-Switch | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY Metro Augment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-YAL-CIN Exfo-Switch | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY Metro Augment POR20 |  |  | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-QNC-CIN Exfo-Switch | CE | TUL | QNC | R PHY | R PHY CE TUL QNC RPHY Metro Initial Deployment POR19 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-QNC-CIN Exfo-Switch | CE | TUL | QNC | R PHY | R PHY CE TUL QNC RPHY Metro Initial Deployment POR19 |  |  | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-FAY-CIN Exfo-Switch | CE | NWA | FAY | R PHY | R PHY CE NWA FAY RPHY Metro Augment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-FAY-CIN Exfo-Switch | CE | NWA | FAY | R PHY | R PHY CE NWA FAY RPHY Metro Augment POR20 |  |  | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-BVL-CIN Exfo-Switch | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-BVL-CIN Exfo-Switch | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY Metro Deployment POR20 |  |  | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-ONA-CIN Exfo-Switch | CE | OMA | ONA | R PHY | R PHY CE OMA ONA RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-ONA-CIN Exfo-Switch | CE | OMA | ONA | R PHY | R PHY CE OMA ONA RPHY Metro Initial Deployment POR20 |  |  | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-OWA-CIN Exfo-Switch | CE | TUL | OWA | R PHY | R PHY CE TUL OWA RPHY Metro Initial Deployment POR19 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-OWA-CIN Exfo-Switch | CE | TUL | OWA | R PHY | R PHY CE TUL OWA RPHY Metro Initial Deployment POR19 |  |  | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-ELK-CIN Exfo-Switch | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY Metro Augment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-ELK-CIN Exfo-Switch | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY Metro Augment POR20 |  |  | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-WLK-CIN Exfo-Switch | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-WLK-CIN Exfo-Switch | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY Metro Deployment POR20 |  |  | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-OKC-CIN Exfo-Switch | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY Metro Augment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-OKC-CIN Exfo-Switch | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY Metro Augment POR20 |  |  | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-BAR-CIN Exfo-Switch | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-BAR-CIN Exfo-Switch | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY Metro Deployment POR20 |  |  | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-FTS-CIN Exfo-Switch | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-11-20 | 2020-09-30 | Active | EP
RPHY MRTR-New-FTS-CIN Exfo-Switch | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY Metro Initial Deployment POR20 |  |  | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-FTS-CIN Exfo-Switch | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY Metro Initial Deployment POR20 |  |  | 1 | 2020-05-31 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-FTS-CIN Exfo-Switch | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-11-20 | 2020-09-30 | Active | Log | Upd | SN-0900 | Schedule Change | Approved | 2020-09-11 09:33 | RPHY Metro: POR Update to activation date for 2 sites Abbeville sue to resource constraints and the site was low priority Adjusting date for Forst SMith as well
RPHY MRTR-New-GAR-CIN Exfo-Switch | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 2 | 2020-05-31 | 2020-11-30 | 2020-11-30 | Active | EP
RPHY MRTR-New-GAR-CIN Exfo-Switch | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY Metro Initial Deployment POR20 |  |  | 2 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-GAR-CIN Exfo-Switch | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY Metro Initial Deployment POR20 |  |  | 2 | 2020-05-31 | 2020-11-30 | 2020-11-30 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-SOU-CIN Exfo-Switch | CE | OMA | SOU | R PHY | R PHY CE OMA SOU RPHY Metro Initial Deployment POR19 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-SOU-CIN Exfo-Switch | CE | OMA | SOU | R PHY | R PHY CE OMA SOU RPHY Metro Initial Deployment POR19 |  |  | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-WES-CIN Exfo-Switch | CE | OMA | WES | R PHY | R PHY CE OMA WES RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-WES-CIN Exfo-Switch | CE | OMA | WES | R PHY | R PHY CE OMA WES RPHY Metro Initial Deployment POR20 |  |  | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-NEH-CIN Exfo-Switch | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-12-31 | 2020-12-31 | Active | EP
RPHY MRTR-New-NEH-CIN Exfo-Switch | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY Metro Initial Deployment POR20 |  |  | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-NEH-CIN Exfo-Switch | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY Metro Initial Deployment POR20 |  |  | 1 | 2020-05-31 | 2020-12-31 | 2020-12-31 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-CLH-CIN Exfo-Switch | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY Metro Initial Deployment POR19 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-CLH-CIN Exfo-Switch | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY Metro Initial Deployment POR19 |  |  | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-TEN-CLH Exfo-Switch | SW | LAS | TEN | R PHY | R PHY SW LAS TEN R PHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 5 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-TEN-CLH Exfo-Switch | SW | LAS | TEN | R PHY | R PHY SW LAS TEN R PHY Metro Deployment POR20 |  |  | 5 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-HEN-CLH Exfo-Switch | SW | LAS | HEN | R PHY | R PHY SW LAS HEN RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 9 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-HEN-CLH Exfo-Switch | SW | LAS | HEN | R PHY | R PHY SW LAS HEN RPHY Metro Deployment POR20 |  |  | 9 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-ERN-CLH Exfo-Switch | SW | LAS | ERN | R PHY | R PHY SW LAS ERN RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 8 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-ERN-CLH Exfo-Switch | SW | LAS | ERN | R PHY | R PHY SW LAS ERN RPHY Metro Deployment POR20 |  |  | 8 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-VLY-CIN Exfo-Switch | SW | LAS | VLY | R PHY | R PHY SW LAS VLY RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 4 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-VLY-CIN Exfo-Switch | SW | LAS | VLY | R PHY | R PHY SW LAS VLY RPHY Metro Deployment POR20 |  |  | 4 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-FWL-CIN Exfo-Switch | SW | ARZ | FWL | R PHY | R PHY SW ARZ FWL RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 8 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-FWL-CIN Exfo-Switch | SW | ARZ | FWL | R PHY | R PHY SW ARZ FWL RPHY Metro Deployment POR20 |  |  | 8 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-MSA-CIN Exfo-Switch | SW | ARZ | MSA | R PHY | R PHY SW ARZ MSA RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 18 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-MSA-CIN Exfo-Switch | SW | ARZ | MSA | R PHY | R PHY SW ARZ MSA RPHY Metro Deployment POR20 |  |  | 18 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-CHD-CIN Exfo-Switch | SW | ARZ | CHD | R PHY | R PHY SW ARZ CHD RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 12 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-CHD-CIN Exfo-Switch | SW | ARZ | CHD | R PHY | R PHY SW ARZ CHD RPHY Metro Deployment POR20 |  |  | 12 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-OSB-CIN Exfo-Switch | SW | LAS | OSB | R PHY | R PHY SW LAS OSB RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 6 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-OSB-CIN Exfo-Switch | SW | LAS | OSB | R PHY | R PHY SW LAS OSB RPHY Metro Initial Deployment POR20 |  |  | 6 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-TUC-CIN Exfo-Switch | SW | ARZ | TUC | R PHY | R PHY SW ARZ TUC RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 4 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-TUC-CIN Exfo-Switch | SW | ARZ | TUC | R PHY | R PHY SW ARZ TUC RPHY Metro Deployment POR20 |  |  | 4 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-SSC-CIN Exfo-Switch | SW | ARZ | SSC | R PHY | R PHY SW ARZ SSC RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 5 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-SSC-CIN Exfo-Switch | SW | ARZ | SSC | R PHY | R PHY SW ARZ SSC RPHY Metro Deployment POR20 |  |  | 5 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-ALI-CIN Exfo-Switch | SW | LAS | ALI | R PHY | R PHY SW LAS ALI RPHY Metro Augment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 4 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-ALI-CIN Exfo-Switch | SW | LAS | ALI | R PHY | R PHY SW LAS ALI RPHY Metro Augment POR20 |  |  | 4 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-VSA-CIN Exfo-Switch | SW | ARZ | VSA | R PHY | R PHY SW ARZ VSA RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-VSA-CIN Exfo-Switch | SW | ARZ | VSA | R PHY | R PHY SW ARZ VSA RPHY Metro Deployment POR20 |  |  | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-PNL-CIN Exfo-Switch | SW | ARZ | PNL | R PHY | R PHY SW ARZ PNL RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 2 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-PNL-CIN Exfo-Switch | SW | ARZ | PNL | R PHY | R PHY SW ARZ PNL RPHY Metro Deployment POR20 |  |  | 2 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-NSC-CIN Exfo-Switch | SW | ARZ | NSC | R PHY | R PHY SW ARZ NSC RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 2 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-NSC-CIN Exfo-Switch | SW | ARZ | NSC | R PHY | R PHY SW ARZ NSC RPHY Metro Deployment POR20 |  |  | 2 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-PEO-CIN Exfo-Switch | SW | ARZ | PEO | R PHY | R PHY SW ARZ PEO R PHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 6 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-PEO-CIN Exfo-Switch | SW | ARZ | PEO | R PHY | R PHY SW ARZ PEO R PHY Metro Deployment POR20 |  |  | 6 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-MCD-CIN Exfo-Switch | SW | ARZ | MCD | R PHY | R PHY SW ARZ MCD RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 2 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-MCD-CIN Exfo-Switch | SW | ARZ | MCD | R PHY | R PHY SW ARZ MCD RPHY Metro Deployment POR20 |  |  | 2 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-BUK-CIN Exfo-Switch | SW | ARZ | BUK | R PHY | R PHY SW ARZ BUK RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 2 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-BUK-CIN Exfo-Switch | SW | ARZ | BUK | R PHY | R PHY SW ARZ BUK RPHY Metro Deployment POR20 |  |  | 2 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-BEL-CIN Exfo-Switch | SW | ARZ | BEL | R PHY | R PHY SW ARZ BEL RPHY Metro Augment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 7 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-BEL-CIN Exfo-Switch | SW | ARZ | BEL | R PHY | R PHY SW ARZ BEL RPHY Metro Augment POR20 |  |  | 7 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-BLU-CIN Exfo-Switch | SW | LAS | BLU | R PHY | R PHY SW LAS BLU RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 7 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-BLU-CIN Exfo-Switch | SW | LAS | BLU | R PHY | R PHY SW LAS BLU RPHY Metro Deployment POR20 |  |  | 7 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-MCY-CIN Exfo-Switch | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-MCY-CIN Exfo-Switch | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY Metro Deployment POR20 |  |  | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-LFY-CIN Exfo-Switch | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY Metro Initial Deployment POR19 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-LFY-CIN Exfo-Switch | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY Metro Initial Deployment POR19 |  |  | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-PNS-CIN Exfo-Switch | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-09-30 | 2020-07-31 | Active | EP
RPHY MRTR-New-PNS-CIN Exfo-Switch | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 |  |  | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-PNS-CIN Exfo-Switch | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 |  |  | 1 | 2020-05-31 | 2020-07-31 | 2020-07-31 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-PNS-CIN Exfo-Switch | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 |  |  | 1 | 2020-05-31 | 2020-08-31 | 2020-07-31 | Active | Log | Upd | SN-0786 | Schedule Change | Approved | 2020-07-27 09:30 | 1 SE OSNAP for Metairie was approved last week in CR 726 2 This POR adds that EPS project created into the POR 3 Also updating OCML Chassis count for Omaha North as to align with the BOM
RPHY MRTR-New-PNS-CIN Exfo-Switch | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-09-30 | 2020-07-31 | Active | Log | Upd | SN-0881 | Schedule Change | Approved | 2020-08-28 10:07 | 1 Moving Pensacola Activation Date from August to September because of Firewall issues 2 Moving BTR dates from August to September because of Resource constraints in with BTR NF team
RPHY MRTR-New-SPC-CIN Exfo-Switch | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-07-31 | 2020-06-30 | Active | EP
RPHY MRTR-New-SPC-CIN Exfo-Switch | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 |  |  | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-SPC-CIN Exfo-Switch | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 |  |  | 1 | 2020-05-31 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-SPC-CIN Exfo-Switch | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 |  |  | 1 | 2020-05-31 | 2020-07-31 | 2020-06-30 | Active | Log | Upd | SN-0741 | Schedule Change | Approved | 2020-07-10 10:12 | RPHY Metro: Updates to POR based on Field inputs
RPHY MRTR-New-FBG-CIN Exfo-Switch | VA | NVA | FBG | R PHY | R PHY VA NVA FBG RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-FBG-CIN Exfo-Switch | VA | NVA | FBG | R PHY | R PHY VA NVA FBG RPHY Metro Initial Deployment POR20 |  |  | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-LTF-CIN Exfo-Switch | VA | HRD | LTF | R PHY | R PHY VA HRD LTF RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-LTF-CIN Exfo-Switch | VA | HRD | LTF | R PHY | R PHY VA HRD LTF RPHY Metro Initial Deployment POR20 |  |  | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-RON-CIN Exfo-Switch | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY Metro Initial Deployment POR19 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-RON-CIN Exfo-Switch | VA | ROA | RON | R PHY | R PHY VA ROA RON RPHY Metro Initial Deployment POR19 |  |  | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-VBC-CIN Exfo-Switch | VA | HRD | VBC | R PHY | R PHY VA HRD VBC R PHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 2 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-VBC-CIN Exfo-Switch | VA | HRD | VBC | R PHY | R PHY VA HRD VBC R PHY Metro Deployment POR20 |  |  | 2 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-PRA-CIN Exfo-Switch | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-PRA-CIN Exfo-Switch | VA | HRD | PRA | R PHY | R PHY VA HRD PRA RPHY Metro Deployment POR20 |  |  | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-PTM-CIN Exfo-Switch | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY Metro Initial Deployment POR19 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch |  |  |  |  | Deleted | EP
RPHY MRTR-New-PTM-CIN Exfo-Switch | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY Metro Initial Deployment POR19 |  |  | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Deleted | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-PTM-CIN Exfo-Switch | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY Metro Initial Deployment POR19 | [6 empty] | Deleted | Log | Del | SN-0741 | Schedule Change | Approved | 2020-07-10 10:12 | RPHY Metro: Updates to POR based on Field inputs
RPHY MRTR-New-OCN-CIN Exfo-Switch | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-OCN-CIN Exfo-Switch | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY Metro Deployment POR20 |  |  | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-NRF-CIN Exfo-Switch | VA | HRD | NRF | R PHY | R PHY VA HRD NRF R PHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-NRF-CIN Exfo-Switch | VA | HRD | NRF | R PHY | R PHY VA HRD NRF R PHY Metro Deployment POR20 |  |  | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-NWP-CIN Exfo-Switch | VA | HRD | NWP | R PHY | R PHY VA HRD NWP RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 4 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-NWP-CIN Exfo-Switch | VA | HRD | NWP | R PHY | R PHY VA HRD NWP RPHY Metro Deployment POR20 |  |  | 4 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-CHS-CIN Exfo-Switch | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY Metro Initial Deployment POR19 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch |  |  |  |  | Deleted | EP
RPHY MRTR-New-CHS-CIN Exfo-Switch | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY Metro Initial Deployment POR19 |  |  | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Deleted | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-CHS-CIN Exfo-Switch | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY Metro Initial Deployment POR19 | [6 empty] | Deleted | Log | Del | SN-0741 | Schedule Change | Approved | 2020-07-10 10:12 | RPHY Metro: Updates to POR based on Field inputs
RPHY MRTR-New-PTH-CIN Exfo-Switch | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY Metro Initial Deployment POR19 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | EP
RPHY MRTR-New-PTH-CIN Exfo-Switch | NE | RHD | PTH | R PHY | R PHY NE RHD PTH RPHY Metro Initial Deployment POR19 |  |  | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-PRV-CIN Exfo-Switch | NE | RHD | PRV | R PHY | R PHY NE RHD PRV RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-11-01 | 2020-08-15 | Active | EP
RPHY MRTR-New-PRV-CIN Exfo-Switch | NE | RHD | PRV | R PHY | R PHY NE RHD PRV RPHY Metro Initial Deployment POR20 |  |  | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | Active | Log | New | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-PRV-CIN Exfo-Switch | NE | RHD | PRV | R PHY | R PHY NE RHD PRV RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-11-01 | 2020-08-15 | Active | Log | Upd | SN-0842 | Schedule Change | Approved | 2020-08-14 15:08 | Providence Activation date change from 10 16 to 11 1
R PHY_CCAP_CLR_OTDR_1 | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-15 | 2020-08-31 |  | Active | EP
R PHY_CCAP_CLR_OTDR_1 | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-15 | 2020-06-30 |  | Active | Log | New | SN-0613 | Schedule Change | Approved | 2020-05-29 16:19 | RPHY CCAP POR Update
R PHY_CCAP_CLR_OTDR_1 | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-15 | 2020-07-31 |  | Active | Log | Upd | SN-0742 | Schedule Change | Approved | 2020-07-10 10:13 | RPHY CCAP POR Update for Warner Robins and South Pecue facilites
R PHY_CCAP_CLR_OTDR_1 | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-15 | 2020-08-31 |  | Active | Log | Upd | SN-0811 | Schedule Change | Approved | 2020-08-07 09:40 | This is to update RPHY CCAP POR for CLR WRB SAB and PNS sites
RPHY MRTR-New-CLR-CIN-ATX-OCML | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 40 | 2020-05-15 | 2020-08-31 | 2020-06-30 | Active | EP
RPHY MRTR-New-CLR-CIN-ATX-OCML | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 40 | 2020-05-15 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-CLR-CIN-ATX-OCML | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 40 | 2020-05-15 | 2020-07-31 | 2020-06-30 | Active | Log | Upd | SN-0741 | Schedule Change | Approved | 2020-07-10 10:12 | RPHY Metro: Updates to POR based on Field inputs
RPHY MRTR-New-CLR-CIN-ATX-OCML | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 40 | 2020-05-15 | 2020-08-31 | 2020-06-30 | Active | Log | Upd | SN-0810 | Schedule Change | Approved | 2020-08-07 09:41 | 1 Warner Robins and Clear View needs to be moved to August as Alrm Testing was not completed
RPHY MRTR-New-CLR-CIN-Exfo-Optical Switch | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 4 | 2020-05-15 | 2020-08-31 | 2020-06-30 | Active | EP
RPHY MRTR-New-CLR-CIN-Exfo-Optical Switch | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 |  |  | 4 | 2020-05-15 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-CLR-CIN-Exfo-Optical Switch | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 |  |  | 4 | 2020-05-15 | 2020-07-31 | 2020-06-30 | Active | Log | Upd | SN-0741 | Schedule Change | Approved | 2020-07-10 10:12 | RPHY Metro: Updates to POR based on Field inputs
RPHY MRTR-New-CLR-CIN-Exfo-Optical Switch | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 4 | 2020-05-15 | 2020-08-31 | 2020-06-30 | Active | Log | Upd | SN-0810 | Schedule Change | Approved | 2020-08-07 09:41 | 1 Warner Robins and Clear View needs to be moved to August as Alrm Testing was not completed
RPHY MRTR-New-WRB-CIN-Exfo-Optical Switch | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-04-05 | 2020-09-30 | 2020-07-31 | Active | EP
RPHY MRTR-New-WRB-CIN-Exfo-Optical Switch | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 |  |  | 1 | 2020-04-05 | 2020-07-31 | 2020-07-31 | Active | Log | New | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-WRB-CIN-Exfo-Optical Switch | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 |  |  | 1 | 2020-04-05 | 2020-08-31 | 2020-07-31 | Active | Log | Upd | SN-0741 | Schedule Change | Approved | 2020-07-10 10:12 | RPHY Metro: Updates to POR based on Field inputs
RPHY MRTR-New-WRB-CIN-Exfo-Optical Switch | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-04-05 | 2020-09-30 | 2020-07-31 | Active | Log | Upd | SN-0810 | Schedule Change | Approved | 2020-08-07 09:41 | 1 Warner Robins and Clear View needs to be moved to August as Alrm Testing was not completed
RPHY MRTR-New-ALI-CIN-ATX-OCML | SW | LAS | ALI | R PHY | R PHY SW LAS ALI RPHY Metro Augment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
RPHY MRTR-New-ALI-CIN-ATX-OCML | SW | LAS | ALI | R PHY | R PHY SW LAS ALI RPHY Metro Augment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | New | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-BLU-CIN-ATX-OCML | SW | LAS | BLU | R PHY | R PHY SW LAS BLU R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
RPHY MRTR-New-BLU-CIN-ATX-OCML | SW | LAS | BLU | R PHY | R PHY SW LAS BLU R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | New | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-ERN-CIN-ATX-OCML | SW | LAS | ERN | R PHY | R PHY SW LAS ERN RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-15 | Active | EP
RPHY MRTR-New-ERN-CIN-ATX-OCML | SW | LAS | ERN | R PHY | R PHY SW LAS ERN RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-15 | Active | Log | New | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-VLY-CIN-ATX-OCML | SW | LAS | VLY | R PHY | R PHY SW LAS VLY RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-15 | Active | EP
RPHY MRTR-New-VLY-CIN-ATX-OCML | SW | LAS | VLY | R PHY | R PHY SW LAS VLY RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-15 | Active | Log | New | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-LTF-CIN-ATX-OCML | VA | HRD | LTF | R PHY | R PHY VA HRD LTF RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-LTF-CIN-ATX-OCML | VA | HRD | LTF | R PHY | R PHY VA HRD LTF RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-FBG-CIN-ATX-OCML | VA | NVA | FBG | R PHY | R PHY VA NVA FBG RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
RPHY MRTR-New-FBG-CIN-ATX-OCML | VA | NVA | FBG | R PHY | R PHY VA NVA FBG RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
R PHY_CCAP_WRB_OTDR_1 | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-06-10 | 2020-09-30 |  | Active | EP
R PHY_CCAP_WRB_OTDR_1 | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-06-10 | 2020-07-31 |  | Active | Log | New | SN-0613 | Schedule Change | Approved | 2020-05-29 16:19 | RPHY CCAP POR Update
R PHY_CCAP_WRB_OTDR_1 | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-06-10 | 2020-08-31 |  | Active | Log | Upd | SN-0742 | Schedule Change | Approved | 2020-07-10 10:13 | RPHY CCAP POR Update for Warner Robins and South Pecue facilites
R PHY_CCAP_WRB_OTDR_1 | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-06-10 | 2020-09-30 |  | Active | Log | Upd | SN-0811 | Schedule Change | Approved | 2020-08-07 09:40 | This is to update RPHY CCAP POR for CLR WRB SAB and PNS sites
RPHY MRTR-New-CHS-CIN-ATX-OCML2 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-CHS-CIN-ATX-OCML2 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
R PHY_CCAP_WIC_OTDR_1 | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-07-20 | 2020-10-30 |  | Active | EP
R PHY_CCAP_WIC_OTDR_1 | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-07-20 | 2020-10-30 |  | Active | Log | New | SN-0637 | Schedule Change | Approved | 2020-06-05 14:50 | RPHY CCAP POR Update
R PHY_CCAP_MWC_OTDR_1 | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-07-20 | 2020-11-30 |  | Active | EP
R PHY_CCAP_MWC_OTDR_1 | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-07-20 | 2020-11-30 |  | Active | Log | New | SN-0637 | Schedule Change | Approved | 2020-06-05 14:50 | RPHY CCAP POR Update
R PHY_CCAP_NEH_OTDR_1 | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-07-31 | 2020-12-31 |  | Active | EP
R PHY_CCAP_NEH_OTDR_1 | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-07-31 | 2020-12-31 |  | Active | Log | New | SN-0637 | Schedule Change | Approved | 2020-06-05 14:50 | RPHY CCAP POR Update
R PHY_CCAP_BLV_OTDR_1 | CE | OMA | BLV | R PHY | R PHY CE OMA BLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-07-20 | 2020-10-30 |  | Active | EP
R PHY_CCAP_BLV_OTDR_1 | CE | OMA | BLV | R PHY | R PHY CE OMA BLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-07-20 | 2020-10-30 |  | Active | Log | New | SN-0637 | Schedule Change | Approved | 2020-06-05 14:50 | RPHY CCAP POR Update
R PHY_CCAP_GAR_OTDR_1 | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-07-20 | 2020-11-30 |  | Active | EP
R PHY_CCAP_GAR_OTDR_1 | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-07-20 | 2020-11-30 |  | Active | Log | New | SN-0637 | Schedule Change | Approved | 2020-06-05 14:50 | RPHY CCAP POR Update
R PHY_CCAP_CLV_OTDR_1 | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-07-20 | 2020-12-31 |  | Active | EP
R PHY_CCAP_CLV_OTDR_1 | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-07-20 | 2020-10-15 |  | Active | Log | New | SN-0637 | Schedule Change | Approved | 2020-06-05 14:50 | RPHY CCAP POR Update
R PHY_CCAP_CLV_OTDR_1 | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-07-20 | 2020-12-31 |  | Active | Log | Upd | SN-0843 | Schedule Change | Approved | 2020-08-15 10:44 | This is to update Activation date for Cleveland
R PHY_CCAP_BTR_OTDR_1 | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-07-20 | 2020-09-30 |  | Active | EP
R PHY_CCAP_BTR_OTDR_1 | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-07-20 | 2020-08-15 |  | Active | Log | New | SN-0637 | Schedule Change | Approved | 2020-06-05 14:50 | RPHY CCAP POR Update
R PHY_CCAP_BTR_OTDR_1 | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-07-20 | 2020-09-30 |  | Active | Log | Upd | SN-0879 | Schedule Change | Approved | 2020-08-28 10:07 | RPHY CCAP POR Update for Roanoke Baton Rouge and Pensacola
R PHY_CCAP_ABV_OTDR_1 | SE | LFY | ABV | R PHY | R PHY SE LFY ABV RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-07-20 | 2020-10-31 |  | Active | EP
R PHY_CCAP_ABV_OTDR_1 | SE | LFY | ABV | R PHY | R PHY SE LFY ABV RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-07-20 | 2020-09-30 |  | Active | Log | New | SN-0637 | Schedule Change | Approved | 2020-06-05 14:50 | RPHY CCAP POR Update
R PHY_CCAP_ABV_OTDR_1 | SE | LFY | ABV | R PHY | R PHY SE LFY ABV RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-07-20 | 2020-10-31 |  | Active | Log | Upd | SN-0899 | Schedule Change | Approved | 2020-09-11 09:34 | RPHY CCAP actiation date updates for Fort Smith and Abbeville sites Material delivery date update for CLV FTS RSM BLU and HEN facilites
R PHY_CCAP_LUL_OTDR_1 | SE | NOR | LUL | R PHY | R PHY SE NOR LUL RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-07-20 | 2020-10-30 |  | Active | EP
R PHY_CCAP_LUL_OTDR_1 | SE | NOR | LUL | R PHY | R PHY SE NOR LUL RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-07-20 | 2020-10-30 |  | Active | Log | New | SN-0637 | Schedule Change | Approved | 2020-06-05 14:50 | RPHY CCAP POR Update
RPHY MRTR-New-SPC Parma-CIN-DPA-5200 (100G DPIC) | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 4 | 2020-08-05 | 2020-12-31 |  | Deleted | EP
RPHY MRTR-New-CLV-CIN-ATX-OCML | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 160 | 2020-08-01 | 2020-12-31 | 2020-12-31 | Active | EP
RPHY MRTR-New-CLV-CIN-ATX-OCML | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 160 | 2020-08-01 | 2020-12-31 | 2020-12-31 | Active | Log | New | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
RPHY MRTR-New-CLV-CIN-Exfo-Optical Switch | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2870 64 Port Optical Switch | 16 | 2020-08-01 | 2020-12-31 | 2020-12-31 | Active | EP
RPHY MRTR-New-CLV-CIN-Exfo-Optical Switch | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY Metro Initial Deployment POR20 |  |  | 16 | 2020-08-01 | 2020-12-31 | 2020-12-31 | Active | Log | New | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
R PHY_CCAP_ONA_Boundary_Clocks | CE | OMA | ONA | R PHY | R PHY CE OMA ONA RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-07-15 | 2020-10-30 |  | Active | EP
R PHY_CCAP_ONA_Boundary_Clocks | CE | OMA | ONA | R PHY | R PHY CE OMA ONA RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-07-15 | 2020-10-30 |  | Active | Log | New | SN-0725 | Schedule Change | Approved | 2020-07-02 11:46 | This is to add projects which were missed previously into POR
R PHY_CCAP_WES_Boundary_Clocks | CE | OMA | WES | R PHY | R PHY CE OMA WES RPHY - CCAP Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-07-15 | 2020-10-30 |  | Active | EP
R PHY_CCAP_WES_Boundary_Clocks | CE | OMA | WES | R PHY | R PHY CE OMA WES RPHY - CCAP Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-07-15 | 2020-10-30 |  | Active | Log | New | SN-0725 | Schedule Change | Approved | 2020-07-02 11:46 | This is to add projects which were missed previously into POR
RPHY MRTR-New-BVL-CIN-RPA2-5110 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-10-01 | 2020-12-31 |  | Active | EP
RPHY MRTR-New-BVL-CIN-RPA2-5110 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-10-01 | 2020-12-31 |  | Active | Log | New | SN-0722 | Scope Change | Approved | 2020-07-15 17:20 | 1 RPHY Metro: New Capacity Requirement for Central for 6 sites 2 Total of 4 OCML Racks that includes 2 RPA 10 Nokia OCML 1 Nxus and 1 Exfo optcal switch 3 Tulsa needs 3 RPA s and Garnet needs 1 4 Raid Log already raised and discussed 5 Self Solving from t
RPHY MRTR-New-BVL-CIN Exfo-Switch2 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-10-01 | 2020-12-31 |  | Active | EP
RPHY MRTR-New-BVL-CIN Exfo-Switch2 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY Metro Deployment POR20 |  |  | 1 | 2020-10-01 | 2020-12-31 |  | Active | Log | New | SN-0722 | Scope Change | Approved | 2020-07-15 17:20 | 1 RPHY Metro: New Capacity Requirement for Central for 6 sites 2 Total of 4 OCML Racks that includes 2 RPA 10 Nokia OCML 1 Nxus and 1 Exfo optcal switch 3 Tulsa needs 3 RPA s and Garnet needs 1 4 Raid Log already raised and discussed 5 Self Solving from t
RPHY MRTR-New-BVL-CIN MGMT2-2K | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-10-01 | 2020-12-31 |  | Active | EP
RPHY MRTR-New-BVL-CIN MGMT2-2K | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-10-01 | 2020-12-31 |  | Active | Log | New | SN-0722 | Scope Change | Approved | 2020-07-15 17:20 | 1 RPHY Metro: New Capacity Requirement for Central for 6 sites 2 Total of 4 OCML Racks that includes 2 RPA 10 Nokia OCML 1 Nxus and 1 Exfo optcal switch 3 Tulsa needs 3 RPA s and Garnet needs 1 4 Raid Log already raised and discussed 5 Self Solving from t
RPHY MRTR-New-BVL-CIN-Nokia3-OCML | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-10-01 | 2020-12-31 |  | Active | EP
RPHY MRTR-New-BVL-CIN-Nokia3-OCML | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-10-01 | 2020-12-31 |  | Active | Log | New | SN-0722 | Scope Change | Approved | 2020-07-15 17:20 | 1 RPHY Metro: New Capacity Requirement for Central for 6 sites 2 Total of 4 OCML Racks that includes 2 RPA 10 Nokia OCML 1 Nxus and 1 Exfo optcal switch 3 Tulsa needs 3 RPA s and Garnet needs 1 4 Raid Log already raised and discussed 5 Self Solving from t
RPHY MRTR-New-BAR-CIN-RPA2-5110 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-10-01 | 2020-12-31 |  | Active | EP
RPHY MRTR-New-BAR-CIN-RPA2-5110 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-10-01 | 2020-12-31 |  | Active | Log | New | SN-0722 | Scope Change | Approved | 2020-07-15 17:20 | 1 RPHY Metro: New Capacity Requirement for Central for 6 sites 2 Total of 4 OCML Racks that includes 2 RPA 10 Nokia OCML 1 Nxus and 1 Exfo optcal switch 3 Tulsa needs 3 RPA s and Garnet needs 1 4 Raid Log already raised and discussed 5 Self Solving from t
RPHY MRTR-New-BAR-CIN MGMT2-2K | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-10-01 | 2020-12-31 |  | Active | EP
RPHY MRTR-New-BAR-CIN MGMT2-2K | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-10-01 | 2020-12-31 |  | Active | Log | New | SN-0722 | Scope Change | Approved | 2020-07-15 17:20 | 1 RPHY Metro: New Capacity Requirement for Central for 6 sites 2 Total of 4 OCML Racks that includes 2 RPA 10 Nokia OCML 1 Nxus and 1 Exfo optcal switch 3 Tulsa needs 3 RPA s and Garnet needs 1 4 Raid Log already raised and discussed 5 Self Solving from t
RPHY MRTR-New-BAR-CIN-Nokia3-OCML | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-10-01 | 2020-12-31 |  | Active | EP
RPHY MRTR-New-BAR-CIN-Nokia3-OCML | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-10-01 | 2020-12-31 |  | Active | Log | New | SN-0722 | Scope Change | Approved | 2020-07-15 17:20 | 1 RPHY Metro: New Capacity Requirement for Central for 6 sites 2 Total of 4 OCML Racks that includes 2 RPA 10 Nokia OCML 1 Nxus and 1 Exfo optcal switch 3 Tulsa needs 3 RPA s and Garnet needs 1 4 Raid Log already raised and discussed 5 Self Solving from t
RPHY MRTR-New-BAR-CIN Exfo-Switch2 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-10-01 | 2020-12-31 |  | Active | EP
RPHY MRTR-New-BAR-CIN Exfo-Switch2 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY Metro Deployment POR20 |  |  | 1 | 2020-10-01 | 2020-12-31 |  | Active | Log | New | SN-0722 | Scope Change | Approved | 2020-07-15 17:20 | 1 RPHY Metro: New Capacity Requirement for Central for 6 sites 2 Total of 4 OCML Racks that includes 2 RPA 10 Nokia OCML 1 Nxus and 1 Exfo optcal switch 3 Tulsa needs 3 RPA s and Garnet needs 1 4 Raid Log already raised and discussed 5 Self Solving from t
RPHY MRTR-New-ELK-CIN-RPA2-5110 | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-10-01 | 2020-12-31 |  | Active | EP
RPHY MRTR-New-ELK-CIN-RPA2-5110 | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-10-01 | 2020-12-31 |  | Active | Log | New | SN-0722 | Scope Change | Approved | 2020-07-15 17:20 | 1 RPHY Metro: New Capacity Requirement for Central for 6 sites 2 Total of 4 OCML Racks that includes 2 RPA 10 Nokia OCML 1 Nxus and 1 Exfo optcal switch 3 Tulsa needs 3 RPA s and Garnet needs 1 4 Raid Log already raised and discussed 5 Self Solving from t
RPHY MRTR-New-ELK-CIN MGMT2-2K | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-10-01 | 2020-12-31 |  | Active | EP
RPHY MRTR-New-ELK-CIN MGMT2-2K | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-10-01 | 2020-12-31 |  | Active | Log | New | SN-0722 | Scope Change | Approved | 2020-07-15 17:20 | 1 RPHY Metro: New Capacity Requirement for Central for 6 sites 2 Total of 4 OCML Racks that includes 2 RPA 10 Nokia OCML 1 Nxus and 1 Exfo optcal switch 3 Tulsa needs 3 RPA s and Garnet needs 1 4 Raid Log already raised and discussed 5 Self Solving from t
RPHY MRTR-New-ELK-CIN Exfo-Switch2 | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY Metro Augment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-10-01 | 2020-12-31 |  | Active | EP
RPHY MRTR-New-ELK-CIN Exfo-Switch2 | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY Metro Augment POR20 |  |  | 1 | 2020-10-01 | 2020-12-31 |  | Active | Log | New | SN-0722 | Scope Change | Approved | 2020-07-15 17:20 | 1 RPHY Metro: New Capacity Requirement for Central for 6 sites 2 Total of 4 OCML Racks that includes 2 RPA 10 Nokia OCML 1 Nxus and 1 Exfo optcal switch 3 Tulsa needs 3 RPA s and Garnet needs 1 4 Raid Log already raised and discussed 5 Self Solving from t
RPHY MRTR-New-ELK-CIN-Nokia3-OCML | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-10-01 | 2020-12-31 |  | Active | EP
RPHY MRTR-New-ELK-CIN-Nokia3-OCML | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-10-01 | 2020-12-31 |  | Active | Log | New | SN-0722 | Scope Change | Approved | 2020-07-15 17:20 | 1 RPHY Metro: New Capacity Requirement for Central for 6 sites 2 Total of 4 OCML Racks that includes 2 RPA 10 Nokia OCML 1 Nxus and 1 Exfo optcal switch 3 Tulsa needs 3 RPA s and Garnet needs 1 4 Raid Log already raised and discussed 5 Self Solving from t
RPHY MRTR-New-GAR-CIN-RPA25110 | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-10-01 | 2020-12-31 |  | Active | EP
RPHY MRTR-New-GAR-CIN-RPA25110 | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-10-01 | 2020-12-31 |  | Active | Log | New | SN-0722 | Scope Change | Approved | 2020-07-15 17:20 | 1 RPHY Metro: New Capacity Requirement for Central for 6 sites 2 Total of 4 OCML Racks that includes 2 RPA 10 Nokia OCML 1 Nxus and 1 Exfo optcal switch 3 Tulsa needs 3 RPA s and Garnet needs 1 4 Raid Log already raised and discussed 5 Self Solving from t
RPHY MRTR-New-OKC-CIN-RPA2-5110 | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-10-01 | 2020-12-31 |  | Active | EP
RPHY MRTR-New-OKC-CIN-RPA2-5110 | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-10-01 | 2020-12-31 |  | Active | Log | New | SN-0722 | Scope Change | Approved | 2020-07-15 17:20 | 1 RPHY Metro: New Capacity Requirement for Central for 6 sites 2 Total of 4 OCML Racks that includes 2 RPA 10 Nokia OCML 1 Nxus and 1 Exfo optcal switch 3 Tulsa needs 3 RPA s and Garnet needs 1 4 Raid Log already raised and discussed 5 Self Solving from t
RPHY MRTR-New-OKC-CIN Exfo-Switch2 | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY Metro Augment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-10-01 | 2020-12-31 |  | Active | EP
RPHY MRTR-New-OKC-CIN Exfo-Switch2 | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY Metro Augment POR20 |  |  | 1 | 2020-10-01 | 2020-12-31 |  | Active | Log | New | SN-0722 | Scope Change | Approved | 2020-07-15 17:20 | 1 RPHY Metro: New Capacity Requirement for Central for 6 sites 2 Total of 4 OCML Racks that includes 2 RPA 10 Nokia OCML 1 Nxus and 1 Exfo optcal switch 3 Tulsa needs 3 RPA s and Garnet needs 1 4 Raid Log already raised and discussed 5 Self Solving from t
RPHY MRTR-New-OKC-CIN MGMT2-2K | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-10-01 | 2020-12-31 |  | Active | EP
RPHY MRTR-New-OKC-CIN MGMT2-2K | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-10-01 | 2020-12-31 |  | Active | Log | New | SN-0722 | Scope Change | Approved | 2020-07-15 17:20 | 1 RPHY Metro: New Capacity Requirement for Central for 6 sites 2 Total of 4 OCML Racks that includes 2 RPA 10 Nokia OCML 1 Nxus and 1 Exfo optcal switch 3 Tulsa needs 3 RPA s and Garnet needs 1 4 Raid Log already raised and discussed 5 Self Solving from t
RPHY MRTR-New-OKC-CIN-Nokia3-OCML | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-10-01 | 2020-12-31 |  | Active | EP
RPHY MRTR-New-OKC-CIN-Nokia3-OCML | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-10-01 | 2020-12-31 |  | Active | Log | New | SN-0722 | Scope Change | Approved | 2020-07-15 17:20 | 1 RPHY Metro: New Capacity Requirement for Central for 6 sites 2 Total of 4 OCML Racks that includes 2 RPA 10 Nokia OCML 1 Nxus and 1 Exfo optcal switch 3 Tulsa needs 3 RPA s and Garnet needs 1 4 Raid Log already raised and discussed 5 Self Solving from t
RPHY MRTR-New-TUL-CIN-RPA3-5110 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 3 | 2020-10-01 | 2020-12-31 |  | Active | EP
RPHY MRTR-New-TUL-CIN-RPA3-5110 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 3 | 2020-10-01 | 2020-12-31 |  | Active | Log | New | SN-0722 | Scope Change | Approved | 2020-07-15 17:20 | 1 RPHY Metro: New Capacity Requirement for Central for 6 sites 2 Total of 4 OCML Racks that includes 2 RPA 10 Nokia OCML 1 Nxus and 1 Exfo optcal switch 3 Tulsa needs 3 RPA s and Garnet needs 1 4 Raid Log already raised and discussed 5 Self Solving from t
RPHY MRTR-Growth-WIC-CIN MGMT2-2K | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-10-01 | 2020-12-31 |  | Active | EP
RPHY MRTR-Growth-WIC-CIN MGMT2-2K | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-10-01 | 2020-12-31 |  | Active | Log | New | SN-0722 | Scope Change | Approved | 2020-07-15 17:20 | 1 RPHY Metro: New Capacity Requirement for Central for 6 sites 2 Total of 4 OCML Racks that includes 2 RPA 10 Nokia OCML 1 Nxus and 1 Exfo optcal switch 3 Tulsa needs 3 RPA s and Garnet needs 1 4 Raid Log already raised and discussed 5 Self Solving from t
RPHY MRTR-New-WIC2-CIN-RPA2-5110 | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-10-01 | 2020-12-31 |  | Active | EP
RPHY MRTR-New-WIC2-CIN-RPA2-5110 | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-10-01 | 2020-12-31 |  | Active | Log | New | SN-0722 | Scope Change | Approved | 2020-07-15 17:20 | 1 RPHY Metro: New Capacity Requirement for Central for 6 sites 2 Total of 4 OCML Racks that includes 2 RPA 10 Nokia OCML 1 Nxus and 1 Exfo optcal switch 3 Tulsa needs 3 RPA s and Garnet needs 1 4 Raid Log already raised and discussed 5 Self Solving from t
RPHY MRTR-New-WIC-CIN Exfo-Switch2 | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-10-01 | 2020-12-31 |  | Active | EP
RPHY MRTR-New-WIC-CIN Exfo-Switch2 | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 |  |  | 1 | 2020-10-01 | 2020-12-31 |  | Active | Log | New | SN-0722 | Scope Change | Approved | 2020-07-15 17:20 | 1 RPHY Metro: New Capacity Requirement for Central for 6 sites 2 Total of 4 OCML Racks that includes 2 RPA 10 Nokia OCML 1 Nxus and 1 Exfo optcal switch 3 Tulsa needs 3 RPA s and Garnet needs 1 4 Raid Log already raised and discussed 5 Self Solving from t
RPHY MRTR-New-WIC-CIN-NOKIA-OCML2 | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-10-01 | 2020-12-31 |  | Active | EP
RPHY MRTR-New-WIC-CIN-NOKIA-OCML2 | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-10-01 | 2020-12-31 |  | Active | Log | New | SN-0722 | Scope Change | Approved | 2020-07-15 17:20 | 1 RPHY Metro: New Capacity Requirement for Central for 6 sites 2 Total of 4 OCML Racks that includes 2 RPA 10 Nokia OCML 1 Nxus and 1 Exfo optcal switch 3 Tulsa needs 3 RPA s and Garnet needs 1 4 Raid Log already raised and discussed 5 Self Solving from t
R PHY_CCAP_TUL_CBR8_2 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL R PHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-09-22 | 2020-12-31 |  | Active | EP
R PHY_CCAP_TUL_CBR8_2 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL R PHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-09-25 | 2020-12-31 |  | Active | Log | New | SN-0725 | Schedule Change | Approved | 2020-07-02 11:46 | This is to add projects which were missed previously into POR
R PHY_CCAP_TUL_CBR8_2 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL R PHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-09-22 | 2020-12-31 |  | Active | Log | Upd | SN-0899 | Schedule Change | Approved | 2020-09-11 09:34 | RPHY CCAP actiation date updates for Fort Smith and Abbeville sites Material delivery date update for CLV FTS RSM BLU and HEN facilites
RPHY MRTR-New-PTM-CIN Exfo-Switch2 | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY Metro Augment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 |  | Active | EP
RPHY MRTR-New-PTM-CIN Exfo-Switch2 | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY Metro Augment POR20 |  |  | 1 | 2020-05-31 | 2020-08-15 |  | Active | Log | New | SN-0741 | Schedule Change | Approved | 2020-07-10 10:12 | RPHY Metro: Updates to POR based on Field inputs
RPHY MRTR-New-CHS-CIN Exfo-Switch2 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 |  | Active | EP
RPHY MRTR-New-CHS-CIN Exfo-Switch2 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY Metro Deployment POR20 |  |  | 1 | 2020-05-31 | 2020-08-15 |  | Active | Log | New | SN-0741 | Schedule Change | Approved | 2020-07-10 10:12 | RPHY Metro: Updates to POR based on Field inputs
RPHY MRTR-New-BTR-CIN-Exfo-Switch | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY Metro Initial Deployment POR19 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-06-15 | 2020-09-30 |  | Active | EP
RPHY MRTR-New-BTR-CIN-Exfo-Switch | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY Metro Initial Deployment POR19 |  |  | 1 | 2020-06-15 | 2020-08-31 |  | Active | Log | New | SN-0741 | Schedule Change | Approved | 2020-07-10 10:12 | RPHY Metro: Updates to POR based on Field inputs
RPHY MRTR-New-BTR-CIN-Exfo-Switch | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY Metro Initial Deployment POR19 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-06-15 | 2020-09-30 |  | Active | Log | Upd | SN-0881 | Schedule Change | Approved | 2020-08-28 10:07 | 1 Moving Pensacola Activation Date from August to September because of Firewall issues 2 Moving BTR dates from August to September because of Resource constraints in with BTR NF team
RPHY MRTR-New-OSNAP-CLR | SE | NOR | CLR | R PHY | R PHY SE NOR CLR Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-10-01 | 2020-12-31 |  | Active | EP
RPHY MRTR-New-OSNAP-CLR | SE | NOR | CLR | R PHY | R PHY SE NOR CLR Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-10-01 | 2020-12-31 |  | Active | Log | New | SN-0786 | Schedule Change | Approved | 2020-07-27 09:30 | 1 SE OSNAP for Metairie was approved last week in CR 726 2 This POR adds that EPS project created into the POR 3 Also updating OCML Chassis count for Omaha North as to align with the BOM
RPHY MRTR-Growth-MCY-CIN-RPA2-5110 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-12-01 | 2021-03-31 |  | Active | EP
RPHY MRTR-Growth-MCY-CIN-RPA2-5110 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-12-01 | 2021-03-31 |  | Active | Log | New | SN-0909 | Scope Change | Approved | 2020-09-25 14:21 | The Mid City OCML plan is for Q1 Jan delivery A forecasted analog split was re worked and designed to be a DNX action and that was not forecasted in 2020 So in order to support this change mid city would need an additional OCML rack by december This CR re
RPHY MRTR-New-MCY-CIN Exfo-Switch2 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-12-01 | 2021-03-31 |  | Active | EP
RPHY MRTR-New-MCY-CIN Exfo-Switch2 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-12-01 | 2021-03-31 |  | Active | Log | New | SN-0909 | Scope Change | Approved | 2020-09-25 14:21 | The Mid City OCML plan is for Q1 Jan delivery A forecasted analog split was re worked and designed to be a DNX action and that was not forecasted in 2020 So in order to support this change mid city would need an additional OCML rack by december This CR re
RPHY MRTR-New-MCY-CIN-ATX-OCML2 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-12-01 | 2021-03-31 |  | Active | EP
RPHY MRTR-New-MCY-CIN-ATX-OCML2 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-12-01 | 2021-03-31 |  | Active | Log | New | SN-0909 | Scope Change | Approved | 2020-09-25 14:21 | The Mid City OCML plan is for Q1 Jan delivery A forecasted analog split was re worked and designed to be a DNX action and that was not forecasted in 2020 So in order to support this change mid city would need an additional OCML rack by december This CR re
R PHY_CCAP_MFD_Grand_Master_Clocks_44119 | VA | NVA | MFD | R PHY CCAP | R PHY VA NVA MFD RPHY - CCAP Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2020-07-15 | 2020-10-01 |  | Active | EP
R PHY_CCAP_MFD_Grand_Master_Clocks_44119 | VA | NVA | MFD | R PHY CCAP | R PHY VA NVA MFD RPHY - CCAP Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2020-07-15 | 2020-10-01 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_MFD_Grand_Master_Clocks_44119 | VA | NVA | MFD | R PHY CCAP |  | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2020-07-15 | 2020-10-01 |  | Active | Log | New | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_CHU_D9485_43845 | CA | SAN | CHU | RSPD - CCAP | R PHY CA SAN CHU RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_CHU_D9485_43845 | CA | SAN | CHU | RSPD - CCAP | R PHY CA SAN CHU R PHY Metro Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | Log | Del | SN-0059 | New | Approved | 2020-02-06 10:24
R PHY_CCAP_CHU_D9485_43845 | CA | SAN | CHU | RSPD - CCAP | R PHY CA SAN CHU RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 2 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_CHU_D9485_43845 | CA | SAN | CHU | RSPD - CCAP | R PHY CA SAN CHU RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_DWN_D9485_43845 | CA | SAN | DWN | RSPD - CCAP | R PHY CA SAN DWN RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_DWN_D9485_43845 | CA | SAN | DWN | RSPD - CCAP | R PHY CA SAN DWN R PHY Metro Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | Log | Del | SN-0059 | New | Approved | 2020-02-06 10:24
R PHY_CCAP_DWN_D9485_43845 | CA | SAN | DWN | RSPD - CCAP | R PHY CA SAN DWN RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 2 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_DWN_D9485_43845 | CA | SAN | DWN | RSPD - CCAP | R PHY CA SAN DWN RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_ELC_D9485_43845 | CA | SAN | ELC | RSPD - CCAP | R PHY CA SAN ELC RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_ELC_D9485_43845 | CA | SAN | ELC | RSPD - CCAP | R PHY CA SAN ELC R PHY CCAP R PHY Metro Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 2 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_ELC_D9485_43845 | CA | SAN | ELC | RSPD - CCAP | R PHY CA SAN ELC RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 2 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | Upd | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_ELC_D9485_43845 | CA | SAN | ELC | RSPD - CCAP | R PHY CA SAN ELC RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_ESC_D9485_43845 | CA | SAN | ESC | RSPD - CCAP | R PHY CA SAN ESC RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_ESC_D9485_43845 | CA | SAN | ESC | RSPD - CCAP | R PHY CA SAN ESC QPSK Augment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_ESC_D9485_43845 | CA | SAN | ESC | RSPD - CCAP | R PHY CA SAN ESC RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | Upd | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_ESC_D9485_43845 | CA | SAN | ESC | RSPD - CCAP | R PHY CA SAN ESC RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_FED_D9485_43845 | CA | SAN | FED | RSPD - CCAP | R PHY CA SAN FED RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_FED_D9485_43845 | CA | SAN | FED | RSPD - CCAP | R PHY CA SAN FED QPSK Augment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 2 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_FED_D9485_43845 | CA | SAN | FED | RSPD - CCAP | R PHY CA SAN FED RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 2 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | Upd | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_FED_D9485_43845 | CA | SAN | FED | RSPD - CCAP | R PHY CA SAN FED RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_OCE_RPHY Unbundled Solution V2_43845 | CA | SAN | OCE | RSPD - CCAP | R PHY CA SAN OCE RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-01-15 | 2020-02-15 |  | Active | EP
R PHY_CCAP_OCE_RPHY Unbundled Solution V2_43845 | CA | SAN | OCE | RSPD - CCAP | R PHY CA SAN OCE QPSK Augment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-01-15 | 2020-02-15 |  | Active | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_OCE_RPHY Unbundled Solution V2_43845 | CA | SAN | OCE | RSPD - CCAP | R PHY CA SAN OCE RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-01-15 | 2020-02-15 |  | Active | Log | Upd | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_OCE_D9485_43845 | CA | SAN | OCE | RSPD - CCAP | R PHY CA SAN OCE RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_OCE_D9485_43845 | CA | SAN | OCE | RSPD - CCAP | R PHY CA SAN OCE QPSK Augment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_OCE_D9485_43845 | CA | SAN | OCE | RSPD - CCAP | R PHY CA SAN OCE RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | Upd | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_OCE_D9485_43845 | CA | SAN | OCE | RSPD - CCAP | R PHY CA SAN OCE RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PWY_D9485_43845 | CA | SAN | PWY | RSPD - CCAP | R PHY CA SAN PWY RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_PWY_D9485_43845 | CA | SAN | PWY | RSPD - CCAP | R PHY CA SAN PWY QPSK Augment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_PWY_D9485_43845 | CA | SAN | PWY | RSPD - CCAP | R PHY CA SAN PWY RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | Upd | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_PWY_D9485_43845 | CA | SAN | PWY | RSPD - CCAP | R PHY CA SAN PWY RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_VST_D9485_43845 | CA | SAN | VST | RSPD - CCAP | R PHY CA SAN VST RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_VST_D9485_43845 | CA | SAN | VST | RSPD - CCAP | R PHY CA SAN VST R PHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 2 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_VST_D9485_43845 | CA | SAN | VST | RSPD - CCAP | R PHY CA SAN VST RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 2 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | Upd | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_VST_D9485_43845 | CA | SAN | VST | RSPD - CCAP | R PHY CA SAN VST RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_BEL_D9485_43845 | SW | ARZ | BEL | RSPD - CCAP | R PHY SW ARZ BEL RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_BEL_D9485_43845 | SW | ARZ | BEL | RSPD - CCAP | R PHY SW ARZ BEL RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 3 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_BEL_D9485_43845 | SW | ARZ | BEL | RSPD - CCAP | R PHY SW ARZ BEL RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 3 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | Upd | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_BEL_D9485_43845 | SW | ARZ | BEL | RSPD - CCAP | R PHY SW ARZ BEL RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_BUK_RPHY Unbundled Solution V2_43845 | SW | ARZ | BUK | RSPD - CCAP | R PHY SW ARZ BUK RPHY CCAP Deployment POR20 | License | License Activation | 2 | 2020-01-15 | 2020-02-15 |  | Active | EP
R PHY_CCAP_BUK_RPHY Unbundled Solution V2_43845 | SW | ARZ | BUK | RSPD - CCAP | R PHY SW ARZ BUK QPSK Augment POR20 | License | License Activation | 2 | 2020-01-15 | 2020-02-15 |  | Active | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_BUK_RPHY Unbundled Solution V2_43845 | SW | ARZ | BUK | RSPD - CCAP | R PHY SW ARZ BUK RPHY CCAP Deployment POR20 | License | License Activation | 2 | 2020-01-15 | 2020-02-15 |  | Active | Log | Upd | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_BUK_D9485_43845 | SW | ARZ | BUK | RSPD - CCAP | R PHY SW ARZ BUK RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_BUK_D9485_43845 | SW | ARZ | BUK | RSPD - CCAP | R PHY SW ARZ BUK RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_BUK_D9485_43845 | SW | ARZ | BUK | RSPD - CCAP | R PHY SW ARZ BUK RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | Upd | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_BUK_D9485_43845 | SW | ARZ | BUK | RSPD - CCAP | R PHY SW ARZ BUK RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_CHD_D9485_43845 | SW | ARZ | CHD | RSPD - CCAP | R PHY SW ARZ CHD RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_CHD_D9485_43845 | SW | ARZ | CHD | RSPD - CCAP | R PHY SW ARZ CHD QPSK Augment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 2 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_CHD_D9485_43845 | SW | ARZ | CHD | RSPD - CCAP | R PHY SW ARZ CHD RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 2 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | Upd | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_CHD_D9485_43845 | SW | ARZ | CHD | RSPD - CCAP | R PHY SW ARZ CHD RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_CHD_RPHY Unbundled Solution V2_43845 | SW | ARZ | CHD | RSPD - CCAP | R PHY SW ARZ CHD RPHY CCAP Deployment POR20 | License | License Activation | 3 | 2020-01-15 | 2020-02-15 |  | Active | EP
R PHY_CCAP_CHD_RPHY Unbundled Solution V2_43845 | SW | ARZ | CHD | RSPD - CCAP | R PHY SW ARZ CHD QPSK Augment POR20 | License | License Activation | 3 | 2020-01-15 | 2020-02-15 |  | Active | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_CHD_RPHY Unbundled Solution V2_43845 | SW | ARZ | CHD | RSPD - CCAP | R PHY SW ARZ CHD RPHY CCAP Deployment POR20 | License | License Activation | 3 | 2020-01-15 | 2020-02-15 |  | Active | Log | Upd | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_FWL_RPHY Unbundled Solution V2_43845 | SW | ARZ | FWL | RSPD - CCAP | R PHY SW ARZ FWL RPHY CCAP Deployment POR20 | License | License Activation | 35 | 2020-01-15 | 2020-02-15 |  | Active | EP
R PHY_CCAP_FWL_RPHY Unbundled Solution V2_43845 | SW | ARZ | FWL | RSPD - CCAP | R PHY SW ARZ FWL QPSK Augment POR20 | License | License Activation | 35 | 2020-01-15 | 2020-02-15 |  | Active | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_FWL_RPHY Unbundled Solution V2_43845 | SW | ARZ | FWL | RSPD - CCAP | R PHY SW ARZ FWL RPHY CCAP Deployment POR20 | License | License Activation | 35 | 2020-01-15 | 2020-02-15 |  | Active | Log | Upd | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_FWL_D9485_43845 | SW | ARZ | FWL | RSPD - CCAP | R PHY SW ARZ FWL RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-02-15 | 2020-05-30 |  | Active | EP
R PHY_CCAP_FWL_D9485_43845 | SW | ARZ | FWL | RSPD - CCAP | R PHY SW ARZ FWL QPSK Augment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 3 | 2020-01-15 | 2020-02-15 |  | Active | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_FWL_D9485_43845 | SW | ARZ | FWL | RSPD - CCAP | R PHY SW ARZ FWL RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 3 | 2020-01-15 | 2020-02-15 |  | Active | Log | Upd | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_FWL_D9485_43845 | SW | ARZ | FWL | RSPD - CCAP | R PHY SW ARZ FWL RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-02-15 | 2020-05-30 |  | Active | Log | Upd | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_MCD_D9485_43845 | SW | ARZ | MCD | RSPD - CCAP | R PHY SW ARZ MCD RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_MCD_D9485_43845 | SW | ARZ | MCD | RSPD - CCAP | R PHY SW ARZ MCD QPSK Augment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_MCD_D9485_43845 | SW | ARZ | MCD | RSPD - CCAP | R PHY SW ARZ MCD RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | Upd | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_MCD_D9485_43845 | SW | ARZ | MCD | RSPD - CCAP | R PHY SW ARZ MCD RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_MCD_RPHY Unbundled Solution V2_43845 | SW | ARZ | MCD | RSPD - CCAP | R PHY SW ARZ MCD RPHY CCAP Deployment POR20 | License | License Activation | 4 | 2020-01-15 | 2020-02-15 |  | Active | EP
R PHY_CCAP_MCD_RPHY Unbundled Solution V2_43845 | SW | ARZ | MCD | RSPD - CCAP | R PHY SW ARZ MCD QPSK Augment POR20 | License | License Activation | 4 | 2020-01-15 | 2020-02-15 |  | Active | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_MCD_RPHY Unbundled Solution V2_43845 | SW | ARZ | MCD | RSPD - CCAP | R PHY SW ARZ MCD RPHY CCAP Deployment POR20 | License | License Activation | 4 | 2020-01-15 | 2020-02-15 |  | Active | Log | Upd | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_MSA_RPHY Unbundled Solution V2_43845 | SW | ARZ | MSA | RSPD - CCAP | R PHY SW ARZ MSA RPHY CCAP Deployment POR20 | License | License Activation | 36 | 2020-01-15 | 2020-02-15 |  | Active | EP
R PHY_CCAP_MSA_RPHY Unbundled Solution V2_43845 | SW | ARZ | MSA | RSPD - CCAP | R PHY SW ARZ MSA R PHY Metro Deployment POR20 | License | License Activation |  |  |  |  | Active | Log | Del | SN-0059 | New | Approved | 2020-02-06 10:24
R PHY_CCAP_MSA_RPHY Unbundled Solution V2_43845 | SW | ARZ | MSA | RSPD - CCAP | R PHY SW ARZ MSA RPHY CCAP Deployment POR20 | License | License Activation | 36 | 2020-01-15 | 2020-02-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_MSA_D9485_43845 | SW | ARZ | MSA | RSPD - CCAP | R PHY SW ARZ MSA RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-02-15 | 2020-05-30 |  | Active | EP
R PHY_CCAP_MSA_D9485_43845 | SW | ARZ | MSA | RSPD - CCAP | R PHY SW ARZ MSA R PHY Metro Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Active | Log | Del | SN-0059 | New | Approved | 2020-02-06 10:24
R PHY_CCAP_MSA_D9485_43845 | SW | ARZ | MSA | RSPD - CCAP | R PHY SW ARZ MSA RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 4 | 2020-01-15 | 2020-02-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_MSA_D9485_43845 | SW | ARZ | MSA | RSPD - CCAP | R PHY SW ARZ MSA RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-02-15 | 2020-05-30 |  | Active | Log | Upd | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_NSC_RPHY Unbundled Solution V2_43845 | SW | ARZ | NSC | RSPD - CCAP | R PHY SW ARZ NSC RPHY CCAP Deployment POR20 | License | License Activation | 3 | 2020-01-15 | 2020-02-15 |  | Active | EP
R PHY_CCAP_NSC_RPHY Unbundled Solution V2_43845 | SW | ARZ | NSC | RSPD - CCAP | R PHY SW ARZ NSC QPSK Augment POR20 | License | License Activation | 3 | 2020-01-15 | 2020-02-15 |  | Active | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_NSC_RPHY Unbundled Solution V2_43845 | SW | ARZ | NSC | RSPD - CCAP | R PHY SW ARZ NSC RPHY CCAP Deployment POR20 | License | License Activation | 3 | 2020-01-15 | 2020-02-15 |  | Active | Log | Upd | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_NSC_D9485_43845 | SW | ARZ | NSC | RSPD - CCAP | R PHY SW ARZ NSC RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_NSC_D9485_43845 | SW | ARZ | NSC | RSPD - CCAP | R PHY SW ARZ NSC QPSK Augment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_NSC_D9485_43845 | SW | ARZ | NSC | RSPD - CCAP | R PHY SW ARZ NSC RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | Upd | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_NSC_D9485_43845 | SW | ARZ | NSC | RSPD - CCAP | R PHY SW ARZ NSC RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PEO_D9485_43845 | SW | ARZ | PEO | RSPD - CCAP | R PHY SW ARZ PEO RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_PEO_D9485_43845 | SW | ARZ | PEO | RSPD - CCAP | R PHY SW ARZ PEO R PHY Metro Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | Log | Del | SN-0059 | New | Approved | 2020-02-06 10:24
R PHY_CCAP_PEO_D9485_43845 | SW | ARZ | PEO | RSPD - CCAP | R PHY SW ARZ PEO RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 2 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_PEO_D9485_43845 | SW | ARZ | PEO | RSPD - CCAP | R PHY SW ARZ PEO RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PEO_RPHY Unbundled Solution V2_43845 | SW | ARZ | PEO | RSPD - CCAP | R PHY SW ARZ PEO RPHY CCAP Deployment POR20 | License | License Activation | 15 | 2020-01-15 | 2020-02-15 |  | Active | EP
R PHY_CCAP_PEO_RPHY Unbundled Solution V2_43845 | SW | ARZ | PEO | RSPD - CCAP | R PHY SW ARZ PEO R PHY Metro Deployment POR20 | License | License Activation |  |  |  |  | Active | Log | Del | SN-0059 | New | Approved | 2020-02-06 10:24
R PHY_CCAP_PEO_RPHY Unbundled Solution V2_43845 | SW | ARZ | PEO | RSPD - CCAP | R PHY SW ARZ PEO RPHY CCAP Deployment POR20 | License | License Activation | 15 | 2020-01-15 | 2020-02-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_PNL_RPHY Unbundled Solution V2_43845 | SW | ARZ | PNL | RSPD - CCAP | R PHY SW ARZ PNL RPHY CCAP Deployment POR20 | License | License Activation | 3 | 2020-01-15 | 2020-02-15 |  | Active | EP
R PHY_CCAP_PNL_RPHY Unbundled Solution V2_43845 | SW | ARZ | PNL | RSPD - CCAP | R PHY SW ARZ PNL QPSK Augment POR20 | License | License Activation | 3 | 2020-01-15 | 2020-02-15 |  | Active | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_PNL_RPHY Unbundled Solution V2_43845 | SW | ARZ | PNL | RSPD - CCAP | R PHY SW ARZ PNL RPHY CCAP Deployment POR20 | License | License Activation | 3 | 2020-01-15 | 2020-02-15 |  | Active | Log | Upd | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_PNL_D9485_43845 | SW | ARZ | PNL | RSPD - CCAP | R PHY SW ARZ PNL RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_PNL_D9485_43845 | SW | ARZ | PNL | RSPD - CCAP | R PHY SW ARZ PNL QPSK Augment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_PNL_D9485_43845 | SW | ARZ | PNL | RSPD - CCAP | R PHY SW ARZ PNL RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | Upd | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_PNL_D9485_43845 | SW | ARZ | PNL | RSPD - CCAP | R PHY SW ARZ PNL RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_SSC_D9485_43845 | SW | ARZ | SSC | RSPD - CCAP | R PHY SW ARZ SSC RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_SSC_D9485_43845 | SW | ARZ | SSC | RSPD - CCAP | R PHY SW ARZ SSC QPSK Augment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 2 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_SSC_D9485_43845 | SW | ARZ | SSC | RSPD - CCAP | R PHY SW ARZ SSC RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 2 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | Upd | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_SSC_D9485_43845 | SW | ARZ | SSC | RSPD - CCAP | R PHY SW ARZ SSC RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_SSC_RPHY Unbundled Solution V2_43845 | SW | ARZ | SSC | RSPD - CCAP | R PHY SW ARZ SSC RPHY CCAP Deployment POR20 | License | License Activation | 26 | 2020-01-15 | 2020-02-15 |  | Active | EP
R PHY_CCAP_SSC_RPHY Unbundled Solution V2_43845 | SW | ARZ | SSC | RSPD - CCAP | R PHY SW ARZ SSC QPSK Augment POR20 | License | License Activation | 26 | 2020-01-15 | 2020-02-15 |  | Active | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_SSC_RPHY Unbundled Solution V2_43845 | SW | ARZ | SSC | RSPD - CCAP | R PHY SW ARZ SSC RPHY CCAP Deployment POR20 | License | License Activation | 26 | 2020-01-15 | 2020-02-15 |  | Active | Log | Upd | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_TUC_RPHY Unbundled Solution V2_43845 | SW | ARZ | TUC | RSPD - CCAP | R PHY SW ARZ TUC RPHY CCAP Deployment POR20 | License | License Activation | 8 | 2020-01-15 | 2020-02-15 |  | Active | EP
R PHY_CCAP_TUC_RPHY Unbundled Solution V2_43845 | SW | ARZ | TUC | RSPD - CCAP | R PHY SW ARZ TUC QPSK Augment POR20 | License | License Activation | 8 | 2020-01-15 | 2020-02-15 |  | Active | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_TUC_RPHY Unbundled Solution V2_43845 | SW | ARZ | TUC | RSPD - CCAP | R PHY SW ARZ TUC RPHY CCAP Deployment POR20 | License | License Activation | 8 | 2020-01-15 | 2020-02-15 |  | Active | Log | Upd | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_TUC_D9485_43845 | SW | ARZ | TUC | RSPD - CCAP | R PHY SW ARZ TUC RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_TUC_D9485_43845 | SW | ARZ | TUC | RSPD - CCAP | R PHY SW ARZ TUC QPSK Augment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 2 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_TUC_D9485_43845 | SW | ARZ | TUC | RSPD - CCAP | R PHY SW ARZ TUC RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 2 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | Upd | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_TUC_D9485_43845 | SW | ARZ | TUC | RSPD - CCAP | R PHY SW ARZ TUC RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_ALI_RPHY Unbundled Solution V2_43845 | SW | LAS | ALI | RSPD - CCAP | R PHY SW LAS ALI RPHY CCAP Deployment POR20 | License | License Activation | 3 | 2020-01-15 | 2020-02-15 |  | Active | EP
R PHY_CCAP_ALI_RPHY Unbundled Solution V2_43845 | SW | LAS | ALI | RSPD - CCAP | R PHY SW LAS ALI QPSK CIN Enablement Augment POR20 | License | License Activation | 3 | 2020-01-15 | 2020-02-15 |  | Active | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_ALI_RPHY Unbundled Solution V2_43845 | SW | LAS | ALI | RSPD - CCAP | R PHY SW LAS ALI RPHY CCAP Deployment POR20 | License | License Activation | 3 | 2020-01-15 | 2020-02-15 |  | Active | Log | Upd | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_ALI_D9485_43845 | SW | LAS | ALI | RSPD - CCAP | R PHY SW LAS ALI RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_ALI_D9485_43845 | SW | LAS | ALI | RSPD - CCAP | R PHY SW LAS ALI QPSK CIN Enablement Augment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_ALI_D9485_43845 | SW | LAS | ALI | RSPD - CCAP | R PHY SW LAS ALI RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | Upd | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_ALI_D9485_43845 | SW | LAS | ALI | RSPD - CCAP | R PHY SW LAS ALI RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_BLU_D9485_43845 | SW | LAS | BLU | RSPD - CCAP | R PHY SW LAS BLU RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_BLU_D9485_43845 | SW | LAS | BLU | RSPD - CCAP | R PHY SW LAS BLU R PHY Metro Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | Log | Del | SN-0059 | New | Approved | 2020-02-06 10:24
R PHY_CCAP_BLU_D9485_43845 | SW | LAS | BLU | RSPD - CCAP | R PHY SW LAS BLU RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 2 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_BLU_D9485_43845 | SW | LAS | BLU | RSPD - CCAP | R PHY SW LAS BLU RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_BLU_RPHY Unbundled Solution V2_43845 | SW | LAS | BLU | RSPD - CCAP | R PHY SW LAS BLU RPHY CCAP Deployment POR20 | License | License Activation | 20 | 2020-01-15 | 2020-02-15 |  | Active | EP
R PHY_CCAP_BLU_RPHY Unbundled Solution V2_43845 | SW | LAS | BLU | RSPD - CCAP | R PHY SW LAS BLU R PHY Metro Deployment POR20 | License | License Activation |  |  |  |  | Active | Log | Del | SN-0059 | New | Approved | 2020-02-06 10:24
R PHY_CCAP_BLU_RPHY Unbundled Solution V2_43845 | SW | LAS | BLU | RSPD - CCAP | R PHY SW LAS BLU RPHY CCAP Deployment POR20 | License | License Activation | 20 | 2020-01-15 | 2020-02-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_ERN_RPHY Unbundled Solution V2_43845 | SW | LAS | ERN | RSPD - CCAP | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | License | License Activation | 9 | 2020-01-15 | 2020-02-15 |  | Active | EP
R PHY_CCAP_ERN_RPHY Unbundled Solution V2_43845 | SW | LAS | ERN | RSPD - CCAP | R PHY SW LAS ERN QPSK Augment POR20 | License | License Activation | 9 | 2020-01-15 | 2020-02-15 |  | Active | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_ERN_RPHY Unbundled Solution V2_43845 | SW | LAS | ERN | RSPD - CCAP | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | License | License Activation | 9 | 2020-01-15 | 2020-02-15 |  | Active | Log | Upd | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_ERN_D9485_43845 | SW | LAS | ERN | RSPD - CCAP | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_ERN_D9485_43845 | SW | LAS | ERN | RSPD - CCAP | R PHY SW LAS ERN QPSK Augment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 2 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_ERN_D9485_43845 | SW | LAS | ERN | RSPD - CCAP | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 2 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | Upd | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_ERN_D9485_43845 | SW | LAS | ERN | RSPD - CCAP | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_HEN_D9485_43845 | SW | LAS | HEN | RSPD - CCAP | R PHY SW LAS HEN RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-02-15 | 2020-05-30 |  | Active | EP
R PHY_CCAP_HEN_D9485_43845 | SW | LAS | HEN | RSPD - CCAP | R PHY SW LAS HEN R PHY Metro Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Active | Log | Del | SN-0059 | New | Approved | 2020-02-06 10:24
R PHY_CCAP_HEN_D9485_43845 | SW | LAS | HEN | RSPD - CCAP | R PHY SW LAS HEN RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 5 | 2020-01-15 | 2020-02-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_HEN_D9485_43845 | SW | LAS | HEN | RSPD - CCAP | R PHY SW LAS HEN RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-02-15 | 2020-05-30 |  | Active | Log | Upd | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_HEN_RPHY Unbundled Solution V2_43845 | SW | LAS | HEN | RSPD - CCAP | R PHY SW LAS HEN RPHY CCAP Deployment POR20 | License | License Activation | 80 | 2020-01-15 | 2020-02-15 |  | Active | EP
R PHY_CCAP_HEN_RPHY Unbundled Solution V2_43845 | SW | LAS | HEN | RSPD - CCAP | R PHY SW LAS HEN R PHY Metro Deployment POR20 | License | License Activation |  |  |  |  | Active | Log | Del | SN-0059 | New | Approved | 2020-02-06 10:24
R PHY_CCAP_HEN_RPHY Unbundled Solution V2_43845 | SW | LAS | HEN | RSPD - CCAP | R PHY SW LAS HEN RPHY CCAP Deployment POR20 | License | License Activation | 80 | 2020-01-15 | 2020-02-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_TEN_D9485_43845 | SW | LAS | TEN | RSPD - CCAP | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_TEN_D9485_43845 | SW | LAS | TEN | RSPD - CCAP | R PHY SW LAS TEN R PHY Metro Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | Log | Del | SN-0059 | New | Approved | 2020-02-06 10:24
R PHY_CCAP_TEN_D9485_43845 | SW | LAS | TEN | RSPD - CCAP | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 6 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_TEN_D9485_43845 | SW | LAS | TEN | RSPD - CCAP | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_TEN_RPHY Unbundled Solution V2_43845 | SW | LAS | TEN | RSPD - CCAP | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 6 | 2020-01-15 | 2020-02-15 |  | Active | EP
R PHY_CCAP_TEN_RPHY Unbundled Solution V2_43845 | SW | LAS | TEN | RSPD - CCAP | R PHY SW LAS TEN R PHY Metro Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Active | Log | Del | SN-0059 | New | Approved | 2020-02-06 10:24
R PHY_CCAP_TEN_RPHY Unbundled Solution V2_43845 | SW | LAS | TEN | RSPD - CCAP | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 6 | 2020-01-15 | 2020-02-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_VLY_RPHY Unbundled Solution V2_43845 | SW | LAS | VLY | RSPD - CCAP | R PHY SW LAS VLY RPHY CCAP Deployment POR20 | License | License Activation | 7 | 2020-01-15 | 2020-02-15 |  | Active | EP
R PHY_CCAP_VLY_RPHY Unbundled Solution V2_43845 | SW | LAS | VLY | RSPD - CCAP | R PHY SW LAS VLY QPSK Augment POR20 | License | License Activation | 7 | 2020-01-15 | 2020-02-15 |  | Active | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_VLY_RPHY Unbundled Solution V2_43845 | SW | LAS | VLY | RSPD - CCAP | R PHY SW LAS VLY RPHY CCAP Deployment POR20 | License | License Activation | 7 | 2020-01-15 | 2020-02-15 |  | Active | Log | Upd | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_VLY_D9485_43845 | SW | LAS | VLY | RSPD - CCAP | R PHY SW LAS VLY RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_VLY_D9485_43845 | SW | LAS | VLY | RSPD - CCAP | R PHY SW LAS VLY QPSK Augment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_VLY_D9485_43845 | SW | LAS | VLY | RSPD - CCAP | R PHY SW LAS VLY RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-01-15 | 2020-02-15 |  | Deleted | Log | Upd | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_VLY_D9485_43845 | SW | LAS | VLY | RSPD - CCAP | R PHY SW LAS VLY RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_SAB_Boundary_Clocks_43936 | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-04-15 | 2020-10-31 |  | Active | EP
R PHY_CCAP_SAB_Boundary_Clocks_43936 | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-07-01 | 2020-10-01 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_SAB_Boundary_Clocks_43936 | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-04-15 | 2020-07-15 |  | Active | Log | Upd | SN-0263 | Schedule Change | Approved | 2020-02-21 16:27 | Requesting Santa Barabara and Warner Robins to be accelerated into Q2 due to the following reasons Santa Barbara - To move the nodes from existing 10Ks to RPHY to alleviate the node conjestion Warner Robins - This is to get the site RPHY Ready for the
R PHY_CCAP_SAB_Boundary_Clocks_43936 | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-04-15 | 2020-10-31 |  | Active | Log | Upd | SN-0637 | Schedule Change | Approved | 2020-06-05 14:50 | RPHY CCAP POR Update
R PHY_CCAP_STB_D9485_43936 | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-02-15 | 2020-10-31 |  | Active | EP
R PHY_CCAP_STB_D9485_43936 | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-07-01 | 2020-10-01 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_STB_D9485_43936 | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-02-15 | 2020-08-15 |  | Active | Log | Upd | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_STB_D9485_43936 | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-02-15 | 2020-10-31 |  | Active | Log | Upd | SN-0637 | Schedule Change | Approved | 2020-06-05 14:50 | RPHY CCAP POR Update
R PHY_CCAP_SAB_Grand_Master_Clocks_43936 | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2020-04-15 | 2020-10-31 |  | Active | EP
R PHY_CCAP_SAB_Grand_Master_Clocks_43936 | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2020-07-01 | 2020-10-01 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_SAB_Grand_Master_Clocks_43936 | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2020-04-15 | 2020-07-15 |  | Active | Log | Upd | SN-0263 | Schedule Change | Approved | 2020-02-21 16:27 | Requesting Santa Barabara and Warner Robins to be accelerated into Q2 due to the following reasons Santa Barbara - To move the nodes from existing 10Ks to RPHY to alleviate the node conjestion Warner Robins - This is to get the site RPHY Ready for the
R PHY_CCAP_SAB_Grand_Master_Clocks_43936 | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2020-04-15 | 2020-10-31 |  | Active | Log | Upd | SN-0637 | Schedule Change | Approved | 2020-06-05 14:50 | RPHY CCAP POR Update
R PHY_CCAP_SAB_RPHY Unbundled Solution V2_43939 | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | EP
R PHY_CCAP_SAB_RPHY Unbundled Solution V2_43939 | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-07-01 | 2020-10-01 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_SAB_RPHY Unbundled Solution V2_43939 | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_SAB_RPHY Unbundled Solution V2_44119 | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | EP
R PHY_CCAP_SAB_RPHY Unbundled Solution V2_44119 | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_SAB_RPHY Unbundled Solution V2_44119 | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_SAB_RPHY Bundled Solution V3_43966 | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 3 | 2020-05-27 | 2020-10-31 | 2020-10-31 | Active | EP
R PHY_CCAP_SAB_RPHY Bundled Solution V3_43966 | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 3 | 2020-07-01 | 2020-10-01 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_SAB_RPHY Bundled Solution V3_43966 | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 3 | 2020-04-15 | 2020-07-15 |  | Active | Log | Upd | SN-0263 | Schedule Change | Approved | 2020-02-21 16:27 | Requesting Santa Barabara and Warner Robins to be accelerated into Q2 due to the following reasons Santa Barbara - To move the nodes from existing 10Ks to RPHY to alleviate the node conjestion Warner Robins - This is to get the site RPHY Ready for the
R PHY_CCAP_SAB_RPHY Bundled Solution V3_43966 | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 3 | 2020-05-27 | 2020-07-30 | 2020-07-30 | Active | Log | Upd | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_SAB_RPHY Bundled Solution V3_43966 | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 3 | 2020-05-27 | 2020-10-31 | 2020-10-31 | Active | Log | Upd | SN-0637 | Schedule Change | Approved | 2020-06-05 14:50 | RPHY CCAP POR Update
R PHY_CCAP_SAB_RPHY Bundled Solution V3_44027 | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_SAB_RPHY Bundled Solution V3_44027 | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-07-01 | 2020-10-01 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_SAB_RPHY Bundled Solution V3_44027 | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_SAB_RPHY Bundled Solution V3_44027 | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-10-15 | 2020-12-31 |  | Deleted | Log | Undel | SN-0811 | Schedule Change | Approved | 2020-08-07 09:40 | This is to update RPHY CCAP POR for CLR WRB SAB and PNS sites
R PHY_CCAP_SAB_RPHY Bundled Solution V3_44027 | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0899 | Schedule Change | Approved | 2020-09-11 09:34 | RPHY CCAP actiation date updates for Fort Smith and Abbeville sites Material delivery date update for CLV FTS RSM BLU and HEN facilites
R PHY_CCAP_AVJ_RPHY Unbundled Solution V2_44027 | CA | ORG | AVJ | RSPD - CCAP | R PHY CA ORG AVJ RPHY CCAP Augment POR20 | License | License Activation | 621 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_AVJ_RPHY Unbundled Solution V2_44027 | CA | ORG | AVJ | RSPD - CCAP | R PHY CA ORG AVJ RPHY CCAP Augment POR20 | License | License Activation | 660 | 2020-07-15 | 2020-08-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_AVJ_RPHY Unbundled Solution V2_44027 | CA | ORG | AVJ | RSPD - CCAP | R PHY CA ORG AVJ RPHY CCAP Augment POR20 | License | License Activation | 621 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_AVJ_RPHY Unbundled Solution V2_44119 | CA | ORG | AVJ | RSPD - CCAP | R PHY CA ORG AVJ RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_AVJ_RPHY Unbundled Solution V2_44119 | CA | ORG | AVJ | RSPD - CCAP | R PHY CA ORG AVJ RPHY CCAP Augment POR20 | License | License Activation | 1144 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_AVJ_RPHY Unbundled Solution V2_44119 | CA | ORG | AVJ | RSPD - CCAP | R PHY CA ORG AVJ RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_DNP_RPHY Unbundled Solution V2_44027 | CA | ORG | DNP | RSPD - CCAP | R PHY CA ORG DNP RPHY CCAP Augment POR20 | License | License Activation | 621 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_DNP_RPHY Unbundled Solution V2_44027 | CA | ORG | DNP | RSPD - CCAP | R PHY CA ORG DNP RPHY CCAP Augment POR20 | License | License Activation | 572 | 2020-07-15 | 2020-08-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_DNP_RPHY Unbundled Solution V2_44027 | CA | ORG | DNP | RSPD - CCAP | R PHY CA ORG DNP RPHY CCAP Augment POR20 | License | License Activation | 621 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_DNP_RPHY Unbundled Solution V2_44119 | CA | ORG | DNP | RSPD - CCAP | R PHY CA ORG DNP RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_DNP_RPHY Unbundled Solution V2_44119 | CA | ORG | DNP | RSPD - CCAP | R PHY CA ORG DNP RPHY CCAP Augment POR20 | License | License Activation | 616 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_DNP_RPHY Unbundled Solution V2_44119 | CA | ORG | DNP | RSPD - CCAP | R PHY CA ORG DNP RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_IRV_RPHY Unbundled Solution V2_44027 | CA | ORG | IRV | RSPD - CCAP | R PHY CA ORG IRV RPHY CCAP Augment POR20 | License | License Activation | 552 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_IRV_RPHY Unbundled Solution V2_44027 | CA | ORG | IRV | RSPD - CCAP | R PHY CA ORG IRV RPHY CCAP Augment POR20 | License | License Activation | 440 | 2020-07-15 | 2020-08-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_IRV_RPHY Unbundled Solution V2_44027 | CA | ORG | IRV | RSPD - CCAP | R PHY CA ORG IRV RPHY CCAP Augment POR20 | License | License Activation | 552 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_IRV_RPHY Unbundled Solution V2_44119 | CA | ORG | IRV | RSPD - CCAP | R PHY CA ORG IRV RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_IRV_RPHY Unbundled Solution V2_44119 | CA | ORG | IRV | RSPD - CCAP | R PHY CA ORG IRV RPHY CCAP Augment POR20 | License | License Activation | 704 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_IRV_RPHY Unbundled Solution V2_44119 | CA | ORG | IRV | RSPD - CCAP | R PHY CA ORG IRV RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_ORG_RPHY Unbundled Solution V2_44027 | CA | ORG | ORG | RSPD - CCAP | R PHY CA ORG ORG RPHY CCAP Augment POR20 | License | License Activation | 1035 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_ORG_RPHY Unbundled Solution V2_44027 | CA | ORG | ORG | RSPD - CCAP | R PHY CA ORG ORG RPHY CCAP Augment POR20 | License | License Activation | 704 | 2020-07-15 | 2020-08-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_ORG_RPHY Unbundled Solution V2_44027 | CA | ORG | ORG | RSPD - CCAP | R PHY CA ORG ORG RPHY CCAP Augment POR20 | License | License Activation | 1035 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_ORG_RPHY Unbundled Solution V2_44119 | CA | ORG | ORG | RSPD - CCAP | R PHY CA ORG ORG RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_ORG_RPHY Unbundled Solution V2_44119 | CA | ORG | ORG | RSPD - CCAP | R PHY CA ORG ORG RPHY CCAP Augment POR20 | License | License Activation | 748 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_ORG_RPHY Unbundled Solution V2_44119 | CA | ORG | ORG | RSPD - CCAP | R PHY CA ORG ORG RPHY CCAP Augment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PAV_RPHY Unbundled Solution V2_44027 | CA | ORG | PAV | RSPD - CCAP | R PHY CA ORG PAV RPHY CCAP Augment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | EP
R PHY_CCAP_PAV_RPHY Unbundled Solution V2_44027 | CA | ORG | PAV | RSPD - CCAP | R PHY CA ORG PAV RPHY CCAP Augment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-07-15 | 2020-08-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_PAV_RPHY Unbundled Solution V2_44027 | CA | ORG | PAV | RSPD - CCAP | R PHY CA ORG PAV RPHY CCAP Augment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PAV_RPHY Unbundled Solution V2_44119 | CA | ORG | PAV | RSPD - CCAP | R PHY CA ORG PAV RPHY CCAP Augment POR20 | License | License Activation | 345 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_PAV_RPHY Unbundled Solution V2_44119 | CA | ORG | PAV | RSPD - CCAP | R PHY CA ORG PAV RPHY CCAP Augment POR20 | License | License Activation | 88 | 2020-10-15 | 2020-11-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_PAV_RPHY Unbundled Solution V2_44119 | CA | ORG | PAV | RSPD - CCAP | R PHY CA ORG PAV RPHY CCAP Augment POR20 | License | License Activation | 345 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_ALI_RPHY Bundled Solution V3_44027 | SW | LAS | ALI | RSPD - CCAP | R PHY SW LAS ALI RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-07-15 | 2020-10-15 | 2020-10-15 | Active | EP
R PHY_CCAP_ALI_RPHY Bundled Solution V3_44027 | SW | LAS | ALI | RSPD - CCAP | R PHY SW LAS ALI RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-07-15 | 2020-08-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_ALI_RPHY Bundled Solution V3_44027 | SW | LAS | ALI | RSPD - CCAP | R PHY SW LAS ALI RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-07-15 | 2020-10-15 | 2020-10-15 | Active | Log | Upd | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_RSM_RPHY Unbundled Solution V2_43936 | CA | ORG | RSM | RSPD - CCAP | R PHY CA ORG RSM RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 2 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_RSM_RPHY Unbundled Solution V2_43936 | CA | ORG | RSM | RSPD - CCAP | R PHY CA ORG RSM RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-04-15 | 2020-05-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_RSM_RPHY Unbundled Solution V2_43936 | CA | ORG | RSM | RSPD - CCAP | R PHY CA ORG RSM RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 2 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_RSM_RPHY Unbundled Solution V2_44027 | CA | ORG | RSM | RSPD - CCAP | R PHY CA ORG RSM RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | EP
R PHY_CCAP_RSM_RPHY Unbundled Solution V2_44027 | CA | ORG | RSM | RSPD - CCAP | R PHY CA ORG RSM RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 2 | 2020-07-15 | 2020-08-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_RSM_RPHY Unbundled Solution V2_44027 | CA | ORG | RSM | RSPD - CCAP | R PHY CA ORG RSM RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-07-15 | 2020-08-15 |  | Deleted | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_RSM_RPHY Unbundled Solution V2_44027 | CA | ORG | RSM | RSPD - CCAP | R PHY CA ORG RSM RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_CHU_RPHY Unbundled Solution V2_44027 | CA | SAN | CHU | RSPD - CCAP | R PHY CA SAN CHU RPHY CCAP Deployment POR20 | License | License Activation | 690 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_CHU_RPHY Unbundled Solution V2_44027 | CA | SAN | CHU | RSPD - CCAP | R PHY CA SAN CHU RPHY CCAP Deployment POR20 | License | License Activation | 1364 | 2020-07-15 | 2020-08-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_CHU_RPHY Unbundled Solution V2_44027 | CA | SAN | CHU | RSPD - CCAP | R PHY CA SAN CHU RPHY CCAP Deployment POR20 | License | License Activation | 690 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_CHU_RPHY Unbundled Solution V2_44119 | CA | SAN | CHU | RSPD - CCAP | R PHY CA SAN CHU RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_CHU_RPHY Unbundled Solution V2_44119 | CA | SAN | CHU | RSPD - CCAP | R PHY CA SAN CHU RPHY CCAP Deployment POR20 | License | License Activation | 1364 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_CHU_RPHY Unbundled Solution V2_44119 | CA | SAN | CHU | RSPD - CCAP | R PHY CA SAN CHU RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_DWN_RPHY Unbundled Solution V2_44027 | CA | SAN | DWN | RSPD - CCAP | R PHY CA SAN DWN RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | EP
R PHY_CCAP_DWN_RPHY Unbundled Solution V2_44027 | CA | SAN | DWN | RSPD - CCAP | R PHY CA SAN DWN RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-07-15 | 2020-08-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_DWN_RPHY Unbundled Solution V2_44027 | CA | SAN | DWN | RSPD - CCAP | R PHY CA SAN DWN RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 414 | 2020-04-15 | 2020-05-15 |  | Deleted | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_DWN_RPHY Unbundled Solution V2_44027 | CA | SAN | DWN | RSPD - CCAP | R PHY CA SAN DWN RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_DWN_RPHY Unbundled Solution V2_44119 | CA | SAN | DWN | RSPD - CCAP | R PHY CA SAN DWN RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | EP
R PHY_CCAP_DWN_RPHY Unbundled Solution V2_44119 | CA | SAN | DWN | RSPD - CCAP | R PHY CA SAN DWN RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_DWN_RPHY Unbundled Solution V2_44119 | CA | SAN | DWN | RSPD - CCAP | R PHY CA SAN DWN RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_BEL_RPHY Bundled Solution V3_44119 | SW | ARZ | BEL | RSPD - CCAP | R PHY SW ARZ BEL RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_BEL_RPHY Bundled Solution V3_44119 | SW | ARZ | BEL | RSPD - CCAP | R PHY SW ARZ BEL RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-09-15 | 2020-11-01 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_BEL_RPHY Bundled Solution V3_44119 | SW | ARZ | BEL | RSPD - CCAP | R PHY SW ARZ BEL RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_ELC_RPHY Unbundled Solution V2_44027 | CA | SAN | ELC | RSPD - CCAP | R PHY CA SAN ELC RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 2 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_ELC_RPHY Unbundled Solution V2_44027 | CA | SAN | ELC | RSPD - CCAP | R PHY CA SAN ELC RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 2 | 2020-07-15 | 2020-08-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_ELC_RPHY Unbundled Solution V2_44027 | CA | SAN | ELC | RSPD - CCAP | R PHY CA SAN ELC RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 2 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | Upd | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_ELC_RPHY Unbundled Solution V2_44119 | CA | SAN | ELC | RSPD - CCAP | R PHY CA SAN ELC RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | EP
R PHY_CCAP_ELC_RPHY Unbundled Solution V2_44119 | CA | SAN | ELC | RSPD - CCAP | R PHY CA SAN ELC RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 3 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_ELC_RPHY Unbundled Solution V2_44119 | CA | SAN | ELC | RSPD - CCAP | R PHY CA SAN ELC RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_ESC_RPHY Unbundled Solution V2_44027 | CA | SAN | ESC | RSPD - CCAP | R PHY CA SAN ESC RPHY CCAP Deployment POR20 | License | License Activation | 69 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_ESC_RPHY Unbundled Solution V2_44027 | CA | SAN | ESC | RSPD - CCAP | R PHY CA SAN ESC RPHY CCAP Deployment POR20 | License | License Activation | 44 | 2020-07-15 | 2020-08-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_ESC_RPHY Unbundled Solution V2_44027 | CA | SAN | ESC | RSPD - CCAP | R PHY CA SAN ESC RPHY CCAP Deployment POR20 | License | License Activation | 69 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_ESC_RPHY Unbundled Solution V2_44119 | CA | SAN | ESC | RSPD - CCAP | R PHY CA SAN ESC RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_ESC_RPHY Unbundled Solution V2_44119 | CA | SAN | ESC | RSPD - CCAP | R PHY CA SAN ESC RPHY CCAP Deployment POR20 | License | License Activation | 177 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_ESC_RPHY Unbundled Solution V2_44119 | CA | SAN | ESC | RSPD - CCAP | R PHY CA SAN ESC RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_FED_RPHY Unbundled Solution V2_44027 | CA | SAN | FED | RSPD - CCAP | R PHY CA SAN FED RPHY CCAP Deployment POR20 | License | License Activation | 690 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_FED_RPHY Unbundled Solution V2_44027 | CA | SAN | FED | RSPD - CCAP | R PHY CA SAN FED RPHY CCAP Deployment POR20 | License | License Activation | 704 | 2020-07-15 | 2020-08-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_FED_RPHY Unbundled Solution V2_44027 | CA | SAN | FED | RSPD - CCAP | R PHY CA SAN FED RPHY CCAP Deployment POR20 | License | License Activation | 690 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_FED_RPHY Unbundled Solution V2_44119 | CA | SAN | FED | RSPD - CCAP | R PHY CA SAN FED RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_FED_RPHY Unbundled Solution V2_44119 | CA | SAN | FED | RSPD - CCAP | R PHY CA SAN FED RPHY CCAP Deployment POR20 | License | License Activation | 1554 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_FED_RPHY Unbundled Solution V2_44119 | CA | SAN | FED | RSPD - CCAP | R PHY CA SAN FED RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_OCE_RPHY Unbundled Solution V2_44027 | CA | SAN | OCE | RSPD - CCAP | R PHY CA SAN OCE RPHY CCAP Deployment POR20 | License | License Activation | 345 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_OCE_RPHY Unbundled Solution V2_44027 | CA | SAN | OCE | RSPD - CCAP | R PHY CA SAN OCE RPHY CCAP Deployment POR20 | License | License Activation | 264 | 2020-07-15 | 2020-08-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_OCE_RPHY Unbundled Solution V2_44027 | CA | SAN | OCE | RSPD - CCAP | R PHY CA SAN OCE RPHY CCAP Deployment POR20 | License | License Activation | 345 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_OCE_RPHY Unbundled Solution V2_44119 | CA | SAN | OCE | RSPD - CCAP | R PHY CA SAN OCE RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | EP
R PHY_CCAP_OCE_RPHY Unbundled Solution V2_44119 | CA | SAN | OCE | RSPD - CCAP | R PHY CA SAN OCE RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 2 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_OCE_RPHY Unbundled Solution V2_44119 | CA | SAN | OCE | RSPD - CCAP | R PHY CA SAN OCE RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PWY_RPHY Unbundled Solution V2_44027 | CA | SAN | PWY | RSPD - CCAP | R PHY CA SAN PWY RPHY CCAP Deployment POR20 | License | License Activation | 69 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_PWY_RPHY Unbundled Solution V2_44027 | CA | SAN | PWY | RSPD - CCAP | R PHY CA SAN PWY RPHY CCAP Deployment POR20 | License | License Activation | 396 | 2020-07-15 | 2020-08-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_PWY_RPHY Unbundled Solution V2_44027 | CA | SAN | PWY | RSPD - CCAP | R PHY CA SAN PWY RPHY CCAP Deployment POR20 | License | License Activation | 69 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_PWY_RPHY Unbundled Solution V2_44119 | CA | SAN | PWY | RSPD - CCAP | R PHY CA SAN PWY RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_PWY_RPHY Unbundled Solution V2_44119 | CA | SAN | PWY | RSPD - CCAP | R PHY CA SAN PWY RPHY CCAP Deployment POR20 | License | License Activation | 88 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_PWY_RPHY Unbundled Solution V2_44119 | CA | SAN | PWY | RSPD - CCAP | R PHY CA SAN PWY RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_VST_RPHY Unbundled Solution V2_43938 | CA | SAN | VST | RSPD - CCAP | R PHY CA SAN VST RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 2 | 2020-04-17 | 2020-05-15 |  | Active | EP
R PHY_CCAP_VST_RPHY Unbundled Solution V2_43938 | CA | SAN | VST | RSPD - CCAP | R PHY CA SAN VST RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 2 | 2020-04-17 | 2020-05-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_VST_RPHY Unbundled Solution V2_44027 | CA | SAN | VST | RSPD - CCAP | R PHY CA SAN VST RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 3 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_VST_RPHY Unbundled Solution V2_44027 | CA | SAN | VST | RSPD - CCAP | R PHY CA SAN VST RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-07-15 | 2020-08-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_VST_RPHY Unbundled Solution V2_44027 | CA | SAN | VST | RSPD - CCAP | R PHY CA SAN VST RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 3 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | Upd | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_VST_RPHY Unbundled Solution V2_44119 | CA | SAN | VST | RSPD - CCAP | R PHY CA SAN VST RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | EP
R PHY_CCAP_VST_RPHY Unbundled Solution V2_44119 | CA | SAN | VST | RSPD - CCAP | R PHY CA SAN VST RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 2 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_VST_RPHY Unbundled Solution V2_44119 | CA | SAN | VST | RSPD - CCAP | R PHY CA SAN VST RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_BLU_RPHY Bundled Solution V3_44119 | SW | LAS | BLU | RSPD - CCAP | R PHY SW LAS BLU RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_BLU_RPHY Bundled Solution V3_44119 | SW | LAS | BLU | RSPD - CCAP | R PHY SW LAS BLU RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_BLU_RPHY Bundled Solution V3_44119 | SW | LAS | BLU | RSPD - CCAP | R PHY SW LAS BLU RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_ELC_RPHY Bundled Solution V3_43937 | CA | SAN | ELC | RSPD - CCAP | R PHY CA SAN ELC RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-05-01 | 2020-07-31 | 2020-07-31 | Active | EP
R PHY_CCAP_ELC_RPHY Bundled Solution V3_43937 | CA | SAN | ELC | RSPD - CCAP | R PHY CA SAN ELC RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-04-16 | 2020-07-01 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_ELC_RPHY Bundled Solution V3_43937 | CA | SAN | ELC | RSPD - CCAP | R PHY CA SAN ELC RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-04-16 | 2020-05-31 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_ELC_RPHY Bundled Solution V3_43937 | CA | SAN | ELC | RSPD - CCAP | R PHY CA SAN ELC RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-05-01 | 2020-07-31 | 2020-07-31 | Active | Log | Upd | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_HEN_RPHY Bundled Solution V3_44119 | SW | LAS | HEN | RSPD - CCAP | R PHY SW LAS HEN RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-09-04 | 2020-10-15 | 2020-10-15 | Active | EP
R PHY_CCAP_HEN_RPHY Bundled Solution V3_44119 | SW | LAS | HEN | RSPD - CCAP | R PHY SW LAS HEN RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-10-15 | 2020-11-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_HEN_RPHY Bundled Solution V3_44119 | SW | LAS | HEN | RSPD - CCAP | R PHY SW LAS HEN RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-07-15 | 2020-10-15 | 2020-10-15 | Active | Log | Upd | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_HEN_RPHY Bundled Solution V3_44119 | SW | LAS | HEN | RSPD - CCAP | R PHY SW LAS HEN RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-09-04 | 2020-10-15 | 2020-10-15 | Active | Log | Upd | SN-0899 | Schedule Change | Approved | 2020-09-11 09:34 | RPHY CCAP actiation date updates for Fort Smith and Abbeville sites Material delivery date update for CLV FTS RSM BLU and HEN facilites
R PHY_CCAP_OSB_RPHY Bundled Solution V2_43845 | SW | LAS | OSB | RSPD - CCAP | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-02-12 | 2020-05-01 |  | Active | EP
R PHY_CCAP_OSB_RPHY Bundled Solution V2_43845 | SW | LAS | OSB | RSPD - CCAP | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-02-12 | 2020-05-01 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_OSB_RPHY Bundled Solution V3_43967 | SW | LAS | OSB | RSPD - CCAP | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-02-12 | 2020-05-01 |  | Active | EP
R PHY_CCAP_OSB_RPHY Bundled Solution V3_43967 | SW | LAS | OSB | RSPD - CCAP | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-02-12 | 2020-05-01 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_BEL_RPHY Unbundled Solution V2_43950 | SW | ARZ | BEL | RSPD - CCAP | R PHY SW ARZ BEL RPHY CCAP Deployment POR20 | License | License Activation | 1311 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_BEL_RPHY Unbundled Solution V2_43950 | SW | ARZ | BEL | RSPD - CCAP | R PHY SW ARZ BEL RPHY CCAP Deployment POR20 | License | License Activation | 30 | 2020-04-29 | 2020-05-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_BEL_RPHY Unbundled Solution V2_43950 | SW | ARZ | BEL | RSPD - CCAP | R PHY SW ARZ BEL RPHY CCAP Deployment POR20 | License | License Activation | 1311 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_BEL_RPHY Unbundled Solution V2_44027 | SW | ARZ | BEL | RSPD - CCAP | R PHY SW ARZ BEL RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | EP
R PHY_CCAP_BEL_RPHY Unbundled Solution V2_44027 | SW | ARZ | BEL | RSPD - CCAP | R PHY SW ARZ BEL RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-07-15 | 2020-08-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_BEL_RPHY Unbundled Solution V2_44027 | SW | ARZ | BEL | RSPD - CCAP | R PHY SW ARZ BEL RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_RSM_RPHY Bundled Solution V2_43845 | CA | ORG | RSM | RSPD - CCAP | R PHY CA ORG RSM RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-01-15 | 2020-04-20 |  | Active | EP
R PHY_CCAP_RSM_RPHY Bundled Solution V2_43845 | CA | ORG | RSM | RSPD - CCAP | R PHY CA ORG RSM RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-01-15 | 2020-04-20 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_BUK_RPHY Unbundled Solution V2_43951 | SW | ARZ | BUK | RSPD - CCAP | R PHY SW ARZ BUK RPHY CCAP Deployment POR20 | License | License Activation | 1 | 2020-04-30 | 2020-05-15 |  | Deleted | EP
R PHY_CCAP_BUK_RPHY Unbundled Solution V2_43951 | SW | ARZ | BUK | RSPD - CCAP | R PHY SW ARZ BUK RPHY CCAP Deployment POR20 | License | License Activation | 1 | 2020-04-30 | 2020-05-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_BUK_RPHY Unbundled Solution V2_43951 | SW | ARZ | BUK | RSPD - CCAP | R PHY SW ARZ BUK RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_BUK_RPHY Unbundled Solution V2_44027 | SW | ARZ | BUK | RSPD - CCAP | R PHY SW ARZ BUK RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_BUK_RPHY Unbundled Solution V2_44027 | SW | ARZ | BUK | RSPD - CCAP | R PHY SW ARZ BUK RPHY CCAP Deployment POR20 | License | License Activation | 177 | 2020-07-15 | 2020-08-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_BUK_RPHY Unbundled Solution V2_44027 | SW | ARZ | BUK | RSPD - CCAP | R PHY SW ARZ BUK RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_BUK_RPHY Unbundled Solution V2_44119 | SW | ARZ | BUK | RSPD - CCAP | R PHY SW ARZ BUK RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | EP
R PHY_CCAP_BUK_RPHY Unbundled Solution V2_44119 | SW | ARZ | BUK | RSPD - CCAP | R PHY SW ARZ BUK RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_BUK_RPHY Unbundled Solution V2_44119 | SW | ARZ | BUK | RSPD - CCAP | R PHY SW ARZ BUK RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_CHD_RPHY Unbundled Solution V2_43952 | SW | ARZ | CHD | RSPD - CCAP | R PHY SW ARZ CHD RPHY CCAP Deployment POR20 | License | License Activation | 552 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_CHD_RPHY Unbundled Solution V2_43952 | SW | ARZ | CHD | RSPD - CCAP | R PHY SW ARZ CHD RPHY CCAP Deployment POR20 | License | License Activation | 14 | 2020-05-01 | 2020-05-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_CHD_RPHY Unbundled Solution V2_43952 | SW | ARZ | CHD | RSPD - CCAP | R PHY SW ARZ CHD RPHY CCAP Deployment POR20 | License | License Activation | 552 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_CHD_RPHY Unbundled Solution V2_44027 | SW | ARZ | CHD | RSPD - CCAP | R PHY SW ARZ CHD RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | EP
R PHY_CCAP_CHD_RPHY Unbundled Solution V2_44027 | SW | ARZ | CHD | RSPD - CCAP | R PHY SW ARZ CHD RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 2 | 2020-07-15 | 2020-08-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_CHD_RPHY Unbundled Solution V2_44027 | SW | ARZ | CHD | RSPD - CCAP | R PHY SW ARZ CHD RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_CHD_RPHY Unbundled Solution V2_44119 | SW | ARZ | CHD | RSPD - CCAP | R PHY SW ARZ CHD RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | EP
R PHY_CCAP_CHD_RPHY Unbundled Solution V2_44119 | SW | ARZ | CHD | RSPD - CCAP | R PHY SW ARZ CHD RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 3 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_CHD_RPHY Unbundled Solution V2_44119 | SW | ARZ | CHD | RSPD - CCAP | R PHY SW ARZ CHD RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_MSA_RPHY Unbundled Solution V2_43953 | SW | ARZ | MSA | RSPD - CCAP | R PHY SW ARZ MSA RPHY CCAP Deployment POR20 | License | License Activation | 1449 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_MSA_RPHY Unbundled Solution V2_43953 | SW | ARZ | MSA | RSPD - CCAP | R PHY SW ARZ MSA RPHY CCAP Deployment POR20 | License | License Activation | 60 | 2020-05-02 | 2020-06-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_MSA_RPHY Unbundled Solution V2_43953 | SW | ARZ | MSA | RSPD - CCAP | R PHY SW ARZ MSA RPHY CCAP Deployment POR20 | License | License Activation | 1449 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_MSA_RPHY Unbundled Solution V2_44027 | SW | ARZ | MSA | RSPD - CCAP | R PHY SW ARZ MSA RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_MSA_RPHY Unbundled Solution V2_44027 | SW | ARZ | MSA | RSPD - CCAP | R PHY SW ARZ MSA RPHY CCAP Deployment POR20 | License | License Activation | 3891 | 2020-07-15 | 2020-08-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_MSA_RPHY Unbundled Solution V2_44027 | SW | ARZ | MSA | RSPD - CCAP | R PHY SW ARZ MSA RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_MSA_RPHY Unbundled Solution V2_44119 | SW | ARZ | MSA | RSPD - CCAP | R PHY SW ARZ MSA RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_MSA_RPHY Unbundled Solution V2_44119 | SW | ARZ | MSA | RSPD - CCAP | R PHY SW ARZ MSA RPHY CCAP Deployment POR20 | License | License Activation | 3822 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_MSA_RPHY Unbundled Solution V2_44119 | SW | ARZ | MSA | RSPD - CCAP | R PHY SW ARZ MSA RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_FWL_RPHY Unbundled Solution V2_43954 | SW | ARZ | FWL | RSPD - CCAP | R PHY SW ARZ FWL RPHY CCAP Deployment POR20 | License | License Activation | 552 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_FWL_RPHY Unbundled Solution V2_43954 | SW | ARZ | FWL | RSPD - CCAP | R PHY SW ARZ FWL RPHY CCAP Deployment POR20 | License | License Activation | 36 | 2020-05-03 | 2020-06-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_FWL_RPHY Unbundled Solution V2_43954 | SW | ARZ | FWL | RSPD - CCAP | R PHY SW ARZ FWL RPHY CCAP Deployment POR20 | License | License Activation | 552 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_FWL_RPHY Unbundled Solution V2_44027 | SW | ARZ | FWL | RSPD - CCAP | R PHY SW ARZ FWL RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | EP
R PHY_CCAP_FWL_RPHY Unbundled Solution V2_44027 | SW | ARZ | FWL | RSPD - CCAP | R PHY SW ARZ FWL RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 2 | 2020-07-15 | 2020-08-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_FWL_RPHY Unbundled Solution V2_44027 | SW | ARZ | FWL | RSPD - CCAP | R PHY SW ARZ FWL RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_FWL_RPHY Unbundled Solution V2_44119 | SW | ARZ | FWL | RSPD - CCAP | R PHY SW ARZ FWL RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_FWL_RPHY Unbundled Solution V2_44119 | SW | ARZ | FWL | RSPD - CCAP | R PHY SW ARZ FWL RPHY CCAP Deployment POR20 | License | License Activation | 2353 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_FWL_RPHY Unbundled Solution V2_44119 | SW | ARZ | FWL | RSPD - CCAP | R PHY SW ARZ FWL RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_MCD_RPHY Unbundled Solution V2_43955 | SW | ARZ | MCD | RSPD - CCAP | R PHY SW ARZ MCD RPHY CCAP Deployment POR20 | License | License Activation | 276 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_MCD_RPHY Unbundled Solution V2_43955 | SW | ARZ | MCD | RSPD - CCAP | R PHY SW ARZ MCD RPHY CCAP Deployment POR20 | License | License Activation | 4 | 2020-05-04 | 2020-06-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_MCD_RPHY Unbundled Solution V2_43955 | SW | ARZ | MCD | RSPD - CCAP | R PHY SW ARZ MCD RPHY CCAP Deployment POR20 | License | License Activation | 276 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_MCD_RPHY Unbundled Solution V2_44027 | SW | ARZ | MCD | RSPD - CCAP | R PHY SW ARZ MCD RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_MCD_RPHY Unbundled Solution V2_44027 | SW | ARZ | MCD | RSPD - CCAP | R PHY SW ARZ MCD RPHY CCAP Deployment POR20 | License | License Activation | 310 | 2020-07-15 | 2020-08-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_MCD_RPHY Unbundled Solution V2_44027 | SW | ARZ | MCD | RSPD - CCAP | R PHY SW ARZ MCD RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_MCD_RPHY Unbundled Solution V2_44119 | SW | ARZ | MCD | RSPD - CCAP | R PHY SW ARZ MCD RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_MCD_RPHY Unbundled Solution V2_44119 | SW | ARZ | MCD | RSPD - CCAP | R PHY SW ARZ MCD RPHY CCAP Deployment POR20 | License | License Activation | 796 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_MCD_RPHY Unbundled Solution V2_44119 | SW | ARZ | MCD | RSPD - CCAP | R PHY SW ARZ MCD RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_NSC_RPHY Unbundled Solution V2_43956 | SW | ARZ | NSC | RSPD - CCAP | R PHY SW ARZ NSC RPHY CCAP Deployment POR20 | License | License Activation | 69 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_NSC_RPHY Unbundled Solution V2_43956 | SW | ARZ | NSC | RSPD - CCAP | R PHY SW ARZ NSC RPHY CCAP Deployment POR20 | License | License Activation | 1 | 2020-05-05 | 2020-06-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_NSC_RPHY Unbundled Solution V2_43956 | SW | ARZ | NSC | RSPD - CCAP | R PHY SW ARZ NSC RPHY CCAP Deployment POR20 | License | License Activation | 69 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_NSC_RPHY Unbundled Solution V2_44027 | SW | ARZ | NSC | RSPD - CCAP | R PHY SW ARZ NSC RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_NSC_RPHY Unbundled Solution V2_44027 | SW | ARZ | NSC | RSPD - CCAP | R PHY SW ARZ NSC RPHY CCAP Deployment POR20 | License | License Activation | 176 | 2020-07-15 | 2020-08-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_NSC_RPHY Unbundled Solution V2_44027 | SW | ARZ | NSC | RSPD - CCAP | R PHY SW ARZ NSC RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_NSC_RPHY Unbundled Solution V2_44119 | SW | ARZ | NSC | RSPD - CCAP | R PHY SW ARZ NSC RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_NSC_RPHY Unbundled Solution V2_44119 | SW | ARZ | NSC | RSPD - CCAP | R PHY SW ARZ NSC RPHY CCAP Deployment POR20 | License | License Activation | 176 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_NSC_RPHY Unbundled Solution V2_44119 | SW | ARZ | NSC | RSPD - CCAP | R PHY SW ARZ NSC RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PEO_RPHY Unbundled Solution V2_43957 | SW | ARZ | PEO | RSPD - CCAP | R PHY SW ARZ PEO RPHY CCAP Deployment POR20 | License | License Activation | 1173 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_PEO_RPHY Unbundled Solution V2_43957 | SW | ARZ | PEO | RSPD - CCAP | R PHY SW ARZ PEO RPHY CCAP Deployment POR20 | License | License Activation | 17 | 2020-05-06 | 2020-06-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_PEO_RPHY Unbundled Solution V2_43957 | SW | ARZ | PEO | RSPD - CCAP | R PHY SW ARZ PEO RPHY CCAP Deployment POR20 | License | License Activation | 1173 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_PEO_RPHY Unbundled Solution V2_44027 | SW | ARZ | PEO | RSPD - CCAP | R PHY SW ARZ PEO RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_PEO_RPHY Unbundled Solution V2_44027 | SW | ARZ | PEO | RSPD - CCAP | R PHY SW ARZ PEO RPHY CCAP Deployment POR20 | License | License Activation | 1860 | 2020-07-15 | 2020-08-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_PEO_RPHY Unbundled Solution V2_44027 | SW | ARZ | PEO | RSPD - CCAP | R PHY SW ARZ PEO RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PEO_RPHY Unbundled Solution V2_44119 | SW | ARZ | PEO | RSPD - CCAP | R PHY SW ARZ PEO RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | EP
R PHY_CCAP_PEO_RPHY Unbundled Solution V2_44119 | SW | ARZ | PEO | RSPD - CCAP | R PHY SW ARZ PEO RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 4 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_PEO_RPHY Unbundled Solution V2_44119 | SW | ARZ | PEO | RSPD - CCAP | R PHY SW ARZ PEO RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PNL_RPHY Unbundled Solution V2_43958 | SW | ARZ | PNL | RSPD - CCAP | R PHY SW ARZ PNL RPHY CCAP Deployment POR20 | License | License Activation | 69 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_PNL_RPHY Unbundled Solution V2_43958 | SW | ARZ | PNL | RSPD - CCAP | R PHY SW ARZ PNL RPHY CCAP Deployment POR20 | License | License Activation | 1 | 2020-05-07 | 2020-06-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_PNL_RPHY Unbundled Solution V2_43958 | SW | ARZ | PNL | RSPD - CCAP | R PHY SW ARZ PNL RPHY CCAP Deployment POR20 | License | License Activation | 69 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_PNL_RPHY Unbundled Solution V2_44027 | SW | ARZ | PNL | RSPD - CCAP | R PHY SW ARZ PNL RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_PNL_RPHY Unbundled Solution V2_44027 | SW | ARZ | PNL | RSPD - CCAP | R PHY SW ARZ PNL RPHY CCAP Deployment POR20 | License | License Activation | 132 | 2020-07-15 | 2020-08-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_PNL_RPHY Unbundled Solution V2_44027 | SW | ARZ | PNL | RSPD - CCAP | R PHY SW ARZ PNL RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PNL_RPHY Unbundled Solution V2_44119 | SW | ARZ | PNL | RSPD - CCAP | R PHY SW ARZ PNL RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | EP
R PHY_CCAP_PNL_RPHY Unbundled Solution V2_44119 | SW | ARZ | PNL | RSPD - CCAP | R PHY SW ARZ PNL RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_PNL_RPHY Unbundled Solution V2_44119 | SW | ARZ | PNL | RSPD - CCAP | R PHY SW ARZ PNL RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_SSC_RPHY Unbundled Solution V2_43959 | SW | ARZ | SSC | RSPD - CCAP | R PHY SW ARZ SSC RPHY CCAP Deployment POR20 | License | License Activation | 690 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_SSC_RPHY Unbundled Solution V2_43959 | SW | ARZ | SSC | RSPD - CCAP | R PHY SW ARZ SSC RPHY CCAP Deployment POR20 | License | License Activation | 19 | 2020-05-08 | 2020-06-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_SSC_RPHY Unbundled Solution V2_43959 | SW | ARZ | SSC | RSPD - CCAP | R PHY SW ARZ SSC RPHY CCAP Deployment POR20 | License | License Activation | 690 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_SSC_RPHY Unbundled Solution V2_44027 | SW | ARZ | SSC | RSPD - CCAP | R PHY SW ARZ SSC RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_SSC_RPHY Unbundled Solution V2_44027 | SW | ARZ | SSC | RSPD - CCAP | R PHY SW ARZ SSC RPHY CCAP Deployment POR20 | License | License Activation | 1112 | 2020-07-15 | 2020-08-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_SSC_RPHY Unbundled Solution V2_44027 | SW | ARZ | SSC | RSPD - CCAP | R PHY SW ARZ SSC RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_SSC_RPHY Unbundled Solution V2_44119 | SW | ARZ | SSC | RSPD - CCAP | R PHY SW ARZ SSC RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_SSC_RPHY Unbundled Solution V2_44119 | SW | ARZ | SSC | RSPD - CCAP | R PHY SW ARZ SSC RPHY CCAP Deployment POR20 | License | License Activation | 983 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_SSC_RPHY Unbundled Solution V2_44119 | SW | ARZ | SSC | RSPD - CCAP | R PHY SW ARZ SSC RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_TUC_RPHY Unbundled Solution V2_43960 | SW | ARZ | TUC | RSPD - CCAP | R PHY SW ARZ TUC RPHY CCAP Deployment POR20 | License | License Activation | 621 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_TUC_RPHY Unbundled Solution V2_43960 | SW | ARZ | TUC | RSPD - CCAP | R PHY SW ARZ TUC RPHY CCAP Deployment POR20 | License | License Activation | 11 | 2020-05-09 | 2020-06-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_TUC_RPHY Unbundled Solution V2_43960 | SW | ARZ | TUC | RSPD - CCAP | R PHY SW ARZ TUC RPHY CCAP Deployment POR20 | License | License Activation | 621 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_TUC_RPHY Unbundled Solution V2_44027 | SW | ARZ | TUC | RSPD - CCAP | R PHY SW ARZ TUC RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | EP
R PHY_CCAP_TUC_RPHY Unbundled Solution V2_44027 | SW | ARZ | TUC | RSPD - CCAP | R PHY SW ARZ TUC RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-07-15 | 2020-08-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_TUC_RPHY Unbundled Solution V2_44027 | SW | ARZ | TUC | RSPD - CCAP | R PHY SW ARZ TUC RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_TUC_RPHY Unbundled Solution V2_44119 | SW | ARZ | TUC | RSPD - CCAP | R PHY SW ARZ TUC RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | EP
R PHY_CCAP_TUC_RPHY Unbundled Solution V2_44119 | SW | ARZ | TUC | RSPD - CCAP | R PHY SW ARZ TUC RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 3 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_TUC_RPHY Unbundled Solution V2_44119 | SW | ARZ | TUC | RSPD - CCAP | R PHY SW ARZ TUC RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_ALI_RPHY Unbundled Solution V2_43961 | SW | LAS | ALI | RSPD - CCAP | R PHY SW LAS ALI RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_ALI_RPHY Unbundled Solution V2_43961 | SW | LAS | ALI | RSPD - CCAP | R PHY SW LAS ALI RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-05-10 | 2020-06-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_ALI_RPHY Unbundled Solution V2_43961 | SW | LAS | ALI | RSPD - CCAP | R PHY SW LAS ALI RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_RSM_RPHY Bundled Solution V3_44119 | CA | ORG | RSM | RSPD - CCAP | R PHY CA ORG RSM RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-09-18 | 2020-10-15 | 2020-10-15 | Active | EP
R PHY_CCAP_RSM_RPHY Bundled Solution V3_44119 | CA | ORG | RSM | RSPD - CCAP | R PHY CA ORG RSM RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-08-05 | 2020-11-01 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_RSM_RPHY Bundled Solution V3_44119 | CA | ORG | RSM | RSPD - CCAP | R PHY CA ORG RSM RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-07-15 | 2020-10-15 | 2020-10-15 | Active | Log | Upd | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_RSM_RPHY Bundled Solution V3_44119 | CA | ORG | RSM | RSPD - CCAP | R PHY CA ORG RSM RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-09-18 | 2020-10-15 | 2020-10-15 | Active | Log | Upd | SN-0899 | Schedule Change | Approved | 2020-09-11 09:34 | RPHY CCAP actiation date updates for Fort Smith and Abbeville sites Material delivery date update for CLV FTS RSM BLU and HEN facilites
R PHY_CCAP_ALI_RPHY Unbundled Solution V2_44119 | SW | LAS | ALI | RSPD - CCAP | R PHY SW LAS ALI RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | EP
R PHY_CCAP_ALI_RPHY Unbundled Solution V2_44119 | SW | LAS | ALI | RSPD - CCAP | R PHY SW LAS ALI RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 3 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_ALI_RPHY Unbundled Solution V2_44119 | SW | LAS | ALI | RSPD - CCAP | R PHY SW LAS ALI RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_BLU_RPHY Unbundled Solution V2_43966 | SW | LAS | BLU | RSPD - CCAP | R PHY SW LAS BLU RPHY CCAP Deployment POR20 | License | License Activation | 2415 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_BLU_RPHY Unbundled Solution V2_43966 | SW | LAS | BLU | RSPD - CCAP | R PHY SW LAS BLU RPHY CCAP Deployment POR20 | License | License Activation | 23 | 2020-05-15 | 2020-06-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_BLU_RPHY Unbundled Solution V2_43966 | SW | LAS | BLU | RSPD - CCAP | R PHY SW LAS BLU RPHY CCAP Deployment POR20 | License | License Activation | 2415 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_BLU_RPHY Unbundled Solution V2_44027 | SW | LAS | BLU | RSPD - CCAP | R PHY SW LAS BLU RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | EP
R PHY_CCAP_BLU_RPHY Unbundled Solution V2_44027 | SW | LAS | BLU | RSPD - CCAP | R PHY SW LAS BLU RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 2 | 2020-07-15 | 2020-08-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_BLU_RPHY Unbundled Solution V2_44027 | SW | LAS | BLU | RSPD - CCAP | R PHY SW LAS BLU RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_ERN_RPHY Unbundled Solution V2_43962 | SW | LAS | ERN | RSPD - CCAP | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | License | License Activation | 1035 | 2020-04-15 | 2020-06-30 |  | Active | EP
R PHY_CCAP_ERN_RPHY Unbundled Solution V2_43962 | SW | LAS | ERN | RSPD - CCAP | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | License | License Activation | 9 | 2020-05-11 | 2020-06-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_ERN_RPHY Unbundled Solution V2_43962 | SW | LAS | ERN | RSPD - CCAP | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | License | License Activation | 1035 | 2020-04-15 | 2020-06-30 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_ERN_RPHY Unbundled Solution V2_44027 | SW | LAS | ERN | RSPD - CCAP | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_ERN_RPHY Unbundled Solution V2_44027 | SW | LAS | ERN | RSPD - CCAP | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | License | License Activation | 1998 | 2020-07-15 | 2020-08-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_ERN_RPHY Unbundled Solution V2_44027 | SW | LAS | ERN | RSPD - CCAP | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_ERN_RPHY Unbundled Solution V2_44119 | SW | LAS | ERN | RSPD - CCAP | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_ERN_RPHY Unbundled Solution V2_44119 | SW | LAS | ERN | RSPD - CCAP | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | License | License Activation | 1249 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_ERN_RPHY Unbundled Solution V2_44119 | SW | LAS | ERN | RSPD - CCAP | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_HEN_RPHY Unbundled Solution V2_43965 | SW | LAS | HEN | RSPD - CCAP | R PHY SW LAS HEN RPHY CCAP Deployment POR20 | License | License Activation | 1449 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_HEN_RPHY Unbundled Solution V2_43965 | SW | LAS | HEN | RSPD - CCAP | R PHY SW LAS HEN RPHY CCAP Deployment POR20 | License | License Activation | 80 | 2020-05-14 | 2020-06-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_HEN_RPHY Unbundled Solution V2_43965 | SW | LAS | HEN | RSPD - CCAP | R PHY SW LAS HEN RPHY CCAP Deployment POR20 | License | License Activation | 1449 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_HEN_RPHY Unbundled Solution V2_44027 | SW | LAS | HEN | RSPD - CCAP | R PHY SW LAS HEN RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | EP
R PHY_CCAP_HEN_RPHY Unbundled Solution V2_44027 | SW | LAS | HEN | RSPD - CCAP | R PHY SW LAS HEN RPHY CCAP Deployment POR20 | License | License Activation | 2486 | 2020-07-15 | 2020-08-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_HEN_RPHY Unbundled Solution V2_44027 | SW | LAS | HEN | RSPD - CCAP | R PHY SW LAS HEN RPHY CCAP Deployment POR20 | License | License Activation |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_OSB_Boundary_Clocks_43845 | SW | LAS | OSB | RSPD - CCAP | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-02-12 | 2020-05-01 |  | Active | EP
R PHY_CCAP_OSB_Boundary_Clocks_43845 | SW | LAS | OSB | RSPD - CCAP | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-02-12 | 2020-05-01 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_OSB_D9485_43845 | SW | LAS | OSB | RSPD - CCAP | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_OSB_D9485_43845 | SW | LAS | OSB | RSPD - CCAP | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-02-12 | 2020-05-01 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_OSB_D9485_43845 | SW | LAS | OSB | RSPD - CCAP | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_TEN_RPHY Bundled Solution V3_43964 | SW | LAS | TEN | RSPD - CCAP | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_TEN_RPHY Bundled Solution V3_43964 | SW | LAS | TEN | RSPD - CCAP | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-05-13 | 2020-06-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_TEN_RPHY Bundled Solution V3_43964 | SW | LAS | TEN | RSPD - CCAP | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-10-01 | 2020-12-31 |  | Deleted | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_TEN_RPHY Bundled Solution V3_43964 | SW | LAS | TEN | RSPD - CCAP | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_TEN_RPHY Bundled Solution V3_44027 | SW | LAS | TEN | RSPD - CCAP | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_TEN_RPHY Bundled Solution V3_44027 | SW | LAS | TEN | RSPD - CCAP | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-07-15 | 2020-08-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_TEN_RPHY Bundled Solution V3_44027 | SW | LAS | TEN | RSPD - CCAP | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_TEN_RPHY Bundled Solution V3_44119 | SW | LAS | TEN | RSPD - CCAP | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_TEN_RPHY Bundled Solution V3_44119 | SW | LAS | TEN | RSPD - CCAP | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_TEN_RPHY Bundled Solution V3_44119 | SW | LAS | TEN | RSPD - CCAP | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_OSB_RPHY Unbundled Solution V2_44027 | SW | LAS | OSB | RSPD - CCAP | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | License | License Activation | 487 | 2020-02-12 | 2020-05-01 |  | Active | EP
R PHY_CCAP_OSB_RPHY Unbundled Solution V2_44027 | SW | LAS | OSB | RSPD - CCAP | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | License | License Activation | 487 | 2020-02-12 | 2020-05-01 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_OSB_RPHY Unbundled Solution V2_44119 | SW | LAS | OSB | RSPD - CCAP | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | License | License Activation | 444 | 2020-02-12 | 2020-05-01 |  | Active | EP
R PHY_CCAP_OSB_RPHY Unbundled Solution V2_44119 | SW | LAS | OSB | RSPD - CCAP | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | License | License Activation | 444 | 2020-02-12 | 2020-05-01 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_VST_RPHY Bundled Solution V2_43845 | CA | SAN | VST | RSPD - CCAP | R PHY CA SAN VST RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-01-15 | 2020-04-20 |  | Active | EP
R PHY_CCAP_VST_RPHY Bundled Solution V2_43845 | CA | SAN | VST | RSPD - CCAP | R PHY CA SAN VST RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-01-15 | 2020-04-20 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_VLY_RPHY Unbundled Solution V2_43963 | SW | LAS | VLY | RSPD - CCAP | R PHY SW LAS VLY RPHY CCAP Deployment POR20 | License | License Activation | 483 | 2020-04-15 | 2020-05-15 |  | Active | EP
R PHY_CCAP_VLY_RPHY Unbundled Solution V2_43963 | SW | LAS | VLY | RSPD - CCAP | R PHY SW LAS VLY RPHY CCAP Deployment POR20 | License | License Activation | 5 | 2020-05-12 | 2020-06-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_VLY_RPHY Unbundled Solution V2_43963 | SW | LAS | VLY | RSPD - CCAP | R PHY SW LAS VLY RPHY CCAP Deployment POR20 | License | License Activation | 483 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_VLY_RPHY Unbundled Solution V2_44027 | SW | LAS | VLY | RSPD - CCAP | R PHY SW LAS VLY RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 2 | 2020-07-15 | 2020-08-31 | 2020-08-31 | Active | EP
R PHY_CCAP_VLY_RPHY Unbundled Solution V2_44027 | SW | LAS | VLY | RSPD - CCAP | R PHY SW LAS VLY RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 2 | 2020-07-15 | 2020-08-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_VLY_RPHY Unbundled Solution V2_44027 | SW | LAS | VLY | RSPD - CCAP | R PHY SW LAS VLY RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 2 | 2020-07-15 | 2020-08-31 | 2020-08-31 | Active | Log | Upd | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_VLY_RPHY Unbundled Solution V2_44119 | SW | LAS | VLY | RSPD - CCAP | R PHY SW LAS VLY RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | EP
R PHY_CCAP_VLY_RPHY Unbundled Solution V2_44119 | SW | LAS | VLY | RSPD - CCAP | R PHY SW LAS VLY RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_VLY_RPHY Unbundled Solution V2_44119 | SW | LAS | VLY | RSPD - CCAP | R PHY SW LAS VLY RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
CCAP Licenses_1 | SW | ARZ | BEL | RSPD - CCAP | R PHY SW ARZ BEL RPHY CCAP Deployment POR20 | License | License Activation | 1311 | 2020-04-15 | 2020-05-15 |  | Deleted | EP
CBR8 Chassis-1 | SW | LAS | ERN | RSPD - CCAP | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
CBR8 Chassis-1 | SW | LAS | ERN | RSPD - CCAP | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-04-15 | 2020-06-30 |  | Deleted | Log | New | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
CBR8 Chassis-1 | SW | LAS | ERN | RSPD - CCAP | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
CBR8 Chassis-3 | SW | LAS | OSB | RSPD - CCAP | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-05-01 | 2020-07-31 | 2020-07-31 | Active | EP
CBR8 Chassis-3 | SW | LAS | OSB | RSPD - CCAP | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-04-15 | 2020-06-30 |  | Active | Log | Undel | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
CBR8 Chassis-3 | SW | LAS | OSB | RSPD - CCAP | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-05-01 | 2020-07-31 | 2020-07-31 | Active | Log | Upd | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
CBR8 Line Card-2 | SW | LAS | TEN | RSPD - CCAP | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-04-15 | 2020-05-15 |  | Active | EP
CBR8 Line Card-2 | SW | LAS | TEN | RSPD - CCAP | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-04-15 | 2020-05-15 |  | Active | Log | Undel | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_BLU_CBR8 Chassis_1 | SW | LAS | BLU | RSPD - CCAP | R PHY SW LAS BLU RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-09-28 | 2020-10-15 | 2020-10-15 | Active | EP
R PHY_CCAP_BLU_CBR8 Chassis_1 | SW | LAS | BLU | RSPD - CCAP | R PHY SW LAS BLU RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-07-15 | 2020-10-15 | 2020-10-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_BLU_CBR8 Chassis_1 | SW | LAS | BLU | RSPD - CCAP | R PHY SW LAS BLU RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-09-18 | 2020-10-15 | 2020-10-15 | Active | Log | Upd | SN-0899 | Schedule Change | Approved | 2020-09-11 09:34 | RPHY CCAP actiation date updates for Fort Smith and Abbeville sites Material delivery date update for CLV FTS RSM BLU and HEN facilites
R PHY_CCAP_BLU_CBR8 Chassis_1 | SW | LAS | BLU | RSPD - CCAP | R PHY SW LAS BLU RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-09-28 | 2020-10-15 | 2020-10-15 | Active | Log | Upd | SN-0959 | Schedule Change | Approved | 2020-09-25 14:13 | 4 X CBR8s planned for Clevelandand in September are delayed into Octobe One CBR8 for Bluediamond is scheduled to arrive at the month end and has a risk of gettting the order closed and the amount hit the books before month end Total amount at risk is 888K
R PHY_CCAP_OCE_RPHY Unbundled Solution V2_44120 | CA | SAN | OCE | RSPD - CCAP | R PHY CA SAN OCE RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-07-15 | 2020-10-15 | 2020-10-15 | Active | EP
R PHY_CCAP_OCE_RPHY Unbundled Solution V2_44120 | CA | SAN | OCE | RSPD - CCAP | R PHY CA SAN OCE RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-07-15 | 2020-10-15 | 2020-10-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_OCE_CBR8 Line Card_1 | SW | LAS | OSB | RSPD - CCAP | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 5 | 2020-07-15 | 2020-10-15 | 2020-10-15 | Active | EP
R PHY_CCAP_OCE_CBR8 Line Card_1 | SW | LAS | OSB | RSPD - CCAP | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 5 | 2020-07-15 | 2020-10-15 | 2020-10-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_TEN_CBR8 Line Card_1 | SW | LAS | TEN | RSPD - CCAP | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 5 | 2020-07-15 | 2020-10-15 | 2020-10-15 | Active | EP
R PHY_CCAP_TEN_CBR8 Line Card_1 | SW | LAS | TEN | RSPD - CCAP | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 5 | 2020-07-15 | 2020-10-15 | 2020-10-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_AVJ_RPHY CCAP Licenses_1 | CA | ORG | AVJ | RSPD - CCAP | R PHY CA ORG AVJ RPHY CCAP Augment POR20 | License | CCAP license | 1014 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_AVJ_RPHY CCAP Licenses_1 | CA | ORG | AVJ | RSPD - CCAP | R PHY CA ORG AVJ RPHY CCAP Augment POR20 | License | CCAP license | 1014 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_DNP_RPHY CCAP Licenses-1 | CA | ORG | DNP | RSPD - CCAP | R PHY CA ORG DNP RPHY CCAP Augment POR20 | License | CCAP license | 182 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_DNP_RPHY CCAP Licenses-1 | CA | ORG | DNP | RSPD - CCAP | R PHY CA ORG DNP RPHY CCAP Augment POR20 | License | CCAP license | 182 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_IRV_RPHY CCAP Licenses-1 | CA | ORG | IRV | RSPD - CCAP | R PHY CA ORG IRV RPHY CCAP Augment POR20 | License | CCAP license | 390 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_IRV_RPHY CCAP Licenses-1 | CA | ORG | IRV | RSPD - CCAP | R PHY CA ORG IRV RPHY CCAP Augment POR20 | License | CCAP license | 390 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_ORG_RPHY CCAP Licenses-1 | CA | ORG | ORG | RSPD - CCAP | R PHY CA ORG ORG RPHY CCAP Augment POR20 | License | CCAP license | 494 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_ORG_RPHY CCAP Licenses-1 | CA | ORG | ORG | RSPD - CCAP | R PHY CA ORG ORG RPHY CCAP Augment POR20 | License | CCAP license | 494 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_CHU_RPHY CCAP Licenses-1 | CA | SAN | CHU | RSPD - CCAP | R PHY CA SAN CHU RPHY CCAP Deployment POR20 | License | CCAP license | 546 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_CHU_RPHY CCAP Licenses-1 | CA | SAN | CHU | RSPD - CCAP | R PHY CA SAN CHU RPHY CCAP Deployment POR20 | License | CCAP license | 546 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_DWN_RPHY CCAP Licenses-1 | CA | SAN | DWN | RSPD - CCAP | R PHY CA SAN DWN RPHY CCAP Deployment POR20 | License | CCAP license | 234 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_DWN_RPHY CCAP Licenses-1 | CA | SAN | DWN | RSPD - CCAP | R PHY CA SAN DWN RPHY CCAP Deployment POR20 | License | CCAP license | 234 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_ESC_RPHY CCAP Licenses-1 | CA | SAN | ESC | RSPD - CCAP | R PHY CA SAN ESC RPHY CCAP Deployment POR20 | License | CCAP license | 233 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_ESC_RPHY CCAP Licenses-1 | CA | SAN | ESC | RSPD - CCAP | R PHY CA SAN ESC RPHY CCAP Deployment POR20 | License | CCAP license | 233 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_FED_RPHY CCAP Licenses-1 | CA | SAN | FED | RSPD - CCAP | R PHY CA SAN FED RPHY CCAP Deployment POR20 | License | CCAP license | 459 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_FED_RPHY CCAP Licenses-1 | CA | SAN | FED | RSPD - CCAP | R PHY CA SAN FED RPHY CCAP Deployment POR20 | License | CCAP license | 459 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PWY_RPHY CCAP Licenses-1 | CA | SAN | PWY | RSPD - CCAP | R PHY CA SAN PWY RPHY CCAP Deployment POR20 | License | CCAP license | 156 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_PWY_RPHY CCAP Licenses-1 | CA | SAN | PWY | RSPD - CCAP | R PHY CA SAN PWY RPHY CCAP Deployment POR20 | License | CCAP license | 156 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_BEL_RPHY CCAP Licenses-1 | SW | ARZ | BEL | RSPD - CCAP | R PHY SW ARZ BEL RPHY CCAP Deployment POR20 | License | CCAP license | 632 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_BEL_RPHY CCAP Licenses-1 | SW | ARZ | BEL | RSPD - CCAP | R PHY SW ARZ BEL RPHY CCAP Deployment POR20 | License | CCAP license | 632 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_BUK_RPHY CCAP Licenses-1 | SW | ARZ | BUK | RSPD - CCAP | R PHY SW ARZ BUK RPHY CCAP Deployment POR20 | License | CCAP license | 78 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_BUK_RPHY CCAP Licenses-1 | SW | ARZ | BUK | RSPD - CCAP | R PHY SW ARZ BUK RPHY CCAP Deployment POR20 | License | CCAP license | 78 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_CHD_RPHY CCAP Licenses-1 | SW | ARZ | CHD | RSPD - CCAP | R PHY SW ARZ CHD RPHY CCAP Deployment POR20 | License | CCAP license | 866 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_CHD_RPHY CCAP Licenses-1 | SW | ARZ | CHD | RSPD - CCAP | R PHY SW ARZ CHD RPHY CCAP Deployment POR20 | License | CCAP license | 866 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_MSA_RPHY CCAP Licenses-1 | SW | ARZ | MSA | RSPD - CCAP | R PHY SW ARZ MSA RPHY CCAP Deployment POR20 | License | CCAP license | 3020 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_MSA_RPHY CCAP Licenses-1 | SW | ARZ | MSA | RSPD - CCAP | R PHY SW ARZ MSA RPHY CCAP Deployment POR20 | License | CCAP license | 3020 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_FWL_RPHY CCAP Licenses-1 | SW | ARZ | FWL | RSPD - CCAP | R PHY SW ARZ FWL RPHY CCAP Deployment POR20 | License | CCAP license | 597 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_FWL_RPHY CCAP Licenses-1 | SW | ARZ | FWL | RSPD - CCAP | R PHY SW ARZ FWL RPHY CCAP Deployment POR20 | License | CCAP license | 597 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_MCD_RPHY CCAP Licenses-1 | SW | ARZ | MCD | RSPD - CCAP | R PHY SW ARZ MCD RPHY CCAP Deployment POR20 | License | CCAP license | 303 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_MCD_RPHY CCAP Licenses-1 | SW | ARZ | MCD | RSPD - CCAP | R PHY SW ARZ MCD RPHY CCAP Deployment POR20 | License | CCAP license | 303 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_NSC_RPHY CCAP Licenses-1 | SW | ARZ | NSC | RSPD - CCAP | R PHY SW ARZ NSC RPHY CCAP Deployment POR20 | License | CCAP license | 26 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_NSC_RPHY CCAP Licenses-1 | SW | ARZ | NSC | RSPD - CCAP | R PHY SW ARZ NSC RPHY CCAP Deployment POR20 | License | CCAP license | 26 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PEO_RPHY CCAP Licenses-1 | SW | ARZ | PEO | RSPD - CCAP | R PHY SW ARZ PEO RPHY CCAP Deployment POR20 | License | CCAP license | 468 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_PEO_RPHY CCAP Licenses-1 | SW | ARZ | PEO | RSPD - CCAP | R PHY SW ARZ PEO RPHY CCAP Deployment POR20 | License | CCAP license | 468 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PNL_RPHY CCAP Licenses-1 | SW | ARZ | PNL | RSPD - CCAP | R PHY SW ARZ PNL RPHY CCAP Deployment POR20 | License | CCAP license | 26 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_PNL_RPHY CCAP Licenses-1 | SW | ARZ | PNL | RSPD - CCAP | R PHY SW ARZ PNL RPHY CCAP Deployment POR20 | License | CCAP license | 26 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_SSC_RPHY CCAP Licenses-1 | SW | ARZ | SSC | RSPD - CCAP | R PHY SW ARZ SSC RPHY CCAP Deployment POR20 | License | CCAP license | 906 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_SSC_RPHY CCAP Licenses-1 | SW | ARZ | SSC | RSPD - CCAP | R PHY SW ARZ SSC RPHY CCAP Deployment POR20 | License | CCAP license | 906 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_TUC_RPHY CCAP Licenses-1 | SW | ARZ | TUC | RSPD - CCAP | R PHY SW ARZ TUC RPHY CCAP Deployment POR20 | License | CCAP license | 78 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_TUC_RPHY CCAP Licenses-1 | SW | ARZ | TUC | RSPD - CCAP | R PHY SW ARZ TUC RPHY CCAP Deployment POR20 | License | CCAP license | 78 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_ERN_RPHY CCAP Licenses-1 | SW | LAS | ERN | RSPD - CCAP | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | License | CCAP license | 624 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | EP
R PHY_CCAP_ERN_RPHY CCAP Licenses-1 | SW | LAS | ERN | RSPD - CCAP | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | License | CCAP license | 624 | 2020-07-15 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_ELC_CBR8_1 | CA | SAN | ELC | RSPD - CCAP | R PHY CA SAN ELC RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | EP
R PHY_CCAP_ELC_CBR8_1 | CA | SAN | ELC | RSPD - CCAP | R PHY CA SAN ELC RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_VST_CBR8_1 | CA | SAN | VST | RSPD - CCAP | R PHY CA SAN VST RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | EP
R PHY_CCAP_VST_CBR8_1 | CA | SAN | VST | RSPD - CCAP | R PHY CA SAN VST RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_BLU_CBR8_1 | SW | LAS | BLU | RSPD - CCAP | R PHY SW LAS BLU RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-11-02 | 2020-12-31 | 2020-12-31 | Active | EP
R PHY_CCAP_BLU_CBR8_1 | SW | LAS | BLU | RSPD - CCAP | R PHY SW LAS BLU RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_BLU_CBR8_1 | SW | LAS | BLU | RSPD - CCAP | R PHY SW LAS BLU RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-11-02 | 2020-12-31 | 2020-12-31 | Active | Log | Upd | SN-0899 | Schedule Change | Approved | 2020-09-11 09:34 | RPHY CCAP actiation date updates for Fort Smith and Abbeville sites Material delivery date update for CLV FTS RSM BLU and HEN facilites
R PHY_CCAP_TEN_CBR8_1 | SW | LAS | TEN | RSPD - CCAP | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | EP
R PHY_CCAP_TEN_CBR8_1 | SW | LAS | TEN | RSPD - CCAP | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_VLY_CBR8_1 | SW | LAS | VLY | RSPD - CCAP | R PHY SW LAS VLY RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | EP
R PHY_CCAP_VLY_CBR8_1 | SW | LAS | VLY | RSPD - CCAP | R PHY SW LAS VLY RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_CHD_CBR8_1 | SW | ARZ | CHD | RSPD - CCAP | R PHY SW ARZ CHD RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 5 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | EP
R PHY_CCAP_CHD_CBR8_1 | SW | ARZ | CHD | RSPD - CCAP | R PHY SW ARZ CHD RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 5 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_DWN_CBR8_1 | CA | SAN | DWN | RSPD - CCAP | R PHY CA SAN DWN RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 2 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | EP
R PHY_CCAP_DWN_CBR8_1 | CA | SAN | DWN | RSPD - CCAP | R PHY CA SAN DWN RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 2 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_ERN_CBR8_1 | SW | LAS | ERN | RSPD - CCAP | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 2 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | EP
R PHY_CCAP_ERN_CBR8_1 | SW | LAS | ERN | RSPD - CCAP | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 2 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_OCE_CBR8_1 | CA | SAN | OCE | RSPD - CCAP | R PHY CA SAN OCE RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | EP
R PHY_CCAP_OCE_CBR8_1 | CA | SAN | OCE | RSPD - CCAP | R PHY CA SAN OCE RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_ORG_CBR8_1 | CA | ORG | ORG | RSPD - CCAP | R PHY CA ORG ORG RPHY CCAP Augment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | EP
R PHY_CCAP_ORG_CBR8_1 | CA | ORG | ORG | RSPD - CCAP | R PHY CA ORG ORG RPHY CCAP Augment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PAV_CBR8_1 | CA | ORG | PAV | RSPD - CCAP | R PHY CA ORG PAV RPHY CCAP Augment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | EP
R PHY_CCAP_PAV_CBR8_1 | CA | ORG | PAV | RSPD - CCAP | R PHY CA ORG PAV RPHY CCAP Augment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PWY_CBR8_1 | CA | SAN | PWY | RSPD - CCAP | R PHY CA SAN PWY RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | EP
R PHY_CCAP_PWY_CBR8_1 | CA | SAN | PWY | RSPD - CCAP | R PHY CA SAN PWY RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_RSM_CBR8_1 | CA | ORG | RSM | RSPD - CCAP | R PHY CA ORG RSM RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 5 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | EP
R PHY_CCAP_RSM_CBR8_1 | CA | ORG | RSM | RSPD - CCAP | R PHY CA ORG RSM RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 5 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_HEN_CBR8_1 | SW | LAS | HEN | RSPD - CCAP | R PHY SW LAS HEN RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 3 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | EP
R PHY_CCAP_HEN_CBR8_1 | SW | LAS | HEN | RSPD - CCAP | R PHY SW LAS HEN RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 3 | 2020-10-15 | 2020-12-31 | 2020-12-31 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_ALI_RPHY CCAP Licenses-1 | SW | LAS | ALI | RSPD - CCAP | R PHY SW LAS ALI RPHY CCAP Deployment POR20 | License | CCAP license | 882 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | EP
R PHY_CCAP_ALI_RPHY CCAP Licenses-1 | SW | LAS | ALI | RSPD - CCAP | R PHY SW LAS ALI RPHY CCAP Deployment POR20 | License | CCAP license | 882 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_AVJ_RPHY CCAP Licenses-2 | CA | ORG | AVJ | RSPD - CCAP | R PHY CA ORG AVJ RPHY CCAP Augment POR20 | License | CCAP license |  |  |  |  | Deleted | EP
R PHY_CCAP_AVJ_RPHY CCAP Licenses-2 | CA | ORG | AVJ | RSPD - CCAP | R PHY CA ORG AVJ RPHY CCAP Augment POR20 | License | CCAP license | 962 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Deleted | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_AVJ_RPHY CCAP Licenses-2 | CA | ORG | AVJ | RSPD - CCAP | R PHY CA ORG AVJ RPHY CCAP Augment POR20 | License | CCAP license |  |  |  |  | Deleted | Log | Del | SN-0813 | Schedule Change | Approved | 2020-08-12 14:14 | Due to Node Action plan changes some of the Q4 Mid Split Licenses in CA and SW regions can be deferred into 2021 The total amount is 600K
R PHY_CCAP_BEL_RPHY CCAP Licenses-2 | SW | ARZ | BEL | RSPD - CCAP | R PHY SW ARZ BEL RPHY CCAP Deployment POR20 | License | CCAP license | 1011 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | EP
R PHY_CCAP_BEL_RPHY CCAP Licenses-2 | SW | ARZ | BEL | RSPD - CCAP | R PHY SW ARZ BEL RPHY CCAP Deployment POR20 | License | CCAP license | 1011 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_BUK_RPHY CCAP Licenses-2 | SW | ARZ | BUK | RSPD - CCAP | R PHY SW ARZ BUK RPHY CCAP Deployment POR20 | License | CCAP license | 26 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | EP
R PHY_CCAP_BUK_RPHY CCAP Licenses-2 | SW | ARZ | BUK | RSPD - CCAP | R PHY SW ARZ BUK RPHY CCAP Deployment POR20 | License | CCAP license | 26 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_CHU_RPHY CCAP Licenses-2 | CA | SAN | CHU | RSPD - CCAP | R PHY CA SAN CHU RPHY CCAP Deployment POR20 | License | CCAP license |  |  |  |  | Deleted | EP
R PHY_CCAP_CHU_RPHY CCAP Licenses-2 | CA | SAN | CHU | RSPD - CCAP | R PHY CA SAN CHU RPHY CCAP Deployment POR20 | License | CCAP license | 624 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Deleted | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_CHU_RPHY CCAP Licenses-2 | CA | SAN | CHU | RSPD - CCAP | R PHY CA SAN CHU RPHY CCAP Deployment POR20 | License | CCAP license |  |  |  |  | Deleted | Log | Del | SN-0813 | Schedule Change | Approved | 2020-08-12 14:14 | Due to Node Action plan changes some of the Q4 Mid Split Licenses in CA and SW regions can be deferred into 2021 The total amount is 600K
R PHY_CCAP_DNP_RPHY CCAP Licenses-2 | CA | ORG | DNP | RSPD - CCAP | R PHY CA ORG DNP RPHY CCAP Augment POR20 | License | CCAP license |  |  |  |  | Deleted | EP
R PHY_CCAP_DNP_RPHY CCAP Licenses-2 | CA | ORG | DNP | RSPD - CCAP | R PHY CA ORG DNP RPHY CCAP Augment POR20 | License | CCAP license | 494 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Deleted | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_DNP_RPHY CCAP Licenses-2 | CA | ORG | DNP | RSPD - CCAP | R PHY CA ORG DNP RPHY CCAP Augment POR20 | License | CCAP license |  |  |  |  | Deleted | Log | Del | SN-0813 | Schedule Change | Approved | 2020-08-12 14:14 | Due to Node Action plan changes some of the Q4 Mid Split Licenses in CA and SW regions can be deferred into 2021 The total amount is 600K
R PHY_CCAP_MSA_RPHY CCAP Licenses-2 | SW | ARZ | MSA | RSPD - CCAP | R PHY SW ARZ MSA RPHY CCAP Deployment POR20 | License | CCAP license | 2196 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | EP
R PHY_CCAP_MSA_RPHY CCAP Licenses-2 | SW | ARZ | MSA | RSPD - CCAP | R PHY SW ARZ MSA RPHY CCAP Deployment POR20 | License | CCAP license | 3392 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_MSA_RPHY CCAP Licenses-2 | SW | ARZ | MSA | RSPD - CCAP | R PHY SW ARZ MSA RPHY CCAP Deployment POR20 | License | CCAP license | 2196 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | Upd | SN-0813 | Schedule Change | Approved | 2020-08-12 14:14 | Due to Node Action plan changes some of the Q4 Mid Split Licenses in CA and SW regions can be deferred into 2021 The total amount is 600K
R PHY_CCAP_ESC_RPHY CCAP Licenses-2 | CA | SAN | ESC | RSPD - CCAP | R PHY CA SAN ESC RPHY CCAP Deployment POR20 | License | CCAP license | 78 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | EP
R PHY_CCAP_ESC_RPHY CCAP Licenses-2 | CA | SAN | ESC | RSPD - CCAP | R PHY CA SAN ESC RPHY CCAP Deployment POR20 | License | CCAP license | 78 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_FED_RPHY CCAP Licenses-2 | CA | SAN | FED | RSPD - CCAP | R PHY CA SAN FED RPHY CCAP Deployment POR20 | License | CCAP license | 598 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | EP
R PHY_CCAP_FED_RPHY CCAP Licenses-2 | CA | SAN | FED | RSPD - CCAP | R PHY CA SAN FED RPHY CCAP Deployment POR20 | License | CCAP license | 624 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_FED_RPHY CCAP Licenses-2 | CA | SAN | FED | RSPD - CCAP | R PHY CA SAN FED RPHY CCAP Deployment POR20 | License | CCAP license | 598 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | Upd | SN-0813 | Schedule Change | Approved | 2020-08-12 14:14 | Due to Node Action plan changes some of the Q4 Mid Split Licenses in CA and SW regions can be deferred into 2021 The total amount is 600K
R PHY_CCAP_FWL_RPHY CCAP Licenses-2 | SW | ARZ | FWL | RSPD - CCAP | R PHY SW ARZ FWL RPHY CCAP Deployment POR20 | License | CCAP license | 390 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | EP
R PHY_CCAP_FWL_RPHY CCAP Licenses-2 | SW | ARZ | FWL | RSPD - CCAP | R PHY SW ARZ FWL RPHY CCAP Deployment POR20 | License | CCAP license | 390 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_IRV_RPHY CCAP Licenses-2 | CA | ORG | IRV | RSPD - CCAP | R PHY CA ORG IRV RPHY CCAP Augment POR20 | License | CCAP license |  |  |  |  | Deleted | EP
R PHY_CCAP_IRV_RPHY CCAP Licenses-2 | CA | ORG | IRV | RSPD - CCAP | R PHY CA ORG IRV RPHY CCAP Augment POR20 | License | CCAP license | 312 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Deleted | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_IRV_RPHY CCAP Licenses-2 | CA | ORG | IRV | RSPD - CCAP | R PHY CA ORG IRV RPHY CCAP Augment POR20 | License | CCAP license |  |  |  |  | Deleted | Log | Del | SN-0813 | Schedule Change | Approved | 2020-08-12 14:14 | Due to Node Action plan changes some of the Q4 Mid Split Licenses in CA and SW regions can be deferred into 2021 The total amount is 600K
R PHY_CCAP_MCD_RPHY CCAP Licenses-2 | SW | ARZ | MCD | RSPD - CCAP | R PHY SW ARZ MCD RPHY CCAP Deployment POR20 | License | CCAP license | 104 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | EP
R PHY_CCAP_MCD_RPHY CCAP Licenses-2 | SW | ARZ | MCD | RSPD - CCAP | R PHY SW ARZ MCD RPHY CCAP Deployment POR20 | License | CCAP license | 104 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_NSC_RPHY CCAP Licenses-2 | SW | ARZ | NSC | RSPD - CCAP | R PHY SW ARZ NSC RPHY CCAP Deployment POR20 | License | CCAP license | 52 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | EP
R PHY_CCAP_NSC_RPHY CCAP Licenses-2 | SW | ARZ | NSC | RSPD - CCAP | R PHY SW ARZ NSC RPHY CCAP Deployment POR20 | License | CCAP license | 52 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_OSB_RPHY CCAP Licenses-1 | SW | LAS | OSB | RSPD - CCAP | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | License | CCAP license | 260 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | EP
R PHY_CCAP_OSB_RPHY CCAP Licenses-1 | SW | LAS | OSB | RSPD - CCAP | R PHY SW LAS OSB R PHY CCAP R PHY Metro Deployment POR20 | License | CCAP license | 260 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_OSB_RPHY CCAP Licenses-1 | SW | LAS | OSB | RSPD - CCAP | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | License | CCAP license | 260 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_PEO_RPHY CCAP Licenses-2 | SW | ARZ | PEO | RSPD - CCAP | R PHY SW ARZ PEO RPHY CCAP Deployment POR20 | License | CCAP license | 234 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | EP
R PHY_CCAP_PEO_RPHY CCAP Licenses-2 | SW | ARZ | PEO | RSPD - CCAP | R PHY SW ARZ PEO RPHY CCAP Deployment POR20 | License | CCAP license | 234 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PNL_RPHY CCAP Licenses-2 | SW | ARZ | PNL | RSPD - CCAP | R PHY SW ARZ PNL RPHY CCAP Deployment POR20 | License | CCAP license | 26 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | EP
R PHY_CCAP_PNL_RPHY CCAP Licenses-2 | SW | ARZ | PNL | RSPD - CCAP | R PHY SW ARZ PNL RPHY CCAP Deployment POR20 | License | CCAP license | 26 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_SSC_RPHY CCAP Licenses- | SW | ARZ | SSC | RSPD - CCAP | R PHY SW ARZ SSC RPHY CCAP Deployment POR20 | License | CCAP license | 830 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | EP
R PHY_CCAP_SSC_RPHY CCAP Licenses- | SW | ARZ | SSC | RSPD - CCAP | R PHY SW ARZ SSC RPHY CCAP Deployment POR20 | License | CCAP license | 830 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_TUC_RPHY CCAP Licenses-2 | SW | ARZ | TUC | RSPD - CCAP | R PHY SW ARZ TUC RPHY CCAP Deployment POR20 | License | CCAP license | 329 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | EP
R PHY_CCAP_TUC_RPHY CCAP Licenses-2 | SW | ARZ | TUC | RSPD - CCAP | R PHY SW ARZ TUC RPHY CCAP Deployment POR20 | License | CCAP license | 329 | 2020-10-15 | 2020-11-15 | 2020-11-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_ALI_CBR8 Chassis-1 | SW | LAS | ALI | RSPD - CCAP | R PHY SW LAS ALI RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-04-20 | 2020-07-20 | 2020-07-20 | Active | EP
R PHY_CCAP_ALI_CBR8 Chassis-1 | SW | LAS | ALI | RSPD - CCAP | R PHY SW LAS ALI RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-04-20 | 2020-07-20 | 2020-07-20 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_DWN_RPHY CCAP Licenses Q2_18.14 | CA | SAN | DWN | RSPD - CCAP | R PHY CA SAN DWN RPHY CCAP Deployment POR20 | License | CCAP license | 414 | 2020-04-15 | 2020-05-15 | 2020-05-15 | Active | EP
R PHY_CCAP_DWN_RPHY CCAP Licenses Q2_18.14 | CA | SAN | DWN | RSPD - CCAP | R PHY CA SAN DWN RPHY CCAP Deployment POR20 | License | CCAP license | 414 | 2020-04-15 | 2020-05-15 | 2020-05-15 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_BLU_CBR8 Line Card | SW | LAS | BLU | RSPD - CCAP | R PHY SW LAS BLU RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_BLU_CBR8 Line Card | SW | LAS | BLU | RSPD - CCAP | R PHY SW LAS BLU RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_RSM_CBR8 Line Card | CA | ORG | RSM | RSPD - CCAP | R PHY CA ORG RSM RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_RSM_CBR8 Line Card | CA | ORG | RSM | RSPD - CCAP | R PHY CA ORG RSM RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PAV_CBR8 Line Card | CA | ORG | PAV | RSPD - CCAP | R PHY CA ORG PAV RPHY CCAP Augment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_PAV_CBR8 Line Card | CA | ORG | PAV | RSPD - CCAP | R PHY CA ORG PAV RPHY CCAP Augment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_ALI_RPHY CCAP Licenses_Q2_18.14 | SW | LAS | ALI | RSPD - CCAP | R PHY SW LAS ALI RPHY CCAP Deployment POR20 | License | CCAP license | 518 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_ALI_RPHY CCAP Licenses_Q2_18.14 | SW | LAS | ALI | RSPD - CCAP | R PHY SW LAS ALI RPHY CCAP Deployment POR20 | License | CCAP license | 518 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_AVJ_RPHY CCAP Licenses_Q2_18.15 | CA | ORG | AVJ | RSPD - CCAP | R PHY CA ORG AVJ RPHY CCAP Augment POR20 | License | CCAP license | 2261 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_BEL_RPHY CCAP Licenses_Q2_18.16 | SW | ARZ | BEL | RSPD - CCAP | R PHY SW ARZ BEL RPHY CCAP Deployment POR20 | License | CCAP license | 1665 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_BUK_RPHY CCAP Licenses_Q2_18.19 | SW | ARZ | BUK | RSPD - CCAP | R PHY SW ARZ BUK RPHY CCAP Deployment POR20 | License | CCAP license | 138 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_CHD_RPHY CCAP Licenses_Q2_18.20 | SW | ARZ | CHD | RSPD - CCAP | R PHY SW ARZ CHD RPHY CCAP Deployment POR20 | License | CCAP license | 837 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_CHU_RPHY CCAP Licenses_Q2_18.22 | CA | SAN | CHU | RSPD - CCAP | R PHY CA SAN CHU RPHY CCAP Deployment POR20 | License | CCAP license | 1287 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_DNP_RPHY CCAP Licenses_Q2_18.23 | CA | ORG | DNP | RSPD - CCAP | R PHY CA ORG DNP RPHY CCAP Augment POR20 | License | CCAP license | 535 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_DWN_RPHY CCAP Licenses_Q2_18.24 | CA | SAN | DWN | RSPD - CCAP | R PHY CA SAN DWN RPHY CCAP Deployment POR20 | License | CCAP license | 26 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_MSA_RPHY CCAP Licenses_Q2_18.25 | SW | ARZ | MSA | RSPD - CCAP | R PHY SW ARZ MSA RPHY CCAP Deployment POR20 | License | CCAP license | 2010 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_ELC_RPHY CCAP Licenses_Q2_18.26 | CA | SAN | ELC | RSPD - CCAP | R PHY CA SAN ELC RPHY CCAP Deployment POR20 | License | CCAP license | 923 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_ERN_RPHY CCAP Licenses_Q2_18.28 | SW | LAS | ERN | RSPD - CCAP | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | License | CCAP license | 1521 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_ESC_RPHY CCAP Licenses_Q2_18.29 | CA | SAN | ESC | RSPD - CCAP | R PHY CA SAN ESC RPHY CCAP Deployment POR20 | License | CCAP license | 138 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_FED_RPHY CCAP Licenses_Q2_18.30 | CA | SAN | FED | RSPD - CCAP | R PHY CA SAN FED RPHY CCAP Deployment POR20 | License | CCAP license | 1527 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_FWL_RPHY CCAP Licenses_Q2_18.31 | SW | ARZ | FWL | RSPD - CCAP | R PHY SW ARZ FWL RPHY CCAP Deployment POR20 | License | CCAP license | 1794 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_IRV_RPHY CCAP Licenses_Q2_18.32 | CA | ORG | IRV | RSPD - CCAP | R PHY CA ORG IRV RPHY CCAP Augment POR20 | License | CCAP license | 1631 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_MCD_RPHY CCAP Licenses_Q2_18.34 | SW | ARZ | MCD | RSPD - CCAP | R PHY SW ARZ MCD RPHY CCAP Deployment POR20 | License | CCAP license | 138 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_NSC_RPHY CCAP Licenses_Q2_18.38 | SW | ARZ | NSC | RSPD - CCAP | R PHY SW ARZ NSC RPHY CCAP Deployment POR20 | License | CCAP license | 138 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_OCE_RPHY CCAP Licenses_Q2_18.40 | CA | SAN | OCE | RSPD - CCAP | R PHY CA SAN OCE RPHY CCAP Deployment POR20 | License | CCAP license | 578 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_ORG_RPHY CCAP Licenses_Q2_18.41 | CA | ORG | ORG | RSPD - CCAP | R PHY CA ORG ORG RPHY CCAP Augment POR20 | License | CCAP license | 828 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_OSB_RPHY CCAP Licenses_Q2_18.42 | SW | LAS | OSB | RSPD - CCAP | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | License | CCAP license | 509 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_PEO_RPHY CCAP Licenses_Q2_18.43 | SW | ARZ | PEO | RSPD - CCAP | R PHY SW ARZ PEO RPHY CCAP Deployment POR20 | License | CCAP license | 828 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_PWY_RPHY CCAP Licenses_Q2_18.45 | CA | SAN | PWY | RSPD - CCAP | R PHY CA SAN PWY RPHY CCAP Deployment POR20 | License | CCAP license | 311 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_HEN_RPHY CCAP Licenses_Q2_18.47 | SW | LAS | HEN | RSPD - CCAP | R PHY SW LAS HEN RPHY CCAP Deployment POR20 | License | CCAP license | 5433 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_SSC_RPHY CCAP Licenses_Q2_18.48 | SW | ARZ | SSC | RSPD - CCAP | R PHY SW ARZ SSC RPHY CCAP Deployment POR20 | License | CCAP license | 1104 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_TEN_RPHY CCAP Licenses_Q2_18.49 | SW | LAS | TEN | RSPD - CCAP | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | License | CCAP license | 1985 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_TUC_RPHY CCAP Licenses_Q2_18.50 | SW | ARZ | TUC | RSPD - CCAP | R PHY SW ARZ TUC RPHY CCAP Deployment POR20 | License | CCAP license | 483 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_VLY_RPHY CCAP Licenses_Q2_18.51 | SW | LAS | VLY | RSPD - CCAP | R PHY SW LAS VLY RPHY CCAP Deployment POR20 | License | CCAP license | 414 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Deleted | EP
R PHY_CCAP_AVJ_RPHY CCAP Licenses_Q2_18.14 | CA | ORG | AVJ | RSPD - CCAP | R PHY CA ORG AVJ RPHY CCAP Augment POR20 | License | CCAP license | 2261 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_AVJ_RPHY CCAP Licenses_Q2_18.14 | CA | ORG | AVJ | RSPD - CCAP | R PHY CA ORG AVJ RPHY CCAP Augment POR20 | License | CCAP license | 2261 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_BEL_RPHY CCAP Licenses_Q2_18.14 | SW | ARZ | BEL | RSPD - CCAP | R PHY SW ARZ BEL RPHY CCAP Deployment POR20 | License | CCAP license | 1665 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_BEL_RPHY CCAP Licenses_Q2_18.14 | SW | ARZ | BEL | RSPD - CCAP | R PHY SW ARZ BEL RPHY CCAP Deployment POR20 | License | CCAP license | 1665 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_BUK_RPHY CCAP Licenses_Q2_18.14 | SW | ARZ | BUK | RSPD - CCAP | R PHY SW ARZ BUK RPHY CCAP Deployment POR20 | License | CCAP license | 138 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_BUK_RPHY CCAP Licenses_Q2_18.14 | SW | ARZ | BUK | RSPD - CCAP | R PHY SW ARZ BUK RPHY CCAP Deployment POR20 | License | CCAP license | 138 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_CHD_RPHY CCAP Licenses_Q2_18.14 | SW | ARZ | CHD | RSPD - CCAP | R PHY SW ARZ CHD RPHY CCAP Deployment POR20 | License | CCAP license | 837 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_CHD_RPHY CCAP Licenses_Q2_18.14 | SW | ARZ | CHD | RSPD - CCAP | R PHY SW ARZ CHD RPHY CCAP Deployment POR20 | License | CCAP license | 837 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_CHU_RPHY CCAP Licenses_Q2_18.14 | CA | SAN | CHU | RSPD - CCAP | R PHY CA SAN CHU RPHY CCAP Deployment POR20 | License | CCAP license | 1287 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_CHU_RPHY CCAP Licenses_Q2_18.14 | CA | SAN | CHU | RSPD - CCAP | R PHY CA SAN CHU RPHY CCAP Deployment POR20 | License | CCAP license | 1287 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_DNP_RPHY CCAP Licenses_Q2_18.14 | CA | ORG | DNP | RSPD - CCAP | R PHY CA ORG DNP RPHY CCAP Augment POR20 | License | CCAP license | 535 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_DNP_RPHY CCAP Licenses_Q2_18.14 | CA | ORG | DNP | RSPD - CCAP | R PHY CA ORG DNP RPHY CCAP Augment POR20 | License | CCAP license | 535 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_DWN_RPHY CCAP Licenses_Q2_18.14 | CA | SAN | DWN | RSPD - CCAP | R PHY CA SAN DWN RPHY CCAP Deployment POR20 | License | CCAP license | 26 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_DWN_RPHY CCAP Licenses_Q2_18.14 | CA | SAN | DWN | RSPD - CCAP | R PHY CA SAN DWN RPHY CCAP Deployment POR20 | License | CCAP license | 26 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_MSA_RPHY CCAP Licenses_Q2_18.14 | SW | ARZ | MSA | RSPD - CCAP | R PHY SW ARZ MSA RPHY CCAP Deployment POR20 | License | CCAP license | 2010 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_MSA_RPHY CCAP Licenses_Q2_18.14 | SW | ARZ | MSA | RSPD - CCAP | R PHY SW ARZ MSA RPHY CCAP Deployment POR20 | License | CCAP license | 2010 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_ELC_RPHY CCAP Licenses_Q2_18.14 | CA | SAN | ELC | RSPD - CCAP | R PHY CA SAN ELC RPHY CCAP Deployment POR20 | License | CCAP license | 923 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_ELC_RPHY CCAP Licenses_Q2_18.14 | CA | SAN | ELC | RSPD - CCAP | R PHY CA SAN ELC RPHY CCAP Deployment POR20 | License | CCAP license | 923 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_ERN_RPHY CCAP Licenses_Q2_18.14 | SW | LAS | ERN | RSPD - CCAP | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | License | CCAP license | 1521 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_ERN_RPHY CCAP Licenses_Q2_18.14 | SW | LAS | ERN | RSPD - CCAP | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | License | CCAP license | 1521 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_ESC_RPHY CCAP Licenses_Q2_18.14 | CA | SAN | ESC | RSPD - CCAP | R PHY CA SAN ESC RPHY CCAP Deployment POR20 | License | CCAP license | 138 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_ESC_RPHY CCAP Licenses_Q2_18.14 | CA | SAN | ESC | RSPD - CCAP | R PHY CA SAN ESC RPHY CCAP Deployment POR20 | License | CCAP license | 138 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_FED_RPHY CCAP Licenses_Q2_18.14 | CA | SAN | FED | RSPD - CCAP | R PHY CA SAN FED RPHY CCAP Deployment POR20 | License | CCAP license | 1527 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_FED_RPHY CCAP Licenses_Q2_18.14 | CA | SAN | FED | RSPD - CCAP | R PHY CA SAN FED RPHY CCAP Deployment POR20 | License | CCAP license | 1527 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_FWL_RPHY CCAP Licenses_Q2_18.14 | SW | ARZ | FWL | RSPD - CCAP | R PHY SW ARZ FWL RPHY CCAP Deployment POR20 | License | CCAP license | 1794 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_FWL_RPHY CCAP Licenses_Q2_18.14 | SW | ARZ | FWL | RSPD - CCAP | R PHY SW ARZ FWL RPHY CCAP Deployment POR20 | License | CCAP license | 1794 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_IRV_RPHY CCAP Licenses_Q2_18.14 | CA | ORG | IRV | RSPD - CCAP | R PHY CA ORG IRV RPHY CCAP Augment POR20 | License | CCAP license | 1631 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_IRV_RPHY CCAP Licenses_Q2_18.14 | CA | ORG | IRV | RSPD - CCAP | R PHY CA ORG IRV RPHY CCAP Augment POR20 | License | CCAP license | 1631 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_MCD_RPHY CCAP Licenses_Q2_18.14 | SW | ARZ | MCD | RSPD - CCAP | R PHY SW ARZ MCD RPHY CCAP Deployment POR20 | License | CCAP license | 138 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_MCD_RPHY CCAP Licenses_Q2_18.14 | SW | ARZ | MCD | RSPD - CCAP | R PHY SW ARZ MCD RPHY CCAP Deployment POR20 | License | CCAP license | 138 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_NSC_RPHY CCAP Licenses_Q2_18.14 | SW | ARZ | NSC | RSPD - CCAP | R PHY SW ARZ NSC RPHY CCAP Deployment POR20 | License | CCAP license | 138 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_NSC_RPHY CCAP Licenses_Q2_18.14 | SW | ARZ | NSC | RSPD - CCAP | R PHY SW ARZ NSC RPHY CCAP Deployment POR20 | License | CCAP license | 138 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_OCE_RPHY CCAP Licenses_Q2_18.14 | CA | SAN | OCE | RSPD - CCAP | R PHY CA SAN OCE RPHY CCAP Deployment POR20 | License | CCAP license | 578 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_OCE_RPHY CCAP Licenses_Q2_18.14 | CA | SAN | OCE | RSPD - CCAP | R PHY CA SAN OCE RPHY CCAP Deployment POR20 | License | CCAP license | 578 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_ORG_RPHY CCAP Licenses_Q2_18.14 | CA | ORG | ORG | RSPD - CCAP | R PHY CA ORG ORG RPHY CCAP Augment POR20 | License | CCAP license | 828 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_ORG_RPHY CCAP Licenses_Q2_18.14 | CA | ORG | ORG | RSPD - CCAP | R PHY CA ORG ORG RPHY CCAP Augment POR20 | License | CCAP license | 828 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_OSB_RPHY CCAP Licenses_Q2_18.14 | SW | LAS | OSB | RSPD - CCAP | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | License | CCAP license | 509 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_OSB_RPHY CCAP Licenses_Q2_18.14 | SW | LAS | OSB | RSPD - CCAP | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | License | CCAP license | 509 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PEO_RPHY CCAP Licenses_Q2_18.14 | SW | ARZ | PEO | RSPD - CCAP | R PHY SW ARZ PEO RPHY CCAP Deployment POR20 | License | CCAP license | 828 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_PEO_RPHY CCAP Licenses_Q2_18.14 | SW | ARZ | PEO | RSPD - CCAP | R PHY SW ARZ PEO RPHY CCAP Deployment POR20 | License | CCAP license | 828 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PWY_RPHY CCAP Licenses_Q2_18.14 | CA | SAN | PWY | RSPD - CCAP | R PHY CA SAN PWY RPHY CCAP Deployment POR20 | License | CCAP license | 311 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_PWY_RPHY CCAP Licenses_Q2_18.14 | CA | SAN | PWY | RSPD - CCAP | R PHY CA SAN PWY RPHY CCAP Deployment POR20 | License | CCAP license | 311 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_HEN_RPHY CCAP Licenses_Q2_18.14 | SW | LAS | HEN | RSPD - CCAP | R PHY SW LAS HEN RPHY CCAP Deployment POR20 | License | CCAP license | 5433 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_HEN_RPHY CCAP Licenses_Q2_18.14 | SW | LAS | HEN | RSPD - CCAP | R PHY SW LAS HEN RPHY CCAP Deployment POR20 | License | CCAP license | 5433 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_SSC_RPHY CCAP Licenses_Q2_18.14 | SW | ARZ | SSC | RSPD - CCAP | R PHY SW ARZ SSC RPHY CCAP Deployment POR20 | License | CCAP license | 1104 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_SSC_RPHY CCAP Licenses_Q2_18.14 | SW | ARZ | SSC | RSPD - CCAP | R PHY SW ARZ SSC RPHY CCAP Deployment POR20 | License | CCAP license | 1104 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_TEN_RPHY CCAP Licenses_Q2_18.14 | SW | LAS | TEN | RSPD - CCAP | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | License | CCAP license | 1985 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_TEN_RPHY CCAP Licenses_Q2_18.14 | SW | LAS | TEN | RSPD - CCAP | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | License | CCAP license | 1985 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_TUC_RPHY CCAP Licenses_Q2_18.14 | SW | ARZ | TUC | RSPD - CCAP | R PHY SW ARZ TUC RPHY CCAP Deployment POR20 | License | CCAP license | 483 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_TUC_RPHY CCAP Licenses_Q2_18.14 | SW | ARZ | TUC | RSPD - CCAP | R PHY SW ARZ TUC RPHY CCAP Deployment POR20 | License | CCAP license | 483 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_VLY_RPHY CCAP Licenses_Q2_18.14 | SW | LAS | VLY | RSPD - CCAP | R PHY SW LAS VLY RPHY CCAP Deployment POR20 | License | CCAP license | 414 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | EP
R PHY_CCAP_VLY_RPHY CCAP Licenses_Q2_18.14 | SW | LAS | VLY | RSPD - CCAP | R PHY SW LAS VLY RPHY CCAP Deployment POR20 | License | CCAP license | 414 | 2020-04-15 | 2020-05-30 | 2020-05-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_ALI_RPHY CCAP Licenses_Q2 NC Video | SW | LAS | ALI | RSPD - CCAP | R PHY SW LAS ALI RPHY CCAP Deployment POR20 | License | CCAP license | 136 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_ALI_RPHY CCAP Licenses_Q2 NC Video | SW | LAS | ALI | RSPD - CCAP | R PHY SW LAS ALI RPHY CCAP Deployment POR20 | License | CCAP license | 136 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_AVJ_RPHY CCAP Licenses_Q2 NC Video | CA | ORG | AVJ | RSPD - CCAP | R PHY CA ORG AVJ RPHY CCAP Augment POR20 | License | CCAP license | 6936 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_AVJ_RPHY CCAP Licenses_Q2 NC Video | CA | ORG | AVJ | RSPD - CCAP | R PHY CA ORG AVJ RPHY CCAP Augment POR20 | License | CCAP license | 6936 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_BEL_RPHY CCAP Licenses_Q2 NC Video | SW | ARZ | BEL | RSPD - CCAP | R PHY SW ARZ BEL RPHY CCAP Deployment POR20 | License | CCAP license | 1632 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_BEL_RPHY CCAP Licenses_Q2 NC Video | SW | ARZ | BEL | RSPD - CCAP | R PHY SW ARZ BEL RPHY CCAP Deployment POR20 | License | CCAP license | 1632 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_BLU_RPHY CCAP Licenses_Q2 NC Video | SW | LAS | BLU | RSPD - CCAP | R PHY SW LAS BLU RPHY CCAP Deployment POR20 | License | CCAP license | 2584 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_BLU_RPHY CCAP Licenses_Q2 NC Video | SW | LAS | BLU | RSPD - CCAP | R PHY SW LAS BLU RPHY CCAP Deployment POR20 | License | CCAP license | 2584 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_CHD_RPHY CCAP Licenses_Q2 NC Video | SW | ARZ | CHD | RSPD - CCAP | R PHY SW ARZ CHD RPHY CCAP Deployment POR20 | License | CCAP license | 272 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_CHD_RPHY CCAP Licenses_Q2 NC Video | SW | ARZ | CHD | RSPD - CCAP | R PHY SW ARZ CHD RPHY CCAP Deployment POR20 | License | CCAP license | 272 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_CHU_RPHY CCAP Licenses_Q2 NC Video | CA | SAN | CHU | RSPD - CCAP | R PHY CA SAN CHU RPHY CCAP Deployment POR20 | License | CCAP license | 136 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_CHU_RPHY CCAP Licenses_Q2 NC Video | CA | SAN | CHU | RSPD - CCAP | R PHY CA SAN CHU RPHY CCAP Deployment POR20 | License | CCAP license | 136 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_DWN_RPHY CCAP Licenses_Q2 NC Video | CA | SAN | DWN | RSPD - CCAP | R PHY CA SAN DWN RPHY CCAP Deployment POR20 | License | CCAP license | 136 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_DWN_RPHY CCAP Licenses_Q2 NC Video | CA | SAN | DWN | RSPD - CCAP | R PHY CA SAN DWN RPHY CCAP Deployment POR20 | License | CCAP license | 136 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_MSA_RPHY CCAP Licenses_Q2 NC Video | SW | ARZ | MSA | RSPD - CCAP | R PHY SW ARZ MSA RPHY CCAP Deployment POR20 | License | CCAP license | 4624 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_MSA_RPHY CCAP Licenses_Q2 NC Video | SW | ARZ | MSA | RSPD - CCAP | R PHY SW ARZ MSA RPHY CCAP Deployment POR20 | License | CCAP license | 4624 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_ELC_RPHY CCAP Licenses_Q2 NC Video | CA | SAN | ELC | RSPD - CCAP | R PHY CA SAN ELC RPHY CCAP Deployment POR20 | License | CCAP license | 272 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_ELC_RPHY CCAP Licenses_Q2 NC Video | CA | SAN | ELC | RSPD - CCAP | R PHY CA SAN ELC RPHY CCAP Deployment POR20 | License | CCAP license | 272 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_ERN_RPHY CCAP Licenses_Q2 NC Video | SW | LAS | ERN | RSPD - CCAP | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | License | CCAP license | 544 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_ERN_RPHY CCAP Licenses_Q2 NC Video | SW | LAS | ERN | RSPD - CCAP | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | License | CCAP license | 544 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_FED_RPHY CCAP Licenses_Q2 NC Video | CA | SAN | FED | RSPD - CCAP | R PHY CA SAN FED RPHY CCAP Deployment POR20 | License | CCAP license | 2856 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_FED_RPHY CCAP Licenses_Q2 NC Video | CA | SAN | FED | RSPD - CCAP | R PHY CA SAN FED RPHY CCAP Deployment POR20 | License | CCAP license | 2856 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_FWL_RPHY CCAP Licenses_Q2 NC Video | SW | ARZ | FWL | RSPD - CCAP | R PHY SW ARZ FWL RPHY CCAP Deployment POR20 | License | CCAP license | 1632 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_FWL_RPHY CCAP Licenses_Q2 NC Video | SW | ARZ | FWL | RSPD - CCAP | R PHY SW ARZ FWL RPHY CCAP Deployment POR20 | License | CCAP license | 1632 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_MCD_RPHY CCAP Licenses_Q2 NC Video | SW | ARZ | MCD | RSPD - CCAP | R PHY SW ARZ MCD RPHY CCAP Deployment POR20 | License | CCAP license | 272 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_MCD_RPHY CCAP Licenses_Q2 NC Video | SW | ARZ | MCD | RSPD - CCAP | R PHY SW ARZ MCD RPHY CCAP Deployment POR20 | License | CCAP license | 272 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_NSC_RPHY CCAP Licenses_Q2 NC Video | SW | ARZ | NSC | RSPD - CCAP | R PHY SW ARZ NSC RPHY CCAP Deployment POR20 | License | CCAP license | 408 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_NSC_RPHY CCAP Licenses_Q2 NC Video | SW | ARZ | NSC | RSPD - CCAP | R PHY SW ARZ NSC RPHY CCAP Deployment POR20 | License | CCAP license | 408 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_OCE_RPHY CCAP Licenses_Q2 NC Video | CA | SAN | OCE | RSPD - CCAP | R PHY CA SAN OCE RPHY CCAP Deployment POR20 | License | CCAP license | 136 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_OCE_RPHY CCAP Licenses_Q2 NC Video | CA | SAN | OCE | RSPD - CCAP | R PHY CA SAN OCE RPHY CCAP Deployment POR20 | License | CCAP license | 136 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_OSB_RPHY CCAP Licenses_Q2 NC Video | SW | LAS | OSB | RSPD - CCAP | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | License | CCAP license | 1496 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_OSB_RPHY CCAP Licenses_Q2 NC Video | SW | LAS | OSB | RSPD - CCAP | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | License | CCAP license | 1496 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PAV_RPHY CCAP Licenses_Q2 NC Video | CA | ORG | PAV | RSPD - CCAP | R PHY CA ORG PAV RPHY CCAP Augment POR20 | License | CCAP license | 136 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_PAV_RPHY CCAP Licenses_Q2 NC Video | CA | ORG | PAV | RSPD - CCAP | R PHY CA ORG PAV RPHY CCAP Augment POR20 | License | CCAP license | 136 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PEO_RPHY CCAP Licenses_Q2 NC Video | SW | ARZ | PEO | RSPD - CCAP | R PHY SW ARZ PEO RPHY CCAP Deployment POR20 | License | CCAP license | 1768 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_PEO_RPHY CCAP Licenses_Q2 NC Video | SW | ARZ | PEO | RSPD - CCAP | R PHY SW ARZ PEO RPHY CCAP Deployment POR20 | License | CCAP license | 1768 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_RSM_RPHY CCAP Licenses_Q2 NC Video | CA | ORG | RSM | RSPD - CCAP | R PHY CA ORG RSM RPHY CCAP Deployment POR20 | License | CCAP license | 408 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_RSM_RPHY CCAP Licenses_Q2 NC Video | CA | ORG | RSM | RSPD - CCAP | R PHY CA ORG RSM RPHY CCAP Deployment POR20 | License | CCAP license | 408 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_HEN_RPHY CCAP Licenses_Q2 NC Video | SW | LAS | HEN | RSPD - CCAP | R PHY SW LAS HEN RPHY CCAP Deployment POR20 | License | CCAP license | 2720 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_HEN_RPHY CCAP Licenses_Q2 NC Video | SW | LAS | HEN | RSPD - CCAP | R PHY SW LAS HEN RPHY CCAP Deployment POR20 | License | CCAP license | 2720 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_SSC_RPHY CCAP Licenses_Q2 NC Video | SW | ARZ | SSC | RSPD - CCAP | R PHY SW ARZ SSC RPHY CCAP Deployment POR20 | License | CCAP license | 5576 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_SSC_RPHY CCAP Licenses_Q2 NC Video | SW | ARZ | SSC | RSPD - CCAP | R PHY SW ARZ SSC RPHY CCAP Deployment POR20 | License | CCAP license | 5576 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_TEN_RPHY CCAP Licenses_Q2 NC Video | SW | LAS | TEN | RSPD - CCAP | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | License | CCAP license | 1224 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_TEN_RPHY CCAP Licenses_Q2 NC Video | SW | LAS | TEN | RSPD - CCAP | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | License | CCAP license | 1224 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_TUC_RPHY CCAP Licenses_Q2 NC Video | SW | ARZ | TUC | RSPD - CCAP | R PHY SW ARZ TUC RPHY CCAP Deployment POR20 | License | CCAP license | 408 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | EP
R PHY_CCAP_TUC_RPHY CCAP Licenses_Q2 NC Video | SW | ARZ | TUC | RSPD - CCAP | R PHY SW ARZ TUC RPHY CCAP Deployment POR20 | License | CCAP license | 408 | 2020-03-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PAV_CBR8_2 | CA | ORG | PAV | RSPD - CCAP | R PHY CA ORG PAV RPHY CCAP Augment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-07-15 | 2020-10-15 |  | Active | EP
R PHY_CCAP_PAV_CBR8_2 | CA | ORG | PAV | RSPD - CCAP | R PHY CA ORG PAV RPHY CCAP Augment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-07-15 | 2020-10-15 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_ALI_OTDR_1 | SW | LAS | ALI | RSPD - CCAP | R PHY SW LAS ALI RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_ALI_OTDR_1 | SW | LAS | ALI | RSPD - CCAP | R PHY SW LAS ALI RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_AVJ_OTDR_1 | CA | ORG | AVJ | RSPD - CCAP | R PHY CA ORG AVJ RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_AVJ_OTDR_1 | CA | ORG | AVJ | RSPD - CCAP | R PHY CA ORG AVJ RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_BEL_OTDR_1 | SW | ARZ | BEL | RSPD - CCAP | R PHY SW ARZ BEL RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_BEL_OTDR_1 | SW | ARZ | BEL | RSPD - CCAP | R PHY SW ARZ BEL RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_BLU_OTDR_1 | SW | LAS | BLU | RSPD - CCAP | R PHY SW LAS BLU RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_BLU_OTDR_1 | SW | LAS | BLU | RSPD - CCAP | R PHY SW LAS BLU RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_BUK_OTDR_1 | SW | ARZ | BUK | RSPD - CCAP | R PHY SW ARZ BUK RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_BUK_OTDR_1 | SW | ARZ | BUK | RSPD - CCAP | R PHY SW ARZ BUK RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_CHD_OTDR_1 | SW | ARZ | CHD | RSPD - CCAP | R PHY SW ARZ CHD RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_CHD_OTDR_1 | SW | ARZ | CHD | RSPD - CCAP | R PHY SW ARZ CHD RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_CHU_OTDR_1 | CA | SAN | CHU | RSPD - CCAP | R PHY CA SAN CHU RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_CHU_OTDR_1 | CA | SAN | CHU | RSPD - CCAP | R PHY CA SAN CHU RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_DNP_OTDR_1 | CA | ORG | DNP | RSPD - CCAP | R PHY CA ORG DNP RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_DNP_OTDR_1 | CA | ORG | DNP | RSPD - CCAP | R PHY CA ORG DNP RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_DWN_OTDR_1 | CA | SAN | DWN | RSPD - CCAP | R PHY CA SAN DWN RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_DWN_OTDR_1 | CA | SAN | DWN | RSPD - CCAP | R PHY CA SAN DWN RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_MSA_OTDR_1 | SW | ARZ | MSA | RSPD - CCAP | R PHY SW ARZ MSA RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_MSA_OTDR_1 | SW | ARZ | MSA | RSPD - CCAP | R PHY SW ARZ MSA RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_ELC_OTDR_1 | CA | SAN | ELC | RSPD - CCAP | R PHY CA SAN ELC RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_ELC_OTDR_1 | CA | SAN | ELC | RSPD - CCAP | R PHY CA SAN ELC RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_ERN_OTDR_1 | SW | LAS | ERN | RSPD - CCAP | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_ERN_OTDR_1 | SW | LAS | ERN | RSPD - CCAP | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_FED_OTDR_1 | CA | SAN | FED | RSPD - CCAP | R PHY CA SAN FED RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_FED_OTDR_1 | CA | SAN | FED | RSPD - CCAP | R PHY CA SAN FED RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_FWL_OTDR_1 | SW | ARZ | FWL | RSPD - CCAP | R PHY SW ARZ FWL RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_FWL_OTDR_1 | SW | ARZ | FWL | RSPD - CCAP | R PHY SW ARZ FWL RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_IRV_OTDR_1 | CA | ORG | IRV | RSPD - CCAP | R PHY CA ORG IRV RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_IRV_OTDR_1 | CA | ORG | IRV | RSPD - CCAP | R PHY CA ORG IRV RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_MCD_OTDR_1 | SW | ARZ | MCD | RSPD - CCAP | R PHY SW ARZ MCD RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_MCD_OTDR_1 | SW | ARZ | MCD | RSPD - CCAP | R PHY SW ARZ MCD RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_NSC_OTDR_1 | SW | ARZ | NSC | RSPD - CCAP | R PHY SW ARZ NSC RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_NSC_OTDR_1 | SW | ARZ | NSC | RSPD - CCAP | R PHY SW ARZ NSC RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_OCE_OTDR_1 | CA | SAN | OCE | RSPD - CCAP | R PHY CA SAN OCE RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_OCE_OTDR_1 | CA | SAN | OCE | RSPD - CCAP | R PHY CA SAN OCE RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_ORG_OTDR_1 | CA | ORG | ORG | RSPD - CCAP | R PHY CA ORG ORG RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_ORG_OTDR_1 | CA | ORG | ORG | RSPD - CCAP | R PHY CA ORG ORG RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_OSB_OTDR_1 | SW | LAS | OSB | RSPD - CCAP | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_OSB_OTDR_1 | SW | LAS | OSB | RSPD - CCAP | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_PAV_OTDR_1 | CA | ORG | PAV | RSPD - CCAP | R PHY CA ORG PAV RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_PAV_OTDR_1 | CA | ORG | PAV | RSPD - CCAP | R PHY CA ORG PAV RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_PEO_OTDR_1 | SW | ARZ | PEO | RSPD - CCAP | R PHY SW ARZ PEO RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_PEO_OTDR_1 | SW | ARZ | PEO | RSPD - CCAP | R PHY SW ARZ PEO RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_PNL_OTDR_1 | SW | ARZ | PNL | RSPD - CCAP | R PHY SW ARZ PNL RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_PNL_OTDR_1 | SW | ARZ | PNL | RSPD - CCAP | R PHY SW ARZ PNL RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_PWY_OTDR_1 | CA | SAN | PWY | RSPD - CCAP | R PHY CA SAN PWY RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_PWY_OTDR_1 | CA | SAN | PWY | RSPD - CCAP | R PHY CA SAN PWY RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_RSM_OTDR_1 | CA | ORG | RSM | RSPD - CCAP | R PHY CA ORG RSM RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_RSM_OTDR_1 | CA | ORG | RSM | RSPD - CCAP | R PHY CA ORG RSM RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_HEN_OTDR_1 | SW | LAS | HEN | RSPD - CCAP | R PHY SW LAS HEN RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_HEN_OTDR_1 | SW | LAS | HEN | RSPD - CCAP | R PHY SW LAS HEN RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_SSC_OTDR_1 | SW | ARZ | SSC | RSPD - CCAP | R PHY SW ARZ SSC RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_SSC_OTDR_1 | SW | ARZ | SSC | RSPD - CCAP | R PHY SW ARZ SSC RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_TEN_OTDR_1 | SW | LAS | TEN | RSPD - CCAP | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_TEN_OTDR_1 | SW | LAS | TEN | RSPD - CCAP | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_TUC_OTDR_1 | SW | ARZ | TUC | RSPD - CCAP | R PHY SW ARZ TUC RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_TUC_OTDR_1 | SW | ARZ | TUC | RSPD - CCAP | R PHY SW ARZ TUC RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_VLY_OTDR_1 | SW | LAS | VLY | RSPD - CCAP | R PHY SW LAS VLY RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_VLY_OTDR_1 | SW | LAS | VLY | RSPD - CCAP | R PHY SW LAS VLY RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_VST_OTDR_1 | CA | SAN | VST | RSPD - CCAP | R PHY CA SAN VST RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | EP
R PHY_CCAP_VST_OTDR_1 | CA | SAN | VST | RSPD - CCAP | R PHY CA SAN VST RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | Active | Log | New | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_SAB_OTDR_1 | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-06-15 | 2020-10-31 |  | Active | EP
R PHY_CCAP_SAB_OTDR_1 | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-06-15 | 2020-07-30 |  | Active | Log | New | SN-0613 | Schedule Change | Approved | 2020-05-29 16:19 | RPHY CCAP POR Update
R PHY_CCAP_SAB_OTDR_1 | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-06-15 | 2020-10-31 |  | Active | Log | Upd | SN-0637 | Schedule Change | Approved | 2020-06-05 14:50 | RPHY CCAP POR Update
R PHY_CCAP_ESC_OTDR_1 | CA | SAN | ESC | RSPD - CCAP | R PHY CA SAN ESC RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-07-20 | 2020-10-31 |  | Active | EP
R PHY_CCAP_ESC_OTDR_1 | CA | SAN | ESC | RSPD - CCAP | R PHY CA SAN ESC RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-07-20 | 2020-10-31 |  | Active | Log | New | SN-0637 | Schedule Change | Approved | 2020-06-05 14:50 | RPHY CCAP POR Update
R PHY_CCAP_SAB_CBR8_2 | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 2 | 2020-10-15 | 2020-12-31 |  | Deleted | EP
R PHY_CCAP_SAB_CBR8_2 | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 2 | 2020-10-15 | 2020-12-31 |  | Deleted | Log | New | SN-0808 | Schedule Change | Draft | 2020-08-05 16:56 | 1 Due to node action plan changes some of the Q4 Mid Split Licenses in CA and SW regions can be deferred into 2021 The total amount is 600K 2 Santa Barbara New Facility requires 3 CBR8s in total 1 was already in the plan 185K is required for additional 2
R PHY_CCAP_SAB_1 X CBR8_New Fac. | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-12-11 | 2021-03-31 |  | Deleted | EP
R PHY_CCAP_SAB_1 X CBR8_New Fac. | CA | SAB | SAB | RSPD - CCAP | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-12-10 | 2021-03-31 |  | Deleted | Log | New | SN-0908 | Scope Change | Draft | 2020-10-01 14:07 | Santa Barbara is looking for one digital CBR8 in Decembe 2020 for the migration from old to new facility Total 3 new CBR8s are required and the remaining 2 are being included in the 2021 submission
V2B COR COR ATL VQ Lab Augment POR20 | COR | COR | ATL | V2B | V2B COR COR ATL VQ Lab Augment POR20 | Labor | Lab | 1 | 2020-01-06 | 2020-02-15 | 2020-12-15 | Active | EP
V2B COR COR ATL Professional Services Augment POR20 | COR | COR | ATL | V2B | V2B COR COR ATL Professional Services Augment POR20 | Labor | Prof Services | 1 | 2020-01-06 | 2020-02-15 | 2020-12-15 | Active | EP
V2B COR COR ATL Centralized Blackout Control Deployment POR20 | COR | COR | ATL | V2B | V2B COR COR ATL Centralized Blackout Control Deployment POR20 | Labor | Other |  |  |  |  | Deleted | EP
V2B COR COR ATL Centralized Blackout Control Deployment POR20 | COR | COR | ATL | V2B | V2B COR COR ATL Centralized Blackout Control Deployment POR20 | Labor | Other | 1 | 2020-04-06 | 2020-05-15 | 2020-12-15 | Deleted | Log | Upd | SN-0171 | Schedule Change | Approved | 2020-02-06 11:24 | This CR delays the Centralized Blackout Control initiative by one quarter and returns the 180k budgeted for Q1
V2B COR COR ATL Centralized Blackout Control Deployment POR20 | COR | COR | ATL | V2B | V2B COR COR ATL Centralized Blackout Control Deployment POR20 | Labor | Other | 1 | 2020-05-06 | 2020-06-15 | 2020-12-15 | Deleted | Log | Upd | SN-0430 | Schedule Change | Approved | 2020-04-10 15:22 | This CR updates the Video to Backbone activity plan with the latest schedule based on the delays due to blackout control and to the Tektronix order that was just completed via Supply Chain
V2B COR COR ATL Centralized Blackout Control Deployment POR20 | COR | COR | ATL | V2B | V2B COR COR ATL Centralized Blackout Control Deployment POR20 | Labor | Other |  |  |  |  | Deleted | Log | Del | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B COR COR DDR Ops Facility Tools Augment POR20 | COR | COR | DDR | V2B | V2B COR COR DDR Ops Facility Tools Augment POR20 | Labor | Other | 1 | 2020-02-06 | 2020-11-15 | 2020-12-15 | Active | EP
V2B COR COR DDR Ops Facility Tools Augment POR20 | COR | COR | DDR | V2B | V2B COR COR DDR Ops Facility Tools Augment POR20 | Labor | Other | 1 | 2020-02-06 | 2020-11-15 | 2020-12-15 | Active | Log | Upd | SN-0430 | Schedule Change | Approved | 2020-04-10 15:22 | This CR updates the Video to Backbone activity plan with the latest schedule based on the delays due to blackout control and to the Tektronix order that was just completed via Supply Chain
V2B NE CLE CLV Market Blackout Control Deployment POR20 | NE | CLE | CLV | V2B | V2B NE CLE CLV V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-12-06 | 2021-01-31 | 2021-02-28 | Active | EP
V2B NE CLE CLV Market Blackout Control Deployment POR20 | NE | CLE | CLV | V2B | V2B NE CLE CLV V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-06-06 | 2020-07-15 | 2020-08-15 | Active | Log | Upd | SN-0430 | Schedule Change | Approved | 2020-04-10 15:22 | This CR updates the Video to Backbone activity plan with the latest schedule based on the delays due to blackout control and to the Tektronix order that was just completed via Supply Chain
V2B NE CLE CLV Market Blackout Control Deployment POR20 | NE | CLE | CLV | V2B | V2B NE CLE CLV V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-12-06 | 2021-01-31 | 2021-02-28 | Active | Log | Upd | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B NE CON MAN Market Blackout Control Deployment POR20 | NE | CON | MAN | V2B | V2B NE CON MAN V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-12-06 | 2021-01-31 | 2021-02-28 | Active | EP
V2B NE CON MAN Market Blackout Control Deployment POR20 | NE | CON | MAN | V2B | V2B NE CON MAN V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-06-06 | 2020-07-15 | 2020-08-15 | Active | Log | Upd | SN-0430 | Schedule Change | Approved | 2020-04-10 15:22 | This CR updates the Video to Backbone activity plan with the latest schedule based on the delays due to blackout control and to the Tektronix order that was just completed via Supply Chain
V2B NE CON MAN Market Blackout Control Deployment POR20 | NE | CON | MAN | V2B | V2B NE CON MAN V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-12-06 | 2021-01-31 | 2021-02-28 | Active | Log | Upd | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B NE RHD WWK Market Blackout Control Deployment POR20 | NE | RHD | WWK | V2B | V2B NE RHD WWK V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-12-06 | 2021-01-31 | 2021-02-28 | Active | EP
V2B NE RHD WWK Market Blackout Control Deployment POR20 | NE | RHD | WWK | V2B | V2B NE RHD WWK V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-06-06 | 2020-07-15 | 2020-08-15 | Active | Log | Upd | SN-0430 | Schedule Change | Approved | 2020-04-10 15:22 | This CR updates the Video to Backbone activity plan with the latest schedule based on the delays due to blackout control and to the Tektronix order that was just completed via Supply Chain
V2B NE RHD WWK Market Blackout Control Deployment POR20 | NE | RHD | WWK | V2B | V2B NE RHD WWK V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-12-06 | 2021-01-31 | 2021-02-28 | Active | Log | Upd | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B VA HRD VBC Market Blackout Control Deployment POR20 | VA | HRD | VBC | V2B | V2B VA HRD VBC V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-12-06 | 2021-01-31 | 2021-02-28 | Active | EP
V2B VA HRD VBC Market Blackout Control Deployment POR20 | VA | HRD | VBC | V2B | V2B VA HRD VBC V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-06-06 | 2020-07-15 | 2020-09-15 | Active | Log | Upd | SN-0430 | Schedule Change | Approved | 2020-04-10 15:22 | This CR updates the Video to Backbone activity plan with the latest schedule based on the delays due to blackout control and to the Tektronix order that was just completed via Supply Chain
V2B VA HRD VBC Market Blackout Control Deployment POR20 | VA | HRD | VBC | V2B | V2B VA HRD VBC V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-12-06 | 2021-01-31 | 2021-02-28 | Active | Log | Upd | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B VA NVA MFD Market Blackout Control Deployment POR20 | VA | NVA | MFD | V2B | V2B VA NVA MFD V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-12-06 | 2021-01-31 | 2021-02-28 | Active | EP
V2B VA NVA MFD Market Blackout Control Deployment POR20 | VA | NVA | MFD | V2B | V2B VA NVA MFD V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-06-06 | 2020-07-15 | 2020-09-15 | Active | Log | Upd | SN-0430 | Schedule Change | Approved | 2020-04-10 15:22 | This CR updates the Video to Backbone activity plan with the latest schedule based on the delays due to blackout control and to the Tektronix order that was just completed via Supply Chain
V2B VA NVA MFD Market Blackout Control Deployment POR20 | VA | NVA | MFD | V2B | V2B VA NVA MFD V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-12-06 | 2021-01-31 | 2021-02-28 | Active | Log | Upd | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B VA ROA RON Market Blackout Control Deployment POR20 | VA | ROA | RON | V2B | V2B VA ROA RON V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-12-06 | 2021-01-31 | 2021-02-28 | Active | EP
V2B VA ROA RON Market Blackout Control Deployment POR20 | VA | ROA | RON | V2B | V2B VA ROA RON V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-06-06 | 2020-07-15 | 2020-08-15 | Active | Log | Upd | SN-0430 | Schedule Change | Approved | 2020-04-10 15:22 | This CR updates the Video to Backbone activity plan with the latest schedule based on the delays due to blackout control and to the Tektronix order that was just completed via Supply Chain
V2B VA ROA RON Market Blackout Control Deployment POR20 | VA | ROA | RON | V2B | V2B VA ROA RON V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-12-06 | 2021-01-31 | 2021-02-28 | Active | Log | Upd | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B CA SAN ELC Collection Platform Deployment POR20 | CA | SAN | ELC | V2B | V2B CA SAN ELC Collection Platform Deployment POR20 | Chassis | IRD (1 RU), satellite and Zixi |  |  |  |  | Deleted | EP
V2B CA SAN ELC Collection Platform Deployment POR20 | CA | SAN | ELC | V2B | V2B CA SAN ELC Collection Platform Deployment POR20 | Chassis | IRD (1 RU), satellite and Zixi | 15 | 2020-07-06 | 2020-10-15 | 2020-12-15 | Deleted | Log | Upd | SN-0430 | Schedule Change | Approved | 2020-04-10 15:22 | This CR updates the Video to Backbone activity plan with the latest schedule based on the delays due to blackout control and to the Tektronix order that was just completed via Supply Chain
V2B CA SAN ELC Collection Platform Deployment POR20 | CA | SAN | ELC | V2B | V2B CA SAN ELC Collection Platform Deployment POR20 | Chassis | IRD (1 RU), satellite and Zixi |  |  |  |  | Deleted | Log | Del | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B CA SAN ELC Monitoring Platform Expansion Augment POR20 | CA | SAN | ELC | V2B | V2B CA SAN ELC Monitoring Platform Expansion Augment POR20 | Chassis | Tektronix Sentry |  |  |  |  | Deleted | EP
V2B CA SAN ELC Monitoring Platform Expansion Augment POR20 | CA | SAN | ELC | V2B | V2B CA SAN ELC Monitoring Platform Expansion Augment POR20 | Chassis | Tektronix Sentry |  |  |  |  | Deleted | Log | Del | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B CA SAN ELC Monitoring Platform Obsolescence Augment POR20 | CA | SAN | ELC | V2B | V2B CA SAN ELC Monitoring Platform Obsolescence Augment POR20 | Chassis | Tektronix Sentry replacement | 13 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | EP
V2B CA SAN ELC Monitoring Platform Obsolescence Augment POR20 | CA | SAN | ELC | V2B | V2B CA SAN ELC Monitoring Platform Obsolescence Augment POR20 | Chassis | Tektronix Sentry replacement | 13 | 2020-07-06 | 2020-08-15 | 2020-09-15 | Active | Log | Upd | SN-0430 | Schedule Change | Approved | 2020-04-10 15:22 | This CR updates the Video to Backbone activity plan with the latest schedule based on the delays due to blackout control and to the Tektronix order that was just completed via Supply Chain
V2B CA SAN ELC Monitoring Platform Obsolescence Augment POR20 | CA | SAN | ELC | V2B | V2B CA SAN ELC Monitoring Platform Obsolescence Augment POR20 | Chassis | Tektronix Sentry replacement | 13 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B COR COR DDR Monitoring Platform Obsolescence Augment POR20 | COR | COR | DDR | V2B | V2B COR COR DDR Monitoring Platform Obsolescence Augment POR20 | Chassis | Tektronix Sentry replacement | 18 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | EP
V2B COR COR DDR Monitoring Platform Obsolescence Augment POR20 | COR | COR | DDR | V2B | V2B COR COR DDR Monitoring Platform Obsolescence Augment POR20 | Chassis | Tektronix Sentry replacement | 18 | 2020-07-06 | 2020-08-15 | 2020-09-15 | Active | Log | Upd | SN-0430 | Schedule Change | Approved | 2020-04-10 15:22 | This CR updates the Video to Backbone activity plan with the latest schedule based on the delays due to blackout control and to the Tektronix order that was just completed via Supply Chain
V2B COR COR DDR Monitoring Platform Obsolescence Augment POR20 | COR | COR | DDR | V2B | V2B COR COR DDR Monitoring Platform Obsolescence Augment POR20 | Chassis | Tektronix Sentry replacement | 18 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B CA SAN ELC POR Service Expansions Deployment POR20 | CA | SAN | ELC | V2B | V2B CA SAN ELC POR Service Expansions Deployment POR20 | Card & Optics | UCS blades and config | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
V2B COR COR DDR POR Service Expansions Deployment POR20 | COR | COR | DDR | V2B | V2B COR COR DDR POR Service Expansions Deployment POR20 | Card & Optics | UCS blades and config | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
V2B CA SAN ELC Market Blackout Control Deployment POR20 | CA | SAN | ELC | V2B | V2B CA SAN ELC Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) |  |  |  |  | Deleted | EP
V2B CA SAN ELC Market Blackout Control Deployment POR20 | CA | SAN | ELC | V2B | V2B CA SAN ELC Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) |  |  |  |  | Deleted | Log | Del | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B CA SAB SAB Market Blackout Control Deployment POR20 | CA | SAB | SAB | V2B | V2B CA SAB SAB Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) |  |  |  |  | Deleted | EP
V2B CA SAB SAB Market Blackout Control Deployment POR20 | CA | SAB | SAB | V2B | V2B CA SAB SAB Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) |  |  |  |  | Deleted | Log | Del | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B CE OKC TUL Market Blackout Control Deployment POR20 | CE | TUL | TUL | V2B | V2B CE TUL TUL V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-12-06 | 2021-01-31 | 2021-02-28 | Active | EP
V2B CE OKC TUL Market Blackout Control Deployment POR20 | CE | TUL | TUL | V2B | V2B CE TUL TUL V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-12-06 | 2021-01-31 | 2021-02-28 | Active | Log | Upd | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B CE OMA OMM Market Blackout Control Deployment POR20 | CE | OMA | OMM | V2B | V2B CE OMA OMM V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-12-06 | 2021-01-31 | 2021-02-28 | Active | EP
V2B CE OMA OMM Market Blackout Control Deployment POR20 | CE | OMA | OMM | V2B | V2B CE OMA OMM V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-12-06 | 2021-01-31 | 2021-02-28 | Active | Log | Upd | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B SE GAN GNS Market Blackout Control Deployment POR20 | SE | GAN | GNS | V2B | V2B SE GAN GNS Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) |  |  |  |  | Deleted | EP
V2B SE GAN GNS Market Blackout Control Deployment POR20 | SE | GAN | GNS | V2B | V2B SE GAN GNS Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-08-06 | 2020-10-15 | 2020-11-15 | Deleted | Log | Upd | SN-0430 | Schedule Change | Approved | 2020-04-10 15:22 | This CR updates the Video to Backbone activity plan with the latest schedule based on the delays due to blackout control and to the Tektronix order that was just completed via Supply Chain
V2B SE GAN GNS Market Blackout Control Deployment POR20 | SE | GAN | GNS | V2B | V2B SE GAN GNS Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) |  |  |  |  | Deleted | Log | Del | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B SE GLA BTR Market Blackout Control Deployment POR20 | SE | BTR | BTR | V2B | V2B SE BTR BTR Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) |  |  |  |  | Deleted | EP
V2B SE GLA BTR Market Blackout Control Deployment POR20 | SE | BTR | BTR | V2B | V2B SE BTR BTR Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-08-06 | 2020-10-15 | 2020-11-15 | Deleted | Log | Upd | SN-0430 | Schedule Change | Approved | 2020-04-10 15:22 | This CR updates the Video to Backbone activity plan with the latest schedule based on the delays due to blackout control and to the Tektronix order that was just completed via Supply Chain
V2B SE GLA BTR Market Blackout Control Deployment POR20 | SE | BTR | BTR | V2B | V2B SE BTR BTR Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) |  |  |  |  | Deleted | Log | Del | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B SE GLA ELM Market Blackout Control Deployment POR20 | SE | NOR | ELM | V2B | V2B SE NOR ELM Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) |  |  |  |  | Deleted | EP
V2B SE GLA ELM Market Blackout Control Deployment POR20 | SE | NOR | ELM | V2B | V2B SE NOR ELM Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-08-06 | 2020-10-15 | 2020-11-15 | Deleted | Log | Upd | SN-0430 | Schedule Change | Approved | 2020-04-10 15:22 | This CR updates the Video to Backbone activity plan with the latest schedule based on the delays due to blackout control and to the Tektronix order that was just completed via Supply Chain
V2B SE GLA ELM Market Blackout Control Deployment POR20 | SE | NOR | ELM | V2B | V2B SE NOR ELM Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) |  |  |  |  | Deleted | Log | Del | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B SE GCT PNS Market Blackout Control Deployment POR20 | SE | GCT | PNS | V2B | V2B SE GCT PNS Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) |  |  |  |  | Deleted | EP
V2B SE GCT PNS Market Blackout Control Deployment POR20 | SE | GCT | PNS | V2B | V2B SE GCT PNS Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-08-06 | 2020-10-15 | 2020-11-15 | Deleted | Log | Upd | SN-0430 | Schedule Change | Approved | 2020-04-10 15:22 | This CR updates the Video to Backbone activity plan with the latest schedule based on the delays due to blackout control and to the Tektronix order that was just completed via Supply Chain
V2B SE GCT PNS Market Blackout Control Deployment POR20 | SE | GCT | PNS | V2B | V2B SE GCT PNS Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) |  |  |  |  | Deleted | Log | Del | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B SE MGA MCN Market Blackout Control Deployment POR20 | SE | MGA | MCN | V2B | V2B SE MGA MCN Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) |  |  |  |  | Deleted | EP
V2B SE MGA MCN Market Blackout Control Deployment POR20 | SE | MGA | MCN | V2B | V2B SE MGA MCN Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-08-06 | 2020-10-15 | 2020-11-15 | Deleted | Log | Upd | SN-0430 | Schedule Change | Approved | 2020-04-10 15:22 | This CR updates the Video to Backbone activity plan with the latest schedule based on the delays due to blackout control and to the Tektronix order that was just completed via Supply Chain
V2B SE MGA MCN Market Blackout Control Deployment POR20 | SE | MGA | MCN | V2B | V2B SE MGA MCN Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) |  |  |  |  | Deleted | Log | Del | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B SW ARZ CHD Market Blackout Control Deployment POR20 | SW | ARZ | CHD | V2B | V2B SW ARZ CHD Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) |  |  |  |  | Deleted | EP
V2B SW ARZ CHD Market Blackout Control Deployment POR20 | SW | ARZ | CHD | V2B | V2B SW ARZ CHD Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-08-06 | 2020-10-15 | 2020-11-15 | Deleted | Log | Upd | SN-0430 | Schedule Change | Approved | 2020-04-10 15:22 | This CR updates the Video to Backbone activity plan with the latest schedule based on the delays due to blackout control and to the Tektronix order that was just completed via Supply Chain
V2B SW ARZ CHD Market Blackout Control Deployment POR20 | SW | ARZ | CHD | V2B | V2B SW ARZ CHD Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) |  |  |  |  | Deleted | Log | Del | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B SW LAS HEN Market Blackout Control Deployment POR20 | SW | LAS | HEN | V2B | V2B SW LAS HEN Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) |  |  |  |  | Deleted | EP
V2B SW LAS HEN Market Blackout Control Deployment POR20 | SW | LAS | HEN | V2B | V2B SW LAS HEN Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-08-06 | 2020-10-15 | 2020-11-15 | Deleted | Log | Upd | SN-0430 | Schedule Change | Approved | 2020-04-10 15:22 | This CR updates the Video to Backbone activity plan with the latest schedule based on the delays due to blackout control and to the Tektronix order that was just completed via Supply Chain
V2B SW LAS HEN Market Blackout Control Deployment POR20 | SW | LAS | HEN | V2B | V2B SW LAS HEN Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) |  |  |  |  | Deleted | Log | Del | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B CE ARK NWA Market Blackout Control Deployment POR20 | CE | NWA | NWA | V2B | V2B CE NWA NWA V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-12-06 | 2021-01-31 | 2021-02-28 | Active | EP
V2B CE ARK NWA Market Blackout Control Deployment POR20 | CE | NWA | NWA | V2B | V2B CE NWA NWA V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-12-06 | 2021-01-31 | 2021-02-28 | Active | Log | Upd | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B CE KAN WIC Market Blackout Control Deployment POR20 | CE | KAN | WIC | V2B | V2B CE KAN WIC V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-12-06 | 2021-01-31 | 2021-02-28 | Active | EP
V2B CE KAN WIC Market Blackout Control Deployment POR20 | CE | KAN | WIC | V2B | V2B CE KAN WIC V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-12-06 | 2021-01-31 | 2021-02-28 | Active | Log | Upd | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B CE OKC OKC Market Blackout Control Deployment POR20 | CE | OKC | OKC | V2B | V2B CE OKC OKC V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-12-06 | 2021-01-31 | 2021-02-28 | Active | EP
V2B CE OKC OKC Market Blackout Control Deployment POR20 | CE | OKC | OKC | V2B | V2B CE OKC OKC V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-12-06 | 2021-01-31 | 2021-02-28 | Active | Log | Upd | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B COR COR DDR Collection Platform Deployment POR20 | COR | COR | DDR | V2B | V2B COR COR DDR Collection Platform Deployment POR20 | Chassis | IRD (1 RU), satellite and Zixi |  |  |  |  | Deleted | EP
V2B COR COR DDR Collection Platform Deployment POR20 | COR | COR | DDR | V2B | V2B COR COR DDR Collection Platform Deployment POR20 | Chassis | IRD (1 RU), satellite and Zixi | 30 | 2020-07-06 | 2020-10-15 | 2020-12-15 | Deleted | Log | Upd | SN-0430 | Schedule Change | Approved | 2020-04-10 15:22 | This CR updates the Video to Backbone activity plan with the latest schedule based on the delays due to blackout control and to the Tektronix order that was just completed via Supply Chain
V2B COR COR DDR Collection Platform Deployment POR20 | COR | COR | DDR | V2B | V2B COR COR DDR Collection Platform Deployment POR20 | Chassis | IRD (1 RU), satellite and Zixi |  |  |  |  | Deleted | Log | Del | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B NE CON MAN Collection Platform Deployment POR20 | NE | CON | MAN | V2B | V2B NE CON MAN Collection Platform Decom POR20 | Labor | Decom 2 - 3 racks |  |  |  |  | Deleted | EP
V2B NE CON MAN Collection Platform Deployment POR20 | NE | CON | MAN | V2B | V2B NE CON MAN Collection Platform Decom POR20 | Labor | Decom 2 - 3 racks | 1 | 2020-11-06 | 2020-12-15 | 2020-12-15 | Deleted | Log | Upd | SN-0430 | Schedule Change | Approved | 2020-04-10 15:22 | This CR updates the Video to Backbone activity plan with the latest schedule based on the delays due to blackout control and to the Tektronix order that was just completed via Supply Chain
V2B NE CON MAN Collection Platform Deployment POR20 | NE | CON | MAN | V2B | V2B NE CON MAN Collection Platform Decom POR20 | Labor | Decom 2 - 3 racks |  |  |  |  | Deleted | Log | Del | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B NE RHD WWK Collection Platform Deployment POR20 | NE | RHD | WWK | V2B | V2B NE RHD WWK Collection Platform Decom POR20 | Labor | Decom 2 - 3 racks |  |  |  |  | Deleted | EP
V2B NE RHD WWK Collection Platform Deployment POR20 | NE | RHD | WWK | V2B | V2B NE RHD WWK Collection Platform Decom POR20 | Labor | Decom 2 - 3 racks | 1 | 2020-11-06 | 2020-12-15 | 2020-12-15 | Deleted | Log | Upd | SN-0430 | Schedule Change | Approved | 2020-04-10 15:22 | This CR updates the Video to Backbone activity plan with the latest schedule based on the delays due to blackout control and to the Tektronix order that was just completed via Supply Chain
V2B NE RHD WWK Collection Platform Deployment POR20 | NE | RHD | WWK | V2B | V2B NE RHD WWK Collection Platform Decom POR20 | Labor | Decom 2 - 3 racks |  |  |  |  | Deleted | Log | Del | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B SE MGA MCN Collection Platform Deployment POR20 | SE | MGA | MCN | V2B | V2B SE MGA MCN Collection Platform Decom POR20 | Labor | Decom 2 - 3 racks |  |  |  |  | Deleted | EP
V2B SE MGA MCN Collection Platform Deployment POR20 | SE | GAN | GNS | V2B | V2B SE MGA MCN Collection Platform Decom POR20 | Labor | Decom 2 - 3 racks | 1 | 2020-09-06 | 2020-10-15 | 2020-12-15 | Deleted | Log | Upd | SN-0221 | True up | Approved | 2020-02-14 15:58 | This CR updates the Video to Backbone activity plan based on January actuals moving a missed January CL accrual ( 20k) to December and using underspend in January to cover accelerated equipment needed for TVRO Maintenance in February ( 11k)
V2B SE MGA MCN Collection Platform Deployment POR20 | SE | MGA | MCN | V2B | V2B SE MGA MCN Collection Platform Decom POR20 | Labor | Decom 2 - 3 racks | 1 | 2020-09-06 | 2020-10-15 | 2020-12-15 | Deleted | Log | Upd | SN-0378 | Schedule Change | Approved | 2020-03-20 15:42 | This CR makes some minor corrections to the POR; there is no financial impact
V2B SE MGA MCN Collection Platform Deployment POR20 | SE | MGA | MCN | V2B | V2B SE MGA MCN Collection Platform Decom POR20 | Labor | Decom 2 - 3 racks | 1 | 2020-11-06 | 2020-12-15 | 2020-12-15 | Deleted | Log | Upd | SN-0430 | Schedule Change | Approved | 2020-04-10 15:22 | This CR updates the Video to Backbone activity plan with the latest schedule based on the delays due to blackout control and to the Tektronix order that was just completed via Supply Chain
V2B SE MGA MCN Collection Platform Deployment POR20 | SE | MGA | MCN | V2B | V2B SE MGA MCN Collection Platform Decom POR20 | Labor | Decom 2 - 3 racks |  |  |  |  | Deleted | Log | Del | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B SE GLA BTR Collection Platform Deployment POR20 | SE | BTR | BTR | V2B | V2B SE BTR BTR Collection Platform Decom POR20 | Labor | Decom 2 - 3 racks |  |  |  |  | Deleted | EP
V2B SE GLA BTR Collection Platform Deployment POR20 | SE | BTR | BTR | V2B | V2B SE BTR BTR Collection Platform Decom POR20 | Labor | Decom 2 - 3 racks |  |  |  |  | Deleted | Log | Del | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B SE GLA ELM Collection Platform Deployment POR20 | SE | NOR | ELM | V2B | V2B SE NOR ELM Collection Platform Decom POR20 | Labor | Decom 2 - 3 racks |  |  |  |  | Deleted | EP
V2B SE GLA ELM Collection Platform Deployment POR20 | SE | NOR | ELM | V2B | V2B SE NOR ELM Collection Platform Decom POR20 | Labor | Decom 2 - 3 racks |  |  |  |  | Deleted | Log | Del | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B SE GCT PNS Collection Platform Deployment POR20 | SE | GCT | PNS | V2B | V2B SE GCT PNS Collection Platform Decom POR20 | Labor | Decom 2 - 3 racks |  |  |  |  | Deleted | EP
V2B SE GCT PNS Collection Platform Deployment POR20 | SE | GCT | PNS | V2B | V2B SE GCT PNS Collection Platform Decom POR20 | Labor | Decom 2 - 3 racks |  |  |  |  | Deleted | Log | Del | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B SE GAN GNS Collection Platform Deployment POR20 | SE | GAN | GNS | V2B | V2B SE GAN GNS Collection Platform Decom POR20 | Labor | Decom 2 - 3 racks |  |  |  |  | Deleted | EP
V2B SE GAN GNS Collection Platform Deployment POR20 | SE | MGA | MCN | V2B | V2B SE GAN GNS Market Blackout Control Deployment POR20 | Labor | Decom 2 - 3 racks | 1 | 2020-11-06 | 2020-12-15 |  | Deleted | Log | Upd | SN-0050 | New | Approved | 2020-02-06 10:22 | This CR makes some administrative corrections to the Plan of Record
V2B SE GAN GNS Collection Platform Deployment POR20 | SE | GAN | GNS | V2B | V2B SE GAN GNS Collection Platform Decom POR20 | Labor | Decom 2 - 3 racks | 1 | 2020-11-06 | 2020-12-15 |  | Deleted | Log | Upd | SN-0378 | Schedule Change | Approved | 2020-03-20 15:42 | This CR makes some minor corrections to the POR; there is no financial impact
V2B SE GAN GNS Collection Platform Deployment POR20 | SE | GAN | GNS | V2B | V2B SE GAN GNS Collection Platform Decom POR20 | Labor | Decom 2 - 3 racks |  |  |  |  | Deleted | Log | Del | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B VA HRD VBC Collection Platform Deployment POR20 | VA | HRD | VBC | V2B | V2B VA HRD VBC Collection Platform Decom POR20 | Labor | Decom 2 - 3 racks |  |  |  |  | Deleted | EP
V2B VA HRD VBC Collection Platform Deployment POR20 | VA | HRD | VBC | V2B | V2B VA HRD VBC Collection Platform Decom POR20 | Labor | Decom 2 - 3 racks | 1 | 2020-08-06 | 2020-09-15 | 2020-12-15 | Deleted | Log | Upd | SN-0430 | Schedule Change | Approved | 2020-04-10 15:22 | This CR updates the Video to Backbone activity plan with the latest schedule based on the delays due to blackout control and to the Tektronix order that was just completed via Supply Chain
V2B VA HRD VBC Collection Platform Deployment POR20 | VA | HRD | VBC | V2B | V2B VA HRD VBC Collection Platform Decom POR20 | Labor | Decom 2 - 3 racks |  |  |  |  | Deleted | Log | Del | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B VA NVA MFD Collection Platform Deployment POR20 | VA | NVA | MFD | V2B | V2B VA NVA MFD Collection Platform Decom POR20 | Labor | Decom 2 - 3 racks |  |  |  |  | Deleted | EP
V2B VA NVA MFD Collection Platform Deployment POR20 | VA | NVA | MFD | V2B | V2B VA NVA MFD Collection Platform Decom POR20 | Labor | Decom 2 - 3 racks | 1 | 2020-11-06 | 2020-12-15 | 2020-12-15 | Deleted | Log | Upd | SN-0430 | Schedule Change | Approved | 2020-04-10 15:22 | This CR updates the Video to Backbone activity plan with the latest schedule based on the delays due to blackout control and to the Tektronix order that was just completed via Supply Chain
V2B VA NVA MFD Collection Platform Deployment POR20 | VA | NVA | MFD | V2B | V2B VA NVA MFD Collection Platform Decom POR20 | Labor | Decom 2 - 3 racks |  |  |  |  | Deleted | Log | Del | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B VA ROA RON Collection Platform Deployment POR20 | VA | ROA | RON | V2B | V2B VA ROA RON Collection Platform Decom POR20 | Labor | Decom 2 - 3 racks |  |  |  |  | Deleted | EP
V2B VA ROA RON Collection Platform Deployment POR20 | VA | ROA | RON | V2B | V2B VA ROA RON Collection Platform Decom POR20 | Labor | Decom 2 - 3 racks | 1 | 2020-11-06 | 2020-12-15 | 2020-12-15 | Deleted | Log | Upd | SN-0430 | Schedule Change | Approved | 2020-04-10 15:22 | This CR updates the Video to Backbone activity plan with the latest schedule based on the delays due to blackout control and to the Tektronix order that was just completed via Supply Chain
V2B VA ROA RON Collection Platform Deployment POR20 | VA | ROA | RON | V2B | V2B VA ROA RON Collection Platform Decom POR20 | Labor | Decom 2 - 3 racks |  |  |  |  | Deleted | Log | Del | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B COR COR DDR Monitoring Platform Expansion Augment POR20 | COR | COR | DDR | V2B | V2B COR COR DDR Monitoring Platform Expansion Augment POR20 | Chassis | Tektronix Sentry |  |  |  |  | Deleted | EP
V2B COR COR DDR Monitoring Platform Expansion Augment POR20 | COR | COR | DDR | V2B | V2B COR COR DDR Monitoring Platform Expansion Augment POR20 | Chassis | Tektronix Sentry |  |  |  |  | Deleted | Log | Del | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B COR COR ATL NOC Infrastructure Enablement POR20 | COR | COR | ATL | V2B | V2B COR COR ATL NOC Infrastructure Augment POR20 | Labor | NOC Infrastructure |  |  |  |  | Deleted | EP
V2B COR COR ATL NOC Infrastructure Enablement POR20 | COR | COR | ATL | V2B | V2B COR COR ATL NOC Infrastructure Augment POR20 | Labor | NOC Infrastructure | 1 | 2020-10-06 | 2020-11-30 | 2020-12-15 | Deleted | Log | Upd | SN-0579 | True up | Approved | 2020-05-14 16:38 | This CR updates the Video to Backbone plan based on April actuals and on updates for the Q2 forecast It transfers 197 905 to Supply Chain rate savings and updates the forecast based on early receipt of a 480k Telestream order expected in July
V2B COR COR ATL NOC Infrastructure Enablement POR20 | COR | COR | ATL | V2B | V2B COR COR ATL NOC Infrastructure Augment POR20 | Labor | NOC Infrastructure |  |  |  |  | Deleted | Log | Del | SN-0877 | Scope Change | Approved | 2020-08-28 14:42 | This CR returns 232 500 from three Video to Backbone projects to support the request from the Portfolio to reduce risk
V2B CA SAN ELC Platform Refresh Augment POR20 | CA | SAN | ELC | V2B | V2B CA SAN ELC Platform Refresh Augment POR20 | Card & Optics | Replace UCS blades | 24 | 2020-11-15 | 2020-12-31 | 2020-12-31 | Active | EP
V2B CA SAN ELC Platform Refresh Augment POR20 | CA | SAN | ELC | V2B | V2B CA SAN ELC Platform Refresh Augment POR20 | Card & Optics | Replace UCS blades | 24 | 2020-11-15 | 2020-12-31 | 2020-12-31 | Active | Log | Upd | SN-1015 | True up | Approved | 2020-10-16 14:50 | This CR updates the Video to Backbone plan based on September actuals by moving 315k to Oct for PSX cluster replacement orders delay and moving 375k to Nov for ESPN receivers to support POR and to cover replacement of 50 M3 blades with M5s at ELC DDR lab
V2B COR COR DDR Platform Refresh Augment POR20 | COR | COR | DDR | V2B | V2B COR COR DDR Platform Refresh Augment POR20 | Card & Optics | Replace UCS blades | 24 | 2020-11-15 | 2020-12-31 | 2020-12-31 | Active | EP
V2B COR COR DDR Platform Refresh Augment POR20 | COR | COR | DDR | V2B | V2B COR COR DDR Platform Refresh Augment POR20 | Card & Optics | Replace UCS blades | 24 | 2020-11-15 | 2020-12-31 | 2020-12-31 | Active | Log | Upd | SN-1015 | True up | Approved | 2020-10-16 14:50 | This CR updates the Video to Backbone plan based on September actuals by moving 315k to Oct for PSX cluster replacement orders delay and moving 375k to Nov for ESPN receivers to support POR and to cover replacement of 50 M3 blades with M5s at ELC DDR lab
V2B CA SAN ELC SD Copy Retirement Decom POR20 | CA | SAN | ELC | V2B | V2B CA SAN ELC SD Copy Retirement Decom POR20 | Labor | Config of encoders and monitors | 1 | 2020-09-08 | 2020-10-15 | 2020-11-15 | Active | EP
V2B CA SAN ELC SD Copy Retirement Decom POR20 | CA | SAN | ELC | V2B | V2B CA SAN ELC SD Copy Retirement Decom POR20 | Labor | Config of encoders and monitors | 1 | 2020-09-08 | 2020-10-15 | 2020-11-15 | Active | Log | Upd | SN-0708 | Schedule Change | Approved | 2020-06-30 11:15 | This CR updates the Video to Backbone plan by moving 37 500 from July Aug to Sept to purchase blades and RAM to support SD and reallocates 200k from July for StratOS Lifecycle and New Objectives to purchase vDCMs to replace a PSX cluster moving the funds
V2B COR COR DDR SD Copy Retirement Decom POR20 | COR | COR | DDR | V2B | V2B COR COR DDR SD Copy Retirement Decom POR20 | Labor | Config of encoders and monitors | 1 | 2020-09-08 | 2020-10-15 | 2020-11-15 | Active | EP
V2B COR COR DDR SD Copy Retirement Decom POR20 | COR | COR | DDR | V2B | V2B COR COR DDR SD Copy Retirement Decom POR20 | Labor | Config of encoders and monitors | 1 | 2020-09-08 | 2020-10-15 | 2020-11-15 | Active | Log | Upd | SN-0708 | Schedule Change | Approved | 2020-06-30 11:15 | This CR updates the Video to Backbone plan by moving 37 500 from July Aug to Sept to purchase blades and RAM to support SD and reallocates 200k from July for StratOS Lifecycle and New Objectives to purchase vDCMs to replace a PSX cluster moving the funds
V2B COR COR ATL StratOS New Objectives Augment POR20 | COR | COR | ATL | V2B | V2B COR COR ATL StratOS New Objectives Augment POR20 | Labor | StratOS | 2 | 2020-09-15 | 2020-10-15 | 2020-12-31 | Active | EP
V2B COR COR ATL StratOS New Objectives Augment POR20 | COR | COR | ATL | V2B | V2B COR COR ATL StratOS New Objectives Augment POR20 | Labor | StratOS | 1 | 2020-07-06 | 2020-08-31 | 2020-10-31 | Active | Log | Upd | SN-0579 | True up | Approved | 2020-05-14 16:38 | This CR updates the Video to Backbone plan based on April actuals and on updates for the Q2 forecast It transfers 197 905 to Supply Chain rate savings and updates the forecast based on early receipt of a 480k Telestream order expected in July
V2B COR COR ATL StratOS New Objectives Augment POR20 | COR | COR | ATL | V2B | V2B COR COR ATL StratOS New Objectives Augment POR20 | Labor | StratOS | 1 | 2020-08-06 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0708 | Schedule Change | Approved | 2020-06-30 11:15 | This CR updates the Video to Backbone plan by moving 37 500 from July Aug to Sept to purchase blades and RAM to support SD and reallocates 200k from July for StratOS Lifecycle and New Objectives to purchase vDCMs to replace a PSX cluster moving the funds
V2B COR COR ATL StratOS New Objectives Augment POR20 | COR | COR | ATL | V2B | V2B COR COR ATL StratOS New Objectives Augment POR20 | Labor | StratOS | 2 | 2020-09-15 | 2020-10-15 | 2020-12-31 | Active | Log | Upd | SN-0901 | True up | Approved | 2020-09-11 16:01 | This CR updates the Video to Backbone plan based on August actuals by moving 520k in material orders that were not received to September
V2B CA SAN ELC 4K UHD HDR Content Augment POR20 | CA | SAN | ELC | V2B | V2B CA SAN ELC 4k UHD HDR Content Augment POR20 | Chassis | 4K UHD HDR | 1 | 2020-06-06 | 2020-08-15 | 2020-12-15 | Active | EP
V2B COR COR DVY 4K UHD HDR Content Augment POR20 | COR | COR | DVY | V2B | V2B COR COR DVY 4k UHD HDR Content Augment POR20 | Chassis | 4K UHD HDR | 1 | 2020-07-06 | 2020-08-15 | 2020-12-15 | Active | EP
V2B COR COR DDR 4K UHD HDR Content Augment POR20 | COR | COR | DDR | V2B | V2B COR COR DDR 4k UHD HDR Content Augment POR20 | Chassis | 4K UHD HDR | 1 | 2020-07-06 | 2020-08-15 | 2020-12-15 | Active | EP
V2B CA SAN ELC 4K UHD HDR Monitoring Augment POR20 | CA | SAN | ELC | V2B | V2B CA SAN ELC 4k UHD HDR Monitoring Augment POR20 | Chassis | Tektronix Sentry |  |  |  |  | Deleted | EP
V2B CA SAN ELC 4K UHD HDR Monitoring Augment POR20 | CA | SAN | ELC | V2B | V2B CA SAN ELC 4k UHD HDR Monitoring Augment POR20 | Chassis | Tektronix Sentry |  |  |  |  | Deleted | Log | Del | SN-0745 | True up | Approved | 2020-07-09 15:35 | This CR updates the V2B plan based on June actuals by moving 66k in material forecast from June to July to cover a single 4k UHD HDR Monitoring Platform order that was originally forecast as a couple of order spanning two months
V2B COR COR DVY 4K UHD HDR Monitoring Augment POR20 | COR | COR | DVY | V2B | V2B COR COR DVY 4k UHD HDR Monitoring Augment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-06 | 2020-08-15 | 2020-12-15 | Active | EP
V2B COR COR DDR 4K UHD HDR Monitoring Augment POR20 | COR | COR | DDR | V2B | V2B COR COR DDR 4k UHD HDR Monitoring Augment POR20 | Chassis | Tektronix Sentry |  |  |  |  | Deleted | EP
V2B COR COR DDR 4K UHD HDR Monitoring Augment POR20 | COR | COR | DDR | V2B | V2B COR COR DDR 4k UHD HDR Monitoring Augment POR20 | Chassis | Tektronix Sentry |  |  |  |  | Deleted | Log | Del | SN-0745 | True up | Approved | 2020-07-09 15:35 | This CR updates the V2B plan based on June actuals by moving 66k in material forecast from June to July to cover a single 4k UHD HDR Monitoring Platform order that was originally forecast as a couple of order spanning two months
V2B CA SAN ELC CB Infrastructure Augment POR20 | CA | SAN | ELC | V2B | V2B CA SAN ELC CB Infrastructure Augment POR20 | Card & Optics | UCS blades and config |  |  |  |  | Deleted | EP
V2B CA SAN ELC CB Infrastructure Augment POR20 | CA | SAN | ELC | V2B | V2B CA SAN ELC CB Infrastructure Augment POR20 | Card & Optics | UCS blades and config |  |  |  |  | Deleted | Log | Del | SN-0617 | Scope Change | Approved | 2020-06-05 14:52 | This CR corrects the Video to Backbone POR by removing the El Cajon CB Infrastructure Engineering Project that was already deferred for Duke Dr just missed in the last CR for this location
V2B COR COR DDR CB Infrastructure Augment POR20 | COR | COR | DDR | V2B | V2B COR COR DDR CB Infrastructure Augment POR20 | Chassis | CB Infrastructure |  |  |  |  | Deleted | EP
V2B COR COR DDR CB Infrastructure Augment POR20 | COR | COR | DDR | V2B | V2B COR COR DDR CB Infrastructure Augment POR20 | Chassis | CB Infrastructure |  |  |  |  | Deleted | Log | Del | SN-0579 | True up | Approved | 2020-05-14 16:38 | This CR updates the Video to Backbone plan based on April actuals and on updates for the Q2 forecast It transfers 197 905 to Supply Chain rate savings and updates the forecast based on early receipt of a 480k Telestream order expected in July
V2B COR COR ATL Executive Channel Augment POR20 | COR | COR | ATL | V2B | V2B COR COR ATL Executive Channel Augment POR20 | Card & Optics | Exec Channel | 2 | 2020-09-15 | 2020-10-15 | 2020-11-15 | Active | EP
V2B COR COR ATL Executive Channel Augment POR20 | COR | COR | ATL | V2B | V2B COR COR ATL Executive Channel Augment POR20 | Card & Optics | Exec Channel | 2 | 2020-09-15 | 2020-10-15 | 2020-11-15 | Active | Log | Upd | SN-0901 | True up | Approved | 2020-09-11 16:01 | This CR updates the Video to Backbone plan based on August actuals by moving 520k in material orders that were not received to September
V2B COR COR DDR Executive Channel Augment POR20 | COR | COR | DDR | V2B | V2B COR COR DDR Executive Channel Augment POR20 | Card & Optics | Exec Channel | 1 | 2020-08-06 | 2020-09-15 | 2020-10-15 | Active | EP
V2B CA SAN ELC Media H264 HEVC Alignment POR20 | CA | SAN | ELC | V2B | V2B CA SAN ELC Media H264 HEVC Alignment POR20 | Card & Optics | UCS blades and config | 1 | 2020-09-15 | 2020-10-15 | 2020-11-15 | Active | EP
V2B CA SAN ELC Media H264 HEVC Alignment POR20 | CA | SAN | ELC | V2B | V2B CA SAN ELC Media H264 HEVC Alignment POR20 | Card & Optics | UCS blades and config | 1 | 2020-09-15 | 2020-10-15 | 2020-11-15 | Active | Log | Upd | SN-0901 | True up | Approved | 2020-09-11 16:01 | This CR updates the Video to Backbone plan based on August actuals by moving 520k in material orders that were not received to September
V2B COR COR DDR Media H264 HEVC Alignment POR20 | COR | COR | DDR | V2B | V2B COR COR DDR Media H264 HEVC Alignment POR20 | Standard | H264 HEVC | 1 | 2020-09-15 | 2020-10-15 | 2020-11-15 | Active | EP
V2B COR COR DDR Media H264 HEVC Alignment POR20 | COR | COR | DDR | V2B | V2B COR COR DDR Media H264 HEVC Alignment POR20 | Standard | H264 HEVC | 1 | 2020-09-15 | 2020-10-15 | 2020-11-15 | Active | Log | Upd | SN-0901 | True up | Approved | 2020-09-11 16:01 | This CR updates the Video to Backbone plan based on August actuals by moving 520k in material orders that were not received to September
V2B SE NAT AT2 Terrestrial Mezzanine Contribution Augment POR20 | COR | NAT | AT2 | V2B | V2B SE NAT AT2 Terrestrial Mezzanine Contribution Augment POR20 | Labor | Contribution | 1 | 2020-06-06 | 2020-07-31 | 2020-12-31 | Active | EP
V2B SE NAT AT2 Terrestrial Mezzanine Contribution Augment POR20 | COR | NAT | AT2 | V2B | V2B SE NAT AT2 Terrestrial Mezzanine Contribution Augment POR20 | Labor | Contribution | 1 | 2020-06-06 | 2020-07-31 | 2020-10-31 | Active | Log | Upd | SN-0579 | True up | Approved | 2020-05-14 16:38 | This CR updates the Video to Backbone plan based on April actuals and on updates for the Q2 forecast It transfers 197 905 to Supply Chain rate savings and updates the forecast based on early receipt of a 480k Telestream order expected in July
V2B SE NAT AT2 Terrestrial Mezzanine Contribution Augment POR20 | COR | NAT | AT2 | V2B | V2B SE NAT AT2 Terrestrial Mezzanine Contribution Augment POR20 | Labor | Contribution | 1 | 2020-06-06 | 2020-07-31 | 2020-12-31 | Active | Log | Upd | SN-0801 | Cost Change | Approved | 2020-07-31 14:24 | This CR updates the Video to Backbone plan by returning 130k of 175k budgeted for Executive Channel improvements in August and shifts 100k planned for Terrestrial and Mezzanine Content Acquisition from August to November Also transfers 30k to supply chain
V2B CA SAN ELC TVRO Maintenance Augment POR20 | CA | SAN | ELC | V2B | V2B CA SAN ELC TVRO Maintenance Augment POR20 | Labor | TVRO | 1 | 2020-04-06 | 2020-06-15 | 2020-10-15 | Active | EP
V2B COR COR DDR TVRO Maintenance Augment POR20 | COR | COR | DDR | V2B | V2B COR COR DDR TVRO Maintenance Augment POR20 | Labor | TVRO | 1 | 2020-05-06 | 2020-06-15 | 2020-10-15 | Active | EP
V2B CA SAN ELC VDN VDE Transition Deployment POR20 | CA | SAN | ELC | V2B | V2B CA SAN ELC VDN VDE Transition Deployment POR20 | Chassis | UCS chassis and blades |  |  |  |  | Deleted | EP
V2B CA SAN ELC VDN VDE Transition Deployment POR20 | CA | SAN | ELC | V2B | V2B CA SAN ELC VDN VDE Transition Deployment POR20 | Chassis | UCS chassis and blades |  |  |  |  | Deleted | Log | Del | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B COR COR DDR VDN VDE Transition Deployment POR20 | COR | COR | DDR | V2B | V2B COR COR DDR VDN VDE Transition Deployment POR20 | Standard | VDN VDE |  |  |  |  | Deleted | EP
V2B COR COR DDR VDN VDE Transition Deployment POR20 | COR | COR | DDR | V2B | V2B COR COR DDR VDN VDE Transition Deployment POR20 | Standard | VDN VDE |  |  |  |  | Deleted | Log | Del | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
V2B CA ORG RSM Market Blackout Control Deployment POR20 | CA | ORG | RSM | V2B | V2B CA ORG RSM Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) |  |  |  |  | Deleted | EP
V2B CA ORG RSM Market Blackout Control Deployment POR20 | CA | ORG | RSM | V2B | V2B CA ORG RSM Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-08-06 | 2020-10-15 | 2020-11-15 | Deleted | Log | New | SN-0050 | New | Approved | 2020-02-06 10:22 | This CR makes some administrative corrections to the Plan of Record
V2B CA ORG RSM Market Blackout Control Deployment POR20 | CA | ORG | RSM | V2B | V2B CA ORG RSM Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) |  |  |  |  | Deleted | Log | Del | SN-0501 | COVID-19 Related | Approved | 2020-05-05 19:30 | This CR defers about 8M from the Video to Backbone plan to 2021 to support the COVID 19 deferral initiative These initiatives were dependent upon Centralized Blackout Control which has been delayed due to contract disagreements with Comcast
VA-RSM-1x Ixia E100 | CA | ORG | RSM | Visibility Architecture | VIA CA ORG RSM Visibility Architecture Gear Decom POR20 | Chassis | 1x Ixia E100 Chassis |  |  |  |  | Deleted | EP
VA-RSM-1x Ixia E100 | CA | ORG | RSM | Visibility Architecture | VIA CA ORG RSM Visibility Architecture Gear Decom POR20 | Chassis | 1x Ixia E100 Chassis |  |  |  |  | Deleted | Log | Del | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-RSM-1x Arista DCS-7280CR2A-60-F | CA | ORG | RSM | Visibility Architecture | VIA CA ORG RSM Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-04-20 | Active | EP
VA-RSM-1x Arista DCS-7280CR2A-60-F | CA | ORG | RSM | Visibility Architecture | VIA CA ORG RSM Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-04-20 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-RSM-1x Juniper EX4600 | CA | ORG | RSM | Visibility Architecture | VIA CA ORG RSM Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-04-20 | Active | EP
VA-RSM-1x Juniper EX4600 | CA | ORG | RSM | Visibility Architecture | VIA CA ORG RSM Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-04-20 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-ELC-1x Ixia E100 | CA | SAN | ELC | Visibility Architecture | VIA CA SAN ELC Visibility Architecture Gear Decom POR20 | Chassis | 1x Ixia E100 Chassis |  |  |  |  | Deleted | EP
VA-ELC-1x Ixia E100 | CA | SAN | ELC | Visibility Architecture | VIA CA SAN ELC Visibility Architecture Gear Decom POR20 | Chassis | 1x Ixia E100 Chassis |  |  |  |  | Deleted | Log | Del | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-ELC-1x Arista DCS-7280CR2A-60-F | CA | SAN | ELC | Visibility Architecture | VIA CA SAN ELC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2020-01-01 | 2020-04-20 | 2020-05-04 | Active | EP
VA-ELC-1x Arista DCS-7280CR2A-60-F | CA | SAN | ELC | Visibility Architecture | VIA CA SAN ELC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-04-20 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-ELC-1x Arista DCS-7280CR2A-60-F | CA | SAN | ELC | Visibility Architecture | VIA CA SAN ELC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2020-01-01 | 2020-04-20 | 2020-05-04 | Active | Log | Upd | SN-0559 | True up | Approved | 2020-05-13 11:46 | April Capex variance of 126K due to ancillary items purchase and power requirements charges for Material and associated labor for Capacity adds in addition to BAU install activities Giving back 5848 opex and realigning the funds for rest of the year
VA-ELC-1x Dell R740 | CA | SAN | ELC | Visibility Architecture | VIA CA SAN ELC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R740 Chassis |  |  |  |  | Deleted | EP
VA-ELC-1x Dell R740 | CA | SAN | ELC | Visibility Architecture | VIA CA SAN ELC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R740 Chassis |  |  |  |  | Deleted | Log | Del | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-ELC-1x Juniper EX4600 | CA | SAN | ELC | Visibility Architecture | VIA CA SAN ELC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-01-01 | 2020-04-20 | 2020-05-04 | Active | EP
VA-ELC-1x Juniper EX4600 | CA | SAN | ELC | Visibility Architecture | VIA CA SAN ELC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-04-20 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-ELC-1x Juniper EX4600 | CA | SAN | ELC | Visibility Architecture | VIA CA SAN ELC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-01-01 | 2020-04-20 | 2020-05-04 | Active | Log | Upd | SN-0559 | True up | Approved | 2020-05-13 11:46 | April Capex variance of 126K due to ancillary items purchase and power requirements charges for Material and associated labor for Capacity adds in addition to BAU install activities Giving back 5848 opex and realigning the funds for rest of the year
VA-FED-1x Ixia E100 | CA | SAN | FED | Visibility Architecture | VIA CA SAN FED Visibility Architecture Gear Decom POR20 | Chassis | 1x Ixia E100 Chassis |  |  |  |  | Deleted | EP
VA-FED-1x Ixia E100 | CA | SAN | FED | Visibility Architecture | VIA CA SAN FED Visibility Architecture Gear Decom POR20 | Chassis | 1x Ixia E100 Chassis |  |  |  |  | Deleted | Log | Del | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-FED-1x Arista DCS-7280CR2A-60-F | CA | SAN | FED | Visibility Architecture | VIA CA SAN FED Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2020-01-01 | 2020-04-27 | 2020-05-11 | Active | EP
VA-FED-1x Arista DCS-7280CR2A-60-F | CA | SAN | FED | Visibility Architecture | VIA CA SAN FED Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-04-20 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-FED-1x Arista DCS-7280CR2A-60-F | CA | SAN | FED | Visibility Architecture | VIA CA SAN FED Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2020-01-01 | 2020-04-27 | 2020-05-11 | Active | Log | Upd | SN-0559 | True up | Approved | 2020-05-13 11:46 | April Capex variance of 126K due to ancillary items purchase and power requirements charges for Material and associated labor for Capacity adds in addition to BAU install activities Giving back 5848 opex and realigning the funds for rest of the year
VA-FED-1x Dell R740 | CA | SAN | FED | Visibility Architecture | VIA CA SAN FED Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R740 Chassis |  |  |  |  | Deleted | EP
VA-FED-1x Dell R740 | CA | SAN | FED | Visibility Architecture | VIA CA SAN FED Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R740 Chassis |  |  |  |  | Deleted | Log | Del | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-FED-1x Juniper EX4600 | CA | SAN | FED | Visibility Architecture | VIA CA SAN FED Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-01-01 | 2020-04-27 | 2020-05-11 | Active | EP
VA-FED-1x Juniper EX4600 | CA | SAN | FED | Visibility Architecture | VIA CA SAN FED Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-04-20 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-FED-1x Juniper EX4600 | CA | SAN | FED | Visibility Architecture | VIA CA SAN FED Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-01-01 | 2020-04-27 | 2020-05-11 | Active | Log | Upd | SN-0559 | True up | Approved | 2020-05-13 11:46 | April Capex variance of 126K due to ancillary items purchase and power requirements charges for Material and associated labor for Capacity adds in addition to BAU install activities Giving back 5848 opex and realigning the funds for rest of the year
VA-OKC-1x Ixia E100 | CE | OKC | OKC | Visibility Architecture | VIA CE OKC OKC Visibility Architecture Gear Decom POR20 | Chassis | 1x Ixia E100 Chassis |  |  |  |  | Deleted | EP
VA-OKC-1x Ixia E100 | CE | OKC | OKC | Visibility Architecture | VIA CE OKC OKC Visibility Architecture Gear Decom POR20 | Chassis | 1x Ixia E100 Chassis |  |  |  |  | Deleted | Log | Del | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-OKC-1x Arista DCS-7280CR2A-60-F | CE | OKC | OKC | Visibility Architecture | VIA CE OKC OKC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2020-02-01 | 2020-03-31 | 2020-03-23 | Active | EP
VA-OKC-1x Arista DCS-7280CR2A-60-F | CE | OKC | OKC | Visibility Architecture | VIA CE OKC OKC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2020-02-01 | 2020-03-31 | 2020-03-23 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-OKC-1x Niagra PT-3225 | CE | OKC | OKC | Visibility Architecture | VIA CE OKC OKC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis |  |  |  |  | Deleted | EP
VA-OKC-1x Niagra PT-3225 | CE | OKC | OKC | Visibility Architecture | VIA CE OKC OKC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis |  |  |  |  | Deleted | Log | Del | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-OKC-1x Juniper EX4600 | CE | OKC | OKC | Visibility Architecture | VIA CE OKC OKC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-02-01 | 2020-03-31 | 2020-03-23 | Active | EP
VA-OKC-1x Juniper EX4600 | CE | OKC | OKC | Visibility Architecture | VIA CE OKC OKC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-02-01 | 2020-03-31 | 2020-03-23 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-OMM-1x Juniper EX4600 | CE | OMA | OMM | Visibility Architecture | VIA CE OMA OMM Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-04-01 | 2020-05-31 | 2020-06-08 | Active | EP
VA-OMM-1x Juniper EX4600 | CE | OMA | OMM | Visibility Architecture |  | Chassis | 1x Juniper EX4600 Chassis | 1 | 2019-12-19 | 2020-02-15 | 2020-02-15 | Active | Log | Upd | SN-0052 | New | Canceled | 2019-10-29 09:37 | Visibility Architecture - POR Correction
VA-OMM-1x Juniper EX4600 | CE | OMA | OMM | Visibility Architecture | VIA CE OMA OMM Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-04-01 | 2020-05-31 | 2020-06-08 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-BTR-1x Dell R740 | SE | BTR | BTR | Visibility Architecture | VIA SE BTR BTR Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R740 Chassis |  |  |  |  | Deleted | EP
VA-BTR-1x Dell R740 | SE | BTR | BTR | Visibility Architecture | VIA SE BTR BTR Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R740 Chassis |  |  |  |  | Deleted | Log | Del | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-BTR-1x ExtraHop EDA6200 (Dell R640) | SE | BTR | BTR | Visibility Architecture | VIA SE BTR BTR Visibility Architecture Gear Deployment POR20 | Chassis | 1x ExtraHop EDA6200 (Dell R640) | 1 | 2020-01-01 | 2020-03-31 | 2020-03-16 | Active | EP
VA-BTR-1x ExtraHop EDA6200 (Dell R640) | SE | BTR | BTR | Visibility Architecture | VIA SE BTR BTR Visibility Architecture Gear Deployment POR20 | Chassis | 1x ExtraHop EDA6200 (Dell R640) | 1 | 2020-01-01 | 2020-03-31 | 2020-03-16 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-BTR-1x Juniper EX4600 | SE | BTR | BTR | Visibility Architecture | VIA SE BTR BTR Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-03-16 | Active | EP
VA-BTR-1x Juniper EX4600 | SE | BTR | BTR | Visibility Architecture | VIA SE BTR BTR Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-03-16 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-CHD-1x Ixia E100 | SW | ARZ | CHD | Visibility Architecture | VIA SW ARZ CHD Visibility Architecture Gear Decom POR20 | Chassis | 1x Ixia E100 Chassis |  |  |  |  | Deleted | EP
VA-CHD-1x Ixia E100 | SW | ARZ | CHD | Visibility Architecture | VIA SW ARZ CHD Visibility Architecture Gear Decom POR20 | Chassis | 1x Ixia E100 Chassis |  |  |  |  | Deleted | Log | Del | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-CHD-1x Arista DCS-7280CR2A-60-F | SW | ARZ | CHD | Visibility Architecture | VIA SW ARZ CHD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-11 | Active | EP
VA-CHD-1x Arista DCS-7280CR2A-60-F | SW | ARZ | CHD | Visibility Architecture | VIA SW ARZ CHD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-11 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-CHD-1x Niagra PT-3225 | SW | ARZ | CHD | Visibility Architecture | VIA SW ARZ CHD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis | 3 | 2020-01-01 | 2020-04-30 | 2020-05-11 | Active | EP
VA-CHD-1x Niagra PT-3225 | SW | ARZ | CHD | Visibility Architecture | VIA SW ARZ CHD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis | 3 | 2020-01-01 | 2020-04-30 | 2020-05-11 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-CHD-1x Dell R740 | SW | ARZ | CHD | Visibility Architecture | VIA SW ARZ CHD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R740 Chassis |  |  |  |  | Deleted | EP
VA-CHD-1x Dell R740 | SW | ARZ | CHD | Visibility Architecture | VIA SW ARZ CHD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R740 Chassis |  |  |  |  | Deleted | Log | Del | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-CHD-1x Juniper EX4600 | SW | ARZ | CHD | Visibility Architecture | VIA SW ARZ CHD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-11 | Active | EP
VA-CHD-1x Juniper EX4600 | SW | ARZ | CHD | Visibility Architecture | VIA SW ARZ CHD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-11 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-MCD-1x Ixia E100 | SW | ARZ | MCD | Visibility Architecture | VIA SW ARZ MCD Visibility Architecture Gear Decom POR20 | Chassis | 1x Ixia E100 Chassis |  |  |  |  | Deleted | EP
VA-MCD-1x Ixia E100 | SW | ARZ | MCD | Visibility Architecture | VIA SW ARZ MCD Visibility Architecture Gear Decom POR20 | Chassis | 1x Ixia E100 Chassis |  |  |  |  | Deleted | Log | Del | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-MCD-1x Arista DCS-7280CR2A-60-F | SW | ARZ | MCD | Visibility Architecture | VIA SW ARZ MCD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-11 | Active | EP
VA-MCD-1x Arista DCS-7280CR2A-60-F | SW | ARZ | MCD | Visibility Architecture | VIA SW ARZ MCD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-11 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-MCD-1x Niagra PT-3225 | SW | ARZ | MCD | Visibility Architecture | VIA SW ARZ MCD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis | 3 | 2020-01-01 | 2020-04-30 | 2020-05-11 | Active | EP
VA-MCD-1x Niagra PT-3225 | SW | ARZ | MCD | Visibility Architecture | VIA SW ARZ MCD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis | 3 | 2020-01-01 | 2020-04-30 | 2020-05-11 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-MCD-1x Dell R740 | SW | ARZ | MCD | Visibility Architecture | VIA SW ARZ MCD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R740 Chassis |  |  |  |  | Deleted | EP
VA-MCD-1x Dell R740 | SW | ARZ | MCD | Visibility Architecture | VIA SW ARZ MCD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R740 Chassis |  |  |  |  | Deleted | Log | Del | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-MCD-1x Juniper EX4600 | SW | ARZ | MCD | Visibility Architecture | VIA SW ARZ MCD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-11 | Active | EP
VA-MCD-1x Juniper EX4600 | SW | ARZ | MCD | Visibility Architecture | VIA SW ARZ MCD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-11 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-NRF-1x Ixia E100 | VA | HRD | NRF | Visibility Architecture | VIA VA HRD NRF Visibility Architecture Gear Decom POR20 | Chassis | 1x Ixia E100 Chassis |  |  |  |  | Deleted | EP
VA-NRF-1x Ixia E100 | VA | HRD | NRF | Visibility Architecture | VIA VA HRD NRF Visibility Architecture Gear Decom POR20 | Chassis | 1x Ixia E100 Chassis |  |  |  |  | Deleted | Log | Del | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-NRF-1x Arista DCS-7280CR2A-60-F | VA | HRD | NRF | Visibility Architecture | VIA VA HRD NRF Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis |  |  |  |  | Deleted | EP
VA-NRF-1x Arista DCS-7280CR2A-60-F | VA | HRD | NRF | Visibility Architecture | VIA VA HRD NRF Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis |  |  |  |  | Deleted | Log | Del | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-NRF-1x Dell R740 | VA | HRD | NRF | Visibility Architecture | VIA VA HRD NRF Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R740 Chassis |  |  |  |  | Deleted | EP
VA-NRF-1x Dell R740 | VA | HRD | NRF | Visibility Architecture | VIA VA HRD NRF Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R740 Chassis |  |  |  |  | Deleted | Log | Del | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-NRF-1x Juniper EX4600 | VA | HRD | NRF | Visibility Architecture | VIA VA HRD NRF Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-05-26 | 2020-08-10 | 2020-08-24 | Active | EP
VA-NRF-1x Juniper EX4600 | VA | HRD | NRF | Visibility Architecture | VIA VA HRD NRF Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-04-01 | 2020-07-31 | 2020-08-10 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-NRF-1x Juniper EX4600 | VA | HRD | NRF | Visibility Architecture | VIA VA HRD NRF Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-05-26 | 2020-08-10 | 2020-08-24 | Active | Log | Upd | SN-0169 | Schedule Change | Approved | 2020-02-06 11:22 | Moving funds ~ 1 2M from Jan to Feb as the Dell servers for location Duke will not be delivered in Jan Also, updating the material plan in Q2 and Q3 to pull 110K in Q2 from Q3
VA-VBC-1x Ixia E100 | VA | HRD | VBC | Visibility Architecture | VIA VA HRD VBC Visibility Architecture Gear Decom POR20 | Chassis | 1x Ixia E100 Chassis |  |  |  |  | Deleted | EP
VA-VBC-1x Ixia E100 | VA | HRD | VBC | Visibility Architecture | VIA VA HRD VBC Visibility Architecture Gear Decom POR20 | Chassis | 1x Ixia E100 Chassis |  |  |  |  | Deleted | Log | Del | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-VBC-1x Arista DCS-7280CR2A-60-F | VA | HRD | VBC | Visibility Architecture | VIA VA HRD VBC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis |  |  |  |  | Deleted | EP
VA-VBC-1x Arista DCS-7280CR2A-60-F | VA | HRD | VBC | Visibility Architecture | VIA VA HRD VBC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis |  |  |  |  | Deleted | Log | Del | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-VBC-1x Dell R740 | VA | HRD | VBC | Visibility Architecture | VIA VA HRD VBC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R740 Chassis |  |  |  |  | Deleted | EP
VA-VBC-1x Dell R740 | VA | HRD | VBC | Visibility Architecture | VIA VA HRD VBC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R740 Chassis |  |  |  |  | Deleted | Log | Del | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-VBC-1x Juniper EX4600 | VA | HRD | VBC | Visibility Architecture | VIA VA HRD VBC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-05-26 | 2020-08-10 | 2020-08-24 | Active | EP
VA-VBC-1x Juniper EX4600 | VA | HRD | VBC | Visibility Architecture | VIA VA HRD VBC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-04-01 | 2020-07-31 | 2020-08-10 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-VBC-1x Juniper EX4600 | VA | HRD | VBC | Visibility Architecture | VIA VA HRD VBC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-05-26 | 2020-08-10 | 2020-08-24 | Active | Log | Upd | SN-0169 | Schedule Change | Approved | 2020-02-06 11:22 | Moving funds ~ 1 2M from Jan to Feb as the Dell servers for location Duke will not be delivered in Jan Also, updating the material plan in Q2 and Q3 to pull 110K in Q2 from Q3
VA-MFD-1x ExtraHop EDA6200 (Dell R640) | VA | NVA | MFD | Visibility Architecture | VIA VA NVA MFD Visibility Architecture Gear Deployment POR20 | Chassis | 1x ExtraHop EDA6200 (Dell R640) |  |  |  |  | Deleted | EP
VA-MFD-1x ExtraHop EDA6200 (Dell R640) | VA | NVA | MFD | Visibility Architecture | VIA VA NVA MFD Visibility Architecture Gear Deployment POR20 | Chassis | 1x ExtraHop EDA6200 (Dell R640) |  |  |  |  | Deleted | Log | Del | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-MFD-1x Juniper EX4600 | VA | NVA | MFD | Visibility Architecture | VIA VA NVA MFD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-03-01 | 2020-06-30 | 2020-06-22 | Active | EP
VA-MFD-1x Juniper EX4600 | VA | NVA | MFD | Visibility Architecture | VIA VA NVA MFD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-03-01 | 2020-06-30 | 2020-06-22 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-NWA-1x Arista DCS-7280CR2A-60-F | CE | NWA | NWA | Visibility Architecture | VIA CE NWA NWA Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis |  |  |  |  | Deleted | EP
VA-NWA-1x Arista DCS-7280CR2A-60-F | CE | NWA | NWA | Visibility Architecture | VIA CE NWA NWA Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis |  |  |  |  | Deleted | Log | Del | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-NWA-1x ExtraHop EDA6200 (Dell R640) | CE | NWA | NWA | Visibility Architecture | VIA CE NWA NWA Visibility Architecture Gear Deployment POR20 | Chassis | 1x ExtraHop EDA6200 (Dell R640) |  |  |  |  | Deleted | EP
VA-NWA-1x ExtraHop EDA6200 (Dell R640) | CE | NWA | NWA | Visibility Architecture | VIA CE NWA NWA Visibility Architecture Gear Deployment POR20 | Chassis | 1x ExtraHop EDA6200 (Dell R640) | 1 | 2020-08-01 | 2020-09-30 | 2020-10-05 | Deleted | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-NWA-1x ExtraHop EDA6200 (Dell R640) | CE | NWA | NWA | Visibility Architecture | VIA CE NWA NWA Visibility Architecture Gear Deployment POR20 | Chassis | 1x ExtraHop EDA6200 (Dell R640) |  |  |  |  | Deleted | Log | Del | SN-0534 | COVID-19 Related | Approved | 2020-05-08 14:25 | Submitting this CR to update Visibility Architecture program POR against the deferrals CR submitted earlier for financial changes
VA-NWA-1x Juniper EX4600 | CE | NWA | NWA | Visibility Architecture | VIA CE NWA NWA Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-08-01 | 2020-09-30 | 2020-10-05 | Active | EP
VA-NWA-1x Juniper EX4600 | CE | NWA | NWA | Visibility Architecture | VIA CE NWA NWA Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-08-01 | 2020-09-30 | 2020-10-05 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-WIC-1x Niagra PT-3225 | CE | KAN | WIC | Visibility Architecture | VIA CE KAN WIC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis |  |  |  |  | Deleted | EP
VA-WIC-1x Niagra PT-3225 | CE | KAN | WIC | Visibility Architecture | VIA CE KAN WIC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis |  |  |  |  | Deleted | Log | Del | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-WIC-1x Dell R740 | CE | KAN | WIC | Visibility Architecture | VIA CE KAN WIC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R740 Chassis |  |  |  |  | Deleted | EP
VA-WIC-1x Dell R740 | CE | KAN | WIC | Visibility Architecture | VIA CE KAN WIC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R740 Chassis |  |  |  |  | Deleted | Log | Del | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-WIC-1x ExtraHop EDA6200 (Dell R640) | CE | KAN | WIC | Visibility Architecture | VIA CE KAN WIC Visibility Architecture Gear Deployment POR20 | Chassis | 1x ExtraHop EDA6200 (Dell R640) | 1 | 2020-02-01 | 2020-03-16 | 2020-03-30 | Active | EP
VA-WIC-1x ExtraHop EDA6200 (Dell R640) | CE | KAN | WIC | Visibility Architecture | VIA CE KAN WIC Visibility Architecture Gear Deployment POR20 | Chassis | 1x ExtraHop EDA6200 (Dell R640) | 1 | 2020-02-01 | 2020-03-16 | 2020-03-30 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-WIC-1x Juniper EX4600 | CE | KAN | WIC | Visibility Architecture | VIA CE KAN WIC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-02-01 | 2020-03-16 | 2020-03-30 | Active | EP
VA-WIC-1x Juniper EX4600 | CE | KAN | WIC | Visibility Architecture | VIA CE KAN WIC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-02-01 | 2020-03-16 | 2020-03-30 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-TUL-1x Niagra PT-3225 | CE | TUL | TUL | Visibility Architecture | VIA CE TUL TUL Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis |  |  |  |  | Deleted | EP
VA-TUL-1x Niagra PT-3225 | CE | TUL | TUL | Visibility Architecture | VIA CE TUL TUL Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis |  |  |  |  | Deleted | Log | Del | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-TUL-1x Juniper EX4600 | CE | TUL | TUL | Visibility Architecture | VIA CE TUL TUL Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-08-01 | 2020-09-30 | 2020-10-12 | Active | EP
VA-TUL-1x Juniper EX4600 | CE | TUL | TUL | Visibility Architecture | VIA CE TUL TUL Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-08-01 | 2020-09-30 | 2020-10-12 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-CLV-1x Juniper EX4600 | NE | CLE | CLV | Visibility Architecture | VIA NE CLE CLV Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-06-01 | 2020-12-15 | 2020-12-31 | Active | EP
VA-CLV-1x Juniper EX4600 | NE | CLE | CLV | Visibility Architecture | VIA NE CLE CLV Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-06-01 | 2020-07-31 | 2020-07-20 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-CLV-1x Juniper EX4600 | NE | CLE | CLV | Visibility Architecture | VIA NE CLE CLV Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-06-01 | 2020-10-17 | 2020-10-31 | Active | Log | Upd | SN-0658 | True up | Approved | 2020-06-11 15:25 | Overall Capex variance of 79K unfavorable mainly due to some part of Parma material order additional ancillary material requirements hitting the budget Realigning funds based on planned material receipt and giving back unspent 19K Opex
VA-CLV-1x Juniper EX4600 | NE | CLE | CLV | Visibility Architecture | VIA NE CLE CLV Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-06-01 | 2020-12-15 | 2020-12-31 | Active | Log | Upd | SN-0967 | Schedule Change | Approved | 2020-10-02 09:36 | Visibility Architecture Arista DCS 7280CR2A 60 F Dell R640 Juniper EX4600 Niagra PT 3225 migration date updates for Cleveland
VA-RON-1x ExtraHop EDA6200 (Dell R640) | VA | ROA | RON | Visibility Architecture | VIA VA ROA RON Visibility Architecture Gear Deployment POR20 | Chassis | 1x ExtraHop EDA6200 (Dell R640) | 1 | 2020-05-05 | 2020-07-20 | 2020-08-03 | Active | EP
VA-RON-1x ExtraHop EDA6200 (Dell R640) | VA | ROA | RON | Visibility Architecture | VIA VA ROA RON Visibility Architecture Gear Deployment POR20 | Chassis | 1x ExtraHop EDA6200 (Dell R640) | 1 | 2020-07-01 | 2020-08-31 | 2020-08-14 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-RON-1x ExtraHop EDA6200 (Dell R640) | VA | ROA | RON | Visibility Architecture | VIA VA ROA RON Visibility Architecture Gear Deployment POR20 | Chassis | 1x ExtraHop EDA6200 (Dell R640) | 1 | 2020-05-05 | 2020-07-20 | 2020-08-03 | Active | Log | Upd | SN-0169 | Schedule Change | Approved | 2020-02-06 11:22 | Moving funds ~ 1 2M from Jan to Feb as the Dell servers for location Duke will not be delivered in Jan Also, updating the material plan in Q2 and Q3 to pull 110K in Q2 from Q3
VA-RON-1x Juniper EX4600 | VA | ROA | RON | Visibility Architecture | VIA VA ROA RON Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-05-05 | 2020-07-20 | 2020-08-03 | Active | EP
VA-RON-1x Juniper EX4600 | VA | ROA | RON | Visibility Architecture | VIA VA ROA RON Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-07-01 | 2020-08-31 | 2020-08-14 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-RON-1x Juniper EX4600 | VA | ROA | RON | Visibility Architecture | VIA VA ROA RON Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-05-05 | 2020-07-20 | 2020-08-03 | Active | Log | Upd | SN-0169 | Schedule Change | Approved | 2020-02-06 11:22 | Moving funds ~ 1 2M from Jan to Feb as the Dell servers for location Duke will not be delivered in Jan Also, updating the material plan in Q2 and Q3 to pull 110K in Q2 from Q3
VA-PRV-1x Juniper EX4600 | NE | RHD | PRV | Visibility Architecture | VIA NE RHD PRV Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-07-01 | 2020-08-31 | 2020-08-24 | Active | EP
VA-PRV-1x Juniper EX4600 | NE | RHD | PRV | Visibility Architecture | VIA NE RHD PRV Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-07-01 | 2020-08-31 | 2020-08-24 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-GNS-1x ExtraHop EDA6200 (Dell R640) | SE | GAN | GNS | Visibility Architecture | VIA SE GAN GNS Visibility Architecture Gear Deployment POR20 | Chassis | 1x ExtraHop EDA6200 (Dell R640) | 1 | 2020-01-01 | 2020-02-29 | 2020-03-09 | Active | EP
VA-GNS-1x ExtraHop EDA6200 (Dell R640) | SE | GAN | GNS | Visibility Architecture | VIA SE GAN GNS Visibility Architecture Gear Deployment POR20 | Chassis | 1x ExtraHop EDA6200 (Dell R640) | 1 | 2020-01-01 | 2020-02-29 | 2020-03-09 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-GNS-1x Juniper EX4600 | SE | GAN | GNS | Visibility Architecture | VIA SE GAN GNS Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-01-01 | 2020-02-29 | 2020-03-09 | Active | EP
VA-GNS-1x Juniper EX4600 | SE | GAN | GNS | Visibility Architecture | VIA SE GAN GNS Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-01-01 | 2020-02-29 | 2020-03-09 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-ELM-1x ExtraHop EDA6200 (Dell R640) | SE | NOR | ELM | Visibility Architecture | VIA SE NOR ELM Visibility Architecture Gear Deployment POR20 | Chassis | 1x ExtraHop EDA6200 (Dell R640) | 1 | 2020-01-01 | 2020-03-31 | 2020-03-16 | Active | EP
VA-ELM-1x ExtraHop EDA6200 (Dell R640) | SE | NOR | ELM | Visibility Architecture |  | Chassis | 1x ExtraHop EDA6200 (Dell R640) | 1 | 2020-02-19 | 2020-04-15 | 2020-04-15 | Active | Log | Upd | SN-0052 | New | Canceled | 2019-10-29 09:37 | Visibility Architecture - POR Correction
VA-ELM-1x ExtraHop EDA6200 (Dell R640) | SE | NOR | ELM | Visibility Architecture | VIA SE NOR ELM Visibility Architecture Gear Deployment POR20 | Chassis | 1x ExtraHop EDA6200 (Dell R640) | 1 | 2020-01-01 | 2020-03-31 | 2020-03-16 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-ELM-1x Juniper EX4600 | SE | NOR | ELM | Visibility Architecture | VIA SE NOR ELM Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-03-16 | Active | EP
VA-ELM-1x Juniper EX4600 | SE | NOR | ELM | Visibility Architecture |  | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-02-19 | 2020-04-15 | 2020-04-15 | Active | Log | Upd | SN-0052 | New | Canceled | 2019-10-29 09:37 | Visibility Architecture - POR Correction
VA-ELM-1x Juniper EX4600 | SE | NOR | ELM | Visibility Architecture | VIA SE NOR ELM Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-03-16 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-PNS-1x ExtraHop EDA6200 (Dell R640) | SE | GCT | PNS | Visibility Architecture | VIA SE GCT PNS Visibility Architecture Gear Deployment POR20 | Chassis | 1x ExtraHop EDA6200 (Dell R640) |  |  |  |  | Deleted | EP
VA-PNS-1x ExtraHop EDA6200 (Dell R640) | SE | GCT | PNS | Visibility Architecture | VIA SE GCT PNS Visibility Architecture Gear Deployment POR20 | Chassis | 1x ExtraHop EDA6200 (Dell R640) | 1 | 2020-05-01 | 2020-06-30 | 2020-07-13 | Deleted | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-PNS-1x ExtraHop EDA6200 (Dell R640) | SE | GCT | PNS | Visibility Architecture | VIA SE GCT PNS Visibility Architecture Gear Deployment POR20 | Chassis | 1x ExtraHop EDA6200 (Dell R640) |  |  |  |  | Deleted | Log | Del | SN-0534 | COVID-19 Related | Approved | 2020-05-08 14:25 | Submitting this CR to update Visibility Architecture program POR against the deferrals CR submitted earlier for financial changes
VA-PNS-1x Juniper EX4600 | SE | GCT | PNS | Visibility Architecture | VIA SE GCT PNS Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-05-01 | 2020-06-30 | 2020-07-13 | Active | EP
VA-PNS-1x Juniper EX4600 | SE | GCT | PNS | Visibility Architecture | VIA SE GCT PNS Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-05-01 | 2020-06-30 | 2020-07-13 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-MCN-1x ExtraHop EDA6200 (Dell R640) | SE | MGA | MCN | Visibility Architecture | VIA SE MGA MCN Visibility Architecture Gear Deployment POR20 | Chassis | 1x ExtraHop EDA6200 (Dell R640) |  |  |  |  | Deleted | EP
VA-MCN-1x ExtraHop EDA6200 (Dell R640) | SE | MGA | MCN | Visibility Architecture | VIA SE MGA MCN Visibility Architecture Gear Deployment POR20 | Chassis | 1x ExtraHop EDA6200 (Dell R640) | 1 | 2020-07-01 | 2020-08-31 | 2020-09-14 | Deleted | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-MCN-1x ExtraHop EDA6200 (Dell R640) | SE | MGA | MCN | Visibility Architecture | VIA SE MGA MCN Visibility Architecture Gear Deployment POR20 | Chassis | 1x ExtraHop EDA6200 (Dell R640) |  |  |  |  | Deleted | Log | Del | SN-0534 | COVID-19 Related | Approved | 2020-05-08 14:25 | Submitting this CR to update Visibility Architecture program POR against the deferrals CR submitted earlier for financial changes
VA-MCN-1x Juniper EX4600 | SE | MGA | MCN | Visibility Architecture | VIA SE MGA MCN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-07-01 | 2020-08-31 | 2020-09-14 | Active | EP
VA-MCN-1x Juniper EX4600 | SE | MGA | MCN | Visibility Architecture | VIA SE MGA MCN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-07-01 | 2020-08-31 | 2020-09-14 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-HEN-1x Arista DCS-7280CR2A-60-F | SW | LAS | HEN | Visibility Architecture | VIA SW LAS HEN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-18 | Active | EP
VA-HEN-1x Arista DCS-7280CR2A-60-F | SW | LAS | HEN | Visibility Architecture | VIA SW LAS HEN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-18 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-HEN-1x Dell R740 | SW | LAS | HEN | Visibility Architecture | VIA SW LAS HEN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R740 Chassis |  |  |  |  | Deleted | EP
VA-HEN-1x Dell R740 | SW | LAS | HEN | Visibility Architecture | VIA SW LAS HEN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R740 Chassis |  |  |  |  | Deleted | Log | Del | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-HEN-1x Juniper EX4600 | SW | LAS | HEN | Visibility Architecture | VIA SW LAS HEN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-18 | Active | EP
VA-HEN-1x Juniper EX4600 | SW | LAS | HEN | Visibility Architecture | VIA SW LAS HEN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-18 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-TEN-1x Arista DCS-7280CR2A-60-F | SW | LAS | TEN | Visibility Architecture | VIA SW LAS TEN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-18 | Active | EP
VA-TEN-1x Arista DCS-7280CR2A-60-F | SW | LAS | TEN | Visibility Architecture | VIA SW LAS TEN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-18 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-TEN-1x Dell R740 | SW | LAS | TEN | Visibility Architecture | VIA SW LAS TEN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R740 Chassis |  |  |  |  | Deleted | EP
VA-TEN-1x Dell R740 | SW | LAS | TEN | Visibility Architecture | VIA SW LAS TEN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R740 Chassis |  |  |  |  | Deleted | Log | Del | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-TEN-1x Juniper EX4600 | SW | LAS | TEN | Visibility Architecture | VIA SW LAS TEN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-18 | Active | EP
VA-TEN-1x Juniper EX4600 | SW | LAS | TEN | Visibility Architecture | VIA SW LAS TEN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-18 | Active | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-NWA-1x Ixia E100 | CE | NWA | NWA | Visibility Architecture | VIA CE NWA NWA Visibility Architecture Gear Decom POR20 | Chassis | 1x Ixia E100 Chassis |  |  |  |  | Deleted | EP
VA-NWA-1x Ixia E100 | CE | NWA | NWA | Visibility Architecture | VIA CE NWA NWA Visibility Architecture Gear Decom POR20 | Chassis | 1x Ixia E100 Chassis |  |  |  |  | Deleted | Log | Del | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-HEN-1x Ixia E100 | SW | LAS | HEN | Visibility Architecture | VIA SW LAS HEN Visibility Architecture Gear Decom POR20 | Chassis | 1x Ixia E100 Chassis |  |  |  |  | Deleted | EP
VA-HEN-1x Ixia E100 | SW | LAS | HEN | Visibility Architecture | VIA SW LAS HEN Visibility Architecture Gear Decom POR20 | Chassis | 1x Ixia E100 Chassis |  |  |  |  | Deleted | Log | Del | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-TEN-1x Ixia E100 | SW | LAS | TEN | Visibility Architecture | VIA SW LAS TEN Visibility Architecture Gear Decom POR20 | Chassis | 1x Ixia E100 Chassis |  |  |  |  | Deleted | EP
VA-TEN-1x Ixia E100 | SW | LAS | TEN | Visibility Architecture | VIA SW LAS TEN Visibility Architecture Gear Decom POR20 | Chassis | 1x Ixia E100 Chassis |  |  |  |  | Deleted | Log | Del | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-RSM-1x Ixia E100 -v1 | CA | ORG | RSM | Visibility Architecture | VIA CA ORG RSM Visibility Architecture Gear Deployment POR20 | Chassis | 1x Ixia E100 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-04-20 | Active | EP
VA-RSM-1x Ixia E100 -v1 | CA | ORG | RSM | Visibility Architecture | VIA CA ORG RSM Visibility Architecture Gear Deployment POR20 | Chassis | 1x Ixia E100 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-04-20 | Active | Log | New | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-RSM-1x Dell R640 | CA | ORG | RSM | Visibility Architecture | VIA CA ORG RSM Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 5 | 2020-01-01 | 2020-04-30 | 2020-04-20 | Active | EP
VA-RSM-1x Dell R640 | CA | ORG | RSM | Visibility Architecture | VIA CA ORG RSM Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 5 | 2020-01-01 | 2020-04-30 | 2020-04-20 | Active | Log | New | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-ELC-1x Niagra PT-3225 | CA | SAN | ELC | Visibility Architecture | VIA CA SAN ELC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis | 1 | 2020-01-01 | 2020-04-20 | 2020-05-04 | Active | EP
VA-ELC-1x Niagra PT-3225 | CA | SAN | ELC | Visibility Architecture | VIA CA SAN ELC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-04-20 | Active | Log | New | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-ELC-1x Niagra PT-3225 | CA | SAN | ELC | Visibility Architecture | VIA CA SAN ELC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis | 1 | 2020-01-01 | 2020-04-20 | 2020-05-04 | Active | Log | Upd | SN-0559 | True up | Approved | 2020-05-13 11:46 | April Capex variance of 126K due to ancillary items purchase and power requirements charges for Material and associated labor for Capacity adds in addition to BAU install activities Giving back 5848 opex and realigning the funds for rest of the year
VA-ELC-1x Dell R640 | CA | SAN | ELC | Visibility Architecture | VIA CA SAN ELC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 4 | 2020-01-01 | 2020-04-20 | 2020-05-04 | Active | EP
VA-ELC-1x Dell R640 | CA | SAN | ELC | Visibility Architecture | VIA CA SAN ELC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 4 | 2020-01-01 | 2020-04-30 | 2020-04-20 | Active | Log | New | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-ELC-1x Dell R640 | CA | SAN | ELC | Visibility Architecture | VIA CA SAN ELC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 4 | 2020-01-01 | 2020-04-20 | 2020-05-04 | Active | Log | Upd | SN-0559 | True up | Approved | 2020-05-13 11:46 | April Capex variance of 126K due to ancillary items purchase and power requirements charges for Material and associated labor for Capacity adds in addition to BAU install activities Giving back 5848 opex and realigning the funds for rest of the year
VA-FED-1x Niagra PT-3225 | CA | SAN | FED | Visibility Architecture | VIA CA SAN FED Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis | 1 | 2020-01-01 | 2020-04-27 | 2020-05-11 | Active | EP
VA-FED-1x Niagra PT-3225 | CA | SAN | FED | Visibility Architecture | VIA CA SAN FED Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-04-20 | Active | Log | New | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-FED-1x Niagra PT-3225 | CA | SAN | FED | Visibility Architecture | VIA CA SAN FED Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis | 1 | 2020-01-01 | 2020-04-27 | 2020-05-11 | Active | Log | Upd | SN-0559 | True up | Approved | 2020-05-13 11:46 | April Capex variance of 126K due to ancillary items purchase and power requirements charges for Material and associated labor for Capacity adds in addition to BAU install activities Giving back 5848 opex and realigning the funds for rest of the year
VA-FED-1x Dell R640 | CA | SAN | FED | Visibility Architecture | VIA CA SAN FED Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 4 | 2020-01-01 | 2020-04-27 | 2020-05-11 | Active | EP
VA-FED-1x Dell R640 | CA | SAN | FED | Visibility Architecture | VIA CA SAN FED Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 4 | 2020-01-01 | 2020-04-30 | 2020-04-20 | Active | Log | New | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-FED-1x Dell R640 | CA | SAN | FED | Visibility Architecture | VIA CA SAN FED Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 4 | 2020-01-01 | 2020-04-27 | 2020-05-11 | Active | Log | Upd | SN-0559 | True up | Approved | 2020-05-13 11:46 | April Capex variance of 126K due to ancillary items purchase and power requirements charges for Material and associated labor for Capacity adds in addition to BAU install activities Giving back 5848 opex and realigning the funds for rest of the year
VA-WIC-1x Arista DCS-7280CR2A-60-F | CE | KAN | WIC | Visibility Architecture | VIA CE KAN WIC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2019-02-01 | 2020-03-16 | 2020-03-30 | Active | EP
VA-WIC-1x Arista DCS-7280CR2A-60-F | CE | KAN | WIC | Visibility Architecture | VIA CE KAN WIC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2019-02-01 | 2020-03-16 | 2020-03-30 | Active | Log | New | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-WIC-1x Dell R640 | CE | KAN | WIC | Visibility Architecture | VIA CE KAN WIC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 1 | 2019-02-01 | 2020-03-16 | 2020-03-30 | Active | EP
VA-WIC-1x Dell R640 | CE | KAN | WIC | Visibility Architecture | VIA CE KAN WIC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 1 | 2019-02-01 | 2020-03-16 | 2020-03-30 | Active | Log | New | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-OMM-1x Niagra PT-3225 | CE | OMA | OMM | Visibility Architecture | VIA CE OMA OMM Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis | 1 | 2020-04-01 | 2020-05-31 | 2020-06-08 | Active | EP
VA-OMM-1x Niagra PT-3225 | CE | OMA | OMM | Visibility Architecture | VIA CE OMA OMM Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis | 1 | 2020-04-01 | 2020-05-31 | 2020-06-08 | Active | Log | New | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-PRV-1x ExtraHop EDA6200 (Dell R640) | NE | RHD | PRV | Visibility Architecture | VIA NE RHD PRV Visibility Architecture Gear Deployment POR20 | Chassis | 1x ExtraHop EDA6200 (Dell R640) |  |  |  |  | Deleted | EP
VA-PRV-1x ExtraHop EDA6200 (Dell R640) | NE | RHD | PRV | Visibility Architecture | VIA NE RHD PRV Visibility Architecture Gear Deployment POR20 | Chassis | 1x ExtraHop EDA6200 (Dell R640) | 1 | 2020-07-01 | 2020-08-31 | 2020-08-24 | Deleted | Log | New | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-PRV-1x ExtraHop EDA6200 (Dell R640) | NE | RHD | PRV | Visibility Architecture | VIA NE RHD PRV Visibility Architecture Gear Deployment POR20 | Chassis | 1x ExtraHop EDA6200 (Dell R640) |  |  |  |  | Deleted | Log | Del | SN-0534 | COVID-19 Related | Approved | 2020-05-08 14:25 | Submitting this CR to update Visibility Architecture program POR against the deferrals CR submitted earlier for financial changes
VA-BTR-1x Arista DCS-7280CR2A-60-F | SE | BTR | BTR | Visibility Architecture | VIA SE BTR BTR Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-03-16 | Active | EP
VA-BTR-1x Arista DCS-7280CR2A-60-F | SE | BTR | BTR | Visibility Architecture | VIA SE BTR BTR Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-03-16 | Active | Log | New | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-BTR-1x Niagra PT-3225 | SE | BTR | BTR | Visibility Architecture | VIA SE BTR BTR Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-03-16 | Active | EP
VA-BTR-1x Niagra PT-3225 | SE | BTR | BTR | Visibility Architecture | VIA SE BTR BTR Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-03-16 | Active | Log | New | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-BTR-1x Dell R640 | SE | BTR | BTR | Visibility Architecture | VIA SE BTR BTR Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 4 | 2020-01-01 | 2020-03-31 | 2020-03-16 | Active | EP
VA-BTR-1x Dell R640 | SE | BTR | BTR | Visibility Architecture | VIA SE BTR BTR Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 4 | 2020-01-01 | 2020-03-31 | 2020-03-16 | Active | Log | New | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-GNS-1x Dell R640 | SE | GAN | GNS | Visibility Architecture | VIA SE GAN GNS Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 4 | 2020-01-01 | 2020-02-29 | 2020-03-09 | Active | EP
VA-GNS-1x Dell R640 | SE | GAN | GNS | Visibility Architecture | VIA SE GAN GNS Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 4 | 2020-01-01 | 2020-02-29 | 2020-03-09 | Active | Log | New | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-GNS-1x Ixia E100 | SE | GAN | GNS | Visibility Architecture | VIA SE GAN GNS Visibility Architecture Gear Deployment POR20 | Chassis | 1x Ixia E100 Chassis | 1 | 2020-01-01 | 2020-02-29 | 2020-03-09 | Active | EP
VA-GNS-1x Ixia E100 | SE | GAN | GNS | Visibility Architecture | VIA SE GAN GNS Visibility Architecture Gear Deployment POR20 | Chassis | 1x Ixia E100 Chassis | 1 | 2020-01-01 | 2020-02-29 | 2020-03-09 | Active | Log | New | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-PNS-1x Dell R640 | SE | GCT | PNS | Visibility Architecture | VIA SE GCT PNS Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 3 | 2020-05-01 | 2020-06-30 | 2020-07-13 | Active | EP
VA-PNS-1x Dell R640 | SE | GCT | PNS | Visibility Architecture | VIA SE GCT PNS Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 3 | 2020-05-01 | 2020-06-30 | 2020-07-13 | Active | Log | New | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-MCN-1x Ixia E100 -v1 | SE | MGA | MCN | Visibility Architecture | VIA SE MGA MCN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Ixia E100 Chassis |  |  |  |  | Deleted | EP
VA-MCN-1x Ixia E100 -v1 | SE | MGA | MCN | Visibility Architecture | VIA SE MGA MCN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Ixia E100 Chassis | 1 |  | 2020-08-31 | 2020-09-14 | Deleted | Log | Upd | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-MCN-1x Ixia E100 -v1 | SE | MGA | MCN | Visibility Architecture | VIA SE MGA MCN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Ixia E100 Chassis |  |  |  |  | Deleted | Log | Del | SN-0534 | COVID-19 Related | Approved | 2020-05-08 14:25 | Submitting this CR to update Visibility Architecture program POR against the deferrals CR submitted earlier for financial changes
VA-MCN-1x Dell R640 | SE | MGA | MCN | Visibility Architecture | VIA SE MGA MCN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis |  |  |  |  | Deleted | EP
VA-MCN-1x Dell R640 | SE | MGA | MCN | Visibility Architecture | VIA SE MGA MCN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 4 | 2020-07-01 | 2020-08-31 | 2020-09-14 | Deleted | Log | New | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-MCN-1x Dell R640 | SE | MGA | MCN | Visibility Architecture | VIA SE MGA MCN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis |  |  |  |  | Deleted | Log | Del | SN-0534 | COVID-19 Related | Approved | 2020-05-08 14:25 | Submitting this CR to update Visibility Architecture program POR against the deferrals CR submitted earlier for financial changes
VA-ELM-1x Dell R640 | SE | NOR | ELM | Visibility Architecture | VIA SE NOR ELM Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-03-16 | Active | EP
VA-ELM-1x Dell R640 | SE | NOR | ELM | Visibility Architecture | VIA SE NOR ELM Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-03-16 | Active | Log | New | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
2020¦VA-MCN-1x Ixia E100 | SE | MGA | MCN | Visibility Architecture | VIA SE MGA MCN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Ixia E100 Chassis |  |  |  |  | Deleted | EP
2020¦VA-MCN-1x Ixia E100 | SE | MGA | MCN | Visibility Architecture | VIA SE MGA MCN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Ixia E100 Chassis | 1 | 2020-07-01 | 2020-08-31 | 2020-09-14 | Deleted | Log | New | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
2020¦VA-MCN-1x Ixia E100 | SE | MGA | MCN | Visibility Architecture | VIA SE MGA MCN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Ixia E100 Chassis |  |  |  |  | Deleted | Log | Del | SN-0534 | COVID-19 Related | Approved | 2020-05-08 14:25 | Submitting this CR to update Visibility Architecture program POR against the deferrals CR submitted earlier for financial changes
VA-CHD-1x Dell R640 | SW | ARZ | CHD | Visibility Architecture | VIA SW ARZ CHD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 9 | 2020-01-01 | 2020-04-30 | 2020-05-11 | Active | EP
VA-CHD-1x Dell R640 | SW | ARZ | CHD | Visibility Architecture | VIA SW ARZ CHD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 9 | 2020-01-01 | 2020-04-30 | 2020-05-11 | Active | Log | New | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-CHD-1x Ixia E100-v1 | SW | ARZ | CHD | Visibility Architecture | VIA SW ARZ CHD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Ixia E100 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-11 | Active | EP
VA-CHD-1x Ixia E100-v1 | SW | ARZ | CHD | Visibility Architecture | VIA SW ARZ CHD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Ixia E100 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-11 | Active | Log | New | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-MCD-1x Dell R640 | SW | ARZ | MCD | Visibility Architecture | VIA SW ARZ MCD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 9 | 2020-01-01 | 2020-04-30 | 2020-05-11 | Active | EP
VA-MCD-1x Dell R640 | SW | ARZ | MCD | Visibility Architecture | VIA SW ARZ MCD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 9 | 2020-01-01 | 2020-04-30 | 2020-05-11 | Active | Log | New | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-MCD-1x Ixia E100-v1 | SW | ARZ | MCD | Visibility Architecture | VIA SW ARZ MCD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Ixia E100 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-11 | Active | EP
VA-MCD-1x Ixia E100-v1 | SW | ARZ | MCD | Visibility Architecture | VIA SW ARZ MCD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Ixia E100 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-11 | Active | Log | New | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-HEN-1x Dell R640 | SW | LAS | HEN | Visibility Architecture | VIA SW LAS HEN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 4 | 2020-01-01 | 2020-04-30 | 2020-05-18 | Active | EP
VA-HEN-1x Dell R640 | SW | LAS | HEN | Visibility Architecture | VIA SW LAS HEN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 4 | 2020-01-01 | 2020-04-30 | 2020-05-18 | Active | Log | New | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-HEN-1x Niagra PT-3225 | SW | LAS | HEN | Visibility Architecture | VIA SW LAS HEN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-18 | Active | EP
VA-HEN-1x Niagra PT-3225 | SW | LAS | HEN | Visibility Architecture | VIA SW LAS HEN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-18 | Active | Log | New | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-TEN-1x Dell R640 | SW | LAS | TEN | Visibility Architecture | VIA SW LAS TEN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 4 | 2020-01-01 | 2020-04-30 | 2020-05-18 | Active | EP
VA-TEN-1x Dell R640 | SW | LAS | TEN | Visibility Architecture | VIA SW LAS TEN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 4 | 2020-01-01 | 2020-04-30 | 2020-05-18 | Active | Log | New | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-TEN-1x Niagra PT-3225 | SW | LAS | TEN | Visibility Architecture | VIA SW LAS TEN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-18 | Active | EP
VA-TEN-1x Niagra PT-3225 | SW | LAS | TEN | Visibility Architecture | VIA SW LAS TEN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-18 | Active | Log | New | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-NRF-1x Dell R640 | VA | HRD | NRF | Visibility Architecture | VIA VA HRD NRF Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 4 | 2020-05-26 | 2020-08-10 | 2020-08-24 | Active | EP
VA-NRF-1x Dell R640 | VA | HRD | NRF | Visibility Architecture | VIA VA HRD NRF Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 4 | 2020-04-01 | 2020-07-31 | 2020-08-10 | Active | Log | New | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-NRF-1x Dell R640 | VA | HRD | NRF | Visibility Architecture | VIA VA HRD NRF Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 4 | 2020-05-26 | 2020-08-10 | 2020-08-24 | Active | Log | Upd | SN-0169 | Schedule Change | Approved | 2020-02-06 11:22 | Moving funds ~ 1 2M from Jan to Feb as the Dell servers for location Duke will not be delivered in Jan Also, updating the material plan in Q2 and Q3 to pull 110K in Q2 from Q3
VA-VBC-1x Dell R640 | VA | HRD | VBC | Visibility Architecture | VIA VA HRD VBC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 4 | 2020-05-26 | 2020-08-10 | 2020-08-24 | Active | EP
VA-VBC-1x Dell R640 | VA | HRD | VBC | Visibility Architecture | VIA VA HRD VBC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 4 | 2020-04-01 | 2020-07-31 | 2020-08-10 | Active | Log | New | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-VBC-1x Dell R640 | VA | HRD | VBC | Visibility Architecture | VIA VA HRD VBC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 4 | 2020-05-26 | 2020-08-10 | 2020-08-24 | Active | Log | Upd | SN-0169 | Schedule Change | Approved | 2020-02-06 11:22 | Moving funds ~ 1 2M from Jan to Feb as the Dell servers for location Duke will not be delivered in Jan Also, updating the material plan in Q2 and Q3 to pull 110K in Q2 from Q3
VA-RON-1x Dell R640 | VA | ROA | RON | Visibility Architecture | VIA VA ROA RON Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 1 | 2020-05-05 | 2020-07-20 | 2020-08-03 | Active | EP
VA-RON-1x Dell R640 | VA | ROA | RON | Visibility Architecture | VIA VA ROA RON Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 1 | 2020-07-01 | 2020-08-31 | 2020-08-14 | Active | Log | New | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-RON-1x Dell R640 | VA | ROA | RON | Visibility Architecture | VIA VA ROA RON Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 1 | 2020-05-05 | 2020-07-20 | 2020-08-03 | Active | Log | Upd | SN-0169 | Schedule Change | Approved | 2020-02-06 11:22 | Moving funds ~ 1 2M from Jan to Feb as the Dell servers for location Duke will not be delivered in Jan Also, updating the material plan in Q2 and Q3 to pull 110K in Q2 from Q3
VA-MFD-1x Dell R640 | VA | NVA | MFD | Visibility Architecture | VIA VA NVA MFD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 3 | 2020-03-01 | 2020-06-30 | 2020-06-22 | Active | EP
VA-MFD-1x Dell R640 | VA | NVA | MFD | Visibility Architecture | VIA VA NVA MFD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 3 | 2020-03-01 | 2020-06-30 | 2020-06-22 | Active | Log | New | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-DDR-1x Dell R640 | COR | COR | DDR | Visibility Architecture | VIA CO COR DDR Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 45 | 2020-01-01 | 2020-04-30 | 2020-04-15 | Active | EP
VA-DDR-1x Dell R640 | COR | COR | DDR | Visibility Architecture | VIA CO COR DDR Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 45 | 2020-01-01 | 2020-04-30 | 2020-04-15 | Active | Log | New | SN-0094 | Schedule Change | Approved | 2020-02-06 10:35 | Updating the Visibility Architecture POR as per the updated material plan and schedule
VA-CLV-1x Niagra PT-3225 | NE | CLE | CLV | Visibility Architecture | VIA NE CLE CLV Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis | 4 | 2020-06-30 | 2020-12-15 | 2020-12-31 | Active | EP
VA-CLV-1x Niagra PT-3225 | NE | CLE | CLV | Visibility Architecture | VIA NE CLE CLV Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis | 4 | 2020-06-30 | 2020-10-17 | 2020-10-31 | Active | Log | New | SN-0658 | True up | Approved | 2020-06-11 15:25 | Overall Capex variance of 79K unfavorable mainly due to some part of Parma material order additional ancillary material requirements hitting the budget Realigning funds based on planned material receipt and giving back unspent 19K Opex
VA-CLV-1x Niagra PT-3225 | NE | CLE | CLV | Visibility Architecture | VIA NE CLE CLV Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis | 4 | 2020-06-30 | 2020-12-15 | 2020-12-31 | Active | Log | Upd | SN-0967 | Schedule Change | Approved | 2020-10-02 09:36 | Visibility Architecture Arista DCS 7280CR2A 60 F Dell R640 Juniper EX4600 Niagra PT 3225 migration date updates for Cleveland
VA-CLV-1x Arista DCS-7280CR2A-60-F | NE | CLE | CLV | Visibility Architecture | VIA NE CLE CLV Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2020-07-31 | 2020-12-15 | 2020-12-31 | Active | EP
VA-CLV-1x Arista DCS-7280CR2A-60-F | NE | CLE | CLV | Visibility Architecture | VIA NE CLE CLV Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2020-07-31 | 2020-10-17 | 2020-10-31 | Active | Log | New | SN-0658 | True up | Approved | 2020-06-11 15:25 | Overall Capex variance of 79K unfavorable mainly due to some part of Parma material order additional ancillary material requirements hitting the budget Realigning funds based on planned material receipt and giving back unspent 19K Opex
VA-CLV-1x Arista DCS-7280CR2A-60-F | NE | CLE | CLV | Visibility Architecture | VIA NE CLE CLV Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2020-07-31 | 2020-12-15 | 2020-12-31 | Active | Log | Upd | SN-0967 | Schedule Change | Approved | 2020-10-02 09:36 | Visibility Architecture Arista DCS 7280CR2A 60 F Dell R640 Juniper EX4600 Niagra PT 3225 migration date updates for Cleveland
VA-CLV-1x Dell R640 | NE | CLE | CLV | Visibility Architecture | VIA NE CLE CLV Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 3 | 2020-06-30 | 2020-12-15 | 2020-12-31 | Active | EP
VA-CLV-1x Dell R640 | NE | CLE | CLV | Visibility Architecture | VIA NE CLE CLV Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 3 | 2020-06-30 | 2020-10-17 | 2020-10-31 | Active | Log | New | SN-0658 | True up | Approved | 2020-06-11 15:25 | Overall Capex variance of 79K unfavorable mainly due to some part of Parma material order additional ancillary material requirements hitting the budget Realigning funds based on planned material receipt and giving back unspent 19K Opex
VA-CLV-1x Dell R640 | NE | CLE | CLV | Visibility Architecture | VIA NE CLE CLV Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 3 | 2020-06-30 | 2020-12-15 | 2020-12-31 | Active | Log | Upd | SN-0967 | Schedule Change | Approved | 2020-10-02 09:36 | Visibility Architecture Arista DCS 7280CR2A 60 F Dell R640 Juniper EX4600 Niagra PT 3225 migration date updates for Cleveland
CB Access NNI SBC Licenses Growth | COR | COR | DDR | Voice Capacity | VCAP CO -CO DDR Voice Capacity Augment POR20 | License | License procurement |  |  |  |  | Deleted | EP
CB Access NNI SBC Licenses Growth | COR | COR | DDR | Voice Capacity | VCAP CO -CO DDR Voice Capacity Augment POR20 | License | License procurement |  |  |  |  | Deleted | Log | Del | SB-0127 | COVID-19 Related | Approved | 2020-05-13 14:52 | Deferred EdgeView Liecense cost License cost of 71500 Deferral CR SB 0117 Deferred MetaSwitch EMS SAS Storage License cost of 96000 in Deferral CR SB 0117
Edgeview EndPoint Licenses | COR | COR | DDR | Voice Capacity | VCAP CO -CO DDR Voice Capacity Augment POR20 | License | License procurement |  |  |  |  | Deleted | EP
Edgeview EndPoint Licenses | COR | COR | DDR | Voice Capacity | VCAP CO -CO DDR Voice Capacity Augment POR20 | License | License procurement |  |  |  |  | Deleted | Log | Del | SB-0127 | COVID-19 Related | Approved | 2020-05-13 14:52 | Deferred EdgeView Liecense cost License cost of 71500 Deferral CR SB 0117 Deferred MetaSwitch EMS SAS Storage License cost of 96000 in Deferral CR SB 0117
MetaSwitch EMS SAS Storage | COR | COR | DDR | Voice Capacity | VCAP CO -CO DDR Voice Capacity Augment POR20 | License | License procurement |  |  |  |  | Deleted | EP
MetaSwitch EMS SAS Storage | COR | COR | DDR | Voice Capacity | VCAP CO -CO DDR Voice Capacity Augment POR20 | License | License procurement |  |  |  |  | Deleted | Log | Del | SB-0127 | COVID-19 Related | Approved | 2020-05-13 14:52 | Deferred EdgeView Liecense cost License cost of 71500 Deferral CR SB 0117 Deferred MetaSwitch EMS SAS Storage License cost of 96000 in Deferral CR SB 0117
SPLUNK Licenses | COR | COR | DDR | Voice Capacity | VCAP CO -CO DDR Voice Capacity Augment POR20 | License | License procurement | 20 | 2020-05-25 | 2020-11-30 |  | Active | EP
SPLUNK Licenses | COR | COR | DDR | Voice Capacity | VCAP CO -CO DDR Voice Capacity Augment POR20 | License | License procurement | 20 | 2020-05-25 | 2020-11-30 |  | Active | Log | Upd | SB-0235 | Schedule Change | Approved | 2020-10-23 14:34 | Moved the material funds of 11k in Voice Growth project from Oct to Nov due to delay in delivery of splunk license
HY CA SAN ELC Voice DMS Decom POR20 | CA | SAN | ELC | Voice Decom and Refortification | VCDR CA SAN ELC Voice El Cajon DMS Decom POR19 | Labor | DMS-500 switch decom | 1 | 2019-10-06 | 2021-02-28 |  | Active | EP
HY CA SAN ELC Voice DMS Decom POR20 | CA | SAN | ELC | Voice Decom and Refortification | Harmony Temporary | Labor | DMS-500 switch decom |  |  |  |  | Active | Log | Del | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY CA SAN ELC Voice DMS Decom POR20 | CA | SAN | ELC | Voice Decom and Refortification | VCDR CA SAN ELC Voice El Cajon DMS Decom POR19 | Labor | DMS-500 switch decom | 1 | 2019-10-06 | 2020-05-15 |  | Active | Log | Upd | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY CA SAN ELC Voice DMS Decom POR20 | CA | SAN | ELC | Voice Decom and Refortification | VCDR CA SAN ELC Voice El Cajon DMS Decom POR19 | Labor | DMS-500 switch decom | 1 | 2019-10-06 | 2021-02-28 |  | Active | Log | Upd | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
HY CA SAN ALP Voice HDT Decom POR20 | CA | SAN | ALP | Voice Decom and Refortification | VCDR CA SAN ALP Voice HDT Decom POR20 v2 | Labor | No Equipment | 1 | 2020-04-01 | 2020-07-30 |  | Active | EP
HY CA SAN ALP Voice HDT Decom POR20 | CA | SAN | ALP | Voice Decom and Refortification | HY CA SAN ALP Voice HDT Decom POR20 | Labor | No Equipment | 2 | 2019-12-07 08:00 | 2021-03-31 |  | Active | Log | New | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY CA SAN ALP Voice HDT Decom POR20 | CA | SAN | ALP | Voice Decom and Refortification | VCDR CA SAN ALP Voice HDT Decom POR20 v2 | Labor | No Equipment | 2 | 2019-12-07 08:00 | 2020-04-10 |  | Active | Log | Upd | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY CA SAN ALP Voice HDT Decom POR20 | CA | SAN | ALP | Voice Decom and Refortification | VCDR CA SAN ALP Voice HDT Decom POR20 v2 | Labor | No Equipment | 1 |  | 2020-06-30 |  | Active | Log | Upd | SN-0423 | Schedule Change | Approved | 2020-04-10 14:17 | POR update only CR for Voice Decom to align Activity Plan to EPS projects
HY CA SAN ALP Voice HDT Decom POR20 | CA | SAN | ALP | Voice Decom and Refortification | VCDR CA SAN ALP Voice HDT Decom POR20 v2 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-30 |  | Active | Log | Upd | SN-0644 | True up | Approved | 2020-06-15 18:09 | 1 Variance of Capex labor 9k has been self solved and Opex labor of 3k self solved and reason for variance is mentioned in the comments section 2 New start dates FCED are updated in the POR
HY CA SAN ALP Voice HDT Decom POR20 | CA | SAN | ALP | Voice Decom and Refortification | VCDR CA SAN ALP Voice HDT Decom POR20 v2 | Labor | No Equipment | 1 | 2020-04-01 | 2020-07-31 |  | Active | Log | Upd | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
HY CA SAN ALP Voice HDT Decom POR20 | CA | SAN | ALP | Voice Decom and Refortification | VCDR CA SAN ALP Voice HDT Decom POR20 v2 | Labor | No Equipment |  |  |  |  | Active | Log | Del | SN-0884 | Schedule Change | Approved | 2020-09-02 13:33 | Allocated the 500k Opex funds in Corp PPM 77906 for Automation resources expenses Details are provided in the additional sheet Break up of 500k Opex plan
HY CA SAN ALP Voice HDT Decom POR20 | CA | SAN | ALP | Voice Decom and Refortification | VCDR CA SAN ALP Voice HDT Decom POR20 v2 | Labor | No Equipment | 1 | 2020-04-01 | 2020-07-30 |  | Active | Log | Undel | SN-1080 | Schedule Change | Approved | 2020-11-20 13:46 | Voice Decom CR only for POR updates
HY CA SAN ELC Voice DMS 2 Decom POR20 | CA | SAN | ELC | Voice Decom and Refortification | VCDR CA SAN ELC Voice Cypress DMS Decom POR20 | Labor | DMS-500 switch decom |  |  |  |  | Deleted | EP
HY CA SAN ELC Voice DMS 2 Decom POR20 | CA | SAN | ELC | Voice Decom and Refortification | VCDR CA SAN ELC Voice Cypress DMS Decom POR20 | Labor | No Equipment | 1 | 2020-07-06 | 2020-12-31 |  | Deleted | Log | New | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY CA SAN ELC Voice DMS 2 Decom POR20 | CA | SAN | ELC | Voice Decom and Refortification | VCDR CA SAN ELC Voice Cypress DMS Decom POR20 | Labor | DMS-500 switch decom | 1 | 2020-07-06 | 2020-12-31 |  | Deleted | Log | Upd | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY CA SAN ELC Voice DMS 2 Decom POR20 | CA | SAN | ELC | Voice Decom and Refortification | VCDR CA SAN ELC Voice Cypress DMS Decom POR20 | Labor | DMS-500 switch decom |  |  |  |  | Deleted | Log | Del | SN-0598 | Schedule Change | Approved | 2020-05-20 16:49 | POR Update only CR for Voice Decom
HY CE KAN DCY Voice POI Decom POR20 | CE | KAN | DCY | Voice Decom and Refortification | VCDR CE KAN DCY Voice POI Decom POR20 | Labor | No Equipment | 1 | 2020-07-06 08:00 | 2020-11-30 |  | Active | EP
HY CE KAN DCY Voice POI Decom POR20 | CE | KAN | DCY | Voice Decom and Refortification | VCDR CE KAN DCY Voice POI Decom POR20 | Labor | No Equipment | 1 | 2020-07-06 08:00 | 2020-11-30 |  | Active | Log | New | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY CE KAN HUT Voice POI Decom POR20 | CE | KAN | HUT | Voice Decom and Refortification | VCDR CE KAN HUT Voice POI Decom POR20 | Labor | No Equipment | 1 | 2020-07-06 08:00 | 2021-02-28 |  | Active | EP
HY CE KAN HUT Voice POI Decom POR20 | CE | KAN | HUT | Voice Decom and Refortification | VCDR CE KAN HUT Voice POI Decom POR20 | Labor | No Equipment | 1 | 2020-07-06 08:00 | 2020-11-30 |  | Active | Log | New | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY CE KAN HUT Voice POI Decom POR20 | CE | KAN | HUT | Voice Decom and Refortification | VCDR CE KAN HUT Voice POI Decom POR20 | Labor | No Equipment | 1 | 2020-07-06 08:00 | 2021-02-28 |  | Active | Log | Upd | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
HY CE KAN HWTHKSXA Voice POI Decom POR20 | CE | KAN | WIC | Voice Decom and Refortification | VCDR CE KAN HWTHKSXA Voice POI Decom POR20 | Labor | No Equipment | 3 | 2020-07-06 08:00 | 2021-02-28 |  | Active | EP
HY CE KAN HWTHKSXA Voice POI Decom POR20 | CE | KAN | WIC | Voice Decom and Refortification | VCDR CE KAN HWTHKSXA Voice POI Decom POR20 | Labor | No Equipment | 3 | 2020-07-06 08:00 | 2020-11-30 |  | Active | Log | New | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY CE KAN HWTHKSXA Voice POI Decom POR20 | CE | KAN | WIC | Voice Decom and Refortification | VCDR CE KAN HWTHKSXA Voice POI Decom POR20 | Labor | No Equipment | 3 | 2020-07-06 08:00 | 2021-02-28 |  | Active | Log | Upd | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
HY CE KAN MNT Voice POI Decom POR20 | CE | KAN | MNT | Voice Decom and Refortification | VCDR CE KAN MNT Voice POI Decom POR20 | Labor | No Equipment | 1 | 2020-07-06 08:00 | 2021-02-28 |  | Active | EP
HY CE KAN MNT Voice POI Decom POR20 | CE | KAN | MNT | Voice Decom and Refortification | VCDR CE KAN MNT Voice POI Decom POR20 | Labor | No Equipment | 1 | 2020-07-06 08:00 | 2020-11-30 |  | Active | Log | New | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY CE KAN MNT Voice POI Decom POR20 | CE | KAN | MNT | Voice Decom and Refortification | VCDR CE KAN MNT Voice POI Decom POR20 | Labor | No Equipment | 1 | 2020-07-06 08:00 | 2021-02-28 |  | Active | Log | Upd | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
HY CE KAN PSN Voice POI Decom POR20 | CE | KAN | PSN | Voice Decom and Refortification | VCDR CE KAN PSN Voice POI Decom POR20 | Labor | No Equipment | 1 | 2020-07-06 08:00 | 2021-02-28 |  | Active | EP
HY CE KAN PSN Voice POI Decom POR20 | CE | KAN | PSN | Voice Decom and Refortification | VCDR CE KAN PSN Voice POI Decom POR20 | Labor | No Equipment | 1 | 2020-07-06 08:00 | 2020-11-30 |  | Active | Log | New | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY CE KAN PSN Voice POI Decom POR20 | CE | KAN | PSN | Voice Decom and Refortification | VCDR CE KAN PSN Voice POI Decom POR20 | Labor | No Equipment | 1 | 2020-07-06 08:00 | 2021-02-28 |  | Active | Log | Upd | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
HY CE KAN SAL Voice POI Decom POR20 | CE | KAN | SAL | Voice Decom and Refortification | VCDR CE KAN SAL Voice POI Decom POR20 | Labor | No Equipment | 1 | 2020-07-06 08:00 | 2021-02-28 |  | Active | EP
HY CE KAN SAL Voice POI Decom POR20 | CE | KAN | SAL | Voice Decom and Refortification | VCDR CE KAN SAL Voice POI Decom POR20 | Labor | No Equipment | 1 | 2020-07-06 08:00 | 2020-11-30 |  | Active | Log | New | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY CE KAN SAL Voice POI Decom POR20 | CE | KAN | SAL | Voice Decom and Refortification | VCDR CE KAN SAL Voice POI Decom POR20 | Labor | No Equipment | 1 | 2020-07-06 08:00 | 2021-02-28 |  | Active | Log | Upd | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
HY CE KAN TOP Voice POI Decom POR20 | CE | KAN | TOP | Voice Decom and Refortification | VCDR CE KAN TOP Voice POI Decom POR20 | Labor | No Equipment | 2 | 2020-07-06 | 2021-02-28 |  | Active | EP
HY CE KAN TOP Voice POI Decom POR20 | CE | KAN | TOP | Voice Decom and Refortification | VCDR CE KAN TOP Voice POI Decom POR20 | Labor | No Equipment | 2 | 2020-07-06 | 2020-11-30 |  | Active | Log | New | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY CE KAN TOP Voice POI Decom POR20 | CE | KAN | TOP | Voice Decom and Refortification | VCDR CE KAN TOP Voice POI Decom POR20 | Labor | No Equipment | 2 | 2020-07-06 | 2021-02-28 |  | Active | Log | Upd | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
HY CE KAN WIC Voice DMS Decom POR20 | CE | KAN | WIC | Voice Decom and Refortification | VCDR CE KAN WIC Voice DMS Decom POR20 | Labor | No Equipment | 1 |  | 2021-03-03 |  | Active | EP
HY CE KAN WIC Voice DMS Decom POR20 | CE | KAN | WIC | Voice Decom and Refortification | VCDR CE KAN WIC Voice DMS Decom POR20 | Labor | No Equipment | 1 | 2020-05-06 | 2020-12-31 |  | Active | Log | New | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY CE KAN WIC Voice DMS Decom POR20 | CE | KAN | WIC | Voice Decom and Refortification | VCDR CE KAN WIC Voice DMS Decom POR20 | Labor | No Equipment | 1 |  | 2021-03-03 |  | Active | Log | Upd | SN-0423 | Schedule Change | Approved | 2020-04-10 14:17 | POR update only CR for Voice Decom to align Activity Plan to EPS projects
HY SW ARZ CHD Voice DMS 2 Decom POR20 | SW | ARZ | CHD | Voice Decom and Refortification | VCDR SW ARZ CHD Voice DMS 2 Decom POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
HY SW ARZ CHD Voice DMS 2 Decom POR20 | SW | ARZ | CHD | Voice Decom and Refortification | VCDR SW ARZ CHD Voice DMS 2 Decom POR20 | Labor | No Equipment | 1 | 2020-03-06 | 2020-08-31 |  | Deleted | Log | New | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY SW ARZ CHD Voice DMS 2 Decom POR20 | SW | ARZ | CHD | Voice Decom and Refortification | VCDR SW ARZ CHD Voice DMS 2 Decom POR20 | Labor | No Equipment | 1 |  | 2020-10-09 |  | Deleted | Log | Upd | SN-0423 | Schedule Change | Approved | 2020-04-10 14:17 | POR update only CR for Voice Decom to align Activity Plan to EPS projects
HY SW ARZ CHD Voice DMS 2 Decom POR20 | SW | ARZ | CHD | Voice Decom and Refortification | VCDR SW ARZ CHD Voice DMS 2 Decom POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0598 | Schedule Change | Approved | 2020-05-20 16:49 | POR Update only CR for Voice Decom
HY SW ARZ PEO Voice HDT Decom POR20 | SW | ARZ | PEO | Voice Decom and Refortification | VCDR SW ARZ PEO Voice HDT Decom POR21 | Labor | No Equipment |  |  |  |  | Deleted | EP
HY SW ARZ PEO Voice HDT Decom POR20 | SW | ARZ | PEO | Voice Decom and Refortification | VCDR SW ARZ PEO Voice HDT Decom POR21 |  |  | 32 | 2020-01-06 | 2020-04-30 |  | Deleted | Log | New | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY SW ARZ PEO Voice HDT Decom POR20 | SW | ARZ | PEO | Voice Decom and Refortification | VCDR SW ARZ PEO Voice HDT Decom POR21 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY CE KAN WIC Voice HDT Decom POR20 | CE | KAN | WIC | Voice Decom and Refortification | VCDR CE KAN WIC Voice HDT Decom POR20 | Labor | No Equipment | 1 |  | 2021-05-05 |  | Active | EP
HY CE KAN WIC Voice HDT Decom POR20 | CE | KAN | WIC | Voice Decom and Refortification | VCDR CE KAN WIC Voice HDT Decom POR20 | Labor | No Equipment | 28 | 2020-05-06 | 2020-12-31 |  | Active | Log | New | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY CE KAN WIC Voice HDT Decom POR20 | CE | KAN | WIC | Voice Decom and Refortification | VCDR CE KAN WIC Voice HDT Decom POR20 | Labor | No Equipment | 1 |  | 2021-05-05 |  | Active | Log | Upd | SN-0423 | Schedule Change | Approved | 2020-04-10 14:17 | POR update only CR for Voice Decom to align Activity Plan to EPS projects
HY CA ORG DNP Voice HDT Decom POR20 | CA | ORG | DNP | Voice Decom and Refortification | VCDR CA ORG DNP Voice HDT Decom POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 |  | Active | EP
HY CA ORG DNP Voice HDT Decom POR20 | CA | ORG | DNP | Voice Decom and Refortification | VCDR CA ORG DNP Voice HDT Decom POR20 | Labor | No Equipment | 17 | 2019-11-07 | 2020-03-15 |  | Active | Log | New | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY CA ORG DNP Voice HDT Decom POR20 | CA | ORG | DNP | Voice Decom and Refortification | VCDR CA ORG DNP Voice HDT Decom POR20 | Labor | No Equipment | 17 | 2019-11-07 | 2020-04-10 |  | Active | Log | Upd | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY CA ORG DNP Voice HDT Decom POR20 | CA | ORG | DNP | Voice Decom and Refortification | VCDR CA ORG DNP Voice HDT Decom POR20 | Labor | No Equipment | 1 |  | 2020-06-30 |  | Active | Log | Upd | SN-0423 | Schedule Change | Approved | 2020-04-10 14:17 | POR update only CR for Voice Decom to align Activity Plan to EPS projects
HY CA ORG DNP Voice HDT Decom POR20 | CA | ORG | DNP | Voice Decom and Refortification | VCDR CA ORG DNP Voice HDT Decom POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-30 |  | Active | Log | Upd | SN-0644 | True up | Approved | 2020-06-15 18:09 | 1 Variance of Capex labor 9k has been self solved and Opex labor of 3k self solved and reason for variance is mentioned in the comments section 2 New start dates FCED are updated in the POR
HY CA ORG DNP Voice HDT Decom POR20 | CA | ORG | DNP | Voice Decom and Refortification | VCDR CA ORG DNP Voice HDT Decom POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 |  | Active | Log | Upd | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
HY CA ORG DNP Voice HDT Decom POR20 | CA | ORG | DNP | Voice Decom and Refortification | VCDR CA ORG DNP Voice HDT Decom POR20 | Labor | No Equipment |  |  |  |  | Active | Log | Del | SN-1028 | Schedule Change | Approved | 2020-10-23 14:37 | Moved the Capex Corp fund to SE SW Central and VA due to change in priorities to complete HDT shutdown activities
HY CA ORG DNP Voice HDT Decom POR20 | CA | ORG | DNP | Voice Decom and Refortification | VCDR CA ORG DNP Voice HDT Decom POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 |  | Active | Log | Undel | SN-1080 | Schedule Change | Approved | 2020-11-20 13:46 | Voice Decom CR only for POR updates
HY VA HRD PTM Voice HDT Decom POR20 | VA | HRD | PTM | Voice Decom and Refortification | VCDR VA HRD PTM Voice HDT Decom POR20 | Labor | No Equipment | 1 | 2020-05-20 | 2020-07-31 |  | Active | EP
HY VA HRD PTM Voice HDT Decom POR20 | VA | HRD | PTM | Voice Decom and Refortification | VCDR VA HRD PTM Voice HDT Decom POR20 | Labor | No Equipment | 7 | 2020-01-13 | 2020-12-31 |  | Active | Log | New | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY VA HRD PTM Voice HDT Decom POR20 | VA | HRD | PTM | Voice Decom and Refortification | VCDR VA HRD PTM Voice HDT Decom POR20 | Labor | No Equipment | 1 |  | 2020-06-30 |  | Active | Log | Upd | SN-0423 | Schedule Change | Approved | 2020-04-10 14:17 | POR update only CR for Voice Decom to align Activity Plan to EPS projects
HY VA HRD PTM Voice HDT Decom POR20 | VA | HRD | PTM | Voice Decom and Refortification | VCDR VA HRD PTM Voice HDT Decom POR20 | Labor | No Equipment | 1 | 2020-05-20 | 2020-06-30 |  | Active | Log | Upd | SN-0644 | True up | Approved | 2020-06-15 18:09 | 1 Variance of Capex labor 9k has been self solved and Opex labor of 3k self solved and reason for variance is mentioned in the comments section 2 New start dates FCED are updated in the POR
HY VA HRD PTM Voice HDT Decom POR20 | VA | HRD | PTM | Voice Decom and Refortification | VCDR VA HRD PTM Voice HDT Decom POR20 | Labor | No Equipment | 1 | 2020-05-20 | 2020-07-31 |  | Active | Log | Upd | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
HY CE NWA HRN Voice POI Decom POR20 | CE | NWA | HRN | Voice Decom and Refortification | VCDR CE NWA HRN Voice POI Decom POR20 | Labor | No Equipment | 1 |  | 2020-12-31 |  | Active | EP
HY CE NWA HRN Voice POI Decom POR20 | CE | NWA | HRN | Voice Decom and Refortification | VCDR CE NWA HRN Voice POI Decom POR20 | Labor | No Equipment | 2 | 2019-11-06 | 2020-03-31 |  | Active | Log | Undel | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY CE NWA HRN Voice POI Decom POR20 | CE | NWA | HRN | Voice Decom and Refortification | VCDR CE NWA HRN Voice POI Decom POR20 | Labor | No Equipment | 1 |  | 2020-10-09 |  | Active | Log | Upd | SN-0423 | Schedule Change | Approved | 2020-04-10 14:17 | POR update only CR for Voice Decom to align Activity Plan to EPS projects
HY CE NWA HRN Voice POI Decom POR20 | CE | NWA | HRN | Voice Decom and Refortification | VCDR CE NWA HRN Voice POI Decom POR20 | Labor | No Equipment | 1 |  | 2020-12-31 |  | Active | Log | Upd | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
HY CE OMA ONA Voice HDT Decom POR20 | CE | OMA | ONA | Voice Decom and Refortification | VCDR CE OMA ONA Voice HDT Decom POR20 | Labor | No Equipment | 17 | 2020-08-03 | 2020-11-30 |  | Active | EP
HY CE OMA ONA Voice HDT Decom POR20 | CE | OMA | ONA | Voice Decom and Refortification | VCDR CE OMA ONA Voice HDT Decom POR20 | Labor | No Equipment | 17 | 2020-08-03 | 2020-10-31 |  | Active | Log | Undel | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY CE OMA ONA Voice HDT Decom POR20 | CE | OMA | ONA | Voice Decom and Refortification | VCDR CE OMA ONA Voice HDT Decom POR20 | Labor | No Equipment | 17 | 2020-08-03 | 2020-11-30 |  | Active | Log | Upd | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
HY CE TUL TULSOKTB Voice POI Decom POR19 | CE | TUL | TUL | Voice Decom and Refortification | VCDR CE TUL TULSOKTB Voice POI Decom POR20 | Labor | No Equipment | 1 |  | 2021-03-02 |  | Active | EP
HY CE TUL TULSOKTB Voice POI Decom POR19 | CE | TUL | TUL | Voice Decom and Refortification | VCDR CE TUL TULSOKTB Voice POI Decom POR20 | Labor | No Equipment | 2 | 2019-11-06 | 2020-02-28 |  | Active | Log | Undel | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY CE TUL TULSOKTB Voice POI Decom POR19 | CE | TUL | TUL | Voice Decom and Refortification | VCDR CE TUL TULSOKTB Voice POI Decom POR20 | Labor | No Equipment | 1 |  | 2020-06-05 |  | Active | Log | Upd | SN-0423 | Schedule Change | Approved | 2020-04-10 14:17 | POR update only CR for Voice Decom to align Activity Plan to EPS projects
HY CE TUL TULSOKTB Voice POI Decom POR19 | CE | TUL | TUL | Voice Decom and Refortification | VCDR CE TUL TULSOKTB Voice POI Decom POR20 | Labor | No Equipment | 1 |  | 2020-12-11 |  | Active | Log | Upd | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
HY CE TUL TULSOKTB Voice POI Decom POR19 | CE | TUL | TUL | Voice Decom and Refortification | VCDR CE TUL TULSOKTB Voice POI Decom POR20 | Labor | No Equipment | 1 |  | 2021-03-02 |  | Active | Log | Upd | SN-0850 | Schedule Change | Approved | 2020-08-20 18:04 | Overall there is a give back of Capex 6300 is due to slow down in HDT Decom activities in all regions except SE Plan Alignment Reasons are mentioned in the comments section of CR
HY SE NOR KNN Voice HDT Decom POR19 | SE | NOR | KNN | Voice Decom and Refortification | VCDR SE NOR KNN Voice HDT Decom POR20 | Labor | No Equipment | 7 | 2020-03-31 | 2020-12-31 |  | Active | EP
HY SE NOR KNN Voice HDT Decom POR19 | SE | NOR | KNN | Voice Decom and Refortification | VCDR SE NOR KNN Voice HDT Decom POR20 | Labor | No Equipment | 7 | 2019-11-06 | 2020-06-30 |  | Active | Log | Undel | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY SE NOR KNN Voice HDT Decom POR19 | SE | NOR | KNN | Voice Decom and Refortification | VCDR SE NOR KNN Voice HDT Decom POR20 | Labor | No Equipment | 7 | 2020-03-31 | 2020-06-30 |  | Active | Log | Upd | SN-0644 | True up | Approved | 2020-06-15 18:09 | 1 Variance of Capex labor 9k has been self solved and Opex labor of 3k self solved and reason for variance is mentioned in the comments section 2 New start dates FCED are updated in the POR
HY SE NOR KNN Voice HDT Decom POR19 | SE | NOR | KNN | Voice Decom and Refortification | VCDR SE NOR KNN Voice HDT Decom POR20 | Labor | No Equipment | 7 | 2020-03-31 | 2020-09-30 |  | Active | Log | Upd | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
HY SE NOR KNN Voice HDT Decom POR19 | SE | NOR | KNN | Voice Decom and Refortification | VCDR SE NOR KNN Voice HDT Decom POR20 | Labor | No Equipment | 7 | 2020-03-31 | 2020-12-31 |  | Active | Log | Upd | SN-0818 | True up | Approved | 2020-08-12 14:16 | Major unfavorable variance of 42k in Opex Corp is due to pending timesheets from previous month and is self solved Reasons for variance are mentioned in the comments section of the CR
HY SE BTR BTR Voice BTS Gateway Decom POR19 | SE | BTR | BTR | Voice Decom and Refortification | VCDR SE BTR BTR Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 | 2020-07-06 | 2020-12-31 |  | Active | EP
HY SE BTR BTR Voice BTS Gateway Decom POR19 | SE | BTR | BTR | Voice Decom and Refortification | VCDR SE BTR BTR Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 | 2019-11-06 | 2020-04-15 |  | Active | Log | Undel | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY SE BTR BTR Voice BTS Gateway Decom POR19 | SE | BTR | BTR | Voice Decom and Refortification | VCDR SE BTR BTR Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 |  | 2020-07-14 |  | Active | Log | Upd | SN-0423 | Schedule Change | Approved | 2020-04-10 14:17 | POR update only CR for Voice Decom to align Activity Plan to EPS projects
HY SE BTR BTR Voice BTS Gateway Decom POR19 | SE | BTR | BTR | Voice Decom and Refortification | VCDR SE BTR BTR Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 | 2020-07-06 | 2020-09-30 |  | Active | Log | Upd | SN-0610 | Schedule Change | Approved | 2020-05-29 15:07 | POR update only CR for Voice Decom
HY SE BTR BTR Voice BTS Gateway Decom POR19 | SE | BTR | BTR | Voice Decom and Refortification | VCDR SE BTR BTR Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 | 2020-07-06 | 2020-12-31 |  | Active | Log | Upd | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
HY SE GAN GNS Voice BTS Gateway Decom POR19 | SE | GAN | GNS | Voice Decom and Refortification | VCDR SE GAN GNS Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 | 2020-05-04 | 2020-11-30 |  | Active | EP
HY SE GAN GNS Voice BTS Gateway Decom POR19 | SE | GAN | GNS | Voice Decom and Refortification | VCDR SE GAN GNS Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 | 2019-10-06 | 2020-05-07 |  | Active | Log | Undel | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY SE GAN GNS Voice BTS Gateway Decom POR19 | SE | GAN | GNS | Voice Decom and Refortification | VCDR SE GAN GNS Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 |  | 2020-07-14 |  | Active | Log | Upd | SN-0423 | Schedule Change | Approved | 2020-04-10 14:17 | POR update only CR for Voice Decom to align Activity Plan to EPS projects
HY SE GAN GNS Voice BTS Gateway Decom POR19 | SE | GAN | GNS | Voice Decom and Refortification | VCDR SE GAN GNS Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 | 2020-05-04 | 2020-09-30 |  | Active | Log | Upd | SN-0610 | Schedule Change | Approved | 2020-05-29 15:07 | POR update only CR for Voice Decom
HY SE GAN GNS Voice BTS Gateway Decom POR19 | SE | GAN | GNS | Voice Decom and Refortification | VCDR SE GAN GNS Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 | 2020-05-04 | 2020-11-30 |  | Active | Log | Upd | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
HY SE GCT PNS Voice BTS Gateway Decom POR19 | SE | GCT | PNS | Voice Decom and Refortification | VCDR SE GCT PNS Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 | 2020-07-06 | 2020-12-31 |  | Active | EP
HY SE GCT PNS Voice BTS Gateway Decom POR19 | SE | GCT | PNS | Voice Decom and Refortification | VCDR SE GCT PNS Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 | 2019-10-07 | 2020-05-07 |  | Active | Log | Undel | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY SE GCT PNS Voice BTS Gateway Decom POR19 | SE | GCT | PNS | Voice Decom and Refortification | VCDR SE GCT PNS Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 |  | 2020-07-14 |  | Active | Log | Upd | SN-0423 | Schedule Change | Approved | 2020-04-10 14:17 | POR update only CR for Voice Decom to align Activity Plan to EPS projects
HY SE GCT PNS Voice BTS Gateway Decom POR19 | SE | GCT | PNS | Voice Decom and Refortification | VCDR SE GCT PNS Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 | 2020-07-06 | 2020-09-30 |  | Active | Log | Upd | SN-0610 | Schedule Change | Approved | 2020-05-29 15:07 | POR update only CR for Voice Decom
HY SE GCT PNS Voice BTS Gateway Decom POR19 | SE | GCT | PNS | Voice Decom and Refortification | VCDR SE GCT PNS Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 | 2020-07-06 | 2020-12-31 |  | Active | Log | Upd | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
HY SE LFY LFY Voice BTS Gateway Decom POR19 | SE | LFY | LFY | Voice Decom and Refortification | VCDR SE LFY LFY Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 | 2020-07-06 | 2020-12-31 |  | Active | EP
HY SE LFY LFY Voice BTS Gateway Decom POR19 | SE | LFY | LFY | Voice Decom and Refortification | VCDR SE LFY LFY Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 | 2019-11-06 | 2020-04-15 |  | Active | Log | Undel | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY SE LFY LFY Voice BTS Gateway Decom POR19 | SE | LFY | LFY | Voice Decom and Refortification | VCDR SE LFY LFY Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 |  | 2020-07-14 |  | Active | Log | Upd | SN-0423 | Schedule Change | Approved | 2020-04-10 14:17 | POR update only CR for Voice Decom to align Activity Plan to EPS projects
HY SE LFY LFY Voice BTS Gateway Decom POR19 | SE | LFY | LFY | Voice Decom and Refortification | VCDR SE LFY LFY Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 | 2020-07-06 | 2020-09-30 |  | Active | Log | Upd | SN-0610 | Schedule Change | Approved | 2020-05-29 15:07 | POR update only CR for Voice Decom
HY SE LFY LFY Voice BTS Gateway Decom POR19 | SE | LFY | LFY | Voice Decom and Refortification | VCDR SE LFY LFY Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 | 2020-07-06 | 2020-12-31 |  | Active | Log | Upd | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
HY SE MGA MCN Voice BTS Gateway Decom POR19 | SE | MGA | MCN | Voice Decom and Refortification | VCDR SE MGA MCN Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 | 2020-06-01 | 2021-01-31 |  | Active | EP
HY SE MGA MCN Voice BTS Gateway Decom POR19 | SE | MGA | MCN | Voice Decom and Refortification | VCDR SE MGA MCN Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 | 2019-10-07 | 2020-04-15 |  | Active | Log | Undel | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY SE MGA MCN Voice BTS Gateway Decom POR19 | SE | MGA | MCN | Voice Decom and Refortification | VCDR SE MGA MCN Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 |  | 2020-07-14 |  | Active | Log | Upd | SN-0423 | Schedule Change | Approved | 2020-04-10 14:17 | POR update only CR for Voice Decom to align Activity Plan to EPS projects
HY SE MGA MCN Voice BTS Gateway Decom POR19 | SE | MGA | MCN | Voice Decom and Refortification | VCDR SE MGA MCN Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 | 2020-06-01 | 2020-09-30 |  | Active | Log | Upd | SN-0610 | Schedule Change | Approved | 2020-05-29 15:07 | POR update only CR for Voice Decom
HY SE MGA MCN Voice BTS Gateway Decom POR19 | SE | MGA | MCN | Voice Decom and Refortification | VCDR SE MGA MCN Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 | 2020-06-01 | 2021-01-31 |  | Active | Log | Upd | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
HY SW ARZ VSA Voice HDT Decom POR20 | SW | ARZ | VSA | Voice Decom and Refortification | VCDR SW ARZ VSA Voice HDT Decom POR20 | Labor | No Equipment | 2 | 2020-05-07 | 2020-07-30 |  | Active | EP
HY SW ARZ VSA Voice HDT Decom POR20 | SW | ARZ | VSA | Voice Decom and Refortification | VCDR SW ARZ VSA Voice HDT Decom POR20 | Labor | No Equipment | 2 | 2020-01-06 | 2020-04-30 |  | Active | Log | Undel | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY SW ARZ VSA Voice HDT Decom POR20 | SW | ARZ | VSA | Voice Decom and Refortification | VCDR SW ARZ VSA Voice HDT Decom POR20 | Labor | No Equipment | 1 |  | 2020-06-30 |  | Active | Log | Upd | SN-0423 | Schedule Change | Approved | 2020-04-10 14:17 | POR update only CR for Voice Decom to align Activity Plan to EPS projects
HY SW ARZ VSA Voice HDT Decom POR20 | SW | ARZ | VSA | Voice Decom and Refortification | VCDR SW ARZ VSA Voice HDT Decom POR20 | Labor | No Equipment | 2 | 2020-05-07 | 2020-06-30 |  | Active | Log | Upd | SN-0598 | Schedule Change | Approved | 2020-05-20 16:49 | POR Update only CR for Voice Decom
HY SW ARZ VSA Voice HDT Decom POR20 | SW | ARZ | VSA | Voice Decom and Refortification | VCDR SW ARZ VSA Voice HDT Decom POR20 | Labor | No Equipment |  |  |  |  | Active | Log | Del | SN-0884 | Schedule Change | Approved | 2020-09-02 13:33 | Allocated the 500k Opex funds in Corp PPM 77906 for Automation resources expenses Details are provided in the additional sheet Break up of 500k Opex plan
HY SW ARZ VSA Voice HDT Decom POR20 | SW | ARZ | VSA | Voice Decom and Refortification | VCDR SW ARZ VSA Voice HDT Decom POR20 | Labor | No Equipment | 2 | 2020-05-07 | 2020-07-30 |  | Active | Log | Undel | SN-1080 | Schedule Change | Approved | 2020-11-20 13:46 | Voice Decom CR only for POR updates
HY VA-HRD-CHS Voice DMS Decom POR19 | VA | HRD | CHS | Voice Decom and Refortification | VCDR VA HRD CHS Voice DMS Decom POR19 | Labor | No Equipment | 1 |  | 2021-03-31 |  | Active | EP
HY VA-HRD-CHS Voice DMS Decom POR19 | VA | HRD | CHS | Voice Decom and Refortification | VCDR VA HRD CHS Voice DMS Decom POR19 | Labor | No Equipment | 1 | 2019-07-12 | 2020-05-29 |  | Active | Log | Undel | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY VA-HRD-CHS Voice DMS Decom POR19 | VA | HRD | CHS | Voice Decom and Refortification | VCDR VA HRD CHS Voice DMS Decom POR19 | Labor | No Equipment | 1 |  | 2020-10-30 |  | Active | Log | Upd | SN-0423 | Schedule Change | Approved | 2020-04-10 14:17 | POR update only CR for Voice Decom to align Activity Plan to EPS projects
HY VA-HRD-CHS Voice DMS Decom POR19 | VA | HRD | CHS | Voice Decom and Refortification | VCDR VA HRD CHS Voice DMS Decom POR19 | Labor | No Equipment | 1 |  | 2021-03-31 |  | Active | Log | Upd | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
HY VA HRD GBR Voice HDT Decom POR19 | VA | HRD | GBR | Voice Decom and Refortification | VCDR VA HRD GBR Voice HDT Decom POR19 | Labor | No Equipment | 1 | 2020-06-08 | 2020-12-31 |  | Active | EP
HY VA HRD GBR Voice HDT Decom POR19 | VA | HRD | GBR | Voice Decom and Refortification | VCDR VA HRD GBR Voice HDT Decom POR19 | Labor | No Equipment | 1 | 2019-08-14 | 2020-04-17 |  | Active | Log | Undel | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY VA HRD GBR Voice HDT Decom POR19 | VA | HRD | GBR | Voice Decom and Refortification | VCDR VA HRD GBR Voice HDT Decom POR19 | Labor | No Equipment | 1 |  | 2020-06-30 |  | Active | Log | Upd | SN-0423 | Schedule Change | Approved | 2020-04-10 14:17 | POR update only CR for Voice Decom to align Activity Plan to EPS projects
HY VA HRD GBR Voice HDT Decom POR19 | VA | HRD | GBR | Voice Decom and Refortification | VCDR VA HRD GBR Voice HDT Decom POR19 | Labor | No Equipment | 1 | 2020-04-10 | 2020-09-30 |  | Active | Log | Upd | SN-0598 | Schedule Change | Approved | 2020-05-20 16:49 | POR Update only CR for Voice Decom
HY VA HRD GBR Voice HDT Decom POR19 | VA | HRD | GBR | Voice Decom and Refortification | VCDR VA HRD GBR Voice HDT Decom POR19 | Labor | No Equipment | 1 | 2020-06-08 | 2020-09-30 |  | Active | Log | Upd | SN-0644 | True up | Approved | 2020-06-15 18:09 | 1 Variance of Capex labor 9k has been self solved and Opex labor of 3k self solved and reason for variance is mentioned in the comments section 2 New start dates FCED are updated in the POR
HY VA HRD GBR Voice HDT Decom POR19 | VA | HRD | GBR | Voice Decom and Refortification | VCDR VA HRD GBR Voice HDT Decom POR19 | Labor | No Equipment | 1 | 2020-06-08 | 2020-12-31 |  | Active | Log | Upd | SN-0884 | Schedule Change | Approved | 2020-09-02 13:33 | Allocated the 500k Opex funds in Corp PPM 77906 for Automation resources expenses Details are provided in the additional sheet Break up of 500k Opex plan
HY VA HRD GLO Voice HDT Decom POR19 | VA | HRD | GLO | Voice Decom and Refortification | VCDR VA HRD GLO Voice HDT Decom POR19 | Labor | No Equipment | 1 | 2020-04-10 | 2020-12-31 |  | Active | EP
HY VA HRD GLO Voice HDT Decom POR19 | VA | HRD | GLO | Voice Decom and Refortification | VCDR VA HRD GLO Voice HDT Decom POR19 | Labor | No Equipment | 2 | 2019-08-14 | 2020-04-17 |  | Active | Log | Undel | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY VA HRD GLO Voice HDT Decom POR19 | VA | HRD | GLO | Voice Decom and Refortification | VCDR VA HRD GLO Voice HDT Decom POR19 | Labor | No Equipment | 1 |  | 2020-06-30 |  | Active | Log | Upd | SN-0423 | Schedule Change | Approved | 2020-04-10 14:17 | POR update only CR for Voice Decom to align Activity Plan to EPS projects
HY VA HRD GLO Voice HDT Decom POR19 | VA | HRD | GLO | Voice Decom and Refortification | VCDR VA HRD GLO Voice HDT Decom POR19 | Labor | No Equipment | 1 | 2020-04-10 | 2020-09-30 |  | Active | Log | Upd | SN-0598 | Schedule Change | Approved | 2020-05-20 16:49 | POR Update only CR for Voice Decom
HY VA HRD GLO Voice HDT Decom POR19 | VA | HRD | GLO | Voice Decom and Refortification | VCDR VA HRD GLO Voice HDT Decom POR19 | Labor | No Equipment | 1 | 2020-04-10 | 2020-09-30 |  | Active | Log | Upd | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
HY VA HRD GLO Voice HDT Decom POR19 | VA | HRD | GLO | Voice Decom and Refortification | VCDR VA HRD GLO Voice HDT Decom POR19 | Labor | No Equipment | 1 | 2020-04-10 | 2020-12-31 |  | Active | Log | Upd | SN-0818 | True up | Approved | 2020-08-12 14:16 | Major unfavorable variance of 42k in Opex Corp is due to pending timesheets from previous month and is self solved Reasons for variance are mentioned in the comments section of the CR
HY VA HRD HCK Voice HDT Decom POR19 | VA | HRD | HCK | Voice Decom and Refortification | VCDR VA HRD HCK Voice HDT Decom POR20 | Labor | No Equipment | 1 | 2020-05-14 | 2020-12-31 |  | Active | EP
HY VA HRD HCK Voice HDT Decom POR19 | VA | HRD | HCK | Voice Decom and Refortification | VCDR VA HRD HCK Voice HDT Decom POR20 | Labor | No Equipment | 7 | 2019-08-14 | 2020-04-17 |  | Active | Log | Undel | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY VA HRD HCK Voice HDT Decom POR19 | VA | HRD | HCK | Voice Decom and Refortification | VCDR VA HRD HCK Voice HDT Decom POR20 | Labor | No Equipment | 1 |  | 2020-06-30 |  | Active | Log | Upd | SN-0423 | Schedule Change | Approved | 2020-04-10 14:17 | POR update only CR for Voice Decom to align Activity Plan to EPS projects
HY VA HRD HCK Voice HDT Decom POR19 | VA | HRD | HCK | Voice Decom and Refortification | VCDR VA HRD HCK Voice HDT Decom POR20 | Labor | No Equipment | 1 | 2020-05-14 | 2020-06-30 |  | Active | Log | Upd | SN-0644 | True up | Approved | 2020-06-15 18:09 | 1 Variance of Capex labor 9k has been self solved and Opex labor of 3k self solved and reason for variance is mentioned in the comments section 2 New start dates FCED are updated in the POR
HY VA HRD HCK Voice HDT Decom POR19 | VA | HRD | HCK | Voice Decom and Refortification | VCDR VA HRD HCK Voice HDT Decom POR20 | Labor | No Equipment | 1 | 2020-05-14 | 2020-07-31 |  | Active | Log | Upd | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
HY VA HRD HCK Voice HDT Decom POR19 | VA | HRD | HCK | Voice Decom and Refortification | VCDR VA HRD HCK Voice HDT Decom POR20 | Labor | No Equipment | 1 | 2020-05-14 | 2020-12-31 |  | Active | Log | Upd | SN-0884 | Schedule Change | Approved | 2020-09-02 13:33 | Allocated the 500k Opex funds in Corp PPM 77906 for Automation resources expenses Details are provided in the additional sheet Break up of 500k Opex plan
HY VA HRD LTF Voice HDT Decom POR19 | VA | HRD | LTF | Voice Decom and Refortification | VCDR VA HRD LTF Voice HDT Decom POR19 | Labor | No Equipment | 1 | 2020-04-10 | 2020-12-31 |  | Active | EP
HY VA HRD LTF Voice HDT Decom POR19 | VA | HRD | LTF | Voice Decom and Refortification | VCDR VA HRD LTF Voice HDT Decom POR19 | Labor | No Equipment | 8 | 2019-11-06 | 2020-04-17 |  | Active | Log | Undel | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY VA HRD LTF Voice HDT Decom POR19 | VA | HRD | LTF | Voice Decom and Refortification | VCDR VA HRD LTF Voice HDT Decom POR19 | Labor | No Equipment | 1 |  | 2020-06-30 |  | Active | Log | Upd | SN-0423 | Schedule Change | Approved | 2020-04-10 14:17 | POR update only CR for Voice Decom to align Activity Plan to EPS projects
HY VA HRD LTF Voice HDT Decom POR19 | VA | HRD | LTF | Voice Decom and Refortification | VCDR VA HRD LTF Voice HDT Decom POR19 | Labor | No Equipment | 1 | 2020-04-10 | 2020-09-30 |  | Active | Log | Upd | SN-0598 | Schedule Change | Approved | 2020-05-20 16:49 | POR Update only CR for Voice Decom
HY VA HRD LTF Voice HDT Decom POR19 | VA | HRD | LTF | Voice Decom and Refortification | VCDR VA HRD LTF Voice HDT Decom POR19 | Labor | No Equipment | 1 | 2020-04-10 | 2020-12-31 |  | Active | Log | Upd | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
HY VA ROA RON Voice BTS Gateway Decom POR19 | VA | ROA | RON | Voice Decom and Refortification | VCDR VA ROA RON Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 | 2020-07-06 | 2020-12-31 |  | Active | EP
HY VA ROA RON Voice BTS Gateway Decom POR19 | VA | ROA | RON | Voice Decom and Refortification | VCDR VA ROA RON Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 | 2019-10-07 | 2020-04-17 |  | Active | Log | Undel | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY VA ROA RON Voice BTS Gateway Decom POR19 | VA | ROA | RON | Voice Decom and Refortification | VCDR VA ROA RON Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 | 2020-07-06 | 2020-09-30 |  | Active | Log | Upd | SN-0610 | Schedule Change | Approved | 2020-05-29 15:07 | POR update only CR for Voice Decom
HY VA ROA RON Voice BTS Gateway Decom POR19 | VA | ROA | RON | Voice Decom and Refortification | VCDR VA ROA RON Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 | 2020-07-06 | 2020-12-31 |  | Active | Log | Upd | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
HY COR COR DDR Voice BTS Decom POR19 | COR | COR | DDR | Voice Decom and Refortification | VCDR COR COR DDR Voice BTS Decom POR19 | Labor | No Equipment | 1 | 2020-07-01 | 2020-10-31 |  | Active | EP
HY COR COR DDR Voice BTS Decom POR19 | COR | COR | DDR | Voice Decom and Refortification | VCDR COR COR DDR Voice BTS Decom POR19 | Labor | No Equipment | 1 | 2019-10-07 | 2020-05-07 |  | Active | Log | Undel | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY COR COR DDR Voice BTS Decom POR19 | COR | COR | DDR | Voice Decom and Refortification | VCDR COR COR DDR Voice BTS Decom POR19 | Labor | No Equipment | 1 |  | 2020-07-23 |  | Active | Log | Upd | SN-0423 | Schedule Change | Approved | 2020-04-10 14:17 | POR update only CR for Voice Decom to align Activity Plan to EPS projects
HY COR COR DDR Voice BTS Decom POR19 | COR | COR | DDR | Voice Decom and Refortification | VCDR COR COR DDR Voice BTS Decom POR19 | Labor | No Equipment | 1 | 2020-07-01 | 2020-10-31 |  | Active | Log | Upd | SN-0610 | Schedule Change | Approved | 2020-05-29 15:07 | POR update only CR for Voice Decom
HY COR COR P6L Voice BTS Decom POR19 | COR | COR | P6L | Voice Decom and Refortification | VCDR COR COR P6L Voice BTS Decom POR19 | Labor | No Equipment | 1 | 2020-07-06 | 2020-10-31 |  | Active | EP
HY COR COR P6L Voice BTS Decom POR19 | COR | COR | P6L | Voice Decom and Refortification | VCDR COR COR P6L Voice BTS Decom POR19 | Labor | No Equipment | 1 | 2019-11-06 | 2020-05-07 |  | Active | Log | Undel | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY COR COR P6L Voice BTS Decom POR19 | COR | COR | P6L | Voice Decom and Refortification | VCDR COR COR P6L Voice BTS Decom POR19 | Labor | No Equipment | 1 |  | 2020-08-10 |  | Active | Log | Upd | SN-0423 | Schedule Change | Approved | 2020-04-10 14:17 | POR update only CR for Voice Decom to align Activity Plan to EPS projects
HY COR COR P6L Voice BTS Decom POR19 | COR | COR | P6L | Voice Decom and Refortification | VCDR COR COR P6L Voice BTS Decom POR19 | Labor | No Equipment | 1 | 2020-07-06 | 2020-10-31 |  | Active | Log | Upd | SN-0610 | Schedule Change | Approved | 2020-05-29 15:07 | POR update only CR for Voice Decom
VCDR CA SAB SAB Voice Gateway Decom POR20 | CA | SAB | SAB | Voice Decom and Refortification | VCDR CA SAB SAB Voice Gateway Decom POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 |  | Active | EP
VCDR CA SAB SAB Voice Gateway Decom POR20 | CA | SAB | SAB | Voice Decom and Refortification | VCDR CA SAB SAB Voice Gateway Decom POR20 | Labor | No Equipment | 1 |  | 2020-06-30 |  | Active | Log | Undel | SN-0423 | Schedule Change | Approved | 2020-04-10 14:17 | POR update only CR for Voice Decom to align Activity Plan to EPS projects
VCDR CA SAB SAB Voice Gateway Decom POR20 | CA | SAB | SAB | Voice Decom and Refortification | VCDR CA SAB SAB Voice Gateway Decom POR20 | Labor | No Equipment | 1 | 2020-04-10 | 2020-09-30 |  | Active | Log | Upd | SN-0598 | Schedule Change | Approved | 2020-05-20 16:49 | POR Update only CR for Voice Decom
VCDR CA SAB SAB Voice Gateway Decom POR20 | CA | SAB | SAB | Voice Decom and Refortification | VCDR CA SAB SAB Voice Gateway Decom POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-09-30 |  | Active | Log | Upd | SN-0644 | True up | Approved | 2020-06-15 18:09 | 1 Variance of Capex labor 9k has been self solved and Opex labor of 3k self solved and reason for variance is mentioned in the comments section 2 New start dates FCED are updated in the POR
VCDR CA SAB SAB Voice Gateway Decom POR20 | CA | SAB | SAB | Voice Decom and Refortification | VCDR CA SAB SAB Voice Gateway Decom POR20 | Labor | No Equipment |  |  |  |  | Active | Log | Del | SN-0884 | Schedule Change | Approved | 2020-09-02 13:33 | Allocated the 500k Opex funds in Corp PPM 77906 for Automation resources expenses Details are provided in the additional sheet Break up of 500k Opex plan
VCDR CA SAB SAB Voice Gateway Decom POR20 | CA | SAB | SAB | Voice Decom and Refortification | VCDR CA SAB SAB Voice Gateway Decom POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 |  | Active | Log | Undel | SN-1080 | Schedule Change | Approved | 2020-11-20 13:46 | Voice Decom CR only for POR updates
VCDR CA SAN ELC Voice HDT Decom POR19 | CA | SAN | ELC | Voice Decom and Refortification | VCDR CA SAN ELC Voice HDT Decom POR19 | Labor | No Equipment | 1 |  | 2020-12-31 |  | Active | EP
VCDR CA SAN ELC Voice HDT Decom POR19 | CA | SAN | ELC | Voice Decom and Refortification | VCDR CA SAN ELC Voice HDT Decom POR19 | Labor | No Equipment | 1 |  | 2020-08-17 |  | Active | Log | Undel | SN-0423 | Schedule Change | Approved | 2020-04-10 14:17 | POR update only CR for Voice Decom to align Activity Plan to EPS projects
VCDR CA SAN ELC Voice HDT Decom POR19 | CA | SAN | ELC | Voice Decom and Refortification | VCDR CA SAN ELC Voice HDT Decom POR19 | Labor | No Equipment | 1 |  | 2020-12-31 |  | Active | Log | Upd | SN-0818 | True up | Approved | 2020-08-12 14:16 | Major unfavorable variance of 42k in Opex Corp is due to pending timesheets from previous month and is self solved Reasons for variance are mentioned in the comments section of the CR
VCDR CE KAN JCY Voice POI Decom POR20 | CE | KAN | JCY | Voice Decom and Refortification | VCDR CE KAN JCY Voice POI Decom POR20 | Labor | No Equipment | 1 |  | 2021-02-28 |  | Active | EP
VCDR CE KAN JCY Voice POI Decom POR20 | CE | KAN | JCY | Voice Decom and Refortification | VCDR CE KAN JCY Voice POI Decom POR20 | Labor | No Equipment | 1 |  | 2020-10-09 |  | Active | Log | Undel | SN-0423 | Schedule Change | Approved | 2020-04-10 14:17 | POR update only CR for Voice Decom to align Activity Plan to EPS projects
VCDR CE KAN JCY Voice POI Decom POR20 | CE | KAN | JCY | Voice Decom and Refortification | VCDR CE KAN JCY Voice POI Decom POR20 | Labor | No Equipment | 1 |  | 2021-02-28 |  | Active | Log | Upd | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
VCDR CE NWA FTS Voice Gateway Decom POR20 | CE | NWA | FTS | Voice Decom and Refortification | VCDR CE NWA FTS Voice Gateway Decom POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-11 |  | Active | EP
VCDR CE NWA FTS Voice Gateway Decom POR20 | CE | NWA | FTS | Voice Decom and Refortification | VCDR CE NWA FTS Voice Gateway Decom POR20 | Labor | No Equipment | 1 |  | 2020-06-19 |  | Active | Log | Undel | SN-0423 | Schedule Change | Approved | 2020-04-10 14:17 | POR update only CR for Voice Decom to align Activity Plan to EPS projects
VCDR CE NWA FTS Voice Gateway Decom POR20 | CE | NWA | FTS | Voice Decom and Refortification | VCDR CE NWA FTS Voice Gateway Decom POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-06-19 |  | Active | Log | Upd | SN-0644 | True up | Approved | 2020-06-15 18:09 | 1 Variance of Capex labor 9k has been self solved and Opex labor of 3k self solved and reason for variance is mentioned in the comments section 2 New start dates FCED are updated in the POR
VCDR CE NWA FTS Voice Gateway Decom POR20 | CE | NWA | FTS | Voice Decom and Refortification | VCDR CE NWA FTS Voice Gateway Decom POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-11 |  | Active | Log | Upd | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
VCDR NE CLE CLV Voice Gateway Decom POR20 | NE | CLE | CLV | Voice Decom and Refortification | VCDR NE CLE CLV Voice Gateway Decom POR20 | Labor | No Equipment | 1 | 2020-06-30 | 2020-10-31 |  | Active | EP
VCDR NE CLE CLV Voice Gateway Decom POR20 | NE | CLE | CLV | Voice Decom and Refortification | VCDR NE CLE CLV Voice Gateway Decom POR20 | Labor | No Equipment | 1 |  | 2020-06-30 |  | Active | Log | New | SN-0423 | Schedule Change | Approved | 2020-04-10 14:17 | POR update only CR for Voice Decom to align Activity Plan to EPS projects
VCDR NE CLE CLV Voice Gateway Decom POR20 | NE | CLE | CLV | Voice Decom and Refortification | VCDR NE CLE CLV Voice Gateway Decom POR20 | Labor | No Equipment | 1 | 2020-04-10 | 2020-08-31 |  | Active | Log | Upd | SN-0598 | Schedule Change | Approved | 2020-05-20 16:49 | POR Update only CR for Voice Decom
VCDR NE CLE CLV Voice Gateway Decom POR20 | NE | CLE | CLV | Voice Decom and Refortification | VCDR NE CLE CLV Voice Gateway Decom POR20 | Labor | No Equipment | 1 | 2020-06-30 | 2020-08-31 |  | Active | Log | Upd | SN-0644 | True up | Approved | 2020-06-15 18:09 | 1 Variance of Capex labor 9k has been self solved and Opex labor of 3k self solved and reason for variance is mentioned in the comments section 2 New start dates FCED are updated in the POR
VCDR NE CLE CLV Voice Gateway Decom POR20 | NE | CLE | CLV | Voice Decom and Refortification | VCDR NE CLE CLV Voice Gateway Decom POR20 | Labor | No Equipment | 1 | 2020-06-30 | 2020-10-31 |  | Active | Log | Upd | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
VCDR NE CLE CLV Voice Gateway Decom POR20 | NE | CLE | CLV | Voice Decom and Refortification | VCDR NE CLE CLV Voice Gateway Decom POR20 | Labor | No Equipment |  |  |  |  | Active | Log | Del | SN-1052 | True up | Approved | 2020-11-12 18:01 | Overall there is a give back of around 30k in Capex contract as Data support work is not required and 13k give back in Opex IHL is mainly from less labor support required for Erisccon Sow
VCDR NE CLE CLV Voice Gateway Decom POR20 | NE | CLE | CLV | Voice Decom and Refortification | VCDR NE CLE CLV Voice Gateway Decom POR20 | Labor | No Equipment | 1 | 2020-06-30 | 2020-10-31 |  | Active | Log | Undel | SN-1080 | Schedule Change | Approved | 2020-11-20 13:46 | Voice Decom CR only for POR updates
VCDR SE NOR ALG Voice HDT Decom POR20 | SE | NOR | ALG | Voice Decom and Refortification | VCDR SE NOR ALG Voice HDT Decom POR20 | Labor | No Equipment | 1 |  | 2020-10-31 |  | Active | EP
VCDR SE NOR ALG Voice HDT Decom POR20 | SE | NOR | ALG | Voice Decom and Refortification | VCDR SE NOR ALG Voice HDT Decom POR20 | Labor | No Equipment | 1 |  | 2020-10-30 |  | Active | Log | New | SN-0423 | Schedule Change | Approved | 2020-04-10 14:17 | POR update only CR for Voice Decom to align Activity Plan to EPS projects
VCDR SE NOR ALG Voice HDT Decom POR20 | SE | NOR | ALG | Voice Decom and Refortification | VCDR SE NOR ALG Voice HDT Decom POR20 | Labor | No Equipment | 1 |  | 2020-10-31 |  | Active | Log | Upd | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
VCDR SE NOR NOE Voice HDT Decom POR20 | SE | NOR | NOE | Voice Decom and Refortification | VCDR SE NOR NOE Voice HDT Decom POR20 | Labor | No Equipment | 1 | 2020-03-31 | 2020-10-30 |  | Active | EP
VCDR SE NOR NOE Voice HDT Decom POR20 | SE | NOR | NOE | Voice Decom and Refortification | VCDR SE NOR NOE Voice HDT Decom POR20 | Labor | No Equipment | 1 |  | 2020-10-30 |  | Active | Log | New | SN-0423 | Schedule Change | Approved | 2020-04-10 14:17 | POR update only CR for Voice Decom to align Activity Plan to EPS projects
VCDR SE NOR NOE Voice HDT Decom POR20 | SE | NOR | NOE | Voice Decom and Refortification | VCDR SE NOR NOE Voice HDT Decom POR20 | Labor | No Equipment | 1 | 2020-03-31 | 2020-10-30 |  | Active | Log | Upd | SN-0644 | True up | Approved | 2020-06-15 18:09 | 1 Variance of Capex labor 9k has been self solved and Opex labor of 3k self solved and reason for variance is mentioned in the comments section 2 New start dates FCED are updated in the POR
VCDR CA SAN FED Voice HDT Decom POR20 | CA | SAN | FED | Voice Decom and Refortification | VCDR CA SAN FED Voice HDT Decom POR20 | Labor | No Equipment | 12 | 2020-04-21 | 2020-08-31 |  | Active | EP
VCDR CA SAN FED Voice HDT Decom POR20 | CA | SAN | FED | Voice Decom and Refortification | VCDR CA SAN FED Voice HDT Decom POR20 | Labor | No Equipment | 12 | 2020-04-21 | 2020-08-31 |  | Active | Log | New | SN-0496 | Schedule Change | Approved | 2020-04-29 16:34 | POR Update Only CR for Voice Decom
VCDR SE NOR STB Voice HDT Decom POR20 | SE | NOR | STB | Voice Decom and Refortification | VCDR SE NOR STB Voice HDT Decom POR20 | Labor | No Equipment | 6 | 2020-03-31 | 2020-10-31 |  | Active | EP
VCDR SE NOR STB Voice HDT Decom POR20 | SE | NOR | STB | Voice Decom and Refortification | VCDR SE NOR STB Voice HDT Decom POR20 | Labor | No Equipment | 6 | 2020-04-21 | 2020-08-31 |  | Active | Log | New | SN-0496 | Schedule Change | Approved | 2020-04-29 16:34 | POR Update Only CR for Voice Decom
VCDR SE NOR STB Voice HDT Decom POR20 | SE | NOR | STB | Voice Decom and Refortification | VCDR SE NOR STB Voice HDT Decom POR20 | Labor | No Equipment | 6 | 2020-03-31 | 2020-08-31 |  | Active | Log | Upd | SN-0644 | True up | Approved | 2020-06-15 18:09 | 1 Variance of Capex labor 9k has been self solved and Opex labor of 3k self solved and reason for variance is mentioned in the comments section 2 New start dates FCED are updated in the POR
VCDR SE NOR STB Voice HDT Decom POR20 | SE | NOR | STB | Voice Decom and Refortification | VCDR SE NOR STB Voice HDT Decom POR20 | Labor | No Equipment | 6 | 2020-03-31 | 2020-10-31 |  | Active | Log | Upd | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
VCDR CE SUN SVI Voice DMS Gateway Decom POR2 | CE | SUN | SVI | Voice Decom and Refortification | VCDR CE SUN SVI Voice DMS Gateway Decom POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
VCDR CE SUN SVI Voice DMS Gateway Decom POR2 | CE | SUN | SVI | Voice Decom and Refortification | VCDR CE SUN SVI Voice DMS Gateway Decom POR20 | Labor | No Equipment | 2 | 2020-04-30 | 2020-04-01 |  | Deleted | Log | New | SN-0529 | Schedule Change | Approved | 2020-05-07 10:54 | POR Update Only CR for Voice Decom
VCDR CE SUN SVI Voice DMS Gateway Decom POR2 | CE | SUN | SVI | Voice Decom and Refortification | VCDR CE SUN SVI Voice DMS Gateway Decom POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0598 | Schedule Change | Approved | 2020-05-20 16:49 | POR Update only CR for Voice Decom
VCDR CA SAN ELC Voice Cypress DMS Decom POR20 | CA | SAN | ELC | Voice Decom and Refortification | VCDR CA SAN ELC Voice Cypress DMS Decom POR20 | Labor | No Equipment | 1 | 2020-09-25 | 2021-02-28 |  | Active | EP
VCDR CA SAN ELC Voice Cypress DMS Decom POR20 | CA | SAN | ELC | Voice Decom and Refortification | VCDR CA SAN ELC Voice Cypress DMS Decom POR20 | Labor | No Equipment | 1 | 2020-05-07 | 2020-05-20 |  | Active | Log | Upd | SN-0552 | Schedule Change | Approved | 2020-05-13 11:45 | POR Update only CR for Voice Decom
VCDR CA SAN ELC Voice Cypress DMS Decom POR20 | CA | SAN | ELC | Voice Decom and Refortification | VCDR CA SAN ELC Voice Cypress DMS Decom POR20 | Labor | No Equipment | 1 | 2020-05-07 | 2021-02-28 |  | Active | Log | Upd | SN-0598 | Schedule Change | Approved | 2020-05-20 16:49 | POR Update only CR for Voice Decom
VCDR CA SAN ELC Voice Cypress DMS Decom POR20 | CA | SAN | ELC | Voice Decom and Refortification | VCDR CA SAN ELC Voice Cypress DMS Decom POR20 | Labor | No Equipment | 1 | 2020-09-25 | 2021-02-28 |  | Active | Log | Upd | SN-0644 | True up | Approved | 2020-06-15 18:09 | 1 Variance of Capex labor 9k has been self solved and Opex labor of 3k self solved and reason for variance is mentioned in the comments section 2 New start dates FCED are updated in the POR
VCDR SW ARZ CHD Voice DMS 2 Decom POR20 | SW | ARZ | CHD | Voice Decom and Refortification | VCDR SW ARZ CHD Voice DMS 2 Decom POR20 | Labor | No Equipment | 1 | 2020-09-30 | 2021-02-28 |  | Active | EP
VCDR SW ARZ CHD Voice DMS 2 Decom POR20 | SW | ARZ | CHD | Voice Decom and Refortification | VCDR SW ARZ CHD Voice DMS 2 Decom POR20 | Labor | No Equipment | 1 | 2020-05-07 | 2020-05-20 |  | Active | Log | Upd | SN-0552 | Schedule Change | Approved | 2020-05-13 11:45 | POR Update only CR for Voice Decom
VCDR SW ARZ CHD Voice DMS 2 Decom POR20 | SW | ARZ | CHD | Voice Decom and Refortification | VCDR SW ARZ CHD Voice DMS 2 Decom POR20 | Labor | No Equipment | 1 | 2020-05-07 | 2021-02-28 |  | Active | Log | Upd | SN-0598 | Schedule Change | Approved | 2020-05-20 16:49 | POR Update only CR for Voice Decom
VCDR SW ARZ CHD Voice DMS 2 Decom POR20 | SW | ARZ | CHD | Voice Decom and Refortification | VCDR SW ARZ CHD Voice DMS 2 Decom POR20 | Labor | No Equipment | 1 | 2020-09-30 | 2021-02-28 |  | Active | Log | Upd | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
VCDR SW ARZ MCD Voice HDT Decom POR20 | SW | ARZ | MCD | Voice Decom and Refortification | VCDR SW ARZ MCD Voice HDT Decom POR20 | Labor | No Equipment | 12 | 2020-08-04 | 2020-10-31 |  | Active | EP
VCDR SW ARZ MCD Voice HDT Decom POR20 | SW | ARZ | MCD | Voice Decom and Refortification | VCDR SW ARZ MCD Voice HDT Decom POR20 | Labor | No Equipment | 12 | 2020-05-07 | 2020-05-20 |  | Active | Log | New | SN-0552 | Schedule Change | Approved | 2020-05-13 11:45 | POR Update only CR for Voice Decom
VCDR SW ARZ MCD Voice HDT Decom POR20 | SW | ARZ | MCD | Voice Decom and Refortification | VCDR SW ARZ MCD Voice HDT Decom POR20 | Labor | No Equipment | 12 | 2020-05-07 | 2020-10-31 |  | Active | Log | Upd | SN-0598 | Schedule Change | Approved | 2020-05-20 16:49 | POR Update only CR for Voice Decom
VCDR SW ARZ MCD Voice HDT Decom POR20 | SW | ARZ | MCD | Voice Decom and Refortification | VCDR SW ARZ MCD Voice HDT Decom POR20 | Labor | No Equipment | 12 | 2020-08-04 | 2020-10-31 |  | Active | Log | Upd | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
VCDR SW ARZ MCD Voice HDT Decom POR20 | SW | ARZ | MCD | Voice Decom and Refortification | VCDR SW ARZ MCD Voice HDT Decom POR20 | Labor | No Equipment |  |  |  |  | Active | Log | Del | SN-1052 | True up | Approved | 2020-11-12 18:01 | Overall there is a give back of around 30k in Capex contract as Data support work is not required and 13k give back in Opex IHL is mainly from less labor support required for Erisccon Sow
VCDR SW ARZ MCD Voice HDT Decom POR20 | SW | ARZ | MCD | Voice Decom and Refortification | VCDR SW ARZ MCD Voice HDT Decom POR20 | Labor | No Equipment | 12 | 2020-08-04 | 2020-10-31 |  | Active | Log | Undel | SN-1080 | Schedule Change | Approved | 2020-11-20 13:46 | Voice Decom CR only for POR updates
VCDR SW ARZ PEO Voice HDT Decom POR20 | SW | ARZ | PEO | Voice Decom and Refortification | VCDR SW ARZ PEO Voice HDT Decom POR20 | Labor | No Equipment | 40 | 2020-08-04 | 2020-09-22 |  | Active | EP
VCDR SW ARZ PEO Voice HDT Decom POR20 | SW | ARZ | PEO | Voice Decom and Refortification | VCDR SW ARZ PEO Voice HDT Decom POR20 | Labor | No Equipment | 40 | 2020-05-07 | 2020-05-20 |  | Active | Log | New | SN-0552 | Schedule Change | Approved | 2020-05-13 11:45 | POR Update only CR for Voice Decom
VCDR SW ARZ PEO Voice HDT Decom POR20 | SW | ARZ | PEO | Voice Decom and Refortification | VCDR SW ARZ PEO Voice HDT Decom POR20 | Labor | No Equipment | 40 | 2020-05-07 | 2020-10-31 |  | Active | Log | Upd | SN-0598 | Schedule Change | Approved | 2020-05-20 16:49 | POR Update only CR for Voice Decom
VCDR SW ARZ PEO Voice HDT Decom POR20 | SW | ARZ | PEO | Voice Decom and Refortification | VCDR SW ARZ PEO Voice HDT Decom POR20 | Labor | No Equipment | 40 | 2020-08-04 | 2020-10-31 |  | Active | Log | Upd | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
VCDR SW ARZ PEO Voice HDT Decom POR20 | SW | ARZ | PEO | Voice Decom and Refortification | VCDR SW ARZ PEO Voice HDT Decom POR20 | Labor | No Equipment | 40 | 2020-08-04 | 2020-09-22 |  | Active | Log | Upd | SN-0940 | Schedule Change | Approved | 2020-09-25 12:46 | Overall Capex contract of 8k moved to Capex IHL in Corp and around 9k of Opex moved from Regions SE SW and VA to topside to support Ericsson transition Reasons for fund movement is mentioned in the comments section
VCDR SW ARZ TUC Voice HDT Decom POR20 | SW | ARZ | TUC | Voice Decom and Refortification | VCDR SW ARZ TUC Voice HDT Decom POR20 | Labor | No Equipment | 24 | 2020-05-07 | 2020-06-30 |  | Active | EP
VCDR SW ARZ TUC Voice HDT Decom POR20 | SW | ARZ | TUC | Voice Decom and Refortification | VCDR SW ARZ TUC Voice HDT Decom POR20 | Labor | No Equipment | 24 | 2020-05-07 | 2020-05-20 |  | Active | Log | New | SN-0552 | Schedule Change | Approved | 2020-05-13 11:45 | POR Update only CR for Voice Decom
VCDR SW ARZ TUC Voice HDT Decom POR20 | SW | ARZ | TUC | Voice Decom and Refortification | VCDR SW ARZ TUC Voice HDT Decom POR20 | Labor | No Equipment | 24 | 2020-05-07 | 2020-07-31 |  | Active | Log | Upd | SN-0598 | Schedule Change | Approved | 2020-05-20 16:49 | POR Update only CR for Voice Decom
VCDR SW ARZ TUC Voice HDT Decom POR20 | SW | ARZ | TUC | Voice Decom and Refortification | VCDR SW ARZ TUC Voice HDT Decom POR20 | Labor | No Equipment |  |  |  |  | Active | Log | Del | SN-0884 | Schedule Change | Approved | 2020-09-02 13:33 | Allocated the 500k Opex funds in Corp PPM 77906 for Automation resources expenses Details are provided in the additional sheet Break up of 500k Opex plan
VCDR SW ARZ TUC Voice HDT Decom POR20 | SW | ARZ | TUC | Voice Decom and Refortification | VCDR SW ARZ TUC Voice HDT Decom POR20 | Labor | No Equipment | 24 | 2020-05-07 | 2020-06-30 |  | Active | Log | Undel | SN-1080 | Schedule Change | Approved | 2020-11-20 13:46 | Voice Decom CR only for POR updates
VCDR CE SUN SVI Voice DMS Gateway Decom POR20 | CE | SUN | SVI | Voice Decom and Refortification | VCDR CE SUN SVI Voice DMS Gateway Decom POR20 | Labor | No Equipment | 2 | 2020-05-31 | 2020-09-30 |  | Active | EP
VCDR CE SUN SVI Voice DMS Gateway Decom POR20 | CE | SUN | SVI | Voice Decom and Refortification | VCDR CE SUN SVI Voice DMS Gateway Decom POR20 | Labor | No Equipment | 2 | 2020-04-07 | 2020-07-20 |  | Active | Log | Upd | SN-0552 | Schedule Change | Approved | 2020-05-13 11:45 | POR Update only CR for Voice Decom
VCDR CE SUN SVI Voice DMS Gateway Decom POR20 | CE | SUN | SVI | Voice Decom and Refortification | VCDR CE SUN SVI Voice DMS Gateway Decom POR20 | Labor | No Equipment | 2 | 2020-04-07 | 2020-09-30 |  | Active | Log | Upd | SN-0598 | Schedule Change | Approved | 2020-05-20 16:49 | POR Update only CR for Voice Decom
VCDR CE SUN SVI Voice DMS Gateway Decom POR20 | CE | SUN | SVI | Voice Decom and Refortification | VCDR CE SUN SVI Voice DMS Gateway Decom POR20 | Labor | No Equipment | 2 | 2020-05-31 | 2020-09-30 |  | Active | Log | Upd | SN-0644 | True up | Approved | 2020-06-15 18:09 | 1 Variance of Capex labor 9k has been self solved and Opex labor of 3k self solved and reason for variance is mentioned in the comments section 2 New start dates FCED are updated in the POR
Voice HDT Decom POR20 | VA | HRD | NKT | Voice Decom and Refortification | VCDR VA HRD NKT Voice HDT Decom POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-11-30 |  | Active | EP
Voice HDT Decom POR20 | VA | HRD | NKT | Voice Decom and Refortification | VCDR VA HRD NKT Voice HDT Decom POR20 | Labor | No Equipment | 2 | 2020-05-18 | 2020-11-30 |  | Active | Log | New | SN-0598 | Schedule Change | Approved | 2020-05-20 16:49 | POR Update only CR for Voice Decom
Voice HDT Decom POR20 | VA | HRD | NKT | Voice Decom and Refortification | VCDR VA HRD NKT Voice HDT Decom POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-11-30 |  | Active | Log | Upd | SN-0644 | True up | Approved | 2020-06-15 18:09 | 1 Variance of Capex labor 9k has been self solved and Opex labor of 3k self solved and reason for variance is mentioned in the comments section 2 New start dates FCED are updated in the POR
Voice Decom Ericson | COR | COR | ATL | Voice Decom and Refortification | VCDR COR COR ATL Ericsson SOW Backoffice Systems Decom POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-12-31 |  | Active | EP
Voice Decom Ericson | COR | COR | ATL | Voice Decom and Refortification | VCDR COR COR ATL Ericsson SOW Backoffice Systems Decom POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-12-31 |  | Active | Log | New | SN-0610 | Schedule Change | Approved | 2020-05-29 15:07 | POR update only CR for Voice Decom
Voice Decom Back Office | COR | COR | ATL | Voice Decom and Refortification | VCDR COR COR ATL Backoffice Systems Decom POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-12-31 |  | Active | EP
Voice Decom Back Office | COR | COR | ATL | Voice Decom and Refortification | VCDR COR COR ATL Backoffice Systems Decom POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-12-31 |  | Active | Log | New | SN-0610 | Schedule Change | Approved | 2020-05-29 15:07 | POR update only CR for Voice Decom
Voice SE NOR CLR Voice HDT Decom POR20 | SE | NOR | CLR | Voice Decom and Refortification | VCDR SE NOR CLR Voice HDT Decom POR20 | Labor | No Equipment | 1 | 2020-06-01 | 2021-03-31 |  | Active | EP
Voice SE NOR CLR Voice HDT Decom POR20 | SE | NOR | CLR | Voice Decom and Refortification | VCDR SE NOR CLR Voice HDT Decom POR20 | Labor | No Equipment | 1 | 2020-06-01 | 2020-11-30 |  | Active | Log | New | SN-0644 | True up | Approved | 2020-06-15 18:09 | 1 Variance of Capex labor 9k has been self solved and Opex labor of 3k self solved and reason for variance is mentioned in the comments section 2 New start dates FCED are updated in the POR
Voice SE NOR CLR Voice HDT Decom POR20 | SE | NOR | CLR | Voice Decom and Refortification | VCDR SE NOR CLR Voice HDT Decom POR20 | Labor | No Equipment | 1 | 2020-06-01 | 2021-03-31 |  | Active | Log | Upd | SN-1002 | True up | Approved | 2020-10-15 17:15 | Voice Decom Refortification CR for Sep True Ups
VCDR SW ARZ MSA Voice HDT Decom POR20 | SW | ARZ | MSA | Voice Decom and Refortification | VCDR SW ARZ MSA Voice HDT Decom POR20 | Labor | No Equipment | 1 |  | 2020-10-31 |  | Active | EP
VCDR SW ARZ MSA Voice HDT Decom POR20 | SW | ARZ | MSA | Voice Decom and Refortification | VCDR SW ARZ MSA Voice HDT Decom POR20 | Labor | No Equipment | 1 |  | 2020-09-30 |  | Active | Log | New | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
VCDR SW ARZ MSA Voice HDT Decom POR20 | SW | ARZ | MSA | Voice Decom and Refortification | VCDR SW ARZ MSA Voice HDT Decom POR20 | Labor | No Equipment | 1 |  | 2020-09-30 |  | Active | Log | Upd | SN-0884 | Schedule Change | Approved | 2020-09-02 13:33 | Allocated the 500k Opex funds in Corp PPM 77906 for Automation resources expenses Details are provided in the additional sheet Break up of 500k Opex plan
VCDR SW ARZ MSA Voice HDT Decom POR20 | SW | ARZ | MSA | Voice Decom and Refortification | VCDR SW ARZ MSA Voice HDT Decom POR20 | Labor | No Equipment | 1 |  | 2020-10-31 |  | Active | Log | Upd | SN-0913 | True up | Approved | 2020-09-17 15:33 | Overall there is 8600 overspent in Capex labor as the work was accelerated due to upcoming PTO of resources and 8900 underspent in Opex labor due to change in priority for FTPM Detailed creasons for variance are mentioned in the comments section
VCDR SW ARZ MSA Voice HDT Decom POR20 | SW | ARZ | MSA | Voice Decom and Refortification | VCDR SW ARZ MSA Voice HDT Decom POR20 | Labor | No Equipment |  |  |  |  | Active | Log | Del | SN-1028 | Schedule Change | Approved | 2020-10-23 14:37 | Moved the Capex Corp fund to SE SW Central and VA due to change in priorities to complete HDT shutdown activities
VCDR SW ARZ MSA Voice HDT Decom POR20 | SW | ARZ | MSA | Voice Decom and Refortification | VCDR SW ARZ MSA Voice HDT Decom POR20 | Labor | No Equipment | 1 |  | 2020-10-31 |  | Active | Log | Undel | SN-1080 | Schedule Change | Approved | 2020-11-20 13:46 | Voice Decom CR only for POR updates
VCDR SE NOR LPL Voice HDT Decom POR20 | SE | NOR | LPL | Voice Decom and Refortification | VCDR SE NOR LPL Voice HDT Decom POR20 | Labor | No Equipment | 1 |  | 2020-11-30 |  | Active | EP
VCDR SE NOR LPL Voice HDT Decom POR20 | SE | NOR | LPL | Voice Decom and Refortification | VCDR SE NOR LPL Voice HDT Decom POR20 | Labor | No Equipment | 1 |  | 2020-11-30 |  | Active | Log | New | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
VCDR SE NOR MCY Voice HDT Decom POR20 | SE | NOR | MCY | Voice Decom and Refortification | VCDR SE NOR MCY Voice HDT Decom POR20 | Labor | No Equipment | 1 |  | 2020-11-30 |  | Active | EP
VCDR SE NOR MCY Voice HDT Decom POR20 | SE | NOR | MCY | Voice Decom and Refortification | VCDR SE NOR MCY Voice HDT Decom POR20 | Labor | No Equipment | 1 |  | 2020-11-30 |  | Active | Log | New | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
VCDR CA SAN CHU Voice HDT Decom POR20 | CA | SAN | CHU | Voice Decom and Refortification | VCDR CA SAN CHU Voice HDT Decom POR20 | Labor | No Equipment | 22 | 2020-07-01 | 2021-06-30 |  | Active | EP
VCDR CA SAN CHU Voice HDT Decom POR20 | CA | SAN | CHU | Voice Decom and Refortification | VCDR CA SAN CHU Voice HDT Decom POR20 | Labor | No Equipment | 22 | 2020-07-01 | 2021-06-30 |  | Active | Log | New | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
VCDR CA SAN ESC Voice HDT Decom POR20 | CA | SAN | ESC | Voice Decom and Refortification | VCDR CA SAN ESC Voice HDT Decom POR20 | Labor | No Equipment | 3 | 2020-07-01 | 2021-06-30 |  | Active | EP
VCDR CA SAN ESC Voice HDT Decom POR20 | CA | SAN | ESC | Voice Decom and Refortification | VCDR CA SAN ESC Voice HDT Decom POR20 | Labor | No Equipment | 3 | 2020-07-01 | 2021-06-30 |  | Active | Log | New | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
VCDR CA SAN OCE Voice HDT Decom POR20 | CA | SAN | OCE | Voice Decom and Refortification | VCDR CA SAN OCE Voice HDT Decom POR20 | Labor | No Equipment | 12 | 2020-07-01 | 2021-12-01 |  | Active | EP
VCDR CA SAN OCE Voice HDT Decom POR20 | CA | SAN | OCE | Voice Decom and Refortification | VCDR CA SAN OCE Voice HDT Decom POR20 | Labor | No Equipment | 12 | 2020-07-01 | 2021-12-01 |  | Active | Log | New | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
VCDR CA SAN VST Voice HDT Decom POR20 | CA | SAN | VST | Voice Decom and Refortification | VCDR CA SAN VST Voice HDT Decom POR20 | Labor | No Equipment | 15 | 2020-07-01 | 2021-12-01 |  | Active | EP
VCDR CA SAN VST Voice HDT Decom POR20 | CA | SAN | VST | Voice Decom and Refortification | VCDR CA SAN VST Voice HDT Decom POR20 | Labor | No Equipment | 15 | 2020-07-01 | 2021-12-01 |  | Active | Log | New | SN-0697 | Schedule Change | Approved | 2020-07-10 10:10 | POR update only CR for Voice Decom
VCDR SE NOR DST Voice HDT Decom POR20 | SE | NOR | DST | Voice Decom and Refortification | VCDR SE NOR DST Voice HDT Decom POR20 | Labor | No Equipment | 1 | 2020-07-15 | 2020-12-31 |  | Active | EP
VCDR SE NOR DST Voice HDT Decom POR20 | SE | NOR | DST | Voice Decom and Refortification | VCDR SE NOR DST Voice HDT Decom POR20 | Labor | No Equipment | 1 | 2020-07-15 | 2020-12-31 |  | Active | Log | New | SN-0783 | Schedule Change | Approved | 2020-07-27 09:31 | POR only update CR for Voice Decom
VCDR CE OKC WEH Voice HDT Decom POR20 | CE | OKC | WEH | Voice Decom and Refortification | VCDR CE OKC WEH Voice HDT Decom POR20 | Labor | No Equipment | 4 | 2020-07-17 | 2020-12-31 |  | Active | EP
VCDR CE OKC WEH Voice HDT Decom POR20 | CE | OKC | WEH | Voice Decom and Refortification | VCDR CE OKC WEH Voice HDT Decom POR20 | Labor | No Equipment | 4 | 2020-07-17 | 2020-12-31 |  | Active | Log | New | SN-0783 | Schedule Change | Approved | 2020-07-27 09:31 | POR only update CR for Voice Decom
VCDR CE KAN WIC Voice HDT Decom POR20 | CE | KAN | WIC | Voice Decom and Refortification | VCDR CE KAN WIC Voice HDT Decom POR20 | Labor | No Equipment | 19 | 2020-07-15 | 2020-12-31 |  | Active | EP
VCDR CE KAN WIC Voice HDT Decom POR20 | CE | KAN | WIC | Voice Decom and Refortification | VCDR CE KAN WIC Voice HDT Decom POR20 | Labor | No Equipment | 19 | 2020-07-15 | 2020-12-31 |  | Active | Log | New | SN-0783 | Schedule Change | Approved | 2020-07-27 09:31 | POR only update CR for Voice Decom
VCDR NE RHD PTH Voice HDT Decom POR20 | NE | RHD | PTH | Voice Decom and Refortification | VCDR NE RHD PTH Voice HDT Decom POR20 | Labor | No Equipment | 1 | 2020-07-20 | 2020-12-31 |  | Active | EP
VCDR NE RHD PTH Voice HDT Decom POR20 | NE | RHD | PTH | Voice Decom and Refortification | VCDR NE RHD PTH Voice HDT Decom POR20 | Labor | No Equipment | 1 | 2020-07-20 | 2020-12-31 |  | Active | Log | New | SN-0783 | Schedule Change | Approved | 2020-07-27 09:31 | POR only update CR for Voice Decom
VCDR SW ARZ SSC Voice HDT Decom POR20 | SW | ARZ | SSC | Voice Decom and Refortification | VCDR SW ARZ SSC Voice HDT Decom POR20 | Labor | No Equipment | 2 | 2020-07-17 | 2021-06-30 |  | Active | EP
VCDR SW ARZ SSC Voice HDT Decom POR20 | SW | ARZ | SSC | Voice Decom and Refortification | VCDR SW ARZ SSC Voice HDT Decom POR20 | Labor | No Equipment | 2 | 2020-07-17 | 2021-06-30 |  | Active | Log | New | SN-0783 | Schedule Change | Approved | 2020-07-27 09:31 | POR only update CR for Voice Decom
Monitoring and Analytics - Network Analytics | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Proactive Alerting Alignment POR20 | Labor | Data collection for Analytics of Voice netwk | 1 | 2020-01-25 | 2020-02-15 |  | Active | EP
Monitoring and Analytics - Network Analytics | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Proactive Alerting Alignment POR20 | Labor | Data collection for Analytics of Voice netwk | 1 | 2020-01-25 | 2020-02-15 |  | Active | Log | Upd | SB-0013 | Schedule Change | Approved | 2020-01-30 10:25 | EPS project name changes
VEO Automation - Managed Router Support Tools | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Workflow and portfolio implementation Deployment POR20 | Labor | Tool dev for Managed Router Solution support | 2 | 2020-02-25 | 2020-03-15 |  | Active | EP
VEO Automation - Managed Router Support Tools | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Workflow and portfolio implementation Deployment POR20 | Labor | Tool dev for Managed Router Solution support | 2 | 2020-02-25 | 2020-03-15 |  | Active | Log | Upd | SB-0013 | Schedule Change | Approved | 2020-01-30 10:25 | EPS project name changes
VEO Automation - SD WAN Support Tools | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Workflow and portfolio implementation Deployment POR20 | Labor | Tool dev for SD WAN Solution support | 2 | 2020-01-25 | 2020-02-15 |  | Active | EP
VEO Automation - SD WAN Support Tools | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Workflow and portfolio implementation Deployment POR20 | Labor | Tool dev for SD WAN Solution support | 2 | 2020-01-25 | 2020-02-15 |  | Active | Log | Upd | SB-0013 | Schedule Change | Approved | 2020-01-30 10:25 | EPS project name changes
Calix Lifecycle B6 Centralized Support 1 | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Calix Life Cycle Deployment POR20 | Labor | Establishing centralized B6 Alarm monitoring |  |  |  |  | Deleted | EP
Calix Lifecycle B6 Centralized Support 1 | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Calix Life Cycle Deployment POR20 | Labor | Establishing centralized B6 Alarm monitoring | 1 | 2020-03-25 | 2020-05-15 |  | Deleted | Log | Upd | SB-0013 | Schedule Change | Approved | 2020-01-30 10:25 | EPS project name changes
Calix Lifecycle B6 Centralized Support 1 | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Calix Life Cycle Deployment POR20 | Labor | Establishing centralized B6 Alarm monitoring | 1 | 2020-03-25 | 2020-12-31 |  | Deleted | Log | Upd | SB-0163 | Schedule Change | Approved | 2020-06-30 11:09 | Deferred the Ansible SW upgrade project due to resource constraints and Re allocated the funds as per the updated Plan for Calix Lifecycle Project
Calix Lifecycle B6 Centralized Support 1 | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Calix Life Cycle Deployment POR20 | Labor | Establishing centralized B6 Alarm monitoring | 1 | 2020-03-25 | 2020-08-31 |  | Deleted | Log | Upd | SB-0199 | Cost Change | Approved | 2020-08-20 18:18 | Overall capex give back of 81k is due to Reforecast of Proactive alerting and Calix project and reasons for Budget reduction Plan Alignment is mentioned in the reasons column of the CR
Calix Lifecycle B6 Centralized Support 1 | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Calix Life Cycle Deployment POR20 | Labor | Establishing centralized B6 Alarm monitoring |  |  |  |  | Deleted | Log | Del | SB-0203 | Schedule Change | Approved | 2020-08-21 11:37 | Deleted Calix Project as no funds allocated till end of the year 2020
Calix Lifecycle B6 Centralized Support 2 | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Calix Life Cycle Deployment POR20 | Labor | Establishing centralized B6 Alarm monitoring |  |  |  |  | Deleted | EP
Calix Lifecycle B6 Centralized Support 2 | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Calix Life Cycle Deployment POR20 | Labor | Establishing centralized B6 Alarm monitoring | 1 | 2020-03-25 | 2020-05-15 |  | Deleted | Log | Upd | SB-0013 | Schedule Change | Approved | 2020-01-30 10:25 | EPS project name changes
Calix Lifecycle B6 Centralized Support 2 | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Calix Life Cycle Deployment POR20 | Labor | Establishing centralized B6 Alarm monitoring |  |  |  |  | Deleted | Log | Del | SB-0128 | COVID-19 Related | Approved | 2020-05-13 14:51 | Deferred in Calix Lifecycle Capex 118850 Opex 3247 as per CR SB 0116
Monitoring and Analytics - Proactive Alerting | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Proactive Alerting Alignment POR20 | Labor | Adding Proactive Alerting. | 1 | 2020-03-25 | 2021-01-30 |  | Active | EP
Monitoring and Analytics - Proactive Alerting | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Proactive Alerting Alignment POR20 | Labor | Adding Proactive Alerting. | 1 | 2020-03-25 | 2020-05-15 |  | Active | Log | Upd | SB-0013 | Schedule Change | Approved | 2020-01-30 10:25 | EPS project name changes
Monitoring and Analytics - Proactive Alerting | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Proactive Alerting Alignment POR20 | Labor | Adding Proactive Alerting. | 1 | 2020-03-25 | 2021-01-30 |  | Active | Log | Upd | SB-0128 | COVID-19 Related | Approved | 2020-05-13 14:51 | Deferred in Calix Lifecycle Capex 118850 Opex 3247 as per CR SB 0116
VEO Automation - Jira Workflow | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Workflow and portfolio implementation Deployment POR20 | Labor | Dev of Jira workflow solution for VEO Projects | 1 | 2020-03-25 | 2020-04-15 |  | Active | EP
VEO Automation - Jira Workflow | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Workflow and portfolio implementation Deployment POR20 | Labor | Dev of Jira workflow solution for VEO Projects | 1 | 2020-03-25 | 2020-04-15 |  | Active | Log | Upd | SB-0013 | Schedule Change | Approved | 2020-01-30 10:25 | EPS project name changes
Ansible SW Upgrade | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Ansible upgrade Deployment POR20 | Labor | SW upgrade for VEO Device Script Mgmt system |  |  |  |  | Deleted | EP
Ansible SW Upgrade | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Ansible upgrade Deployment POR20 | Labor | SW upgrade for VEO Device Script Mgmt system | 2 | 2020-07-10 | 2020-08-15 |  | Deleted | Log | Upd | SB-0013 | Schedule Change | Approved | 2020-01-30 10:25 | EPS project name changes
Ansible SW Upgrade | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Ansible upgrade Deployment POR20 | Labor | SW upgrade for VEO Device Script Mgmt system |  |  |  |  | Deleted | Log | Del | SB-0163 | Schedule Change | Approved | 2020-06-30 11:09 | Deferred the Ansible SW upgrade project due to resource constraints and Re allocated the funds as per the updated Plan for Calix Lifecycle Project
Empirix Lifecyle - Cloud Portal Server | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Chassis | Deploy Cloud Portal Server with new UI. |  |  |  |  | Deleted | EP
Empirix Lifecyle - Cloud Portal Server | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Chassis | Deploy Cloud Portal Server with new UI. | 1 | 2020-06-25 | 2020-08-15 | 2020-09-15 | Deleted | Log | Upd | SB-0013 | Schedule Change | Approved | 2020-01-30 10:25 | EPS project name changes
Empirix Lifecyle - Cloud Portal Server | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Chassis | Deploy Cloud Portal Server with new UI. | 1 | 2020-01-02 | 2020-05-29 | 2020-12-05 | Deleted | Log | Upd | SB-0045 | Schedule Change | Approved | 2020-01-31 14:57 | Empirix material early delivery and POR update
Empirix Lifecyle - Cloud Portal Server | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Chassis | Deploy Cloud Portal Server with new UI. |  |  |  |  | Deleted | Log | Del | SB-0128 | COVID-19 Related | Approved | 2020-05-13 14:51 | Deferred in Calix Lifecycle Capex 118850 Opex 3247 as per CR SB 0116
Empirix Lifecyle - Monitoring Probes | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Chassis | Install probes to collect ntwk data from taps |  |  |  |  | Deleted | EP
Empirix Lifecyle - Monitoring Probes | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Chassis | Install probes to collect ntwk data from taps | 3 | 2020-06-25 | 2020-08-15 | 2020-09-15 | Deleted | Log | Upd | SB-0013 | Schedule Change | Approved | 2020-01-30 10:25 | EPS project name changes
Empirix Lifecyle - Monitoring Probes | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Chassis | Install probes to collect ntwk data from taps |  |  |  |  | Deleted | Log | Del | SB-0128 | COVID-19 Related | Approved | 2020-05-13 14:51 | Deferred in Calix Lifecycle Capex 118850 Opex 3247 as per CR SB 0116
Empirix Lifecyle - SBC Core HAROS | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Standard | Replace SBC Core East and West HCOSs with HAROS |  |  |  |  | Deleted | EP
Empirix Lifecyle - SBC Core HAROS | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Standard | Replace SBC Core East and West HCOSs with HAROS | 2 | 2020-06-25 | 2020-08-15 | 2020-09-15 | Deleted | Log | Upd | SB-0013 | Schedule Change | Approved | 2020-01-30 10:25 | EPS project name changes
Empirix Lifecyle - SBC Core HAROS | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Standard | Replace SBC Core East and West HCOSs with HAROS |  |  |  |  | Deleted | Log | Del | SB-0128 | COVID-19 Related | Approved | 2020-05-13 14:51 | Deferred in Calix Lifecycle Capex 118850 Opex 3247 as per CR SB 0116
Monitoring and Analytics - VEO Process Analytics | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Proactive Alerting Alignment POR20 | Labor | Data collection for Analytics of VEO Dev, trblsht | 1 | 2020-06-25 | 2020-07-15 |  | Active | EP
Monitoring and Analytics - VEO Process Analytics | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Proactive Alerting Alignment POR20 | Labor | Data collection for Analytics of VEO Dev, trblsht | 1 | 2020-06-25 | 2020-07-15 |  | Active | Log | Upd | SB-0013 | Schedule Change | Approved | 2020-01-30 10:25 | EPS project name changes
VEO Automation - Jira Portfolio Implementation | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Workflow and portfolio implementation Deployment POR20 | Labor | Dev of Jira Proj Mgmt soln for VEO projects | 1 | 2020-06-25 | 2020-07-15 |  | Active | EP
VEO Automation - Jira Portfolio Implementation | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Workflow and portfolio implementation Deployment POR20 | Labor | Dev of Jira Proj Mgmt soln for VEO projects | 1 | 2020-06-25 | 2020-07-15 |  | Active | Log | Upd | SB-0013 | Schedule Change | Approved | 2020-01-30 10:25 | EPS project name changes
Bus Req Proj Concept Doc Empirix SoW | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other | 1 | 2020-01-02 | 2020-05-25 |  | Active | EP
Bus Req Proj Concept Doc Empirix SoW | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other | 1 | 2020-01-02 | 2020-03-16 |  | Active | Log | Undel | SB-0045 | Schedule Change | Approved | 2020-01-31 14:57 | Empirix material early delivery and POR update
Bus Req Proj Concept Doc Empirix SoW | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other | 1 | 2020-01-02 | 2020-05-25 |  | Active | Log | Upd | SB-0140 | Schedule Change | Approved | 2020-05-28 11:40 | 1 Movement of Capex labor 30k from May to Jun as there was a delay in Empirix Diagnostix cloud build and more details are in comments section
Upgrade lab E-XMS systems to 5.7.5 | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other | 1 | 2020-03-17 | 2020-05-25 |  | Active | EP
Upgrade lab E-XMS systems to 5.7.5 | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other | 1 | 2020-03-17 | 2020-04-15 |  | Active | Log | Undel | SB-0045 | Schedule Change | Approved | 2020-01-31 14:57 | Empirix material early delivery and POR update
Upgrade lab E-XMS systems to 5.7.5 | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other | 1 | 2020-03-17 | 2020-05-25 |  | Active | Log | Upd | SB-0140 | Schedule Change | Approved | 2020-05-28 11:40 | 1 Movement of Capex labor 30k from May to Jun as there was a delay in Empirix Diagnostix cloud build and more details are in comments section
Add HDFS system to Lab Env | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other | 1 | 2020-06-10 | 2020-06-30 |  | Active | EP
Add HDFS system to Lab Env | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other | 1 | 2020-04-16 | 2020-05-01 |  | Active | Log | Undel | SB-0045 | Schedule Change | Approved | 2020-01-31 14:57 | Empirix material early delivery and POR update
Add HDFS system to Lab Env | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other | 1 | 2020-06-10 | 2020-06-30 |  | Active | Log | Upd | SB-0140 | Schedule Change | Approved | 2020-05-28 11:40 | 1 Movement of Capex labor 30k from May to Jun as there was a delay in Empirix Diagnostix cloud build and more details are in comments section
Augment ODI Environment | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other | 1 | 2020-05-04 | 2020-05-29 |  | Active | EP
Augment ODI Environment | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other | 1 | 2020-05-04 | 2020-05-29 |  | Active | Log | Undel | SB-0045 | Schedule Change | Approved | 2020-01-31 14:57 | Empirix material early delivery and POR update
Upgrade Prod E-XMS Systems to 5.7.5 | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other | 1 | 2020-07-10 | 2020-08-31 |  | Active | EP
Upgrade Prod E-XMS Systems to 5.7.5 | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other | 1 | 2020-05-04 | 2020-05-29 |  | Active | Log | Undel | SB-0045 | Schedule Change | Approved | 2020-01-31 14:57 | Empirix material early delivery and POR update
Upgrade Prod E-XMS Systems to 5.7.5 | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other | 1 | 2020-07-10 | 2020-08-31 |  | Active | Log | Upd | SB-0140 | Schedule Change | Approved | 2020-05-28 11:40 | 1 Movement of Capex labor 30k from May to Jun as there was a delay in Empirix Diagnostix cloud build and more details are in comments section
Functional testing, Upgrade lab to D-Cloud in Lab | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other | 1 | 2020-06-01 | 2020-06-30 |  | Active | EP
Functional testing, Upgrade lab to D-Cloud in Lab | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other | 1 | 2020-06-01 | 2020-06-30 |  | Active | Log | Undel | SB-0045 | Schedule Change | Approved | 2020-01-31 14:57 | Empirix material early delivery and POR update
Add HDFS Cluster in Prod | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other |  |  |  |  | Deleted | EP
Add HDFS Cluster in Prod | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other | 1 | 2020-06-01 | 2020-06-30 |  | Deleted | Log | Undel | SB-0045 | Schedule Change | Approved | 2020-01-31 14:57 | Empirix material early delivery and POR update
Add HDFS Cluster in Prod | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other |  |  |  |  | Deleted | Log | Del | SB-0128 | COVID-19 Related | Approved | 2020-05-13 14:51 | Deferred in Calix Lifecycle Capex 118850 Opex 3247 as per CR SB 0116
Augment Duke Prod Voice ODI Env | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other |  |  |  |  | Deleted | EP
Augment Duke Prod Voice ODI Env | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other | 1 | 2020-07-01 | 2020-07-31 |  | Deleted | Log | Undel | SB-0045 | Schedule Change | Approved | 2020-01-31 14:57 | Empirix material early delivery and POR update
Augment Duke Prod Voice ODI Env | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other |  |  |  |  | Deleted | Log | Del | SB-0140 | Schedule Change | Approved | 2020-05-28 11:40 | 1 Movement of Capex labor 30k from May to Jun as there was a delay in Empirix Diagnostix cloud build and more details are in comments section
Install and Configure D-Cloud VMs in Prod | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other |  |  |  |  | Deleted | EP
Install and Configure D-Cloud VMs in Prod | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other | 1 | 2020-08-01 | 2020-08-31 |  | Deleted | Log | Undel | SB-0045 | Schedule Change | Approved | 2020-01-31 14:57 | Empirix material early delivery and POR update
Install and Configure D-Cloud VMs in Prod | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other |  |  |  |  | Deleted | Log | Del | SB-0128 | COVID-19 Related | Approved | 2020-05-13 14:51 | Deferred in Calix Lifecycle Capex 118850 Opex 3247 as per CR SB 0116
Re-configure SBC and Harmony probes in Prod | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other |  |  |  |  | Deleted | EP
Re-configure SBC and Harmony probes in Prod | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other | 1 | 2020-09-01 | 2020-09-30 |  | Deleted | Log | Undel | SB-0045 | Schedule Change | Approved | 2020-01-31 14:57 | Empirix material early delivery and POR update
Re-configure SBC and Harmony probes in Prod | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other |  |  |  |  | Deleted | Log | Del | SB-0128 | COVID-19 Related | Approved | 2020-05-13 14:51 | Deferred in Calix Lifecycle Capex 118850 Opex 3247 as per CR SB 0116
Functional testing in Prod | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other |  |  |  |  | Deleted | EP
Functional testing in Prod | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other | 1 | 2020-10-01 | 2020-10-30 |  | Deleted | Log | Undel | SB-0045 | Schedule Change | Approved | 2020-01-31 14:57 | Empirix material early delivery and POR update
Functional testing in Prod | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other |  |  |  |  | Deleted | Log | Del | SB-0128 | COVID-19 Related | Approved | 2020-05-13 14:51 | Deferred in Calix Lifecycle Capex 118850 Opex 3247 as per CR SB 0116
Training internal users | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other |  |  |  |  | Deleted | EP
Training internal users | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other | 1 | 2020-11-02 | 2020-11-20 |  | Deleted | Log | Undel | SB-0045 | Schedule Change | Approved | 2020-01-31 14:57 | Empirix material early delivery and POR update
Training internal users | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other |  |  |  |  | Deleted | Log | Del | SB-0128 | COVID-19 Related | Approved | 2020-05-13 14:51 | Deferred in Calix Lifecycle Capex 118850 Opex 3247 as per CR SB 0116
Prod Deploy and Project closeout | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other |  |  |  |  | Deleted | EP
Prod Deploy and Project closeout | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other | 1 | 2020-11-02 | 2020-12-30 |  | Deleted | Log | Undel | SB-0045 | Schedule Change | Approved | 2020-01-31 14:57 | Empirix material early delivery and POR update
Prod Deploy and Project closeout | COR | COR | ATL | Voice Monitoring and Analytics | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other |  |  |  |  | Deleted | Log | Del | SB-0128 | COVID-19 Related | Approved | 2020-05-13 14:51 | Deferred in Calix Lifecycle Capex 118850 Opex 3247 as per CR SB 0116
Test Automation - Voice Test Automation | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL Test Automation Alignment POR20 | Labor | Automate testing of Voice services. |  |  |  |  | Deleted | EP
Test Automation - Voice Test Automation | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL Test Automation Alignment POR20 | Labor | Automate testing of Voice services. | 1 | 2020-01-25 | 2020-02-15 |  | Deleted | Log | Upd | SB-0013 | Schedule Change | Approved | 2020-01-30 10:25 | EPS project name changes
Test Automation - Voice Test Automation | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL Test Automation Alignment POR20 | Labor | Automate testing of Voice services. |  |  |  |  | Deleted | Log | Del | SB-0129 | COVID-19 Related | Approved | 2020-05-13 14:51 | POR Update only CR for Voice Network Upgrades
BroadSoft R23 Upgrade 1 | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL BroadSoft LifeCycle Deployment POR20 | Labor | Upgrade BroadSoft SW to Release 23 | 1 | 2020-03-06 | 2021-03-31 |  | Active | EP
BroadSoft R23 Upgrade 1 | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL BroadSoft LifeCycle Deployment POR20 | Labor | Upgrade BroadSoft SW to Release 23 | 1 | 2020-03-06 | 2021-03-31 |  | Active | Log | Upd | SB-0193 | True up | Approved | 2020-08-14 15:16 | Major favorable variance in capex labor of BroadSoft and Delivery expansion Project Reasons for all Projects are mentioned in the comments section of the CR
BroadSoft R23 Upgrade 2 | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL BroadSoft LifeCycle Deployment POR20 | Labor | Upgrade BroadSoft SW to Release 23 | 1 | 2020-03-06 | 2020-11-15 |  | Deleted | EP
Delivery Expansion - Delivery Service Expansion | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL ODI and SD WAN Infra Env Alignment POR20 | Labor | Build additional Dev environments. | 1 | 2020-07-10 | 2020-12-31 |  | Active | EP
Delivery Expansion - Delivery Service Expansion | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL ODI and SD WAN Infra Env Alignment POR20 | Labor | Build additional Dev environments. | 1 | 2020-01-25 | 2020-04-15 |  | Active | Log | Upd | SB-0013 | Schedule Change | Approved | 2020-01-30 10:25 | EPS project name changes
Delivery Expansion - Delivery Service Expansion | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL ODI and SD WAN Infra Env Alignment POR20 | Labor | Build additional Dev environments. | 1 | 2020-07-10 | 2020-08-31 |  | Active | Log | Upd | SB-0139 | Schedule Change | Approved | 2020-05-28 11:40 | 1 Movement of Capex material 90k from May to July is due to Vendor delay in delivery and movement of Capex material 85k is due to delay in ODI build and more details are in the comments section 2 Reversal charges of Capex labor 65k moved to Jul and Aug
Delivery Expansion - Delivery Service Expansion | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL ODI and SD WAN Infra Env Alignment POR20 | Labor | Build additional Dev environments. | 1 | 2020-07-10 | 2020-12-31 |  | Active | Log | Upd | SB-0162 | Schedule Change | Approved | 2020-06-30 11:08 | Capex ask of 138k is due to additional VM requirement in Delivery Expansion and also Security issues in vendor product used by CPE Upgrades VEO Security Enhancements and Adtran CPE Projects More Details are mentioned in the Comments section
Test Automation - BroadSoft Test Automation | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL Test Automation Alignment POR20 | Labor | Automate testing of BroadSoft solution. |  |  |  |  | Deleted | EP
Test Automation - BroadSoft Test Automation | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL Test Automation Alignment POR20 | Labor | Automate testing of BroadSoft solution. | 1 | 2020-06-25 | 2020-07-15 |  | Deleted | Log | Upd | SB-0013 | Schedule Change | Approved | 2020-01-30 10:25 | EPS project name changes
Test Automation - BroadSoft Test Automation | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL Test Automation Alignment POR20 | Labor | Automate testing of BroadSoft solution. |  |  |  |  | Deleted | Log | Del | SB-0129 | COVID-19 Related | Approved | 2020-05-13 14:51 | POR Update only CR for Voice Network Upgrades
Test Automation - Metaswitch Test Automation | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL Test Automation Alignment POR20 | Labor | Automate testing of Metaswitch SBC solution. |  |  |  |  | Deleted | EP
Test Automation - Metaswitch Test Automation | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL Test Automation Alignment POR20 | Labor | Automate testing of Metaswitch SBC solution. | 1 | 2020-04-25 | 2020-05-15 |  | Deleted | Log | Upd | SB-0013 | Schedule Change | Approved | 2020-01-30 10:25 | EPS project name changes
Test Automation - Metaswitch Test Automation | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL Test Automation Alignment POR20 | Labor | Automate testing of Metaswitch SBC solution. |  |  |  |  | Deleted | Log | Del | SB-0129 | COVID-19 Related | Approved | 2020-05-13 14:51 | POR Update only CR for Voice Network Upgrades
Delivery Expansion - SD WAN | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL ODI and SD WAN Infra Env Alignment POR20 | Labor | Build Dev environment for SD WAN services |  |  |  |  | Deleted | EP
Delivery Expansion - SD WAN | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL ODI and SD WAN Infra Env Alignment POR20 | Labor | Build Dev environment for SD WAN services | 1 | 2020-05-25 | 2020-07-15 |  | Deleted | Log | Upd | SB-0013 | Schedule Change | Approved | 2020-01-30 10:25 | EPS project name changes
Delivery Expansion - SD WAN | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL ODI and SD WAN Infra Env Alignment POR20 | Labor | Build Dev environment for SD WAN services |  |  |  |  | Deleted | Log | Del | SB-0139 | Schedule Change | Approved | 2020-05-28 11:40 | 1 Movement of Capex material 90k from May to July is due to Vendor delay in delivery and movement of Capex material 85k is due to delay in ODI build and more details are in the comments section 2 Reversal charges of Capex labor 65k moved to Jul and Aug
Metaswitch SBC ODI Virtualization 1 | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL Metaswitch Lifecycle Deployment POR20 | Labor | Migration of Metaswitch SBC to ODI virt platform |  |  |  |  | Deleted | EP
Metaswitch SBC ODI Virtualization 1 | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL Metaswitch Lifecycle Deployment POR20 | Labor | Migration of Metaswitch SBC to ODI virt platform | 1 | 2020-06-25 | 2020-09-15 | 2020-10-15 | Deleted | Log | Upd | SB-0013 | Schedule Change | Approved | 2020-01-30 10:25 | EPS project name changes
Metaswitch SBC ODI Virtualization 1 | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL Metaswitch Lifecycle Deployment POR20 | Labor | Migration of Metaswitch SBC to ODI virt platform |  |  |  |  | Deleted | Log | Del | SB-0047 | Scope Change | Approved | 2020-01-31 14:56 | Need to procure DSP cards for processing transcoding on Metaswitch servers Self solving using remaining funds for SBC ODI Virtualization (Some of these funds were used for PRI automation)
Metaswitch SBC ODI Virtualization 2 | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL Metaswitch Lifecycle Deployment POR20 | Labor | Transition Metaswitch SBC to ODI virt platform. |  |  |  |  | Deleted | EP
Metaswitch SBC ODI Virtualization 2 | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL Metaswitch Lifecycle Deployment POR20 | Labor | Transition Metaswitch SBC to ODI virt platform. | 1 | 2020-06-25 | 2020-09-15 | 2020-10-15 | Deleted | Log | Upd | SB-0013 | Schedule Change | Approved | 2020-01-30 10:25 | EPS project name changes
Metaswitch SBC ODI Virtualization 2 | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL Metaswitch Lifecycle Deployment POR20 | Labor | Transition Metaswitch SBC to ODI virt platform. |  |  |  |  | Deleted | Log | Del | SB-0047 | Scope Change | Approved | 2020-01-31 14:56 | Need to procure DSP cards for processing transcoding on Metaswitch servers Self solving using remaining funds for SBC ODI Virtualization (Some of these funds were used for PRI automation)
UC App SW Upgrade 1 | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL UC App Upgrade Deployment POR20 | Labor | Certify and deploy updated UC App SW. | 4 | 2020-09-08 | 2020-12-15 |  | Active | EP
UC App SW Upgrade 1 | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL UC App Upgrade Deployment POR20 | Labor | Certify and deploy updated UC App SW. | 4 | 2020-09-08 | 2020-12-15 |  | Active | Log | Upd | SB-0013 | Schedule Change | Approved | 2020-01-30 10:25 | EPS project name changes
UC App SW Upgrade 2 | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL UC App Upgrade Deployment POR20 | Labor | Certify and deploy updated UC App SW. |  |  |  |  | Deleted | EP
UC App SW Upgrade 2 | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL UC App Upgrade Deployment POR20 | Labor | Certify and deploy updated UC App SW. | 4 | 2020-09-08 | 2020-12-15 |  | Deleted | Log | Upd | SB-0013 | Schedule Change | Approved | 2020-01-30 10:25 | EPS project name changes
UC App SW Upgrade 2 | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL UC App Upgrade Deployment POR20 | Labor | Certify and deploy updated UC App SW. |  |  |  |  | Deleted | Log | Del | SB-0162 | Schedule Change | Approved | 2020-06-30 11:08 | Capex ask of 138k is due to additional VM requirement in Delivery Expansion and also Security issues in vendor product used by CPE Upgrades VEO Security Enhancements and Adtran CPE Projects More Details are mentioned in the Comments section
Market Segmentation | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL Metaswitch Lifecycle Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-02 | 2020-02-14 | 2020-02-14 | Active | EP
Market Segmentation | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL Metaswitch Lifecycle Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-02 | 2020-02-14 | 2020-02-14 | Active | Log | New | SB-0047 | Scope Change | Approved | 2020-01-31 14:56 | Need to procure DSP cards for processing transcoding on Metaswitch servers Self solving using remaining funds for SBC ODI Virtualization (Some of these funds were used for PRI automation)
Metaswitch 4.3.4 Upgrade CB | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL Metaswitch Lifecycle Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-05 | 2020-10-31 | 2020-04-15 | Active | EP
Metaswitch 4.3.4 Upgrade CB | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL Metaswitch Lifecycle Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-05 | 2020-04-15 | 2020-04-15 | Active | Log | New | SB-0047 | Scope Change | Approved | 2020-01-31 14:56 | Need to procure DSP cards for processing transcoding on Metaswitch servers Self solving using remaining funds for SBC ODI Virtualization (Some of these funds were used for PRI automation)
Metaswitch 4.3.4 Upgrade CB | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL Metaswitch Lifecycle Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-05 | 2020-10-31 | 2020-04-15 | Active | Log | Upd | SB-0162 | Schedule Change | Approved | 2020-06-30 11:08 | Capex ask of 138k is due to additional VM requirement in Delivery Expansion and also Security issues in vendor product used by CPE Upgrades VEO Security Enhancements and Adtran CPE Projects More Details are mentioned in the Comments section
DTMF and Audio issues fix | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL Metaswitch Lifecycle Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-03-10 | 2020-03-10 | Active | EP
DTMF and Audio issues fix | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL Metaswitch Lifecycle Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-03-10 | 2020-03-10 | Active | Log | New | SB-0047 | Scope Change | Approved | 2020-01-31 14:56 | Need to procure DSP cards for processing transcoding on Metaswitch servers Self solving using remaining funds for SBC ODI Virtualization (Some of these funds were used for PRI automation)
SBC resiliency - failover and service restoration | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL Metaswitch Lifecycle Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-02 | 2020-05-29 | 2020-05-29 | Active | EP
SBC resiliency - failover and service restoration | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL Metaswitch Lifecycle Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-02 | 2020-05-29 | 2020-05-29 | Active | Log | New | SB-0047 | Scope Change | Approved | 2020-01-31 14:56 | Need to procure DSP cards for processing transcoding on Metaswitch servers Self solving using remaining funds for SBC ODI Virtualization (Some of these funds were used for PRI automation)
Metaswitch DSP Cards | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL Metaswitch Lifecycle Deployment POR20 | Labor | Other | 1 | 2020-05-01 | 2020-10-31 | 2020-07-26 | Active | EP
Metaswitch DSP Cards | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL Metaswitch Lifecycle Deployment POR20 | Labor | Other | 1 | 2020-05-01 | 2020-07-26 | 2020-07-26 | Active | Log | New | SB-0047 | Scope Change | Approved | 2020-01-31 14:56 | Need to procure DSP cards for processing transcoding on Metaswitch servers Self solving using remaining funds for SBC ODI Virtualization (Some of these funds were used for PRI automation)
Metaswitch DSP Cards | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL Metaswitch Lifecycle Deployment POR20 | Labor | Other | 1 | 2020-05-01 | 2020-10-31 | 2020-07-26 | Active | Log | Upd | SB-0162 | Schedule Change | Approved | 2020-06-30 11:08 | Capex ask of 138k is due to additional VM requirement in Delivery Expansion and also Security issues in vendor product used by CPE Upgrades VEO Security Enhancements and Adtran CPE Projects More Details are mentioned in the Comments section
Metaswitch 4.6 Upgrade CB | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL Metaswitch Lifecycle Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-08-15 | 2020-12-15 | 2020-12-15 | Active | EP
Metaswitch 4.6 Upgrade CB | COR | COR | ATL | Voice Network Upgrades | VNU CO -CO ATL Metaswitch Lifecycle Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-08-15 | 2020-12-15 | 2020-12-15 | Active | Log | New | SB-0047 | Scope Change | Approved | 2020-01-31 14:56 | Need to procure DSP cards for processing transcoding on Metaswitch servers Self solving using remaining funds for SBC ODI Virtualization (Some of these funds were used for PRI automation)
Static IP PBX Migrations to Metaswitch | COR | COR | ATL | Voice Obsolescence | VOBS CO -CO ATL SBC Metaswitch Migration Deployment POR20 | Labor | Continue ACME SBC to Metaswitch migration | 30 | 2020-01-10 | 2020-12-31 |  | Active | EP
Static IP PBX Migrations to Metaswitch | COR | COR | ATL | Voice Obsolescence | VOBS CO -CO ATL SBC Metaswitch Migration Deployment POR20 | Labor | Continue ACME SBC to Metaswitch migration | 30 | 2020-01-10 | 2020-06-15 |  | Active | Log | Upd | SB-0013 | Schedule Change | Approved | 2020-01-30 10:25 | EPS project name changes
Static IP PBX Migrations to Metaswitch | COR | COR | ATL | Voice Obsolescence | VOBS CO -CO ATL SBC Metaswitch Migration Deployment POR20 | Labor | Continue ACME SBC to Metaswitch migration | 30 | 2020-01-10 | 2020-12-31 |  | Active | Log | Upd | SB-0164 | Schedule Change | Approved | 2020-06-30 11:09 | Capex Labor return of 29k and Opex labor return of 45k in majorly due to SBC migration project and detail comments are mentioned in comments section Modified CR to give back 91k to Self solve the Unfavorable funds of Voice Network Upgrades as discussed in
Sonus LD Migration | COR | COR | ATL | Voice Obsolescence | VOBS CO -CO ATL Sonus routing Deployment POR20 | Labor | Migrate Long Distance routing off of Sonus SBC | 1 | 2020-01-10 | 2020-12-31 | 2020-09-15 | Active | EP
Sonus LD Migration | COR | COR | ATL | Voice Obsolescence | VOBS CO -CO ATL Sonus routing Deployment POR20 | Labor | Migrate Long Distance routing off of Sonus SBC | 1 | 2020-01-10 | 2020-09-15 | 2020-09-15 | Active | Log | Upd | SB-0013 | Schedule Change | Approved | 2020-01-30 10:25 | EPS project name changes
Sonus LD Migration | COR | COR | ATL | Voice Obsolescence | VOBS CO -CO ATL Sonus routing Deployment POR20 | Labor | Migrate Long Distance routing off of Sonus SBC | 1 | 2020-01-10 | 2020-12-31 | 2020-09-15 | Active | Log | Upd | SB-0164 | Schedule Change | Approved | 2020-06-30 11:09 | Capex Labor return of 29k and Opex labor return of 45k in majorly due to SBC migration project and detail comments are mentioned in comments section Modified CR to give back 91k to Self solve the Unfavorable funds of Voice Network Upgrades as discussed in
Niagara 4248 replacement 1 | COR | COR | ATL | Voice Obsolescence | VOBS CO -CO ATL Niagara 4248 replacement Deployment POR20 | Labor | Certify a replacement for EOL Niagara 4248. | 1 | 2020-03-06 | 2020-05-15 | 2020-06-15 | Deleted | EP
Niagara 4248 replacement 2 | COR | COR | ATL | Voice Obsolescence | VOBS CO -CO ATL Niagara 4248 replacement Deployment POR20 | Labor | Certify a replacement for EOL Niagara 4248. | 1 | 2020-03-06 | 2020-05-15 | 2020-06-15 | Deleted | EP
Niagara 4248 replacement 3 | COR | COR | ATL | Voice Obsolescence | VOBS CO -CO ATL Niagara 4248 replacement Deployment POR20 | Labor | Certify a replacement for EOL Niagara 4248. | 1 | 2020-03-06 | 2020-05-15 | 2020-06-15 | Deleted | EP
Niagara 4248 replacement 10 | COR | COR | ATL | Voice Obsolescence | VOBS CO -CO ATL Niagara 4248 replacement Deployment POR20 | Labor | Certify a replacement for EOL Niagara 4248. | 1 | 2020-03-06 | 2020-05-15 | 2020-06-15 | Deleted | EP
Niagara 4248 replacement 4 | COR | COR | ATL | Voice Obsolescence | VOBS CO -CO ATL Niagara 4248 replacement Deployment POR20 | Labor | Certify a replacement for EOL Niagara 4248. | 1 | 2020-03-06 | 2020-05-15 | 2020-06-15 | Deleted | EP
Niagara 4248 replacement 5 | COR | COR | ATL | Voice Obsolescence | VOBS CO -CO ATL Niagara 4248 replacement Deployment POR20 | Labor | Certify a replacement for EOL Niagara 4248. | 1 | 2020-03-06 | 2020-05-15 | 2020-06-15 | Deleted | EP
Niagara 4248 replacement 6 | COR | COR | ATL | Voice Obsolescence | VOBS CO -CO ATL Niagara 4248 replacement Deployment POR20 | Labor | Certify a replacement for EOL Niagara 4248. | 1 | 2020-03-06 | 2020-05-15 | 2020-06-15 | Deleted | EP
Niagara 4248 replacement 7 | COR | COR | ATL | Voice Obsolescence | VOBS CO -CO ATL Niagara 4248 replacement Deployment POR20 | Labor | Certify a replacement for EOL Niagara 4248. | 1 | 2020-03-06 | 2020-05-15 | 2020-06-15 | Deleted | EP
Niagara 4248 replacement 8 | COR | COR | ATL | Voice Obsolescence | VOBS CO -CO ATL Niagara 4248 replacement Deployment POR20 | Labor | Certify a replacement for EOL Niagara 4248. | 3 | 2020-03-06 | 2020-05-15 | 2020-06-15 | Deleted | EP
Niagara 4248 replacement 9 | COR | COR | ATL | Voice Obsolescence | VOBS CO -CO ATL Niagara 4248 replacement Deployment POR20 | Labor | Certify a replacement for EOL Niagara 4248. | 1 | 2020-03-06 | 2020-05-15 | 2020-06-15 | Deleted | EP
VOBS CA ORG RSM Voice ACME Decom POR20 | CA | ORG | RSM | Voice Obsolescence | VOBS CA ORG RSM Voice ACME Decom POR20 | Labor | No Equipment | 1 | 2020-01-06 | 2020-01-31 |  | Active | EP
VOBS CA ORG RSM Voice ACME Decom POR20 | CA | ORG | RSM | Voice Obsolescence | VOBS CA ORG RSM Voice ACME Decom POR20 |  |  | 1 | 2020-01-06 | 2020-01-31 |  | Active | Log | Undel | SB-0029 | New | Approved | 2020-01-21 09:44 | This CR requests ACME 9200 decom work at three facilities in Q1--Rancho Santa Margerita, Providence, and Elmwood
VOBS NE RHD PRV Voice ACME Decom POR20 | NE | RHD | PRV | Voice Obsolescence | VOBS NE RHD PRV Voice ACME Decom POR20 | Labor | No Equipment | 1 | 2020-01-06 | 2020-01-31 |  | Active | EP
VOBS NE RHD PRV Voice ACME Decom POR20 | NE | RHD | PRV | Voice Obsolescence | VOBS NE RHD PRV Voice ACME Decom POR20 |  |  | 1 | 2020-01-06 | 2020-01-31 |  | Active | Log | Undel | SB-0029 | New | Approved | 2020-01-21 09:44 | This CR requests ACME 9200 decom work at three facilities in Q1--Rancho Santa Margerita, Providence, and Elmwood
VOBS SE NOR ELM Voice ACME Decom POR20 | SE | NOR | ELM | Voice Obsolescence | VOBS SE NOR ELM Voice ACME Decom POR20 | Labor | No Equipment | 1 | 2020-01-20 | 2020-02-14 |  | Active | EP
VOBS SE NOR ELM Voice ACME Decom POR20 | SE | NOR | ELM | Voice Obsolescence | VOBS SE NOR ELM Voice ACME Decom POR20 |  |  | 1 | 2020-01-20 | 2020-02-14 |  | Active | Log | Undel | SB-0029 | New | Approved | 2020-01-21 09:44 | This CR requests ACME 9200 decom work at three facilities in Q1--Rancho Santa Margerita, Providence, and Elmwood
Wifi Lifecycle | COR | COR | ATL | Wifi | WFI COR COR ATL WIFI LIFECYCLE ALIGNMENT POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-12-15 |  | Active | EP
WIFI Standardization | COR | COR | ATL | Wifi | WFI COR COR ATL WIFI STANDARDIZATION ALIGNMENT POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-12-15 |  | Active | EP
WiFi Trial | COR | COR | ATL | Wifi | WFI COR COR ATL WIFI TRIAL ALIGNMENT POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-12-15 |  | Active | EP