## POR
|  |  |  | LRP: | 2020 | [5 empty] | StratPlat Plan Of Record
|  |  |  | Version: | As Of 11/23/2020 | [11 empty] | Last Approved CR
Dpt | Identifier | Reg | Mkt | TLA | Facility | Program | POR Src | EPS | Watts | EPS Project Name | Kit Type | Kit Name | Qty | Need By Date | Activation Month | Migration Month | CR Id | Date Effect | Action | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
34970 | CFG SW ARZ CHD HV-CFG Deployment POR20 - 2 | SW | ARZ | CHD | Chandler | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ CHD HV-CFG Deployment POR20 - 2 | Labor | No Equipment | 1 |  | 2019-01-20 |  | SN-0130 | 2020-02-06 | Chg
34645 | BWM SW LAS TEN MSSA Augment POR20 | SW | LAS | TEN | Tenaya | Bandwidth Management | POInt | Yes | No | BWM SW LAS TEN MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | SN-0426 | 2020-04-10 | Chg
34761 | BWM SW ARZ WCG MSSA Augment POR20 | SW | ARZ | WCG | Wickenburg | Bandwidth Management | POInt | Yes | No | BWM SW ARZ WCG MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | SN-0426 | 2020-04-10 | Chg
34761 | BWM SW ARZ PEO MSSA Augment POR20 | SW | ARZ | PEO | Peoria | Bandwidth Management | POInt | Yes | No | BWM SW ARZ PEO MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | SN-0426 | 2020-04-10 | Chg
34761 | BWM SW ARZ CHD MSSA Augment POR20 | SW | ARZ | CHD | Chandler | Bandwidth Management | POInt | Yes | No | BWM SW ARZ CHD MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | SN-0426 | 2020-04-10 | Chg
34761 | BWM SW ARZ PNL MSSA Augment POR20 | SW | ARZ | PNL | Pinal County | Bandwidth Management | POInt | Yes | No | BWM SW ARZ PNL MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | SN-0426 | 2020-04-10 | Chg
34761 | BWM SW ARZ VAL MSSA Augment POR20 | SW | ARZ | VAL | Vail | Bandwidth Management | POInt | Yes | No | BWM SW ARZ VAL MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | SN-0426 | 2020-04-10 | Chg
34645 | BWM SW LAS OSB MSSA Augment POR20 | SW | LAS | OSB | Oso Blanca | Bandwidth Management | POInt | Yes | No | BWM SW LAS OSB MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | SN-0426 | 2020-04-10 | Chg
34645 | BWM SW LAS CEN MSSA Augment POR20 | SW | LAS | CEN | Central | Bandwidth Management | POInt | Yes | No | BWM SW LAS CEN MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | SN-0426 | 2020-04-10 | Chg
34761 | BWM SW ARZ BEL MSSA _Labor Only_ Augment POR20 | SW | ARZ | BEL | Bell | Bandwidth Management | POInt | Yes | No | BWM SW ARZ BEL MSSA _Labor Only_ Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | SN-0426 | 2020-04-10 | Chg
34761 | BWM SW ARZ TUC MSSA Augment POR20 | SW | ARZ | TUC | Tucson | Bandwidth Management | POInt | Yes | No | BWM SW ARZ TUC MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | SN-0426 | 2020-04-10 | Chg
34761 | BWM SW ARZ SVA MSSA Augment POR20 | SW | ARZ | VSA | Vistancia | Bandwidth Management | POInt | Yes | No | BWM SW ARZ VSA MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | SN-0426 | 2020-04-10 | Chg
34761 | BWM SW ARZ VSA MSSA Augment POR20 | SW | ARZ | VSA | Vistancia | Bandwidth Management | POInt | Yes | No | BWM SW ARZ VSA MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | SN-0426 | 2020-04-10 | Chg
34761 | BWM SW ARZ FWL MSSA Augment POR20 | SW | ARZ | FWL | Fowler | Bandwidth Management | POInt | Yes | No | BWM SW ARZ FWL MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | SN-0426 | 2020-04-10 | Chg
34761 | BWM SW ARZ BUK MSSA Augment POR20 | SW | ARZ | BUK | Buckeye | Bandwidth Management | POInt | Yes | No | BWM SW ARZ BUK MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | SN-0426 | 2020-04-10 | Chg
34645 | BWM SW LAS AMI MSSA Augment POR20 | SW | LAS | AMI | Amigo | Bandwidth Management | POInt | Yes | No | BWM SW LAS AMI MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | SN-0426 | 2020-04-10 | Chg
34761 | BWM SW ARZ SSC MSSA Augment POR20 | SW | ARZ | SSC | South Scottsdale | Bandwidth Management | POInt | Yes | No | BWM SW ARZ SSC MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | SN-0426 | 2020-04-10 | Chg
34761 | BWM SW ARZ MSA MSSA Augment POR20 | SW | ARZ | MSA | Mesa | Bandwidth Management | POInt | Yes | No | BWM SW ARZ MSA MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | SN-0426 | 2020-04-10 | Chg
34645 | BWM SW LAS HEN MSSA Augment POR20 | SW | LAS | HEN | Henderson | Bandwidth Management | POInt | Yes | No | BWM SW LAS HEN MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | SN-0426 | 2020-04-10 | Chg
34761 | BWM SW ARZ CSG MSSA Augment POR20 | SW | ARZ | CSG | Casa Grande | Bandwidth Management | POInt | Yes | No | BWM SW ARZ CSG MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | SN-0426 | 2020-04-10 | Chg
34761 | BWM SW ARZ GVA MSSA Augment POR20 | SW | ARZ | GVA | Green Valley | Bandwidth Management | POInt | Yes | No | BWM SW ARZ GVA MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | SN-0426 | 2020-04-10 | Chg
34761 | BWM SW ARZ BEN MSSA Augment POR20 | SW | ARZ | BEN | Benson with (Insite tower) | Bandwidth Management | POInt | Yes | No | BWM SW ARZ BEN MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | SN-0426 | 2020-04-10 | Chg
34761 | BWM SW ARZ MCD MSSA Augment POR20 | SW | ARZ | MCD | McDowell | Bandwidth Management | POInt | Yes | No | BWM SW ARZ MCD MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | SN-0426 | 2020-04-10 | Chg
34645 | BWM SW LAS VLY MSSA Augment POR20 | SW | LAS | VLY | Valley | Bandwidth Management | POInt | Yes | No | BWM SW LAS VLY MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | SN-0426 | 2020-04-10 | Chg
34761 | BWM SW ARZ NSC MSSA Augment POR20 | SW | ARZ | NSC | North Scottsdale | Bandwidth Management | POInt | Yes | No | BWM SW ARZ NSC MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | SN-0426 | 2020-04-10 | Chg
34645 | BWM SW LAS ALI MSSA _Labor Only_ Augment POR20 | SW | LAS | ALI | Aliante | Bandwidth Management | POInt | Yes | No | BWM SW LAS ALI MSSA _Labor Only_ Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | SN-0426 | 2020-04-10 | Chg
34645 | BWM SW LAS BOC MSSA Augment POR20 | SW | LAS | BOC | Boulder City | Bandwidth Management | POInt | Yes | No | BWM SW LAS BOC MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | SN-0426 | 2020-04-10 | Chg
34645 | BWM SW LAS ERN MSSA Augment POR20 | SW | LAS | ERN | Ernest May | Bandwidth Management | POInt | Yes | No | BWM SW LAS ERN MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | SN-0426 | 2020-04-10 | Chg
34761 | BWM SW ARZ DGL MSSA Augment POR20 | SW | ARZ | DGL | Douglas | Bandwidth Management | POInt | Yes | No | BWM SW ARZ DGL MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | SN-0426 | 2020-04-10 | Chg
34761 | BWM SW ARZ JMX MSSA Augment POR20 | SW | ARZ | JMX | Jomax | Bandwidth Management | POInt | Yes | No | BWM SW ARZ JMX MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | SN-0426 | 2020-04-10 | Chg
34645 | BWM SW LAS BLU MSSA Augment POR20 | SW | LAS | BLU | Blue Diamond | Bandwidth Management | POInt | Yes | No | BWM SW LAS BLU MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | SN-0426 | 2020-04-10 | Chg
34636 | BWM_MCN_MSSA_Spectrum Phase II Start | SE | MGA | MCN | Macon | Bandwidth Management | POInt | Yes | No | BWM SE MGA MCN MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-19 | 2020-03-11 | SN-0498 | 2020-04-29 | Chg
75731 | CORP CFS VA HRD NWP FS-CFS Augment POR20 | VA | HRD | NWP | Newport News | Critical Facilities Sustaining (Corp) | POInt | Yes | No | CORP CFS VA HRD NWP FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | SB-0023 | 2020-01-30 | New
75731 | CORP CFS VA ROA RON FS-CFS Augment POR20 | VA | ROA | RON | Roanoke | Critical Facilities Sustaining (Corp) | POInt | Yes | No | CORP CFS VA ROA RON FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | SB-0023 | 2020-01-30 | New
75731 | CORP CFS VA NVA GCR FS-CFS Augment POR20 | VA | NVA | GCR | Gunston | Critical Facilities Sustaining (Corp) | POInt | Yes | No | CORP CFS VA NVA GCR FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | SB-0023 | 2020-01-30 | New
75731 | CORP CFS VA NVA DRA FS-CFS Augment POR20 | VA | NVA | DRA | Dranesville | Critical Facilities Sustaining (Corp) | POInt | Yes | No | CORP CFS VA NVA DRA FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | SB-0023 | 2020-01-30 | New
75731 | CORP CFS VA NVA RHL FS-CFS Augment POR20 | VA | NVA | RHL | Rose Hill | Critical Facilities Sustaining (Corp) | POInt | Yes | No | CORP CFS VA NVA RHL FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | SB-0023 | 2020-01-30 | New
75731 | CORP CFS VA NVA FLK FS-CFS Augment POR20 | VA | NVA | FLK | Fair Lakes | Critical Facilities Sustaining (Corp) | POInt | Yes | No | CORP CFS VA NVA FLK FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | SB-0023 | 2020-01-30 | New
75731 | CORP CFS VA HRD VBC FS-CFS Augment POR20 | VA | HRD | VBC | Virginia Beach | Critical Facilities Sustaining (Corp) | POInt | Yes | No | CORP CFS VA HRD VBC FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | SB-0023 | 2020-01-30 | New
75731 | CORP CFS VA NVA FST FS-CFS Augment POR20 | VA | NVA | FST | Fairfax Station | Critical Facilities Sustaining (Corp) | POInt | Yes | No | CORP CFS VA NVA FST FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | SB-0023 | 2020-01-30 | New
75731 | CORP CFS VA NVA TCR FS-CFS Augment POR20 | VA | NVA | TCR | Tysons Corner | Critical Facilities Sustaining (Corp) | POInt | Yes | No | CORP CFS VA NVA TCR FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE TUL TUL BD-CFS Augment POR20 | CE | TUL | TUL | Tulsa | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE TUL TUL BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE TUL TUL GN-CFS Augment POR20 | CE | TUL | TUL | Tulsa | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE TUL TUL GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ CHD DC-CFS Augment POR20 | SW | ARZ | CHD | Chandler | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ CHD DC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE NWA NWA BD-CFS Augment POR20 | CE | NWA | NWA | Johnson | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE NWA NWA BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE TUL TUL SC-CFS Augment POR20 | CE | TUL | TUL | Tulsa | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE TUL TUL SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | SB-0023 | 2020-01-30 | New
54572 | CFS VA HRD OCN BM-CFS Augment POR20 | VA | HRD | OCN | Oceana | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD OCN BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | SB-0023 | 2020-01-30 | New
39251 | BWM_ALP_MSSA_Spectrum Phase II Start | CA | SAN | ALP | Alpine | Bandwidth Management | POInt | Yes | No | BWM CA SAN ALP MSSA _Labor Only_ Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-10 | 2020-03-11 | SN-0426 | 2020-04-10 | Chg
34972 | CFG CE OKC CLH BS-CFG Deployment POR20 | CE | OKC | CLH | County Line | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC CLH BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE OMA BLV GN-CFG Deployment POR20 | CE | OMA | BLV | Bellevue | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OMA BLV GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE OMA SOU BD-CFG Deployment POR20 | CE | OMA | SOU | South (OM) | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OMA SOU BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE KAN OLA GN-CFG Deployment POR20 | CE | KAN | OLA | Iola | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE KAN OLA GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE TUL GAR BD-CFG Deployment POR20 | CE | TUL | GAR | Garnett | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE TUL GAR BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE KAN NWT HV-CFG Deployment POR20 | CE | KAN | NWT | Newton | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE KAN NWT HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE ARK NWA BD-CFG Deployment POR20 | CE | NWA | NWA | Johnson | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE ARK NWA BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE OKC NCH HV-CFG Deployment POR20 | CE | OKC | NCH | North Central | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC NCH HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE OKC CHO BS-CFG Deployment POR20 | CE | OKC | CHO | Choctaw | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC CHO BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE ARK HRN RK-CFG Deployment POR20 | CE | NWA | HRN | Harrison | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE ARK HRN RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE OKC NOR BD-CFG Deployment POR20 | CE | OKC | NOR | Norman | Critical Facilities (Grow) | POInt | Yes | No | CFG CE OKC NOR BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE KAN GBD HV-CFG Deployment POR20 | CE | KAN | GBD | Great Bend | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE KAN GBD HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE KAN DBY GN-CFG Deployment POR20 | CE | KAN | DBY | Derby | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE KAN DBY GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE NWA SSP GN-CFG Deployment POR20 | CE | NWA | SSP | Siloam Springs | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE NWA SSP GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE OKC WLH RK-CFG Deployment POR20 | CE | OKC | WLH | Waterloo | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC WLH RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE OKC WLH HV-CFG Deployment POR20 | CE | OKC | WLH | Waterloo | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC WLH HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE KAN SDN GN-CFG Deployment POR20 | CE | KAN | SDN | Sedan | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE KAN SDN GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE TUL SAP RK-CFG Deployment POR20 | CE | TUL | SAP | Sapulpa | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE TUL SAP RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE OMA ONA BS-CFG Deployment POR20 | CE | OMA | ONA | North (OM) | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OMA ONA BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE OMA ONA BD-CFG Deployment POR20 | CE | OMA | ONA | North (OM) | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OMA ONA BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE OKC SEH AC-CFG Deployment POR20 | CE | OKC | SEH | South East | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC SEH AC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE OKC MOO RK-CFG Deployment POR20 | CE | OKC | MOO | Moore | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC MOO RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE TUL QNC RK-CFG Deployment POR20 | CE | TUL | QNC | Quincy | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE TUL QNC RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE OKC SEH DC-CFG Deployment POR20 | CE | OKC | SEH | South East | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC SEH DC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE OKC ELR RK-CFG Deployment POR20 | CE | OKC | ELR | El Reno | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC ELR RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE OKC OKC RC-CFG Deployment POR20 | CE | OKC | OKC | OKC MTC | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC OKC RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE OMA WES BD-CFG Deployment POR20 | CE | OMA | WES | West (OM) | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OMA WES BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE ARK VBN RK-CFG Deployment POR20 | CE | NWA | VBN | Van Buren | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE ARK VBN RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE OMA WES RK-CFG Deployment POR20 | CE | OMA | WES | West (OM) | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OMA WES RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE KAN TOP RK-CFG Deployment POR20 | CE | KAN | TOP | Topeka | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE KAN TOP RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE OKC WLH BS-CFG Deployment POR20 | CE | OKC | WLH | Waterloo | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC WLH BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE OKC SEH RK-CFG Deployment POR20 | CE | OKC | SEH | South East | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC SEH RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE TUL OWA RK-CFG Deployment POR20 | CE | TUL | OWA | Owasso | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE TUL OWA RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE TUL BAR RK-CFG Deployment POR20 | CE | TUL | BAR | Broken Arrow | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE TUL BAR RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE KAN GDY GN-CFG Deployment POR20 | CE | KAN | GDY | Garden City | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE KAN GDY GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE OMA CBL RK-CFG Deployment POR20 | CE | OMA | CBL | Council Bluffs | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OMA CBL RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE OKC SEH HV-CFG Deployment POR20 | CE | OKC | SEH | South East | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC SEH HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE TUL SAP BD-CFG Deployment POR20 | CE | TUL | SAP | Sapulpa | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE TUL SAP BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE OMA SOU RK-CFG Deployment POR20 | CE | OMA | SOU | South (OM) | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OMA SOU RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE OKC NEH HV-CFG Deployment POR20 | CE | OKC | NEH | North East | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC NEH HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE ARK NWA RK-CFG Deployment POR20 | CE | NWA | NWA | Johnson | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE ARK NWA RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE OKC CLH HV-CFG Deployment POR20 | CE | OKC | CLH | County Line | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC CLH HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE KAN GBD BD-CFG Deployment POR20 | CE | KAN | GBD | Great Bend | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE KAN GBD BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE TUL OWA BD-CFG Deployment POR20 | CE | TUL | OWA | Owasso | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE TUL OWA BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE KAN WIC BD-CFG Deployment POR20 | CE | KAN | WIC | Wichita | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE KAN WIC BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE OKC NEH AC-CFG Deployment POR20 | CE | OKC | NEH | North East | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC NEH AC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE KAN PIT GN-CFG Deployment POR20 | CE | KAN | PIT | Pittsburg | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE KAN PIT GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE OKC MOO AC-CFG Deployment POR20 | CE | OKC | MOO | Moore | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC MOO AC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE KAN WIC IV-CFG Deployment POR20 | CE | KAN | WIC | Wichita | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE KAN WIC IV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE KAN STR RC-CFG Deployment POR20 | CE | KAN | STR | Strotherfield | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE KAN STR RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE KAN CNY GN-CFG Deployment POR20 | CE | KAN | CNY | Cheney | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE KAN CNY GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE ARK BER RK-CFG Deployment POR20 | CE | NWA | BER | Berryville | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE ARK BER RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE ARK BVL RK-CFG Deployment POR20 | CE | NWA | BVL | Bentonville | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE ARK BVL RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE OMA WES HV-CFG Deployment POR20 | CE | OMA | WES | West (OM) | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OMA WES HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE TUL QNC BD-CFG Deployment POR20 | CE | TUL | QNC | Quincy | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE TUL QNC BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE OMA CBL HV-CFG Deployment POR20 | CE | OMA | CBL | Council Bluffs | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OMA CBL HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE OMA OMM GN-CFG Deployment POR20 | CE | OMA | OMM | Omaha | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OMA OMM GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE OKC OKC BS-CFG Deployment POR20 | CE | OKC | OKC | OKC MTC | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC OKC BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE KAN DBY HV-CFG Deployment POR20 | CE | KAN | DBY | Derby | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE KAN DBY HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE OKC SEH BS-CFG Deployment POR20 | CE | OKC | SEH | South East | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC SEH BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE TUL DTN BD-CFG Deployment POR20 | CE | TUL | DTN | Downtown (TUL) | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE TUL DTN BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE TUL BRD BD-CFG Deployment POR20 | CE | TUL | BRD | Braden | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE TUL BRD BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE KAN MPN HV-CFG Deployment POR20 | CE | KAN | MPN | McPherson | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE KAN MPN HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE OKC WLH BD-CFG Deployment POR20 | CE | OKC | WLH | Waterloo | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC WLH BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW LAS HEN IV-CFG Deployment POR20 | SW | LAS | HEN | Henderson | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW LAS HEN IV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW ARZ TUC RC-CFG Deployment POR20 | SW | ARZ | TUC | Tucson | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ TUC RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW LAS TEN BD-CFG Deployment POR20 | SW | LAS | TEN | Tenaya | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW LAS TEN BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW LAS HEN RC-CFG Deployment POR20 | SW | LAS | HEN | Henderson | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW LAS HEN RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW LAS OSB DC-CFG Deployment POR20 | SW | LAS | OSB | Oso Blanca | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW LAS OSB DC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW ARZ BEL HV-CFG Deployment POR20 | SW | ARZ | BEL | Bell | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ BEL HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW LAS HEN BS-CFG Deployment POR20 | SW | LAS | HEN | Henderson | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW LAS HEN BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW ARZ CHD BS-CFG Deployment POR20 | SW | ARZ | CHD | Chandler | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ CHD BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW ARZ CHD BD-CFG Deployment POR20 | SW | ARZ | CHD | Chandler | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ CHD BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW LAS OSB IV-CFG Deployment POR20 | SW | LAS | OSB | Oso Blanca | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW LAS OSB IV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW ARZ PNL GN-CFG Deployment POR20 | SW | ARZ | PNL | Pinal County | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ PNL GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW ARZ BEN RC-CFG Deployment POR20 | SW | ARZ | CHD | Chandler | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ BEN RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW ARZ SSC BD-CFG Deployment POR20 | SW | ARZ | SSC | South Scottsdale | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ SSC BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW LAS HEN HV-CFG Deployment POR20 | SW | LAS | HEN | Henderson | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW LAS HEN HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW ARZ MSA HV-CFG Deployment POR20 | SW | ARZ | MSA | Mesa | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ MSA HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW ARZ WCG RC-CFG Deployment POR20 | SW | ARZ | WCG | Wickenburg | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ WCG RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW ARZ CHD DC-CFG Deployment POR20 | SW | ARZ | CHD | Chandler | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ CHD DC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW LAS OSB BD-CFG Deployment POR20 | SW | LAS | OSB | Oso Blanca | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW LAS OSB BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW ARZ MSA RC-CFG Deployment POR20 | SW | ARZ | MSA | Mesa | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ MSA RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW ARZ SSC GN-CFG Deployment POR20 | SW | ARZ | SSC | South Scottsdale | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ SSC GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW ARZ WCG BS-CFG Deployment POR20 | SW | ARZ | WCG | Wickenburg | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ WCG BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW ARZ PEO RC-CFG Deployment POR20 | SW | ARZ | PEO | Peoria | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ PEO RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW LAS ERN RC-CFG Deployment POR20 | SW | LAS | ERN | Ernest May | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW LAS ERN RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW LAS TEN RC-CFG Deployment POR20 | SW | LAS | TEN | Tenaya | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW LAS TEN RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW LAS TEN HV-CFG Deployment POR20 | SW | LAS | TEN | Tenaya | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW LAS TEN HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW ARZ TUC BD-CFG Deployment POR20 | SW | ARZ | TUC | Tucson | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ TUC BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW LAS HEN BU-CFG Deployment POR20 | SW | LAS | HEN | Henderson | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW LAS HEN BU-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW ARZ SSC AC-CFG Deployment POR20 | SW | ARZ | SSC | South Scottsdale | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ SSC AC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW ARZ PNL HV-CFG Deployment POR20 | SW | ARZ | PNL | Pinal County | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ PNL HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW ARZ PEO BD-CFG Deployment POR20 | SW | ARZ | PEO | Peoria | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ PEO BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW ARZ PNL AC-CFG Deployment POR20 | SW | ARZ | PNL | Pinal County | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ PNL AC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW ARZ FWL DC-CFG Deployment POR20 | SW | ARZ | FWL | Fowler | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ FWL DC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-19 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW ARZ CHD IV-CFG Deployment POR20 | SW | ARZ | CHD | Chandler | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ CHD IV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-19 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW ARZ FWL BD-CFG Deployment POR20 | SW | ARZ | FWL | Fowler | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ FWL BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-19 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW ARZ FWL RC-CFG Deployment POR20 | SW | ARZ | FWL | Fowler | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ FWL RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-19 |  | SN-0130 | 2020-02-06 | Chg
34976 | CFG NE CLE CLV RK LARGE Deployment POR20 | NE | CLE | CLV | Cleveland | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE CLE CLV RK LARGE Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-19 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW ARZ DGL RC-CFG Deployment POR20 | SW | ARZ | DGL | Douglas | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ DGL RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-19 |  | SN-0130 | 2020-02-06 | Chg
34970 | CFG SW ARZ MCD RC-CFG Deployment POR20 | SW | ARZ | MCD | McDowell | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ MCD RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-19 |  | SN-0130 | 2020-02-06 | Chg
35169 | MRTR NCS-Growth-CHD-NCS Line Card | SW | ARZ | CHD | Chandler | Metro Routers | POInt | Yes | Yes | MRTR SW ARZ CHD NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2019-10-01 | 2019-12-31 | 2020-03-31 | SN-0158 | 2020-02-06 | Chg
54570 | CFS NE RHD PAW SC-CFS Augment POR20 | NE | RHD | PAW | Pawtucket | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD PAW SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54574 | CFS NE RHD EXT FS-CFS Augment POR20 - 1 | NE | RHD | EXT | Exeter | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD EXT FS-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE OMA ONA BU-CFS Augment POR20 | CE | OMA | ONA | North (OM) | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE OMA ONA BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54572 | CFS VA NVA DRA BU-CFS Augment POR20 | VA | NVA | DRA | Dranesville | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA NVA DRA BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54574 | CFS NE RHD PTH FS-CFS Augment POR20 | NE | RHD | PTH | Portsmouth (RI) | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD PTH FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE RHD RMD SC-CFS Augment POR20 | NE | RHD | RMD | Richmond (RI) | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD RMD SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE OMA BLV FF-CFS Augment POR20 | CE | OMA | BLV | Bellevue | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE OMA BLV FF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
34970 | CFG SE NOR LUL BS-CFG Deployment POR20 | SE | NOR | LUL | Luling | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SE NOR LUL BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SN-0130 | 2020-02-06 | Chg
54574 | CFS NE CON MER FS-CFS Augment POR20 - 1 | NE | CON | MER | Meriden | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON MER FS-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ CSG SC-CFS Augment POR20 | SW | ARZ | CSG | Casa Grande | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ CSG SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE OKC WLH GN-CFS Augment POR20 | CE | OKC | WLH | Waterloo | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE OKC WLH GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE OMA OMM FS-CFS Augment POR20 | CE | OMA | OMM | Omaha | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE OMA OMM FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE CON MER FS-CFS Augment POR20 - 3 | NE | CON | MER | Meriden | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON MER FS-CFS Augment POR20 - 3 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ BUK SC-CFS Augment POR20 | SW | ARZ | BUK | Buckeye | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ BUK SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE TUL QNC BD-CFS Augment POR20 | CE | TUL | QNC | Quincy | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE TUL QNC BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE CON STF HV-CFS Augment POR20 | NE | CON | STF | Old Stafford Tower (Insite tower, Cox hut & antennas) | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON STF HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54574 | CFS NE RHD CRN FS-CFS Augment POR20 | NE | RHD | CRN | Cranston | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD CRN FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
34972 | CFG CE OMA BLV RK-CFG Deployment POR20 | CE | TUL | SAP | Sapulpa | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OMA BLV RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54569 | CFS CA SAN FED BM-CFS Augment POR20 - 2 | CA | SAN | FED | Federal | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CA SAN FED BM-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE LFY CRW LM-CFS Augment POR20 | SE | LFY | CRW | Crowley | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE LFY CRW LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0031 | 2020-01-21 | New
54574 | CFS NE CON MER FS-CFS Augment POR20 - 2 | NE | CON | MER | Meriden | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON MER FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54574 | CFS NE CON SFD FS-CFS Augment POR20 | NE | CON | SFD | Stafford | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON SFD FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE RHD LNC FS-CFS Augment POR20 - 3 | NE | RHD | LNC | Lincoln | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD LNC FS-CFS Augment POR20 - 3 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54574 | CFS NE RHD RMD FS-CFS Augment POR20 - 2 | NE | RHD | RMD | Richmond (RI) | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD RMD FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE GCT CRV BM-CFS Augment POR20 | SE | GCT | CRV | Crestview | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE GCT CRV BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0031 | 2020-01-21 | New
54572 | CFS VA HRD NRF BU-CFS Augment POR20 | VA | HRD | NRF | Norfolk | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD NRF BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE OMA WES BU-CFS Augment POR20 | CE | OMA | WES | West (OM) | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE OMA WES BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54574 | CFS NE RHD PAW LM-CFS Augment POR20 | NE | RHD | PAW | Pawtucket | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD PAW LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE RHD WWK BS-CFS Augment POR20 | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD WWK BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE OMA ONA FF-CFS Augment POR20 | CE | OMA | ONA | North (OM) | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE OMA ONA FF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54574 | CFS NE RHD CRN BS-CFS Augment POR20 - 2 | NE | RHD | CRN | Cranston | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD CRN BS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE CON MAN FS-CFS Augment POR20 - 3 | NE | CON | MAN | Manchester | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON MAN FS-CFS Augment POR20 - 3 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE TUL OWA BU-CFS Augment POR20 | CE | TUL | OWA | Owasso | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE TUL OWA BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54569 | CFS CA ORG DNP HV-CFS Augment POR20 - 2 | CA | ORG | DNP | Dana Point | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CA ORG DNP HV-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ VSA SC-CFS Augment POR20 | SW | ARZ | VSA | Vistancia | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ VSA SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE RHD EXT FS-CFS Augment POR20 - 3 | NE | RHD | EXT | Exeter | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD EXT FS-CFS Augment POR20 - 3 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54569 | CFS CA SAN DWN HV-CFS Augment POR20 | CA | SAN | DWN | Downtown | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CA SAN DWN HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54569 | CFS CA ORG RSM BM-CFS Augment POR20 | CA | ORG | RSM | Rancho Santa Margarita | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CA ORG RSM BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE GCT DES BM-CFS Augment POR20 | SE | GCT | DES | Destin | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE GCT DES BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0031 | 2020-01-21 | New
54573 | CFS SW ARZ CHD SC-CFS Augment POR20 - 1 | SW | ARZ | CHD | Chandler | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ CHD SC-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE BTR BTR BU-CFS Augment POR20 - 1 | SE | BTR | BTR | Baton Rouge | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE BTR BTR BU-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
34970 | CFG SE LFY LFY BS-CFG Deployment POR20 | SE | LFY | LFY | Lafayette | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SE LFY LFY BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SN-0130 | 2020-02-06 | Chg
34972 | CFG CE OMA ONA RK-CFG Deployment POR20 | CE | TUL | OWA | Owasso | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OMA ONA RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE OMA SOU FF-CFS Augment POR20 | CE | OMA | SOU | South (OM) | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE OMA SOU FF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54569 | CFS CA ORG AVJ BM-CFS Augment POR20 | CA | ORG | AVJ | Aliso Viejo | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CA ORG AVJ BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54574 | CFS NE CON ENF FS-CFS Augment POR20 - 2 | NE | CON | ENF | Enfield | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON ENF FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54574 | CFS NE RHD LNC FS-CFS Augment POR20 - 2 | NE | RHD | LNC | Lincoln | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD LNC FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54574 | CFS NE RHD BUR FS-CFS Augment POR20 | NE | RHD | BUR | Burrillville | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD BUR FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE RHD RMD GN-CFS Augment POR20 | NE | RHD | RMD | Richmond (RI) | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD RMD GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE KAN JCY HV-CFS Augment POR20 | CE | KAN | JCY | Junction City | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE KAN JCY HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE GCT FWB BD-CFS Augment POR20 | SE | GCT | FWB | Ft. Walton Beach with (Insite tower) | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE GCT FWB BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54569 | CFS CA ORG ORG BU-CFS Augment POR20 | CA | ORG | ORG | Orange | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CA ORG ORG BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE LFY FRK BM-CFS Augment POR20 | SE | LFY | FRK | Franklin | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE LFY FRK BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0031 | 2020-01-21 | New
54572 | CFS VA HRD NRF DC-CFS Augment POR20 | VA | HRD | NRF | Norfolk | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD NRF DC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE BTR DVL HV-CFS Augment POR20 | SE | BTR | DVL | Donaldsonville | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE BTR DVL HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE CON RKH GN-CFS Augment POR20 | NE | CON | RKH | Rocky Hill | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON RKH GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ MSA HV-CFS Augment POR20 | SW | ARZ | MSA | Mesa | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ MSA HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE TUL DTN BS-CFS Augment POR20 | CE | TUL | DTN | Downtown (TUL) | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE TUL DTN BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE RHD BUR GN-CFS Augment POR20 | NE | RHD | BUR | Burrillville | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD BUR GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW LAS HEN SC-CFS Augment POR20 | SW | LAS | HEN | Henderson | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW LAS HEN SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ CHD HV-CFS Augment POR20 - 1 | SW | ARZ | CHD | Chandler | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ CHD HV-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ BEN HV-CFS Augment POR20 | SW | ARZ | BEN | Benson with (Insite tower) | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ BEN HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54572 | CFS VA NVA TCR BU-CFS Augment POR20 | VA | NVA | TCR | Tysons Corner | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA NVA TCR BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
34970 | CFG SW LAS TEN HV-CFG Deployment POR20 - 2 | SW | LAS | TEN | Tenaya | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW LAS TEN HV-CFG Deployment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SN-0130 | 2020-02-06 | Chg
54570 | CFS NE RHD PTH LM-CFS Augment POR20 | NE | RHD | PTH | Portsmouth (RI) | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD PTH LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54574 | CFS NE RHD LNC FS-CFS Augment POR20 - 1 | NE | RHD | LNC | Lincoln | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD LNC FS-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE RHD EXT LM-CFS Augment POR20 | NE | RHD | EXT | Exeter | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD EXT LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE KAN GBD FF-CFS Augment POR20 | CE | KAN | GBD | Great Bend | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE KAN GBD FF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ BUK LM-CFS Augment POR20 | SW | ARZ | BUK | Buckeye | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ BUK LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ SSC HV-CFS Augment POR20 | SW | ARZ | SSC | South Scottsdale | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ SSC HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE NWA NWA HV-CFS Augment POR20 | CE | NWA | NWA | Johnson | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE NWA NWA HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE BTR PLQ BM-CFS Augment POR20 | SE | BTR | PLQ | Plaquemine | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE BTR PLQ BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0031 | 2020-01-21 | New
34970 | CFG SE GCT PNS BD-CFG Deployment POR20 | SE | GCT | PNS | Pensacola with (Insite tower) | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SE GCT PNS BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SN-0130 | 2020-02-06 | Chg
54571 | CFS SE BTR SPC BS-CFS Augment POR20 | SE | BTR | SPC | Pecue | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE BTR SPC BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54569 | CFS CA ORG CTA BM-CFS Augment POR20 | CA | ORG | CTA | Cota | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CA ORG CTA BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE BTR PLQ BU-CFS Augment POR20 | SE | BTR | PLQ | Plaquemine | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE BTR PLQ BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0031 | 2020-01-21 | New
54574 | CFS NE CON RKH FS-CFS Augment POR20 - 1 | NE | CON | RKH | Rocky Hill | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON RKH FS-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE OMA ONA BD-CFS Augment POR20 | CE | OMA | ONA | North (OM) | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE OMA ONA BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE RHD LNC GN-CFS Augment POR20 | NE | RHD | LNC | Lincoln | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD LNC GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE OMA BLV HV-CFS Augment POR20 | CE | OMA | BLV | Bellevue | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE OMA BLV HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE KAN DCY BU-CFS Augment POR20 | CE | KAN | DCY | Dodge City | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE KAN DCY BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE RHD BUR AT-CFS Augment POR20 | NE | RHD | BUR | Burrillville | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD BUR AT-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE RHD LNC SC-CFS Augment POR20 | NE | RHD | LNC | Lincoln | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD LNC SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE NOR NOE BM-CFS Augment POR20 | SE | NOR | NOE | New Orleans East | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE NOR NOE BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0031 | 2020-01-21 | New
54571 | CFS SE GCT PNS BD-CFS Augment POR20 | SE | GCT | PNS | Pensacola with (Insite tower) | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE GCT PNS BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE RHD PRV FS-CFS Augment POR20 - 2 | NE | RHD | PRV | Providence | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD PRV FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ BUK HV-CFS Augment POR20 | SW | ARZ | BUK | Buckeye | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ BUK HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE RHD PTH FS-CFS Augment POR20 - 2 | NE | RHD | PTH | Portsmouth (RI) | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD PTH FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE TUL OWA BD-CFS Augment POR20 | CE | TUL | OWA | Owasso | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE TUL OWA BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE CON RKH SC-CFS Augment POR20 | NE | CON | RKH | Rocky Hill | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON RKH SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54574 | CFS NE RHD WWK LM-CFS Augment POR20 | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD WWK LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54572 | CFS VA NVA MFD BU-CFS Augment POR20 | VA | NVA | MFD | Merrifield | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA NVA MFD BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE OKC OKC HV-CFS Augment POR20 | CE | OKC | OKC | OKC MTC | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE OKC OKC HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54569 | CFS CA SAN DWN BM-CFS Augment POR20 | CA | SAN | DWN | Downtown | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CA SAN DWN BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW LAS BOC HV-CFS Augment POR20 | SW | LAS | BOC | Boulder City | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW LAS BOC HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE LFY LFY BU-CFS Augment POR20 | SE | LFY | LFY | Lafayette | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE LFY LFY BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0031 | 2020-01-21 | New
54571 | CFS SE NOR MCY SC-CFS Augment POR20 - 2 | SE | NOR | MCY | Mid-City | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE NOR MCY SC-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0031 | 2020-01-21 | New
54574 | CFS NE RHD CRN BS-CFS Augment POR20 - 1 | NE | RHD | CRN | Cranston | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD CRN BS-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE RHD SCT SC-CFS Augment POR20 | NE | RHD | SCT | Scituate | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD SCT SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE RHD SCT AT-CFS Augment POR20 | NE | RHD | SCT | Scituate | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD SCT AT-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE KAN FSC BU-CFS Augment POR20 | CE | KAN | FSC | Fort Scott | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE KAN FSC BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE TUL BRD BS-CFS Augment POR20 | CE | TUL | BRD | Braden | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE TUL BRD BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE CON MER SC-CFS Augment POR20 | NE | CON | MER | Meriden | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON MER SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54572 | CFS VA HRD JEF RC-CFS Augment POR20 | VA | HRD | JEF | Jefferson Ave | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD JEF RC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE GCT CRV RF-CFS Augment POR20 | SE | GCT | CRV | Crestview | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE GCT CRV RF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0031 | 2020-01-21 | New
54570 | CFS NE RHD EXT SC-CFS Augment POR20 | NE | RHD | EXT | Exeter | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD EXT SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE GCT NCV LM-CFS Augment POR20 | SE | GCT | NCV | Niceville | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE GCT NCV LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0031 | 2020-01-21 | New
54570 | CFS NE RHD CRN SC-CFS Augment POR20 | NE | RHD | CRN | Cranston | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD CRN SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54574 | CFS NE RHD EXT RK-CFS Augment POR20 | NE | RHD | EXT | Exeter | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD EXT RK-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54569 | CFS CA SAN VST BM-CFS Augment POR20 | CA | SAN | VST | Vista | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CA SAN VST BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE GAN GNS BM-CFS Augment POR20 | SE | GAN | GNS | Gainesville | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE GAN GNS BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0031 | 2020-01-21 | New
54570 | CFS CE OMA ELK FF-CFS Augment POR20 | CE | OMA | ELK | Elkhorn | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE OMA ELK FF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE KAN GDY HV-CFS Augment POR20 | CE | KAN | GDY | Garden City | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE KAN GDY HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE CON STF RF-CFS Augment POR20 | NE | CON | STF | Old Stafford Tower (Insite tower, Cox hut & antennas) | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON STF RF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE OKC NEH GN-CFS Augment POR20 | CE | OKC | NEH | North East | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE OKC NEH GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE RHD WWK SC-CFS Augment POR20 | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD WWK SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE RHD PRV BU-CFS Augment POR20 | NE | RHD | PRV | Providence | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD PRV BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE LFY CRW BS-CFS Augment POR20 | SE | LFY | CRW | Crowley | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE LFY CRW BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE NWA BVL BU-CFS Augment POR20 | CE | NWA | BVL | Bentonville | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE NWA BVL BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ PNL HV-CFS Augment POR20 - 2 | SW | ARZ | PNL | Pinal County | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ PNL HV-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE BTR BTR BS-CFS Augment POR20 | SE | BTR | BTR | Baton Rouge | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE BTR BTR BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
34972 | CFG CE OKC NOR BS-CFG Deployment POR20 | CE | NWA | BVL | Bentonville | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC NOR BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE RHD SCT RF-CFS Augment POR20 | NE | RHD | SCT | Scituate | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD SCT RF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54569 | CFS CA SAN CHU HV-CFS Augment POR20 | CA | SAN | CHU | Chula Vista | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CA SAN CHU HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ CHD HV-CFS Augment POR20 - 2 | SW | ARZ | CHD | Chandler | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ CHD HV-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE BTR DVL BU-CFS Augment POR20 | SE | BTR | DVL | Donaldsonville | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE BTR DVL BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54574 | CFS NE RHD WWK FS-CFS Augment POR20 - 2 | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD WWK FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54574 | CFS NE RHD EXT BU-CFS Augment POR20 | NE | RHD | EXT | Exeter | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD EXT BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
34970 | CFG SE NOR LUL RC-CFG Deployment POR20 | SE | NOR | LUL | Luling | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SE NOR LUL RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SN-0130 | 2020-02-06 | Chg
54570 | CFS CE TUL GAR SC-CFS Augment POR20 | CE | TUL | GAR | Garnett | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE TUL GAR SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54572 | CFS VA HRD JEF BS-CFS Augment POR20 | VA | HRD | JEF | Jefferson Ave | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD JEF BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE OKC NOR GN-CFS Augment POR20 | CE | OKC | NOR | Norman | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE OKC NOR GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE NWA BVL BD-CFS Augment POR20 | CE | NWA | BVL | Bentonville | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE NWA BVL BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE CON ENF BU-CFS Augment POR20 | NE | CON | ENF | Enfield | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON ENF BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54572 | CFS VA HRD GBR RC-CFS Augment POR20 | NE | CON | GRB | Granby | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD GBR RC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE OMA SOU BU-CFS Augment POR20 | CE | OMA | SOU | South (OM) | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE OMA SOU BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE TUL YAL BU-CFS Augment POR20 | CE | TUL | YAL | Yale | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE TUL YAL BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE BTR DVL BM-CFS Augment POR20 | SE | BTR | DVL | Donaldsonville | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE BTR DVL BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0031 | 2020-01-21 | New
54570 | CFS CE TUL TUL BS-CFS Augment POR20 | CE | TUL | TUL | Tulsa | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE TUL TUL BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ DGL SC-CFS Augment POR20 | SW | ARZ | DGL | Douglas | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ DGL SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE OKC CHO RK-CFS Augment POR20 | CE | OKC | CHO | Choctaw | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE OKC CHO RK-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE KAN TOP FF-CFS Augment POR20 | CE | KAN | TOP | Topeka | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE KAN TOP FF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54574 | CFS NE CON MAN FS-CFS Augment POR20 - 2 | NE | CON | MAN | Manchester | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON MAN FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE LFY CRW BM-CFS Augment POR20 | SE | LFY | CRW | Crowley | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE LFY CRW BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0031 | 2020-01-21 | New
54573 | CFS SW ARZ NSC HV-CFS Augment POR20 | SW | ARZ | NSC | North Scottsdale | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ NSC HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54574 | CFS NE CON RKH FS-CFS Augment POR20 - 2 | NE | CON | RKH | Rocky Hill | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON RKH FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE OMA OMM BD-CFS Augment POR20 | CE | OMA | OMM | Omaha | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE OMA OMM BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54569 | CFS CA SAN OCE BM-CFS Augment POR20 | CA | SAN | OCE | Oceanside | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CA SAN OCE BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE CON RKH BU-CFS Augment POR20 | NE | CON | RKH | Rocky Hill | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON RKH BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE NOR KNN LM-CFS Augment POR20 | SE | NOR | KNN | Kenner | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE NOR KNN LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0031 | 2020-01-21 | New
54572 | CFS VA HRD CYP BU-CFS Augment POR20 | VA | HRD | CYP | Cypress Point CEC | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD CYP BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE KAN KCY RK-CFS Augment POR20 | COR | NAT | KCY | Kansas City (1102 Grand) | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE KAN KCY RK-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE LFY FRK GN-CFS Augment POR20 | SE | LFY | FRK | Franklin | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE LFY FRK GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0031 | 2020-01-21 | New
54570 | CFS NE CON GRB AT-CFS Augment POR20 | NE | CON | GRB | Granby | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON GRB AT-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54572 | CFS VA NVA FLK BU-CFS Augment POR20 | VA | NVA | FLK | Fair Lakes | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA NVA FLK BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54569 | CFS CA ORG RSM HV-CFS Augment POR20 | CA | ORG | RSM | Rancho Santa Margarita | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CA ORG RSM HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE CON GRB SC-CFS Augment POR20 | NE | CON | GRB | Granby | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON GRB SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE OKC MOO BU-CFS Augment POR20 | CE | OKC | MOO | Moore | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE OKC MOO BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ BEL SC-CFS Augment POR20 | SW | ARZ | BEL | Bell | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ BEL SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
34970 | CFG SW ARZ CHD DC-CFG Deployment POR20 - 2 | SW | ARZ | CHD | Chandler | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ CHD DC-CFG Deployment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SN-0130 | 2020-02-06 | Chg
54571 | CFS SE NOR LPL BM-CFS Augment POR20 | SE | NOR | LPL | Lapalco | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE NOR LPL BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0031 | 2020-01-21 | New
54570 | CFS NE CON GRB RF-CFS Augment POR20 | NE | CON | GRB | Granby | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON GRB RF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE OKC MOO HV-CFS Augment POR20 | CE | OKC | MOO | Moore | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE OKC MOO HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54574 | CFS NE CON ENF FS-CFS Augment POR20 - 1 | NE | CON | ENF | Enfield | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON ENF FS-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ CHD SC-CFS Augment POR20 - 2 | SW | ARZ | CHD | Chandler | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ CHD SC-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54569 | CFS CA SAN ESC BM-CFS Augment POR20 | CA | SAN | ESC | Escondido | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CA SAN ESC BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54569 | CFS CA SAB SAB BM-CFS Augment POR20 | CA | SAB | SAB | Santa Barbara | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CA SAB SAB BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54569 | CFS CA SAN ELC AC-CFS Augment POR20 | CA | SAN | ELC | El Cajon | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CA SAN ELC AC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE GAN OCL BM-CFS Augment POR20 | SE | GAN | OCL | Ocala | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE GAN OCL BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0031 | 2020-01-21 | New
54574 | CFS NE CON MER BU-CFS Augment POR20 | NE | CON | MER | Meriden | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON MER BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54574 | CFS NE CON MAN AC-CFS Augment POR20 | NE | CON | MAN | Manchester | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON MAN AC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE CON MER AC-CFS Augment POR20 | NE | CON | MER | Meriden | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON MER AC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54574 | CFS NE RHD PAW FS-CFS Augment POR20 | NE | RHD | PAW | Pawtucket | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD PAW FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE RHD PAW GN-CFS Augment POR20 | NE | RHD | PAW | Pawtucket | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD PAW GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE CON ENF SC-CFS Augment POR20 | NE | CON | ENF | Enfield | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON ENF SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE CON STN BS-CFS Augment POR20 - 2 | NE | CON | STN | Southington | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON STN BS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE GCT PNS RC-CFS Augment POR20 | SE | GCT | PNS | Pensacola with (Insite tower) | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE GCT PNS RC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54574 | CFS NE RHD PRV LM-CFS Augment POR20 | NE | RHD | PRV | Providence | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD PRV LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE RHD BUR BU-CFS Augment POR20 | NE | RHD | BUR | Burrillville | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD BUR BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE CON MER AT-CFS Augment POR20 | NE | CON | MER | Meriden | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON MER AT-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE OMA WES HV-CFS Augment POR20 | CE | OMA | WES | West (OM) | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE OMA WES HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE RHD SCT GN-CFS Augment POR20 | NE | RHD | SCT | Scituate | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD SCT GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
34970 | CFG SE LFY LFY HV-CFG Deployment POR20 | SE | LFY | LFY | Lafayette | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SE LFY LFY HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SN-0130 | 2020-02-06 | Chg
54573 | CFS SW ARZ MSA SC-CFS Augment POR20 | SW | ARZ | MSA | Mesa | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ MSA SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE GCT CRV SC-CFS Augment POR20 | SE | GCT | CRV | Crestview | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE GCT CRV SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE KAN SDN HV-CFS Augment POR20 | CE | KAN | SDN | Sedan | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE KAN SDN HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE RHD PRV AC-CFS Augment POR20 | NE | RHD | PRV | Providence | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD PRV AC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ WCG HV-CFS Augment POR20 | SW | ARZ | WCG | Wickenburg | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ WCG HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE LFY LFY RF-CFS Augment POR20 - 2 | SE | LFY | LFY | Lafayette | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE LFY LFY RF-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE LFY STM HV-CFS Augment POR20 | SE | LFY | STM | St. Martinville | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE LFY STM HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0031 | 2020-01-21 | New
54571 | CFS SE BTR BTR BU-CFS Augment POR20 - 2 | SE | BTR | BTR | Baton Rouge | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE BTR BTR BU-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE GCT FWB SC-CFS Augment POR20 | SE | GCT | FWB | Ft. Walton Beach with (Insite tower) | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE GCT FWB SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE BTR NTH HV-CFS Augment POR20 | SE | BTR | NTH | Baker | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE BTR NTH HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE TUL SAP GN-CFS Augment POR20 | CE | TUL | SAP | Sapulpa | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE TUL SAP GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE KAN GBD HV-CFS Augment POR20 | CE | KAN | GBD | Great Bend | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE KAN GBD HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE KAN PIT HV-CFS Augment POR20 | CE | KAN | PIT | Pittsburg | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE KAN PIT HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54574 | CFS NE CON GRB FS-CFS Augment POR20 | NE | CON | GRB | Granby | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON GRB FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE OMA SOU HV-CFS Augment POR20 | CE | OMA | SOU | South (OM) | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE OMA SOU HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE CON SFD SC-CFS Augment POR20 | NE | CON | SFD | Stafford | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON SFD SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE KAN DCY HV-CFS Augment POR20 | CE | KAN | DCY | Dodge City | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE KAN DCY HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE NOR MCY SC-CFS Augment POR20 | SE | NOR | MCY | Mid-City | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE NOR MCY SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE BTR DNS BU-CFS Augment POR20 | SE | BTR | DNS | Denham Springs | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE BTR DNS BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
34970 | CFG SE BTR BTR BS-CFG Deployment POR20 | SE | BTR | BTR | Baton Rouge | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SE BTR BTR BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SN-0130 | 2020-02-06 | Chg
54571 | CFS SE GAN OCL SC-CFS Augment POR20 | SE | GAN | OCL | Ocala | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE GAN OCL SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0031 | 2020-01-21 | New
54571 | CFS SE NOR MCY BM-CFS Augment POR20 | SE | NOR | MCY | Mid-City | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE NOR MCY BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0031 | 2020-01-21 | New
54572 | CFS VA HRD PRA GN-CFS Augment POR20 | VA | HRD | PRA | Princess Anne | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD PRA GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54569 | CFS CA ORG IRV BM-CFS Augment POR20 | CA | ORG | IRV | Irvine | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CA ORG IRV BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ WCG SC-CFS Augment POR20 | SW | ARZ | WCG | Wickenburg | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ WCG SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54574 | CFS NE CON STN FS-CFS Augment POR20 | NE | CON | STN | Southington | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON STN FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE LFY LFY RF-CFS Augment POR20 - 1 | SE | LFY | LFY | Lafayette | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE LFY LFY RF-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE OMA ELK HV-CFS Augment POR20 | CE | OMA | ELK | Elkhorn | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE OMA ELK HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE NWA FAY BD-CFS Augment POR20 | CE | NWA | FAY | Fayetteville | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE NWA FAY BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE KAN WIC HV-CFS Augment POR20 | CE | KAN | WIC | Wichita | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE KAN WIC HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE KAN PIT RF-CFS Augment POR20 | CE | KAN | PIT | Pittsburg | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE KAN PIT RF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54569 | CFS CA ORG DNP BM-CFS Augment POR20 | CA | ORG | DNP | Dana Point | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CA ORG DNP BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE RHD BUR SC-CFS Augment POR20 | NE | RHD | BUR | Burrillville | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD BUR SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54574 | CFS NE CON GRB RC-CFS Augment POR20 | NE | CON | GRB | Granby | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON GRB RC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54569 | CFS CA ORG IRV HV-CFS Augment POR20 | CA | ORG | IRV | Irvine | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CA ORG IRV HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ BEL HV-CFS Augment POR20 - 1 | SW | ARZ | BEL | Bell | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ BEL HV-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE RHD RMD FS-CFS Augment POR20 - 3 | NE | RHD | RMD | Richmond (RI) | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD RMD FS-CFS Augment POR20 - 3 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE RHD CRN FS-CFS Augment POR20 - 2 | NE | RHD | CRN | Cranston | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD CRN FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54569 | CFS CA ORG DNP HV-CFS Augment POR20 | CA | ORG | DNP | Dana Point | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CA ORG DNP HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE CON ENF FS-CFS Augment POR20 - 3 | NE | CON | ENF | Enfield | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON ENF FS-CFS Augment POR20 - 3 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54569 | CFS CA SAN FED BM-CFS Augment POR20 | CA | SAN | FED | Federal | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CA SAN FED BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE LFY CRW HV-CFS Augment POR20 | SE | LFY | CRW | Crowley | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE LFY CRW HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0031 | 2020-01-21 | New
54570 | CFS CE OKC CHO BU-CFS Augment POR20 | CE | OKC | CHO | Choctaw | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE OKC CHO BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54574 | CFS NE RHD PRV FS-CFS Augment POR20 | NE | RHD | PRV | Providence | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD PRV FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54574 | CFS NE RHD EXT FS-CFS Augment POR20 - 2 | NE | RHD | EXT | Exeter | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD EXT FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54574 | CFS NE RHD WWK FS-CFS Augment POR20 - 1 | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD WWK FS-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE TUL YAL SC-CFS Augment POR20 | CE | TUL | YAL | Yale | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE TUL YAL SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE CON GRB GN-CFS Augment POR20 | NE | CON | GRB | Granby | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON GRB GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE NWA BVL HV-CFS Augment POR20 | CE | NWA | BVL | Bentonville | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE NWA BVL HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE CON STN BS-CFS Augment POR20 | NE | CON | STN | Southington | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON STN BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE RHD WWK BU-CFS Augment POR20 | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD WWK BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54574 | CFS NE RHD RMD FS-CFS Augment POR20 - 1 | NE | RHD | RMD | Richmond (RI) | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD RMD FS-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE TUL OWA GN-CFS Augment POR20 | CE | TUL | OWA | Owasso | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE TUL OWA GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE CON MAN SC-CFS Augment POR20 | NE | CON | MAN | Manchester | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON MAN SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE BTR NTH BU-CFS Augment POR20 | SE | BTR | NTH | Baker | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE BTR NTH BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54574 | CFS NE CON MAN FS-CFS Augment POR20 - 1 | NE | CON | MAN | Manchester | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON MAN FS-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE OKC OKC BD-CFS Augment POR20 | CE | OKC | OKC | OKC MTC | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE OKC OKC BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE RHD WWK FS-CFS Augment POR20 - 3 | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD WWK FS-CFS Augment POR20 - 3 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE CON ENF HV-CFS Augment POR20 | NE | CON | ENF | Enfield | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON ENF HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE RHD PAW HV-CFS Augment POR20 | NE | RHD | PAW | Pawtucket | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD PAW HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE TUL TUL BU-CFS Augment POR20 | CE | TUL | TUL | Tulsa | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE TUL TUL BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE OMA CBL FF-CFS Augment POR20 | CE | OMA | CBL | Council Bluffs | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE OMA CBL FF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE NWA BVL LM-CFS Augment POR20 | CE | NWA | BVL | Bentonville | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE NWA BVL LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE KAN PSN BU-CFS Augment POR20 | CE | KAN | PSN | Parsons | Critical Facilities Sustaining (Field) | POInt | Yes | No | CFS CE KAN PSN BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE KAN FSC HV-CFS Augment POR20 | CE | KAN | FSC | Fort Scott | Critical Facilities Sustaining (Field) | POInt | Yes | No | CFS CE KAN FSC HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE NWA NWA BU-CFS Augment POR20 | CE | NWA | NWA | Johnson | Critical Facilities Sustaining (Field) | POInt | Yes | No | CFS CE NWA NWA BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE KAN PIT SC-CFS Augment POR20 | CE | KAN | PIT | Pittsburg | Critical Facilities Sustaining (Field) | POInt | Yes | No | CFS CE KAN PIT SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
34972 | CFG CE TUL GAR RK-CFG Deployment POR20 | CE | TUL | GAR | Garnett | Critical Facilities (Grow) | POInt | Yes | No | CFG CE TUL GAR RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE KAN PSN HV-CFS Augment POR20 | CE | KAN | PSN | Parsons | Critical Facilities Sustaining (Field) | POInt | Yes | No | CFS CE KAN PSN HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE TUL QNC BU-CFS Augment POR20 | CE | TUL | QNC | Quincy | Critical Facilities Sustaining (Field) | POInt | Yes | No | CFS CE TUL QNC BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE KAN PSN SC-CFS Augment POR20 | CE | KAN | PSN | Parsons | Critical Facilities Sustaining (Field) | POInt | Yes | No | CFS CE KAN PSN SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE KAN FSC SC-CFS Augment POR20 | CE | KAN | FSC | Fort Scott | Critical Facilities Sustaining (Field) | POInt | Yes | No | CFS CE KAN FSC SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE RHD CRN HV-CFS Augment POR20 | NE | RHD | CRN | Cranston | Critical Facilities Sustaining (Field) | POInt | Yes | No | CFS NE RHD CRN HV-CFS Augment POR20 - 3 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE KAN NWT HV-CFS Augment POR20 | CE | KAN | NWT | Newton | Critical Facilities Sustaining (Field) | POInt | Yes | No | CFS CE KAN NWT HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE KAN PSN LM-CFS Augment POR20 | CE | KAN | PSN | Parsons | Critical Facilities Sustaining (Field) | POInt | Yes | No | CFS CE KAN PSN LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE CON GLB BU-CFS Augment POR20 | NE | CON | GLB | Glastonbury | Critical Facilities Sustaining (Field) | POInt | Yes | No | CFS NE CON GLB BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE CON RKH FS-CFS Augment POR20 - 3 | NE | CON | RKH | Rocky Hill | Critical Facilities Sustaining (Field) | POInt | Yes | No | CFS NE CON RKH FS-CFS Augment POR20 - 3 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE CON STN SC-CFS Augment POR20 | NE | CON | STN | Southington | Critical Facilities Sustaining (Field) | POInt | Yes | No | CFS NE CON STN SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE TUL OWA BU-CFS Augment POR20 - 2 | CE | TUL | OWA | Owasso | Critical Facilities Sustaining (Field) | POInt | Yes | No | CFS CE TUL OWA BU-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE TUL SAP BU-CFS Augment POR20 | CE | TUL | SAP | Sapulpa | Critical Facilities Sustaining (Field) | POInt | Yes | No | CFS CE TUL SAP BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE KAN PSN FF-CFS Augment POR20 | CE | KAN | PSN | Parsons | Critical Facilities Sustaining (Field) | POInt | Yes | No | CFS CE KAN PSN FF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE RHD PAW FS-CFS Augment POR20 - 2 | NE | RHD | PAW | Pawtucket | Critical Facilities Sustaining (Field) | POInt | Yes | No | CFS NE RHD PAW FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE OKC OKC HV-CFS Augment POR20 - 2 | CE | OKC | OKC | OKC MTC | Critical Facilities Sustaining (Field) | POInt | Yes | No | CFS CE OKC OKC HV-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS NE RHD PTH SC-CFS Augment POR20 | NE | RHD | PTH | Portsmouth (RI) | Critical Facilities Sustaining (Field) | POInt | Yes | No | CFS NE RHD PTH SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | SB-0023 | 2020-01-30 | New
34970 | CFG SE GCT PNS BS-CFG Deployment POR20 | SE | GCT | PNS | Pensacola with (Insite tower) | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SE GCT PNS BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-02 |  | SB-0023 | 2020-01-30 | New
34972 | CFG MOO AC-CFG GEN GROW PROJECT - MEDIUM | CE | OKC | MOO | Moore | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC MOO AC-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15
34972 | CFG MOO RK-CFG GEN GROW PROJECT - SMALL | CE | OKC | MOO | Moore | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC MOO AC-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-01-01 | 2020-01-15
54571 | CFG SE NOR MCY RK-CFG Deployment POR20 | SE | NOR | MCY | Mid-City | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFG SE NOR MCY RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | SN-0228 | 2020-02-07 | New
34685 | CCAP licenses_NWP | VA | HRD | NWP | Newport News | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS VA HRD NWP CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34975 | CFG PTM BD-CFG GEN GROW PROJECT - MEDIUM | VA | HRD | PTM | Portsmouth (VA) | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA HRD PTM BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15
34687 | CCAP licenses_NCH | CE | OKC | NCH | North Central | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE OKC NCH CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34972 | CFG NEH AC-CFG GEN GROW PROJECT - MEDIUM | CE | OKC | NEH | North East | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC NEH AC-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15
34972 | CFG NEH HV-CFG GEN GROW PROJECT - MEDIUM | CE | OKC | NEH | North East | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC NEH AC-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15
34690 | CCAP licenses_SSP | CE | NWA | SSP | Siloam Springs | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE NWA SSP CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34685 | CCAP licenses_NKT | VA | HRD | NKT | New Kent | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS VA HRD NKT CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34685 | CCAP licenses_TCR | VA | NVA | TCR | Tysons Corner | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS VA NVA TCR CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34690 | CCAP licenses_MPN | CE | KAN | MPN | McPherson | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE KAN MPN CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34972 | CFG WIC BD-CFG GEN GROW PROJECT - MEDIUM | CE | KAN | WIC | Wichita | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE KAN WIC BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15
34972 | CFG WIC IV-CFG GEN GROW PROJECT - MEDIUM | CE | KAN | WIC | Wichita | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE KAN WIC BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15
34972 | CFG OWA BD-CFG GEN GROW PROJECT - MEDIUM | CE | TUL | OWA | Owasso | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE TUL OWA BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15
34972 | CFG OWA RK-CBMC GEN GROW PROJECT - SMALL | CE | TUL | OWA | Owasso | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE TUL OWA BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-01-01 | 2020-01-15
34685 | CCAP licenses_FLK | VA | NVA | FLK | Fair Lakes | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS VA NVA FLK CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34695 | CCAP licenses_DWN | CA | SAN | DWN | Downtown | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CA SAN DWN CCAP Augment POR20 | License | CCAP license | 3 | 2020-01-06 | 2020-01-15
39225 | CCAP licenses_NCV | SE | GCT | NCV | Niceville | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SE GCT NCV CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34972 | CFG GBD BD-CFG GEN GROW PROJECT - LARGE | CE | KAN | GBD | Great Bend | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE KAN GBD BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-01-01 | 2020-01-15
34972 | CFG CBL RK-R PHY GEN GROW PROJECT - MEDIUM | CE | OMA | CBL | Council Bluffs | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OMA CBL RK-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15
34687 | CCAP licenses_NEH | CE | OKC | NEH | North East | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE OKC NEH CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34690 | CCAP licenses_BER | CE | NWA | BER | Berryville | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE NWA BER CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34604 | CB Transport - New Router Lafayette, St. Martinville - LFY - Card Add | SE | LFY | LFY | Lafayette | CB - Metro Core | POInt | Yes | Yes | CBMC SE LFY LFY Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-01 | 2020-01-15
34972 | CFG GDY GN-CFG GEN GROW PROJECT - LARGE | CE | KAN | GDY | Garden City | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE KAN GDY GN-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-01-01 | 2020-01-15
39225 | CCAP licenses_PNS | SE | GCT | PNS | Pensacola with (Insite tower) | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SE GCT PNS CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
39225 | CCAP blades_ PNS | SE | GCT | PNS | Pensacola with (Insite tower) | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SE GCT PNS CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-01-06 | 2020-01-15
34972 | CFG SAP BD-CFG GEN GROW PROJECT - MEDIUM | CE | TUL | SAP | Sapulpa | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE TUL SAP BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15
34972 | CFG SAP RK-CBMC GEN GROW PROJECT - SMALL | CE | TUL | SAP | Sapulpa | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE TUL SAP BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-01-01 | 2020-01-15
34690 | CCAP blades_ BLV | CE | OMA | BLV | Bellevue | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE OMA BLV CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-01-06 | 2020-01-15
34690 | CCAP licenses_BLV | CE | OMA | BLV | Bellevue | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE OMA BLV CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34695 | CCAP licenses_IRV | CA | ORG | IRV | Irvine | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CA ORG IRV CCAP Augment POR20 | License | CCAP license | 3 | 2020-01-06 | 2020-01-15
34692 | CCAP licenses_HEN | SW | LAS | HEN | Henderson | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SW LAS HEN CCAP Augment POR20 | License | CCAP license | 5 | 2020-01-06 | 2020-01-15
34841 | CCAP licenses_ELM | SE | NOR | ELM | Elmwood | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SE NOR ELM CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34685 | CCAP licenses_RHL | VA | NVA | RHL | Rose Hill | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS VA NVA RHL CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34841 | CCAP licenses_SPC | SE | BTR | SPC | Pecue | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SE BTR SPC CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34972 | CFG QNC BD-CFG GEN GROW PROJECT - MEDIUM | CE | TUL | QNC | Quincy | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE TUL QNC BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15
34972 | CFG QNC RK-CBMC GEN GROW PROJECT - SMALL | CE | TUL | QNC | Quincy | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE TUL QNC BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-01-01 | 2020-01-15
34685 | CCAP licenses_VBC | VA | HRD | VBC | Virginia Beach | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS VA HRD VBC CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34694 | CCAP licenses_MCD | SW | ARZ | MCD | McDowell | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SW ARZ MCD CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34685 | CCAP licenses_FBG | VA | NVA | FBG | Fredericksburg | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS VA NVA FBG CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34695 | CCAP licenses_ESC | CA | SAN | ESC | Escondido | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CA SAN ESC CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34690 | CCAP licenses_CBL | CE | OMA | CBL | Council Bluffs | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE OMA CBL CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34604 | CB Transport - New Router BTR uplink, POY - MCY - Optics | SE | NOR | MCY | Mid-City | CB - Metro Core | POInt | Yes | Yes | CBMC SE NOR MCY Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-01-01 | 2020-01-15
34685 | CCAP licenses_CHS | VA | HRD | CHS | Chesapeake | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS VA HRD CHS CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34687 | CCAP licenses_MWC | CE | OKC | MWC | Midwest City | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE OKC MWC CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34683 | CCAP licenses_PTH | NE | RHD | PTH | Portsmouth (RI) | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS NE RHD PTH CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34683 | CCAP blades_ PTH | NE | RHD | PTH | Portsmouth (RI) | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS NE RHD PTH CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-01-06 | 2020-01-15
34972 | CFG CNY GN-CFG GEN GROW PROJECT - MEDIUM | CE | KAN | CNY | Cheney | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE KAN CNY GN-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15
34694 | CCAP licenses_GVA | SW | ARZ | GVA | Green Valley | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SW ARZ GVA CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34687 | CCAP licenses_BAR | CE | TUL | BAR | Broken Arrow | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE TUL BAR CCAP Augment POR20 | License | CCAP license | 3 | 2020-01-06 | 2020-01-15
34972 | CFG STR RC-CFG GEN GROW PROJECT - MEDIUM | CE | KAN | STR | Strotherfield | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE KAN STR RC-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15
34974 | CFG SE NOR NOE BS-CFG Deployment POR20 | SE | NOR | NOE | New Orleans East | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SE NOR NOE BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | SN-0228 | 2020-02-07 | New
34972 | CFG BER RK-CBMC GEN GROW PROJECT - SMALL | CE | NWA | BER | Berryville | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE ARK BER RK-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-01-01 | 2020-01-15
34972 | CFG WLH BD-CFG GEN GROW PROJECT - MEDIUM | CE | OKC | WLH | Waterloo | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC WLH BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15
34972 | CFG WLH HV-CFG GEN GROW PROJECT - MEDIUM | CE | OKC | WLH | Waterloo | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC WLH BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15
34972 | CFG WLH RK-CFG GEN GROW PROJECT - SMALL | CE | OKC | WLH | Waterloo | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC WLH BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-01-01 | 2020-01-15
34972 | CFG WLH BS-CFG GEN GROW PROJECT - MEDIUM | CE | OKC | WLH | Waterloo | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC WLH BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15
34694 | CCAP licenses_NSC | SW | ARZ | NSC | North Scottsdale | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SW ARZ NSC CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34971 | CFG CA ORG ORG RK-CFG Deployment POR20 | CA | ORG | ORG | Orange | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA ORG ORG RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | SN-0228 | 2020-02-07 | New
34972 | CFG NOR BS-CFG GEN GROW PROJECT - LARGE | CE | OKC | NOR | Norman | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC NOR BS-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-01-01 | 2020-01-15
34972 | CFG MPN HV-CFG GEN GROW PROJECT - LARGE | CE | KAN | MPN | McPherson | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE KAN MPN HV-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-01-01 | 2020-01-15
34841 | CCAP licenses_NTH | SE | BTR | NTH | Baker | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SE BTR NTH CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34694 | CCAP licenses_CHD | SW | ARZ | CHD | Chandler | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SW ARZ CHD CCAP Augment POR20 | License | CCAP license | 7 | 2020-01-06 | 2020-01-15
34841 | CCAP blades_ CLR 1 | SE | NOR | CLR | Metairie | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SE NOR CLR CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-01-06 | 2020-01-15
34841 | CCAP licenses_NOE | SE | NOR | NOE | New Orleans East | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SE NOR NOE CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34972 | CFG BRD BD-CFG GEN GROW PROJECT - MEDIUM | CE | TUL | BRD | Braden | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE TUL BRD BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15
39225 | CCAP licenses_WRB | SE | MGA | WRB | Warner Robins | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SE MGA WRB CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34690 | CCAP licenses_MNT | CE | KAN | MNT | Manhattan | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE KAN MNT CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34972 | CFG DTN BD-CFG GEN GROW PROJECT - MEDIUM | CE | TUL | DTN | Downtown (TUL) | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE TUL DTN BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15
34687 | CCAP licenses_WEH | CE | OKC | WEH | West (OKC) | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE OKC WEH CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34685 | CCAP licenses_OCN | VA | HRD | OCN | Oceana | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS VA HRD OCN CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34690 | CCAP licenses_WIC | CE | KAN | WIC | Wichita | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE KAN WIC CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34690 | CCAP blades_ WIC | CE | KAN | WIC | Wichita | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE KAN WIC CCAP Augment POR20 | Card & Optics | CCAP blade and license | 4 | 2020-01-06 | 2020-01-15
34972 | CFG DBY GN-CFG GEN GROW PROJECT - LARGE | CE | KAN | DBY | Derby | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE KAN DBY HV-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-01-01 | 2020-01-15
34972 | CFG OKC RC-CFG GEN GROW PROJECT - MEDIUM | CE | OKC | OKC | OKC MTC | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC OKC BS-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15
34972 | CFG OKC BS-CFG GEN GROW PROJECT - MEDIUM | CE | OKC | OKC | OKC MTC | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC OKC BS-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15
34687 | CCAP blades_ OKC 1 | CE | OKC | OKC | OKC MTC | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE OKC OKC CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-01-06 | 2020-01-15
34687 | CCAP licenses_OKC | CE | OKC | OKC | OKC MTC | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE OKC OKC CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34604 | CB Transport - New Router BTR uplink, POY - ELM - Optics | SE | NOR | ELM | Elmwood | CB - Metro Core | POInt | Yes | Yes | CBMC SE NOR ELM Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-01-01 | 2020-01-15
34604 | CB Transport - New Router New Orleans East - ELM - Optics | SE | NOR | ELM | Elmwood | CB - Metro Core | POInt | Yes | Yes | CBMC SE NOR ELM Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-01-01 | 2020-01-15
34690 | CCAP licenses_ELK | CE | OMA | ELK | Elkhorn | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE OMA ELK CCAP Augment POR20 | License | CCAP license | 4 | 2020-01-06 | 2020-01-15
34695 | CCAP licenses_FED | CA | SAN | FED | Federal | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CA SAN FED CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34694 | CCAP licenses_PEO 1 | SW | ARZ | PEO | Peoria | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SW ARZ PEO CCAP Augment POR20 | License | CCAP license | 5 | 2020-01-06 | 2020-01-15
34694 | CCAP licenses_PEO 2 | SW | ARZ | PEO | Peoria | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SW ARZ PEO CCAP Augment POR20 | License | CCAP license | 3 | 2020-01-06 | 2020-01-15
34685 | CCAP licenses_HCK | VA | HRD | HCK | Hickory | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS VA HRD HCK CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34687 | CCAP licenses_ILH | CE | OKC | ILH | Irish Lane | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE OKC ILH CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34974 | CFG SE NOR NOE RC-CFG Deployment POR20 | SE | NOR | NOE | New Orleans East | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SE NOR NOE RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | SN-0228 | 2020-02-07 | New
34690 | CCAP blades_ BVL | CE | NWA | BVL | Bentonville | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE NWA BVL CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-01-06 | 2020-01-15
34974 | CFG SE GCT PNS RK-CFG Deployment POR20 | SE | GCT | PNS | Pensacola with (Insite tower) | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SE GCT PNS RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | SN-0228 | 2020-02-07 | New
34687 | CCAP licenses_SRH | CE | OKC | SRH | Sara Road | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE OKC SRH CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34974 | CFG SE NOR CLR RC-CFG Deployment POR20 | SE | NOR | CLR | Metairie | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SE NOR CLR RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | SN-0228 | 2020-02-07 | New
34623 | CB Transport - New Router Tucson - CHD - Card Add | SW | ARZ | CHD | Chandler | CB - Metro Core | POInt | Yes | Yes | CBMC SW ARZ CHD Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-01 | 2020-01-15
34687 | CCAP licenses_WLH | CE | OKC | WLH | Waterloo | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE OKC WLH CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34685 | CCAP licenses_NRF | VA | HRD | NRF | Norfolk | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS VA HRD NRF CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34841 | CCAP licenses_GNZ | SE | BTR | GNZ | Gonzales | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SE BTR GNZ CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
35175 | NEXUS-RMD-3048-01 | NE | RHD | RMD | Richmond (RI) | Metro Routers | POInt | Yes | Yes | MRTR NE RHD RMD Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 |  | 2020-01-15 | 2020-01-15 | SN-0047 | 2020-02-06 | Chg
34687 | CCAP licenses_NOR | CE | OKC | NOR | Norman | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE OKC NOR CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34975 | CFG NWP AT-CFG GEN GROW PROJECT - MEDIUM | VA | HRD | NWP | Newport News | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA HRD NWP AT-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15
34683 | CCAP licenses_RMD | NE | RHD | RMD | Richmond (RI) | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS NE RHD RMD CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34687 | CCAP licenses_CLA | CE | TUL | CLA | Claremore | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE TUL CLA CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34692 | CCAP licenses_TEN | SW | LAS | TEN | Tenaya | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SW LAS TEN CCAP Augment POR20 | License | CCAP license | 3 | 2020-01-06 | 2020-01-15
34683 | CCAP licenses_GLB | NE | CON | GLB | Glastonbury | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS NE CON GLB CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34695 | CCAP licenses_VST | CA | SAN | VST | Vista | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CA SAN VST CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34601 | CB Transport - New Router Manchester P - PRV - Optics | NE | RHD | PRV | Providence | CB - Metro Core | POInt | Yes | Yes | CBMC NE RHD PRV Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-01-01 | 2020-01-15
34685 | CCAP licenses_GLO | VA | HRD | GLO | Gloucester | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS VA HRD GLO CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34841 | CCAP licenses_LFY | SE | LFY | LFY | Lafayette | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SE LFY LFY CCAP Augment POR20 | License | CCAP license | 5 | 2020-01-06 | 2020-01-15
34683 | CCAP licenses_EXT | NE | RHD | EXT | Exeter | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS NE RHD EXT CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34695 | CCAP licenses_AVJ | CA | ORG | AVJ | Aliso Viejo | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CA ORG AVJ CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34695 | CCAP licenses_PWY | CA | SAN | PWY | Poway | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CA SAN PWY CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34974 | CFG SE NOR CLR BM-CFG Deployment POR20 | SE | NOR | CLR | Metairie | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SE NOR CLR BM-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | SN-0228 | 2020-02-07 | New
34692 | CCAP licenses_BLU | SW | LAS | BLU | Blue Diamond | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SW LAS BLU CCAP Augment POR20 | License | CCAP license | 7 | 2020-01-06 | 2020-01-15
34687 | CCAP licenses_MOO | CE | OKC | MOO | Moore | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE OKC MOO CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34694 | CCAP licenses_FWL | SW | ARZ | FWL | Fowler | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SW ARZ FWL CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34685 | CCAP licenses_PRA | VA | HRD | PRA | Princess Anne | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS VA HRD PRA CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34687 | CCAP licenses_BRD | CE | TUL | BRD | Braden | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE TUL BRD CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34841 | CCAP licenses_PLQ | SE | BTR | PLQ | Plaquemine | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SE BTR PLQ CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34604 | CB Transport - New Router New Orleans East - MCY - Card Add | SE | NOR | MCY | Mid-City | CB - Metro Core | POInt | Yes | Yes | CBMC SE NOR MCY Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-01 | 2020-01-15
34683 | CCAP licenses_RKH | NE | CON | RKH | Rocky Hill | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS NE CON RKH CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34695 | CCAP licenses_OCE | CA | SAN | OCE | Oceanside | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CA SAN OCE CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34690 | CCAP licenses_FAY | CE | NWA | FAY | Fayetteville | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE NWA FAY CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34972 | CFG ELR RK-CBMC GEN GROW PROJECT - SMALL | CE | OKC | ELR | El Reno | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC ELR RK-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-01-01 | 2020-01-15
34841 | CCAP licenses_BTR | SE | BTR | BTR | Baton Rouge | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SE BTR BTR CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34687 | CCAP licenses_ELR | CE | OKC | ELR | El Reno | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE OKC ELR CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34841 | CCAP licenses_DNS | SE | BTR | DNS | Denham Springs | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SE BTR DNS CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34974 | CFG SE NOR MCY HV-CFG Deployment POR20 | SE | NOR | MCY | Mid-City | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SE NOR MCY HV-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | SN-0228 | 2020-02-07 | New
39225 | CCAP licenses_GNS | SE | GAN | GNS | Gainesville | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SE GAN GNS CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34685 | CCAP licenses_MFD | VA | NVA | MFD | Merrifield | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS VA NVA MFD CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
39225 | CCAP licenses_CRV | SE | GCT | CRV | Crestview | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SE GCT CRV CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34694 | CCAP licenses_MSA | SW | ARZ | MSA | Mesa | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SW ARZ MSA CCAP Augment POR20 | License | CCAP license | 5 | 2020-01-06 | 2020-01-15
34972 | CFG VBN RK-CBMC GEN GROW PROJECT - SMALL | CE | NWA | VBN | Van Buren | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE ARK VBN RK-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-01-01 | 2020-01-15
34974 | CFG SE NOR CLR BS-CFG Deployment POR20 - 2 | SE | NOR | CLR | Metairie | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SE NOR CLR BS-CFG Deployment POR20 - 2 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | SN-0228 | 2020-02-07 | New
34690 | CCAP licenses_ONA | CE | OMA | ONA | North (OM) | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE OMA ONA CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
39225 | CCAP licenses_MCN | SE | MGA | MCN | Macon | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SE MGA MCN CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34687 | CCAP licenses_CLH | CE | OKC | CLH | County Line | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE OKC CLH CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34623 | CB Transport - New Router Tucson - TUC - Card Add | SW | ARZ | TUC | Tucson | CB - Metro Core | POInt | Yes | Yes | CBMC SW ARZ TUC Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-01 | 2020-01-15
34687 | CCAP licenses_QNC | CE | TUL | QNC | Quincy | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE TUL QNC CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34687 | CCAP blades_ QNC | CE | TUL | QNC | Quincy | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE TUL QNC CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-01-06 | 2020-01-15
34695 | CCAP licenses_ELC | CA | SAN | ELC | El Cajon | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CA SAN ELC CCAP Augment POR20 | License | CCAP license | 3 | 2020-01-06 | 2020-01-15
34685 | CCAP licenses_GCR | VA | NVA | GCR | Gunston | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS VA NVA GCR CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34604 | CB Transport - New Router New Orleans East - NOE - Optics | SE | NOR | NOE | New Orleans East | CB - Metro Core | POInt | Yes | Yes | CBMC SE NOR NOE Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 3 | 2020-01-01 | 2020-01-15
34695 | CCAP licenses_ORG | CA | ORG | ORG | Orange | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CA ORG ORG CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34690 | CCAP licenses_DBY | CE | KAN | DBY | Derby | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE KAN DBY CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34685 | CCAP licenses_RON | VA | ROA | RON | Roanoke | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS VA ROA RON CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34695 | CCAP licenses_DNP | CA | ORG | DNP | Dana Point | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CA ORG DNP CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34683 | CCAP licenses_PAW | NE | RHD | PAW | Pawtucket | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS NE RHD PAW CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34690 | CCAP licenses_SOU | CE | OMA | SOU | South (OM) | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE OMA SOU CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34972 | CFG BAR RK-CBMC GEN GROW PROJECT - SMALL | CE | TUL | BAR | Broken Arrow | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE TUL BAR RK-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-01-01 | 2020-01-15
34841 | CCAP licenses_MCY | SE | NOR | MCY | Mid-City | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SE NOR MCY CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
39225 | CCAP licenses_DES | SE | GCT | DES | Destin | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SE GCT DES CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34974 | CFG SE NOR NOE BS-CFG Deployment POR20 - 2 | SE | NOR | NOE | New Orleans East | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SE NOR NOE BS-CFG Deployment POR20 - 2 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | SN-0228 | 2020-02-07 | New
34695 | CCAP licenses_CHU | CA | SAN | CHU | Chula Vista | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CA SAN CHU CCAP Augment POR20 | License | CCAP license | 3 | 2020-01-06 | 2020-01-15
34683 | CCAP licenses_PRV | NE | RHD | PRV | Providence | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS NE RHD PRV CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34694 | CCAP licenses_SSC | SW | ARZ | SSC | South Scottsdale | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SW ARZ SSC CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
75647 | Nokia 1830 Add 10 | COR | NAT | AT1 | Atlanta - Digital Realty (Cage SBT.M03) | C4 & C4B Transport Network | POInt | Yes | No | C4B SE-NAT-AT1 Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis | 5 | 2019-11-10 | 2020-01-15 |  | SN-0165 | 2020-02-06 | New
75647 | Nokia 1830 Add 1 | COR | NAT | LA1 | Los Angeles - Equinix (cage 280/610) | C4 & C4B Transport Network | POInt | Yes | No | C4B CA NAT LA1 Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis | 5 | 2019-11-10 | 2020-01-15
75645 | CGN Replacement 1 | SE | BTR | BTR | Baton Rouge | Data Center Capacity | POInt | Yes | No | DTC SE BTR BTR CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2019-11-17 | 2020-01-15
34972 | CFG HRN RK-CFG GEN GROW PROJECT - SMALL | CE | NWA | HRN | Harrison | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE ARK HRN RK-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-01-01 | 2020-01-15
34972 | CFG CLH HV-CFG GEN GROW PROJECT - MEDIUM | CE | OKC | CLH | County Line | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC CLH BS-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15
34972 | CFG CLH BS-CFG GEN GROW PROJECT - LARGE | CE | OKC | CLH | County Line | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC CLH BS-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-01-01 | 2020-01-15
34972 | CFG BLV GN-CFG GEN GROW PROJECT - LARGE | CE | OMA | BLV | Bellevue | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OMA BLV GN-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-01-01 | 2020-01-15
34694 | CCAP licenses_VSA | SW | ARZ | VSA | Vistancia | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SW ARZ VSA CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34695 | CCAP licenses_SAB | CA | SAB | SAB | Santa Barbara | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CA SAB SAB CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34695 | CCAP licenses_RSM | CA | ORG | RSM | Rancho Santa Margarita | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CA ORG RSM CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34690 | CCAP licenses_NWT | CE | KAN | NWT | Newton | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE KAN NWT CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34972 | CFG OLA GN-CFG GEN GROW PROJECT - MEDIUM | CE | KAN | OLA | Iola | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE KAN OLA GN-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15
39225 | CCAP licenses_HLT | SE | MGA | HLT | Holt | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SE MGA HLT CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34694 | CCAP licenses_BEL 1 | SW | ARZ | BEL | Bell | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SW ARZ BEL CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34694 | CCAP licenses_BEL 2 | SW | ARZ | BEL | Bell | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SW ARZ BEL CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34694 | CCAP licenses_BEL 3 | SW | ARZ | BEL | Bell | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SW ARZ BEL CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34694 | CCAP licenses_BEL 4 | SW | ARZ | BEL | Bell | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SW ARZ BEL CCAP Augment POR20 | License | CCAP license | 3 | 2020-01-06 | 2020-01-15
34683 | CCAP licenses_MAN | NE | CON | MAN | Manchester | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS NE CON MAN CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34692 | CCAP licenses_ALI | SW | LAS | ALI | Aliante | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SW LAS ALI CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34623 | CB Transport - New Router Tucson - MCD - Optics | SW | ARZ | MCD | McDowell | CB - Metro Core | POInt | Yes | Yes | CBMC SW ARZ MCD Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-01-01 | 2020-01-15
34841 | CCAP licenses_DST | SE | NOR | DST | Destrehan | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SE NOR DST CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34972 | CFG GAR BD-CFG GEN GROW PROJECT - MEDIUM | CE | TUL | GAR | Garnett | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE TUL GAR BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15
34972 | CFG GAR RK-CFG GEN GROW PROJECT - MEDIUM | CE | TUL | GAR | Garnett | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE TUL GAR BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15
34685 | CCAP licenses_LTF | VA | HRD | LTF | Lightfoot | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS VA HRD LTF CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34974 | CFG SE NOR NOE BM-CFG Deployment POR20 | SE | NOR | NOE | New Orleans East | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SE NOR NOE BM-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | SN-0228 | 2020-02-07 | New
34687 | CCAP licenses_DTN | CE | TUL | DTN | Downtown (TUL) | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE TUL DTN CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34974 | CFG SE NOR CLR BS-CFG Deployment POR20 | SE | NOR | CLR | Metairie | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SE NOR CLR BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | SN-0228 | 2020-02-07 | New
34683 | CCAP licenses_ENF | NE | CON | ENF | Enfield | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS NE CON ENF CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34690 | CCAP blades_ WES | CE | OMA | WES | West (OM) | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE OMA WES CCAP Augment POR20 | Card & Optics | CCAP blade and license | 2 | 2020-01-06 | 2020-01-15
34690 | CCAP licenses_WES | CE | OMA | WES | West (OM) | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE OMA WES CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34971 | CFG FED BS-CFG GEN GROW PROJECT - MEDIUM | CA | SAN | FED | Federal | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA SAN FED BS-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-02 | 2020-01-15
34972 | CFG CHO BS-CFG GEN GROW PROJECT - MEDIUM | CE | OKC | CHO | Choctaw | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC CHO BS-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15
34687 | CCAP licenses_OWA | CE | TUL | OWA | Owasso | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE TUL OWA CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15
34971 | CFG CA SAN FED BS-CFG Augment POR20 | CA | SAN | FED | Federal | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA SAN FED BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | SN-0130 | 2020-02-06 | Chg
34975 | CFG VA NVA FBG BS-CFG Deployment POR20 | VA | NVA | FBG | Fredericksburg | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA NVA FBG BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | SN-0130 | 2020-02-06 | Chg
34975 | CFG VA HRD CHS RC-CFG Deployment POR20 | VA | HRD | CHS | Chesapeake | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA HRD CHS RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | SN-0130 | 2020-02-06 | Chg
34975 | CFG VA HRD NRF AT-CFG Deployment POR20 | VA | HRD | NRF | Norfolk | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA HRD NRF AT-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | SN-0130 | 2020-02-06 | Chg
34975 | CFG VA ROA RON BS-CFG Deployment POR20 | VA | ROA | RON | Roanoke | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA ROA RON BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | SN-0130 | 2020-02-06 | Chg
34976 | CFG NE RHD PTH BD-CFG Deployment POR20 | NE | RHD | PTH | Portsmouth (RI) | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE RHD PTH BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | SN-0130 | 2020-02-06 | Chg
34975 | CFG VA NVA DRA BS-CFG Deployment POR20 | VA | NVA | DRA | Dranesville | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA NVA DRA BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | SN-0130 | 2020-02-06 | Chg
54572 | CFS VA HRD GLO BU-CFS Augment POR20 | VA | HRD | GLO | Gloucester | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD GLO BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-20 |  | SB-0046 | 2020-02-07 | New
34975 | CFG VA HRD NWP AT-CFG Deployment POR20 | VA | HRD | NWP | Newport News | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA HRD NWP AT-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | SN-0130 | 2020-02-06 | Chg
34975 | CFG VA HRD OCN BD-CFG Deployment POR20 | VA | HRD | OCN | Oceana | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA HRD OCN BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | SN-0130 | 2020-02-06 | Chg
34976 | CFG NE CON MAN BD-CFG Deployment POR20 | NE | CON | MAN | Manchester | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE CON MAN BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | SN-0130 | 2020-02-06 | Chg
34975 | CFG VA HRD LTF BS-CFG Deployment POR20 | VA | HRD | LTF | Lightfoot | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA HRD LTF BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | SN-0130 | 2020-02-06 | Chg
34975 | CFG VA HRD JCC BS-CFG Deployment POR20 | VA | HRD | JCC | James City County | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA HRD JCC BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | SN-0130 | 2020-02-06 | Chg
34976 | CFG NE CON ENF BD-CFG Deployment POR20 | NE | CON | ENF | Enfield | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE CON ENF BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | SN-0130 | 2020-02-06 | Chg
34975 | CFG VA NVA MFD BS-CFG Deployment POR20 | VA | NVA | MFD | Merrifield | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA NVA MFD BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | SN-0130 | 2020-02-06 | Chg
34975 | CFG VA HRD PTM BD-CFG Deployment POR20 | VA | HRD | PTM | Portsmouth (VA) | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA HRD PTM BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | SN-0130 | 2020-02-06 | Chg
54572 | CFS VA HRD CHS BU-CFS Augment POR20 | VA | HRD | CHS | Chesapeake | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD CHS BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-20 |  | SB-0046 | 2020-02-07 | New
39251 | BWM_ORG_MSSA_Spectrum Phase II Start | CA | ORG | ORG | Orange | Bandwidth Management | POInt | Yes | No | BWM CA ORG ORG MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-01-27 | 2020-03-13 | SN-0587 | 2020-05-14 | Chg
39251 | BWM_DNP_MSSA_Spectrum Phase II Start | CA | ORG | DNP | Dana Point | Bandwidth Management | POInt | Yes | No | BWM CA ORG DNP MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-01-27 | 2020-03-13 | SN-0587 | 2020-05-14 | Chg
39251 | BWM_AVJ_ MSSA_Spectrum Phase II Start | CA | ORG | AVJ | Aliso Viejo | Bandwidth Management | POInt | Yes | No | BWM CA ORG AVJ MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-01-27 | 2020-03-13 | SN-0587 | 2020-05-14 | Chg
39251 | BWM_PAV_MSSA_Spectrum Phase II Start | CA | ORG | PAV | Palos Verdes | Bandwidth Management | POInt | Yes | No | BWM CA ORG PAV MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-01-27 | 2020-03-13 | SN-0587 | 2020-05-14 | Chg
39251 | BWM_RSM_MSSA_Spectrum Phase II Start | CA | ORG | RSM | Rancho Santa Margarita | Bandwidth Management | POInt | Yes | No | BWM CA ORG RSM MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-01-27 | 2020-03-13 | SN-0587 | 2020-05-14 | Chg
39251 | BWM_IRV_MSSA_Spectrum Phase II Start | CA | ORG | IRV | Irvine | Bandwidth Management | POInt | Yes | No | BWM CA ORG IRV MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-01-27 | 2020-03-13 | SN-0587 | 2020-05-14 | Chg
35175 | MRTR NCS-Growth-PRV-100G Grow | NE | RHD | PRV | Providence | Metro Routers | POInt | Yes | Yes | MRTR NE RHD PRV 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-01-30 | 2020-01-30 | SN-0158 | 2020-02-06 | Chg
35170 | MRTR NCS-Growth-FED-100G Grow | CA | SAN | FED | Federal | Metro Routers | POInt | Yes | Yes | MRTR CA SAN FED 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-01-30 | 2020-01-30 | SN-0158 | 2020-02-06 | Chg
75751 | VOBS NE RHD PRV Voice ACME Decom POR20 | NE | RHD | PRV | Providence | Voice Obsolescence | POInt | Yes | Yes | VOBS NE RHD PRV Voice ACME Decom POR20 | Labor | No Equipment | 1 | 2020-01-06 | 2020-01-31 |  | SB-0029 | 2020-01-21
75751 | VOBS CA ORG RSM Voice ACME Decom POR20 | CA | ORG | RSM | Rancho Santa Margarita | Voice Obsolescence | POInt | Yes | Yes | VOBS CA ORG RSM Voice ACME Decom POR20 | Labor | No Equipment | 1 | 2020-01-06 | 2020-01-31 |  | SB-0029 | 2020-01-21
34948 | MTRN-CLR- T5-01 | SE | NOR | CLR | Metairie | Metro Transport | POInt | Yes | Yes | MTRN SE NOR CLR T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-01 | 2020-02-01 | 2020-03-01 | SN-0154 | 2020-02-06 | Chg
34970 | CFG SW ARZ SSC HV-CFG Deployment POR20 | SW | ARZ | SSC | South Scottsdale | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ SSC HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-02-01 |  | SB-0023 | 2020-01-30 | New
34947 | MTRN-HEN- T5-03 | SW | LAS | HEN | Henderson | Metro Transport | POInt | Yes | Yes | MTRN SW LAS HEN T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-20 | 2020-02-01 | 2020-03-31 | SN-0154 | 2020-02-06 | Chg
34687 | CCAP licenses_DSH | CE | OKC | DSH | Far South (aka Deep South) | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE OKC DSH CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-02-01
34943 | MTRN-MCD- T5-04 | SW | ARZ | MCD | McDowell | Metro Transport | POInt | Yes | Yes | MTRN SW ARZ MCD T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 4 | 2020-01-20 | 2020-02-01 |  | SN-0154 | 2020-02-06
54571 | CFS SE BTR ERW BU-CFS Augment POR20 | SE | BTR | ERW | Erwinville | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE BTR ERW BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-02-01 |  | SB-0023 | 2020-01-30 | New
34948 | MTRN-GNS- T5-01 | SE | GAN | GNS | Gainesville | Metro Transport | POInt | Yes | Yes | MTRN SE GAN GNS T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-01 | 2020-02-01 | 2020-02-01 | SN-0053 | 2020-02-06 | Chg
34947 | MTRN-HEN- T5-01 | SW | LAS | HEN | Henderson | Metro Transport | POInt | Yes | Yes | MTRN SW LAS HEN T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-20 | 2020-02-01 | 2020-03-31 | SN-0154 | 2020-02-06 | Chg
34947 | MTRN-HEN- T5-04 | SW | LAS | HEN | Henderson | Metro Transport | POInt | Yes | Yes | MTRN SW LAS HEN T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-20 | 2020-02-01 | 2020-03-31 | SN-0154 | 2020-02-06 | Chg
34604 | CB Transport - New Router Donaldsonville - BTR - Optics | SE | BTR | BTR | Baton Rouge | CB - Metro Core | POInt | Yes | Yes | CBMC SE BTR BTR Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-01-01 | 2020-02-01
34685 | CCAP blades_ PRA | VA | HRD | PRA | Princess Anne | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS VA HRD PRA CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-01-06 | 2020-02-01
34948 | MTRN-OCL- T5-01 | SE | GAN | OCL | Ocala | Metro Transport | POInt | Yes | Yes | MTRN SE GAN OCL T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-01 | 2020-02-01 | 2020-02-01 | SN-0053 | 2020-02-06 | Chg
34970 | CFG SW LAS OSB BS-CFG Deployment POR20 | SW | LAS | OSB | Oso Blanca | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW LAS OSB BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-02-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE GCT PNS SC-CFS Augment POR20 | SE | GCT | PNS | Pensacola with (Insite tower) | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE GCT PNS SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-02-01 |  | SB-0023 | 2020-01-30 | New
34687 | CCAP licenses_SOH | CE | OKC | SOH | South (OKC) | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE OKC SOH CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-02-01
34970 | CFG SW ARZ CHD HV-CFG Deployment POR20 | SW | ARZ | CHD | Chandler | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ CHD HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-02-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE NOR STB SC-CFS Augment POR20 | SE | NOR | STB | St. Bernard | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE NOR STB SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-02-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE BTR BTR BD-CFS Augment POR20 | SE | BTR | BTR | Baton Rouge | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE BTR BTR BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-02-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE NOR ALG SC-CFS Augment POR20 | SE | NOR | ALG | Algiers | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE NOR ALG SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-02-01 |  | SB-0023 | 2020-01-30 | New
34947 | MTRN-TEN- T5-01 | SW | LAS | TEN | Tenaya | Metro Transport | POInt | Yes | Yes | MTRN SW LAS TEN T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-20 | 2020-02-01 | 2020-02-01 | SN-0154 | 2020-02-06 | Chg
34947 | MTRN-TEN- T5-04 | SW | LAS | TEN | Tenaya | Metro Transport | POInt | Yes | Yes | MTRN SW LAS TEN T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-20 | 2020-02-01 | 2020-02-01 | SN-0154 | 2020-02-06 | Chg
34947 | MTRN-TEN- T5-03 | SW | LAS | TEN | Tenaya | Metro Transport | POInt | Yes | Yes | MTRN SW LAS TEN T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-20 | 2020-02-01 | 2020-02-01 | SN-0154 | 2020-02-06 | Chg
34604 | CB Transport - New Router St Martinville - LFY - Optics | SE | LFY | LFY | Lafayette | CB - Metro Core | POInt | Yes | No | CBMC SE LFY LFY Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-01-01 | 2020-02-01 |  | SN-0419 | 2020-04-02 | Chg
75830 | Market Segmentation | COR | COR | ATL | Atlanta | Voice Network Upgrades | POInt | Yes | No | VNU CO -CO ATL Metaswitch Lifecycle Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-02 | 2020-02-14 | 2020-02-14 | SB-0047 | 2020-01-31 | New
75751 | VOBS SE NOR ELM Voice ACME Decom POR20 | SE | NOR | ELM | Elmwood | Voice Obsolescence | POInt | Yes | No | VOBS SE NOR ELM Voice ACME Decom POR20 | Labor | No Equipment | 1 | 2020-01-20 | 2020-02-14 |  | SB-0029 | 2020-01-21
44923 | MTCH CA SAN CHU Grow Fiber Bay Replace Augment POR19 | CA | SAN | CHU | Chula Vista | MTC HE - Hub Signaling | POInt | Yes | No | MTCH CA SAN CHU Grow Fiber Bay Replace Augment POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-02-15 | 2020-03-31 | SN-0188 | 2020-01-21
75703 | MTCS CE KAN WIC Channel Growth Deployment POR20 | CE | KAN | WIC | Wichita | MTC - Servers and Software | POInt | Yes | No | MTCS CE KAN WIC Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
75703 | MTCS NE CLE CLV Remote Video Monitoring Expansion Augment POR20 | NE | CLE | CLV | Cleveland | MTC - Servers and Software | POInt | Yes | No | MTCS NE CLE CLV Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
75703 | MTCS SE GCT PNS Channel Growth Deployment POR20 | SE | GCT | PNS | Pensacola with (Insite tower) | MTC - Servers and Software | POInt | Yes | No | MTCS SE GCT PNS Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
44924 | MTCH SW LAS HEN Replace HDrx Decom POR19 | SW | LAS | HEN | Henderson | MTC HE - Hub Signaling | POInt | Yes | No | MTCH SW LAS HEN Replace HDrx Decom POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-02-15 | 2020-03-15 | SN-0188 | 2020-01-21
75703 | MTCS CA SAB SAB Channel Growth Deployment POR20 | CA | SAB | SAB | Santa Barbara | MTC - Servers and Software | POInt | Yes | No | MTCS CA SAB SAB Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
75703 | MTCS CE ARK NWA Remote Video Monitoring Expansion Augment POR20 | CE | NWA | NWA | Johnson | MTC - Servers and Software | POInt | Yes | No | MTCS CE NWA NWA Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
44924 | MTCH SW LAS BLU Replace HDrx Decom POR19 | SW | LAS | BLU | Blue Diamond | MTC HE - Hub Signaling | POInt | Yes | No | MTCH SW LAS BLU Replace HDrx Decom POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-02-15 | 2020-03-15 | SN-0188 | 2020-01-21
75703 | MTCS CA ORG RSM Channel Growth Deployment POR20 | CA | ORG | RSM | Rancho Santa Margarita | MTC - Servers and Software | POInt | Yes | No | MTCS CA ORG RSM Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
75703 | MTCS CE OKC OKC Remote Video Monitoring Expansion Augment POR20 | CE | OKC | OKC | OKC MTC | MTC - Servers and Software | POInt | Yes | No | MTCS CE OKC OKC Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
75703 | MTCS SW ARZ CHD Remote Video Monitoring Expansion Augment POR20 | SW | ARZ | CHD | Chandler | MTC - Servers and Software | POInt | Yes | No | MTCS SW ARZ CHD Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
75703 | MTCS CE OKC OKC Channel Growth Deployment POR20 | CE | OKC | OKC | OKC MTC | MTC - Servers and Software | POInt | Yes | No | MTCS CE OKC OKC Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
75703 | MTCS NE RHD WWK Channel Growth Deployment POR20 | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | MTC - Servers and Software | POInt | Yes | No | MTCS NE RHD WWK Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
75703 | MTCS SW ARZ CHD Channel Growth Deployment POR20 | SW | ARZ | CHD | Chandler | MTC - Servers and Software | POInt | Yes | No | MTCS SW ARZ CHD Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
75703 | MTCS SW LAS HEN Channel Growth Deployment POR20 | SW | LAS | HEN | Henderson | MTC - Servers and Software | POInt | Yes | No | MTCS SW LAS HEN Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
75703 | MTCS CA SAN ELC Remote Video Monitoring Expansion Augment POR20 | CA | SAN | ELC | El Cajon | MTC - Servers and Software | POInt | Yes | No | MTCS CA SAN ELC Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
44923 | MTCH CA SAN ESC Grow Fiber Bay Replace Augment POR19 | CA | SAN | ESC | Escondido | MTC HE - Hub Signaling | POInt | Yes | No | MTCH CA SAN ESC Grow Fiber Bay Replace Augment POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-02-15 | 2020-03-31 | SN-0188 | 2020-01-21
75703 | MTCS CE KAN WIC Remote Video Monitoring Expansion Augment POR20 | CE | KAN | WIC | Wichita | MTC - Servers and Software | POInt | Yes | No | MTCS CE KAN WIC Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
75703 | MTCS NE RHD WWK Remote Video Monitoring Expansion Augment POR20 | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | MTC - Servers and Software | POInt | Yes | No | MTCS NE RHD WWK Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
44927 | MTCH VA NVA DRA Replace RF Rebuild Decom POR19 | VA | NVA | DRA | Dranesville | MTC HE - Hub Signaling | POInt | Yes | No | MTCH VA NVA DRA Replace RF Rebuild Decom POR19 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-24 | 2020-02-15 | 2020-03-15 | SN-0188 | 2020-01-21
75794 | VEO Automation - SD WAN Support Tools | COR | COR | ATL | Atlanta | Voice Monitoring and Analytics | POInt | Yes | No | VMA CO -CO ATL Workflow and portfolio implementation Deployment POR20 | Labor | Tool dev for SD WAN Solution support | 2 | 2020-01-25 | 2020-02-15 |  | SB-0013 | 2020-01-30 | Chg
75703 | MTCS VA HRD VBC Channel Growth Deployment POR20 | VA | HRD | VBC | Virginia Beach | MTC - Servers and Software | POInt | Yes | No | MTCS VA HRD VBC Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
44923 | MTCH CA SAN FED Grow Fiber Management Augment POR19 | CA | SAN | FED | Federal | MTC HE - Hub Signaling | POInt | Yes | No | MTCH CA SAN FED Grow Fiber Management Augment POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-02-15 | 2020-03-31 | SN-0188 | 2020-01-21
44927 | MTCH VA NVA MFD Replace Tektronix Upgrade Decom POR19 | VA | NVA | MFD | Merrifield | MTC HE - Hub Signaling | POInt | Yes | No | MTCH VA NVA MFD Replace Tektronix Upgrade Decom POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-02-15 | 2020-03-31 | SN-0188 | 2020-01-21
75699 | MTCS COR COR ATL Lab Equipment Deployment POR20 | COR | COR | ATL | Atlanta | MTC - Servers and Software | POInt | Yes | No | MTCS CO COR ATL Lab Equipment Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-09-15
75703 | MTCS SE GCT PNS Remote Video Monitoring Expansion Augment POR20 | SE | GCT | PNS | Pensacola with (Insite tower) | MTC - Servers and Software | POInt | Yes | No | MTCS SE GCT PNS Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
75663 | V2B COR COR ATL VQ Lab Augment POR20 | COR | COR | ATL | Atlanta | V2B | POInt | Yes | No | V2B COR COR ATL VQ Lab Augment POR20 | Labor | Lab | 1 | 2020-01-06 | 2020-02-15 | 2020-12-15
75703 | MTCS SW LAS HEN Remote Video Monitoring Expansion Augment POR20 | SW | LAS | HEN | Henderson | MTC - Servers and Software | POInt | Yes | No | MTCS SW LAS HEN Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
75703 | MTCS VA NVA MFD Remote Video Monitoring Expansion Augment POR20 | VA | NVA | MFD | Merrifield | MTC - Servers and Software | POInt | Yes | No | MTCS VA NVA MFD Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
75703 | MTCS CE OMA OMM Remote Video Monitoring Expansion Augment POR20 | CE | OMA | OMM | Omaha | MTC - Servers and Software | POInt | Yes | No | MTCS CE OMA OMM Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
75703 | MTCS CA SAN ELC Channel Growth Deployment POR20 | CA | SAN | ELC | El Cajon | MTC - Servers and Software | POInt | Yes | No | MTCS CA SAN ELC Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
75792 | Monitoring and Analytics - Network Analytics | COR | COR | ATL | Atlanta | Voice Monitoring and Analytics | POInt | Yes | No | VMA CO -CO ATL Proactive Alerting Alignment POR20 | Labor | Data collection for Analytics of Voice netwk | 1 | 2020-01-25 | 2020-02-15 |  | SB-0013 | 2020-01-30 | Chg
75703 | MTCS SE GLA ELM Channel Growth Deployment POR20 | SE | NOR | ELM | Elmwood | MTC - Servers and Software | POInt | Yes | No | MTCS SE NOR ELM Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
75699 | MTCS SW ARZ CHD PDC Tear Down Deployment POR20 | SW | ARZ | CHD | Chandler | MTC - Servers and Software | POInt | Yes | No | MTCS SW ARZ CHD PDC Tear Down Deployment POR20 | Labor | Power down, unrack, scrap, and uncable racks | 1 | 2020-01-06 | 2020-02-15 | 2020-10-15
75703 | MTCS SE GAN GNS Remote Video Monitoring Expansion Augment POR20 | SE | GAN | GNS | Gainesville | MTC - Servers and Software | POInt | Yes | No | MTCS SE GAN GNS Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
75699 | MTCS CE KAN WIC PDC Tear Down Deployment POR20 | CE | KAN | WIC | Wichita | MTC - Servers and Software | POInt | Yes | No | MTCS CE KAN WIC PDC Tear Down Deployment POR20 | Labor | Power down, unrack, scrap, and uncable racks | 1 | 2020-01-06 | 2020-02-15 | 2020-10-15
75703 | MTCS CA ORG RSM Remote Video Monitoring Expansion Augment POR20 | CA | ORG | RSM | Rancho Santa Margarita | MTC - Servers and Software | POInt | Yes | No | MTCS CA ORG RSM Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
75699 | MTCS VA HRD VBC PDC Tear Down Deployment POR20 | VA | HRD | VBC | Virginia Beach | MTC - Servers and Software | POInt | Yes | No | MTCS VA HRD VBC PDC Tear Down Deployment POR20 | Labor | Power down, unrack, scrap, and uncable racks | 1 | 2020-01-06 | 2020-02-15 | 2020-10-15
75703 | MTCS CE OKC TUL Channel Growth Deployment POR20 | CE | TUL | TUL | Tulsa | MTC - Servers and Software | POInt | Yes | No | MTCS CE TUL TUL Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
75703 | MTCS VA HRD VBC Remote Video Monitoring Expansion Augment POR20 | VA | HRD | VBC | Virginia Beach | MTC - Servers and Software | POInt | Yes | No | MTCS VA HRD VBC Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
75703 | MTCS VA ROA RON Remote Video Monitoring Expansion Augment POR20 | VA | ROA | RON | Roanoke | MTC - Servers and Software | POInt | Yes | No | MTCS VA ROA RON Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
75703 | MTCS SE GLA BTR Remote Video Monitoring Expansion Augment POR20 | SE | BTR | BTR | Baton Rouge | MTC - Servers and Software | POInt | Yes | No | MTCS SE BTR BTR Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
75703 | MTCS VA NVA MFD Channel Growth Deployment POR20 | VA | NVA | MFD | Merrifield | MTC - Servers and Software | POInt | Yes | No | MTCS VA NVA MFD Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
75703 | MTCS SE MGA MCN Channel Growth Deployment POR20 | SE | MGA | MCN | Macon | MTC - Servers and Software | POInt | Yes | No | MTCS SE MGA MCN Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
44875 | MTCH SE GLA MCY Fiber Management Augment POR19 | SE | NOR | MCY | Mid-City | MTC HE - Hub Signaling | POInt | Yes | No | MTCH SE GLA MCY Fiber Management Augment POR19 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-30 | 2020-02-15 | 2020-03-31 | SN-0188 | 2020-01-21
75703 | MTCS SE GLA ELM Remote Video Monitoring Expansion Augment POR20 | SE | NOR | ELM | Elmwood | MTC - Servers and Software | POInt | Yes | No | MTCS SE NOR ELM Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
75703 | MTCS NE CON MAN Remote Video Monitoring Expansion Augment POR20 | NE | CON | MAN | Manchester | MTC - Servers and Software | POInt | Yes | No | MTCS NE CON MAN Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
75703 | MTCS CA SAB SAB Remote Video Monitoring Expansion Augment POR20 | CA | SAB | SAB | Santa Barbara | MTC - Servers and Software | POInt | Yes | No | MTCS CA SAB SAB Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
75703 | MTCS SE MGA MCN Remote Video Monitoring Expansion Augment POR20 | SE | MGA | MCN | Macon | MTC - Servers and Software | POInt | Yes | No | MTCS SE MGA MCN Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
75699 | MTCS SE GLA BTR PDC Tear Down Deployment POR20 | SE | BTR | BTR | Baton Rouge | MTC - Servers and Software | POInt | Yes | No | MTCS SE BTR BTR PDC Tear Down Deployment POR20 | Labor | Power down, unrack, scrap, and uncable racks | 1 | 2020-01-06 | 2020-02-15 | 2020-10-15
75703 | MTCS CE OKC TUL Remote Video Monitoring Expansion Augment POR20 | CE | TUL | TUL | Tulsa | MTC - Servers and Software | POInt | Yes | No | MTCS CE TUL TUL Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
75703 | MTCS CE ARK NWA Channel Growth Deployment POR20 | CE | NWA | NWA | Johnson | MTC - Servers and Software | POInt | Yes | No | MTCS CE NWA NWA Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
34972 | CFG BLV RK-CFG GEN GROW PROJECT - MEDIUM | CE | OMA | BLV | Bellevue | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OMA BLV GN-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-06 | 2020-02-15
34943 | MTRN-TUC- T5-01 | SW | ARZ | TUC | Tucson | Metro Transport | POInt | Yes | Yes | MTRN SW ARZ TUC T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-02-15 | 2020-06-15 | SN-0154 | 2020-02-06 | Chg
59522 | R PHY_CCAP_MCD_RPHY Unbundled Solution V2_43845 | SW | ARZ | MCD | McDowell | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ MCD RPHY CCAP Deployment POR20 | License | License Activation | 4 | 2020-01-15 | 2020-02-15 |  | SN-0097 | 2020-02-06 | Chg
34623 | CB Transport - New Router Bell - MCD - Optics | SW | ARZ | MCD | McDowell | CB - Metro Core | POInt | Yes | Yes | CBMC SW ARZ MCD Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-01-01 | 2020-02-15
34972 | CFG NWA RK-CFG GEN GROW PROJECT - MEDIUM | CE | NWA | NWA | Johnson | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE ARK NWA BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-06 | 2020-02-15
34972 | CFG NWA BD-CFG GEN GROW PROJECT - MEDIUM | CE | NWA | NWA | Johnson | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE ARK NWA BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-06 | 2020-02-15
44923 | MTCH CA SAN ELC Grow Fiber Management Augment POR19 | CA | SAN | ELC | El Cajon | MTC HE - Hub Signaling | POInt | Yes | No | MTCH CA SAN ELC Grow Fiber Management Augment POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-02-15 | 2020-03-31 | SN-0188 | 2020-01-21
75703 | MTCS CE OMA OMM Channel Growth Deployment POR20 | CE | OMA | OMM | Omaha | MTC - Servers and Software | POInt | Yes | No | MTCS CE OMA OMM Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
75703 | MTCS SE GLA BTR Channel Growth Deployment POR20 | SE | BTR | BTR | Baton Rouge | MTC - Servers and Software | POInt | Yes | No | MTCS SE BTR BTR Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
44923 | MTCH CA SAN VST Grow Fiber Bay Replace Augment POR19 | CA | SAN | VST | Vista | MTC HE - Hub Signaling | POInt | Yes | No | MTCH CA SAN VST Grow Fiber Bay Replace Augment POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-02-15 | 2020-03-31 | SN-0188 | 2020-01-21
44924 | MTCH SW LAS TEN Replace HDrx Decom POR19 | SW | LAS | TEN | Tenaya | MTC HE - Hub Signaling | POInt | Yes | No | MTCH SW LAS TEN Replace HDrx Decom POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-02-15 | 2020-03-15 | SN-0188 | 2020-01-21
75703 | MTCS NE CLE CLV Channel Growth Deployment POR20 | NE | CLE | CLV | Cleveland | MTC - Servers and Software | POInt | Yes | No | MTCS NE CLE CLV Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
75703 | MTCS VA ROA RON Channel Growth Deployment POR20 | VA | ROA | RON | Roanoke | MTC - Servers and Software | POInt | Yes | No | MTCS VA ROA RON Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
44876 | MTCH CE OKC OKC Fiber Management Augment POR19 | CE | OKC | OKC | OKC MTC | MTC HE - Hub Signaling | POInt | Yes | No | MTCH CE OKC OKC Fiber Management Augment POR19 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-03-15 | SN-0188 | 2020-01-21
75663 | V2B COR COR ATL Professional Services Augment POR20 | COR | COR | ATL | Atlanta | V2B | POInt | Yes | No | V2B COR COR ATL Professional Services Augment POR20 | Labor | Prof Services | 1 | 2020-01-06 | 2020-02-15 | 2020-12-15
44923 | MTCH CA ORG RSM Rack Consolidation Augment POR19 | CA | ORG | RSM | Rancho Santa Margarita | MTC HE - Hub Signaling | POInt | Yes | No | MTCH CA ORG RSM Rack Consolidation Augment POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-02-15 | 2020-03-31 | SN-0188 | 2020-01-21
75699 | MTCS NE CON MAN Channel Growth Deployment POR20 | NE | CON | MAN | Manchester | MTC - Servers and Software | POInt | Yes | No | MTCS NE CON MAN Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
75703 | MTCS SE GAN GNS Channel Growth Deployment POR20 | SE | GAN | GNS | Gainesville | MTC - Servers and Software | POInt | Yes | No | MTCS SE GAN GNS Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15
59522 | R PHY_CCAP_FWL_RPHY Unbundled Solution V2_43845 | SW | ARZ | FWL | Fowler | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ FWL RPHY CCAP Deployment POR20 | License | License Activation | 35 | 2020-01-15 | 2020-02-15 |  | SN-0097 | 2020-02-06 | Chg
59522 | R PHY_CCAP_MSA_RPHY Unbundled Solution V2_43845 | SW | ARZ | MSA | Mesa | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ MSA RPHY CCAP Deployment POR20 | License | License Activation | 36 | 2020-01-15 | 2020-02-15 |  | SN-0060 | 2020-02-06 | New
34623 | CB Transport - New Router Bell, Peoria - CHD - Card Add | SW | ARZ | CHD | Chandler | CB - Metro Core | POInt | Yes | Yes | CBMC SW ARZ CHD Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-15 | 2020-02-15
34975 | CFG OCN BD-CFG NEWBDCBB_6_PANEL | VA | HRD | OCN | Oceana | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA HRD OCN BD-CFG Deployment POR20 | Critical Facilities | NEWBDCBB_6_PANEL | 1 | 2020-01-01 | 2020-02-15
34623 | CB Transport - New Router Bell - BEL - Optics | SW | ARZ | BEL | Bell | CB - Metro Core | POInt | Yes | Yes | CBMC SW ARZ BEL Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-01-15 | 2020-02-15
34601 | CB Transport - New Router Richmond - RMD - Optics | NE | RHD | RMD | Richmond (RI) | CB - Metro Core | POInt | Yes | Yes | CBMC NE RHD RMD Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 3 | 2020-01-15 | 2020-02-15
34601 | CB Transport - New Router Richmond - PRV - Optics | NE | RHD | PRV | Providence | CB - Metro Core | POInt | Yes | Yes | CBMC NE RHD PRV Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-01-15 | 2020-02-15 |  | SN-0309 | 2020-03-02 | Chg
59522 | R PHY_CCAP_TEN_RPHY Unbundled Solution V2_43845 | SW | LAS | TEN | Tenaya | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 6 | 2020-01-15 | 2020-02-15 |  | SN-0060 | 2020-02-06 | New
59522 | R PHY_CCAP_PNL_RPHY Unbundled Solution V2_43845 | SW | ARZ | PNL | Pinal County | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ PNL RPHY CCAP Deployment POR20 | License | License Activation | 3 | 2020-01-15 | 2020-02-15 |  | SN-0097 | 2020-02-06 | Chg
54569 | CFS CTA BM-CFS CF CONSTRUCTION PROJECT - MEDIUM | CA | ORG | CTA | Cota | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CA ORG CTA BM-CFS Augment POR20 | Critical Facilities | CF CONSTRUCTION PROJECT - MEDIUM | 1 | 2020-01-15 | 2020-02-15 |  | SB-0010 | 2020-01-30 | Chg
34945 | MTRN-TOP- T5-01 | CE | KAN | TOP | Topeka | Metro Transport | POInt | Yes | Yes | MTRN CE KAN TOP T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-02-15 | 2020-02-28 | SN-0154 | 2020-02-06 | Chg
59522 | R PHY_CCAP_ALI_RPHY Unbundled Solution V2_43845 | SW | LAS | ALI | Aliante | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS ALI RPHY CCAP Deployment POR20 | License | License Activation | 3 | 2020-01-15 | 2020-02-15 |  | SN-0097 | 2020-02-06 | Chg
34604 | CB Transport - New Router Lafayette - BTR - Optics | SE | BTR | BTR | Baton Rouge | CB - Metro Core | POInt | Yes | Yes | CBMC SE BTR BTR Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-01-01 | 2020-02-15 |  | SN-0309 | 2020-03-02 | Chg
34604 | CB Transport - New Router North - BTR - Optics | SE | BTR | BTR | Baton Rouge | CB - Metro Core | POInt | Yes | Yes | CBMC SE BTR BTR Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-01-01 | 2020-02-15 |  | SN-0309 | 2020-03-02 | Chg
34604 | CB Transport - New Router South - BTR - Optics | SE | BTR | BTR | Baton Rouge | CB - Metro Core | POInt | Yes | Yes | CBMC SE BTR BTR Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-01-01 | 2020-02-15 |  | SN-0309 | 2020-03-02 | Chg
34604 | CB Transport - New Router St Charles - BTR - Optics | SE | BTR | BTR | Baton Rouge | CB - Metro Core | POInt | Yes | Yes | CBMC SE BTR BTR Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-01-01 | 2020-02-15 |  | SN-0309 | 2020-03-02 | Chg
59522 | R PHY_CCAP_PEO_RPHY Unbundled Solution V2_43845 | SW | ARZ | PEO | Peoria | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ PEO RPHY CCAP Deployment POR20 | License | License Activation | 15 | 2020-01-15 | 2020-02-15 |  | SN-0060 | 2020-02-06 | New
59522 | R PHY_CCAP_TUC_RPHY Unbundled Solution V2_43845 | SW | ARZ | TUC | Tucson | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ TUC RPHY CCAP Deployment POR20 | License | License Activation | 8 | 2020-01-15 | 2020-02-15 |  | SN-0097 | 2020-02-06 | Chg
34975 | CFG RON BS-CFG LARGE_2V_BATTSTRING | VA | ROA | RON | Roanoke | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA ROA RON BS-CFG Deployment POR20 | Critical Facilities | LARGE_2V_BATTSTRING | 1 | 2020-01-01 | 2020-02-15
59522 | R PHY_CCAP_HEN_RPHY Unbundled Solution V2_43845 | SW | LAS | HEN | Henderson | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS HEN RPHY CCAP Deployment POR20 | License | License Activation | 80 | 2020-01-15 | 2020-02-15 |  | SN-0060 | 2020-02-06 | New
34608 | NRFLVAJT8AW-A701JT7950-100G CARD | VA | HRD | NRF | Norfolk | CB - Metro Core | POInt | Yes | Yes | CBMC VA HRD NRF 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-01-15 | 2020-02-15
34604 | BRX02-SFM | SE | BTR | BTR | Baton Rouge | CB - Metro Core | POInt | Yes | Yes | CBMC SE BTR BTR SFM-7950 XRS-20 Augment POR20 | Card & Optics | Nokia SFM-7950 XRS-20/20e SFM2-SA | 16 | 2020-01-15 | 2020-02-15 |  | SN-0419 | 2020-04-02 | Chg
59522 | R PHY_CCAP_CHD_RPHY Unbundled Solution V2_43845 | SW | ARZ | CHD | Chandler | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ CHD RPHY CCAP Deployment POR20 | License | License Activation | 3 | 2020-01-15 | 2020-02-15 |  | SN-0097 | 2020-02-06 | Chg
34972 | CFG NOR BD-CFG GEN GROW PROJECT - MEDIUM | CE | OKC | NOR | Norman | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC NOR BS-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-06 | 2020-02-15
34608 | VRBHVAZD8BW-A701JT7950-100G CARD | VA | HRD | VBC | Virginia Beach | CB - Metro Core | POInt | Yes | Yes | CBMC VA HRD VBC 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-01-15 | 2020-02-15
34608 | FLCHVA1948W-100G CARD | VA | NVA | MFD | Merrifield | CB - Metro Core | POInt | Yes | Yes | CBMC VA NVA MFD 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-01-15 | 2020-02-15
35011 | MTRN-FLK- T5-01 | VA | NVA | FLK | Fair Lakes | Metro Transport | POInt | Yes | Yes | MTRN VA NVA FLK T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-02-15 | 2020-06-15 | SN-0154 | 2020-02-06 | Chg
34608 | FRFYVA0648W-100G CARD | VA | NVA | FLK | Fair Lakes | CB - Metro Core | POInt | Yes | Yes | CBMC VA NVA FLK 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-01-15 | 2020-02-15
59745 | R PHY_CCAP_OCE_RPHY Unbundled Solution V2_43845 | CA | SAN | OCE | Oceanside | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN OCE RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-01-15 | 2020-02-15 |  | SN-0097 | 2020-02-06 | Chg
35011 | MTRN-MFD- T5-01 | VA | NVA | MFD | Merrifield | Metro Transport | POInt | Yes | Yes | MTRN VA NVA MFD T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-02-15 | 2020-03-15 | SN-0154 | 2020-02-06 | Chg
59522 | R PHY_CCAP_VLY_RPHY Unbundled Solution V2_43845 | SW | LAS | VLY | Valley | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS VLY RPHY CCAP Deployment POR20 | License | License Activation | 7 | 2020-01-15 | 2020-02-15 |  | SN-0097 | 2020-02-06 | Chg
34604 | HRHNLA061BW-100G CARD | SE | NOR | ELM | Elmwood | CB - Metro Core | POInt | Yes | Yes | CBMC SE NOR ELM 100G CARD Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-01-15 | 2020-02-15 |  | SN-0246 | 2020-02-24 | Chg
34947 | MTRN-VLY- T5-02 | SW | LAS | VLY | Valley | Metro Transport | POInt | Yes | Yes | MTRN SW LAS VLY T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-02-15 | 2020-03-31 | SN-0154 | 2020-02-06 | Chg
59522 | R PHY_CCAP_NSC_RPHY Unbundled Solution V2_43845 | SW | ARZ | NSC | North Scottsdale | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ NSC RPHY CCAP Deployment POR20 | License | License Activation | 3 | 2020-01-15 | 2020-02-15 |  | SN-0097 | 2020-02-06 | Chg
59522 | R PHY_CCAP_BUK_RPHY Unbundled Solution V2_43845 | SW | ARZ | BUK | Buckeye | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ BUK RPHY CCAP Deployment POR20 | License | License Activation | 2 | 2020-01-15 | 2020-02-15 |  | SN-0097 | 2020-02-06 | Chg
59522 | R PHY_CCAP_ERN_RPHY Unbundled Solution V2_43845 | SW | LAS | ERN | Ernest May | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | License | License Activation | 9 | 2020-01-15 | 2020-02-15 |  | SN-0097 | 2020-02-06 | Chg
34601 | CB Transport - New Router Richmond - WWK - Optics | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | CB - Metro Core | POInt | Yes | Yes | CBMC NE RHD WWK Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-01-01 | 2020-02-15
34604 | HRHNLA061BW-SFM | SE | NOR | ELM | Elmwood | CB - Metro Core | POInt | Yes | Yes | CBMC SE NOR ELM Nokia SFM - 7950 Augment POR20 | Card & Optics | Nokia SFM-7950 XRS-20/20e SFM2-SA | 8 | 2020-01-15 | 2020-02-15 |  | SN-0246 | 2020-02-24 | Chg
59522 | R PHY_CCAP_BLU_RPHY Unbundled Solution V2_43845 | SW | LAS | BLU | Blue Diamond | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS BLU RPHY CCAP Deployment POR20 | License | License Activation | 20 | 2020-01-15 | 2020-02-15 |  | SN-0060 | 2020-02-06 | New
75187 | R PHY_CCAP_TUL_RPHY Unbundled Solution V2_43845 | CE | TUL | TUL | Tulsa | R PHY | POInt | Yes | Yes | R PHY CE TUL TUL RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 4 | 2020-01-15 | 2020-02-15 |  | SN-0097 | 2020-02-06 | Chg
34622 | CB Transport - New Router El Cajon - ELC - Optics | CA | SAN | ELC | El Cajon | CB - Metro Core | POInt | Yes | Yes | CBMC CA SAN ELC Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-01-15 | 2020-02-15
34622 | CB Transport - New Router El Cajon - FED - Optics | CA | SAN | FED | Federal | CB - Metro Core | POInt | Yes | Yes | CBMC CA SAN FED Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-01-15 | 2020-02-15
59522 | R PHY_CCAP_SSC_RPHY Unbundled Solution V2_43845 | SW | ARZ | SSC | South Scottsdale | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ SSC RPHY CCAP Deployment POR20 | License | License Activation | 26 | 2020-01-15 | 2020-02-15 |  | SN-0097 | 2020-02-06 | Chg
54572 | CFS VA HRD VBC DC-CFS Augment POR20 | VA | HRD | VBC | Virginia Beach | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD VBC DC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-17 |  | SB-0049 | 2020-02-28 | New
54572 | CFS VA HRD NKT DC-CFS Augment POR20 | VA | HRD | NKT | New Kent | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD NKT DC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | SB-0049 | 2020-02-28 | New
34970 | CFG SW ARZ DGL RK-CFG Deployment POR20 | SW | ARZ | DGL | Douglas | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ DGL RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | SN-0228 | 2020-02-07 | New
34975 | CFG VA HRD NRF AC-CFG Deployment POR20 | VA | HRD | NRF | Norfolk | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA HRD NRF AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | SN-0262 | 2020-02-28
54572 | CFS VA HRD JEF DC-CFS Augment POR20 | VA | HRD | JEF | Jefferson Ave | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD JEF DC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | SB-0049 | 2020-02-28 | New
34971 | CFG CA ORG IRV BS-CFG Deployment POR20 | CA | ORG | IRV | Irvine | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA ORG IRV BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-03 | 2020-02-20 |  | SN-0411 | 2020-03-27
34975 | CFG VA HRD OCN AC-CFG Deployment POR20 | VA | HRD | OCN | Oceana | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA HRD OCN AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | SN-0262 | 2020-02-28
54572 | CFS VA NVA RHL HV-CFS Augment POR20 | VA | NVA | RHL | Rose Hill | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA NVA RHL HV-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-25 | 2020-02-20 |  | SB-0091 | 2020-03-27 | New
34975 | CFG VA HRD PTM AC-CFG Deployment POR20 | VA | HRD | PTM | Portsmouth (VA) | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA HRD PTM AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | SN-0262 | 2020-02-28
34971 | CFG CA SAN ELC BS-CFG Augment POR20 | CA | SAN | ELC | El Cajon | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA SAN ELC BS-CFG Augment POR20 | Labor | No Equipment | 1 | 2020-02-03 | 2020-02-20 |  | SN-0262 | 2020-02-28 | Chg
34975 | CFG VA NVA FLK BD-CFG Deployment POR20 | VA | NVA | FLK | Fair Lakes | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA NVA FLK BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | SN-0262 | 2020-02-28
54574 | CFS NE RHD CRN HV-CFS Augment POR20 - 1 | NE | RHD | CRN | Cranston | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD CRN HV-CFS Augment POR20 - 1 | Labor | No Equipment | 1 | 2020-02-28 | 2020-02-20 |  | SB-0091 | 2020-03-27 | New
34976 | CFG NE CON SFD BD-CFG Deployment POR20 | NE | CON | SFD | Stafford | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE CON SFD BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | SN-0228 | 2020-02-07 | New
54572 | CFS VA NVA MFD HV-CFS Augment POR20 | VA | NVA | MFD | Merrifield | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA NVA MFD HV-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-26 | 2020-02-20 |  | SB-0091 | 2020-03-27 | New
54572 | CFS VA HRD LTF DC-CFS Augment POR20 | VA | HRD | LTF | Lightfoot | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD LTF DC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | SB-0049 | 2020-02-28 | New
34975 | CFG VA HRD OCN BS-CFG Deployment POR20 | VA | HRD | OCN | Oceana | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA HRD OCN BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | SN-0228 | 2020-02-07 | New
34974 | CFG SE NOR KNN BD-CFG Deployment POR20 | SE | NOR | KNN | Kenner | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SE NOR KNN BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | SN-0228 | 2020-02-07 | New
34976 | CFG NE RHD PRV AC-CFG Deployment POR20 | NE | RHD | PRV | Providence | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE RHD PRV AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | SN-0262 | 2020-02-28
54574 | CFS NE CON SFD AT-CFS Augment POR20 | NE | CON | SFD | Stafford | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON SFD AT-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-28 | 2020-02-20 |  | SB-0091 | 2020-03-27 | New
34970 | CFG SW ARZ PEO RK-CFG Deployment POR20 | SW | ARZ | PEO | Peoria | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ PEO RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-03 | 2020-02-20 |  | SN-0262 | 2020-02-28
34976 | CFG NE RHD RMD BS-CFG Deployment POR20 | NE | RHD | RMD | Richmond (RI) | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE RHD RMD BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-02-20 |  | SN-0130 | 2020-02-06 | Chg
54574 | CFS NE RHD PAW HV-CFS Augment POR20 - 1 | NE | RHD | PAW | Pawtucket | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE RHD PAW HV-CFS Augment POR20 - 1 | Labor | No Equipment | 1 | 2020-02-28 | 2020-02-20 |  | SB-0091 | 2020-03-27 | New
54572 | CFS VA HRD GLO DC-CFS Augment POR20 | VA | HRD | GLO | Gloucester | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD GLO DC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | SB-0049 | 2020-02-28 | New
34976 | CFG NE RHD LNC BD-CFG Deployment POR20 | NE | RHD | LNC | Lincoln | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE RHD LNC BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | SN-0228 | 2020-02-07 | New
54574 | CFS NE CON STN RF-CFS Augment POR20 | NE | CON | STN | Southington | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON STN RF-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | SB-0046 | 2020-02-07 | New
54572 | CFS VA HRD JCC FF-CFS Augment POR20 | VA | HRD | JCC | James City County | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD JCC FF-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | SB-0046 | 2020-02-07 | New
54572 | CFS VA NVA WOX BU-CFS Augment POR20 | VA | NVA | WOX | West Ox Colo | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA NVA WOX BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-14 | 2020-02-20 |  | SB-0091 | 2020-03-27 | New
34975 | CFG VA HRD CHS AC-CFG Deployment POR20 | VA | HRD | CHS | Chesapeake | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA HRD CHS AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | SN-0262 | 2020-02-28
34976 | CFG NE CLE CLV RC-CFG Deployment POR20 | NE | CLE | CLV | Cleveland | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE CLE CLV RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | SN-0228 | 2020-02-07 | New
34976 | CFG NE RHD PAW AC-CFG Deployment POR20 | NE | RHD | PAW | Pawtucket | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE RHD PAW AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | SN-0262 | 2020-02-28
34976 | CFG NE CON ENF AC-CFG Deployment POR20 | NE | CON | ENF | Enfield | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE CON ENF AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | SN-0262 | 2020-02-28
34970 | CFG SW ARZ CHD RK-CFG Deployment POR20 | SW | ARZ | CHD | Chandler | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ CHD RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | SN-0228 | 2020-02-07 | New
34971 | CFG CA SAN ESC BS-CFG Augment POR20 | CA | SAN | ESC | Escondido | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA SAN ESC BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-02-20 |  | SN-0130 | 2020-02-06 | Chg
34975 | CFG VA HRD PRA AC-CFG Deployment POR20 | VA | HRD | PRA | Princess Anne | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA HRD PRA AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | SN-0262 | 2020-02-28
34975 | CFG VA HRD HCK AC-CFG Deployment POR20 | VA | HRD | HCK | Hickory | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA HRD HCK AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | SN-0262 | 2020-02-28
34971 | CFG CA ORG AVJ RC-CFG Deployment POR20 | CA | ORG | AVJ | Aliso Viejo | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA ORG AVJ RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | SN-0228 | 2020-02-07 | New
54572 | CFS VA HRD JEF FF-CFS Augment POR20 | VA | HRD | JEF | Jefferson Ave | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD JEF FF-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | SB-0046 | 2020-02-07 | New
34975 | CFG VA ROA RON AC-CFG Deployment POR20 | VA | ROA | RON | Roanoke | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA ROA RON AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | SN-0262 | 2020-02-28
54572 | CFS VA HRD GBR RC-CFS Deployment POR20 | VA | HRD | GBR | Greenbrier | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD GBR RC-CFS Deployment POR20 | Labor | No Equipment | 1 | 2020-02-03 | 2020-02-20 |  | SB-0049 | 2020-02-28 | New
54572 | CFS VA HRD NWP BU-CFS Augment POR20 | VA | HRD | NWP | Newport News | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD NWP BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | SB-0046 | 2020-02-07 | New
34971 | CFG CA ORG AVJ BD-CFG Deployment POR20 | CA | ORG | AVJ | Aliso Viejo | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA ORG AVJ BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | SN-0228 | 2020-02-07 | New
34975 | CFG VA HRD LTF AC-CFG Deployment POR20 | VA | HRD | LTF | Lightfoot | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA HRD LTF AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | SN-0262 | 2020-02-28
76108 | DCPS PA3260 DDR | COR | COR | DDR | Duke Drive | Data Center Perimeter Security | POInt | Yes | No | DCPS COR COR DDR PA3260 Deploy POR20 | Labor | No Equipment | 4 |  | 2020-02-20 | 2020-06-20 | SN-0685 | 2020-06-17 | Chg
54574 | CFS NE RHD CRN HV-CFS Augment POR20 - 2 | NE | RHD | CRN | Cranston | Critical Facilities Sustaining (Field) | POInt | Yes | No | CFS NE RHD CRN HV-CFS Augment POR20 - 2 | Labor | No Equipment | 1 | 2020-02-28 | 2020-02-20 |  | SB-0091 | 2020-03-27 | New
54574 | CFS NE RHD PAW HV-CFS Augment POR20 - 2 | NE | RHD | PAW | Pawtucket | Critical Facilities Sustaining (Field) | POInt | Yes | No | CFS NE RHD PAW HV-CFS Augment POR20 - 2 | Labor | No Equipment | 1 | 2020-02-28 | 2020-02-20 |  | SB-0091 | 2020-03-27 | New
75655 | Arbor 11 | SE | GAN | GNS | Gainesville | Arbor DDoS | POInt | Yes | No | DDoS SE GAN GNS Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-01-10 | 2020-02-24 | 2020-03-09 | SN-0107 | 2020-02-06 | Chg
75655 | Arbor 5 | COR | NAT | AT1 | Atlanta - Digital Realty (Cage SBT.M03) | Arbor DDoS | POInt | Yes | No | DDoS SE NAT AT1 Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-01-01 | 2020-02-26 | 2020-03-27 | SN-0122 | 2020-02-06 | Chg
75647 | Nokia 1830 Add 2 | COR | NAT | DC2 | Ashburn/DC - Equinix (cage 2500 - Transport) | C4 & C4B Transport Network | POInt | Yes | No | C4B VA NAT DC2 Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis | 5 |  | 2020-02-28 |  | SN-0229 | 2020-02-03 | Chg
34943 | MTRN-CHD- T5-04 | SW | ARZ | CHD | Chandler | Metro Transport | POInt | Yes | Yes | MTRN SW ARZ CHD T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-02-28 |  | SN-0154 | 2020-02-06
75658 | VA-GNS-1x Dell R640 | SE | GAN | GNS | Gainesville | Visibility Architecture | POInt | Yes | No | VIA SE GAN GNS Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 4 | 2020-01-01 | 2020-02-29 | 2020-03-09 | SN-0094 | 2020-02-06 | New
75658 | VA-GNS-1x Ixia E100 | SE | GAN | GNS | Gainesville | Visibility Architecture | POInt | Yes | No | VIA SE GAN GNS Visibility Architecture Gear Deployment POR20 | Chassis | 1x Ixia E100 Chassis | 1 | 2020-01-01 | 2020-02-29 | 2020-03-09 | SN-0094 | 2020-02-06 | New
75658 | VA-GNS-1x ExtraHop EDA6200 (Dell R640) | SE | GAN | GNS | Gainesville | Visibility Architecture | POInt | Yes | No | VIA SE GAN GNS Visibility Architecture Gear Deployment POR20 | Chassis | 1x ExtraHop EDA6200 (Dell R640) | 1 | 2020-01-01 | 2020-02-29 | 2020-03-09 | SN-0094 | 2020-02-06 | Chg
75658 | VA-GNS-1x Juniper EX4600 | SE | GAN | GNS | Gainesville | Visibility Architecture | POInt | Yes | No | VIA SE GAN GNS Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-01-01 | 2020-02-29 | 2020-03-09 | SN-0094 | 2020-02-06 | Chg
39256 | BWM_MAN_VIDEO SG_2020 DOCSIS node split-based Video SG | NE | CON | MAN | Manchester | Bandwidth Management | POInt | Yes | No | BWM NE CON MAN Video SG Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-01 | 2020-03-01 | SN-0195 | 2020-01-24 | Chg
34644 | BWM_SAL_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | KAN | SAL | Salina | Bandwidth Management | POInt | Yes | No | BWM CE KAN SAL VIDEO SG Augment POR20 | Labor | No Equipment | 1 | 2020-01-16 | 2020-03-01 |  | SN-0195 | 2020-01-24 | Chg
54571 | CFS SE GCT NCV SC-CFS Augment POR20 | SE | GCT | NCV | Niceville | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE GCT NCV SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE BTR STC BU-CFS Augment POR20 | SE | BTR | STC | St. Charles | Critical Facilities Sustaining (Field) | POInt | Yes | No | CFS SE BTR STC BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-01 |  | SB-0023 | 2020-01-30 | New
34644 | BWM_TOW_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | KAN | TOW | Towanda | Bandwidth Management | POInt | Yes | No | BWM CE KAN TOW VIDEO SG Augment POR20 | Labor | No Equipment | 1 | 2020-01-16 | 2020-03-01 |  | SN-0195 | 2020-01-24 | Chg
54571 | CFS SE GCT NCV BS-CFS Augment POR20 | SE | GCT | NCV | Niceville | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE GCT NCV BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE BTR BTR SC-CFS Augment POR20 | SE | BTR | BTR | Baton Rouge | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE BTR BTR SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-01 |  | SB-0023 | 2020-01-30 | New
34604 | CB Transport - New Router South - SPC - Optics | SE | BTR | SPC | Pecue | CB - Metro Core | POInt | Yes | Yes | CBMC SE BTR SPC Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-01-01 | 2020-03-01
34943 | MTRN-BEL- T5-01 | SW | ARZ | BEL | Bell | Metro Transport | POInt | Yes | Yes | MTRN SW ARZ BEL T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-03-01 | 2020-04-01 | SN-0154 | 2020-02-06 | Chg
54571 | CFS SE GCT DES SC-CFS Augment POR20 | SE | GCT | DES | Destin | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE GCT DES SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE NOR LUL IV-CFS Augment POR20 | SE | NOR | LUL | Luling | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE NOR LUL IV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-01 |  | SB-0023 | 2020-01-30 | New
34971 | CFG CA ORG AVJ RK-CFG Deployment POR20 | CA | ORG | AVJ | Aliso Viejo | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA ORG AVJ RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | SN-0262 | 2020-02-28 | New
54573 | CFS SW LAS ERN LM-CFS Augment POR20 | SW | LAS | ERN | Ernest May | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW LAS ERN LM-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | SB-0049 | 2020-02-28 | New
54572 | CFS VA HRD OAK GN-CFS Augment POR20 | VA | HRD | OAK | Oakdale CEC | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD OAK GN-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | SB-0049 | 2020-02-28 | New
54573 | CFS SW LAS VLY FF-CFS Augment POR20 | SW | LAS | VLY | Valley | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW LAS VLY FF-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | SB-0049 | 2020-02-28 | New
54569 | CFS CA SAN ESC BS-CFS Augment POR20 | CA | SAN | ESC | Escondido | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CA SAN ESC BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | SB-0049 | 2020-02-28 | New
54569 | CFS CA SAB SAB RC-CFS Augment POR20 | CA | SAB | SAB | Santa Barbara | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CA SAB SAB RC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | SB-0049 | 2020-02-28 | New
54572 | CFS VA HRD NRF BD-CFS Augment POR20 | VA | HRD | NRF | Norfolk | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD NRF BD-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | SB-0049 | 2020-02-28 | New
34971 | CFG CA ORG IRV RK-CFG Deployment POR20 | CA | ORG | IRV | Irvine | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA ORG IRV RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | SN-0262 | 2020-02-28 | New
54573 | CFS SW LAS TEN FF-CFS Augment POR20 | SW | LAS | TEN | Tenaya | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW LAS TEN FF-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | SB-0049 | 2020-02-28 | New
54573 | CFS SW ARZ DGL RF-CFS Augment POR20 | SW | ARZ | DGL | Douglas | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ DGL RF-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | SB-0049 | 2020-02-28 | New
54572 | CFS VA HRD LTF HV-CFS Augment POR20 | VA | HRD | LTF | Lightfoot | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD LTF HV-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | SB-0049 | 2020-02-28 | New
75655 | Arbor 22 | SE | NOR | ELM | Elmwood | Arbor DDoS | POInt | Yes | No | DDoS SE NOR ELM Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-01-17 | 2020-03-02 | 2020-03-16 | SN-0107 | 2020-02-06 | Chg
54572 | CFS VA HRD PRA RC-CFS Augment POR20 | VA | HRD | PRA | Princess Anne | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD PRA RC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | SB-0049 | 2020-02-28 | New
75655 | Arbor 21 | SE | BTR | BTR | Baton Rouge | Arbor DDoS | POInt | Yes | No | DDoS SE BTR BTR Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-01-13 | 2020-03-02 | 2020-03-16 | SN-0107 | 2020-02-06 | Chg
34608 | CB Transport - New Router Tysons - FLK - Optics | VA | NVA | FLK | Fair Lakes | CB - Metro Core | POInt | Yes | Yes | CBMC VA NVA FLK Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-04-15 | 2020-03-03 |  | SN-0934 | 2020-09-18 | Chg
75655 | Arbor 24 | CE | OKC | OKC | OKC MTC | Arbor DDoS | POInt | Yes | No | DDoS CE OKC OKC Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-01-24 | 2020-03-09 | 2020-03-23 | SN-0107 | 2020-02-06 | Chg
75830 | DTMF and Audio issues fix | COR | COR | ATL | Atlanta | Voice Network Upgrades | POInt | Yes | No | VNU CO -CO ATL Metaswitch Lifecycle Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-03-10 | 2020-03-10 | SB-0047 | 2020-01-31 | New
39251 | BWM ORG DOCSIS Expansion 96 MHz | CA | ORG | AVJ | Aliso Viejo | Bandwidth Management | POInt | Yes | No | BWM CA ORG AVJ DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-12 | 2022-04-01 | SN-0558 | 2020-05-12 | New
39251 | BWM ORG DOCSIS Expansion 192 MHz | CA | ORG | AVJ | Aliso Viejo | Bandwidth Management | POInt | Yes | No | BWM CA ORG AVJ DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-12 | 2022-04-01 | SN-0558 | 2020-05-12 | Chg
75703 | MTCS SE MGA MCN MPEG4 Field Transitions Deployment POR20 | SE | MGA | MCN | Macon | MTC - Servers and Software | POInt | Yes | No | MTCS SE MGA MCN MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15
75844 | NE RHD CRN VAM Splitter Augment POR20 | NE | RHD | CRN | Cranston | MTC Fiber and Rack Management | POInt | Yes | No | MVFM NE RHD CRN Fiber Bay Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-03-15 | 2020-03-15
75703 | MTCS VA HRD VBC MPEG4 Field Transitions Deployment POR20 | VA | HRD | VBC | Virginia Beach | MTC - Servers and Software | POInt | Yes | No | MTCS VA HRD VBC MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15
75703 | MTCS SE GCT PNS MPEG4 Field Transitions Deployment POR20 | SE | GCT | PNS | Pensacola with (Insite tower) | MTC - Servers and Software | POInt | Yes | No | MTCS SE GCT PNS MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15
59850 | RPHY MRTR-New-PAV-CIN-ATX-OCML | CA | ORG | PAV | Palos Verdes | R PHY | POInt | Yes | No | R PHY CA ORG PAV R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2020-01-01 | 2020-03-15 | 2020-06-30 | SN-0487 | 2020-05-12 | New
59850 | RPHY MRTR-New-PAV-CIN-RPA-5110 | CA | ORG | PAV | Palos Verdes | R PHY | POInt | Yes | No | R PHY CA ORG PAV R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-01-01 | 2020-03-15 | 2020-06-30 | SN-0301 | 2020-02-24 | Chg
75703 | MTCS SE GAN GNS MPEG4 Field Transitions Deployment POR20 | SE | GAN | GNS | Gainesville | MTC - Servers and Software | POInt | Yes | No | MTCS SE GAN GNS MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15
75844 | NE RHD PRV VAM Splitter Augment POR20 | NE | RHD | PRV | Providence | MTC Fiber and Rack Management | POInt | Yes | No | MVFM NE RHD PRV Fiber Bay Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-03-15 | 2020-03-15
75703 | MTCS CE OKC OKC MPEG4 Field Transitions Deployment POR20 | CE | OKC | OKC | OKC MTC | MTC - Servers and Software | POInt | Yes | No | MTCS CE OKC OKC MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15
75703 | MTCS SE GLA ELM MPEG4 Field Transitions Deployment POR20 | SE | NOR | ELM | Elmwood | MTC - Servers and Software | POInt | Yes | No | MTCS SE NOR ELM MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15
39251 | BWM_SAB_VIDEO SG_2020 DOCSIS node split-based Video SG | CA | SAB | SAB | Santa Barbara | Bandwidth Management | POInt | Yes | No | BWM CA SAB SAB VIDEO SG Augment POR20 | Labor | No Equipment | 4 | 2019-10-01 | 2020-03-15 | 2020-03-01 | SN-0195 | 2020-01-24 | Chg
75703 | MTCS VA ROA RON MPEG4 Field Transitions Deployment POR20 | VA | ROA | RON | Roanoke | MTC - Servers and Software | POInt | Yes | No | MTCS VA ROA RON MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15
75794 | VEO Automation - Managed Router Support Tools | COR | COR | ATL | Atlanta | Voice Monitoring and Analytics | POInt | Yes | No | VMA CO -CO ATL Workflow and portfolio implementation Deployment POR20 | Labor | Tool dev for Managed Router Solution support | 2 | 2020-02-25 | 2020-03-15 |  | SB-0013 | 2020-01-30 | Chg
57300 | REP_NE.RHD.WWK.REPACK | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | FCC Repack | POInt | Yes | No | FCC NE RHD WWK Channel Move Alignment POR20 | Chassis | Channel Move / Inca 8VSB / Wade WH | 8 | 2020-01-01 | 2020-03-15
75703 | MTCS NE RHD WWK MPEG4 Field Transitions Deployment POR20 | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | MTC - Servers and Software | POInt | Yes | No | MTCS NE RHD WWK MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15
34623 | CB Transport - New Router Peoria - MCD - Card Add | SW | ARZ | MCD | McDowell | CB - Metro Core | POInt | Yes | No | CBMC SW ARZ MCD Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-17 | 2020-03-15 |  | SN-0419 | 2020-04-02 | Chg
75703 | MTCS NE CON MAN MPEG4 Field Transitions Deployment POR20 | NE | CON | MAN | Manchester | MTC - Servers and Software | POInt | Yes | No | MTCS NE CON MAN MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15
75844 | NE RHD LNC VAM Splitter Augment POR20 | NE | RHD | LNC | Lincoln | MTC Fiber and Rack Management | POInt | Yes | No | MVFM NE RHD LNC Fiber Bay Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-03-15 | 2020-03-15
57299 | REP_VA.NVA.MFD.REPACK | VA | NVA | MFD | Merrifield | FCC Repack | POInt | Yes | No | FCC VA NVA MFD Channel Move Alignment POR20 | Chassis | Channel Move / Inca 8VSB / Wade WH | 1 | 2020-01-18 | 2020-03-15
75703 | MTCS CA SAN ELC MPEG4 Field Transitions Deployment POR20 | CA | SAN | ELC | El Cajon | MTC - Servers and Software | POInt | Yes | No | MTCS CA SAN ELC MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15
57300 | REP_NE.CON.SFD.REPACK | NE | CON | SFD | Stafford | FCC Repack | POInt | Yes | No | FCC NE CON SFD Channel Move Alignment POR20 | Chassis | Channel Move / Inca 8VSB / Wade WH | 9 | 2020-01-01 | 2020-03-15
34635 | BWM_MFD_VIDEO SG_2020 DOCSIS node split-based Video SG | VA | NVA | MFD | Merrifield | Bandwidth Management | POInt | Yes | No | BWM VA NVA MFD Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-03-15 | 2020-03-15
75699 | MTCS COR COR P6L Lab NE3000 Deployment POR20 | COR | COR | P6L | P6 Lab | MTC - Servers and Software | POInt | Yes | No | MTCS CO COR P6L Lab NE3000 Deployment POR20 | Chassis | NE3000 | 1 | 2020-02-06 | 2020-03-15 | 2020-04-15
75703 | MTCS CA SAB SAB MPEG4 Field Transitions Deployment POR20 | CA | SAB | SAB | Santa Barbara | MTC - Servers and Software | POInt | Yes | No | MTCS CA SAB SAB MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15
34642 | BWM_OKC_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | OKC | OKC | OKC MTC | Bandwidth Management | POInt | Yes | No | BWM CE OKC OKC VIDEO SG Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-03-15 | 2020-03-15
75703 | MTCS CE KAN WIC MPEG4 Field Transitions Deployment POR20 | CE | KAN | WIC | Wichita | MTC - Servers and Software | POInt | Yes | No | MTCS CE KAN WIC MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15
75703 | MTCS SW LAS HEN MPEG4 Field Transitions Deployment POR20 | SW | LAS | HEN | Henderson | MTC - Servers and Software | POInt | Yes | No | MTCS SW LAS HEN MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15
34644 | BWM_PSN_VIDEO SG_2020 DOCSIS node split-based Video SG I | CE | KAN | PSN | Parsons | Bandwidth Management | POInt | Yes | No | BWM CE KAN PSN VIDEO SG Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-03-15 | 2020-03-15
75703 | MTCS NE CLE CLV MPEG4 Field Transitions Deployment POR20 | NE | CLE | CLV | Cleveland | MTC - Servers and Software | POInt | Yes | No | MTCS NE CLE CLV MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15
75703 | MTCS CE OMA OMM MPEG4 Field Transitions Deployment POR20 | CE | OMA | OMM | Omaha | MTC - Servers and Software | POInt | Yes | No | MTCS CE OMA OMM MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15
75703 | MTCS VA NVA MFD MPEG4 Field Transitions Deployment POR20 | VA | NVA | MFD | Merrifield | MTC - Servers and Software | POInt | Yes | No | MTCS VA NVA MFD MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15
34944 | MTRN-DWN-TNCS/TNCSO-01 | CA | SAN | DWN | Downtown | Metro Transport | POInt | Yes | Yes | MTRN CA SAN DWN DWDM-OLS Deployment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-01-20 | 2020-03-15 | 2020-04-15 | SN-0098 | 2020-02-06 | Chg
35173 | MRTR NCS-Growth-VLY-100G Grow | SW | LAS | VLY | Valley | Metro Routers | POInt | Yes | Yes | MRTR SW LAS VLY 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15
35171 | MRTR NCS-Growth-WIC-100G Grow | CE | KAN | WIC | Wichita | Metro Routers | POInt | Yes | Yes | MRTR CE KAN WIC 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15
34619 | CB Transport - New Router Council Bluffs - CBL - Optics | CE | OMA | CBL | Council Bluffs | CB - Metro Core | POInt | Yes | Yes | CBMC CE OMA CBL Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 3 | 2020-02-15 | 2020-03-15
34975 | CFG FBG BS-CFG LARGE_2V_BATTSTRING | VA | NVA | FBG | Fredericksburg | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA NVA FBG BS-CFG Deployment POR20 | Critical Facilities | LARGE_2V_BATTSTRING | 1 | 2020-01-01 | 2020-03-15
35010 | Metro OTN-OKC-Ciena 6500 S2 | CE | OKC | OKC | OKC MTC | Metro Transport | POInt | Yes | Yes | MTRN CE OKC OKC OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 1 | 2020-01-31 | 2020-03-15 | 2020-05-15
34944 | MTRN-OCE-TNCS/TNCSO-01 | CA | SAN | OCE | Oceanside | Metro Transport | POInt | Yes | Yes | MTRN CA SAN OCE DWDM-OLS Deployment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-01-20 | 2020-03-15 | 2020-04-15 | SN-0098 | 2020-02-06 | Chg
59744 | RPHY MRTR-Growth-BEL-CIN-CBR8 Add - Optics Only | SW | ARZ | BEL | Bell | R PHY | POInt | Yes | Yes | R PHY SW ARZ BEL RPHY Metro Augment POR20 | Card & Optics | CIN-CBR8 Add - Optics Only | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | SN-0059 | 2020-02-06 | New
35171 | MRTR NCS-Growth-TOP-100G Grow | CE | KAN | TOP | Topeka | Metro Routers | POInt | Yes | Yes | MRTR CE KAN TOP 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15
35169 | MRTR NCS-Growth-BEL-100G Grow | SW | ARZ | BEL | Bell | Metro Routers | POInt | Yes | Yes | MRTR SW ARZ BEL 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | SN-0099 | 2020-02-06 | New
34944 | MTRN-ESC-TNCS/TNCSO-01 | CA | SAN | ESC | Escondido | Metro Transport | POInt | Yes | Yes | MTRN CA SAN ESC DWDM-OLS Deployment POR20 | Card & Optics | TNCS/TNCSO | 3 | 2020-01-20 | 2020-03-15 | 2020-04-15 | SN-0098 | 2020-02-06 | Chg
35175 | MRTR NCS-Growth-WWK-100G Grow | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | Metro Routers | POInt | Yes | Yes | MRTR NE RHD WWK 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15
75699 | MTCS COR COR P6L Lab NSG Deployment POR20 | COR | COR | P6L | P6 Lab | MTC - Servers and Software | POInt | Yes | No | MTCS CO COR P6L Lab NSG Deployment POR20 | Chassis | NSG | 1 | 2020-02-06 | 2020-03-15 | 2020-04-15
57264 | REP_CE.OKC.OKC.REPACK | CE | OKC | OKC | OKC MTC | FCC Repack | POInt | Yes | No | FCC CE OKC OKC Channel Move Alignment POR20 | Chassis | Channel Move / Inca 8VSB / Wade WH | 2 | 2020-01-18 | 2020-03-15
75703 | MTCS CA ORG RSM MPEG4 Field Transitions Deployment POR20 | CA | ORG | RSM | Rancho Santa Margarita | MTC - Servers and Software | POInt | Yes | No | MTCS CA ORG RSM MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15
75703 | MTCS SE GLA BTR MPEG4 Field Transitions Deployment POR20 | SE | BTR | BTR | Baton Rouge | MTC - Servers and Software | POInt | Yes | No | MTCS SE BTR BTR MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15
75703 | MTCS CE OKC TUL MPEG4 Field Transitions Deployment POR20 | CE | TUL | TUL | Tulsa | MTC - Servers and Software | POInt | Yes | No | MTCS CE TUL TUL MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15
75703 | MTCS CE ARK NWA MPEG4 Field Transitions Deployment POR20 | CE | NWA | NWA | Johnson | MTC - Servers and Software | POInt | Yes | No | MTCS CE NWA NWA MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15
59850 | RPHY MRTR-Growth-DWN-CIN-RPA-5110 | CA | SAN | DWN | Downtown | R PHY | POInt | Yes | No | R PHY CA SAN DWN R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-01-01 | 2020-03-15 | 2020-06-30 | SN-0301 | 2020-02-24 | Chg
34635 | BWM_FLK_VIDEO SG_2020 DOCSIS node split-based Video SG | VA | NVA | FLK | Fair Lakes | Bandwidth Management | POInt | Yes | No | BWM VA NVA FLK Video SG Augment POR20 v2 | Labor | No Equipment | 1 | 2020-01-01 | 2020-03-15 | 2020-03-15
57299 | REP_VA.NVA.FBG.REPACK | VA | NVA | FBG | Fredericksburg | FCC Repack | POInt | Yes | No | FCC VA NVA FBG Channel Move Alignment POR20 | Chassis | Channel Move / Inca 8VSB / Wade WH | 3 | 2020-01-18 | 2020-03-15
75703 | MTCS SW ARZ CHD MPEG4 Field Transitions Deployment POR20 | SW | ARZ | CHD | Chandler | MTC - Servers and Software | POInt | Yes | No | MTCS SW ARZ CHD MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15
59850 | RPHY MRTR-New-DWN-CIN-ATX-OCML | CA | SAN | DWN | Downtown | R PHY | POInt | Yes | No | R PHY CA SAN DWN R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-30 | SN-0487 | 2020-05-12 | New
34971 | CFG CA SAN OCE RC-CFG Deployment POR20 | CA | SAN | OCE | Oceanside | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA SAN OCE RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-15 |  | SN-0228 | 2020-02-07 | New
59744 | RPHY MRTR-Growth-HEN-CIN-CBR8 Add - Optics Only | SW | LAS | HEN | Henderson | R PHY | POInt | Yes | Yes | R PHY SW LAS HEN RPHY Metro Deployment POR20 | Card & Optics | CIN-CBR8 Add - Optics Only | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | SN-0059 | 2020-02-06 | New
35169 | MRTR NCS-Growth-MSA-100G Grow | SW | ARZ | MSA | Mesa | Metro Routers | POInt | Yes | Yes | MRTR SW ARZ MSA 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15
34623 | CB Transport - New Router Peoria - CHD - Optics | SW | ARZ | CHD | Chandler | CB - Metro Core | POInt | Yes | Yes | CBMC SW ARZ CHD Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-01-17 | 2020-03-15
35011 | MTRN-vbc-DWDM-upgrade-01 | VA | HRD | VBC | Virginia Beach | Metro Transport | POInt | Yes | Yes | MTRN VA HRD VBC DWDM Deployment POR20 | Card & Optics | DWDM-upgrade | 2 | 2020-01-20 | 2020-03-15 | 2020-04-15 | SN-0774 | 2020-07-27 | Chg
59744 | RPHY MRTR-New-VLY-CIN-ATX-OCML | SW | LAS | VLY | Valley | R PHY | POInt | Yes | Yes | R PHY SW LAS VLY RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-15 | SN-0612 | 2020-05-29 | New
35176 | MRTR NCS-Growth-NEH-100G Grow | CE | OKC | NEH | North East | Metro Routers | POInt | Yes | Yes | MRTR CE OKC NEH 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15
35011 | MTRN-NRF- T5-01 | VA | HRD | NRF | Norfolk | Metro Transport | POInt | Yes | Yes | MTRN VA HRD NRF T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-20 | 2020-03-15 | 2020-04-15 | SN-0098 | 2020-02-06 | Chg
35011 | MTRN-NRF- T5-02 | VA | HRD | NRF | Norfolk | Metro Transport | POInt | Yes | Yes | MTRN VA HRD NRF T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-20 | 2020-03-15 | 2020-04-15 | SN-0098 | 2020-02-06 | Chg
34944 | MTRN-FED-TNCS/TNCSO-01 | CA | SAN | FED | Federal | Metro Transport | POInt | Yes | Yes | MTRN CA SAN FED DWDM-OLS Deployment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-01-20 | 2020-03-15 | 2020-04-15 | SN-0098 | 2020-02-06 | Chg
34970 | CFG SSC HV-CFG GEN GROW PROJECT - LARGE | SW | ARZ | SSC | South Scottsdale | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ SSC GN-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-03-01 | 2020-03-15
59850 | RPHY MRTR-New-AVJ-CIN-RPA-5110 | CA | ORG | AVJ | Aliso Viejo | R PHY | POInt | Yes | Yes | R PHY CA ORG AVJ RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-01-01 | 2020-03-15 | 2020-03-15 | SN-0301 | 2020-02-24 | Chg
59850 | RPHY MRTR-New-AVJ-CIN-ATX-OCML | CA | ORG | AVJ | Aliso Viejo | R PHY | POInt | Yes | Yes | R PHY CA ORG AVJ RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-30 | SN-0487 | 2020-05-12 | New
35177 | MRTR NCS-Growth-MFD-100G Grow | VA | NVA | MFD | Merrifield | Metro Routers | POInt | Yes | Yes | MRTR VA NVA MFD 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15
34975 | CFG VA HRD PTM BS-CFG Deployment POR20 | VA | HRD | PTM | Portsmouth (VA) | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA HRD PTM BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-15 |  | SN-0228 | 2020-02-07 | New
59744 | RPHY MRTR-New-ERN-CIN-ATX-OCML | SW | LAS | ERN | Ernest May | R PHY | POInt | Yes | Yes | R PHY SW LAS ERN RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-15 | SN-0612 | 2020-05-29 | New
34944 | MTRN-FED- T5-01 | CA | SAN | FED | Federal | Metro Transport | POInt | Yes | Yes | MTRN CA SAN FED T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 3 | 2020-01-20 | 2020-03-15 | 2020-04-15 | SN-0098 | 2020-02-06 | Chg
59850 | RPHY MRTR-New-IRV-CIN-RPA-5110 | CA | ORG | IRV | Irvine | R PHY | POInt | Yes | Yes | R PHY CA ORG IRV RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 3 | 2020-01-01 | 2020-03-15 | 2020-03-15 | SN-0059 | 2020-02-06 | New
59850 | RPHY MRTR-New-IRV-CIN-ATX-OCML | CA | ORG | IRV | Irvine | R PHY | POInt | Yes | Yes | R PHY CA ORG IRV RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-30 | SN-0487 | 2020-05-12 | New
35011 | MTRN-nrf-DWDM-upgrade-01 | VA | HRD | NRF | Norfolk | Metro Transport | POInt | Yes | Yes | MTRN VA HRD NRF DWDM Deployment POR20 | Card & Optics | DWDM-upgrade | 2 | 2020-01-20 | 2020-03-15 | 2020-04-15 | SN-0774 | 2020-07-27 | Chg
34975 | CFG VA HRD VBC BS-CFG Deployment POR20 | VA | HRD | VBC | Virginia Beach | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA HRD VBC BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-15 |  | SN-0228 | 2020-02-07 | New
34945 | MTRN-WIC- T5-01 | CE | KAN | WIC | Wichita | Metro Transport | POInt | Yes | Yes | MTRN CE KAN WIC T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-03-15 | 2020-03-15 | SN-0098 | 2020-02-06 | Chg
34944 | MTRN-VST-TNCS/TNCSO-01 | CA | SAN | VST | Vista | Metro Transport | POInt | Yes | Yes | MTRN CA SAN VST DWDM-OLS Deployment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-01-20 | 2020-03-15 | 2020-04-15 | SN-0098 | 2020-02-06 | Chg
34972 | CFG CE OMA OMM RK-CFG Deployment POR20 | CE | OMA | OMM | Omaha | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OMA OMM RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-15 |  | SN-0228 | 2020-02-07 | New
35174 | MRTR NCS-Growth-MCY-100G Grow | SE | NOR | MCY | Mid-City | Metro Routers | POInt | Yes | Yes | MRTR SE NOR MCY 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15
34619 | OKCMOKJN9AW-XR01.WLK.OKC.OK-100G CARD | CE | OKC | WLK | Walker Hub | CB - Metro Core | POInt | Yes | Yes | CBMC CE OKC WLK 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 2 | 2020-02-15 | 2020-03-15 |  | SN-0246 | 2020-02-24 | Chg
59850 | RPHY MRTR-New-FED-CIN-ATX-OCML | CA | SAN | FED | Federal | R PHY | POInt | Yes | Yes | R PHY CA SAN FED RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-30 | SN-0487 | 2020-05-12 | New
59850 | RPHY MRTR-New-ORG-CIN-ATX-OCML | CA | ORG | ORG | Orange | R PHY | POInt | Yes | Yes | R PHY CA ORG ORG RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-30 | SN-0487 | 2020-05-12 | New
34971 | CFG ESC BS-CFG GEN GROW PROJECT - MEDIUM | CA | SAN | ESC | Escondido | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA SAN ESC BS-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-02-02 | 2020-03-15
34604 | CB Transport - New Router Holt - MCN - Card Add | SE | MGA | MCN | Macon | CB - Metro Core | POInt | Yes | Yes | CBMC SE MGA MCN Optics Only for Cisco T5 Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 6 | 2020-01-20 | 2020-03-15 |  | SN-0419 | 2020-04-02 | Chg
34623 | CB Transport - New Router Peoria - PEO - Card Add | SW | ARZ | PEO | Peoria | CB - Metro Core | POInt | Yes | Yes | CBMC SW ARZ PEO Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-10 | 2020-03-15
59744 | RPHY MRTR-Growth-BLU-CIN-CBR8 Add - Optics Only | SW | LAS | BLU | Blue Diamond | R PHY | POInt | Yes | Yes | R PHY SW LAS BLU RPHY Metro Deployment POR20 | Card & Optics | CIN-CBR8 Add - Optics Only | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | SN-0059 | 2020-02-06 | New
59744 | RPHY MRTR-New-FWL-CIN-Nokia-OCML | SW | ARZ | FWL | Fowler | R PHY | POInt | Yes | Yes | R PHY SW ARZ FWL RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-03-15 | SN-0487 | 2020-05-12 | Chg
34975 | CFG JCC BS-CFG LARGE_2V_BATTSTRING | VA | HRD | JCC | James City County | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA HRD JCC BS-CFG Deployment POR20 | Critical Facilities | LARGE_2V_BATTSTRING | 1 | 2020-01-01 | 2020-03-15
35172 | MRTR NCS-Growth-WRB-100G Grow | SE | MGA | WRB | Warner Robins | Metro Routers | POInt | Yes | Yes | MRTR SE MGA WRB 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15
34975 | CFG VA HRD GBR RC-CFG Deployment POR20 | VA | HRD | GBR | Greenbrier | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA HRD GBR RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-15 |  | SN-0228 | 2020-02-07 | New
34976 | CFG ENF BD-MTRN BDFBSPLIT_0-150 | NE | CON | ENF | Enfield | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE CON ENF BD-CFG Deployment POR20 | Critical Facilities | BDFBSPLIT_0-150 | 1 | 2020-01-20 | 2020-03-15
34619 | CB Transport - New Router Council Bluffs, North - BLV - Card Add | CE | OMA | BLV | Bellevue | CB - Metro Core | POInt | Yes | Yes | CBMC CE OMA BLV Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-02-15 | 2020-03-15
59744 | RPHY MRTR-New-NSC-CIN-Nokia-OCML | SW | ARZ | NSC | North Scottsdale | R PHY | POInt | Yes | Yes | R PHY SW ARZ NSC RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2020-01-01 | 2020-03-15 | 2020-06-15 | SN-0487 | 2020-05-12 | Chg
35175 | NEXUS-CLV-93180-01 | NE | CLE | CLV | Cleveland | Metro Routers | POInt | Yes | Yes | MRTR NE CLE CLV 100G Grow Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-01-20 | 2020-03-15 | 2020-04-15
35175 | NEXUS-CLV-2248-01 | NE | CLE | CLV | Cleveland | Metro Routers | POInt | Yes | Yes | MRTR NE CLE CLV 100G Grow Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-01-20 | 2020-03-15 | 2020-04-15
59744 | RPHY MRTR-New-CHD-CIN-Nokia-OCML | SW | ARZ | CHD | Chandler | R PHY | POInt | Yes | Yes | R PHY SW ARZ CHD RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-03-15 | SN-0487 | 2020-05-12 | Chg
59850 | RPHY MRTR-Growth-CHU-CIN-RPA-5110 | CA | SAN | CHU | Chula Vista | R PHY | POInt | Yes | Yes | R PHY CA SAN CHU RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-01-01 | 2020-03-15 | 2020-03-15 | SN-0059 | 2020-02-06 | New
59744 | RPHY MRTR-New-SSC-CIN-Nokia2-OCML | SW | ARZ | SSC | South Scottsdale | R PHY | POInt | Yes | Yes | R PHY SW ARZ SSC RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-30 | SN-0487 | 2020-05-12 | New
34971 | CFG ELC BS-CFG GEN GROW PROJECT - MEDIUM | CA | SAN | ELC | El Cajon | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA SAN ELC BS-CFG Augment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-02-02 | 2020-03-15
59850 | RPHY MRTR-New-OCE-CIN-ATX-OCML | CA | SAN | OCE | Oceanside | R PHY | POInt | Yes | Yes | R PHY CA SAN OCE RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2020-01-01 | 2020-03-15 | 2020-06-30 | SN-0487 | 2020-05-12 | New
35173 | MRTR NCS-Growth-TEN-100G Grow | SW | LAS | TEN | Tenaya | Metro Routers | POInt | Yes | Yes | MRTR SW LAS TEN 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15
34971 | CFG CA SAN VST BS-CFG Deployment POR20 | CA | SAN | VST | Vista | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA SAN VST BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-15 |  | SN-0228 | 2020-02-07 | New
59744 | RPHY MRTR-New-MCD-CIN-Nokia-OCML | SW | ARZ | MCD | McDowell | R PHY | POInt | Yes | Yes | R PHY SW ARZ MCD RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2020-01-01 | 2020-03-15 | 2020-03-15 | SN-0487 | 2020-05-12 | Chg
34975 | CFG DRA BS-CFG LARGE_2V_BATTSTRING | VA | NVA | DRA | Dranesville | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA NVA DRA BS-CFG Deployment POR20 | Critical Facilities | LARGE_2V_BATTSTRING | 1 | 2020-01-01 | 2020-03-15
34944 | MTRN-ELC- T5-01 | CA | SAN | ELC | El Cajon | Metro Transport | POInt | Yes | Yes | MTRN CA SAN ELC T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-03-15 | 2020-04-15 | SN-0098 | 2020-02-06 | Chg
34976 | CFG PTH BD-MRTR BDFBSPLIT_0-150 | NE | RHD | PTH | Portsmouth (RI) | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE RHD PTH BD-CFG Deployment POR20 | Critical Facilities | BDFBSPLIT_0-150 | 1 | 2020-01-20 | 2020-03-15
35011 | MTRN-vbc- T5-01 | VA | HRD | VBC | Virginia Beach | Metro Transport | POInt | Yes | Yes | MTRN VA HRD VBC T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-20 | 2020-03-15 | 2020-04-15 | SN-0098 | 2020-02-06 | Chg
35011 | MTRN-VBC- T5-02 | VA | HRD | VBC | Virginia Beach | Metro Transport | POInt | Yes | Yes | MTRN VA HRD VBC T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-20 | 2020-03-15 | 2020-04-15 | SN-0098 | 2020-02-06 | Chg
59850 | RPHY MRTR-Growth-VST-CIN-CBR8 Add - Optics Only | CA | SAN | VST | Vista | R PHY | POInt | Yes | Yes | R PHY CA SAN VST RPHY Metro Augment POR20 | Card & Optics | CIN-CBR8 Add - Optics Only | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | SN-0059 | 2020-02-06 | New
59850 | RPHY MRTR-New-VST-CIN-ATX-OCML | CA | SAN | VST | Vista | R PHY | POInt | Yes | Yes | R PHY CA SAN VST RPHY Metro Augment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-30 | SN-0487 | 2020-05-12 | New
34976 | CFG CLV RK-CFG GEN GROW PROJECT - LARGE | NE | CLE | CLV | Cleveland | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE CLE CLV RK LARGE Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-03-18 | 2020-03-15
35174 | MRTR NCS-Growth-LPL-100G Grow | SE | NOR | LPL | Lapalco | Metro Routers | POInt | Yes | Yes | MRTR SE NOR LPL 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15
34971 | CFG CA SAN VST RC-CFG Deployment POR20 | CA | SAN | VST | Vista | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA SAN VST RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-15 |  | SN-0228 | 2020-02-07 | New
59744 | RPHY MRTR-New-PNL-CIN-Nokia-OCML | SW | ARZ | PNL | Pinal County | R PHY | POInt | Yes | Yes | R PHY SW ARZ PNL RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2020-01-01 | 2020-03-15 | 2020-03-15 | SN-0487 | 2020-05-12 | Chg
59850 | RPHY MRTR-New-PWY-CIN-Nokia-OCML2 | CA | SAN | PWY | Poway | R PHY | POInt | Yes | Yes | R PHY CA SAN PWY RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2020-01-01 | 2020-03-15 | 2020-06-30 | SN-0487 | 2020-05-12 | New
34944 | MTRN-PWY-TNCS/TNCSO-01 | CA | SAN | PWY | Poway | Metro Transport | POInt | Yes | Yes | MTRN CA SAN PWY DWDM-OLS Deployment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-01-20 | 2020-03-15 | 2020-04-15 | SN-0098 | 2020-02-06 | Chg
59744 | RPHY MRTR-New-TUC-CIN-Nokia2-OCML | SW | ARZ | TUC | Tucson | R PHY | POInt | Yes | Yes | R PHY SW ARZ TUC RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-15 | SN-0487 | 2020-05-12 | New
34971 | CFG CA SAN PWY RC-CFG Deployment POR20 | CA | SAN | PWY | Poway | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA SAN PWY RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-15 |  | SN-0228 | 2020-02-07 | New
34944 | MTRN-ELC-TNCS/TNCSO-01 | CA | SAN | ELC | El Cajon | Metro Transport | POInt | Yes | Yes | MTRN CA SAN ELC DWDM-OLS Deployment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-01-20 | 2020-03-15 | 2020-04-15 | SN-0098 | 2020-02-06 | Chg
59850 | RPHY MRTR-Growth-ELC-CIN-CBR8 Add - Optics Only | CA | SAN | ELC | El Cajon | R PHY | POInt | Yes | Yes | R PHY CA SAN ELC RPHY Metro Deployment POR20 | Card & Optics | CIN-CBR8 Add - Optics Only | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | SN-0059 | 2020-02-06 | New
59850 | RPHY MRTR-New-ELC-CIN-ATX-OCML | CA | SAN | ELC | El Cajon | R PHY | POInt | Yes | Yes | R PHY CA SAN ELC RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-30 | SN-0487 | 2020-05-12 | New
35173 | MRTR NCS-Growth-HEN-100G Grow | SW | LAS | HEN | Henderson | Metro Routers | POInt | Yes | Yes | MRTR SW LAS HEN 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15
34944 | MTRN-CHU- T5-01 | CA | SAN | CHU | Chula Vista | Metro Transport | POInt | Yes | Yes | MTRN CA SAN CHU T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-03-15 | 2020-04-15 | SN-0098 | 2020-02-06 | Chg
34619 | OMAJNEOT9DW-ELKHBSRA21-100G CARD | CE | OMA | ELK | Elkhorn | CB - Metro Core | POInt | Yes | Yes | CBMC CE OMA ELK 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 2 | 2020-02-15 | 2020-03-15 |  | SN-0246 | 2020-02-24 | Chg
59850 | RPHY MRTR-Growth-RSM-CIN-CBR8 Add - Optics Only | CA | ORG | RSM | Rancho Santa Margarita | R PHY | POInt | Yes | Yes | R PHY CA ORG RSM RPHY Metro Deployment POR20 | Card & Optics | CIN-CBR8 Add - Optics Only | 4 | 2020-01-01 | 2020-03-15 | 2020-03-15 | SN-0059 | 2020-02-06 | New
59850 | RPHY MRTR-New-RSM-CIN-RPA-5110 | CA | ORG | RSM | Rancho Santa Margarita | R PHY | POInt | Yes | Yes | R PHY CA ORG RSM RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | SN-0059 | 2020-02-06 | New
59744 | RPHY MRTR-New-BUK-CIN-Nokia-OCML | SW | ARZ | BUK | Buckeye | R PHY | POInt | Yes | Yes | R PHY SW ARZ BUK RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2020-01-01 | 2020-03-15 | 2020-03-15 | SN-0487 | 2020-05-12 | Chg
34971 | CFG CA SAN ESC RC-CFG Deployment POR20 | CA | SAN | ESC | Escondido | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA SAN ESC RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-15 |  | SN-0228 | 2020-02-07 | New
35171 | MRTR NCS-Growth-FTS-100G Grow | CE | NWA | FTS | Fort Smith | Metro Routers | POInt | Yes | Yes | MRTR CE NWA FTS 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15
59850 | RPHY MRTR-New-DNP-CIN-ATX-OCML | CA | ORG | DNP | Dana Point | R PHY | POInt | Yes | Yes | R PHY CA ORG DNP RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-15 | 2020-06-30 | SN-0487 | 2020-05-12 | New
34976 | CFG MAN BD-MTRN NEWBDCBB_6_PANEL | NE | CON | MAN | Manchester | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE CON MAN GN-CFG Deployment POR20 | Critical Facilities | NEWBDCBB_6_PANEL | 1 | 2020-01-20 | 2020-03-15
34976 | CFG MAN GN-CFG GENSET_500-750KW | NE | CON | MAN | Manchester | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE CON MAN GN-CFG Deployment POR20 | Critical Facilities | GENSET_500-750KW | 1 | 2020-03-20 | 2020-03-15
34976 | CFG MAN BS-MTRN LARGE_2V_BATTSTRING | NE | CON | MAN | Manchester | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE CON MAN GN-CFG Deployment POR20 | Critical Facilities | LARGE_2V_BATTSTRING | 1 | 2020-03-20 | 2020-03-15
34635 | BWM_HCK_MSSA_Spectrum Phase II Start | VA | HRD | HCK | Hickory | Bandwidth Management | POInt | Yes | No | BWM VA HRD HCK MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-03-16 | 2020-05-20 | SN-0703 | 2020-06-30 | Chg
34635 | BWM_VBC_MSSA_Spectrum Phase II Start | VA | HRD | VBC | Virginia Beach | Bandwidth Management | POInt | Yes | No | BWM VA HRD VBC MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-05-20 | SN-0703 | 2020-06-30 | Chg
34635 | BWM_NWP_MSSA_Spectrum Phase II Start | VA | HRD | NWP | Newport News | Bandwidth Management | POInt | Yes | No | BWM VA HRD NWP MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-05-20 | SN-0703 | 2020-06-30 | Chg
34635 | BWM_PTM_MSSA_Spectrum Phase II Start | VA | HRD | PTM | Portsmouth (VA) | Bandwidth Management | POInt | Yes | No | BWM VA HRD PTM MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-05-20 | SN-0703 | 2020-06-30 | Chg
34635 | BWM_GLO_MSSA_Spectrum Phase II Start | VA | HRD | GLO | Gloucester | Bandwidth Management | POInt | Yes | No | BWM VA HRD GLO MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-05-20 | SN-0703 | 2020-06-30 | Chg
34635 | BWM_NKT_MSSA_Spectrum Phase II Start | VA | HRD | NKT | New Kent | Bandwidth Management | POInt | Yes | No | BWM VA HRD NKT MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-05-20 | SN-0703 | 2020-06-30 | Chg
34635 | BWM_OCN_MSSA_Spectrum Phase II Start | VA | HRD | OCN | Oceana | Bandwidth Management | POInt | Yes | No | BWM VA HRD OCN MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-05-20 | SN-0703 | 2020-06-30 | Chg
34635 | BWM_LTF_MSSA_Spectrum Phase II Start | VA | HRD | LTF | Lightfoot | Bandwidth Management | POInt | Yes | No | BWM VA HRD LTF MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-05-20 | SN-0703 | 2020-06-30 | Chg
75658 | VA-WIC-1x ExtraHop EDA6200 (Dell R640) | CE | KAN | WIC | Wichita | Visibility Architecture | POInt | Yes | No | VIA CE KAN WIC Visibility Architecture Gear Deployment POR20 | Chassis | 1x ExtraHop EDA6200 (Dell R640) | 1 | 2020-02-01 | 2020-03-16 | 2020-03-30 | SN-0094 | 2020-02-06 | Chg
75658 | VA-WIC-1x Juniper EX4600 | CE | KAN | WIC | Wichita | Visibility Architecture | POInt | Yes | No | VIA CE KAN WIC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-02-01 | 2020-03-16 | 2020-03-30 | SN-0094 | 2020-02-06 | Chg
75658 | VA-WIC-1x Arista DCS-7280CR2A-60-F | CE | KAN | WIC | Wichita | Visibility Architecture | POInt | Yes | No | VIA CE KAN WIC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2019-02-01 | 2020-03-16 | 2020-03-30 | SN-0094 | 2020-02-06 | New
75658 | VA-WIC-1x Dell R640 | CE | KAN | WIC | Wichita | Visibility Architecture | POInt | Yes | No | VIA CE KAN WIC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 1 | 2019-02-01 | 2020-03-16 | 2020-03-30 | SN-0094 | 2020-02-06 | New
34635 | BWM_PRA_MSSA_Spectrum Phase II Start | VA | HRD | PRA | Princess Anne | Bandwidth Management | POInt | Yes | No | BWM VA HRD PRA MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-05-20 | SN-0703 | 2020-06-30 | Chg
75655 | Arbor 23 | CE | KAN | WIC | Wichita | Arbor DDoS | POInt | Yes | No | DDoS CE KAN WIC Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-01-31 | 2020-03-16 | 2020-03-30 | SN-0107 | 2020-02-06 | Chg
34635 | BWM_NRF_VIDEO SG_2020 DOCSIS node split-based Video SG | VA | HRD | NRF | Norfolk | Bandwidth Management | POInt | Yes | No | BWM VA HRD NRF MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-05-20 | SN-0703 | 2020-06-30 | Chg
34635 | BWM _CHS_MSSA_Spectrum Phase II Start | VA | HRD | CHS | Chesapeake | Bandwidth Management | POInt | Yes | No | BWM VA HRD CHS MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-05-20 | SN-0703 | 2020-06-30 | Chg
34635 | BWM_NRF_MSSA_Spectrum Phase II Start | VA | HRD | NRF | Norfolk | Bandwidth Management | POInt | Yes | No | BWM VA HRD NRF MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-05-20 | SN-0703 | 2020-06-30 | Chg
54570 | CFS NE RHD CRN HV-CFS Augment POR20 - 3 | NE | RHD | CRN | Cranston | Critical Facilities Sustaining (Field) | POInt | Yes | No | CFS NE RHD CRN HV-CFS Augment POR20 - 3 | Labor | No Equipment | 1 | 2020-03-09 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
54570 | CFS CE KAN MNT SC-CFS Augment POR20 | CE | KAN | MNT | Manhattan | Critical Facilities Sustaining (Field) | POInt | Yes | No | CFS CE KAN MNT SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
54570 | CFS CE TUL BRD SC-CFS Augment POR20 | CE | TUL | BRD | Braden | Critical Facilities Sustaining (Field) | POInt | Yes | No | CFS CE TUL BRD SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-17 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
54570 | CFS CE KAN SAL SC-CFS Augment POR20 | CE | KAN | SAL | Salina | Critical Facilities Sustaining (Field) | POInt | Yes | No | CFS CE KAN SAL SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
54570 | CFS CE KAN HUT SC-CFS Augment POR20 | CE | KAN | HUT | Hutchinson | Critical Facilities Sustaining (Field) | POInt | Yes | No | CFS CE KAN HUT SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
54570 | CFS CE KAN DBY SC-CFS Augment POR20 | CE | KAN | DBY | Derby | Critical Facilities Sustaining (Field) | POInt | Yes | No | CFS CE KAN DBY SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
54570 | CFS CE KAN TOP SC-CFS Augment POR20 | CE | KAN | TOP | Topeka | Critical Facilities Sustaining (Field) | POInt | Yes | No | CFS CE KAN TOP SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
54572 | CFS VA HRD PTM BS-CFS Augment POR20 | VA | HRD | PTM | Portsmouth (VA) | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD PTM BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
54572 | CFS VA ROA RON BU-CFS Augment POR20 | VA | ROA | RON | Roanoke | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA ROA RON BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-06 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
54572 | CFS VA HRD NWP FF-CFS Augment POR20 | VA | HRD | NWP | Newport News | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD NWP FF-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-20 |  | SB-0046 | 2020-02-07 | New
54570 | CFS CE KAN DCY SC-CFS Augment POR20 | CE | KAN | DCY | Dodge City | Critical Facilities Sustaining (Field) | POInt | Yes | No | CFS CE KAN DCY SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
54572 | CFS VA NVA RHL BS-CFS Augment POR20 | VA | NVA | RHL | Rose Hill | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA NVA RHL BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
34976 | CFG NE RHD PRV BD-CFG Deployment POR20 | NE | RHD | PRV | Providence | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE RHD PRV BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | SN-0411 | 2020-03-27
34971 | CFG CA ORG RSM BS-CFG Deployment POR20 | CA | ORG | RSM | Rancho Santa Margarita | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA ORG RSM BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | SN-0262 | 2020-02-28 | New
34971 | CFG CA ORG AVJ BS-CFG Augment POR20 | CA | ORG | AVJ | Aliso Viejo | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA ORG AVJ BS-CFG Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-20 |  | SN-0130 | 2020-02-06 | Chg
34971 | CFG CA SAN DWN RC-CFG Deployment POR20 | CA | SAN | DWN | Downtown | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA SAN DWN RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | SN-0262 | 2020-02-28 | New
34976 | CFG NE CON MAN GN-CFG Deployment POR20 | NE | CON | MAN | Manchester | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE CON MAN GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-03-20 |  | SN-0130 | 2020-02-06 | Chg
34974 | CFG SE NOR CLR RK-CFG Deployment POR20 | SE | NOR | CLR | Metairie | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SE NOR CLR RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | SN-0262 | 2020-02-28
34976 | CFG NE RHD PRV RK-CFG Deployment POR20 | NE | RHD | PRV | Providence | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE RHD PRV RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | SN-0411 | 2020-03-27
54572 | CFS VA HRD NKT BS-CFS Augment POR20 | VA | HRD | NKT | New Kent | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD NKT BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
34971 | CFG CA ORG ORG BS-CFG Augment POR20 | CA | ORG | ORG | Orange | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA ORG ORG BS-CFG Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-20 |  | SN-0130 | 2020-02-06 | Chg
34971 | CFG CA ORG DNP BS-CFG Augment POR20 | CA | ORG | DNP | Dana Point | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA ORG DNP BS-CFG Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-20 |  | SN-0130 | 2020-02-06 | Chg
34971 | CFG CA ORG IRV BS-CFG Augment POR20 | CA | ORG | IRV | Irvine | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA ORG IRV BS-CFG Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-20 |  | SN-0130 | 2020-02-06 | Chg
34976 | CFG NE CLE CLV FF-CFG Deployment POR20 | NE | CLE | CLV | Cleveland | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE CLE CLV FF-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-16 | 2020-03-20 |  | SN-0411 | 2020-03-27
34976 | CFG NE CON MAN BS-CFG Deployment POR20 | NE | CON | MAN | Manchester | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE CON MAN BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-03-20 |  | SN-0130 | 2020-02-06 | Chg
54572 | CFS VA HRD NWP BS-CFS Augment POR20 | VA | HRD | NWP | Newport News | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD NWP BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
34970 | CFG SW LAS OSB HV-CFG Deployment POR20 | SW | LAS | OSB | Oso Blanca | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW LAS OSB HV-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | SN-0262 | 2020-02-28
34976 | CFG NE CLE CLV RK-CFG Deployment POR20 | NE | CLE | CLV | Cleveland | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE CLE CLV RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-03-20 |  | SN-0130 | 2020-02-06 | Chg
54572 | CFS VA NVA DRA SC-CFS Augment POR20 | VA | NVA | DRA | Dranesville | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA NVA DRA SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-09 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
54572 | CFS VA NVA RHL BU-CFS Augment POR20 | VA | NVA | RHL | Rose Hill | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA NVA RHL BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-17 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
54572 | CFS VA NVA MFD AC-CFS Augment POR20 | VA | NVA | MFD | Merrifield | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA NVA MFD AC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-09 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
54572 | CFS VA NVA FST BS-CFS Augment POR20 | VA | NVA | FST | Fairfax Station | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA NVA FST BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
34974 | CFG SE BTR BTR RK-CFG Deployment POR20 | SE | BTR | BTR | Baton Rouge | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SE BTR BTR RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | SN-0262 | 2020-02-28
34971 | CFG CA SAN ELC RK-CFG Deployment POR20 | CA | SAN | ELC | El Cajon | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA SAN ELC RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | SN-0262 | 2020-02-28
54572 | CFS VA HRD PTM FF-CFS Augment POR20 | VA | HRD | PTM | Portsmouth (VA) | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD PTM FF-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-20 |  | SB-0046 | 2020-02-07 | New
54572 | CFS VA HRD NRF BS-CFS Augment POR20 | VA | HRD | NRF | Norfolk | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD NRF BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
34974 | CFG SE BTR SPC AC-CFG Deployment POR20 | SE | BTR | SPC | Pecue | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SE BTR SPC AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | SN-0262 | 2020-02-28
54572 | CFS VA NVA FLK SC-CFS Augment POR20 | VA | NVA | FLK | Fair Lakes | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA NVA FLK SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-09 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
34971 | CFG CA SAN FED RC-CFG Deployment POR20 | CA | SAN | FED | Federal | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA SAN FED RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | SN-0262 | 2020-02-28
34974 | CFG SE MGA MCN RK-CFG Deployment POR20 | SE | MGA | MCN | Macon | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SE MGA MCN RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | SN-0262 | 2020-02-28
54572 | CFS VA NVA GCR SC-CFS Augment POR20 | VA | NVA | GCR | Gunston | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA NVA GCR SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-09 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
54572 | CFS VA HRD JCC BS-CFS Augment POR20 | VA | HRD | JCC | James City County | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD JCC BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
34971 | CFG CA SAN DWN RK-CFG Deployment POR20 | CA | SAN | DWN | Downtown | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA SAN DWN RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | SN-0411 | 2020-03-27
54573 | CFG SW ARZ BEL BD-CFG Deployment POR20 | SW | ARZ | BEL | Bell | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFG SW ARZ BEL BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | SN-0411 | 2020-03-27
34971 | CFG CA ORG AVJ BS-CFG Deployment POR20 | CA | ORG | AVJ | Aliso Viejo | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA ORG AVJ BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | SN-0411 | 2020-03-27
34974 | CFG SE LFY LFY RK-CFG Deployment POR20 | SE | LFY | LFY | Lafayette | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SE LFY LFY RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | SN-0262 | 2020-02-28
34971 | CFG CA ORG RSM RK-CFG Deployment POR20 | CA | ORG | RSM | Rancho Santa Margarita | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA ORG RSM RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | SN-0262 | 2020-02-28 | New
54572 | CFS VA NVA DRA BS-CFS Augment POR20 | VA | NVA | DRA | Dranesville | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA NVA DRA BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
54572 | CFS VA HRD GLO BS-CFS Augment POR20 | VA | HRD | GLO | Gloucester | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD GLO BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
54572 | CFS VA HRD HCK BU-CFS Augment POR20 | VA | HRD | HCK | Hickory | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD HCK BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
54572 | CFS VA HRD LTF FF-CFS Augment POR20 | VA | HRD | LTF | Lightfoot | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD LTF FF-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-20 |  | SB-0046 | 2020-02-07 | New
34971 | CFG CA ORG ORG BS-CFG Deployment POR20 | CA | ORG | ORG | Orange | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA ORG ORG BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | SN-0411 | 2020-03-27
34975 | CFG VA NVA FBG BD-CFG Deployment POR20 | VA | NVA | FBG | Fredericksburg | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA NVA FBG BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | SN-0262 | 2020-02-28
34971 | CFG CA SAN OCE RK-CFG Deployment POR20 | CA | SAN | OCE | Oceanside | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA SAN OCE RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | SN-0262 | 2020-02-28
34971 | CFG CA SAN PWY BS-CFG Deployment POR20 | CA | SAN | PWY | Poway | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA SAN PWY BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | SN-0262 | 2020-02-28
34971 | CFG CA ORG PAV BS-CFG Augment POR20 | CA | ORG | PAV | Palos Verdes | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA ORG PAV BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-03-20 |  | SN-0130 | 2020-02-06 | Chg
34974 | CFG SE GAN GNS RK-CFG Deployment POR20 | SE | GAN | GNS | Gainesville | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SE GAN GNS RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | SN-0262 | 2020-02-28
34974 | CFG SE MGA WRB RK-CFG Deployment POR20 | SE | MGA | WRB | Warner Robins | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SE MGA WRB RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | SN-0411 | 2020-03-27
54572 | CFS VA NVA FBG BS-CFS Augment POR20 | VA | NVA | FBG | Fredericksburg | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA NVA FBG BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
54572 | CFS VA HRD GBR BS-CFS Augment POR20 | VA | HRD | GBR | Greenbrier | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD GBR BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
54572 | CFS VA HRD CHS BS-CFS Augment POR20 | VA | HRD | CHS | Chesapeake | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD CHS BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-20 |  | SB-0046 | 2020-02-07 | New
34975 | CFG VA NVA MFD BD-CFG Deployment POR20 | VA | NVA | MFD | Merrifield | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA NVA MFD BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | SN-0262 | 2020-02-28
34971 | CFG CA ORG DNP BS-CFG Deployment POR20 | CA | ORG | DNP | Dana Point | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA ORG DNP BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | SN-0411 | 2020-03-27
34976 | CFG NE CON ENF RK-CFG Deployment POR20 | NE | CON | ENF | Enfield | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE CON ENF RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | SN-0411 | 2020-03-27
54572 | CFS VA NVA GCR BU-CFS Augment POR20 | VA | NVA | GCR | Gunston | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA NVA GCR BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-17 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
54572 | CFS VA HRD NKT FF-CFS Augment POR20 | VA | HRD | NKT | New Kent | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD NKT FF-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-20 |  | SB-0046 | 2020-02-07 | New
54572 | CFS VA NVA FST BU-CFS Augment POR20 | VA | NVA | FST | Fairfax Station | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA NVA FST BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-17 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
34976 | CFG NE CLE CLV RC-CFS Deployment POR20 | NE | CLE | CLV | Cleveland | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE CLE CLV RC-CFS Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | SN-0262 | 2020-02-28
54572 | CFS VA HRD LTF AC-CFS Augment POR20 | VA | HRD | LTF | Lightfoot | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD LTF AC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-17 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
54572 | CFS VA HRD JEF BU-CFS Augment POR20 | VA | HRD | JEF | Jefferson Ave | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD JEF BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
54572 | CFS VA NVA MFD RC-CFS Augment POR20 | VA | NVA | MFD | Merrifield | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA NVA MFD RC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-09 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
54572 | CFS VA HRD HCK BS-CFS Augment POR20 | VA | HRD | HCK | Hickory | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD HCK BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
54572 | CFS VA HRD LTF BS-CFS Augment POR20 | VA | HRD | LTF | Lightfoot | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD LTF BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
34975 | CFG VA HRD PRA BD-CFG Deployment POR20 | VA | HRD | PRA | Princess Anne | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA HRD PRA BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | SN-0262 | 2020-02-28
34974 | CFG SE NOR NOE AC-CFG Deployment POR20 | SE | NOR | NOE | New Orleans East | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SE NOR NOE AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | SN-0262 | 2020-02-28
34971 | CFG CA SAN CHU RC-CFG Deployment POR20 | CA | SAN | CHU | Chula Vista | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA SAN CHU RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | SN-0262 | 2020-02-28 | New
34976 | CFG NE RHD RMD RK-CFG Deployment POR20 | NE | RHD | RMD | Richmond (RI) | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE RHD RMD RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-16 | 2020-03-20 |  | SN-0411 | 2020-03-27
54572 | CFS VA HRD PRA BS-CFS Augment POR20 | VA | HRD | PRA | Princess Anne | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD PRA BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
54572 | CFS VA NVA FST SC-CFS Augment POR20 | VA | NVA | FST | Fairfax Station | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA NVA FST SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-09 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
34974 | CFG SE BTR SPC RK-CFG Deployment POR20 | SE | BTR | SPC | Pecue | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SE BTR SPC RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | SN-0411 | 2020-03-27
54572 | CFS VA NAT MCB BU-CFS Augment POR20 | VA | NVA | MFD | Merrifield | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA NAT MCB BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-17 | 2020-03-20 |  | SB-0091 | 2020-03-27 | New
34619 | CB Transport - New Router Waterloo - WLH - Optics | CE | OKC | WLH | Waterloo | CB - Metro Core | POInt | Yes | Yes | CBMC CE OKC WLH Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-02-15 | 2020-03-30 |  | SN-0329 | 2020-03-03 | Chg
34619 | CB Transport - New Router Waterloo - OKC - Card Add | CE | OKC | OKC | OKC MTC | CB - Metro Core | POInt | Yes | Yes | CBMC CE OKC OKC Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-02-15 | 2020-03-30 |  | SN-0329 | 2020-03-03 | Chg
34619 | TULVOKFZ9DW-XR03.MTN.TUL.OK-100G CARD | CE | TUL | TUL | Tulsa | CB - Metro Core | POInt | Yes | Yes | CBMC CE TUL TUL 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 3 | 2020-02-15 | 2020-03-30 |  | SN-0329 | 2020-03-03 | Chg
34619 | CB Transport - New Router Waterloo - NOR - Chassis Add | CE | OKC | NOR | Norman | CB - Metro Core | POInt | Yes | Yes | CBMC CE OKC NOR Cisco M6_M15 Chassis Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 1 | 2020-02-15 | 2020-03-30 |  | SN-0329 | 2020-03-03 | Chg
34619 | CB Transport - New Router Bellevue - BLV - Card Add | CE | OMA | BLV | Bellevue | CB - Metro Core | POInt | Yes | Yes | CBMC CE OMA BLV Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-02-15 | 2020-03-30 |  | SN-0329 | 2020-03-03 | Chg
34619 | xr01.mtc.okc.ok-100G CARD | CE | OKC | OKC | OKC MTC | CB - Metro Core | POInt | Yes | Yes | CBMC CE OKC OKC 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 3 | 2020-02-15 | 2020-03-30 |  | SN-0329 | 2020-03-03 | Chg
34619 | xr01.nor.okc.ok-100G CARD | CE | OKC | NOR | Norman | CB - Metro Core | POInt | Yes | Yes | CBMC CE OKC NOR 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-02-15 | 2020-03-30 |  | SN-0329 | 2020-03-03 | Chg
35175 | NEXUS-RKH-3048-01 | NE | CON | RKH | Rocky Hill | Metro Routers | POInt | Yes | Yes | MRTR NE CON RKH Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 | 2020-01-01 | 2020-03-30 | 2020-03-30 | SN-0555 | 2020-05-12 | Chg
35175 | NEXUS-RKH-93108-01 | NE | CON | RKH | Rocky Hill | Metro Routers | POInt | Yes | Yes | MRTR NE CON RKH Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-01-01 | 2020-03-30 | 2020-03-30 | SN-0555 | 2020-05-12 | Chg
34635 | BWM_NKT_VIDEO SG_2020 DOCSIS node split-based Video SG | VA | HRD | NKT | New Kent | Bandwidth Management | POInt | Yes | No | BWM VA HRD NKT Video SG Augment POR20 v2 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | SN-0245 | 2020-02-24 | Chg
34636 | BWM_GNS_MSSA_Spectrum Phase II Start | SE | GAN | GNS | Gainesville | Bandwidth Management | POInt | Yes | No | BWM SE GAN GNS MSSA_Labor Only_Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-30 | 2020-03-30 | SN-0195 | 2020-01-24 | Chg
34616 | CB Transport - New Router Waterloo, Irish Lane - NOR - Card Add | CE | OKC | NOR | Norman | CB - Metro Core | POInt | Yes | No | CBMC CE OKC NOR Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-02-15 | 2020-03-30 |  | SN-0329 | 2020-03-03 | Chg
34636 | BWM_OCL_MSSA_Spectrum Phase II Start | SE | GAN | OCL | Ocala | Bandwidth Management | POInt | Yes | No | BWM SE GAN OCL MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-30 | 2020-03-30 | SN-0587 | 2020-05-14 | Chg
34636 | BWM_GNS_VIDEO SG_2020 DOCSIS node split-based Video SG I | SE | GAN | GNS | Gainesville | Bandwidth Management | POInt | Yes | No | BWM SE GAN GNS Video SG Augment POR20 v2 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | SN-0245 | 2020-02-24 | Chg
75187 | R PHY_CCAP_NWA_GMC1 | CE | NWA | NWA | Johnson | R PHY | POInt | Yes | No | R PHY CE NWA NWA RPHY CCAP Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-03-31 |  | SN-0208 | 2020-01-24 | New
35176 | MRTR NCS-Growth-DTN-NCS Line Card | CE | TUL | DTN | Downtown (TUL) | Metro Routers | POInt | Yes | No | MRTR CE TUL DTN NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-01-01 03:01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
59744 | RPHY MRTR-New-HEN-CIN-RPA-5110 | SW | LAS | HEN | Henderson | R PHY | POInt | Yes | No | R PHY SW LAS HEN R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 13 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0190 | 2020-01-23
59744 | RPHY MRTR-New-HEN-CIN-ATX-OCML | SW | LAS | HEN | Henderson | R PHY | POInt | Yes | No | R PHY SW LAS HEN R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 36 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0487 | 2020-05-12 | New
75658 | VA-OKC-1x Arista DCS-7280CR2A-60-F | CE | OKC | OKC | OKC MTC | Visibility Architecture | POInt | Yes | No | VIA CE OKC OKC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2020-02-01 | 2020-03-31 | 2020-03-23 | SN-0094 | 2020-02-06 | Chg
75658 | VA-OKC-1x Juniper EX4600 | CE | OKC | OKC | OKC MTC | Visibility Architecture | POInt | Yes | No | VIA CE OKC OKC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-02-01 | 2020-03-31 | 2020-03-23 | SN-0094 | 2020-02-06 | Chg
59744 | RPHY MRTR-New-BLU-CIN-ATX-OCML | SW | LAS | BLU | Blue Diamond | R PHY | POInt | Yes | No | R PHY SW LAS BLU R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0612 | 2020-05-29 | New
75187 | R PHY_CCAP_OMM_GMC1 | CE | OMA | OMM | Omaha | R PHY | POInt | Yes | No | R PHY CE OMA OMM RPHY CCAP Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-03-31 |  | SN-0208 | 2020-01-24 | New
74648 | RPHY MRTR-Growth-NRF-CIN-RPA-5110 | VA | HRD | NRF | Norfolk | R PHY | POInt | Yes | No | R PHY VA HRD NRF R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0190 | 2020-01-23 | Chg
59744 | RPHY MRTR-New-PEO-CIN-Nokia-OCML | SW | ARZ | PEO | Peoria | R PHY | POInt | Yes | No | R PHY SW ARZ PEO R PHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 24 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0487 | 2020-05-12 | New
59744 | RPHY MRTR-New-PEO-CIN-RPA-5110 | SW | ARZ | PEO | Peoria | R PHY | POInt | Yes | No | R PHY SW ARZ PEO R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0487 | 2020-05-12 | Chg
75658 | VA-BTR-1x ExtraHop EDA6200 (Dell R640) | SE | BTR | BTR | Baton Rouge | Visibility Architecture | POInt | Yes | No | VIA SE BTR BTR Visibility Architecture Gear Deployment POR20 | Chassis | 1x ExtraHop EDA6200 (Dell R640) | 1 | 2020-01-01 | 2020-03-31 | 2020-03-16 | SN-0094 | 2020-02-06 | Chg
75658 | VA-BTR-1x Juniper EX4600 | SE | BTR | BTR | Baton Rouge | Visibility Architecture | POInt | Yes | No | VIA SE BTR BTR Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-03-16 | SN-0094 | 2020-02-06 | Chg
75658 | VA-BTR-1x Arista DCS-7280CR2A-60-F | SE | BTR | BTR | Baton Rouge | Visibility Architecture | POInt | Yes | No | VIA SE BTR BTR Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-03-16 | SN-0094 | 2020-02-06 | New
75658 | VA-BTR-1x Niagra PT-3225 | SE | BTR | BTR | Baton Rouge | Visibility Architecture | POInt | Yes | No | VIA SE BTR BTR Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-03-16 | SN-0094 | 2020-02-06 | New
75658 | VA-BTR-1x Dell R640 | SE | BTR | BTR | Baton Rouge | Visibility Architecture | POInt | Yes | No | VIA SE BTR BTR Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 4 | 2020-01-01 | 2020-03-31 | 2020-03-16 | SN-0094 | 2020-02-06 | New
75658 | VA-ELM-1x ExtraHop EDA6200 (Dell R640) | SE | NOR | ELM | Elmwood | Visibility Architecture | POInt | Yes | No | VIA SE NOR ELM Visibility Architecture Gear Deployment POR20 | Chassis | 1x ExtraHop EDA6200 (Dell R640) | 1 | 2020-01-01 | 2020-03-31 | 2020-03-16 | SN-0094 | 2020-02-06 | Chg
75658 | VA-ELM-1x Juniper EX4600 | SE | NOR | ELM | Elmwood | Visibility Architecture | POInt | Yes | No | VIA SE NOR ELM Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-03-16 | SN-0094 | 2020-02-06 | Chg
75658 | VA-ELM-1x Dell R640 | SE | NOR | ELM | Elmwood | Visibility Architecture | POInt | Yes | No | VIA SE NOR ELM Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-03-16 | SN-0094 | 2020-02-06 | New
75246 | R PHY_CCAP_ELM_GMC1 | SE | NOR | ELM | Elmwood | R PHY | POInt | Yes | No | R PHY SE NOR ELM RPHY CCAP Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-03-31 |  | SN-0208 | 2020-01-24 | New
59744 | RPHY MRTR-New-TEN-CIN-DPA-5200 (100G DPIC) | SW | LAS | TEN | Tenaya | R PHY | POInt | Yes | No | R PHY SW LAS TEN R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0190 | 2020-01-23 | Chg
35170 | MRTR NCS-Growth-ELC-NCS Line Card | CA | SAN | ELC | El Cajon | Metro Routers | POInt | Yes | No | MRTR CA SAN ELC NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-01-01 03:01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
59744 | RPHY MRTR-New-BLU-CIN-RPA-5110 | SW | LAS | BLU | Blue Diamond | R PHY | POInt | Yes | No | R PHY SW LAS BLU R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 7 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0190 | 2020-01-23 | New
35173 | MRTR SLR-New-TEN-SLR-ASR9906 | SW | LAS | TEN | Tenaya | Metro Routers | POInt | Yes | Yes | MRTR SW LAS TEN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
75244 | RPHY MRTR-New-PTH-CIN-RPA-5110 | NE | RHD | PTH | Portsmouth (RI) | R PHY | POInt | Yes | Yes | R PHY NE RHD PTH RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23 | New
75244 | RPHY MRTR-New-PTH-CIN-DPA-5200 | NE | RHD | PTH | Portsmouth (RI) | R PHY | POInt | Yes | Yes | R PHY NE RHD PTH RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23 | New
75244 | RPHY MRTR-New-PTH-CIN MGMT-2K | NE | RHD | PTH | Portsmouth (RI) | R PHY | POInt | Yes | Yes | R PHY NE RHD PTH RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23 | New
75244 | RPHY MRTR-New-PTH-CIN-ATX-OCML | NE | RHD | PTH | Portsmouth (RI) | R PHY | POInt | Yes | Yes | R PHY NE RHD PTH RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | SN-0606 | 2020-05-22 | New
75245 | RPHY MRTR-New-SOU-CIN-RPA-5110 | CE | OMA | SOU | South (OM) | R PHY | POInt | Yes | Yes | R PHY CE OMA SOU RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23 | New
75245 | RPHY MRTR-New-SOU-CIN-DPA-5200 | CE | OMA | SOU | South (OM) | R PHY | POInt | Yes | Yes | R PHY CE OMA SOU RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23 | New
75245 | RPHY MRTR-New-SOU-CIN MGMT-2K | CE | OMA | SOU | South (OM) | R PHY | POInt | Yes | Yes | R PHY CE OMA SOU RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23 | New
75245 | RPHY MRTR-New-SOU-CIN-Nokia2-OCML | CE | OMA | SOU | South (OM) | R PHY | POInt | Yes | Yes | R PHY CE OMA SOU RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | SN-0606 | 2020-05-22 | New
35175 | MRTR OOB-New-PTH-OOB Server | NE | RHD | PTH | Portsmouth (RI) | Metro Routers | POInt | Yes | Yes | MRTR NE RHD PTH OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | New
35170 | MRTR NCS-Growth-IRV-NCS Line Card | CA | ORG | IRV | Irvine | Metro Routers | POInt | Yes | Yes | MRTR CA ORG IRV NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-01-01 03:01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
74648 | RPHY MRTR-Growth-PRA-CIN-RPA-5110 | VA | HRD | PRA | Princess Anne | R PHY | POInt | Yes | Yes | R PHY VA HRD PRA RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0487 | 2020-05-12 | Chg
35175 | MRTR NCS-Growth-PTH-100G Grow | NE | RHD | PTH | Portsmouth (RI) | Metro Routers | POInt | Yes | Yes | MRTR NE RHD WWK 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | New
35177 | MRTR OOB-New-VBC-OOB Server | VA | HRD | VBC | Virginia Beach | Metro Routers | POInt | Yes | Yes | MRTR VA HRD VBC OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 4 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
75187 | R PHY_CCAP_QNC_CBR8-1 | CE | TUL | QNC | Quincy | R PHY | POInt | Yes | Yes | R PHY CE TUL QNC RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | SN-0208 | 2020-01-24 | New
75187 | R PHY_CCAP_QNC_Boundary_Clocks-1 | CE | TUL | QNC | Quincy | R PHY | POInt | Yes | Yes | R PHY CE TUL QNC RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0605 | 2020-05-22 | Chg
35176 | MRTR OOB-New-TUL-OOB Server | CE | TUL | TUL | Tulsa | Metro Routers | POInt | Yes | Yes | MRTR CE TUL TUL OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
75245 | RPHY MRTR-New-QNC-CIN MGMT-2K | CE | TUL | QNC | Quincy | R PHY | POInt | Yes | Yes | R PHY CE TUL QNC RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23
75245 | RPHY MRTR-New-QNC-CIN-DPA-5200 | CE | TUL | QNC | Quincy | R PHY | POInt | Yes | Yes | R PHY CE TUL QNC RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23
75245 | RPHY MRTR-New-QNC-CIN-RPA-5110 | CE | TUL | QNC | Quincy | R PHY | POInt | Yes | Yes | R PHY CE TUL QNC RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23
75245 | RPHY MRTR-New-QNC-CIN-Nokia2-OCML | CE | TUL | QNC | Quincy | R PHY | POInt | Yes | Yes | R PHY CE TUL QNC RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | SN-0606 | 2020-05-22 | New
74648 | RPHY MRTR-Growth-CHS-CIN-RPA-5110 | VA | HRD | CHS | Chesapeake | R PHY | POInt | Yes | Yes | R PHY VA HRD CHS RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0190 | 2020-01-23 | Chg
35174 | MRTR SLR-New-BTR-SLR-ASR9906 | SE | BTR | BTR | Baton Rouge | Metro Routers | POInt | Yes | Yes | MRTR SE BTR BTR SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-11-30 | SN-0662 | 2020-06-14 | Chg
35176 | MRTR OOB-New-OWA-OOB Server | CE | TUL | OWA | Owasso | Metro Routers | POInt | Yes | Yes | MRTR CE TUL OWA OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
75655 | Arbor 1 | COR | NAT | LA1 | Los Angeles - Equinix (cage 280/610) | Arbor DDoS | POInt | Yes | No | DDoS CA NAT LA1 Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-02-28 | 2020-03-31 | 2020-04-30 | SN-0220 | 2020-02-03 | Chg
74548 | R PHY_CCAP_NRF_CBR8-1 | VA | HRD | NRF | Norfolk | R PHY | POInt | Yes | Yes | R PHY VA HRD NRF RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | SN-0208 | 2020-01-24 | New
74548 | R PHY_CCAP_NRF_Boundary_Clocks-1 | VA | HRD | NRF | Norfolk | R PHY | POInt | Yes | Yes | R PHY VA HRD NRF RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0605 | 2020-05-22 | Chg
35170 | MRTR NCS-Growth-VST-NCS Line Card | CA | SAN | VST | Vista | Metro Routers | POInt | Yes | Yes | MRTR CA SAN VST NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-01-01 03:01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
59744 | RPHY MRTR-Growth-MSA-CIN-RPA-5110 | SW | ARZ | MSA | Mesa | R PHY | POInt | Yes | Yes | R PHY SW ARZ MSA RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0190 | 2020-01-23 | Chg
75245 | RPHY MRTR-New-WLK-CIN MGMT-2K | CE | OKC | WLK | Walker Hub | R PHY | POInt | Yes | Yes | R PHY CE OKC WLK RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23
75245 | RPHY MRTR-New-WLK-CIN-DPA-5200 | CE | OKC | WLK | Walker Hub | R PHY | POInt | Yes | Yes | R PHY CE OKC WLK RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23
75245 | RPHY MRTR-New-WLK-CIN-RPA-5110 | CE | OKC | WLK | Walker Hub | R PHY | POInt | Yes | Yes | R PHY CE OKC WLK RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23
75245 | RPHY MRTR-New-WLK-CIN-Nokia2-OCML | CE | OKC | WLK | Walker Hub | R PHY | POInt | Yes | Yes | R PHY CE OKC WLK RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | SN-0606 | 2020-05-22 | New
75245 | RPHY MRTR-New-OWA-CIN-Nokia2-OCML | CE | TUL | OWA | Owasso | R PHY | POInt | Yes | Yes | R PHY CE TUL OWA RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | SN-0606 | 2020-05-22 | New
75245 | RPHY MRTR-New-OWA-CIN MGMT-2K | CE | TUL | OWA | Owasso | R PHY | POInt | Yes | Yes | R PHY CE TUL OWA RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23
75245 | RPHY MRTR-New-OWA-CIN-DPA-5200 | CE | TUL | OWA | Owasso | R PHY | POInt | Yes | Yes | R PHY CE TUL OWA RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23
75245 | RPHY MRTR-New-OWA-CIN-RPA-5110 | CE | TUL | OWA | Owasso | R PHY | POInt | Yes | Yes | R PHY CE TUL OWA RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23
75245 | RPHY MRTR-New-CLH-CIN-Nokia2-OCML | CE | OKC | CLH | County Line | R PHY | POInt | Yes | Yes | R PHY CE OKC CLH RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | SN-0606 | 2020-05-22 | New
75245 | RPHY MRTR-New-CLH-CIN-RPA-5110 | CE | OKC | CLH | County Line | R PHY | POInt | Yes | Yes | R PHY CE OKC CLH RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23 | New
75245 | RPHY MRTR-New-CLH-CIN-DPA-5200 | CE | OKC | CLH | County Line | R PHY | POInt | Yes | Yes | R PHY CE OKC CLH RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23 | New
75245 | RPHY MRTR-New-CLH-CIN MGMT-2K | CE | OKC | CLH | County Line | R PHY | POInt | Yes | Yes | R PHY CE OKC CLH RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23 | New
75243 | RPHY MRTR-New-MCY-CIN MGMT-2K | SE | NOR | MCY | Mid-City | R PHY | POInt | Yes | Yes | R PHY SE NOR MCY RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23
75243 | RPHY MRTR-New-MCY-CIN-DPA-5200 | SE | NOR | MCY | Mid-City | R PHY | POInt | Yes | Yes | R PHY SE NOR MCY RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23
75243 | RPHY MRTR-New-MCY-CIN-RPA-5110 | SE | NOR | MCY | Mid-City | R PHY | POInt | Yes | Yes | R PHY SE NOR MCY RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23
75243 | RPHY MRTR-New-MCY-CIN-ATX-OCML | SE | NOR | MCY | Mid-City | R PHY | POInt | Yes | Yes | R PHY SE NOR MCY RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | SN-0606 | 2020-05-22 | New
75245 | RPHY MRTR-New-FAY-CIN MGMT-2K | CE | NWA | FAY | Fayetteville | R PHY | POInt | Yes | Yes | R PHY CE NWA FAY RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23
75245 | RPHY MRTR-New-FAY-CIN-DPA-5200 | CE | NWA | FAY | Fayetteville | R PHY | POInt | Yes | Yes | R PHY CE NWA FAY RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23
75245 | RPHY MRTR-New-FAY-CIN-RPA-5110 | CE | NWA | FAY | Fayetteville | R PHY | POInt | Yes | Yes | R PHY CE NWA FAY RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23
75245 | RPHY MRTR-New-FAY-CIN-Nokia2-OCML | CE | NWA | FAY | Fayetteville | R PHY | POInt | Yes | Yes | R PHY CE NWA FAY RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | SN-0606 | 2020-05-22 | New
75245 | RPHY MRTR-New-YAL-CIN MGMT-2K | CE | TUL | YAL | Yale | R PHY | POInt | Yes | Yes | R PHY CE TUL YAL RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23
75245 | RPHY MRTR-New-YAL-CIN-DPA-5200 | CE | TUL | YAL | Yale | R PHY | POInt | Yes | Yes | R PHY CE TUL YAL RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23
75245 | RPHY MRTR-New-YAL-CIN-RPA-5110 | CE | TUL | YAL | Yale | R PHY | POInt | Yes | Yes | R PHY CE TUL YAL RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23
75245 | RPHY MRTR-New-YAL-CIN-Nokia2-OCML | CE | TUL | YAL | Yale | R PHY | POInt | Yes | Yes | R PHY CE TUL YAL RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | SN-0606 | 2020-05-22 | New
75187 | R PHY_CCAP_CL_CBR8-1 | CE | OKC | CLH | County Line | R PHY | POInt | Yes | Yes | R PHY CE OKC CLH RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | SN-0208 | 2020-01-24 | New
75187 | R PHY_CCAP_CL_Boundary_Clocks-1 | CE | OKC | CLH | County Line | R PHY | POInt | Yes | Yes | R PHY CE OKC CLH RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0605 | 2020-05-22 | Chg
75187 | R PHY_CCAP_CL_QPSK-1 | CE | OKC | CLH | County Line | R PHY | POInt | Yes | Yes | R PHY CE OKC CLH RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2019-11-15 | 2020-03-31 |  | SN-0208 | 2020-01-24 | New
35170 | MRTR NCS-Growth-RSM-NCS Line Card | CA | ORG | RSM | Rancho Santa Margarita | Metro Routers | POInt | Yes | Yes | MRTR CA ORG RSM NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
35170 | MRTR NCS-Growth-RSM2-100G Grow | CA | ORG | RSM | Rancho Santa Margarita | Metro Routers | POInt | Yes | Yes | MRTR CA ORG RSM NCS Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06
75187 | R PHY_CCAP_WLK_CBR8-1 | CE | OKC | WLK | Walker Hub | R PHY | POInt | Yes | Yes | R PHY CE OKC WLK RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | SN-0208 | 2020-01-24 | New
75187 | R PHY_CCAP_WLK_Boundary_Clocks-1 | CE | OKC | WLK | Walker Hub | R PHY | POInt | Yes | Yes | R PHY CE OKC WLK RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0605 | 2020-05-22 | Chg
75187 | R PHY_CCAP_WLK_QPSK-1 | CE | OKC | WLK | Walker Hub | R PHY | POInt | Yes | Yes | R PHY CE OKC WLK RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2019-11-15 | 2020-03-31 |  | SN-0208 | 2020-01-24 | New
35176 | MRTR NCS-Growth-NOR-100G Grow | CE | OKC | NOR | Norman | Metro Routers | POInt | Yes | Yes | MRTR CE OKC NOR 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
35176 | MRTR OOB-New-NOR-OOB Server | CE | OKC | NOR | Norman | Metro Routers | POInt | Yes | Yes | MRTR CE OKC NOR 100G Grow Augment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
75187 | R PHY_CCAP_FAY_CBR8-1 | CE | NWA | FAY | Fayetteville | R PHY | POInt | Yes | Yes | R PHY CE NWA FAY RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | SN-0208 | 2020-01-24 | New
75187 | R PHY_CCAP_FAY_Boundary_Clocks-1 | CE | NWA | FAY | Fayetteville | R PHY | POInt | Yes | Yes | R PHY CE NWA FAY RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0605 | 2020-05-22 | Chg
35177 | MRTR NCS-Growth-NRF-100G Grow | VA | HRD | NRF | Norfolk | Metro Routers | POInt | Yes | Yes | MRTR VA HRD NRF 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
75187 | R PHY_CCAP_SOU_CBR8-1 | CE | OMA | SOU | South (OM) | R PHY | POInt | Yes | Yes | R PHY CE OMA SOU RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | SN-0208 | 2020-01-24 | New
75187 | R PHY_CCAP_SOU_Boundary_Clocks-1 | CE | OMA | SOU | South (OM) | R PHY | POInt | Yes | Yes | R PHY CE OMA SOU RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0605 | 2020-05-22 | Chg
75187 | R PHY_CCAP_TUL_CBR8-1 | CE | TUL | TUL | Tulsa | R PHY | POInt | Yes | Yes | R PHY CE TUL TUL RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | SN-0208 | 2020-01-24 | New
75187 | R PHY_CCAP_TUL_Boundary_Clocks-1 | CE | TUL | TUL | Tulsa | R PHY | POInt | Yes | Yes | R PHY CE TUL TUL RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0605 | 2020-05-22 | Chg
75187 | R PHY_CCAP_TUL_GMC1 | CE | TUL | TUL | Tulsa | R PHY | POInt | Yes | Yes | R PHY CE TUL TUL RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-03-31 |  | SN-0208 | 2020-01-24 | New
75187 | R PHY_CCAP_OKC_CBR8-1 | CE | OKC | OKC | OKC MTC | R PHY | POInt | Yes | Yes | R PHY CE OKC OKC RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | SN-0208 | 2020-01-24 | New
75187 | R PHY_CCAP_OKC_Boundary_Clocks-1 | CE | OKC | OKC | OKC MTC | R PHY | POInt | Yes | Yes | R PHY CE OKC OKC RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0605 | 2020-05-22 | Chg
75187 | R PHY_CCAP_OKC_GMC1 | CE | OKC | OKC | OKC MTC | R PHY | POInt | Yes | Yes | R PHY CE OKC OKC RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-03-31 |  | SN-0208 | 2020-01-24 | New
75187 | R PHY_CCAP_OKC_QPSK-1 | CE | OKC | OKC | OKC MTC | R PHY | POInt | Yes | Yes | R PHY CE OKC OKC RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2019-11-15 | 2020-03-31 |  | SN-0208 | 2020-01-24 | New
35170 | MRTR NCS-Growth-ORG-NCS Line Card | CA | ORG | ORG | Orange | Metro Routers | POInt | Yes | Yes | MRTR CA ORG ORG NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
35177 | MRTR OOB-New-NRF-OOB Server | VA | HRD | NRF | Norfolk | Metro Routers | POInt | Yes | Yes | MRTR VA HRD NRF OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 4 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
35176 | MRTR OOB-New-YAL-OOB Server | CE | TUL | YAL | Yale | Metro Routers | POInt | Yes | Yes | MRTR CE TUL YAL OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
35173 | MRTR SLR-New-BLU-SLR-ASR9906 | SW | LAS | BLU | Blue Diamond | Metro Routers | POInt | Yes | Yes | MRTR SW LAS BLU SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
74648 | RPHY MRTR-New-NRF-CIN-ATX-OCML | VA | HRD | NRF | Norfolk | R PHY | POInt | Yes | Yes | R PHY VA HRD NRF RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | SN-0606 | 2020-05-22 | New
35176 | MRTR OOB-New-NCH-OOB Server | CE | OKC | NCH | North Central | Metro Routers | POInt | Yes | Yes | MRTR CE OKC NCH OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
35173 | MRTR NCS-Growth-BLU-NCS Line Card | SW | LAS | BLU | Blue Diamond | Metro Routers | POInt | Yes | Yes | MRTR SW LAS BLU NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-01-01 03:01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
74648 | RPHY MRTR-Growth-OCN-CIN-RPA-5110 | VA | HRD | OCN | Oceana | R PHY | POInt | Yes | Yes | R PHY VA HRD OCN RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0190 | 2020-01-23 | Chg
75187 | R PHY_CCAP_BAR_CBR8-1 | CE | TUL | BAR | Broken Arrow | R PHY | POInt | Yes | Yes | R PHY CE TUL BAR RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | SN-0208 | 2020-01-24 | New
75187 | R PHY_CCAP_BAR_Boundary_Clocks-1 | CE | TUL | BAR | Broken Arrow | R PHY | POInt | Yes | Yes | R PHY CE TUL BAR RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0605 | 2020-05-22 | Chg
35171 | MRTR OOB-New-FAY-OOB Server | CE | NWA | FAY | Fayetteville | Metro Routers | POInt | Yes | Yes | MRTR CE NWA FAY OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
75245 | RPHY MRTR-New-OKC-CIN MGMT-2K | CE | OKC | OKC | OKC MTC | R PHY | POInt | Yes | Yes | R PHY CE OKC OKC RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23
75245 | RPHY MRTR-New-OKC-CIN-DPA-5200 | CE | OKC | OKC | OKC MTC | R PHY | POInt | Yes | Yes | R PHY CE OKC OKC RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23
75245 | RPHY MRTR-New-OKC-CIN-RPA-5110 | CE | OKC | OKC | OKC MTC | R PHY | POInt | Yes | Yes | R PHY CE OKC OKC RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23
75245 | RPHY MRTR-New-OKC-CIN-Nokia2-OCML | CE | OKC | OKC | OKC MTC | R PHY | POInt | Yes | Yes | R PHY CE OKC OKC RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | SN-0606 | 2020-05-22 | New
35176 | MRTR OOB-New-OKC-OOB Server | CE | OKC | OKC | OKC MTC | Metro Routers | POInt | Yes | Yes | MRTR CE OKC OKC OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 7 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
35175 | NEXUS-RMD-93108-01 | NE | RHD | RMD | Richmond (RI) | Metro Routers | POInt | Yes | Yes | MRTR NE RHD RMD Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-01-05 | 2020-03-31 | 2020-03-31 | SN-0239 | 2020-02-07 | Chg
75245 | RPHY MRTR-New-ELK-CIN MGMT-2K | CE | OMA | ELK | Elkhorn | R PHY | POInt | Yes | Yes | R PHY CE OMA ELK RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23
75245 | RPHY MRTR-New-ELK-CIN-DPA-5200 | CE | OMA | ELK | Elkhorn | R PHY | POInt | Yes | Yes | R PHY CE OMA ELK RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23
75245 | RPHY MRTR-New-ELK-CIN-RPA-5110 | CE | OMA | ELK | Elkhorn | R PHY | POInt | Yes | Yes | R PHY CE OMA ELK RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23
75245 | RPHY MRTR-New-ELK-CIN-Nokia2-OCML | CE | OMA | ELK | Elkhorn | R PHY | POInt | Yes | Yes | R PHY CE OMA ELK RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | SN-0606 | 2020-05-22 | New
35170 | MRTR NCS-Growth-ELC-100G Grow | CA | SAN | ELC | El Cajon | Metro Routers | POInt | Yes | Yes | MRTR CA SAN ELC 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 03:01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
74648 | RPHY MRTR-New-CHS-CIN MGMT-2K | VA | HRD | CHS | Chesapeake | R PHY | POInt | Yes | Yes | R PHY VA HRD CHS RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23
74648 | RPHY MRTR-New-CHS-CIN-DPA-5200 | VA | HRD | CHS | Chesapeake | R PHY | POInt | Yes | Yes | R PHY VA HRD CHS RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23
74648 | RPHY MRTR-New-CHS-CIN-RPA-5110 | VA | HRD | CHS | Chesapeake | R PHY | POInt | Yes | Yes | R PHY VA HRD CHS RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23
74648 | RPHY MRTR-New-CHS-CIN-Nokia-OCML | VA | HRD | CHS | Chesapeake | R PHY | POInt | Yes | Yes | R PHY VA HRD CHS RPHY Metro Initial Deployment POR19 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 12 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23 | New
74648 | RPHY MRTR-New-CHS-CIN-ATX-OCML2 | VA | HRD | CHS | Chesapeake | R PHY | POInt | Yes | Yes | R PHY VA HRD CHS RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | SN-0612 | 2020-05-29 | New
35170 | MRTR NCS-Growth-AVJ-100G Grow | CA | ORG | AVJ | Aliso Viejo | Metro Routers | POInt | Yes | Yes | MRTR CA ORG AVJ 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 03:01 | 2020-03-31 | 2020-05-30 | SN-0158 | 2020-02-06 | New
75187 | R PHY_CCAP_BVL_CBR8-1 | CE | NWA | BVL | Bentonville | R PHY | POInt | Yes | Yes | R PHY CE NWA BVL RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | SN-0208 | 2020-01-24 | New
75187 | R PHY_CCAP_BVL_Boundary_Clocks-1 | CE | NWA | BVL | Bentonville | R PHY | POInt | Yes | Yes | R PHY CE NWA BVL RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0605 | 2020-05-22 | Chg
35176 | MRTR OOB-New-WLH-OOB Server | CE | OKC | WLH | Waterloo | Metro Routers | POInt | Yes | Yes | MRTR CE OKC WLH OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
35171 | MRTR SLR-New-ELK-SLR-ASR9906 | CE | OMA | ELK | Elkhorn | Metro Routers | POInt | Yes | Yes | MRTR CE OMA ELK SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-09-30 | SN-0662 | 2020-06-14 | Chg
35173 | MRTR SLR-New-HEN-SLR-ASR9906 | SW | LAS | HEN | Henderson | Metro Routers | POInt | Yes | Yes | MRTR SW LAS HEN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
35177 | MRTR OOB-New-PRA-OOB Server | VA | HRD | PRA | Princess Anne | Metro Routers | POInt | Yes | Yes | MRTR VA HRD PRA OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
35170 | MRTR NCS-Growth-CHU-100G Grow | CA | SAN | CHU | Chula Vista | Metro Routers | POInt | Yes | Yes | MRTR CA SAN CHU 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
35177 | MRTR NCS-Growth-PTM-100G Grow | VA | HRD | PTM | Portsmouth (VA) | Metro Routers | POInt | Yes | Yes | MRTR VA HRD PTM OOB Deployment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
75187 | R PHY_CCAPOWA_CBR8-1 | CE | TUL | OWA | Owasso | R PHY | POInt | Yes | Yes | R PHY CE TUL OWA R PHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | SN-0208 | 2020-01-24 | New
75187 | R PHY_CCAPOWA_Boundary_Clocks-1 | CE | TUL | OWA | Owasso | R PHY | POInt | Yes | Yes | R PHY CE TUL OWA R PHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0605 | 2020-05-22 | Chg
75243 | RPHY MRTR-Growth-MCY-CIN-RPA-5110 | SE | NOR | MCY | Mid-City | R PHY | POInt | Yes | Yes | R PHY SE NOR MCY RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0190 | 2020-01-23 | Chg
75245 | RPHY MRTR-New-BVL-CIN-Nokia2-OCML | CE | NWA | BVL | Bentonville | R PHY | POInt | Yes | Yes | R PHY CE NWA BVL RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | SN-0606 | 2020-05-22 | New
75245 | RPHY MRTR-New-BVL-CIN MGMT-2K | CE | NWA | BVL | Bentonville | R PHY | POInt | Yes | Yes | R PHY CE NWA BVL RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23 | New
75245 | RPHY MRTR-New-BVL-CIN-DPA-5200 | CE | NWA | BVL | Bentonville | R PHY | POInt | Yes | Yes | R PHY CE NWA BVL RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23 | New
75245 | RPHY MRTR-New-BVL-CIN-RPA-5110 | CE | NWA | BVL | Bentonville | R PHY | POInt | Yes | Yes | R PHY CE NWA BVL RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23 | New
59744 | RPHY MRTR-New-ALI-CIN-ATX-OCML | SW | LAS | ALI | Aliante | R PHY | POInt | Yes | Yes | R PHY SW LAS ALI RPHY Metro Augment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0612 | 2020-05-29 | New
35175 | MRTR NCS-Growth-CLV-100G Grow | NE | CLE | CLV | Cleveland | Metro Routers | POInt | Yes | Yes | MRTR NE CLE CLV 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
35170 | MRTR NCS-Growth-DNP-NCS Line Card | CA | ORG | DNP | Dana Point | Metro Routers | POInt | Yes | Yes | MRTR CA ORG DNP NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
34608 | CB Transport - New Router Fairlakes - MFD - Optics | VA | NVA | MFD | Merrifield | CB - Metro Core | POInt | Yes | Yes | CBMC VA NVA MFD Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-04-15 | 2020-03-31 |  | SN-0934 | 2020-09-18 | Chg
34608 | CB Transport - New Router Tysons - MFD - Optics | VA | NVA | MFD | Merrifield | CB - Metro Core | POInt | Yes | Yes | CBMC VA NVA MFD Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-04-15 | 2020-03-31 |  | SN-0934 | 2020-09-18 | Chg
35170 | MRTR NCS-Growth-VST-100G Grow | CA | SAN | VST | Vista | Metro Routers | POInt | Yes | Yes | MRTR CA SAN VST 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
35170 | NEXUS-RSM-93108-01 | CA | ORG | RSM | Rancho Santa Margarita | Metro Routers | POInt | Yes | Yes | MRTR CA ORG RSM Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-01-01 03:01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
35170 | MRTR NCS-Growth-CHU-NCS Line Card | CA | SAN | CHU | Chula Vista | Metro Routers | POInt | Yes | Yes | MRTR CA SAN CHU NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
35175 | NEXUS-MAN-3048-01 | NE | CON | MAN | Manchester | Metro Routers | POInt | Yes | Yes | MRTR NE CON MAN Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0555 | 2020-05-12 | Chg
35175 | NEXUS-MAN-93108-01 | NE | CON | MAN | Manchester | Metro Routers | POInt | Yes | Yes | MRTR NE CON MAN Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 4 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0555 | 2020-05-12 | Chg
35175 | NEXUS-MAN-93180-01 | NE | CON | MAN | Manchester | Metro Routers | POInt | Yes | Yes | MRTR NE CON MAN Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 4 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0555 | 2020-05-12 | Chg
35176 | MRTR OOB-New-QNC-OOB Server | CE | TUL | QNC | Quincy | Metro Routers | POInt | Yes | Yes | MRTR CE TUL QNC OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
75246 | R PHY_CCAP_MCY_CBR8-1 | SE | NOR | MCY | Mid-City | R PHY | POInt | Yes | Yes | R PHY SE NOR MCY RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | SN-0208 | 2020-01-24 | New
75246 | R PHY_CCAP_MCY_Boundary_Clocks-1 | SE | NOR | MCY | Mid-City | R PHY | POInt | Yes | Yes | R PHY SE NOR MCY RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0605 | 2020-05-22 | Chg
35177 | MRTR OOB-New-NWP-OOB Server | VA | HRD | NWP | Newport News | Metro Routers | POInt | Yes | Yes | MRTR VA HRD NWP OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 4 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
75187 | R PHY_CCAP_ELK_CBR8-1 | CE | OMA | ELK | Elkhorn | R PHY | POInt | Yes | Yes | R PHY CE OMA ELK RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | SN-0208 | 2020-01-24 | New
75187 | R PHY_CCAP_ELK_Boundary_Clocks-1 | CE | OMA | ELK | Elkhorn | R PHY | POInt | Yes | Yes | R PHY CE OMA ELK RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0605 | 2020-05-22 | Chg
35171 | MRTR OOB-New-ELK-OOB Server | CE | OMA | ELK | Elkhorn | Metro Routers | POInt | Yes | Yes | MRTR CE OMA ELK 100G Grow Augment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
35177 | MRTR OOB-New-RON-OOB Server | VA | ROA | RON | Roanoke | Metro Routers | POInt | Yes | Yes | MRTR VA ROA RON OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
35175 | NEXUS-MER-3048-01 | NE | CON | MER | Meriden | Metro Routers | POInt | Yes | Yes | MRTR NE CON MER Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 | 2020-01-05 | 2020-03-31 | 2020-03-31 | SN-0239 | 2020-02-07 | Chg
35175 | NEXUS-MER-93108-01 | NE | CON | MER | Meriden | Metro Routers | POInt | Yes | Yes | MRTR NE CON MER Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-01-05 | 2020-03-31 | 2020-03-31 | SN-0239 | 2020-02-07 | Chg
35170 | MRTR NCS-Growth-ORG-100G Grow | CA | ORG | ORG | Orange | Metro Routers | POInt | Yes | Yes | MRTR CA ORG ORG 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
35177 | MRTR NCS-Growth-FLK-100G Grow | VA | NVA | FLK | Fair Lakes | Metro Routers | POInt | Yes | Yes | MRTR VA NVA FLK 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
75245 | RPHY MRTR-New-BAR-CIN MGMT-2K | CE | TUL | BAR | Broken Arrow | R PHY | POInt | Yes | Yes | R PHY CE TUL BAR RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23
75245 | RPHY MRTR-New-BAR-CIN-DPA-5200 | CE | TUL | BAR | Broken Arrow | R PHY | POInt | Yes | Yes | R PHY CE TUL BAR RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23
75245 | RPHY MRTR-New-BAR-CIN-RPA-5110 | CE | TUL | BAR | Broken Arrow | R PHY | POInt | Yes | Yes | R PHY CE TUL BAR RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23
75245 | RPHY MRTR-New-BAR-CIN-Nokia2-OCML | CE | TUL | BAR | Broken Arrow | R PHY | POInt | Yes | Yes | R PHY CE TUL BAR RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | SN-0606 | 2020-05-22 | New
34608 | CB Transport - New Router Fairlakes - FLK - Optics | VA | NVA | FLK | Fair Lakes | CB - Metro Core | POInt | Yes | Yes | CBMC VA NVA FLK Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-04-15 | 2020-03-31 |  | SN-0934 | 2020-09-18 | Chg
35169 | MRTR NCS-Growth-PEO-100G Grow | SW | ARZ | PEO | Peoria | Metro Routers | POInt | Yes | Yes | MRTR SW ARZ MSA 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-04-30 | SN-0158 | 2020-02-06 | New
75245 | RPHY MRTR-New-TUL-CIN MGMT-2K | CE | TUL | TUL | Tulsa | R PHY | POInt | Yes | Yes | R PHY CE TUL TUL RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23
75245 | RPHY MRTR-New-TUL-CIN-DPA-5200 | CE | TUL | TUL | Tulsa | R PHY | POInt | Yes | Yes | R PHY CE TUL TUL RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23
75245 | RPHY MRTR-New-TUL-CIN-RPA-5110 | CE | TUL | TUL | Tulsa | R PHY | POInt | Yes | Yes | R PHY CE TUL TUL RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0211 | 2020-01-23
75245 | RPHY MRTR-New-TUL-CIN-Nokia2-OCML | CE | TUL | TUL | Tulsa | R PHY | POInt | Yes | Yes | R PHY CE TUL TUL RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 12 | 2019-11-15 | 2020-03-31 |  | SN-0606 | 2020-05-22 | New
35177 | MRTR NCS-Growth-OCN-100G Grow | VA | HRD | OCN | Oceana | Metro Routers | POInt | Yes | Yes | MRTR VA HRD OCN 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
35169 | MRTR NCS-Growth-BEL-NCS Line Card | SW | ARZ | BEL | Bell | Metro Routers | POInt | Yes | Yes | MRTR SW ARZ BEL NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-01-01 03:01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
74548 | R PHY_CCAP_CHS_CBR8-1 | VA | HRD | CHS | Chesapeake | R PHY | POInt | Yes | Yes | R PHY VA HRD CHS RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-03-31 |  | SN-0208 | 2020-01-24 | New
74548 | R PHY_CCAP_CHS_Boundary_Clocks-1 | VA | HRD | CHS | Chesapeake | R PHY | POInt | Yes | Yes | R PHY VA HRD CHS RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-03-31 |  | SN-0605 | 2020-05-22 | Chg
35175 | MRTR NCS-Growth-PAW-100G Grow | NE | RHD | PAW | Pawtucket | Metro Routers | POInt | Yes | Yes | MRTR NE RHD PAW 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
34608 | CB Transport - New Router Tysons - TCR - Optics | VA | NVA | TCR | Tysons Corner | CB - Metro Core | POInt | Yes | Yes | CBMC VA NVA TCR Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 3 | 2020-04-15 | 2020-03-31 |  | SN-0934 | 2020-09-18 | Chg
54573 | CFS SW ARZ SVA SC-CFS Augment POR20 | SW | ARZ | SVA | Sierra Vista | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ SVA SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE TUL QNC BS-CFS Augment POR20 | CE | TUL | QNC | Quincy | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE TUL QNC BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-01 |  | SB-0049 | 2020-02-28 | New
54573 | CFS SW ARZ SVA BS-CFS Augment POR20 | SW | ARZ | SVA | Sierra Vista | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ SVA BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ CSG LM-CFS Augment POR20 | SW | ARZ | CSG | Casa Grande | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ CSG LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ PNL BS-CFS Augment POR20 | SW | ARZ | PNL | Pinal County | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ PNL BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54572 | CFS VA HRD OCN HV-CFS Augment POR20 | VA | HRD | OCN | Oceana | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD OCN HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ MSA BS-CFS Augment POR20 | SW | ARZ | MSA | Mesa | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ MSA BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE GCT CRV BS-CFS Augment POR20 | SE | GCT | CRV | Crestview | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE GCT CRV BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ MCD HV-CFS Augment POR20 | SW | ARZ | MCD | McDowell | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ MCD HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ SVA HV-CFS Augment POR20 | SW | ARZ | SVA | Sierra Vista | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ SVA HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54572 | CFS VA ROA RON BS-CFS Augment POR20 | VA | ROA | RON | Roanoke | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA ROA RON BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ CHD BS-CFS Augment POR20 | SW | ARZ | CHD | Chandler | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ CHD BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ GVA SC-CFS Augment POR20 | SW | ARZ | GVA | Green Valley | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ GVA SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ SSC SC-CFS Augment POR20 | SW | ARZ | SSC | South Scottsdale | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ SSC SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW LAS BLU BS-CFS Augment POR20 | SW | LAS | BLU | Blue Diamond | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW LAS BLU BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ NSC SC-CFS Augment POR20 | SW | ARZ | NSC | North Scottsdale | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ NSC SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54572 | CFS VA NVA GCR DC-CFS Augment POR20 | VA | NVA | GCR | Gunston | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA NVA GCR DC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ TUC SC-CFS Augment POR20 | SW | ARZ | TUC | Tucson | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ TUC SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54572 | CFS VA HRD JEF HV-CFS Augment POR20 | VA | HRD | JEF | Jefferson Ave | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD JEF HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE LFY FRK SC-CFS Augment POR20 | SE | LFY | FRK | Franklin | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE LFY FRK SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE NOR ALG HV-CFS Augment POR20 | SE | NOR | ALG | Algiers | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE NOR ALG HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
34946 | MTRN-SPC- T5-01 | SE | BTR | SPC | Pecue | Metro Transport | POInt | Yes | Yes | MTRN SE BTR SPC T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-04-01 | 2020-05-01 | SN-0154 | 2020-02-06 | Chg
54572 | CFS VA HRD PRA DC-CFS Augment POR20 | VA | HRD | PRA | Princess Anne | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD PRA DC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ PNL SC-CFS Augment POR20 | SW | ARZ | PNL | Pinal County | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ PNL SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54572 | CFS VA HRD OCN BS-CFS Augment POR20 | VA | HRD | OCN | Oceana | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD OCN BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ FWL SC-CFS Augment POR20 | SW | ARZ | FWL | Fowler | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ FWL SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ FWL HV-CFS Augment POR20 - 1 | SW | ARZ | FWL | Fowler | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ FWL HV-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
34970 | CFG SW ARZ MCD BS-CFG Deployment POR20 | SW | ARZ | MCD | McDowell | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ MCD BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE MGA HLT HV-CFS Augment POR20 - 2 | SE | MGA | HLT | Holt | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE MGA HLT HV-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ BEL HV-CFS Augment POR20 - 2 | SW | ARZ | BEL | Bell | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ BEL HV-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54572 | CFS VA NVA MFD DC-CFS Augment POR20 | VA | NVA | MFD | Merrifield | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA NVA MFD DC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ FWL BS-CFS Augment POR20 | SW | ARZ | FWL | Fowler | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ FWL BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE MGA HLT HV-CFS Augment POR20 - 1 | SE | MGA | HLT | Holt | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE MGA HLT HV-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ PEO HV-CFS Augment POR20 | SW | ARZ | PEO | Peoria | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ PEO HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE BTR DNS SC-CFS Augment POR20 | SE | BTR | DNS | Denham Springs | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE BTR DNS SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE LFY LFY BD-CFS Augment POR20 | SE | LFY | LFY | Lafayette | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE LFY LFY BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ FWL HV-CFS Augment POR20 - 2 | SW | ARZ | FWL | Fowler | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ FWL HV-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54572 | CFS VA HRD LTF GN-CFS Augment POR20 | VA | HRD | LTF | Lightfoot | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD LTF GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54572 | CFS VA HRD PRA RF-CFS Augment POR20 | VA | HRD | PRA | Princess Anne | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD PRA RF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
34943 | MTRN-MCD- T5-05 | SW | ARZ | MCD | McDowell | Metro Transport | POInt | Yes | Yes | MTRN SW ARZ MCD T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 4 | 2020-03-01 | 2020-04-01 |  | SN-0154 | 2020-02-06
54573 | CFS SW ARZ PEO SC-CFS Augment POR20 | SW | ARZ | PEO | Peoria | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ PEO SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ TUC HV-CFS Augment POR20 | SW | ARZ | TUC | Tucson | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ TUC HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ MCD SC-CFS Augment POR20 | SW | ARZ | MCD | McDowell | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ MCD SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
75246 | R PHY_CCAP_MCY_RPHY Unbundled Solution V2_43949 | SE | NOR | MCY | Mid-City | R PHY | POInt | Yes | Yes | R PHY SE NOR MCY RPHY CCAP Augment POR20 | License | License Activation | 8 | 2020-03-01 | 2020-04-01 |  | SN-0060 | 2020-02-06 | New
54571 | CFS SE LFY ABV SC-CFS Augment POR20 | SE | LFY | ABV | Abbeville | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE LFY ABV SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE BTR DVL SC-CFS Augment POR20 | SE | BTR | DVL | Donaldsonville | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE BTR DVL SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
34943 | MTRN-MSA- T5-01 | SW | ARZ | MSA | Mesa | Metro Transport | POInt | Yes | Yes | MTRN SW ARZ MSA T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-03-20 | 2020-04-01 | 2020-05-01 | SN-0154 | 2020-02-06 | Chg
54573 | CFS SW LAS CEN BS-CFS Augment POR20 | SW | LAS | CEN | Central | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW LAS CEN BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | SB-0023 | 2020-01-30 | New
44927 | MTCH VA HRD NRF RPHY Test Rack Deployment POR20 | VA | HRD | NRF | Norfolk | MTC HE - Hub Signaling | POInt | Yes | No | MTCH VA HRD NRF RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-01-06 | 2020-04-01 |  | SN-0219 | 2020-04-03
75655 | Arbor 19 | CA | ORG | RSM | Rancho Santa Margarita | Arbor DDoS | POInt | Yes | No | DDoS CA ORG RSM Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-01-06 | 2020-04-05 | 2020-04-20 | SN-0107 | 2020-02-06 | Chg
75647 | Nokia 1830 Add 3 | CA | ORG | RSM | Rancho Santa Margarita | C4 & C4B Transport Network | POInt | Yes | No | C4B CA ORG RSM Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis | 5 |  | 2020-04-07 |  | SN-0551 | 2020-05-13 | Chg
75655 | Arbor 8 | SW | ARZ | CHD | Chandler | Arbor DDoS | POInt | Yes | No | DDoS SW ARZ CHD Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-01-13 | 2020-04-12 | 2020-05-11 | SN-0107 | 2020-02-06 | Chg
75655 | Arbor 9 | SW | ARZ | MCD | McDowell | Arbor DDoS | POInt | Yes | No | DDoS SW ARZ MCD Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-01-13 | 2020-04-12 | 2020-05-11 | SN-0107 | 2020-02-06 | Chg
75699 | MTCS CA SAN ELC PCG VSM Refresh Deployment POR20 | CA | SAN | ELC | El Cajon | MTC - Servers and Software | POInt | Yes | No | MTCS CA SAN ELC PCG VSM Refresh Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-03-06 | 2020-04-15 | 2020-07-15
75699 | MTCS SE GLA ELM 1 Way UDCP OOB Deployment POR20 | SE | NOR | ELM | Elmwood | MTC - Servers and Software | POInt | Yes | No | MTCS SE NOR ELM 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
34608 | CB Transport - New Router Greenbrier - VBC - Optics | VA | HRD | VBC | Virginia Beach | CB - Metro Core | POInt | Yes | Yes | CBMC VA HRD VBC Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-03-15 | 2020-04-15
75699 | MTCS CE OKC TUL 1 Way UDCP OOB Deployment POR20 | CE | TUL | TUL | Tulsa | MTC - Servers and Software | POInt | Yes | No | MTCS CE TUL TUL 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
75699 | MTCS VA NVA MFD PCG VSM Refresh Deployment POR20 | VA | NVA | MFD | Merrifield | MTC - Servers and Software | POInt | Yes | No | MTCS VA NVA MFD PCG VSM Refresh Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-03-06 | 2020-04-15 | 2020-07-15
75699 | MTCS SE GLA ELM EC 9.0 DTAC 5.2 Centralization Deployment POR20 | SE | NOR | ELM | Elmwood | MTC - Servers and Software | POInt | Yes | No | MTCS SE NOR ELM EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
44876 | MTCH CE OMA SVI 8VSB Replacement Deployment POR20 | CE | SUN | SVI | Sun Valley | MTC HE - Hub Signaling | POInt | Yes | No | MTCH CE SUN SVI 8VSB Replacement Deployment POR20 | Chassis | Inca 4110 (2 RU) | 1 | 2020-02-06 | 2020-04-15 | 2020-05-15
75699 | MTCS CE OMA OMM EC 9.0 DTAC 5.2 Centralization Deployment POR20 | CE | OMA | OMM | Omaha | MTC - Servers and Software | POInt | Yes | No | MTCS CE OMA OMM EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
75699 | MTCS NE CLE CLV 1 Way UDCP OOB Deployment POR20 | NE | CLE | CLV | Cleveland | MTC - Servers and Software | POInt | Yes | No | MTCS NE CLE CLV 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
75699 | MTCS SE GLA BTR EC 9.0 DTAC 5.2 Centralization Deployment POR20 | SE | BTR | BTR | Baton Rouge | MTC - Servers and Software | POInt | Yes | No | MTCS SE BTR BTR EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
75699 | MTCS NE CLE CLV PCG VSM Refresh Deployment POR20 | NE | CLE | CLV | Cleveland | MTC - Servers and Software | POInt | Yes | No | MTCS NE CLE CLV PCG VSM Refresh Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-03-06 | 2020-04-15 | 2020-07-15
75699 | MTCS VA HRD VBC 1 Way UDCP OOB Deployment POR20 | VA | HRD | VBC | Virginia Beach | MTC - Servers and Software | POInt | Yes | No | MTCS VA HRD VBC 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
75699 | MTCS VA NVA MFD 1 Way UDCP OOB Deployment POR20 | VA | NVA | MFD | Merrifield | MTC - Servers and Software | POInt | Yes | No | MTCS VA NVA MFD 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
75699 | MTCS CE OKC OKC PCG VSM Refresh Deployment POR20 | CE | OKC | OKC | OKC MTC | MTC - Servers and Software | POInt | Yes | No | MTCS CE OKC OKC PCG VSM Refresh Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-03-06 | 2020-04-15 | 2020-07-15
75699 | MTCS COR COR P6L Lab Firewall Deployment POR20 | COR | COR | P6L | P6 Lab | MTC - Servers and Software | POInt | Yes | No | MTCS CO COR P6L Lab Firewall Deployment POR20 | Labor | Firewall | 1 | 2020-03-06 | 2020-04-15 | 2020-09-15
75699 | MTCS NE CLE CLV EC 9.0 DTAC 5.2 Centralization Deployment POR20 | NE | CLE | CLV | Cleveland | MTC - Servers and Software | POInt | Yes | No | MTCS NE CLE CLV EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
75699 | MTCS SE GCT PNS EC 9.0 DTAC 5.2 Centralization Deployment POR20 | SE | GCT | PNS | Pensacola with (Insite tower) | MTC - Servers and Software | POInt | Yes | No | MTCS SE GCT PNS EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
75699 | MTCS CA SAB SAB PCG VSM Refresh Deployment POR20 | CA | SAB | SAB | Santa Barbara | MTC - Servers and Software | POInt | Yes | No | MTCS CA SAB SAB PCG VSM Refresh Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-03-06 | 2020-04-15 | 2020-07-15
57264 | REP_CE.OKC.TUL.REPACK | CE | TUL | TUL | Tulsa | FCC Repack | POInt | Yes | No | FCC CE TUL TUL Channel Move Alignment POR20 | Chassis | Channel Move / Inca 8VSB / Wade WH | 2 | 2020-03-14 | 2020-04-15
39251 | BWM_SAB_MSSA_Spectrum Phase II Start | CA | SAB | SAB | Santa Barbara | Bandwidth Management | POInt | Yes | No | BWM CA SAB SAB MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-15 | 2020-06-03 | SN-0703 | 2020-06-30 | Chg
75699 | MTCS CE ARK NWA EC 9.0 DTAC 5.2 Centralization Deployment POR20 | CE | NWA | NWA | Johnson | MTC - Servers and Software | POInt | Yes | No | MTCS CE NWA NWA EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
57299 | REP_VA.HRD.VBC.REPACK | VA | HRD | VBC | Virginia Beach | FCC Repack | POInt | Yes | No | FCC VA HRD VBC Channel Move Alignment POR20 | Chassis | Channel Move / Inca 8VSB / Wade WH | 16 | 2020-01-01 | 2020-04-15
75749 | MTCS COR COR ATL Local VOD Packaging Deployment POR20 | COR | COR | ATL | Atlanta | MTC - Servers and Software | POInt | Yes | No | MTCS CO COR ATL Local VOD Packaging Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-03-06 | 2020-04-15 | 2020-10-15
34972 | CFG SOU BD-CFG GEN GROW PROJECT - MEDIUM | CE | OMA | SOU | South (OM) | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OMA SOU BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-04-01 | 2020-04-15
34623 | CB Transport - New Router McDowell - MCD - Optics | SW | ARZ | MCD | McDowell | CB - Metro Core | POInt | Yes | Yes | CBMC SW ARZ MCD Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-03-13 | 2020-04-15
34949 | MTRN-PRV- T5-02 | NE | RHD | PRV | Providence | Metro Transport | POInt | Yes | Yes | MTRN NE RHD PRV T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-03-01 | 2020-04-15 | 2020-04-15 | SN-0154 | 2020-02-06 | New
34619 | Elkhorn-OCML-IXR | CE | OMA | ELK | Elkhorn | CB - Metro Core | POInt | Yes | Yes | CBMC CE OMA ELK OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-04-15
34972 | CFG NCH HV-CFG GEN GROW PROJECT - MEDIUM | CE | OKC | NCH | North Central | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC NCH HV-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-04-01 | 2020-04-15
75699 | MTCS SE GCT PNS PCG VSM Refresh Deployment POR20 | SE | GCT | PNS | Pensacola with (Insite tower) | MTC - Servers and Software | POInt | Yes | No | MTCS SE GCT PNS PCG VSM Refresh Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-03-06 | 2020-04-15 | 2020-07-15
75749 | MTCS COR COR ATL Expand Automation Deployment POR20 | COR | COR | ATL | Atlanta | MTC - Servers and Software | POInt | Yes | No | MTCS CO COR ATL Expand Automation Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-03-06 | 2020-04-15 | 2020-10-15
75699 | MTCS SE GAN GNS PCG VSM Refresh Deployment POR20 | SE | GAN | GNS | Gainesville | MTC - Servers and Software | POInt | Yes | No | MTCS SE GAN GNS PCG VSM Refresh Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-03-06 | 2020-04-15 | 2020-07-15
75699 | MTCS VA NVA MFD EC 9.0 DTAC 5.2 Centralization Deployment POR20 | VA | NVA | MFD | Merrifield | MTC - Servers and Software | POInt | Yes | No | MTCS VA NVA MFD EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
75699 | MTCS CA SAB SAB EC 9.0 DTAC 5.2 Centralization Deployment POR20 | CA | SAB | SAB | Santa Barbara | MTC - Servers and Software | POInt | Yes | No | MTCS CA SAB SAB EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
44876 | MTCH CE KAN DCY 8VSB Replacement Deployment POR20 | CE | KAN | DCY | Dodge City | MTC HE - Hub Signaling | POInt | Yes | No | MTCH CE KAN DCY 8VSB Replacement Deployment POR20 | Chassis | Inca 4110 (2 RU) | 1 | 2020-02-06 | 2020-04-15 | 2020-05-15
75699 | MTCS CE OKC OKC EC 9.0 DTAC 5.2 Centralization Deployment POR20 | CE | OKC | OKC | OKC MTC | MTC - Servers and Software | POInt | Yes | No | MTCS CE OKC OKC EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
75699 | MTCS CE ARK NWA 1 Way UDCP OOB Deployment POR20 | CE | NWA | NWA | Johnson | MTC - Servers and Software | POInt | Yes | No | MTCS CE NWA NWA 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
75663 | V2B CA SAN ELC POR Service Expansions Deployment POR20 | CA | SAN | ELC | El Cajon | V2B | POInt | Yes | No | V2B CA SAN ELC POR Service Expansions Deployment POR20 | Card & Optics | UCS blades and config | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
75699 | MTCS NE RHD WWK 1 Way UDCP OOB Deployment POR20 | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | MTC - Servers and Software | POInt | Yes | No | MTCS NE RHD WWK 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
75699 | MTCS VA ROA RON EC 9.0 DTAC 5.2 Centralization Deployment POR20 | VA | ROA | RON | Roanoke | MTC - Servers and Software | POInt | Yes | No | MTCS VA ROA RON EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
44876 | MTCH CE ARK FAY 8VSB Replacement Deployment POR20 | CE | NWA | FAY | Fayetteville | MTC HE - Hub Signaling | POInt | Yes | No | MTCH CE NWA FAY 8VSB Replacement Deployment POR20 | Chassis | Inca 4110 (2 RU) | 1 | 2020-02-06 | 2020-04-15 | 2020-05-15
75699 | MTCS SE GAN GNS 1 Way UDCP OOB Deployment POR20 | SE | GAN | GNS | Gainesville | MTC - Servers and Software | POInt | Yes | No | MTCS SE GAN GNS 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
75699 | MTCS SW ARZ CHD PCG VSM Refresh Deployment POR20 | SW | ARZ | CHD | Chandler | MTC - Servers and Software | POInt | Yes | No | MTCS SW ARZ CHD PCG VSM Refresh Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-03-06 | 2020-04-15 | 2020-07-15
75699 | MTCS CA ORG RSM EC 9.0 DTAC 5.2 Centralization Deployment POR20 | CA | ORG | RSM | Rancho Santa Margarita | MTC - Servers and Software | POInt | Yes | No | MTCS CA ORG RSM EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
75699 | MTCS VA HRD VBC EC 9.0 DTAC 5.2 Centralization Deployment POR20 | VA | HRD | VBC | Virginia Beach | MTC - Servers and Software | POInt | Yes | No | MTCS VA HRD VBC EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
75699 | MTCS COR COR DDR Service Gateway to Regional Servers Deployment POR20 | COR | COR | DDR | Duke Drive | MTC - Servers and Software | POInt | Yes | No | MTCS CO COR DDR Service Gateway to Regional Servers Deployment POR20 | Labor | Rack and config servers | 1 | 2020-03-06 | 2020-04-15 | 2020-11-15
75663 | V2B COR COR DDR POR Service Expansions Deployment POR20 | COR | COR | DDR | Duke Drive | V2B | POInt | Yes | No | V2B COR COR DDR POR Service Expansions Deployment POR20 | Card & Optics | UCS blades and config | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
75699 | MTCS CE OKC OKC 1 Way UDCP OOB Deployment POR20 | CE | OKC | OKC | OKC MTC | MTC - Servers and Software | POInt | Yes | No | MTCS CE OKC OKC 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
75699 | MTCS SW ARZ CHD EC 9.0 DTAC 5.2 Centralization Deployment POR20 | SW | ARZ | CHD | Chandler | MTC - Servers and Software | POInt | Yes | No | MTCS SW ARZ CHD EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
75699 | MTCS SW LAS HEN PCG VSM Refresh Deployment POR20 | SW | LAS | HEN | Henderson | MTC - Servers and Software | POInt | Yes | No | MTCS SW LAS HEN PCG VSM Refresh Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-03-06 | 2020-04-15 | 2020-07-15
75699 | MTCS CE OKC TUL EC 9.0 DTAC 5.2 Centralization Deployment POR20 | CE | TUL | TUL | Tulsa | MTC - Servers and Software | POInt | Yes | No | MTCS CE TUL TUL EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
57298 | REP_SE.GCT.FWB.REPACK | SE | GCT | FWB | Ft. Walton Beach with (Insite tower) | FCC Repack | POInt | Yes | No | FCC SE GCT FWB Channel Move Alignment POR20 | Chassis | Channel Move / Inca 8VSB / Wade WH | 27 | 2020-01-01 | 2020-04-15
75703 | MTCS NE CON MAN EC 9.0 DTAC 5.2 Centralization Deployment POR20 | NE | CON | MAN | Manchester | MTC - Servers and Software | POInt | Yes | No | MTCS NE CON MAN EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
75647 | Nokia 1830 Add 5 | SW | ARZ | CHD | Chandler | C4 & C4B Transport Network | POInt | Yes | No | C4B SW ARZ CHD Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis | 5 | 2020-02-01 | 2020-04-15
75749 | MTCS COR COR ATL MPEG4 VOD Transition Deployment POR20 | COR | COR | ATL | Atlanta | MTC - Servers and Software | POInt | Yes | No | MTCS CO COR ATL MPEG4 VOD Transition Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-03-06 | 2020-04-15 | 2020-10-15
44876 | MTCH CE OKC OKC 8VSB Replacement Deployment POR20 | CE | OKC | OKC | OKC MTC | MTC HE - Hub Signaling | POInt | Yes | No | MTCH CE OKC OKC 8VSB Replacement Deployment POR20 | Chassis | Inca 4110 (2 RU) | 1 | 2020-02-06 | 2020-04-15 | 2020-05-15 | SN-0242 | 2020-02-24 | New
75794 | VEO Automation - Jira Workflow | COR | COR | ATL | Atlanta | Voice Monitoring and Analytics | POInt | Yes | No | VMA CO -CO ATL Workflow and portfolio implementation Deployment POR20 | Labor | Dev of Jira workflow solution for VEO Projects | 1 | 2020-03-25 | 2020-04-15 |  | SB-0013 | 2020-01-30 | Chg
34616 | CB Transport - New Router Sapulpa - SAP - Optics | CE | TUL | SAP | Sapulpa | CB - Metro Core | POInt | Yes | No | CB Metro Core OKC SAP CB Card 2018 | Card & Optics | Optics Only for Cisco T5 | 3 | 2020-03-15 | 2020-04-15
57299 | REP_VA.HRD.NKT.REPACK | VA | HRD | NKT | New Kent | FCC Repack | POInt | Yes | No | FCC VA HRD NKT Channel Move Alignment POR20 | Chassis | Channel Move / Inca 8VSB / Wade WH | 16 | 2020-01-01 | 2020-04-15
75699 | MTCS SE MGA MCN 1 Way UDCP OOB Deployment POR20 | SE | MGA | MCN | Macon | MTC - Servers and Software | POInt | Yes | No | MTCS SE MGA MCN 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
34619 | CB Transport - New Router Owasso - TUL - Optics | CE | TUL | TUL | Tulsa | CB - Metro Core | POInt | Yes | No | CBMC CE TUL TUL Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-03-15 | 2020-04-15
75699 | MTCS SW LAS HEN EC 9.0 DTAC 5.2 Centralization Deployment POR20 | SW | LAS | HEN | Henderson | MTC - Servers and Software | POInt | Yes | No | MTCS SW LAS HEN EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
75699 | MTCS NE RHD WWK EC 9.0 DTAC 5.2 Centralization Deployment POR20 | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | MTC - Servers and Software | POInt | Yes | No | MTCS NE RHD WWK EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
75699 | MTCS SE GAN GNS EC 9.0 DTAC 5.2 Centralization Deployment POR20 | SE | GAN | GNS | Gainesville | MTC - Servers and Software | POInt | Yes | No | MTCS SE GAN GNS EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
75699 | MTCS SW LAS HEN 1 Way UDCP OOB Deployment POR20 | SW | LAS | HEN | Henderson | MTC - Servers and Software | POInt | Yes | No | MTCS SW LAS HEN 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
44876 | MTCH CE OMA ONA 8VSB Replacement Deployment POR20 | CE | OMA | ONA | North (OM) | MTC HE - Hub Signaling | POInt | Yes | No | MTCH CE OMA ONA 8VSB Replacement Deployment POR20 | Chassis | Inca 4110 (2 RU) | 1 | 2020-02-06 | 2020-04-15 | 2020-05-15
75699 | MTCS SW ARZ CHD 1 Way UDCP OOB Deployment POR20 | SW | ARZ | CHD | Chandler | MTC - Servers and Software | POInt | Yes | No | MTCS SW ARZ CHD 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
75699 | MTCS CE KAN WIC 1 Way UDCP OOB Deployment POR20 | CE | KAN | WIC | Wichita | MTC - Servers and Software | POInt | Yes | No | MTCS CE KAN WIC 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
57299 | REP_VA.ROA.RON.REPACK | VA | ROA | RON | Roanoke | FCC Repack | POInt | Yes | No | FCC VA ROA RON Channel Move Alignment POR20 | Chassis | Channel Move / Inca 8VSB / Wade WH | 1 | 2020-03-14 | 2020-04-15
75699 | MTCS NE CON MAN 1 Way UDCP OOB Deployment POR20 | NE | CON | MAN | Manchester | MTC - Servers and Software | POInt | Yes | No | MTCS NE CON MAN 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
75699 | MTCS SE GCT PNS 1 Way UDCP OOB Deployment POR20 | SE | GCT | PNS | Pensacola with (Insite tower) | MTC - Servers and Software | POInt | Yes | No | MTCS SE GCT PNS 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
75699 | MTCS SE GLA BTR 1 Way UDCP OOB Deployment POR20 | SE | BTR | BTR | Baton Rouge | MTC - Servers and Software | POInt | Yes | No | MTCS SE BTR BTR 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
75699 | MTCS SE MGA MCN EC 9.0 DTAC 5.2 Centralization Deployment POR20 | SE | MGA | MCN | Macon | MTC - Servers and Software | POInt | Yes | No | MTCS SE MGA MCN EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
75699 | MTCS CA ORG RSM 1 Way UDCP OOB Deployment POR20 | CA | ORG | RSM | Rancho Santa Margarita | MTC - Servers and Software | POInt | Yes | No | MTCS CA ORG RSM 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
75699 | MTCS CA SAN ELC EC 9.0 DTAC 5.2 Centralization Deployment POR20 | CA | SAN | ELC | El Cajon | MTC - Servers and Software | POInt | Yes | No | MTCS CA SAN ELC EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
75699 | MTCS VA ROA RON 1 Way UDCP OOB Deployment POR20 | VA | ROA | RON | Roanoke | MTC - Servers and Software | POInt | Yes | No | MTCS VA ROA RON 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
75699 | MTCS CA SAN ELC 1 Way UDCP OOB Deployment POR20 | CA | SAN | ELC | El Cajon | MTC - Servers and Software | POInt | Yes | No | MTCS CA SAN ELC 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
75699 | MTCS CE KAN WIC EC 9.0 DTAC 5.2 Centralization Deployment POR20 | CE | KAN | WIC | Wichita | MTC - Servers and Software | POInt | Yes | No | MTCS CE KAN WIC EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
75699 | MTCS CE OMA OMM 1 Way UDCP OOB Deployment POR20 | CE | OMA | OMM | Omaha | MTC - Servers and Software | POInt | Yes | No | MTCS CE OMA OMM 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
75699 | MTCS CA SAB SAB 1 Way UDCP OOB Deployment POR20 | CA | SAB | SAB | Santa Barbara | MTC - Servers and Software | POInt | Yes | No | MTCS CA SAB SAB 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15
34604 | HRHNLA061AW-SFM | SE | NOR | MCY | Mid-City | CB - Metro Core | POInt | Yes | Yes | CBMC SE NOR MCY SFM-7950 XRS-20 Augment POR20 | Card & Optics | Nokia SFM-7950 XRS-20/20e SFM2-SA | 8 | 2020-01-15 | 2020-04-15 |  | SN-0419 | 2020-04-02 | Chg
34972 | CFG WES BD-CFG GEN GROW PROJECT - LARGE | CE | OMA | WES | West (OM) | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OMA WES BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-04-01 | 2020-04-15
34972 | CFG WES HV-CFG GEN GROW PROJECT - SMALL | CE | OMA | WES | West (OM) | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OMA WES BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-04-01 | 2020-04-15
34604 | MCTYCBPN01-100G CARD | SE | NOR | MCY | Mid-City | CB - Metro Core | POInt | Yes | Yes | CBMC SE NOR MCY 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 2 | 2020-01-15 | 2020-04-15 |  | SN-0419 | 2020-04-02 | Chg
34972 | CFG TOP RK-CFG GEN GROW PROJECT - SMALL | CE | KAN | TOP | Topeka | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE KAN TOP RK-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-04-01 | 2020-04-15
34690 | CCAP blades_ ONA 1 | CE | OMA | ONA | North (OM) | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE OMA ONA CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-04-06 | 2020-04-15
34622 | CB Transport - New Router Escondido, Vista - FED - Chassis Add | CA | SAN | FED | Federal | CB - Metro Core | POInt | Yes | Yes | CBMC CA SAN FED Cisco M6_M15 Chassis Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 1 | 2020-01-01 | 2020-04-15
34970 | CFG WCG RC-CFG GEN GROW PROJECT - SMALL | SW | ARZ | WCG | Wickenburg | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ WCG BS-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-03-01 | 2020-04-15
34975 | CFG NRF AT-CFG GEN GROW PROJECT - MEDIUM | VA | HRD | NRF | Norfolk | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA HRD NRF AT-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-04-15
34972 | CFG ONA BD-CFG GEN GROW PROJECT - MEDIUM | CE | OMA | ONA | North (OM) | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OMA ONA BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-04-01 | 2020-04-15
34972 | CFG ONA RK-R PHY GEN GROW PROJECT - MEDIUM | CE | OMA | ONA | North (OM) | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OMA ONA BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-04-01 | 2020-04-15
34972 | CFG ONA BS-CFG GEN GROW PROJECT - MEDIUM | CE | OMA | ONA | North (OM) | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OMA ONA BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-04-01 | 2020-04-15
34687 | CCAP blades_ BRD 2 | CE | TUL | BRD | Braden | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE TUL BRD CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-04-06 | 2020-04-15
34970 | CFG MCD RC-CFG GEN GROW PROJECT - SMALL | SW | ARZ | MCD | McDowell | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ MCD BS-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-03-01 | 2020-04-15
34685 | CCAP blades_ NRF | VA | HRD | NRF | Norfolk | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS VA HRD NRF CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-03-05 | 2020-04-15
34687 | CCAP blades_ WLH | CE | OKC | WLH | Waterloo | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE OKC WLH CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-04-06 | 2020-04-15
34972 | CFG SDN GN-CFG GEN GROW PROJECT - MEDIUM | CE | KAN | SDN | Sedan | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE KAN SDN GN-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-04-01 | 2020-04-15
34972 | CFG SSP GN-CFG GEN GROW PROJECT - LARGE | CE | NWA | SSP | Siloam Springs | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE NWA SSP GN-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-04-01 | 2020-04-15
34687 | CCAP blades_ NOR 1 | CE | OKC | NOR | Norman | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE OKC NOR CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-04-06 | 2020-04-15
34619 | CB Transport - New Router Owasso - OWA - Optics | CE | TUL | OWA | Owasso | CB - Metro Core | POInt | Yes | Yes | CBMC CE TUL OWA Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-03-15 | 2020-04-15
34949 | MTRN-WWK- T5-01 | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | Metro Transport | POInt | Yes | Yes | MTRN NE RHD WWK T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-03-01 | 2020-04-15 | 2020-05-15 | SN-0154 | 2020-02-06 | Chg
34946 | MTRN-MCY- T5-01 | SE | NOR | MCY | Mid-City | Metro Transport | POInt | Yes | Yes | MTRN SE NOR MCY T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-04-15 | 2020-05-15 | SN-0154 | 2020-02-06 | Chg
34622 | CB Transport - New Router Escondido, Vista - FED - Card Add | CA | SAN | FED | Federal | CB - Metro Core | POInt | Yes | Yes | CBMC CA SAN FED Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-03-15 | 2020-04-15
34972 | CFG DBY HV-CFG GEN GROW PROJECT - LARGE | CE | KAN | DBY | Derby | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE KAN DBY HV-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-04-01 | 2020-04-15
34619 | BLVUBSRA99-ROUTER | CE | OMA | BLV | Bellevue | CB - Metro Core | POInt | Yes | Yes | CBMC CE OMA BLV ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-05 | 2020-04-15 |  | SN-0144 | 2020-02-06 | Chg
34972 | CFG OMM GN-CFG GEN GROW PROJECT - LARGE | CE | OMA | OMM | Omaha | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OMA OMM GN-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-04-01 | 2020-04-15
34622 | CB Transport - New Router Vista - VST - Optics | CA | SAN | VST | Vista | CB - Metro Core | POInt | Yes | Yes | CBMC CA SAN VST Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-03-15 | 2020-04-15
34970 | CFG PNL AC-CFG GEN GROW PROJECT - LARGE | SW | ARZ | PNL | Pinal County | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ PNL GN-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-01-01 | 2020-04-15
34623 | CB Transport - New Router McDowell - CHD - Optics | SW | ARZ | CHD | Chandler | CB - Metro Core | POInt | Yes | Yes | CBMC SW ARZ CHD Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-02-14 | 2020-04-15
34972 | CFG CBL HV-CFG GEN GROW PROJECT - SMALL | CE | OMA | CBL | Council Bluffs | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OMA CBL RK-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-04-01 | 2020-04-15
34619 | OKCKOKCE9AW-xr01.clh.okc.ok-SFM | CE | OKC | CLH | County Line | CB - Metro Core | POInt | Yes | Yes | CBMC CE OKC CLH SFM-7950 XRS-20 Augment POR20 | Card & Optics | Nokia SFM-7950 XRS-20/20e SFM2-SA | 8 | 2020-03-15 | 2020-04-15
34619 | OKCKOKCE9BW-xr02.clh.okc.ok-SFM | CE | OKC | CLH | County Line | CB - Metro Core | POInt | Yes | Yes | CBMC CE OKC CLH SFM-7950 XRS-20 Augment POR20 | Card & Optics | Nokia SFM-7950 XRS-20/20e SFM2-SA | 8 | 2020-03-15 | 2020-04-15
34604 | BRX02-100G CARD | SE | BTR | BTR | Baton Rouge | CB - Metro Core | POInt | Yes | Yes | CBMC SE BTR BTR 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-01-15 | 2020-04-15 |  | SN-0419 | 2020-04-02 | Chg
34619 | CB Transport - New Router Garnett, Owasso - BAR - Card Add | CE | TUL | BAR | Broken Arrow | CB - Metro Core | POInt | Yes | Yes | CBMC CE TUL BAR Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-03-15 | 2020-04-15
34619 | CB Transport - New Router Sapulpa, Quincy - BAR - Card Add | CE | TUL | BAR | Broken Arrow | CB - Metro Core | POInt | Yes | Yes | CBMC CE TUL BAR Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-03-15 | 2020-04-15
34972 | CFG GBD HV-CFG GEN GROW PROJECT - MEDIUM | CE | KAN | GBD | Great Bend | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE KAN GBD BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-04-01 | 2020-04-15
34970 | CFG MSA RC-CFG GEN GROW PROJECT - SMALL | SW | ARZ | MSA | Mesa | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ MSA HV-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-03-01 | 2020-04-15
34622 | CB Transport - New Router Escondido, Vista - ELC - Card Add | CA | SAN | ELC | El Cajon | CB - Metro Core | POInt | Yes | Yes | CBMC CA SAN ELC Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-03-15 | 2020-04-15
34619 | OKCKOKCE9AW-xr01.clh.okc.ok-100G CARD | CE | OKC | CLH | County Line | CB - Metro Core | POInt | Yes | Yes | CBMC CE OKC CLH 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 2 | 2020-03-15 | 2020-04-15 |  | SN-0246 | 2020-02-24 | Chg
34972 | CFG PIT GN-CFG GEN GROW PROJECT - LARGE | CE | KAN | PIT | Pittsburg | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE KAN PIT GN-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-04-01 | 2020-04-15
34946 | MTRN-BTR- T5-01 | SE | BTR | BTR | Baton Rouge | Metro Transport | POInt | Yes | Yes | MTRN SE BTR BTR T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-04-15 | 2020-05-15 | SN-0154 | 2020-02-06 | Chg
54572 | CFS VA HRD HCK DC-CFS Augment POR20 | VA | HRD | HCK | Hickory | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD HCK DC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | SB-0049 | 2020-02-28 | New
34974 | CFG SE NOR NOE BD-CFG Deployment POR20 | SE | NOR | NOE | New Orleans East | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SE NOR NOE BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | SN-0262 | 2020-02-28
59745 | R PHY_CCAP_RSM_RPHY Bundled Solution V2_43845 | CA | ORG | RSM | Rancho Santa Margarita | RSPD - CCAP | POInt | Yes | Yes | R PHY CA ORG RSM RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-01-15 | 2020-04-20 |  | SN-0060 | 2020-02-06 | New
34976 | CFG NE RHD PAW RK-CFG Deployment POR20 | NE | RHD | PAW | Pawtucket | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE RHD PAW RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | SN-0411 | 2020-03-27
54572 | CFS VA HRD NWP HV-CFS Augment POR20 | VA | HRD | NWP | Newport News | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD NWP HV-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | SB-0049 | 2020-02-28 | New
34972 | CFG CE OKC MWC RK-CFG Deployment POR20 | CE | OKC | MWC | Midwest City | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OKC MWC RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | SN-0262 | 2020-02-28
34971 | CFG CA SAN CHU RK-CFG Deployment POR20 | CA | SAN | CHU | Chula Vista | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA SAN CHU RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | SN-0411 | 2020-03-27
34971 | CFG CA SAN CHU BD-CFG Deployment POR20 | CA | SAN | CHU | Chula Vista | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA SAN CHU BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | SN-0411 | 2020-03-27
34971 | CFG CA SAN DWN RK-CFG Deployment POR20 - 2 | CA | SAN | DWN | Downtown | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA SAN DWN RK-CFG Deployment POR20 - 2 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | SN-0411 | 2020-03-27
34976 | CFG NE RHD BUR BD-CFG Deployment POR20 | NE | RHD | BUR | Burrillville | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE RHD BUR BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | SN-0411 | 2020-03-27
54572 | CFS VA HRD CHS DC-CFS Augment POR20 | VA | HRD | CHS | Chesapeake | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD CHS DC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | SB-0049 | 2020-02-28 | New
34974 | CFG SE GAN OCL RK-CFG Deployment POR20 | SE | GAN | OCL | Ocala | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SE GAN OCL RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | SN-0411 | 2020-03-27
59745 | R PHY_CCAP_VST_RPHY Bundled Solution V2_43845 | CA | SAN | VST | Vista | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN VST RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-01-15 | 2020-04-20 |  | SN-0060 | 2020-02-06 | New
34974 | CFG SE NOR CLR AC-CFG Deployment POR20 | SE | NOR | CLR | Metairie | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SE NOR CLR AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | SN-0262 | 2020-02-28
75658 | VA-ELC-1x Arista DCS-7280CR2A-60-F | CA | SAN | ELC | El Cajon | Visibility Architecture | POInt | Yes | No | VIA CA SAN ELC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2020-01-01 | 2020-04-20 | 2020-05-04 | SN-0559 | 2020-05-13 | Chg
75658 | VA-ELC-1x Juniper EX4600 | CA | SAN | ELC | El Cajon | Visibility Architecture | POInt | Yes | No | VIA CA SAN ELC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-01-01 | 2020-04-20 | 2020-05-04 | SN-0559 | 2020-05-13 | Chg
75658 | VA-ELC-1x Niagra PT-3225 | CA | SAN | ELC | El Cajon | Visibility Architecture | POInt | Yes | No | VIA CA SAN ELC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis | 1 | 2020-01-01 | 2020-04-20 | 2020-05-04 | SN-0559 | 2020-05-13 | Chg
75658 | VA-ELC-1x Dell R640 | CA | SAN | ELC | El Cajon | Visibility Architecture | POInt | Yes | No | VIA CA SAN ELC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 4 | 2020-01-01 | 2020-04-20 | 2020-05-04 | SN-0559 | 2020-05-13 | Chg
75788 | CDN Deploy 1 | SW | ARZ | CHD | Chandler | CDN | POInt | Yes | No | CDN SW ARZ CHD Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 2 | 2020-02-20 | 2020-04-20 | 2020-05-04 | SN-0285 | 2020-02-24 | Chg
34976 | CFG NE RHD BUR GN-CFG Deployment POR20 | NE | RHD | BUR | Burrillville | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE RHD BUR GN-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | SN-0411 | 2020-03-27
75247 | R PHY_CCAP_PTH_CBR8-1 | NE | RHD | PTH | Portsmouth (RI) | R PHY | POInt | Yes | Yes | R PHY NE RHD PTH RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-04-21 |  | SN-0958 | 2020-09-25 | Chg
75247 | R PHY_CCAP_PTH_Boundary_Clocks-1 | NE | RHD | PTH | Portsmouth (RI) | R PHY | POInt | Yes | Yes | R PHY NE RHD PTH RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-04-21 |  | SN-0958 | 2020-09-25 | Chg
75247 | R PHY_CCAP_PTH_RPHY CCAP Licenses | NE | RHD | PTH | Portsmouth (RI) | R PHY | POInt | Yes | Yes | R PHY NE RHD PTH RPHY CCAP Initial Deployment POR19 | License | CCAP license | 207 | 2020-07-15 | 2020-04-21 | 2020-04-21 | SN-0958 | 2020-09-25 | Chg
75247 | R PHY_CCAP_PTH_RPHY CCAP Licenses-1 | NE | RHD | PTH | Portsmouth (RI) | R PHY | POInt | Yes | Yes | R PHY NE RHD PTH RPHY CCAP Augment POR20 | License | CCAP license | 345 | 2020-10-15 | 2020-04-21 | 2020-04-21 | SN-0958 | 2020-09-25 | Chg
75247 | R PHY_CCAP_PTH_RPHY CCAP Licenses_Q2 NC Video | NE | RHD | PTH | Portsmouth (RI) | R PHY | POInt | Yes | Yes | R PHY NE RHD PTH RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-04-21 | 2020-04-21 | SN-0958 | 2020-09-25 | Chg
75658 | VA-FED-1x Arista DCS-7280CR2A-60-F | CA | SAN | FED | Federal | Visibility Architecture | POInt | Yes | No | VIA CA SAN FED Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2020-01-01 | 2020-04-27 | 2020-05-11 | SN-0559 | 2020-05-13 | Chg
75658 | VA-FED-1x Juniper EX4600 | CA | SAN | FED | Federal | Visibility Architecture | POInt | Yes | No | VIA CA SAN FED Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-01-01 | 2020-04-27 | 2020-05-11 | SN-0559 | 2020-05-13 | Chg
75658 | VA-FED-1x Niagra PT-3225 | CA | SAN | FED | Federal | Visibility Architecture | POInt | Yes | No | VIA CA SAN FED Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis | 1 | 2020-01-01 | 2020-04-27 | 2020-05-11 | SN-0559 | 2020-05-13 | Chg
75658 | VA-FED-1x Dell R640 | CA | SAN | FED | Federal | Visibility Architecture | POInt | Yes | No | VIA CA SAN FED Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 4 | 2020-01-01 | 2020-04-27 | 2020-05-11 | SN-0559 | 2020-05-13 | Chg
34943 | MTRN-CHD- T5-05 | SW | ARZ | CHD | Chandler | Metro Transport | POInt | Yes | Yes | MTRN SW ARZ CHD T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-03-01 | 2020-04-28 |  | SN-0154 | 2020-02-06
35010 | Metro OTN-ILH-Ciena 6500 S14 | CE | OKC | ILH | Irish Lane | Metro Transport | POInt | Yes | Yes | MTRN CE OKC ILH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | SN-0161 | 2020-02-18 | Chg
35010 | Metro OTN-ILH-Ciena 6500 S2 | CE | OKC | ILH | Irish Lane | Metro Transport | POInt | Yes | Yes | MTRN CE OKC ILH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-02-17 | 2020-04-30 | 2020-05-31 | SN-0161 | 2020-02-18 | Chg
35010 | Metro OTN-NCH-Ciena 6500 S14 | CE | OKC | NCH | North Central | Metro Transport | POInt | Yes | Yes | MTRN CE OKC NCH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | SN-0161 | 2020-02-18 | Chg
35010 | Metro OTN-NCH-Ciena 6500 S2 | CE | OKC | NCH | North Central | Metro Transport | POInt | Yes | Yes | MTRN CE OKC NCH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-04-30 | 2020-05-31 | SN-0161 | 2020-02-18 | Chg
34619 | CB Transport - New Router Braden - BRD - Optics | CE | TUL | BRD | Braden | CB - Metro Core | POInt | Yes | Yes | CBMC CE TUL BRD Optics Only for Cisco T5 POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-01-15 | 2020-04-30 |  | SN-0386 | 2020-03-27
35010 | Metro OTN-WLK-Ciena 6500 S14 | CE | OKC | WLK | Walker Hub | Metro Transport | POInt | Yes | Yes | MTRN CE OKC WLK OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | SN-0161 | 2020-02-18 | Chg
35010 | Metro OTN-WLK-Ciena 6500 S2 | CE | OKC | WLK | Walker Hub | Metro Transport | POInt | Yes | Yes | MTRN CE OKC WLK OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 4 | 2020-02-17 | 2020-04-30 | 2020-05-31 | SN-0161 | 2020-02-18 | Chg
35171 | MRTR OOB-New-KCY-OOB Server | COR | NAT | KCY | Kansas City (1102 Grand) | Metro Routers | POInt | Yes | Yes | MRTR CE KAN KCY OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 3 | 2020-02-01 | 2020-04-30 | 2020-07-31 | SN-0158 | 2020-02-06 | Chg
75842 | CA ORG RSM Backbone Growth Edge Augment POR20 | CA | ORG | RSM | Rancho Santa Margarita | MTC Fiber and Rack Management | POInt | Yes | Yes | MVFM CA ORG RSM Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-04-30 | 2020-05-31 | SN-0230 | 2020-01-31 | Chg
35011 | Metro OTN-GCR-Ciena 6500 S14 | VA | NVA | GCR | Gunston | Metro Transport | POInt | Yes | Yes | MTRN VA NVA GCR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | SN-0161 | 2020-02-18 | Chg
35011 | Metro OTN-GCR-Ciena 6500 S2 | VA | NVA | GCR | Gunston | Metro Transport | POInt | Yes | Yes | MTRN VA NVA GCR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-04-30 | 2020-05-31 | SN-0161 | 2020-02-18 | Chg
74548 | R PHY_CCAP_OCN_CBR8-1 | VA | HRD | OCN | Oceana | R PHY | POInt | Yes | Yes | R PHY VA HRD OCN RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-04-30 |  | SN-0208 | 2020-01-24 | New
74548 | R PHY_CCAP_OCN_Boundary_Clocks-1 | VA | HRD | OCN | Oceana | R PHY | POInt | Yes | Yes | R PHY VA HRD OCN RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-04-30 |  | SN-0605 | 2020-05-22 | Chg
74648 | RPHY MRTR-New-OCN-CIN MGMT-2K | VA | HRD | OCN | Oceana | R PHY | POInt | Yes | Yes | R PHY VA HRD OCN RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-04-30 |  | SN-0211 | 2020-01-23
74648 | RPHY MRTR-New-OCN-CIN-DPA-5200 | VA | HRD | OCN | Oceana | R PHY | POInt | Yes | Yes | R PHY VA HRD OCN RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-04-30 |  | SN-0211 | 2020-01-23
74648 | RPHY MRTR-New-OCN-CIN-RPA-5110 | VA | HRD | OCN | Oceana | R PHY | POInt | Yes | Yes | R PHY VA HRD OCN RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-04-30 |  | SN-0211 | 2020-01-23
74648 | RPHY MRTR-New-OCN-CIN-ATX-OCML | VA | HRD | OCN | Oceana | R PHY | POInt | Yes | Yes | R PHY VA HRD OCN RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-04-30 |  | SN-0606 | 2020-05-22 | New
34619 | BRAROKKA9CW-XR03.BA.TUL.OK-SFM | CE | TUL | BAR | Broken Arrow | CB - Metro Core | POInt | Yes | Yes | CBMC CE TUL BAR SFM-7950 XRS-20 Augment POR20 | Card & Optics | Nokia SFM-7950 XRS-20/20e SFM2-SA | 8 | 2020-02-15 | 2020-04-30 |  | SN-0386 | 2020-03-27 | Chg
34619 | BRAROKKA9DW-XR04.BA.TUL.OK-SFM | CE | TUL | BAR | Broken Arrow | CB - Metro Core | POInt | Yes | Yes | CBMC CE TUL BAR SFM-7950 XRS-20 Augment POR20 | Card & Optics | Nokia SFM-7950 XRS-20/20e SFM2-SA | 8 | 2020-02-15 | 2020-04-30 |  | SN-0386 | 2020-03-27 | Chg
35010 | Metro OTN-MWC-Ciena 6500 S14 | CE | OKC | MWC | Midwest City | Metro Transport | POInt | Yes | Yes | MTRN CE OKC MWC OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | SN-0161 | 2020-02-18 | Chg
35010 | Metro OTN-MWC-Ciena 6500 S2 | CE | OKC | MWC | Midwest City | Metro Transport | POInt | Yes | Yes | MTRN CE OKC MWC OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-02-17 | 2020-04-30 | 2020-05-31 | SN-0161 | 2020-02-18 | Chg
35171 | MRTR OOB-New-NWA-OOB Server | CE | NWA | NWA | Johnson | Metro Routers | POInt | Yes | Yes | MRTR CE NWA NWA OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-02-01 | 2020-04-30 | 2020-07-31 | SN-0158 | 2020-02-06 | Chg
35173 | MRTR SLR-New-OSB-SLR-ASR9906 | SW | LAS | OSB | Oso Blanca | Metro Routers | POInt | Yes | Yes | MRTR SW LAS OSB SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-02-05 | 2020-04-30 | 2020-07-31 | SN-0158 | 2020-02-06 | Chg
34619 | BRAROKKA9CW-XR03.BA.TUL.OK-100G CARD | CE | TUL | BAR | Broken Arrow | CB - Metro Core | POInt | Yes | Yes | CBMC CE TUL BAR 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-02-15 | 2020-04-30 |  | SN-0386 | 2020-03-27 | Chg
34619 | BRAROKKA9DW-XR04.BA.TUL.OK-100G CARD | CE | TUL | BAR | Broken Arrow | CB - Metro Core | POInt | Yes | Yes | CBMC CE TUL BAR 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-02-15 | 2020-04-30 |  | SN-0386 | 2020-03-27 | Chg
34619 | xr01.ba.tul.ok-100G CARD | CE | TUL | BAR | Broken Arrow | CB - Metro Core | POInt | Yes | Yes | CBMC CE TUL BAR 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-02-15 | 2020-04-30 |  | SN-0386 | 2020-03-27 | Chg
34619 | CB Transport - New Router Bellevue - BLV - Chassis Add | CE | OMA | BLV | Bellevue | CB - Metro Core | POInt | Yes | Yes | CBMC CE OMA BLV Cisco M6_M15 Chassis Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-03-30 | 2020-04-30 |  | SN-0326 | 2020-03-02 | Chg
35011 | Metro OTN-RHL-Ciena 6500 S14 | VA | NVA | RHL | Rose Hill | Metro Transport | POInt | Yes | Yes | MTRN VA NVA RHL OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | SN-0161 | 2020-02-18 | Chg
35011 | Metro OTN-RHL-Ciena 6500 S2 | VA | NVA | RHL | Rose Hill | Metro Transport | POInt | Yes | Yes | MTRN VA NVA RHL OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-04-30 | 2020-05-31 | SN-0161 | 2020-02-18 | Chg
35011 | Metro OTN-TCR-Ciena 6500 S14 | VA | NVA | TCR | Tysons Corner | Metro Transport | POInt | Yes | Yes | MTRN VA NVA TCR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | SN-0161 | 2020-02-18 | Chg
35011 | Metro OTN-TCR-Ciena 6500 S2 | VA | NVA | TCR | Tysons Corner | Metro Transport | POInt | Yes | Yes | MTRN VA NVA TCR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-04-30 | 2020-05-31 | SN-0161 | 2020-02-18 | Chg
35011 | Metro OTN-FBG-Ciena 6500 S2 | VA | NVA | FBG | Fredericksburg | Metro Transport | POInt | Yes | Yes | MTRN VA NVA FBG OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-04-30 | 2020-05-31 | SN-0161 | 2020-02-18 | Chg
35011 | Metro OTN-FBG-Ciena 6500 S14 | VA | NVA | FBG | Fredericksburg | Metro Transport | POInt | Yes | Yes | MTRN VA NVA FBG OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | SN-0161 | 2020-02-18 | Chg
35010 | Metro OTN-SRH-Ciena 6500 S2 | CE | OKC | SRH | Sara Road | Metro Transport | POInt | Yes | Yes | MTRN CE OKC SRH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-02-17 | 2020-04-30 | 2020-05-31 | SN-0161 | 2020-02-18 | Chg
35010 | Metro OTN-MOO-Ciena 6500 S14 | CE | OKC | MOO | Moore | Metro Transport | POInt | Yes | Yes | MTRN CE OKC MOO OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | SN-0161 | 2020-02-18 | Chg
35010 | Metro OTN-MOO-Ciena 6500 S2 | CE | OKC | MOO | Moore | Metro Transport | POInt | Yes | Yes | MTRN CE OKC MOO OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-04-30 | 2020-05-31 | SN-0161 | 2020-02-18 | Chg
35171 | MRTR OOB-New-SSP-OOB Server | CE | NWA | SSP | Siloam Springs | Metro Routers | POInt | Yes | Yes | MRTR CE NWA SSP OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-02-01 | 2020-04-30 | 2020-07-31 | SN-0158 | 2020-02-06 | Chg
35171 | MRTR OOB-New-HRN-OOB Server | CE | NWA | HRN | Harrison | Metro Routers | POInt | Yes | Yes | MRTR CE NWA HRN OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-02-01 | 2020-04-30 | 2020-07-31 | SN-0158 | 2020-02-06 | Chg
35011 | Metro OTN-FLK-Ciena 6500 S2 | VA | NVA | FLK | Fair Lakes | Metro Transport | POInt | Yes | Yes | MTRN VA NVA FLK OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 4 | 2020-02-17 | 2020-04-30 | 2020-05-31 | SN-0161 | 2020-02-18 | Chg
35011 | Metro OTN-FLK-Ciena 6500 S14 | VA | NVA | FLK | Fair Lakes | Metro Transport | POInt | Yes | Yes | MTRN VA NVA FLK OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | SN-0161 | 2020-02-18 | Chg
34619 | CB Transport - New Router Braden, Downtown (TUL) - BAR - Card Add | CE | TUL | BAR | Broken Arrow | CB - Metro Core | POInt | Yes | Yes | CBMC CE TUL BAR Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-02-15 | 2020-04-30 |  | SN-0386 | 2020-03-27 | Chg
35010 | Metro OTN-SEH-Ciena 6500 S14 | CE | OKC | SEH | South East | Metro Transport | POInt | Yes | Yes | MTRN CE OKC SEH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | SN-0161 | 2020-02-18 | Chg
35010 | Metro OTN-SEH-Ciena 6500 S2 | CE | OKC | SEH | South East | Metro Transport | POInt | Yes | Yes | MTRN CE OKC SEH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-04-30 | 2020-05-31 | SN-0161 | 2020-02-18 | Chg
75658 | VA-MCD-1x Dell R640 | SW | ARZ | MCD | McDowell | Visibility Architecture | POInt | Yes | No | VIA SW ARZ MCD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 9 | 2020-01-01 | 2020-04-30 | 2020-05-11 | SN-0094 | 2020-02-06 | New
75658 | VA-MCD-1x Ixia E100-v1 | SW | ARZ | MCD | McDowell | Visibility Architecture | POInt | Yes | No | VIA SW ARZ MCD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Ixia E100 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-11 | SN-0094 | 2020-02-06 | New
75658 | VA-MCD-1x Arista DCS-7280CR2A-60-F | SW | ARZ | MCD | McDowell | Visibility Architecture | POInt | Yes | No | VIA SW ARZ MCD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-11 | SN-0094 | 2020-02-06 | Chg
75658 | VA-MCD-1x Niagra PT-3225 | SW | ARZ | MCD | McDowell | Visibility Architecture | POInt | Yes | No | VIA SW ARZ MCD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis | 3 | 2020-01-01 | 2020-04-30 | 2020-05-11 | SN-0094 | 2020-02-06 | Chg
75658 | VA-MCD-1x Juniper EX4600 | SW | ARZ | MCD | McDowell | Visibility Architecture | POInt | Yes | No | VIA SW ARZ MCD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-11 | SN-0094 | 2020-02-06 | Chg
75658 | VA-DDR-1x Dell R640 | COR | COR | DDR | Duke Drive | Visibility Architecture | POInt | Yes | No | VIA CO COR DDR Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 45 | 2020-01-01 | 2020-04-30 | 2020-04-15 | SN-0094 | 2020-02-06 | New
75842 | CA SAN FED Backbone Growth Edge Augment POR20 | CA | SAN | FED | Federal | MTC Fiber and Rack Management | POInt | Yes | No | MVFM CA SAN FED Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-04-30 | 2020-05-31 | SN-0230 | 2020-01-31 | Chg
44926 | MTCH NE CON SFD HFC Receiver Deployment POR20 | NE | CON | SFD | Stafford | MTC HE - Hub Signaling | POInt | Yes | No | MTCH NE CON SFD HFC Receiver Deployment POR20 | Chassis | Receiver (1 RU) | 1 | 2020-03-06 | 2020-04-30 |  | SN-0288 | 2020-03-05 | Chg
75788 | CDN Deploy 13 | CE | OKC | OKC | OKC MTC | CDN | POInt | Yes | No | CDN CE OKC OKC Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-03-01 | 2020-04-30 | 2020-05-14 | SN-0421 | 2020-04-02 | Chg
75658 | VA-TEN-1x Arista DCS-7280CR2A-60-F | SW | LAS | TEN | Tenaya | Visibility Architecture | POInt | Yes | No | VIA SW LAS TEN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-18 | SN-0094 | 2020-02-06 | Chg
75658 | VA-TEN-1x Juniper EX4600 | SW | LAS | TEN | Tenaya | Visibility Architecture | POInt | Yes | No | VIA SW LAS TEN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-18 | SN-0094 | 2020-02-06 | Chg
75658 | VA-TEN-1x Dell R640 | SW | LAS | TEN | Tenaya | Visibility Architecture | POInt | Yes | No | VIA SW LAS TEN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 4 | 2020-01-01 | 2020-04-30 | 2020-05-18 | SN-0094 | 2020-02-06 | New
75658 | VA-TEN-1x Niagra PT-3225 | SW | LAS | TEN | Tenaya | Visibility Architecture | POInt | Yes | No | VIA SW LAS TEN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-18 | SN-0094 | 2020-02-06 | New
75658 | VA-HEN-1x Arista DCS-7280CR2A-60-F | SW | LAS | HEN | Henderson | Visibility Architecture | POInt | Yes | No | VIA SW LAS HEN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-18 | SN-0094 | 2020-02-06 | Chg
75658 | VA-HEN-1x Juniper EX4600 | SW | LAS | HEN | Henderson | Visibility Architecture | POInt | Yes | No | VIA SW LAS HEN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-18 | SN-0094 | 2020-02-06 | Chg
75658 | VA-HEN-1x Dell R640 | SW | LAS | HEN | Henderson | Visibility Architecture | POInt | Yes | No | VIA SW LAS HEN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 4 | 2020-01-01 | 2020-04-30 | 2020-05-18 | SN-0094 | 2020-02-06 | New
75658 | VA-HEN-1x Niagra PT-3225 | SW | LAS | HEN | Henderson | Visibility Architecture | POInt | Yes | No | VIA SW LAS HEN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-18 | SN-0094 | 2020-02-06 | New
75658 | VA-CHD-1x Dell R640 | SW | ARZ | CHD | Chandler | Visibility Architecture | POInt | Yes | No | VIA SW ARZ CHD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 9 | 2020-01-01 | 2020-04-30 | 2020-05-11 | SN-0094 | 2020-02-06 | New
75658 | VA-CHD-1x Ixia E100-v1 | SW | ARZ | CHD | Chandler | Visibility Architecture | POInt | Yes | No | VIA SW ARZ CHD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Ixia E100 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-11 | SN-0094 | 2020-02-06 | New
75658 | VA-CHD-1x Arista DCS-7280CR2A-60-F | SW | ARZ | CHD | Chandler | Visibility Architecture | POInt | Yes | No | VIA SW ARZ CHD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-11 | SN-0094 | 2020-02-06 | Chg
75658 | VA-CHD-1x Niagra PT-3225 | SW | ARZ | CHD | Chandler | Visibility Architecture | POInt | Yes | No | VIA SW ARZ CHD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis | 3 | 2020-01-01 | 2020-04-30 | 2020-05-11 | SN-0094 | 2020-02-06 | Chg
75658 | VA-CHD-1x Juniper EX4600 | SW | ARZ | CHD | Chandler | Visibility Architecture | POInt | Yes | No | VIA SW ARZ CHD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-05-11 | SN-0094 | 2020-02-06 | Chg
75844 | NE RHD BUR ALU Nokia Fiber Augment POR20 | NE | RHD | BUR | Burrillville | MTC Fiber and Rack Management | POInt | Yes | No | MVFM NE RHD BUR ALU Nokia Fiber Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-04-30 | 2020-08-13 | SN-0793 | 2020-08-20 | Chg
35171 | MRTR NCS-Growth-NWA-100G Grow | CE | NWA | NWA | Johnson | Metro Routers | POInt | Yes | Yes | MRTR CE NWA NWA 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-02-01 | 2020-04-30 | 2020-07-31 | SN-0158 | 2020-02-06 | Chg
35010 | Metro OTN-OKC-Ciena 6500 S32 | CE | OKC | OKC | OKC MTC | Metro Transport | POInt | Yes | Yes | MTRN CE OKC OKC OTN Deployment POR20 | Chassis | 1x Ciena 6500 S32 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | SN-0161 | 2020-02-18 | New
35175 | MRTR NCS-Growth-MAN-100G Grow | NE | CON | MAN | Manchester | Metro Routers | POInt | Yes | Yes | MRTR NE RHD WWK 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-04-01 | 2020-04-30 | 2020-05-30 | SN-0158 | 2020-02-06 | New
34944 | Metro OTN-MCLNVA23-Ciena 6500 S14 | CA | SAN | FED | Federal | Metro Transport | POInt | Yes | Yes | MTRN CA SAN FED EdgeConnex OTN_OLS Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | SN-0161 | 2020-02-18 | Chg
34944 | Metro OTN-MCLNVA23-Ciena 6500 S2 | CA | SAN | FED | Federal | Metro Transport | POInt | Yes | Yes | MTRN CA SAN FED EdgeConnex OTN_OLS Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-04-30 | 2020-05-31 | SN-0161 | 2020-02-18 | Chg
44926 | MTCH NE CON GLB RF Passive Splitter Deployment POR20 | NE | CON | GLB | Glastonbury | MTC HE - Hub Signaling | POInt | Yes | No | MTCH NE CON GLB RF Passive Splitter Deployment POR20 | Chassis | 8-way splitter | 1 | 2020-03-06 | 2020-04-30 |  | SN-0021 | 2020-02-06 | Chg
35010 | Metro OTN-CLH-Ciena 6500 S2 | CE | OKC | CLH | County Line | Metro Transport | POInt | Yes | Yes | MTRN CE OKC CLH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-04-30 | 2020-05-31 | SN-0161 | 2020-02-18 | Chg
35010 | Metro OTN-CLH-Ciena 6500 S14 | CE | OKC | CLH | County Line | Metro Transport | POInt | Yes | Yes | MTRN CE OKC CLH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | SN-0161 | 2020-02-18 | Chg
75788 | CDN Deploy 2 | SW | ARZ | CHD | Chandler | CDN | POInt | Yes | No | CDN SW ARZ CHD Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-03-01 | 2020-04-30 | 2020-05-14 | SN-0285 | 2020-02-24 | Chg
44926 | MTCH NE CON GLB HFC Receiver Deployment POR20 | NE | CON | GLB | Glastonbury | MTC HE - Hub Signaling | POInt | Yes | No | MTCH NE CON GLB HFC Receiver Deployment POR20 | Chassis | Receiver (1 RU) | 1 | 2020-03-06 | 2020-04-30 |  | SN-0288 | 2020-03-05 | Chg
75842 | CA SAN ELC Backbone Growth Edge Augment POR20 | CA | SAN | ELC | El Cajon | MTC Fiber and Rack Management | POInt | Yes | No | MVFM CA SAN ELC Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-04-30 | 2020-05-31 | SN-0230 | 2020-01-31 | Chg
75788 | CDN Deploy 3 | SW | ARZ | MCD | McDowell | CDN | POInt | Yes | No | CDN SW ARZ MCD Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 2 | 2020-02-20 | 2020-04-30 | 2020-05-04 | SN-0285 | 2020-02-24 | Chg
75788 | CDN Deploy 4 | SW | ARZ | MCD | McDowell | CDN | POInt | Yes | No | CDN SW ARZ MCD Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-03-01 | 2020-04-30 | 2020-05-14 | SN-0285 | 2020-02-24 | Chg
75658 | VA-RSM-1x Arista DCS-7280CR2A-60-F | CA | ORG | RSM | Rancho Santa Margarita | Visibility Architecture | POInt | Yes | No | VIA CA ORG RSM Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-04-20 | SN-0094 | 2020-02-06 | Chg
75658 | VA-RSM-1x Juniper EX4600 | CA | ORG | RSM | Rancho Santa Margarita | Visibility Architecture | POInt | Yes | No | VIA CA ORG RSM Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-04-20 | SN-0094 | 2020-02-06 | Chg
75658 | VA-RSM-1x Ixia E100 -v1 | CA | ORG | RSM | Rancho Santa Margarita | Visibility Architecture | POInt | Yes | No | VIA CA ORG RSM Visibility Architecture Gear Deployment POR20 | Chassis | 1x Ixia E100 Chassis | 1 | 2020-01-01 | 2020-04-30 | 2020-04-20 | SN-0094 | 2020-02-06 | New
75658 | VA-RSM-1x Dell R640 | CA | ORG | RSM | Rancho Santa Margarita | Visibility Architecture | POInt | Yes | No | VIA CA ORG RSM Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 5 | 2020-01-01 | 2020-04-30 | 2020-04-20 | SN-0094 | 2020-02-06 | New
44926 | MTCH NE CON GRB HFC Receiver Deployment POR20 | NE | CON | GRB | Granby | MTC HE - Hub Signaling | POInt | Yes | No | MTCH NE CON GRB HFC Receiver Deployment POR20 | Chassis | Receiver (1 RU) | 1 | 2020-03-06 | 2020-04-30 |  | SN-0288 | 2020-03-05 | Chg
44927 | MTCH VA HRD PTM RPHY Test Rack Deployment POR20 | VA | HRD | PTM | Portsmouth (VA) | MTC HE - Hub Signaling | POInt | Yes | No | MTCH VA HRD PTM RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-02-06 | 2020-05-01 |  | SN-0219 | 2020-04-03
44927 | MTCH VA HRD PRA RPHY Test Rack Deployment POR20 | VA | HRD | PRA | Princess Anne | MTC HE - Hub Signaling | POInt | Yes | No | MTCH VA HRD PRA RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-02-06 | 2020-05-01 |  | SN-0219 | 2020-04-03
44927 | MTCH VA ROA RON RPHY Test Rack Deployment POR20 | VA | ROA | RON | Roanoke | MTC HE - Hub Signaling | POInt | Yes | No | MTCH VA ROA RON RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-03-06 | 2020-05-01 |  | SN-0219 | 2020-04-03
54570 | CFS CE TUL CLA SC-CFS Augment POR20 | CE | TUL | CLA | Claremore | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE TUL CLA SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-01 |  | SB-0049 | 2020-02-28 | New
34944 | MTRN-RSM-TNCS/TNCSO-01 | CA | ORG | RSM | Rancho Santa Margarita | Metro Transport | POInt | Yes | Yes | MTRN CA ORG RSM T5 Card Augment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-02-03 | 2020-05-01 | 2020-06-01 | SN-0098 | 2020-02-06 | Chg
44927 | MTCH VA HRD CHS RPHY Test Rack Deployment POR20 | VA | HRD | CHS | Chesapeake | MTC HE - Hub Signaling | POInt | Yes | No | MTCH VA HRD CHS RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-02-06 | 2020-05-01 |  | SN-0219 | 2020-04-03
44927 | MTCH VA HRD OCN RPHY Test Rack Deployment POR20 | VA | HRD | OCN | Oceana | MTC HE - Hub Signaling | POInt | Yes | No | MTCH VA HRD OCN RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-03-06 | 2020-05-01 |  | SN-0219 | 2020-04-03
54574 | CFS NE CON RKH HV-CFS Augment POR20 | NE | CON | RKH | Rocky Hill | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS NE CON RKH HV-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-01 |  | SB-0049 | 2020-02-28 | New
35172 | MRTR NCS-Growth-PNS-100G Grow | SE | GCT | PNS | Pensacola with (Insite tower) | Metro Routers | POInt | Yes | Yes | MRTR SE GCT PNS 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-04-01 | 2020-05-01
34943 | MTRN-PEO- T5-01 | SW | ARZ | BEL | Bell | Metro Transport | POInt | Yes | Yes | MTRN SW ARZ BEL T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-01 |  | SN-0098 | 2020-02-06 | New
34944 | MTRN-AVJ-TNCS/TNCSO-01 | CA | ORG | AVJ | Aliso Viejo | Metro Transport | POInt | Yes | Yes | MTRN CA ORG AVJ DWDM Deployment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-02-03 | 2020-05-01 | 2020-06-01 | SN-0098 | 2020-02-06 | Chg
34944 | MTRN-IRV-TNCS/TNCSO-01 | CA | ORG | IRV | Irvine | Metro Transport | POInt | Yes | Yes | MTRN CA ORG IRV DWDM Deployment POR20 | Card & Optics | TNCS/TNCSO | 4 | 2020-02-03 | 2020-05-01 | 2020-06-01 | SN-0098 | 2020-02-06 | Chg
34944 | MTRN-RSM- T5-02 | CA | ORG | RSM | Rancho Santa Margarita | Metro Transport | POInt | Yes | Yes | MTRN CA ORG RSM T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-02-03 | 2020-05-01 | 2020-06-01 | SN-0098 | 2020-02-06 | Chg
34944 | MTRN-AVJ- T5-01 | CA | ORG | AVJ | Aliso Viejo | Metro Transport | POInt | Yes | Yes | MTRN CA ORG AVJ T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-02-03 | 2020-05-01 | 2020-06-01 | SN-0098 | 2020-02-06 | Chg
54571 | CFS SE LFY CRW SC-CFS Augment POR20 | SE | LFY | CRW | Crowley | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE LFY CRW SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-05-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE TUL TDC SC-CFS Augment POR20 | CE | TUL | TDC | Tulsa Data Center | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE TUL TDC SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-01 |  | SB-0049 | 2020-02-28 | New
54570 | CFS CE TUL WST SC-CFS Augment POR20 | CE | TUL | WST | West (TUL) | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE TUL WST SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-01 |  | SB-0049 | 2020-02-28 | New
54571 | CFS SE LFY LFY SC-CFS Augment POR20 | SE | LFY | LFY | Lafayette | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE LFY LFY SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-05-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE TUL IND SC-CFS Augment POR20 | CE | TUL | IND | Indianapolis | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE TUL IND SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-01 |  | SB-0049 | 2020-02-28 | New
34943 | MTRN-MCD- T5-03 | SW | ARZ | MCD | McDowell | Metro Transport | POInt | Yes | Yes | MTRN SW ARZ MCD T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 4 | 2020-04-20 | 2020-05-01 |  | SN-0098 | 2020-02-06 | Chg
34944 | MTRN-ORG-TNCS/TNCSO-01 | CA | ORG | ORG | Orange | Metro Transport | POInt | Yes | Yes | MTRN CA ORG ORG T5 Card Augment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-02-03 | 2020-05-01 | 2020-06-01 | SN-0098 | 2020-02-06 | Chg
34944 | MTRN-DNP-TNCS/TNCSO-01 | CA | ORG | DNP | Dana Point | Metro Transport | POInt | Yes | Yes | MTRN CA ORG DNP DWDM Deployment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-02-03 | 2020-05-01 | 2020-06-01 | SN-0098 | 2020-02-06 | Chg
54570 | CFS CE TUL BAR SC-CFS Augment POR20 | CE | TUL | BAR | Broken Arrow | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE TUL BAR SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-01 |  | SB-0049 | 2020-02-28 | New
35170 | MRTR NCS-Growth-PAV-100G Grow | CA | ORG | PAV | Palos Verdes | Metro Routers | POInt | Yes | Yes | MRTR CA ORG AVJ 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-04-01 | 2020-05-01 | 2020-09-01 | SN-0158 | 2020-02-06 | New
34945 | MTRN-NWA- T5-01 | CE | NWA | NWA | Johnson | Metro Transport | POInt | Yes | Yes | MTRN CE NWA NWA T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-01 | 2020-06-01 | SN-0154 | 2020-02-06 | Chg
34944 | MTRN-CHU-TNCS/TNCSO-01 | CA | SAN | CHU | Chula Vista | Metro Transport | POInt | Yes | Yes | MTRN CA SAN CHU DWDM-OLS Deployment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-02-03 | 2020-05-01 | 2020-06-01 | SN-0098 | 2020-02-06 | Chg
34943 | MTRN-CHD- T5-03 | SW | ARZ | CHD | Chandler | Metro Transport | POInt | Yes | Yes | MTRN SW ARZ CHD T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-01
54571 | CFS SE BTR GNZ SC-CFS Augment POR20 | SE | BTR | GNZ | Gonzales | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE BTR GNZ SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-05-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE BTR ERW SC-CFS Augment POR20 | SE | BTR | ERW | Erwinville | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE BTR ERW SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-05-01 |  | SB-0023 | 2020-01-30 | New
34944 | MTRN-ALP-TNCS/TNCSO-01 | CA | SAN | ALP | Alpine | Metro Transport | POInt | Yes | Yes | MTRN CA SAN ALP DWDM Deployment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-02-03 | 2020-05-01 | 2020-06-01 | SN-0098 | 2020-02-06 | Chg
59522 | R PHY_CCAP_OSB_RPHY Unbundled Solution V2_44119 | SW | LAS | OSB | Oso Blanca | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | License | License Activation | 444 | 2020-02-12 | 2020-05-01 |  | SN-0060 | 2020-02-06 | New
59522 | R PHY_CCAP_OSB_RPHY Bundled Solution V2_43845 | SW | LAS | OSB | Oso Blanca | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-02-12 | 2020-05-01 |  | SN-0060 | 2020-02-06 | New
59522 | R PHY_CCAP_OSB_RPHY Bundled Solution V3_43967 | SW | LAS | OSB | Oso Blanca | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-02-12 | 2020-05-01 |  | SN-0060 | 2020-02-06 | New
59522 | R PHY_CCAP_OSB_Boundary_Clocks_43845 | SW | LAS | OSB | Oso Blanca | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-02-12 | 2020-05-01 |  | SN-0060 | 2020-02-06 | New
59522 | R PHY_CCAP_OSB_RPHY Unbundled Solution V2_44027 | SW | LAS | OSB | Oso Blanca | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | License | License Activation | 487 | 2020-02-12 | 2020-05-01 |  | SN-0060 | 2020-02-06 | New
75645 | CGN Replacement 5 | CE | OKC | OKC | OKC MTC | Data Center Capacity | POInt | Yes | No | DTC CE OKC OKC CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2019-12-29 | 2020-05-13 |  | SN-0554 | 2020-05-13 | Chg
75703 | MTCS CE OKC OKC EOS Testing Hardware Deployment POR20 | CE | OKC | OKC | OKC MTC | MTC - Servers and Software | POInt | Yes | No | MTCS CE OKC OKC EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15
75663 | V2B COR COR DDR Monitoring Platform Obsolescence Augment POR20 | COR | COR | DDR | Duke Drive | V2B | POInt | Yes | No | V2B COR COR DDR Monitoring Platform Obsolescence Augment POR20 | Chassis | Tektronix Sentry replacement | 18 | 2020-04-20 | 2020-05-15 | 2020-06-15 | SN-0501 | 2020-05-05 | Chg
75703 | MTCS CE ARK NWA EOS Testing Hardware Deployment POR20 | CE | NWA | NWA | Johnson | MTC - Servers and Software | POInt | Yes | No | MTCS CE NWA NWA EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15
75703 | MTCS VA ROA RON EOS Testing Hardware Deployment POR20 | VA | ROA | RON | Roanoke | MTC - Servers and Software | POInt | Yes | No | MTCS VA ROA RON EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15
75703 | MTCS CA ORG RSM EOS Testing Hardware Deployment POR20 | CA | ORG | RSM | Rancho Santa Margarita | MTC - Servers and Software | POInt | Yes | No | MTCS CA ORG RSM EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15
75838 | SW ARZ CHD Cabling Refortification Augment POR20 | SW | ARZ | CHD | Chandler | MTC Fiber and Rack Management | POInt | Yes | No | MVFM SW ARZ CHD Cabling Refortification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-04-06 | 2020-05-15 | 2020-05-15 | SN-0388 | 2020-03-30 | Chg
75703 | MTCS NE CON MAN EOS Testing Hardware Deployment POR20 | NE | CON | MAN | Manchester | MTC - Servers and Software | POInt | Yes | No | MTCS NE CON MAN EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15
75699 | MTCS COR COR P6L Lab Remote Phy Deployment POR20 | COR | COR | P6L | P6 Lab | MTC - Servers and Software | POInt | Yes | No | MTCS CO COR P6L Lab Remote Phy Deployment POR20 | Standard | RPHY | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15
75703 | MTCS CE OMA OMM EOS Testing Hardware Deployment POR20 | CE | OMA | OMM | Omaha | MTC - Servers and Software | POInt | Yes | No | MTCS CE OMA OMM EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15
44926 | MTCH NE RHD WEK NSG 3G 6G Replacement Deployment POR20 | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | MTC HE - Hub Signaling | POInt | Yes | No | MTCH NE RHD WWK NSG 3G 6G Replacement Deployment POR20 | Chassis | NSG 40G | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15
75842 | CA SAN VST Backbone Growth Edge Augment POR20 | CA | SAN | VST | Vista | MTC Fiber and Rack Management | POInt | Yes | No | MVFM CA SAN VST Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | SN-0230 | 2020-01-31 | Chg
75842 | CA SAN ESC Backbone Growth Edge Augment POR20 | CA | SAN | ESC | Escondido | MTC Fiber and Rack Management | POInt | Yes | No | MVFM CA SAN ESC Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | SN-0230 | 2020-01-31 | Chg
75703 | MTCS VA HRD VBC EOS Testing Hardware Deployment POR20 | VA | HRD | VBC | Virginia Beach | MTC - Servers and Software | POInt | Yes | No | MTCS VA HRD VBC EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15
75838 | SW ARZ SSC Cabling Refortification Augment POR20 | SW | ARZ | SSC | South Scottsdale | MTC Fiber and Rack Management | POInt | Yes | No | MVFM SW ARZ SSC Cabling Refortification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | SN-0388 | 2020-03-30 | Chg
75703 | MTCS CE KAN WIC EOS Testing Hardware Deployment POR20 | CE | KAN | WIC | Wichita | MTC - Servers and Software | POInt | Yes | No | MTCS CE KAN WIC EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15
59745 | R PHY_CCAP_DNP_RPHY Unbundled Solution V2_44027 | CA | ORG | DNP | Dana Point | RSPD - CCAP | POInt | Yes | No | R PHY CA ORG DNP RPHY CCAP Augment POR20 | License | License Activation | 621 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
44876 | MTCH CE KAN TOP 8VSB Replacement Deployment POR20 | CE | KAN | TOP | Topeka | MTC HE - Hub Signaling | POInt | Yes | No | MTCH CE KAN TOP 8VSB Replacement Deployment POR20 | Chassis | Inca 4110 (2 RU) | 1 | 2020-04-15 | 2020-05-15 | 2020-06-15 | SN-0456 | 2020-04-17 | New
75703 | MTCS SW ARZ CHD EOS Testing Hardware Deployment POR20 | SW | ARZ | CHD | Chandler | MTC - Servers and Software | POInt | Yes | No | MTCS SW ARZ CHD EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15
75663 | V2B CA SAN ELC Monitoring Platform Obsolescence Augment POR20 | CA | SAN | ELC | El Cajon | V2B | POInt | Yes | No | V2B CA SAN ELC Monitoring Platform Obsolescence Augment POR20 | Chassis | Tektronix Sentry replacement | 13 | 2020-04-20 | 2020-05-15 | 2020-06-15 | SN-0501 | 2020-05-05 | Chg
59745 | R PHY_CCAP_ORG_RPHY Unbundled Solution V2_44027 | CA | ORG | ORG | Orange | RSPD - CCAP | POInt | Yes | No | R PHY CA ORG ORG RPHY CCAP Augment POR20 | License | License Activation | 1035 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
75703 | MTCS SE GAN GNS EOS Testing Hardware Deployment POR20 | SE | GAN | GNS | Gainesville | MTC - Servers and Software | POInt | Yes | No | MTCS SE GAN GNS EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15
75838 | SW ARZ MSA Cabling Refortification Augment POR20 | SW | ARZ | MSA | Mesa | MTC Fiber and Rack Management | POInt | Yes | No | MVFM SW ARZ MSA Cabling Refortification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-04-06 | 2020-05-15 | 2020-05-15 | SN-0388 | 2020-03-30 | Chg
75703 | MTCS SE GCT PNS EOS Testing Hardware Deployment POR20 | SE | GCT | PNS | Pensacola with (Insite tower) | MTC - Servers and Software | POInt | Yes | No | MTCS SE GCT PNS EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15
75703 | MTCS SW LAS HEN EOS Testing Hardware Deployment POR20 | SW | LAS | HEN | Henderson | MTC - Servers and Software | POInt | Yes | No | MTCS SW LAS HEN EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15
75187 | R PHY_CCAP_YAL_RPHY Unbundled Solution V2_44027 | CE | TUL | YAL | Yale | R PHY | POInt | Yes | No | R PHY CE TUL YAL RPHY CCAP Augment POR20 | License | License Activation | 69 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
75703 | MTCS NE CLE CLV EOS Testing Hardware Deployment POR20 | NE | CLE | CLV | Cleveland | MTC - Servers and Software | POInt | Yes | No | MTCS NE CLE CLV EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15
44876 | MTCH CE OKC OKC PEG Transport Deployment POR20 | CE | OKC | OKC | OKC MTC | MTC HE - Hub Signaling | POInt | Yes | No | MTCH CE OKC OKC PEG Transport Deployment POR20 | Chassis | Drake encoder (1 RU) | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | SN-0292 | 2020-02-24 | New
75703 | MTCS NE RHD WWK EOS Testing Hardware Deployment POR20 | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | MTC - Servers and Software | POInt | Yes | No | MTCS NE RHD WWK EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15
44876 | MTCH CE TUL TUL PEG Transport Deployment POR20 | CE | TUL | TUL | Tulsa | MTC HE - Hub Signaling | POInt | Yes | No | MTCH CE TUL TUL PEG Transport Deployment POR20 | Chassis | Drake encoder (1 RU) | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | SN-0292 | 2020-02-24 | New
75842 | CA SAN OCE Backbone Growth Edge Augment POR20 | CA | SAN | OCE | Oceanside | MTC Fiber and Rack Management | POInt | Yes | No | MVFM CA SAN OCE Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | SN-0230 | 2020-01-31 | Chg
44876 | MTCH CE KAN WIC PEG Transport Deployment POR20 | CE | KAN | WIC | Wichita | MTC HE - Hub Signaling | POInt | Yes | No | MTCH CE KAN WIC PEG Transport Deployment POR20 | Chassis | Drake encoder (1 RU) | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15
35011 | MTRN-PTM- T5-01 | VA | HRD | PTM | Portsmouth (VA) | Metro Transport | POInt | Yes | Yes | MTRN VA HRD PTM T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15
34604 | CB Transport - New Router North - NTH - Optics | SE | BTR | NTH | Baker | CB - Metro Core | POInt | Yes | Yes | CBMC SE BTR NTH Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-04-15 | 2020-05-15
34975 | CFG CHS RC-CFG GEN GROW PROJECT - MEDIUM | VA | HRD | CHS | Chesapeake | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA HRD CHS RC-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-05-15
44876 | MTCH CE NWA NWA PEG Transport Deployment POR20 | CE | NWA | NWA | Johnson | MTC HE - Hub Signaling | POInt | Yes | No | MTCH CE NWA NWA PEG Transport Deployment POR20 | Chassis | Drake encoder (1 RU) | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | SN-0292 | 2020-02-24 | New
75703 | MTCS CA SAN ELC EOS Testing Hardware Deployment POR20 | CA | SAN | ELC | El Cajon | MTC - Servers and Software | POInt | Yes | No | MTCS CA SAN ELC EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15
44926 | MTCH NE CON STN RF Passive Splitter Deployment POR20 | NE | CON | STN | Southington | MTC HE - Hub Signaling | POInt | Yes | No | MTCH NE CON STN RF Passive Splitter Deployment POR20 | Chassis | 8-way splitter | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15
59745 | R PHY_CCAP_PAV_RPHY Unbundled Solution V2_44119 | CA | ORG | PAV | Palos Verdes | RSPD - CCAP | POInt | Yes | No | R PHY CA ORG PAV RPHY CCAP Augment POR20 | License | License Activation | 345 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
75246 | R PHY_CCAP_MCY_RPHY Unbundled Solution V2_44027 | SE | NOR | MCY | Mid-City | R PHY | POInt | Yes | Yes | R PHY SE NOR MCY RPHY CCAP Augment POR20 | License | License Activation | 483 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
35010 | MTRN-NOR- T5-01 | CE | OKC | NOR | Norman | Metro Transport | POInt | Yes | Yes | MTRN CE OKC NOR T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15
34949 | MTRN-PRV- T5-01 | NE | RHD | PRV | Providence | Metro Transport | POInt | Yes | Yes | MTRN NE RHD PRV T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | SN-0154 | 2020-02-06 | Chg
74548 | R PHY_CCAP_PTM_RPHY Unbundled Solution V2_43946 | VA | HRD | PTM | Portsmouth (VA) | R PHY | POInt | Yes | Yes | R PHY VA HRD PTM RPHY CCAP Augment POR20 | License | License Activation | 69 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
34619 | CB Transport - New Router Harrison - FAY - Card Add | CE | NWA | FAY | Fayetteville | CB - Metro Core | POInt | Yes | Yes | CBMC CE NWA FAY Optics Only for Cisco T5 Augment POR20_V2 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-04-15 | 2020-05-15
34619 | CB Transport - New Router Harrison - HRN - Optics | CE | NWA | HRN | Harrison | CB - Metro Core | POInt | Yes | Yes | CBMC CE NWA FAY Optics Only for Cisco T5 Augment POR20_V2 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-04-15 | 2020-05-15
59522 | R PHY_CCAP_MCD_RPHY Unbundled Solution V2_43955 | SW | ARZ | MCD | McDowell | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ MCD RPHY CCAP Deployment POR20 | License | License Activation | 276 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
59745 | R PHY_CCAP_PWY_RPHY Unbundled Solution V2_44027 | CA | SAN | PWY | Poway | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN PWY RPHY CCAP Deployment POR20 | License | License Activation | 69 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
75703 | MTCS CE OKC TUL EOS Testing Hardware Deployment POR20 | CE | TUL | TUL | Tulsa | MTC - Servers and Software | POInt | Yes | No | MTCS CE TUL TUL EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15
59745 | R PHY_CCAP_IRV_RPHY Unbundled Solution V2_44027 | CA | ORG | IRV | Irvine | RSPD - CCAP | POInt | Yes | No | R PHY CA ORG IRV RPHY CCAP Augment POR20 | License | License Activation | 552 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
59745 | R PHY_CCAP_AVJ_RPHY Unbundled Solution V2_44027 | CA | ORG | AVJ | Aliso Viejo | RSPD - CCAP | POInt | Yes | No | R PHY CA ORG AVJ RPHY CCAP Augment POR20 | License | License Activation | 621 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
75703 | MTCS CA SAB SAB EOS Testing Hardware Deployment POR20 | CA | SAB | SAB | Santa Barbara | MTC - Servers and Software | POInt | Yes | No | MTCS CA SAB SAB EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-12-15
44876 | MTCH CE OMA OMM PEG Transport Deployment POR20 | CE | OMA | OMM | Omaha | MTC HE - Hub Signaling | POInt | Yes | No | MTCH CE OMA OMM PEG Transport Deployment POR20 | Chassis | Drake encoder (1 RU) | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | SN-0292 | 2020-02-24 | New
75838 | SW LAS HEN Cabling Refortification Augment POR20 | SW | LAS | HEN | Henderson | MTC Fiber and Rack Management | POInt | Yes | No | MVFM SW LAS HEN Cabling Refortification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-04-06 | 2020-05-15 | 2020-05-15 | SN-0388 | 2020-03-30 | Chg
75703 | MTCS SE MGA MCN EOS Testing Hardware Deployment POR20 | SE | MGA | MCN | Macon | MTC - Servers and Software | POInt | Yes | No | MTCS SE MGA MCN EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15
75703 | MTCS VA NVA MFD EOS Testing Hardware Deployment POR20 | VA | NVA | MFD | Merrifield | MTC - Servers and Software | POInt | Yes | No | MTCS VA NVA MFD EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15
75703 | MTCS SE GLA BTR EOS Testing Hardware Deployment POR20 | SE | BTR | BTR | Baton Rouge | MTC - Servers and Software | POInt | Yes | No | MTCS SE BTR BTR EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15
75703 | MTCS SE GLA ELM EOS Testing Hardware Deployment POR20 | SE | NOR | ELM | Elmwood | MTC - Servers and Software | POInt | Yes | No | MTCS SE NOR ELM EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15
59522 | R PHY_CCAP_ALI_RPHY Unbundled Solution V2_43961 | SW | LAS | ALI | Aliante | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS ALI RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
74548 | R PHY_CCAP_OCN_RPHY Unbundled Solution V2_44027 | VA | HRD | OCN | Oceana | R PHY | POInt | Yes | Yes | R PHY VA HRD OCN RPHY CCAP Augment POR20 | License | License Activation | 207 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
74548 | R PHY_CCAP_NRF_RPHY Unbundled Solution V2_44027 | VA | HRD | NRF | Norfolk | R PHY | POInt | Yes | Yes | R PHY VA HRD NRF RPHY CCAP Augment POR20 | License | License Activation | 483 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
34619 | CB Transport - New Router Strotherfield - WIC - Card Add | CE | KAN | WIC | Wichita | CB - Metro Core | POInt | Yes | Yes | CBMC CE KAN WIC Cisco T5 Card and Optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-04-15 | 2020-05-15 |  | SN-0419 | 2020-04-02 | Chg
75187 | R PHY_CCAP_OKC_RPHY Unbundled Solution V2_43942 | CE | OKC | OKC | OKC MTC | R PHY | POInt | Yes | Yes | R PHY CE OKC OKC RPHY CCAP Augment POR20 | License | License Activation | 69 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
34623 | CB Transport - New Router Valley - HEN - Optics | SW | LAS | HEN | Henderson | CB - Metro Core | POInt | Yes | Yes | CBMC SW LAS HEN Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-03-02 | 2020-05-15
59745 | R PHY_CCAP_CHU_RPHY Unbundled Solution V2_44027 | CA | SAN | CHU | Chula Vista | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN CHU RPHY CCAP Deployment POR20 | License | License Activation | 690 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
59522 | R PHY_CCAP_PNL_RPHY Unbundled Solution V2_43958 | SW | ARZ | PNL | Pinal County | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ PNL RPHY CCAP Deployment POR20 | License | License Activation | 69 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
35173 | MRTR NCS-Growth-BLU-100G Grow | SW | LAS | BLU | Blue Diamond | Metro Routers | POInt | Yes | Yes | MRTR SW LAS BLU NCS Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-04-01 | 2020-05-15 | 2020-06-15 | SN-0099 | 2020-02-06 | New
59522 | CBR8 Line Card-2 | SW | LAS | TEN | Tenaya | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03
34949 | MTRN-PAW- T5-01 | NE | RHD | PAW | Pawtucket | Metro Transport | POInt | Yes | Yes | MTRN NE RHD PAW T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15
34601 | WWCKBSPA01.RI.RI-SFM | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | CB - Metro Core | POInt | Yes | Yes | CBMC NE RHD WWK SFM-7950 XRS-20 Augment POR20 | Card & Optics | Nokia SFM-7950 XRS-20/20e SFM2-SA | 8 | 2020-01-15 | 2020-05-15 |  | SN-0419 | 2020-04-02 | Chg
59522 | R PHY_CCAP_MSA_RPHY Unbundled Solution V2_43953 | SW | ARZ | MSA | Mesa | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ MSA RPHY CCAP Deployment POR20 | License | License Activation | 1449 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
59522 | R PHY_CCAP_FWL_RPHY Unbundled Solution V2_43954 | SW | ARZ | FWL | Fowler | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ FWL RPHY CCAP Deployment POR20 | License | License Activation | 552 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
34970 | CFG TEN HV-CFG GEN GROW PROJECT - LARGE | SW | LAS | TEN | Tenaya | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW LAS TEN HV-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-02-01 | 2020-05-15
34946 | MTRN-ELM- T5-01 | SE | NOR | ELM | Elmwood | Metro Transport | POInt | Yes | Yes | MTRN SE NOR ELM T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-05-15 | 2020-06-15 | SN-0154 | 2020-02-06 | Chg
34619 | CB Transport - New Router Harrison - NWA - Card Add | CE | NWA | NWA | Johnson | CB - Metro Core | POInt | Yes | Yes | CBMC CE NWA NWA Optics Only for Cisco T5 Augment POR20_V2 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-04-15 | 2020-05-15
34623 | CB Transport - New Router Valley - TEN - Optics | SW | LAS | TEN | Tenaya | CB - Metro Core | POInt | Yes | Yes | CBMC SW LAS TEN Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-03-02 | 2020-05-15
34604 | CB Transport - New Router St Charles - STC - Card Add | SE | BTR | STC | St. Charles | CB - Metro Core | POInt | Yes | Yes | CBMC SE BTR STC Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-15 | 2020-05-15
35010 | MTRN-NEH- T5-01 | CE | OKC | NEH | North East | Metro Transport | POInt | Yes | Yes | MTRN CE OKC NEH T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15
34944 | MTRN-VST- T5-01 | CA | SAN | VST | Vista | Metro Transport | POInt | Yes | Yes | MTRN CA SAN VST T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | SN-0154 | 2020-02-06 | Chg
75842 | CA ORG AVJ Backbone Growth Edge Augment POR20 | CA | ORG | AVJ | Aliso Viejo | MTC Fiber and Rack Management | POInt | Yes | Yes | MVFM CA ORG AVJ Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15
34976 | CFG RMD BS-CBMC LARGE_2V_BATTSTRING | NE | RHD | RMD | Richmond (RI) | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE RHD RMD BS-CFG Deployment POR20 | Critical Facilities | LARGE_2V_BATTSTRING | 1 | 2020-02-15 | 2020-05-15
75187 | R PHY_CCAP_BAR_RPHY Unbundled Solution V2_43944 | CE | TUL | BAR | Broken Arrow | R PHY | POInt | Yes | Yes | R PHY CE TUL BAR RPHY CCAP Deployment POR20 | License | License Activation | 276 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
59522 | R PHY_CCAP_PEO_RPHY Unbundled Solution V2_43957 | SW | ARZ | PEO | Peoria | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ PEO RPHY CCAP Deployment POR20 | License | License Activation | 1173 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
34623 | CB Transport - New Router Valley - VLY - Optics | SW | LAS | VLY | Valley | CB - Metro Core | POInt | Yes | Yes | CBMC SW LAS VLY Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-03-02 | 2020-05-15
59522 | R PHY_CCAP_TUC_RPHY Unbundled Solution V2_43960 | SW | ARZ | TUC | Tucson | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ TUC RPHY CCAP Deployment POR20 | License | License Activation | 621 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
34619 | CB Transport - New Router Strotherfield - STR - Card Add | CE | KAN | STR | Strotherfield | CB - Metro Core | POInt | Yes | Yes | CBMC CE KAN STR Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-15 | 2020-05-15
59522 | R PHY_CCAP_HEN_RPHY Unbundled Solution V2_43965 | SW | LAS | HEN | Henderson | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS HEN RPHY CCAP Deployment POR20 | License | License Activation | 1449 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
59745 | R PHY_CCAP_VST_RPHY Unbundled Solution V2_43938 | CA | SAN | VST | Vista | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN VST RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 2 | 2020-04-17 | 2020-05-15 |  | SN-0060 | 2020-02-06 | New
74548 | R PHY_CCAP_PRA_RPHY Unbundled Solution V2_44027 | VA | HRD | PRA | Princess Anne | R PHY | POInt | Yes | Yes | R PHY VA HRD PRA RPHY CCAP Augment POR20 | License | License Activation | 69 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
35011 | MTRN-OCN- T5-01 | VA | HRD | OCN | Oceana | Metro Transport | POInt | Yes | Yes | MTRN VA HRD OCN T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15
75187 | R PHY_CCAP_ELK_RPHY Unbundled Solution V2_43943 | CE | OMA | ELK | Elkhorn | R PHY | POInt | Yes | Yes | R PHY CE OMA ELK RPHY CCAP Augment POR20 | License | License Activation | 138 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
35010 | MTRN-TUL- T5-01 | CE | TUL | TUL | Tulsa | Metro Transport | POInt | Yes | Yes | MTRN CE TUL TUL T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15
54569 | CFS FED BM-CFS GEN SUSTAIN PROJECT - MEDIUM | CA | SAN | FED | Federal | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CA SAN FED BM-CFS Augment POR20 - 2 | Critical Facilities | GEN SUSTAIN PROJECT - MEDIUM | 1 | 2020-04-01 | 2020-05-15 |  | SB-0010 | 2020-01-30 | Chg
75246 | R PHY_CCAP_LFY_RPHY Unbundled Solution V2_44027 | SE | LFY | LFY | Lafayette | R PHY | POInt | Yes | Yes | R PHY SE LFY LFY RPHY CCAP Augment POR20 | License | License Activation | 207 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
59745 | R PHY_CCAP_OCE_RPHY Unbundled Solution V2_44027 | CA | SAN | OCE | Oceanside | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN OCE RPHY CCAP Deployment POR20 | License | License Activation | 345 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
34619 | CB Transport - New Router Harrison - FAY - Chassis Add | CE | NWA | FAY | Fayetteville | CB - Metro Core | POInt | Yes | Yes | CBMC CE NWA FAY Cisco M6_M15 Chassis Augment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 1 | 2020-04-15 | 2020-05-15 |  | SN-0419 | 2020-04-02 | Chg
34975 | CFG LTF BS-CFG LARGE_2V_BATTSTRING | VA | HRD | LTF | Lightfoot | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA HRD LTF BS-CFG Deployment POR20 | Critical Facilities | LARGE_2V_BATTSTRING | 1 | 2020-01-01 | 2020-05-15
34623 | BELLSYSA01-ROUTER | SW | ARZ | BEL | Bell | CB - Metro Core | POInt | Yes | Yes | CBMC SW ARZ BEL ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-05-15 |  | SN-0144 | 2020-02-06 | Chg
59522 | R PHY_CCAP_CHD_RPHY Unbundled Solution V2_43952 | SW | ARZ | CHD | Chandler | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ CHD RPHY CCAP Deployment POR20 | License | License Activation | 552 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
35172 | NEXUS-GNS-93180-01 | SE | GAN | GNS | Gainesville | Metro Routers | POInt | Yes | Yes | MRTR SE GAN GNS Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 5 | 2020-04-20 | 2020-05-15 | 2020-06-15
75187 | R PHY_CCAP_FAY_RPHY Unbundled Solution V2_43941 | CE | NWA | FAY | Fayetteville | R PHY | POInt | Yes | Yes | R PHY CE NWA FAY RPHY CCAP Augment POR20 | License | License Activation | 69 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
34619 | CB Transport - New Router Strotherfield - KCY - Card Add | COR | NAT | KCY | Kansas City (1102 Grand) | CB - Metro Core | POInt | Yes | Yes | CBMC CE KAN KCY Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-04-15 | 2020-05-15
34619 | CB Transport - New Router Topeka - KCY - Card Add | COR | NAT | KCY | Kansas City (1102 Grand) | CB - Metro Core | POInt | Yes | Yes | CBMC CE KAN KCY Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-04-15 | 2020-05-15 |  | SN-0309 | 2020-03-02 | Chg
34970 | CFG CHD DC-CFG GEN GROW PROJECT - SMALL | SW | ARZ | CHD | Chandler | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ CHD BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-03-01 | 2020-05-15
74548 | R PHY_CCAP_VBC_RPHY Unbundled Solution V2_44027 | VA | HRD | VBC | Virginia Beach | R PHY | POInt | Yes | Yes | R PHY VA HRD VBC RPHY CCAP Augment POR20 | License | License Activation | 207 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
59522 | R PHY_CCAP_VLY_RPHY Unbundled Solution V2_43963 | SW | LAS | VLY | Valley | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS VLY RPHY CCAP Deployment POR20 | License | License Activation | 483 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
59745 | R PHY_CCAP_FED_RPHY Unbundled Solution V2_44027 | CA | SAN | FED | Federal | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN FED RPHY CCAP Deployment POR20 | License | License Activation | 690 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
34619 | CB Transport - New Router Topeka - TOP - Card Add | CE | KAN | TOP | Topeka | CB - Metro Core | POInt | Yes | Yes | CBMC CE KAN TOP Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-15 | 2020-05-15
59522 | R PHY_CCAP_SSC_RPHY Unbundled Solution V2_43959 | SW | ARZ | SSC | South Scottsdale | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ SSC RPHY CCAP Deployment POR20 | License | License Activation | 690 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
59745 | R PHY_CCAP_RSM_RPHY Unbundled Solution V2_43936 | CA | ORG | RSM | Rancho Santa Margarita | RSPD - CCAP | POInt | Yes | Yes | R PHY CA ORG RSM RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 2 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
59522 | R PHY_CCAP_BEL_RPHY Unbundled Solution V2_43950 | SW | ARZ | BEL | Bell | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ BEL RPHY CCAP Deployment POR20 | License | License Activation | 1311 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
35010 | MTRN-OKC- T5-01 | CE | OKC | OKC | OKC MTC | Metro Transport | POInt | Yes | Yes | MTRN CE OKC OKC T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-04-20 | 2020-05-15 | 2020-06-15
34601 | PROVBSPA01.RI.RI-SFM | NE | RHD | PRV | Providence | CB - Metro Core | POInt | Yes | Yes | CBMC NE RHD PRV SFM-7950 XRS-20 Augment POR20 | Card & Optics | Nokia SFM-7950 XRS-20/20e SFM2-SA | 8 | 2020-01-15 | 2020-05-15 |  | SN-0419 | 2020-04-02 | Chg
75187 | R PHY_CCAP_BVL_RPHY Unbundled Solution V2_43940 | CE | NWA | BVL | Bentonville | R PHY | POInt | Yes | Yes | R PHY CE NWA BVL RPHY CCAP Augment POR20 | License | License Activation | 138 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
34945 | MTRN-FTS- T5-01 | CE | NWA | FTS | Fort Smith | Metro Transport | POInt | Yes | Yes | MTRN CE NWA FTS T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | SN-0154 | 2020-02-06 | Chg
34619 | CB Transport - New Router Topeka - NWT - Card Add | CE | KAN | NWT | Newton | CB - Metro Core | POInt | Yes | Yes | CBMC CE KAN NWT Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-04-15 | 2020-05-15
59745 | R PHY_CCAP_DWN_RPHY CCAP Licenses Q2_18.14 | CA | SAN | DWN | Downtown | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN DWN RPHY CCAP Deployment POR20 | License | CCAP license | 414 | 2020-04-15 | 2020-05-15 | 2020-05-15 | SN-0550 | 2020-05-12 | New
34946 | MTRN-LPL- T5-01 | SE | NOR | LPL | Lapalco | Metro Transport | POInt | Yes | Yes | MTRN SE NOR LPL T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-05-15 | 2020-06-15 | SN-0154 | 2020-02-06 | Chg
59522 | R PHY_CCAP_BLU_RPHY Unbundled Solution V2_43966 | SW | LAS | BLU | Blue Diamond | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS BLU RPHY CCAP Deployment POR20 | License | License Activation | 2415 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
74548 | R PHY_CCAP_CHS_RPHY Unbundled Solution V2_44027 | VA | HRD | CHS | Chesapeake | R PHY | POInt | Yes | Yes | R PHY VA HRD CHS RPHY CCAP Augment POR20 | License | License Activation | 276 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
59745 | R PHY_CCAP_ESC_RPHY Unbundled Solution V2_44027 | CA | SAN | ESC | Escondido | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN ESC RPHY CCAP Deployment POR20 | License | License Activation | 69 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
59522 | R PHY_CCAP_NSC_RPHY Unbundled Solution V2_43956 | SW | ARZ | NSC | North Scottsdale | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ NSC RPHY CCAP Deployment POR20 | License | License Activation | 69 | 2020-04-15 | 2020-05-15 |  | SN-0217 | 2020-02-03 | Chg
35010 | MTRN-DTN- T5-01 | CE | TUL | DTN | Downtown (TUL) | Metro Transport | POInt | Yes | Yes | MTRN CE TUL DTN T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15
35172 | NEXUS-PNS-93180-01 | SE | GCT | PNS | Pensacola with (Insite tower) | Metro Routers | POInt | Yes | Yes | MRTR SE GCT PNS Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15
54572 | CFS VA HRD GBR DC-CFS Augment POR20 | VA | HRD | GBR | Greenbrier | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD GBR DC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-20 |  | SB-0049 | 2020-02-28 | New
34601 | WWCKBSPA01.RI.RI-100G CARD | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | CB - Metro Core | POInt | Yes | Yes | CBMC NE RHD WWK 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-01-15 | 2020-05-20 |  | SN-0478 | 2020-04-24 | Chg
34971 | CFG CA SAN DWN BS-CFG Deployment POR20 | CA | SAN | DWN | Downtown | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA SAN DWN BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-20 |  | SN-0411 | 2020-03-27
34976 | CFG NE CON ENF HV-CFG Deployment POR20 | NE | CON | ENF | Enfield | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE CON ENF HV-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-20 |  | SN-0262 | 2020-02-28
34601 | PROVBSPA01.RI.RI-100G CARD | NE | RHD | PRV | Providence | CB - Metro Core | POInt | Yes | Yes | CBMC NE RHD PRV 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-01-15 | 2020-05-20 |  | SN-0478 | 2020-04-24 | Chg
34971 | CFG CA ORG RSM AC-CFG Deployment POR20 | CA | ORG | RSM | Rancho Santa Margarita | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA ORG RSM AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-20 |  | SN-0262 | 2020-02-28 | New
34976 | CFG NE CLE CLV IV-CFG Deployment POR20 | NE | CLE | CLV | Cleveland | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE CLE CLV IV-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-20 |  | SN-0411 | 2020-03-27
34976 | CFG NE CON RKH HV-CFG Deployment POR20 | NE | CON | RKH | Rocky Hill | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE CON RKH HV-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-20 |  | SN-0262 | 2020-02-28
34622 | FED1EWAA03-100G CARD | CA | SAN | FED | Federal | CB - Metro Core | POInt | Yes | Yes | CBMC CA SAN FED 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 2 | 2020-02-15 | 2020-05-20 |  | SN-0478 | 2020-04-24 | Chg
34619 | CB Transport - New Router Braden - BAR - Chassis Add | CE | TUL | BAR | Broken Arrow | CB - Metro Core | POInt | Yes | Yes | CBMC CE TUL BAR Cisco M6_M15 Chassis Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 1 | 2020-02-15 | 2020-05-20 |  | SN-0586 | 2020-05-14 | Chg
34619 | Walker-OCML-IXR | CE | OKC | WLK | Walker Hub | CB - Metro Core | POInt | Yes | Yes | CBMC CE OKC WLK OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-05-20 |  | SN-0586 | 2020-05-14 | Chg
75655 | Arbor 4 | COR | NAT | NY1 | New York (cage 634.M25) | Arbor DDoS | POInt | Yes | No | DDoS NE NAT NY1 Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-04-17 | 2020-05-20 | 2020-06-19 | SN-0220 | 2020-02-03 | Chg
34619 | CB Transport - New Router Sapulpa - TUL - Optics | CE | TUL | TUL | Tulsa | CB - Metro Core | POInt | Yes | No | CBMC CE TUL TUL Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-03-15 | 2020-05-20 |  | SN-0586 | 2020-05-14 | Chg
34972 | CFG CE TUL BRD RK-CFG Deployment POR20 | CE | TUL | BRD | Braden | Critical Facilities (Grow) | POInt | Yes | No | CFG CE TUL BRD RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-20 |  | SN-0411 | 2020-03-27
34635 | BWM HRD DOCSIS Expansion 96 MHz | VA | HRD | CHS | Chesapeake | Bandwidth Management | POInt | Yes | No | BWM VA HRD CHS DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-05-21 | 2021-07-01 | SN-0558 | 2020-05-12 | New
34635 | BWM HRD DOCSIS Expansion 192 MHz | VA | HRD | CHS | Chesapeake | Bandwidth Management | POInt | Yes | No | BWM VA HRD CHS DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-05-21 | 2022-04-01 | SN-0558 | 2020-05-12 | New
75647 | Nokia 1830 Add 6 | SW | LAS | TEN | Tenaya | C4 & C4B Transport Network | POInt | Yes | No | C4B SW LAS TEN Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis | 5 | 2020-03-01 | 2020-05-22 |  | SN-0551 | 2020-05-13 | Chg
75655 | Arbor 7 | COR | NAT | DC2/6 | Ashburn/DC (cage 2500/61445) | Arbor DDoS | POInt | Yes | No | DDoS VA NAT DC2 Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-04-23 | 2020-05-23 | 2020-06-21 | SN-0220 | 2020-02-03 | Chg
75655 | Arbor 20 | CE | OMA | OMM | Omaha | Arbor DDoS | POInt | Yes | No | DDoS CE OMA OMM Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-03-26 | 2020-05-25 | 2020-06-08 | SN-0107 | 2020-02-06 | Chg
75758 | Bus Req Proj Concept Doc Empirix SoW | COR | COR | ATL | Atlanta | Voice Monitoring and Analytics | POInt | Yes | No | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other | 1 | 2020-01-02 | 2020-05-25 |  | SB-0140 | 2020-05-28 | Chg
75758 | Upgrade lab E-XMS systems to 5.7.5 | COR | COR | ATL | Atlanta | Voice Monitoring and Analytics | POInt | Yes | No | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other | 1 | 2020-03-17 | 2020-05-25 |  | SB-0140 | 2020-05-28 | Chg
75655 | Arbor 3 | COR | NAT | CH1 | Chicago - Digital Realty (cage 1060.M03 - Backbone) | Arbor DDoS | POInt | Yes | No | DDoS CE NAT CH1 Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-04-24 | 2020-05-27 | 2020-06-26 | SN-0220 | 2020-02-03 | Chg
75645 | CGN Replacement 6 | CA | SAN | FED | Federal | Data Center Capacity | POInt | Yes | No | DTC CA SAN FED CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-01-04 | 2020-05-27 |  | SN-0554 | 2020-05-13 | Chg
75758 | Augment ODI Environment | COR | COR | ATL | Atlanta | Voice Monitoring and Analytics | POInt | Yes | No | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other | 1 | 2020-05-04 | 2020-05-29 |  | SB-0045 | 2020-01-31
75830 | SBC resiliency - failover and service restoration | COR | COR | ATL | Atlanta | Voice Network Upgrades | POInt | Yes | No | VNU CO -CO ATL Metaswitch Lifecycle Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-02 | 2020-05-29 | 2020-05-29 | SB-0047 | 2020-01-31 | New
59745 | R PHY_CCAP_PAV_CBR8 Line Card | CA | ORG | PAV | Palos Verdes | RSPD - CCAP | POInt | Yes | No | R PHY CA ORG PAV RPHY CCAP Augment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
59745 | R PHY_CCAP_VST_RPHY CCAP Licenses_Q2_18.14 | CA | SAN | VST | Vista | R PHY | POInt | Yes | No | R PHY CA SAN VST R PHY CCAP Deployment POR20 | License | CCAP license | 552 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
75187 | R PHY_CCAP_WLK_RPHY CCAP Licenses_Q2_18.14 | CE | OKC | WLK | Walker Hub | R PHY | POInt | Yes | Yes | R PHY CE OKC WLK RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
59745 | R PHY_CCAP_PWY_RPHY CCAP Licenses_Q2_18.14 | CA | SAN | PWY | Poway | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN PWY RPHY CCAP Deployment POR20 | License | CCAP license | 311 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_MCD_RPHY CCAP Licenses_Q2_18.14 | SW | ARZ | MCD | McDowell | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ MCD RPHY CCAP Deployment POR20 | License | CCAP license | 138 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
74548 | R PHY_CCAP_PTM_RPHY CCAP Licenses_Q2_18.14 | VA | HRD | PTM | Portsmouth (VA) | R PHY | POInt | Yes | Yes | R PHY VA HRD PTM RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
75246 | R PHY_CCAP_MCY_RPHY CCAP Licenses_Q2_18.14 | SE | NOR | MCY | Mid-City | R PHY | POInt | Yes | Yes | R PHY SE NOR MCY RPHY CCAP Augment POR20 | License | CCAP license | 828 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
59745 | R PHY_CCAP_ORG_RPHY CCAP Licenses_Q2_18.14 | CA | ORG | ORG | Orange | RSPD - CCAP | POInt | Yes | No | R PHY CA ORG ORG RPHY CCAP Augment POR20 | License | CCAP license | 828 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
59745 | R PHY_CCAP_DNP_RPHY CCAP Licenses_Q2_18.14 | CA | ORG | DNP | Dana Point | RSPD - CCAP | POInt | Yes | No | R PHY CA ORG DNP RPHY CCAP Augment POR20 | License | CCAP license | 535 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
75187 | R PHY_CCAP_YAL_RPHY CCAP Licenses_Q2_18.14 | CE | TUL | YAL | Yale | R PHY | POInt | Yes | No | R PHY CE TUL YAL RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
59745 | R PHY_CCAP_AVJ_RPHY CCAP Licenses_Q2_18.14 | CA | ORG | AVJ | Aliso Viejo | RSPD - CCAP | POInt | Yes | No | R PHY CA ORG AVJ RPHY CCAP Augment POR20 | License | CCAP license | 2261 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
59745 | R PHY_CCAP_IRV_RPHY CCAP Licenses_Q2_18.14 | CA | ORG | IRV | Irvine | RSPD - CCAP | POInt | Yes | No | R PHY CA ORG IRV RPHY CCAP Augment POR20 | License | CCAP license | 1631 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_OSB_RPHY CCAP Licenses_Q2_18.14 | SW | LAS | OSB | Oso Blanca | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | License | CCAP license | 509 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
74548 | R PHY_CCAP_NRF_RPHY CCAP Licenses_Q2_18.14 | VA | HRD | NRF | Norfolk | R PHY | POInt | Yes | Yes | R PHY VA HRD NRF RPHY CCAP Augment POR20 | License | CCAP license | 483 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
74548 | R PHY_CCAP_OCN_RPHY CCAP Licenses_Q2_18.14 | VA | HRD | OCN | Oceana | R PHY | POInt | Yes | Yes | R PHY VA HRD OCN RPHY CCAP Augment POR20 | License | CCAP license | 138 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_TEN_RPHY CCAP Licenses_Q2_18.14 | SW | LAS | TEN | Tenaya | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | License | CCAP license | 1985 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
59745 | R PHY_CCAP_CHU_RPHY CCAP Licenses_Q2_18.14 | CA | SAN | CHU | Chula Vista | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN CHU RPHY CCAP Deployment POR20 | License | CCAP license | 1287 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_ALI_RPHY CCAP Licenses_Q2_18.14 | SW | LAS | ALI | Aliante | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS ALI RPHY CCAP Deployment POR20 | License | CCAP license | 518 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_FWL_RPHY CCAP Licenses_Q2_18.14 | SW | ARZ | FWL | Fowler | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ FWL RPHY CCAP Deployment POR20 | License | CCAP license | 1794 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_FWL_D9485_43845 | SW | ARZ | FWL | Fowler | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ FWL RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-02-15 | 2020-05-30 |  | SN-0550 | 2020-05-12 | Chg
59522 | R PHY_CCAP_MSA_RPHY CCAP Licenses_Q2_18.14 | SW | ARZ | MSA | Mesa | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ MSA RPHY CCAP Deployment POR20 | License | CCAP license | 2010 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_MSA_D9485_43845 | SW | ARZ | MSA | Mesa | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ MSA RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-02-15 | 2020-05-30 |  | SN-0550 | 2020-05-12 | Chg
59522 | R PHY_CCAP_HEN_D9485_43845 | SW | LAS | HEN | Henderson | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS HEN RPHY CCAP Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-02-15 | 2020-05-30 |  | SN-0550 | 2020-05-12 | Chg
59522 | R PHY_CCAP_HEN_RPHY CCAP Licenses_Q2_18.14 | SW | LAS | HEN | Henderson | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS HEN RPHY CCAP Deployment POR20 | License | CCAP license | 5433 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_TUC_RPHY CCAP Licenses_Q2_18.14 | SW | ARZ | TUC | Tucson | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ TUC RPHY CCAP Deployment POR20 | License | CCAP license | 483 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_PEO_RPHY CCAP Licenses_Q2_18.14 | SW | ARZ | PEO | Peoria | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ PEO RPHY CCAP Deployment POR20 | License | CCAP license | 828 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
75187 | R PHY_CCAP_BAR_RPHY CCAP Licenses_Q2_18.14 | CE | TUL | BAR | Broken Arrow | R PHY | POInt | Yes | Yes | R PHY CE TUL BAR RPHY CCAP Deployment POR20 | License | CCAP license | 207 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
75187 | R PHY_CCAP_ELK_RPHY CCAP Licenses_Q2_18.14 | CE | OMA | ELK | Elkhorn | R PHY | POInt | Yes | Yes | R PHY CE OMA ELK RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
75246 | R PHY_CCAP_LFY_RPHY CCAP Licenses_Q2_18.14 | SE | LFY | LFY | Lafayette | R PHY | POInt | Yes | Yes | R PHY SE LFY LFY RPHY CCAP Augment POR20 | License | CCAP license | 207 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
74548 | R PHY_CCAP_PRA_RPHY CCAP Licenses_Q2_18.14 | VA | HRD | PRA | Princess Anne | R PHY | POInt | Yes | Yes | R PHY VA HRD PRA RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
59745 | R PHY_CCAP_OCE_RPHY CCAP Licenses_Q2_18.14 | CA | SAN | OCE | Oceanside | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN OCE RPHY CCAP Deployment POR20 | License | CCAP license | 578 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_CHD_RPHY CCAP Licenses_Q2_18.14 | SW | ARZ | CHD | Chandler | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ CHD RPHY CCAP Deployment POR20 | License | CCAP license | 837 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
74548 | R PHY_CCAP_VBC_RPHY CCAP Licenses_Q2_18.14 | VA | HRD | VBC | Virginia Beach | R PHY | POInt | Yes | Yes | R PHY VA HRD VBC RPHY CCAP Augment POR20 | License | CCAP license | 414 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_VLY_RPHY CCAP Licenses_Q2_18.14 | SW | LAS | VLY | Valley | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS VLY RPHY CCAP Deployment POR20 | License | CCAP license | 414 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
59745 | R PHY_CCAP_FED_RPHY CCAP Licenses_Q2_18.14 | CA | SAN | FED | Federal | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN FED RPHY CCAP Deployment POR20 | License | CCAP license | 1527 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
74548 | R PHY_CCAP_NWP_RPHY CCAP Licenses_Q2_18.14 | VA | HRD | NWP | Newport News | R PHY | POInt | Yes | Yes | R PHY VA HRD NWP RPHY CCAP Augment POR20 | License | CCAP license | 2208 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
59745 | R PHY_CCAP_ELC_RPHY CCAP Licenses_Q2_18.14 | CA | SAN | ELC | El Cajon | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN ELC RPHY CCAP Deployment POR20 | License | CCAP license | 923 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
59745 | R PHY_CCAP_DWN_RPHY CCAP Licenses_Q2_18.14 | CA | SAN | DWN | Downtown | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN DWN RPHY CCAP Deployment POR20 | License | CCAP license | 26 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
75187 | R PHY_CCAP_BVL_RPHY CCAP Licenses_Q2_18.14 | CE | NWA | BVL | Bentonville | R PHY | POInt | Yes | Yes | R PHY CE NWA BVL RPHY CCAP Augment POR20 | License | CCAP license | 138 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_BEL_RPHY CCAP Licenses_Q2_18.14 | SW | ARZ | BEL | Bell | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ BEL RPHY CCAP Deployment POR20 | License | CCAP license | 1665 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
59745 | R PHY_CCAP_RSM_CBR8 Line Card | CA | ORG | RSM | Rancho Santa Margarita | RSPD - CCAP | POInt | Yes | Yes | R PHY CA ORG RSM RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_SSC_RPHY CCAP Licenses_Q2_18.14 | SW | ARZ | SSC | South Scottsdale | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ SSC RPHY CCAP Deployment POR20 | License | CCAP license | 1104 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_NSC_RPHY CCAP Licenses_Q2_18.14 | SW | ARZ | NSC | North Scottsdale | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ NSC RPHY CCAP Deployment POR20 | License | CCAP license | 138 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
59745 | R PHY_CCAP_ESC_RPHY CCAP Licenses_Q2_18.14 | CA | SAN | ESC | Escondido | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN ESC RPHY CCAP Deployment POR20 | License | CCAP license | 138 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
74548 | R PHY_CCAP_CHS_RPHY CCAP Licenses_Q2_18.14 | VA | HRD | CHS | Chesapeake | R PHY | POInt | Yes | Yes | R PHY VA HRD CHS RPHY CCAP Augment POR20 | License | CCAP license | 276 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_ERN_RPHY CCAP Licenses_Q2_18.14 | SW | LAS | ERN | Ernest May | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | License | CCAP license | 1521 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_BUK_RPHY CCAP Licenses_Q2_18.14 | SW | ARZ | BUK | Buckeye | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ BUK RPHY CCAP Deployment POR20 | License | CCAP license | 138 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_BLU_CBR8 Line Card | SW | LAS | BLU | Blue Diamond | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS BLU RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-04-15 | 2020-05-30 | 2020-05-30 | SN-0550 | 2020-05-12 | New
74648 | RPHY MRTR-New-PRA-CIN-RPA-5110 | VA | HRD | PRA | Princess Anne | R PHY | POInt | Yes | Yes | R PHY VA HRD PRA RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-05-31 |  | SN-0211 | 2020-01-23 | New
74648 | RPHY MRTR-New-PRA-CIN-DPA-5200 | VA | HRD | PRA | Princess Anne | R PHY | POInt | Yes | Yes | R PHY VA HRD PRA RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-05-31 |  | SN-0211 | 2020-01-23 | New
74648 | RPHY MRTR-New-PRA-CIN MGMT-2K | VA | HRD | PRA | Princess Anne | R PHY | POInt | Yes | Yes | R PHY VA HRD PRA RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-05-31 |  | SN-0211 | 2020-01-23 | New
74648 | RPHY MRTR-New-PRA-CIN-ATX-OCML | VA | HRD | PRA | Princess Anne | R PHY | POInt | Yes | Yes | R PHY VA HRD PRA RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-05-31 |  | SN-0606 | 2020-05-22 | New
74648 | RPHY MRTR-New-PTM-CIN MGMT-2K | VA | HRD | PTM | Portsmouth (VA) | R PHY | POInt | Yes | Yes | R PHY VA HRD PTM RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-05-31 |  | SN-0211 | 2020-01-23
74648 | RPHY MRTR-New-PTM-CIN-DPA-5200 | VA | HRD | PTM | Portsmouth (VA) | R PHY | POInt | Yes | Yes | R PHY VA HRD PTM RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-05-31 |  | SN-0211 | 2020-01-23
74648 | RPHY MRTR-New-PTM-CIN-RPA-5110 | VA | HRD | PTM | Portsmouth (VA) | R PHY | POInt | Yes | Yes | R PHY VA HRD PTM RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-05-31 |  | SN-0211 | 2020-01-23
74648 | RPHY MRTR-New-PTM-CIN-ATX-OCML | VA | HRD | PTM | Portsmouth (VA) | R PHY | POInt | Yes | Yes | R PHY VA HRD PTM RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-05-31 |  | SN-0606 | 2020-05-22 | New
75842 | CA ORG RSM Backbone GrowthRDC Augment POR20 | CA | ORG | RSM | Rancho Santa Margarita | MTC Fiber and Rack Management | POInt | Yes | Yes | MVFM CA ORG RSM Raceway Reforification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-05-31 | 2020-06-30 | SN-0230 | 2020-01-31 | Chg
74548 | R PHY_CCAP_PRA_CBR8-1 | VA | HRD | PRA | Princess Anne | R PHY | POInt | Yes | Yes | R PHY VA HRD PRA RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-05-31 |  | SN-0208 | 2020-01-24 | New
74548 | R PHY_CCAP_PRA_Boundary_Clocks-1 | VA | HRD | PRA | Princess Anne | R PHY | POInt | Yes | Yes | R PHY VA HRD PRA RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-05-31 |  | SN-0605 | 2020-05-22 | Chg
74548 | R PHY_CCAP_PTM_CBR8-1 | VA | HRD | PTM | Portsmouth (VA) | R PHY | POInt | Yes | Yes | R PHY VA HRD PTM RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-05-31 |  | SN-0208 | 2020-01-24 | New
74548 | R PHY_CCAP_PTM_Boundary_Clocks-1 | VA | HRD | PTM | Portsmouth (VA) | R PHY | POInt | Yes | Yes | R PHY VA HRD PTM RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-05-31 |  | SN-0605 | 2020-05-22 | Chg
75246 | R PHY_CCAP_LFY_RPHY Unbundled Solution V2_43948 | SE | LFY | LFY | Lafayette | R PHY | POInt | Yes | Yes | R PHY SE LFY LFY RPHY CCAP Augment POR20 | License | License Activation | 3 | 2020-03-01 | 2020-05-31 |  | SN-0605 | 2020-05-22 | Chg
75246 | R PHY_CCAP_LFY_CBR8-1 | SE | LFY | LFY | Lafayette | R PHY | POInt | Yes | Yes | R PHY SE LFY LFY RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-05-31 |  | SN-0208 | 2020-01-24 | New
75246 | R PHY_CCAP_LFY_Boundary_Clocks-1 | SE | LFY | LFY | Lafayette | R PHY | POInt | Yes | Yes | R PHY SE LFY LFY RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-05-31 |  | SN-0613 | 2020-05-29 | Chg
75788 | CDN Deploy 8 | SW | LAS | TEN | Tenaya | CDN | POInt | Yes | No | CDN SW LAS TEN Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 1 | 2020-04-01 | 2020-05-31 | 2020-06-14 | SN-0285 | 2020-02-24 | Chg
75842 | CA SAN FED Backbone GrowthRDC Augment POR20 | CA | SAN | FED | Federal | MTC Fiber and Rack Management | POInt | Yes | No | MVFM CA SAN FED Raceway Reforification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-05-31 | 2020-06-30 | SN-0230 | 2020-01-31 | Chg
75844 | NE CON GLB ALU Nokia Fiber Augment POR20 | NE | CON | GLB | Glastonbury | MTC Fiber and Rack Management | POInt | Yes | No | MVFM NE CON GLB ALU Nokia Fiber Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-05-31 | 2020-05-31 | SN-0308 | 2020-02-28 | Chg
75658 | VA-OMM-1x Niagra PT-3225 | CE | OMA | OMM | Omaha | Visibility Architecture | POInt | Yes | No | VIA CE OMA OMM Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis | 1 | 2020-04-01 | 2020-05-31 | 2020-06-08 | SN-0094 | 2020-02-06 | New
75658 | VA-OMM-1x Juniper EX4600 | CE | OMA | OMM | Omaha | Visibility Architecture | POInt | Yes | No | VIA CE OMA OMM Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-04-01 | 2020-05-31 | 2020-06-08 | SN-0094 | 2020-02-06 | Chg
75788 | CDN Deploy 9 | SW | LAS | HEN | Henderson | CDN | POInt | Yes | No | CDN SW LAS HEN Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 1 | 2020-04-01 | 2020-05-31 | 2020-06-14 | SN-0285 | 2020-02-24 | Chg
75243 | RPHY MRTR-New-LFY-CIN MGMT-2K | SE | LFY | LFY | Lafayette | R PHY | POInt | Yes | Yes | R PHY SE LFY LFY RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-05-31 |  | SN-0211 | 2020-01-23 | New
75243 | RPHY MRTR-New-LFY-CIN-DPA-5200 | SE | LFY | LFY | Lafayette | R PHY | POInt | Yes | Yes | R PHY SE LFY LFY RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-05-31 |  | SN-0211 | 2020-01-23 | New
75243 | RPHY MRTR-New-LFY-CIN-RPA-5110 | SE | LFY | LFY | Lafayette | R PHY | POInt | Yes | Yes | R PHY SE LFY LFY RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-05-31 |  | SN-0211 | 2020-01-23 | New
75243 | RPHY MRTR-New-LFY-CIN-ATX-OCML | SE | LFY | LFY | Lafayette | R PHY | POInt | Yes | Yes | R PHY SE LFY LFY RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-05-31 |  | SN-0606 | 2020-05-22 | New
75844 | NE RHD SCT ALU Nokia Fiber Augment POR20 | NE | RHD | SCT | Scituate | MTC Fiber and Rack Management | POInt | Yes | No | MVFM NE RHD SCT ALU Nokia Fiber Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-05-31 | 2020-05-31 | SN-0308 | 2020-02-28 | Chg
75842 | CA SAN ELC Backbone GrowthRDC Augment POR20 | CA | SAN | ELC | El Cajon | MTC Fiber and Rack Management | POInt | Yes | No | MVFM CA SAN ELC Raceway Reforification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-05-31 | 2020-06-30 | SN-0230 | 2020-01-31 | Chg
34608 | Roanoke-OCML-IXR | VA | ROA | RON | Roanoke | CB - Metro Core | POInt | Yes | Yes | CBMC VA ROA RON OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | SN-0246 | 2020-02-24 | Chg
44923 | MTCH CA SAB SAB RPHY Test Rack Deployment POR20 | CA | SAB | SAB | Santa Barbara | MTC HE - Hub Signaling | POInt | Yes | No | MTCH CA SAB SAB RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-04-06 | 2020-06-01 |  | SN-0219 | 2020-04-03
34622 | Oceanside-OCML-IXR | CA | SAN | OCE | Oceanside | CB - Metro Core | POInt | Yes | Yes | CBMC CA SAN OCE OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | SN-0246 | 2020-02-24 | Chg
34622 | Irvine (IR)-OCML-IXR | CA | ORG | IRV | Irvine | CB - Metro Core | POInt | Yes | Yes | CBMC CA ORG IRV OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | SN-0246 | 2020-02-24 | Chg
34622 | Palos Verdes (PV)-OCML-IXR | CA | ORG | PAV | Palos Verdes | CB - Metro Core | POInt | Yes | Yes | CBMC CA ORG PAV OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | SN-0246 | 2020-02-24 | Chg
34604 | St. Charles West-OCML-IXR | SE | NOR | LUL | Luling | CB - Metro Core | POInt | Yes | Yes | CBMC SE NOR LUL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | SN-0246 | 2020-02-24 | Chg
34619 | Tulsa MTC-OCML-IXR | CE | TUL | TUL | Tulsa | CB - Metro Core | POInt | Yes | No | CBMC CE TUL TUL OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | SN-0246 | 2020-02-24 | Chg
44926 | MTCH NE CLE CLV RPHY Test Rack Deployment POR20 | NE | CLE | CLV | Cleveland | MTC HE - Hub Signaling | POInt | Yes | No | MTCH NE CLE CLV RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-04-06 | 2020-06-01 |  | SN-0219 | 2020-04-03
44927 | MTCH VA HRD LTF RPHY Test Rack Deployment POR20 | VA | HRD | LTF | Lightfoot | MTC HE - Hub Signaling | POInt | Yes | No | MTCH VA HRD LTF RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-04-06 | 2020-06-01 |  | SN-0219 | 2020-04-03
44924 | MTCH SW LAS OSB RPHY Test Rack Deployment POR20 | SW | LAS | OSB | Oso Blanca | MTC HE - Hub Signaling | POInt | Yes | No | MTCH SW LAS OSB RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-04-06 | 2020-06-01 |  | SN-0219 | 2020-04-03
76106 | Grafana DDR | COR | COR | DDR | Duke Drive | Data Center Network Health | POInt | Yes | No | DCNH COR COR DDR NetworkHealth POR20 | Labor | No Equipment | 1 |  | 2020-06-01 |  | SN-0129 | 2020-02-06 | New
34604 | Mid City-OCML-IXR | SE | NOR | MCY | Mid-City | CB - Metro Core | POInt | Yes | Yes | CBMC SE NOR MCY OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | SN-0246 | 2020-02-24 | Chg
34622 | Poway-OCML-IXR | CA | SAN | PWY | Poway | CB - Metro Core | POInt | Yes | Yes | CBMC CA SAN PWY OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | SN-0246 | 2020-02-24 | Chg
35177 | NEXUS-FBG-93180-01 | VA | NVA | FBG | Fredericksburg | Metro Routers | POInt | Yes | Yes | MRTR VA NVA FBG Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-04-20 | 2020-06-01 | 2020-06-01 | SN-0239 | 2020-02-07 | New
35177 | NEXUS-FBG-2248-01 | VA | NVA | FBG | Fredericksburg | Metro Routers | POInt | Yes | Yes | MRTR VA NVA FBG Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-04-20 | 2020-06-01 | 2020-06-01 | SN-0239 | 2020-02-07 | New
35010 | Metro OTN-GAR-Ciena 6500 S14 | CE | TUL | GAR | Garnett | Metro Transport | POInt | Yes | Yes | MTRN CE TUL GAR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-06-01 | 2020-08-01
35010 | Metro OTN-GAR-Ciena 6500 S2 | CE | TUL | GAR | Garnett | Metro Transport | POInt | Yes | Yes | MTRN CE TUL GAR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-06-01 | 2020-08-01
35010 | Metro OTN-YAL-Ciena 6500 S14 | CE | TUL | YAL | Yale | Metro Transport | POInt | Yes | Yes | MTRN CE TUL YAL OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-06-01 | 2020-08-01
35010 | Metro OTN-YAL-Ciena 6500 S2 | CE | TUL | YAL | Yale | Metro Transport | POInt | Yes | Yes | MTRN CE TUL YAL OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-06-01 | 2020-08-01
35010 | Metro OTN-QNC-Ciena 6500 S14 | CE | TUL | QNC | Quincy | Metro Transport | POInt | Yes | Yes | MTRN CE TUL QNC OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-06-01 | 2020-08-01
35010 | Metro OTN-QNC-Ciena 6500 S2 | CE | TUL | QNC | Quincy | Metro Transport | POInt | Yes | Yes | MTRN CE TUL QNC OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-06-01 | 2020-08-01
35175 | NEXUS-SCT-93180-01 | NE | RHD | SCT | Scituate | Metro Routers | POInt | Yes | Yes | MRTR NE RHD SCT Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-04-20 | 2020-06-01
35010 | Metro OTN-IND-Ciena 6500 S14 | CE | TUL | IND | Indianapolis | Metro Transport | POInt | Yes | Yes | MTRN CE TUL IND OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-06-01 | 2020-08-01
35010 | Metro OTN-IND-Ciena 6500 S2 | CE | TUL | IND | Indianapolis | Metro Transport | POInt | Yes | Yes | MTRN CE TUL IND OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-04-15 | 2020-06-01 | 2020-08-01
34622 | Dana Point (DP)-OCML-IXR | CA | ORG | DNP | Dana Point | CB - Metro Core | POInt | Yes | Yes | CBMC CA ORG DNP OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | SN-0246 | 2020-02-24 | Chg
35010 | Metro OTN-OWA-Ciena 6500 S14 | CE | TUL | OWA | Owasso | Metro Transport | POInt | Yes | Yes | MTRN CE TUL OWA OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-06-01 | 2020-08-01
35010 | Metro OTN-OWA-Ciena 6500 S2 | CE | TUL | OWA | Owasso | Metro Transport | POInt | Yes | Yes | MTRN CE TUL OWA OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-06-01 | 2020-08-01
54571 | CFS SE BTR LGR SC-CFS Augment POR20 | SE | BTR | LGR | Lutcher | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE BTR LGR SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-01 |  | SB-0023 | 2020-01-30 | New
54570 | CFS CE OMA ELK SC-CFS Augment POR20 | CE | OMA | ELK | Elkhorn | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE OMA ELK SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-06-01 | 2020-06-01 |  | SB-0049 | 2020-02-28 | New
54571 | CFS SE NOR ELM SC-CFS Augment POR20 | SE | NOR | ELM | Elmwood | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE NOR ELM SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-01 |  | SB-0023 | 2020-01-30 | New
35177 | NEXUS-RON-2248-01 | VA | ROA | RON | Roanoke | Metro Routers | POInt | Yes | Yes | MRTR VA ROA RON Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 3 | 2020-04-20 | 2020-06-01 | 2020-06-01 | SN-0239 | 2020-02-07 | Chg
35177 | NEXUS-RON-93108-01 | VA | ROA | RON | Roanoke | Metro Routers | POInt | Yes | Yes | MRTR VA ROA RON Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 2 | 2020-04-20 | 2020-06-01 | 2020-06-01 | SN-0588 | 2020-05-14
35177 | NEXUS-RON-93180-01 | VA | ROA | RON | Roanoke | Metro Routers | POInt | Yes | Yes | MRTR VA ROA RON Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 4 | 2020-04-20 | 2020-06-01 | 2020-06-01 | SN-0239 | 2020-02-07 | Chg
54571 | CFS SE LFY NIB SC-CFS Augment POR20 | SE | LFY | NIB | New Iberia | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE LFY NIB SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-01 |  | SB-0023 | 2020-01-30 | New
35177 | NEXUS-MFD-3048-01 | VA | NVA | MFD | Merrifield | Metro Routers | POInt | Yes | Yes | MRTR VA NVA MFD Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 | 2020-04-20 | 2020-06-01
35177 | NEXUS-MFD-93180-01 | VA | NVA | MFD | Merrifield | Metro Routers | POInt | Yes | Yes | MRTR VA NVA MFD Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 4 | 2020-04-20 | 2020-06-01 | 2020-06-01 | SN-0239 | 2020-02-07 | Chg
54571 | CFS SE LFY STM SC-CFS Augment POR20 | SE | LFY | STM | St. Martinville | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE LFY STM SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-01 |  | SB-0023 | 2020-01-30 | New
34604 | PNS-NEW-P02-ROUTER | SE | GCT | PNS | Pensacola with (Insite tower) | CB - Metro Core | POInt | Yes | Yes | CBMC SE GCT PNS ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-06-01 |  | SN-0419 | 2020-04-02 | Chg
35177 | NEXUS-NRF-2248-01 | VA | HRD | NRF | Norfolk | Metro Routers | POInt | Yes | Yes | MRTR VA HRD NRF Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-04-20 | 2020-06-01 | 2020-06-01 | SN-0239 | 2020-02-07 | Chg
35177 | NEXUS-VBC-93180-01 | VA | HRD | VBC | Virginia Beach | Metro Routers | POInt | Yes | Yes | MRTR VA HRD VBC Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-04-20 | 2020-06-01
34608 | NWNWCRBSRA7750-1-ROUTER | VA | HRD | NWP | Newport News | CB - Metro Core | POInt | Yes | Yes | CBMC VA HRD NWP ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-03-15 | 2020-06-01 |  | SN-0144 | 2020-02-06 | Chg
34601 | Portsmouth-OCML-IXR | NE | RHD | PTH | Portsmouth (RI) | CB - Metro Core | POInt | Yes | Yes | CBMC NE RHD PTH OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | SN-0246 | 2020-02-24 | Chg
35010 | Metro OTN-DTN-Ciena 6500 S14 | CE | TUL | DTN | Downtown (TUL) | Metro Transport | POInt | Yes | Yes | MTRN CE TUL DTN OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-06-01 | 2020-08-01
35010 | Metro OTN-DTN-Ciena 6500 S2 | CE | TUL | DTN | Downtown (TUL) | Metro Transport | POInt | Yes | Yes | MTRN CE TUL DTN OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-04-15 | 2020-06-01 | 2020-08-01
54570 | CFS CE OMA BLV SC-CFS Augment POR20 | CE | OMA | BLV | Bellevue | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE OMA BLV SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-06-01 | 2020-06-01 |  | SB-0049 | 2020-02-28 | New
35010 | Metro OTN-WST-Ciena 6500 S14 | CE | TUL | WST | West (TUL) | Metro Transport | POInt | Yes | Yes | MTRN CE TUL WST OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-06-01 | 2020-08-01
35010 | Metro OTN-WST-Ciena 6500 S2 | CE | TUL | WST | West (TUL) | Metro Transport | POInt | Yes | Yes | MTRN CE TUL WST OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-06-01 | 2020-08-01
34604 | CB Transport - New Router Holt - HLT - Optics | SE | MGA | HLT | Holt | CB - Metro Core | POInt | Yes | Yes | CBMC SE MGA HLT Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-04-15 | 2020-06-01
54570 | CFS CE OMA CBL SC-CFS Augment POR20 | CE | OMA | CBL | Council Bluffs | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CE OMA CBL SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-06-01 | 2020-06-01 |  | SB-0049 | 2020-02-28 | New
34622 | Rancho Santa Margarita (RSM)-OCML-IXR | CA | ORG | RSM | Rancho Santa Margarita | CB - Metro Core | POInt | Yes | Yes | CBMC CA ORG RSM OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | SN-0246 | 2020-02-24 | Chg
34622 | Aliso Viejo (AV)-OCML-IXR | CA | ORG | AVJ | Aliso Viejo | CB - Metro Core | POInt | Yes | Yes | CBMC CA ORG AVJ OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | SN-0246 | 2020-02-24 | Chg
54571 | CFS SE BTR SPC SC-CFS Augment POR20 | SE | BTR | SPC | Pecue | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE BTR SPC SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-01 |  | SB-0023 | 2020-01-30 | New
34608 | Chesapeake-OCML-IXR | VA | HRD | CHS | Chesapeake | CB - Metro Core | POInt | Yes | Yes | CBMC VA HRD CHS OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | SN-0246 | 2020-02-24 | Chg
34608 | Newport-OCML-IXR | VA | HRD | NWP | Newport News | CB - Metro Core | POInt | Yes | Yes | CBMC VA HRD NWP OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | SN-0246 | 2020-02-24 | Chg
34604 | LFY-NEW-P02-ROUTER | SE | LFY | LFY | Lafayette | CB - Metro Core | POInt | Yes | Yes | CBMC SE LFY LFY ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-06-01 |  | SN-0419 | 2020-04-02 | Chg
34619 | County Line STC-OCML-IXR | CE | OKC | CLH | County Line | CB - Metro Core | POInt | Yes | Yes | CBMC CE OKC CLH OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | SN-0246 | 2020-02-24 | Chg
35175 | NEXUS-BUR-3048-01 | NE | RHD | BUR | Burrillville | Metro Routers | POInt | Yes | Yes | MRTR NE RHD BUR Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 | 2020-04-20 | 2020-06-01
35175 | NEXUS-BUR-93108-01 | NE | RHD | BUR | Burrillville | Metro Routers | POInt | Yes | Yes | MRTR NE RHD BUR Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 2 | 2020-04-20 | 2020-06-01
35175 | NEXUS-BUR-93180-01 | NE | RHD | BUR | Burrillville | Metro Routers | POInt | Yes | Yes | MRTR NE RHD BUR Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-04-20 | 2020-06-01
34604 | CB Transport - New Router Holt - HLT - Chassis Add | SE | MGA | HLT | Holt | CB - Metro Core | POInt | Yes | Yes | CBMC SE MGA HLT Cisco M6_M15 Chassis Augment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-04-15 | 2020-06-01
35175 | NEXUS-WWK-3048-01 | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | Metro Routers | POInt | Yes | Yes | MRTR NE RHD WWK Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 | 2020-04-20 | 2020-06-01
35175 | NEXUS-WWK-93108-01 | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | Metro Routers | POInt | Yes | Yes | MRTR NE RHD WWK Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 4 | 2020-04-20 | 2020-06-01
35175 | NEXUS-WWK-93180-01 | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | Metro Routers | POInt | Yes | Yes | MRTR NE RHD WWK Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 4 | 2020-04-20 | 2020-06-01
35010 | Metro OTN-SAP-Ciena 6500 S14 | CE | TUL | SAP | Sapulpa | Metro Transport | POInt | Yes | Yes | MTRN CE TUL SAP OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-06-01 | 2020-08-01
35010 | Metro OTN-SAP-Ciena 6500 S2 | CE | TUL | SAP | Sapulpa | Metro Transport | POInt | Yes | Yes | MTRN CE TUL SAP OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-06-01 | 2020-08-01
35177 | NEXUS-PRA-2248-01 | VA | HRD | PRA | Princess Anne | Metro Routers | POInt | Yes | Yes | MRTR VA HRD PRA Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-04-20 | 2020-06-01
39251 | BWM SAB DOCSIS Expansion 192 MHz | CA | SAB | SAB | Santa Barbara | Bandwidth Management | POInt | Yes | No | BWM CA SAB SAB DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-03 | 2023-10-05 | SN-0558 | 2020-05-12 | New
39251 | BWM SAB DOCSIS Expansion 96 MHz | CA | SAB | SAB | Santa Barbara | Bandwidth Management | POInt | Yes | No | BWM CA SAB SAB DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-03 | 2022-10-03 | SN-0558 | 2020-05-12 | New
34642 | BWM_IND_MSSA_Spectrum Phase II Start | CE | TUL | IND | Indianapolis | Bandwidth Management | POInt | Yes | No | BWM CE TUL IND MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-06-11 | SN-0703 | 2020-06-30 | Chg
34642 | BWM_SAP_MSSA_Spectrum Phase II Start | CE | TUL | SAP | Sapulpa | Bandwidth Management | POInt | Yes | No | BWM CE TUL SAP MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-06-11 | SN-0703 | 2020-06-30 | Chg
34642 | BWM_QNC_MSSA_Spectrum Phase II Start | CE | TUL | QNC | Quincy | Bandwidth Management | POInt | Yes | No | BWM CE TUL QNC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-06-11 | SN-0703 | 2020-06-30 | Chg
34642 | BWM_DTN_MSSA_Spectrum Phase II Start | CE | TUL | DTN | Downtown (TUL) | Bandwidth Management | POInt | Yes | No | BWM CE TUL DTN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-06-11 | SN-0703 | 2020-06-30 | Chg
34642 | BWM_OWA_MSSA_Spectrum Phase II Start | CE | TUL | OWA | Owasso | Bandwidth Management | POInt | Yes | No | BWM CE TUL OWA MSSA Augment POR20 v2 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-06-11 | SN-0703 | 2020-06-30 | Chg
34642 | BWM_GAR_MSSA_Spectrum Phase II Start | CE | TUL | GAR | Garnett | Bandwidth Management | POInt | Yes | No | BWM CE TUL GAR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-06-11 | SN-0703 | 2020-06-30 | Chg
34642 | BWM_TUL_MSSA_Spectrum Phase II Start | CE | TUL | TUL | Tulsa | Bandwidth Management | POInt | Yes | No | BWM CE TUL TUL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-06-11 | SN-0703 | 2020-06-30 | Chg
34642 | BWM_BRD_MSSA_Spectrum Phase II Start | CE | TUL | BRD | Braden | Bandwidth Management | POInt | Yes | No | BWM CE TUL BRD MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-06-11 | SN-0703 | 2020-06-30 | Chg
75655 | Arbor 17 | VA | NVA | MFD | Merrifield | Arbor DDoS | POInt | Yes | No | DDoS VA NVA MFD Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-03-10 | 2020-06-08 | 2020-06-22 | SN-0107 | 2020-02-06 | Chg
34642 | BWM_BAR_MSSA_Spectrum Phase II Start | CE | TUL | BAR | Broken Arrow | Bandwidth Management | POInt | Yes | No | BWM CE TUL BAR MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-06-11 | SN-0703 | 2020-06-30 | Chg
34642 | BWM_YAL_MSSA_Spectrum Phase II Start | CE | TUL | YAL | Yale | Bandwidth Management | POInt | Yes | No | BWM CE TUL YAL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-06-11 | SN-0703 | 2020-06-30 | Chg
34642 | BWM_CLA_MSSA_Spectrum Phase II Start | CE | TUL | CLA | Claremore | Bandwidth Management | POInt | Yes | No | BWM CE TUL CLA MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-06-11 | SN-0703 | 2020-06-30 | Chg
75645 | CGN Replacement 7 | VA | NVA | MFD | Merrifield | Data Center Capacity | POInt | Yes | No | DTC VA NVA MFD CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-01-11 | 2020-06-09 |  | SN-0554 | 2020-05-13 | Chg
39256 | BWM CLE DOCSIS Expansion 96 MHz | NE | CLE | CLV | Cleveland | Bandwidth Management | POInt | Yes | No | BWM NE CLE CLV DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-10 | 2022-10-03 | SN-0558 | 2020-05-12 | New
39256 | BWM CLE DOCSIS Expansion 192 MHz | NE | CLE | CLV | Cleveland | Bandwidth Management | POInt | Yes | No | BWM NE CLE CLV DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-10 | 2021-10-01 | SN-0558 | 2020-05-12 | New
75645 | CGN Replacement 4 | VA | HRD | NRF | Norfolk | Data Center Capacity | POInt | Yes | No | DTC VA HRD NRF CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2019-12-22 | 2020-06-10 |  | SN-0554 | 2020-05-13 | Chg
34642 | BWM BAR DOCSIS Expansion 96 MHz | CE | TUL | BAR | Broken Arrow | Bandwidth Management | POInt | Yes | No | BWM CE TUL BAR DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-11 | 2021-10-01 | SN-0558 | 2020-05-12 | New
34642 | BWM BRD DOCSIS Expansion 192 MHz | CE | TUL | BRD | Braden | Bandwidth Management | POInt | Yes | No | BWM CE TUL BRD DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-11 | 2020-10-15 | SN-0558 | 2020-05-12 | New
34644 | BWM_GDY_MSSA_Spectrum Phase II Start | CE | KAN | GDY | Garden City | Bandwidth Management | POInt | Yes | No | BWM CE KAN GDY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | SN-0703 | 2020-06-30 | Chg
75663 | V2B CA SAN ELC TVRO Maintenance Augment POR20 | CA | SAN | ELC | El Cajon | V2B | POInt | Yes | No | V2B CA SAN ELC TVRO Maintenance Augment POR20 | Labor | TVRO | 1 | 2020-04-06 | 2020-06-15 | 2020-10-15
34644 | BWM_PRT_MSSA_Spectrum Phase II Start | CE | KAN | PRT | Pratt | Bandwidth Management | POInt | Yes | No | BWM CE KAN PRT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-15 | 2020-06-25 | SN-0703 | 2020-06-30 | Chg
75663 | V2B COR COR DDR TVRO Maintenance Augment POR20 | COR | COR | DDR | Duke Drive | V2B | POInt | Yes | No | V2B COR COR DDR TVRO Maintenance Augment POR20 | Labor | TVRO | 1 | 2020-05-06 | 2020-06-15 | 2020-10-15
34644 | BWM_TOP_MSSA_Spectrum Phase II Start | CE | KAN | TOP | Topeka | Bandwidth Management | POInt | Yes | No | BWM CE KAN TOP MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | SN-0703 | 2020-06-30 | Chg
34619 | CB Transport - New Router Downtown (TUL) - DTN - Optics | CE | TUL | DTN | Downtown (TUL) | CB - Metro Core | POInt | Yes | No | CBMC CE OKC DTN Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-05-15 | 2020-06-15
34644 | BWM_BER_MSSA_Spectrum Phase II Start | CE | NWA | BER | Berryville | Bandwidth Management | POInt | Yes | No | BWM CE NWA BER MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-24 | SN-0703 | 2020-06-30 | Chg
34619 | CB Transport - New Router Fayetteville - NWA - Optics | CE | NWA | NWA | Johnson | CB - Metro Core | POInt | Yes | No | CBMC CE ARK NWA Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-05-15 | 2020-06-15
34619 | CB Transport - New Router Johnson - NWA - Optics | CE | NWA | NWA | Johnson | CB - Metro Core | POInt | Yes | No | CBMC CE ARK NWA Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-05-15 | 2020-06-15
75844 | NE RHD EXT VAM Splitter Augment POR20 | NE | RHD | EXT | Exeter | MTC Fiber and Rack Management | POInt | Yes | No | MVFM NE RHD EXT Fiber Bay Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-06-08 | 2020-06-15 | 2020-06-15
34644 | BWM_TOW_MSSA_Spectrum Phase II Start | CE | KAN | TOW | Towanda | Bandwidth Management | POInt | Yes | No | BWM CE KAN TOW MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | SN-0703 | 2020-06-30 | Chg
34644 | BWM_MNT_MSSA_Spectrum Phase II Start | CE | KAN | MNT | Manhattan | Bandwidth Management | POInt | Yes | No | BWM CE KAN MNT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | SN-0703 | 2020-06-30 | Chg
34644 | BWM_FAY_MSSA_Spectrum Phase II Start | CE | NWA | FAY | Fayetteville | Bandwidth Management | POInt | Yes | No | BWM CE NWA FAY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-24 | SN-0703 | 2020-06-30 | Chg
34644 | BWM_VBN_MSSA_Spectrum Phase II Start | CE | NWA | VBN | Van Buren | Bandwidth Management | POInt | Yes | No | BWM CE NWA VBN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-24 | SN-0703 | 2020-06-30 | Chg
34975 | CFD CHS BUP DMS/HDT PROJECT - LARGE | VA | HRD | CHS | Chesapeake | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA HRD CHS RC-CFG Deployment POR20 | Critical Facilities | DMS/HDT PROJECT - LARGE | 1 | 2020-04-06 | 2020-06-15
34644 | BWM_WIC_MSSA_Spectrum Phase II Start | CE | KAN | WIC | Wichita | Bandwidth Management | POInt | Yes | No | BWM CE KAN WIC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | SN-0703 | 2020-06-30 | Chg
34644 | BWM_PSN_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | KAN | PSN | Parsons | Bandwidth Management | POInt | Yes | No | BWM CE KAN PSN VIDEO SG Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-15 | 2020-06-15
34644 | BWM_STR_MSSA_Spectrum Phase II Start | CE | KAN | STR | Strotherfield | Bandwidth Management | POInt | Yes | No | BWM CE KAN STR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | SN-0703 | 2020-06-30 | Chg
75842 | CA SAN PWY Backbone Growth Edge Augment POR20 | CA | SAN | PWY | Poway | MTC Fiber and Rack Management | POInt | Yes | No | MVFM CA SAN PWY Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-05-06 | 2020-06-15 | 2020-07-15 | SN-0388 | 2020-03-30 | Chg
34644 | BWM_PIT_MSSA_Spectrum Phase II Start | CE | KAN | PIT | Pittsburg | Bandwidth Management | POInt | Yes | No | BWM CE KAN PIT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | SN-0703 | 2020-06-30 | Chg
34644 | BWM_WIC_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | KAN | WIC | Wichita | Bandwidth Management | POInt | Yes | No | BWM CE KAN WIC VIDEO SG Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-15 | 2020-06-15
34642 | BWM_ONA_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | OKC | NOR | Norman | Bandwidth Management | POInt | Yes | No | BWM CE OKC NOR VIDEO SG Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-15 | 2020-06-15
34644 | BWM_JCY_MSSA_Spectrum Phase II Start | CE | KAN | JCY | Junction City | Bandwidth Management | POInt | Yes | No | BWM CE KAN JCY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | SN-0703 | 2020-06-30 | Chg
34623 | CB Transport - New Router South Scottsdale - MCD - Card Add | SW | ARZ | MCD | McDowell | CB - Metro Core | POInt | Yes | No | CBMC SW ARZ MCD Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-04-17 | 2020-06-15 |  | SN-0419 | 2020-04-02 | Chg
34644 | BWM_SAL_MSSA_Spectrum Phase II Start | CE | KAN | SAL | Salina | Bandwidth Management | POInt | Yes | No | BWM CE KAN SAL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-15 | 2020-06-25 | SN-0703 | 2020-06-30 | Chg
34644 | BWM_OLA_MSSA_Spectrum Phase II Start | CE | KAN | OLA | Iola | Bandwidth Management | POInt | Yes | No | BWM CE KAN OLA MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | SN-0703 | 2020-06-30 | Chg
44923 | MTCH CA SAN FED Vecima Replacement Deployment POR20 | CA | SAN | FED | Federal | MTC HE - Hub Signaling | POInt | Yes | No | MTCH CA SAN FED Vecima Replacement Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-04-06 | 2020-06-15
34635 | BWM_ROA_ MSSA_Spectrum Phase II Start | VA | ROA | RON | Roanoke | Bandwidth Management | POInt | Yes | No | BWM VA ROA RON MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-15 | 2020-06-18 | SN-0703 | 2020-06-30 | Chg
34644 | BWM_DCY_MSSA_Spectrum Phase II Start | CE | KAN | DCY | Dodge City | Bandwidth Management | POInt | Yes | No | BWM CE KAN DCY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | SN-0703 | 2020-06-30 | Chg
34644 | BWM_NWA_VIDEO SG_2020 DOCSIS node split-based Video SG I | CE | NWA | NWA | Johnson | Bandwidth Management | POInt | Yes | No | BWM CE NWA NWA MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-24 | SN-0703 | 2020-06-30 | Chg
34644 | BWM_NWA_MSSA_Spectrum Phase II Start | CE | NWA | NWA | Johnson | Bandwidth Management | POInt | Yes | No | BWM CE NWA NWA MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-24 | SN-0703 | 2020-06-30 | Chg
75844 | NE CON STN VAM Splitter Augment POR20 | NE | CON | STN | Southington | MTC Fiber and Rack Management | POInt | Yes | No | MVFM NE CON STN Fiber Bay Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-06-08 | 2020-06-15 | 2020-06-15
34644 | BWM_MPN_MSSA_Spectrum Phase II Start | CE | KAN | MPN | McPherson | Bandwidth Management | POInt | Yes | No | BWM CE KAN MPN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | SN-0703 | 2020-06-30 | Chg
34636 | BWM_GNS_VIDEO SG_2020 DOCSIS node split-based Video SG | SE | GAN | GNS | Gainesville | Bandwidth Management | POInt | Yes | No | BWM SE GAN GNS Video SG Augment POR20 v4 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-15 | 2020-06-15
34619 | CB Transport - New Router Downtown (TUL) - TUL - Optics | CE | TUL | TUL | Tulsa | CB - Metro Core | POInt | Yes | No | CBMC CE TUL TUL Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-05-15 | 2020-06-15
34644 | BWM_SSP_MSSA_Spectrum Phase II Start | CE | NWA | SSP | Siloam Springs | Bandwidth Management | POInt | Yes | No | BWM CE NWA SSP MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-24 | SN-0703 | 2020-06-30 | Chg
75844 | NE CON GLB VAM Splitter Augment POR20 | NE | CON | GLB | Glastonbury | MTC Fiber and Rack Management | POInt | Yes | No | MVFM NE CON GLB Fiber Bay Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-06-08 | 2020-06-15 | 2020-06-15
75838 | SW ARZ PEO Cabling Refortification Augment POR20 | SW | ARZ | PEO | Peoria | MTC Fiber and Rack Management | POInt | Yes | No | MVFM SW ARZ PEO Cabling Refortification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-05-06 | 2020-06-15 | 2020-06-15 | SN-0388 | 2020-03-30 | Chg
34644 | BWM_GBD_MSSA_Spectrum Phase II Start | CE | KAN | GBD | Great Bend | Bandwidth Management | POInt | Yes | No | BWM CE KAN GBD MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | SN-0703 | 2020-06-30 | Chg
34644 | BWM_DBY_MSSA_Spectrum Phase II Start | CE | KAN | DBY | Derby | Bandwidth Management | POInt | Yes | No | BWM CE KAN DBY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | SN-0703 | 2020-06-30 | Chg
34644 | BWM_FTS_MSSA_Spectrum Phase II Start | CE | NWA | FTS | Fort Smith | Bandwidth Management | POInt | Yes | No | BWM CE NWA FTS MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-24 | SN-0703 | 2020-06-30 | Chg
34644 | BWM_CFV_MSSA_Spectrum Phase II Start | CE | KAN | CFV | Coffeyville | Bandwidth Management | POInt | Yes | No | BWM CE KAN CFV MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | SN-0703 | 2020-06-30 | Chg
34619 | CB Transport - New Router Fayetteville - FAY - Optics | CE | NWA | FAY | Fayetteville | CB - Metro Core | POInt | Yes | No | CBMC CE ARK FAY Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-05-15 | 2020-06-15
34644 | BWM_BVL_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | NWA | BVL | Bentonville | Bandwidth Management | POInt | Yes | No | BWM CE NWA BVL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-06-15 | 2020-06-24 | SN-0703 | 2020-06-30 | Chg
34644 | BWM_HRN_MSSA_Spectrum Phase II Start | CE | NWA | HRN | Harrison | Bandwidth Management | POInt | Yes | No | BWM CE NWA HRN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-24 | SN-0703 | 2020-06-30 | Chg
34644 | BWM_BVL_MSSA_Spectrum Phase II Start | CE | NWA | BVL | Bentonville | Bandwidth Management | POInt | Yes | No | BWM CE NWA BVL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-06 | 2020-06-15 | 2020-06-24 | SN-0703 | 2020-06-30 | Chg
34644 | BWM_HUT_MSSA_Spectrum Phase II Start | CE | KAN | HUT | Hutchinson | Bandwidth Management | POInt | Yes | No | BWM CE KAN HUT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | SN-0703 | 2020-06-30 | Chg
34644 | BWM_NWT_MSSA_Spectrum Phase II Start | CE | KAN | NWT | Newton | Bandwidth Management | POInt | Yes | No | BWM CE KAN NWT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | SN-0703 | 2020-06-30 | Chg
39256 | BWM_MER_VIDEO SG_2020 DOCSIS node split-based Video SG I | NE | CON | MER | Meriden | Bandwidth Management | POInt | Yes | No | BWM NE CON MER VIDEO SG Augment POR20 v2 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-15 | 2020-06-15
75842 | CA ORG DNP Backbone Growth Edge Augment POR20 | CA | ORG | DNP | Dana Point | MTC Fiber and Rack Management | POInt | Yes | Yes | MVFM CA ORG DNP Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-05-06 | 2020-06-15 | 2020-07-15 | SN-0388 | 2020-03-30 | Chg
75842 | CA ORG IRV Backbone Growth Edge Augment POR20 | CA | ORG | IRV | Irvine | MTC Fiber and Rack Management | POInt | Yes | Yes | MVFM CA ORG IRV Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-05-06 | 2020-06-15 | 2020-07-15 | SN-0388 | 2020-03-30 | Chg
34975 | CFG MFD BS-CFG LARGE_2V_BATTSTRING | VA | NVA | MFD | Merrifield | Critical Facilities (Grow) | POInt | Yes | Yes | CFG VA NVA MFD BS-CFG Deployment POR20 | Critical Facilities | LARGE_2V_BATTSTRING | 1 | 2020-01-01 | 2020-06-15
75842 | CA ORG PAV Backbone Growth Edge Augment POR20 | CA | ORG | PAV | Palos Verdes | MTC Fiber and Rack Management | POInt | Yes | Yes | MVFM CA ORG PAV Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-05-06 | 2020-06-15 | 2020-07-15 | SN-0388 | 2020-03-30 | Chg
34970 | CFG SSC BD-CFG GEN GROW PROJECT - LARGE | SW | ARZ | SSC | South Scottsdale | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ SSC GN-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-04-01 | 2020-06-15
75842 | CA SAN DWN Backbone Growth Edge Augment POR20 | CA | SAN | DWN | Downtown | MTC Fiber and Rack Management | POInt | Yes | Yes | MVFM CA SAN DWN Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-05-06 | 2020-06-15 | 2020-07-15 | SN-0388 | 2020-03-30 | Chg
34604 | CB Transport - New Router Donaldsonville - DVL - Optics | SE | BTR | DVL | Donaldsonville | CB - Metro Core | POInt | Yes | Yes | CBMC SE BTR DVL Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-05-15 | 2020-06-15
34623 | CB Transport - New Router South Scottsdale - SSC - Card Add | SW | ARZ | SSC | South Scottsdale | CB - Metro Core | POInt | Yes | Yes | CBMC SW ARZ SSC Optics Only for Cisco T5 Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-17 | 2020-06-15
34623 | CB Transport - New Router South Scottsdale - CHD - Card Add | SW | ARZ | CHD | Chandler | CB - Metro Core | POInt | Yes | Yes | CBMC SW ARZ CHD Cisco T5 card and optics Augment POR20_V2 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-04-17 | 2020-06-15 |  | SN-0419 | 2020-04-02 | Chg
59850 | RPHY MRTR-New-RSM-CIN-ATX-OCML | CA | ORG | RSM | Rancho Santa Margarita | R PHY | POInt | Yes | Yes | R PHY CA ORG RSM RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-06-15 | 2020-06-15 | SN-0487 | 2020-05-12 | New
34971 | CFD ELC BUP DMS/HDT PROJECT - LARGE | CA | SAN | ELC | El Cajon | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA SAN ELC BS-CFG Augment POR20 | Critical Facilities | DMS/HDT PROJECT - LARGE | 1 | 2020-04-06 | 2020-06-15
59850 | RPHY MRTR-New-CHU-CIN-ATX-OCML | CA | SAN | CHU | Chula Vista | R PHY | POInt | Yes | Yes | R PHY CA SAN CHU RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-01-01 | 2020-06-15 | 2020-06-30 | SN-0487 | 2020-05-12 | New
34970 | CFG TEN BD-CFG GEN GROW PROJECT - LARGE | SW | LAS | TEN | Tenaya | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW LAS TEN HV-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-07-01 | 2020-06-15
34619 | CB Transport - New Router Downtown (TUL) - BAR - Optics | CE | TUL | BAR | Broken Arrow | CB - Metro Core | POInt | Yes | Yes | CBMC CE TUL BAR Optics Only for Cisco T5 Augment POR20 v1 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-05-15 | 2020-06-15
34619 | CB Transport - New Router Garnett - GAR - Optics | CE | TUL | GAR | Garnett | CB - Metro Core | POInt | Yes | Yes | CBMC CE TUL GAR Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-03-15 | 2020-06-20 |  | SN-0586 | 2020-05-14 | Chg
34971 | CFG CA ORG RSM BD-CFG Deployment POR20 | CA | ORG | RSM | Rancho Santa Margarita | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CA ORG RSM BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-06-01 | 2020-06-20 |  | SN-0262 | 2020-02-28 | New
34976 | CFG NE CON SFD GN-CFG Deployment POR20 | NE | CON | SFD | Stafford | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE CON SFD GN-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-06-01 | 2020-06-20 |  | SN-0411 | 2020-03-27
34976 | CFG NE RHD EXT RK-CFG Deployment POR20 | NE | RHD | EXT | Exeter | Critical Facilities (Grow) | POInt | Yes | No | CFG NE RHD EXT RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-06-01 | 2020-06-20 |  | SN-0411 | 2020-03-27
34642 | BWM_BRD_VIDEO SG_2020 DOCSIS node split-based Video SG Calculations per facility Dup | CE | TUL | BRD | Braden | Bandwidth Management | POInt | Yes | No | BWM CE TUL BRD VIDEO SG Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-20 | 2020-06-20 | SN-0245 | 2020-02-24 | Chg
75651 | PTX Add FOA | SE | GAN | GNS | Gainesville | Backbone | POInt | Yes | No | BBCAP SE GAN GNS PTX10 Deployment POR20 | Chassis | 1x Juniper PTX10K Chassis | 2 | 2020-03-14 | 2020-06-22 |  | SN-0549 | 2020-05-13 | Chg
39256 | BWM_CLV_MSSA_Spectrum Phase II Start | NE | CLE | CLV | Cleveland | Bandwidth Management | POInt | Yes | No | BWM NE CLE CLV MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-24 | 2020-06-10 | SN-0703 | 2020-06-30 | Chg
39256 | BWM_PAW_MSSA_Spectrum Phase II Start | NE | RHD | PAW | Pawtucket | Bandwidth Management | POInt | Yes | No | BWM NE RHD PAW MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-07-08 | SN-0703 | 2020-06-30 | Chg
39256 | BWM_LNC_MSSA_Spectrum Phase II Start | NE | RHD | LNC | Lincoln | Bandwidth Management | POInt | Yes | No | BWM NE RHD LNC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-07-08 | SN-0703 | 2020-06-30 | Chg
75655 | Arbor 14 | SE | GCT | PNS | Pensacola with (Insite tower) | Arbor DDoS | POInt | Yes | No | DDoS SE GCT PNS Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-05-15 | 2020-06-29 | 2020-07-13 | SN-0107 | 2020-02-06 | Chg
39256 | BWM_CRN_MSSA_Spectrum Phase II Start | NE | RHD | CRN | Cranston | Bandwidth Management | POInt | Yes | No | BWM NE RHD CRN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-07-08 | SN-0703 | 2020-06-30 | Chg
39256 | BWM_WWK_MSSA_Spectrum Phase II Start | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | Bandwidth Management | POInt | Yes | No | BWM NE RHD WWK MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-07-08 | SN-0703 | 2020-06-30 | Chg
39256 | BWM_SCT_MSSA_Spectrum Phase II Start | NE | RHD | SCT | Scituate | Bandwidth Management | POInt | Yes | No | BWM NE RHD SCT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-07-08 | SN-0703 | 2020-06-30 | Chg
39256 | BWM_PTH_MSSA_Spectrum Phase II Start | NE | RHD | PTH | Portsmouth (RI) | Bandwidth Management | POInt | Yes | No | BWM NE RHD PTH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-07-08 | SN-0703 | 2020-06-30 | Chg
39256 | BWM_PRV_MSSA_Spectrum Phase II Start | NE | RHD | PRV | Providence | Bandwidth Management | POInt | Yes | No | BWM NE RHD PRV MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-07-08 | SN-0703 | 2020-06-30 | Chg
39256 | BWM_EXT_MSSA_Spectrum Phase II Start | NE | RHD | EXT | Exeter | Bandwidth Management | POInt | Yes | No | BWM NE RHD EXT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-07-08 | SN-0703 | 2020-06-30 | Chg
39256 | BWM_BUR_MSSA_Spectrum Phase II Start | NE | RHD | BUR | Burrillville | Bandwidth Management | POInt | Yes | No | BWM NE RHD BUR MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-07-08 | SN-0703 | 2020-06-30 | Chg
39256 | BWM SA RHD COVID-19_ LABOR ONLY | NE | RHD | BUR | Burrillville | Bandwidth Management | POInt | Yes | No | BWM NE RHD BUR MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-29 | 2020-07-08 | SN-0703 | 2020-06-30 | Chg
75658 | VA-PNS-1x Juniper EX4600 | SE | GCT | PNS | Pensacola with (Insite tower) | Visibility Architecture | POInt | Yes | No | VIA SE GCT PNS Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-05-01 | 2020-06-30 | 2020-07-13 | SN-0094 | 2020-02-06 | Chg
75788 | CDN Deploy 17 | NE | RHD | PRV | Providence | CDN | POInt | Yes | No | CDN NE RHD PRV Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-05-01 | 2020-06-30 | 2020-07-14 | SN-0285 | 2020-02-24 | Chg
59745 | R PHY_CCAP_VST_RPHY CCAP Licenses_Q2 NC Video | CA | SAN | VST | Vista | R PHY | POInt | Yes | No | R PHY CA SAN VST R PHY CCAP Deployment POR20 | License | CCAP license | 476 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
75658 | VA-PNS-1x Dell R640 | SE | GCT | PNS | Pensacola with (Insite tower) | Visibility Architecture | POInt | Yes | No | VIA SE GCT PNS Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 3 | 2020-05-01 | 2020-06-30 | 2020-07-13 | SN-0094 | 2020-02-06 | New
35715 | MRTR AAR-New-ENF-NEW-AAR | NE | CON | ENF | Enfield | Metro Routers | POInt | Yes | Yes | MRTR NE CON ENF AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | SN-0158 | 2020-02-06 | Chg
35010 | Metro OTN-BRD-Ciena 6500 S14 | CE | TUL | BRD | Braden | Metro Transport | POInt | Yes | Yes | MTRN CE TUL BRD OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-06-30 | 2020-08-30 | SN-0161 | 2020-02-18 | Chg
35010 | Metro OTN-BRD-Ciena 6500 S2 | CE | TUL | BRD | Braden | Metro Transport | POInt | Yes | Yes | MTRN CE TUL BRD OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-06-30 | 2020-08-30 | SN-0161 | 2020-02-18 | Chg
59745 | R PHY_CCAP_PAV_RPHY CCAP Licenses_Q2 NC Video | CA | ORG | PAV | Palos Verdes | RSPD - CCAP | POInt | Yes | No | R PHY CA ORG PAV RPHY CCAP Augment POR20 | License | CCAP license | 136 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
34642 | BWM SA OKC COVID-19_ LABOR ONLY | CE | OKC | CHO | Choctaw | Bandwidth Management | POInt | Yes | No | BWM CE OKC CHO SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | SN-0479 | 2020-04-24 | New
75647 | Nokia 1830 Add 11 | CE | OKC | OKC | OKC MTC | C4 & C4B Transport Network | POInt | Yes | No | C4B CE OKC OKC Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis | 5 |  | 2020-06-30 |  | SN-0229 | 2020-02-03 | New
34635 | BWM SA HRD COVID-19_ LABOR ONLY | VA | HRD | ALX | Alexandria CEC | Bandwidth Management | POInt | Yes | No | BWM VA NVA DRA SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | SN-0587 | 2020-05-14 | Chg
34635 | BWM SA NVA COVID-19_ LABOR ONLY | VA | NVA | DRA | Dranesville | Bandwidth Management | POInt | Yes | No | BWM VA NVA DRA SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | SN-0479 | 2020-04-24 | New
34635 | BWM_GLO_VIDEO SG_2020 DOCSIS node split-based Video SG | VA | HRD | GLO | Gloucester | Bandwidth Management | POInt | Yes | No | BWM VA HRD GLO Video SG Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 | 2020-06-30 | SN-0245 | 2020-02-24 | Chg
75187 | R PHY_CCAP_SOU_RPHY CCAP Licenses_Q2 NC Video | CE | OMA | SOU | South (OM) | R PHY | POInt | Yes | No | R PHY CE OMA SOU RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
34644 | BWM SA KAN COVID-19_ LABOR ONLY | CE | KAN | CFV | Coffeyville | Bandwidth Management | POInt | Yes | No | BWM CE KAN CFV SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | SN-0479 | 2020-04-24 | New
75658 | VA-MFD-1x Juniper EX4600 | VA | NVA | MFD | Merrifield | Visibility Architecture | POInt | Yes | No | VIA VA NVA MFD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-03-01 | 2020-06-30 | 2020-06-22 | SN-0094 | 2020-02-06 | Chg
75658 | VA-MFD-1x Dell R640 | VA | NVA | MFD | Merrifield | Visibility Architecture | POInt | Yes | No | VIA VA NVA MFD Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 3 | 2020-03-01 | 2020-06-30 | 2020-06-22 | SN-0094 | 2020-02-06 | New
34635 | BWM_FBG_VIDEO SG_2020 DOCSIS node split-based Video SG | VA | NVA | FBG | Fredericksburg | Bandwidth Management | POInt | Yes | No | BWM VA NVA FBG Video SG Augment POR20 v2 | Labor | No Equipment | 1 |  | 2020-06-30 | 2020-06-30 | SN-0245 | 2020-02-24 | Chg
75187 | R PHY_CCAP_WLK_RPHY CCAP Licenses_Q2 NC Video | CE | OKC | WLK | Walker Hub | R PHY | POInt | Yes | Yes | R PHY CE OKC WLK RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
34604 | NWORLAUI1AW-ROUTER | SE | NOR | NOE | New Orleans East | CB - Metro Core | POInt | Yes | Yes | CBMC SE NOR NOE ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-06-30 |  | SN-0654 | 2020-06-14 | Chg
34601 | CB Transport - New Router Enfield P - ENF - Card Add | NE | CON | ENF | Enfield | CB - Metro Core | POInt | Yes | Yes | CBMC NE CON ENF Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-01 | 2020-06-30 |  | SN-0618 | 2020-06-05 | Chg
59522 | R PHY_CCAP_MCD_RPHY CCAP Licenses_Q2 NC Video | SW | ARZ | MCD | McDowell | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ MCD RPHY CCAP Deployment POR20 | License | CCAP license | 272 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
35715 | MRTR AAR-New-PTH-NEW-AAR | NE | RHD | PTH | Portsmouth (RI) | Metro Routers | POInt | Yes | Yes | MRTR NE RHD PTH AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | SN-0158 | 2020-02-06 | Chg
35172 | MRTR NCS-Growth-GNS-100G Grow | SE | GAN | GNS | Gainesville | Metro Routers | POInt | Yes | Yes | MRTR SE GAN GNS 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-06-30 | 2020-06-30 | SN-0555 | 2020-05-12 | Chg
35172 | MRTR NCS-Growth-OCL-100G Grow | SE | GAN | OCL | Ocala | Metro Routers | POInt | Yes | Yes | MRTR SE GAN OCL 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-06-30 | 2020-06-30 | SN-0555 | 2020-05-12 | Chg
54573 | CFS SW ARZ TUC BS-CFS Augment POR20 | SW | ARZ | TUC | Tucson | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ TUC BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 |  | SB-0023 | 2020-01-30 | New
35179 | MRTR OOB-New-ELC-OOB Server | CA | SAN | ELC | El Cajon | Metro Routers | POInt | Yes | Yes | MRTR CA SAN ELC OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-04-05 | 2020-06-30 | 2020-09-30 | SN-0158 | 2020-02-06 | New
75187 | R PHY_CCAP_CLH_RPHY CCAP Licenses_Q2 NC Video | CE | OKC | CLH | County Line | R PHY | POInt | Yes | Yes | R PHY CE OKC CLH RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
75246 | R PHY_CCAP_MCY_RPHY CCAP Licenses_Q2 NC Video | SE | NOR | MCY | Mid-City | R PHY | POInt | Yes | Yes | R PHY SE NOR MCY RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
74548 | R PHY_CCAP_PTM_RPHY CCAP Licenses_Q2 NC Video | VA | HRD | PTM | Portsmouth (VA) | R PHY | POInt | Yes | Yes | R PHY VA HRD PTM RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
54573 | CFS SW LAS VLY BS-CFS Augment POR20 | SW | LAS | VLY | Valley | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW LAS VLY BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 |  | SB-0023 | 2020-01-30 | New
35171 | MRTR OOB-New-SVI-OOB Server | CE | SUN | SVI | Sun Valley | Metro Routers | POInt | Yes | Yes | MRTR CE SUN SVI OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-01 | 2020-06-30 | 2020-09-30 | SN-0158 | 2020-02-06 | Chg
75788 | CDN Deploy 11 | CA | SAN | ELC | El Cajon | CDN | POInt | Yes | No | CDN CA SAN ELC Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 1 | 2020-04-01 | 2020-06-30 | 2020-07-14 | SN-0285 | 2020-02-24 | Chg
39251 | BWM SA SAB COVID-19_ LABOR ONLY | CA | SAB | SAB | Santa Barbara | Bandwidth Management | POInt | Yes | No | BWM CA SAB SAB SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | SN-0479 | 2020-04-24 | New
39251 | BWM SA SAN COVID-19_ LABOR ONLY | CA | SAN | ALP | Alpine | Bandwidth Management | POInt | Yes | No | BWM CA SAN ALP SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | SN-0479 | 2020-04-24 | New
75187 | R PHY_CCAP_YAL_RPHY CCAP Licenses_Q2 NC Video | CE | TUL | YAL | Yale | R PHY | POInt | Yes | No | R PHY CE TUL YAL RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
34642 | BWM SA TUL COVID-19_ LABOR ONLY | CE | TUL | BAR | Broken Arrow | Bandwidth Management | POInt | Yes | No | BWM CE TUL BAR SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | SN-0479 | 2020-04-24 | New
35169 | MRTR NCS-New-JMX-NCS-5504-250 Sup Card | SW | ARZ | JMX | Jomax | Metro Routers | POInt | Yes | No | MRTR SW ARZ JMX NCS Deployment POR20 | Card & Optics | NCS-5504-250 Sup Card | 2 | 2020-04-01 03:01 | 2020-06-30 | 2020-09-30 | SN-0158 | 2020-02-06 | Chg
39256 | BWM SA CON COVID-19_ LABOR ONLY | NE | CON | ENF | Enfield | Bandwidth Management | POInt | Yes | No | BWM NE CON ENF SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | SN-0479 | 2020-04-24 | New
75187 | R PHY_CCAP_OWA_RPHY CCAP Licenses_Q2 NC Video | CE | TUL | OWA | Owasso | R PHY | POInt | Yes | No | R PHY CE TUL OWA RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
75187 | R PHY_CCAP_TUL_RPHY CCAP Licenses_Q2 NC Video | CE | TUL | TUL | Tulsa | R PHY | POInt | Yes | No | R PHY CE TUL TUL R PHY CCAP Deployment POR20 | License | CCAP license | 1496 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
75844 | NE CON SFD ALU Nokia Fiber Augment POR20 | NE | CON | SFD | Stafford | MTC Fiber and Rack Management | POInt | Yes | No | MVFM NE CON SFD ALU Nokia Fiber Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-06-30 | 2020-06-30 | SN-0308 | 2020-02-28 | Chg
34645 | BWM SA ARZ COVID-19_ LABOR ONLY | SW | ARZ | PNL | Pinal County | Bandwidth Management | POInt | Yes | No | BWM SW ARZ PNL SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | SN-0479 | 2020-04-24 | New
75788 | CDN Deploy 10 | CA | SAN | FED | Federal | CDN | POInt | Yes | No | CDN CA SAN FED Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 1 | 2020-04-01 | 2020-06-30 | 2020-07-14 | SN-0285 | 2020-02-24 | Chg
34638 | BWM SA NOR COVID-19_ LABOR ONLY | SE | NOR | ALG | Algiers | Bandwidth Management | POInt | Yes | No | BWM SE NOR ALN SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | SN-0479 | 2020-04-24 | New
34635 | BWM SA ROA COVID-19_ LABOR ONLY | VA | ROA | RON | Roanoke | Bandwidth Management | POInt | Yes | No | BWM VA ROA RON SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | SN-0479 | 2020-04-24 | New
34636 | BWM SA MGA COVID-19_ LABOR ONLY | SE | MGA | GRY | Gray | Bandwidth Management | POInt | Yes | No | BWM SE MGA GRY SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | SN-0479 | 2020-04-24 | New
75848 | MVFM VA HRD VBC Meet Me Rack Augment POR20 | VA | HRD | VBC | Virginia Beach | MTC Fiber and Rack Management | POInt | Yes | No | MVFM VA HRD VBC Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-05-06 | 2020-06-30 | 2020-07-31 | SN-0793 | 2020-08-20 | Chg
34638 | BWM SA LFY COVID-19_ LABOR ONLY | SE | LFY | ABV | Abbeville | Bandwidth Management | POInt | Yes | No | BWM SE LFY ABV SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | SN-0479 | 2020-04-24 | New
34642 | BWM SA OMA COVID-19_ LABOR ONLY | CE | OMA | BLV | Bellevue | Bandwidth Management | POInt | Yes | No | BWM CE OMA BLV SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | SN-0479 | 2020-04-24 | New
34636 | BWM SA GCT COVID-19_ LABOR ONLY | SE | GCT | CRV | Crestview | Bandwidth Management | POInt | Yes | No | BWM SE GCT CRV SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | SN-0479 | 2020-04-24 | New
39251 | BWM SA ORG COVID-19_ LABOR ONLY | CA | ORG | AVJ | Aliso Viejo | Bandwidth Management | POInt | Yes | No | BWM CA ORG AVJ SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | SN-0479 | 2020-04-24 | New
75848 | MVFM VA HRD NWP Meet Me Rack Augment POR20 | VA | HRD | NWP | Newport News | MTC Fiber and Rack Management | POInt | Yes | No | MVFM VA HRD NWP Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-05-06 | 2020-06-30 | 2020-07-31 | SN-0793 | 2020-08-20 | Chg
75758 | Add HDFS system to Lab Env | COR | COR | ATL | Atlanta | Voice Monitoring and Analytics | POInt | Yes | No | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other | 1 | 2020-06-10 | 2020-06-30 |  | SB-0140 | 2020-05-28 | Chg
44926 | MTCH NE CON SFD RF Passive Splitter Deployment POR20 | NE | CON | SFD | Stafford | MTC HE - Hub Signaling | POInt | Yes | No | MTCH NE CON SFD RF Passive Splitter Deployment POR20 | Chassis | 8-way splitter | 1 | 2020-05-06 | 2020-06-30 |  | SN-0021 | 2020-02-06 | Chg
39256 | BWM SA CLE COVID-19_ LABOR ONLY | NE | CLE | CLV | Cleveland | Bandwidth Management | POInt | Yes | No | BWM NE CLE CLV SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | SN-0479 | 2020-04-24 | New
75844 | NE CON GRB ALU Nokia Fiber Augment POR20 | NE | CON | GRB | Granby | MTC Fiber and Rack Management | POInt | Yes | No | MVFM NE CON GRB ALU Nokia Fiber Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-06-30 | 2020-06-30 | SN-0308 | 2020-02-28 | Chg
34644 | BWM_NWA_VIDEO SG_2020 DOCSIS node split-based Video SG 2 | CE | NWA | NWA | Johnson | Bandwidth Management | POInt | Yes | No | BWM CE NWA NWA Video SG Augment POR20 v3 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | SN-0195 | 2020-01-24 | Chg
75758 | Functional testing, Upgrade lab to D-Cloud in Lab | COR | COR | ATL | Atlanta | Voice Monitoring and Analytics | POInt | Yes | No | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other | 1 | 2020-06-01 | 2020-06-30 |  | SB-0045 | 2020-01-31
34638 | BWM SA BTR COVID-19_ LABOR ONLY | SE | BTR | BTR | Baton Rouge | Bandwidth Management | POInt | Yes | No | BWM SE BTR BTR SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | SN-0479 | 2020-04-24 | New
34642 | BWM SA SUN COVID-19_ LABOR ONLY | CE | SUN | SVI | Sun Valley | Bandwidth Management | POInt | Yes | No | BWM CE SUN SVI SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | SN-0479 | 2020-04-24 | New
34644 | BWM_BLV_VIDEO SG_2020 DOCSIS node split-based Video SG I | CE | OMA | BLV | Bellevue | Bandwidth Management | POInt | Yes | No | BWM CE OMA BLV Video SG Augment POR20 1 | Labor | No Equipment | 1 |  | 2020-06-30 | 2020-06-30 | SN-0245 | 2020-02-24 | Chg
34636 | BWM_WRB_VIDEO SG_2020 DOCSIS node split-based Video SG I | SE | MGA | WRB | Warner Robins | Bandwidth Management | POInt | Yes | No | BWM SE MGA WRB Video SG Augment POR20 v2 | Labor | No Equipment | 1 | 2020-01-16 | 2020-06-30 | 2020-06-30 | SN-0195 | 2020-01-24 | Chg
34761 | BWM SA LAS COVID-19_ LABOR ONLY | SW | LAS | ALI | Aliante | Bandwidth Management | POInt | Yes | No | BWM SW LAS ALI SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | SN-0479 | 2020-04-24 | New
75788 | CDN Deploy 7 | SE | BTR | BTR | Baton Rouge | CDN | POInt | Yes | No | CDN SE BTR BTR Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-05-01 | 2020-06-30 | 2020-07-14 | SN-0285 | 2020-02-24 | Chg
34636 | BWM SA GAN COVID-19_ LABOR ONLY | SE | GAN | GNS | Gainesville | Bandwidth Management | POInt | Yes | No | BWM SE GAN GNS SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | SN-0479 | 2020-04-24 | New
34636 | BWM_OCL_VIDEO SG_2020 DOCSIS node split-based Video SG | SE | GAN | OCL | Ocala | Bandwidth Management | POInt | Yes | No | BWM SE GAN OCL Video SG Augment POR20 v3 | Labor | No Equipment | 1 |  | 2020-06-30 | 2020-06-30 | SN-0245 | 2020-02-24 | Chg
59745 | R PHY_CCAP_AVJ_RPHY CCAP Licenses_Q2 NC Video | CA | ORG | AVJ | Aliso Viejo | RSPD - CCAP | POInt | Yes | No | R PHY CA ORG AVJ RPHY CCAP Augment POR20 | License | CCAP license | 6936 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
34644 | BWM SA NWA COVID-19_ LABOR ONLY | CE | OMA | BLV | Bellevue | Bandwidth Management | POInt | Yes | No | BWM CE NWA BVL SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | SN-0479 | 2020-04-24 | New
35010 | Metro OTN-CLA-Ciena 6500 S14 | CE | TUL | CLA | Claremore | Metro Transport | POInt | Yes | Yes | MTRN CE TUL CLA OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-06-30 | 2020-08-30 | SN-0161 | 2020-02-18 | Chg
35010 | Metro OTN-CLA-Ciena 6500 S2 | CE | TUL | CLA | Claremore | Metro Transport | POInt | Yes | Yes | MTRN CE TUL CLA OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-06-30 | 2020-08-30 | SN-0161 | 2020-02-18 | Chg
35170 | MRTR OOB-New-PWY-OOB Server | CA | SAN | PWY | Poway | Metro Routers | POInt | Yes | Yes | MRTR CA SAN PWY OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-06-30 | 2020-09-30 | SN-0158 | 2020-02-06 | New
74548 | R PHY_CCAP_VBC_RPHY CCAP Licenses_Q2 NC Video | VA | HRD | VBC | Virginia Beach | R PHY | POInt | Yes | Yes | R PHY VA HRD VBC RPHY CCAP Augment POR20 | License | CCAP license | 544 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
54573 | CFS SW LAS TEN BS-CFS Augment POR20 | SW | LAS | TEN | Tenaya | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW LAS TEN BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 |  | SB-0023 | 2020-01-30 | New
59745 | R PHY_CCAP_FED_RPHY CCAP Licenses_Q2 NC Video | CA | SAN | FED | Federal | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN FED RPHY CCAP Deployment POR20 | License | CCAP license | 2856 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
35010 | Metro OTN-BAR-Ciena 6500 S14 | CE | TUL | BAR | Broken Arrow | Metro Transport | POInt | Yes | Yes | MTRN CE TUL BAR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-06-30 | 2020-08-30 | SN-0161 | 2020-02-18 | Chg
35010 | Metro OTN-BAR-Ciena 6500 S2 | CE | TUL | BAR | Broken Arrow | Metro Transport | POInt | Yes | Yes | MTRN CE TUL BAR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-06-30 | 2020-08-30 | SN-0161 | 2020-02-18 | Chg
78099 | VCDR SW ARZ TUC Voice HDT Decom POR20 | SW | ARZ | TUC | Tucson | Voice Decom and Refortification | POInt | Yes | Yes | VCDR SW ARZ TUC Voice HDT Decom POR20 | Labor | No Equipment | 24 | 2020-05-07 | 2020-06-30 |  | SN-1080 | 2020-11-20
74548 | R PHY_CCAP_NWP_RPHY CCAP Licenses_Q2 NC Video | VA | HRD | NWP | Newport News | R PHY | POInt | Yes | Yes | R PHY VA HRD NWP RPHY CCAP Augment POR20 | License | CCAP license | 2040 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
35174 | MRTR NCS-Growth-CLR-100G Grow | SE | NOR | CLR | Metairie | Metro Routers | POInt | Yes | Yes | MRTR SE NOR CLR 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-06-30 | 2020-06-30 | SN-0555 | 2020-05-12 | Chg
59745 | R PHY_CCAP_ELC_RPHY CCAP Licenses_Q2 NC Video | CA | SAN | ELC | El Cajon | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN ELC RPHY CCAP Deployment POR20 | License | CCAP license | 272 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
35715 | MRTR AAR-New-EXT-NEW-AAR | NE | RHD | EXT | Exeter | Metro Routers | POInt | Yes | Yes | MRTR NE RHD EXT AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | SN-0158 | 2020-02-06 | Chg
54573 | CFS SW ARZ PNL LM-CFS Augment POR20 | SW | ARZ | PNL | Pinal County | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ PNL LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 |  | SB-0023 | 2020-01-30 | New
75187 | R PHY_CCAP_FAY_RPHY CCAP Licenses_Q2 NC Video | CE | NWA | FAY | Fayetteville | R PHY | POInt | Yes | Yes | R PHY CE NWA FAY RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_CHD_RPHY CCAP Licenses_Q2 NC Video | SW | ARZ | CHD | Chandler | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ CHD RPHY CCAP Deployment POR20 | License | CCAP license | 272 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
35176 | MRTR NCS-Growth-DTN-100G Grow | CE | TUL | DTN | Downtown (TUL) | Metro Routers | POInt | Yes | Yes | MRTR CE TUL DTN 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | SN-0158 | 2020-02-06 | Chg
35176 | MRTR OOB-New-BAR-OOB Server | CE | TUL | BAR | Broken Arrow | Metro Routers | POInt | Yes | Yes | MRTR CE TUL BAR OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | SN-0158 | 2020-02-06 | Chg
59745 | R PHY_CCAP_OCE_RPHY CCAP Licenses_Q2 NC Video | CA | SAN | OCE | Oceanside | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN OCE RPHY CCAP Deployment POR20 | License | CCAP license | 136 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
54573 | CFS SW ARZ GVA BS-CFS Augment POR20 | SW | ARZ | GVA | Green Valley | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ GVA BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 |  | SB-0023 | 2020-01-30 | New
35177 | MRTR OOB-New-GLO-OOB Server | VA | HRD | GLO | Gloucester | Metro Routers | POInt | Yes | Yes | MRTR VA HRD GLO OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | SN-0158 | 2020-02-06 | Chg
35170 | MRTR OOB-New-OCE-OOB Server | CA | SAN | OCE | Oceanside | Metro Routers | POInt | Yes | Yes | MRTR CA SAN OCE OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-06-30 | 2020-09-30 | SN-0158 | 2020-02-06 | New
35715 | MRTR AAR-New-MAN-NEW-AAR | NE | CON | MAN | Manchester | Metro Routers | POInt | Yes | Yes | MRTR NE CON MAN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | SN-0158 | 2020-02-06 | Chg
35174 | MRTR SLR-New-SPC-SLR-ASR9906 | SE | BTR | SPC | Pecue | Metro Routers | POInt | Yes | Yes | MRTR SE BTR SPC SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-12-31 | SN-0662 | 2020-06-14 | Chg
35177 | NEXUS-CHS-2248-01 | VA | HRD | CHS | Chesapeake | Metro Routers | POInt | Yes | Yes | MRTR VA HRD CHS Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-04-20 | 2020-06-30 | 2020-06-30 | SN-0588 | 2020-05-14 | Chg
54573 | CFS SW LAS HEN BS-CFS Augment POR20 | SW | LAS | HEN | Henderson | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW LAS HEN BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 |  | SB-0023 | 2020-01-30 | New
35177 | MRTR NCS-Growth-LTF-100G Grow | VA | HRD | LTF | Lightfoot | Metro Routers | POInt | Yes | Yes | MRTR VA HRD LTF 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-06-30 | 2020-06-30 | SN-0158 | 2020-02-06 | Chg
59745 | R PHY_CCAP_DWN_RPHY CCAP Licenses_Q2 NC Video | CA | SAN | DWN | Downtown | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN DWN RPHY CCAP Deployment POR20 | License | CCAP license | 136 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
75187 | R PHY_CCAP_BVL_RPHY CCAP Licenses_Q2 NC Video | CE | NWA | BVL | Bentonville | R PHY | POInt | Yes | Yes | R PHY CE NWA BVL RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
59745 | R PHY_CCAP_RSM_RPHY CCAP Licenses_Q2 NC Video | CA | ORG | RSM | Rancho Santa Margarita | RSPD - CCAP | POInt | Yes | Yes | R PHY CA ORG RSM RPHY CCAP Deployment POR20 | License | CCAP license | 408 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_BEL_RPHY CCAP Licenses_Q2 NC Video | SW | ARZ | BEL | Bell | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ BEL RPHY CCAP Deployment POR20 | License | CCAP license | 1632 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
74648 | RPHY MRTR-New-RON-CIN-ATX-OCML | VA | ROA | RON | Roanoke | R PHY | POInt | Yes | Yes | R PHY VA ROA RON RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-06-30 |  | SN-0606 | 2020-05-22 | New
74648 | RPHY MRTR-New-RON-CIN-DPA-5200 | VA | ROA | RON | Roanoke | R PHY | POInt | Yes | Yes | R PHY VA ROA RON RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-06-30 |  | SN-0211 | 2020-01-23 | New
74648 | RPHY MRTR-New-RON-CIN MGMT-2K | VA | ROA | RON | Roanoke | R PHY | POInt | Yes | Yes | R PHY VA ROA RON RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-06-30 |  | SN-0211 | 2020-01-23 | New
34604 | LFYTLAUO1BW-42LAFMTC7750X02-ROUTER | SE | LFY | LFY | Lafayette | CB - Metro Core | POInt | Yes | Yes | CBMC SE LFY LFY ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-06-30 |  | SN-0654 | 2020-06-14 | Chg
59522 | R PHY_CCAP_SSC_RPHY CCAP Licenses_Q2 NC Video | SW | ARZ | SSC | South Scottsdale | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ SSC RPHY CCAP Deployment POR20 | License | CCAP license | 5576 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_ERN_RPHY Unbundled Solution V2_43962 | SW | LAS | ERN | Ernest May | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | License | License Activation | 1035 | 2020-04-15 | 2020-06-30 |  | SN-0217 | 2020-02-03 | Chg
35170 | MRTR OOB-New-VST-OOB Server | CA | SAN | VST | Vista | Metro Routers | POInt | Yes | Yes | MRTR CA SAN VST OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-06-30 | 2020-09-30 | SN-0158 | 2020-02-06 | New
59522 | R PHY_CCAP_ERN_RPHY CCAP Licenses_Q2 NC Video | SW | LAS | ERN | Ernest May | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | License | CCAP license | 544 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
34601 | CB Transport - New Router Providence - WWK - Optics | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | CB - Metro Core | POInt | Yes | Yes | CBMC NE RHD WWK Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-03-15 | 2020-06-30 |  | SN-0618 | 2020-06-05 | Chg
74548 | R PHY_CCAP_CHS_RPHY CCAP Licenses_Q2 NC Video | VA | HRD | CHS | Chesapeake | R PHY | POInt | Yes | Yes | R PHY VA HRD CHS RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
35171 | MRTR OOB-New-DNP-OOB Server | CA | ORG | DNP | Dana Point | Metro Routers | POInt | Yes | Yes | MRTR CA ORG DNP OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-06-30 | 2020-09-30 | SN-0158 | 2020-02-06 | New
59522 | R PHY_CCAP_NSC_RPHY CCAP Licenses_Q2 NC Video | SW | ARZ | NSC | North Scottsdale | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ NSC RPHY CCAP Deployment POR20 | License | CCAP license | 408 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
35175 | MRTR OOB-New-RSM-OOB Server | CA | ORG | RSM | Rancho Santa Margarita | Metro Routers | POInt | Yes | Yes | MRTR CA ORG RSM OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 4 | 2020-04-05 | 2020-06-30 | 2020-09-30 | SN-0158 | 2020-02-06 | New
35177 | MRTR OOB-New-NKT-OOB Server | VA | HRD | NKT | New Kent | Metro Routers | POInt | Yes | Yes | MRTR VA HRD NKT OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | SN-0158 | 2020-02-06 | Chg
54573 | CFS SW ARZ DGL BS-CFS Augment POR20 | SW | ARZ | DGL | Douglas | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ DGL BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 |  | SB-0023 | 2020-01-30 | New
35173 | MRTR OOB-New-ORG-OOB Server | CA | ORG | ORG | Orange | Metro Routers | POInt | Yes | Yes | MRTR CA ORG ORG OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-06-30 | 2020-09-30 | SN-0158 | 2020-02-06 | New
35172 | MRTR SLR-New-WRB-SLR-ASR9906 | SE | MGA | WRB | Warner Robins | Metro Routers | POInt | Yes | Yes | MRTR SE MGA WRB SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-12-31 | SN-0662 | 2020-06-14 | Chg
59522 | R PHY_CCAP_BLU_RPHY CCAP Licenses_Q2 NC Video | SW | LAS | BLU | Blue Diamond | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS BLU RPHY CCAP Deployment POR20 | License | CCAP license | 2584 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
35175 | NEXUS-SCT-93108-01 | NE | RHD | SCT | Scituate | Metro Routers | POInt | Yes | Yes | MRTR NE RHD SCT Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 1 | 2020-04-01 | 2020-06-30 | 2020-06-30 | SN-0239 | 2020-02-07 | Chg
35175 | NEXUS-SCT-3048-01 | NE | RHD | SCT | Scituate | Metro Routers | POInt | Yes | Yes | MRTR NE RHD SCT Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 | 2020-04-01 | 2020-06-30 | 2020-06-30 | SN-0239 | 2020-02-07 | Chg
59522 | R PHY_CCAP_MSA_RPHY CCAP Licenses_Q2 NC Video | SW | ARZ | MSA | Mesa | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ MSA RPHY CCAP Deployment POR20 | License | CCAP license | 4624 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
35174 | MRTR NCS-Growth-SPC-100G Grow | SE | BTR | SPC | Pecue | Metro Routers | POInt | Yes | Yes | MRTR SE BTR SPC 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-06-30 | 2020-06-30 | SN-0555 | 2020-05-12 | Chg
59522 | R PHY_CCAP_FWL_RPHY CCAP Licenses_Q2 NC Video | SW | ARZ | FWL | Fowler | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ FWL RPHY CCAP Deployment POR20 | License | CCAP license | 1632 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
34601 | CB Transport - New Router Enfield P, Richmond - WWK - Card Add | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | CB - Metro Core | POInt | Yes | Yes | CBMC NE RHD WWK Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-01 | 2020-06-30 |  | SN-0618 | 2020-06-05 | Chg
34601 | CB Transport - New Router Enfield P, Manchester P - MAN - Card Add | NE | CON | MAN | Manchester | CB - Metro Core | POInt | Yes | Yes | CBMC NE CON MAN Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-01 | 2020-06-30 |  | SN-0618 | 2020-06-05 | Chg
35175 | MRTR SLR-New-MAN-SLR-ASR9906 | NE | CON | MAN | Manchester | Metro Routers | POInt | Yes | Yes | MRTR NE CON MAN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | SN-0158 | 2020-02-06 | Chg
59522 | R PHY_CCAP_TEN_RPHY CCAP Licenses_Q2 NC Video | SW | LAS | TEN | Tenaya | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | License | CCAP license | 1224 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
35174 | MRTR OOB-New-PAV-OOB Server | CA | ORG | PAV | Palos Verdes | Metro Routers | POInt | Yes | Yes | MRTR CA ORG PAV OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-06-30 | 2020-09-30 | SN-0158 | 2020-02-06 | New
35177 | MRTR OOB-New-LTF-OOB Server | VA | HRD | LTF | Lightfoot | Metro Routers | POInt | Yes | Yes | MRTR VA HRD LTF OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | SN-0158 | 2020-02-06 | Chg
35177 | MRTR OOB-New-CHS-OOB Server | VA | HRD | CHS | Chesapeake | Metro Routers | POInt | Yes | Yes | MRTR VA HRD CHS OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-04-01 03:01 | 2020-06-30 | 2020-09-30 | SN-0158 | 2020-02-06 | Chg
34619 | CB Transport - New Router Council Bluffs - OMM - Optics | CE | OMA | OMM | Omaha | CB - Metro Core | POInt | Yes | Yes | CBMC CE OMA OMM Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-02-15 | 2020-06-30 |  | SN-0386 | 2020-03-27 | Chg
35170 | MRTR OOB-New-ESC-OOB Server | CA | SAN | ESC | Escondido | Metro Routers | POInt | Yes | Yes | MRTR CA SAN ESC OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-06-30 | 2020-09-30 | SN-0158 | 2020-02-06 | New
75187 | R PHY_CCAP_QNC_RPHY CCAP Licenses_Q2 NC Video | CE | TUL | QNC | Quincy | R PHY | POInt | Yes | Yes | R PHY CE TUL QNC RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
34601 | CB Transport - New Router Providence - PRV - Optics | NE | RHD | PRV | Providence | CB - Metro Core | POInt | Yes | Yes | CBMC NE RHD PRV Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-03-15 | 2020-06-30 |  | SN-0618 | 2020-06-05 | Chg
59522 | R PHY_CCAP_ALI_RPHY CCAP Licenses_Q2 NC Video | SW | LAS | ALI | Aliante | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS ALI RPHY CCAP Deployment POR20 | License | CCAP license | 136 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
35170 | MRTR OOB-New-FED-OOB Server | CA | SAN | FED | Federal | Metro Routers | POInt | Yes | Yes | MRTR CA SAN FED OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-04-05 | 2020-06-30 | 2020-09-30 | SN-0158 | 2020-02-06 | New
34619 | MTC1BSRA99-ROUTER | CE | OMA | OMM | Omaha | CB - Metro Core | POInt | Yes | Yes | CBMC CE OMA OMM ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-05 | 2020-06-30 |  | SN-0386 | 2020-03-27 | Chg
59745 | R PHY_CCAP_CHU_RPHY CCAP Licenses_Q2 NC Video | CA | SAN | CHU | Chula Vista | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN CHU RPHY CCAP Deployment POR20 | License | CCAP license | 136 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
74548 | R PHY_CCAP_OCN_RPHY CCAP Licenses_Q2 NC Video | VA | HRD | OCN | Oceana | R PHY | POInt | Yes | Yes | R PHY VA HRD OCN RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
74548 | R PHY_CCAP_NRF_RPHY CCAP Licenses_Q2 NC Video | VA | HRD | NRF | Norfolk | R PHY | POInt | Yes | Yes | R PHY VA HRD NRF RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
75187 | R PHY_CCAP_OKC_RPHY CCAP Licenses_Q2 NC Video | CE | OKC | OKC | OKC MTC | R PHY | POInt | Yes | Yes | R PHY CE OKC OKC RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
35172 | MRTR OOB-New-IRV-OOB Server | CA | ORG | IRV | Irvine | Metro Routers | POInt | Yes | Yes | MRTR CA ORG IRV OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-06-30 | 2020-09-30 | SN-0158 | 2020-02-06 | New
59522 | R PHY_CCAP_OSB_RPHY CCAP Licenses_Q2 NC Video | SW | LAS | OSB | Oso Blanca | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | License | CCAP license | 1496 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
35177 | NEXUS-GLO-2248-01 | VA | HRD | GLO | Gloucester | Metro Routers | POInt | Yes | Yes | MRTR VA HRD GLO Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-04-15 | 2020-06-30 | 2020-06-30 | SN-0588 | 2020-05-14 | Chg
35175 | MRTR SLR-New-ENF-SLR-ASR9906 | NE | CON | ENF | Enfield | Metro Routers | POInt | Yes | Yes | MRTR NE CON ENF SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | SN-0158 | 2020-02-06 | Chg
35177 | MRTR OOB-New-HCK-OOB Server | VA | HRD | HCK | Hickory | Metro Routers | POInt | Yes | Yes | MRTR VA HRD HCK OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | SN-0158 | 2020-02-06 | Chg
34619 | CB Transport - New Router Bellevue, Omaha MTC - OMM - Card Add | CE | OMA | OMM | Omaha | CB - Metro Core | POInt | Yes | Yes | CBMC CE OMA OMM Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-02-15 | 2020-06-30 |  | SN-0386 | 2020-03-27 | Chg
59522 | R PHY_CCAP_PEO_RPHY CCAP Licenses_Q2 NC Video | SW | ARZ | PEO | Peoria | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ PEO RPHY CCAP Deployment POR20 | License | CCAP license | 1768 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
75187 | R PHY_CCAP_BAR_RPHY CCAP Licenses_Q2 NC Video | CE | TUL | BAR | Broken Arrow | R PHY | POInt | Yes | Yes | R PHY CE TUL BAR RPHY CCAP Deployment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
34622 | Federal-OCML-IXR | CA | SAN | FED | Federal | CB - Metro Core | POInt | Yes | Yes | CBMC CA SAN FED OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-06-30 |  | SN-0618 | 2020-06-05 | Chg
35176 | MRTR OOB-New-ALP-OOB Server | CA | SAN | ALP | Alpine | Metro Routers | POInt | Yes | Yes | MRTR CA SAN ALP OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-06-30 | 2020-09-30 | SN-0158 | 2020-02-06 | New
35171 | MRTR OOB-New-BER-OOB Server | CE | NWA | BER | Berryville | Metro Routers | POInt | Yes | Yes | MRTR CE NWA BER OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-01 | 2020-06-30 | 2020-09-30 | SN-0158 | 2020-02-06 | Chg
35177 | MRTR OOB-New-CHU-OOB Server | CA | SAN | CHU | Chula Vista | Metro Routers | POInt | Yes | Yes | MRTR CA SAN CHU OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-06-30 | 2020-09-30 | SN-0158 | 2020-02-06 | New
59522 | R PHY_CCAP_HEN_RPHY CCAP Licenses_Q2 NC Video | SW | LAS | HEN | Henderson | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS HEN RPHY CCAP Deployment POR20 | License | CCAP license | 2720 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_TUC_RPHY CCAP Licenses_Q2 NC Video | SW | ARZ | TUC | Tucson | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ TUC RPHY CCAP Deployment POR20 | License | CCAP license | 408 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
74548 | R PHY_CCAP_PRA_RPHY CCAP Licenses_Q2 NC Video | VA | HRD | PRA | Princess Anne | R PHY | POInt | Yes | Yes | R PHY VA HRD PRA RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
35177 | MRTR OOB-New-OCN-OOB Server | VA | HRD | OCN | Oceana | Metro Routers | POInt | Yes | Yes | MRTR VA HRD OCN OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | SN-0158 | 2020-02-06 | Chg
35170 | MRTR OOB-New-DWN-OOB Server | CA | SAN | DWN | Downtown | Metro Routers | POInt | Yes | Yes | MRTR CA SAN DWN OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-06-30 | 2020-09-30 | SN-0158 | 2020-02-06 | New
35177 | NEXUS-NWP-2248-01 | VA | HRD | NWP | Newport News | Metro Routers | POInt | Yes | Yes | MRTR VA HRD NWP 100G Grow Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-04-20 | 2020-06-30 | 2020-06-30 | SN-0588 | 2020-05-14 | Chg
75246 | R PHY_CCAP_LFY_RPHY CCAP Licenses_Q2 NC Video | SE | LFY | LFY | Lafayette | R PHY | POInt | Yes | Yes | R PHY SE LFY LFY RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
75187 | R PHY_CCAP_ELK_RPHY CCAP Licenses_Q2 NC Video | CE | OMA | ELK | Elkhorn | R PHY | POInt | Yes | Yes | R PHY CE OMA ELK RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-06-30 | 2020-06-30 | SN-0550 | 2020-05-12 | New
34601 | RMNDCBSA01.RI.RI-ROUTER | NE | RHD | RMD | Richmond (RI) | CB - Metro Core | POInt | Yes | Yes | CBMC NE RHD RMD ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-06-30 |  | SN-0618 | 2020-06-05 | Chg
35170 | MRTR OOB-New-AVJ-OOB Server | CA | ORG | AVJ | Aliso Viejo | Metro Routers | POInt | Yes | Yes | MRTR CA ORG AVJ OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-07-01 | 2020-07-01 | SN-0158 | 2020-02-06 | New
54573 | CFS SW LAS TEN HV-CFS Augment POR20 | SW | LAS | TEN | Tenaya | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW LAS TEN HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW LAS HEN HV-CFS Augment POR20 | SW | LAS | HEN | Henderson | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW LAS HEN HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ CSG HV-CFS Augment POR20 | SW | ARZ | CSG | Casa Grande | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ CSG HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE BTR NTH SC-CFS Augment POR20 | SE | BTR | NTH | Baker | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE BTR NTH SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW LAS VLY HV-CFS Augment POR20 | SW | LAS | VLY | Valley | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW LAS VLY HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | SB-0023 | 2020-01-30 | New
35175 | NEXUS-GRB-3048-01 | NE | CON | GRB | Granby | Metro Routers | POInt | Yes | Yes | MRTR NE CON GRB Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 | 2020-05-18 | 2020-07-01
35175 | NEXUS-GRB-93108-01 | NE | CON | GRB | Granby | Metro Routers | POInt | Yes | Yes | MRTR NE CON GRB Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 2 | 2020-05-18 | 2020-07-01
35175 | NEXUS-GRB-93180-01 | NE | CON | GRB | Granby | Metro Routers | POInt | Yes | Yes | MRTR NE CON GRB Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-05-18 | 2020-07-01
54572 | CFS VA HRD OCN DC-CFS Augment POR20 | VA | HRD | OCN | Oceana | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD OCN DC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE NOR KNN SC-CFS Augment POR20 | SE | NOR | KNN | Kenner | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE NOR KNN SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE LFY STM IV-CFS Augment POR20 | SE | LFY | STM | St. Martinville | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE LFY STM IV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | SB-0023 | 2020-01-30 | New
54573 | CFS SW ARZ PNL HV-CFS Augment POR20 | SW | ARZ | PNL | Pinal County | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SW ARZ PNL HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | SB-0023 | 2020-01-30 | New
54572 | CFS VA ROA RON DC-CFS Augment POR20 - 2 | VA | ROA | RON | Roanoke | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA ROA RON DC-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-07-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE BTR PLQ SC-CFS Augment POR20 | SE | BTR | PLQ | Plaquemine | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE BTR PLQ SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | SB-0023 | 2020-01-30 | New
54572 | CFS VA NVA MFD BD-CFS Augment POR20 | VA | NVA | MFD | Merrifield | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA NVA MFD BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE NOR MCY BD-CFS Augment POR20 | SE | NOR | MCY | Mid-City | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE NOR MCY BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | SB-0023 | 2020-01-30 | New
54572 | CFS VA HRD PTM DC-CFS Augment POR20 | VA | HRD | PTM | Portsmouth (VA) | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD PTM DC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | SB-0023 | 2020-01-30 | New
34761 | BWM_BEL_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | BEL | Bell | Bandwidth Management | POInt | Yes | No | BWM SW ARZ BEL DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | SN-0143 | 2020-02-06 | Chg
34761 | BWM_TUC_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | TUC | Tucson | Bandwidth Management | POInt | Yes | No | BWM SW ARZ TUC DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | SN-0143 | 2020-02-06 | Chg
34761 | BWM_MSA_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | MSA | Mesa | Bandwidth Management | POInt | Yes | No | BWM SW ARZ MSA DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | SN-0143 | 2020-02-06 | Chg
34761 | BWM_WKB_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | WCG | Wickenburg | Bandwidth Management | POInt | Yes | No | BWM SW ARZ WCG DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | SN-0473 | 2020-04-17 | Chg
34761 | BWM_MCD_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | MCD | McDowell | Bandwidth Management | POInt | Yes | No | BWM SW ARZ MCD DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | SN-0143 | 2020-02-06 | Chg
34761 | BWM_DGL_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | DGL | Douglas | Bandwidth Management | POInt | Yes | No | BWM SW ARZ DGL DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | SN-0143 | 2020-02-06 | Chg
34761 | BWM_NSC_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | NSC | North Scottsdale | Bandwidth Management | POInt | Yes | No | BWM SW ARZ NSC DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | SN-0143 | 2020-02-06 | Chg
34761 | BWM_PNL_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | PNL | Pinal County | Bandwidth Management | POInt | Yes | No | BWM SW ARZ PNL DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | SN-0143 | 2020-02-06 | Chg
34761 | BWM_CHD_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | CHD | Chandler | Bandwidth Management | POInt | Yes | No | BWM SW ARZ CHD DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | SN-0143 | 2020-02-06 | Chg
34761 | BWM_SVA_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | SVA | Sierra Vista | Bandwidth Management | POInt | Yes | No | BWM SW ARZ SVA DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | SN-0143 | 2020-02-06 | Chg
34761 | BWM_GVA_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | GVA | Green Valley | Bandwidth Management | POInt | Yes | No | BWM SW ARZ GVA DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | SN-0143 | 2020-02-06 | Chg
34761 | BWM_CSG_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | CSG | Casa Grande | Bandwidth Management | POInt | Yes | No | BWM SW ARZ CSG DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | SN-0143 | 2020-02-06 | Chg
54572 | CFS VA ROA RON DC-CFS Augment POR20 | VA | ROA | RON | Roanoke | Critical Facilities Sustaining (Field) | POInt | Yes | No | CFS VA ROA RON DC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | SB-0023 | 2020-01-30 | New
34761 | BWM_FWL_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | FWL | Fowler | Bandwidth Management | POInt | Yes | No | BWM SW ARZ FWL DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | SN-0143 | 2020-02-06 | Chg
34761 | BWM_VSA_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | VSA | Vistancia | Bandwidth Management | POInt | Yes | No | BWM SW ARZ VSA DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | SN-0143 | 2020-02-06 | Chg
54572 | CFS VA NVA GCR BS-CFS Augment POR20 | VA | NVA | GCR | Gunston | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA NVA GCR BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | SB-0023 | 2020-01-30 | New
34761 | BWM_BEN_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | BEN | Benson with (Insite tower) | Bandwidth Management | POInt | Yes | No | BWM SW ARZ BEN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | SN-0143 | 2020-02-06 | Chg
34761 | BWM_BUK_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | BUK | Buckeye | Bandwidth Management | POInt | Yes | No | BWM SW ARZ BUK DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | SN-0143 | 2020-02-06 | Chg
34761 | BWM_SSC_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | SSC | South Scottsdale | Bandwidth Management | POInt | Yes | No | BWM SW ARZ SSC DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | SN-0143 | 2020-02-06 | Chg
34761 | BWM_PEO_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | PEO | Peoria | Bandwidth Management | POInt | Yes | No | BWM SW ARZ PEO DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | SN-0143 | 2020-02-06 | Chg
75655 | Arbor 2 | COR | NAT | SV5 | San Jose - Equinix (cage 51235) | Arbor DDoS | POInt | Yes | No | DDoS CA NAT SV5 Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-06-12 | 2020-07-05 | 2020-08-14 | SN-0220 | 2020-02-03 | Chg
75655 | Arbor 10 | NE | CLE | CLV | Cleveland | Arbor DDoS | POInt | Yes | No | DDoS NE CLE CLV Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-05-22 | 2020-07-06 | 2020-07-20 | SN-0107 | 2020-02-06 | Chg
75645 | CGN Replacement 12 | SW | LAS | TEN | Tenaya | Data Center Capacity | POInt | Yes | No | DTC SW LAS TEN CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-02-15 | 2020-07-08 |  | SN-0554 | 2020-05-13 | Chg
39256 | BWM RHD DOCSIS Expansion 96 MHz | NE | RHD | PAW | Pawtucket | Bandwidth Management | POInt | Yes | No | BWM NE RHD PAW DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-08 | 2021-07-01 | SN-0558 | 2020-05-12 | New
39256 | BWM RHD DOCSIS Expansion 192 MHz | NE | RHD | CRN | Cranston | Bandwidth Management | POInt | Yes | No | BWM NE RHD CRN DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-08 | 2022-04-01 | SN-0558 | 2020-05-12 | New
34619 | CB Transport - New Router Bentonville - NWA - Optics | CE | NWA | NWA | Johnson | CB - Metro Core | POInt | Yes | No | CBMC CE ARK NWA Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-06-15 | 2020-07-15
44876 | MTCH CE OKC NEH Signal Rewire Augment POR20 | CE | OKC | NEH | North East | MTC HE - Hub Signaling | POInt | Yes | No | MTCH CE OKC NEH Signal Rewire Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-05-06 | 2020-07-15 | 2020-08-15
75651 | PTX Add 2 | SE | GCT | PNS | Pensacola with (Insite tower) | Backbone | POInt | Yes | No | BBCAP SE GCT PNS PTX10 Deployment POR20 | Chassis | 1x Juniper PTX10K Chassis | 2 | 2020-04-23 | 2020-07-15 |  | SN-0448 | 2020-04-17 | Chg
44876 | MTCH CE OKC NOR Signal Rewire Augment POR20 | CE | OKC | NOR | Norman | MTC HE - Hub Signaling | POInt | Yes | No | MTCH CE OKC NOR Signal Rewire Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-05-06 | 2020-07-15 | 2020-08-15
75794 | VEO Automation - Jira Portfolio Implementation | COR | COR | ATL | Atlanta | Voice Monitoring and Analytics | POInt | Yes | No | VMA CO -CO ATL Workflow and portfolio implementation Deployment POR20 | Labor | Dev of Jira Proj Mgmt soln for VEO projects | 1 | 2020-06-25 | 2020-07-15 |  | SB-0013 | 2020-01-30 | Chg
75699 | MTCS COR COR P6L Lab vDCM Deployment POR20 | COR | COR | P6L | P6 Lab | MTC - Servers and Software | POInt | Yes | No | MTCS CO COR P6L Lab vDCM Deployment POR20 | Chassis | 1x Synamedia D9902 DCM Chassis | 1 | 2020-06-06 | 2020-07-15 | 2020-08-15
57297 | REP_NE.CON.MAN.REPACK | SW | ARZ | FWL | Fowler | FCC Repack | POInt | Yes | No | FCC SW ARZ FWL Channel Move Alignment POR20 | Chassis | Channel Move / Inca 8VSB / Wade WH | 2 | 2020-05-02 | 2020-07-15
75738 | MTCH COR COR ATL MPEG4 ATX Upgrade Deployment POR20 | COR | COR | ATL | Atlanta | MTC HE - Hub Signaling | POInt | Yes | No | MTCH CO COR ATL MPEG4 ATX Upgrade Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-06-10 | 2020-07-15 |  | SN-0680 | 2020-06-17 | Chg
34601 | CB Transport - New Router Manchester PE - ENF - Optics | NE | CON | ENF | Enfield | CB - Metro Core | POInt | Yes | No | CBMC NE CON ENF Optics Only for Cisco T5 Augment POR20_V2 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-06-15 | 2020-07-15
34685 | CCAP blades_ TCR 1 | VA | NVA | TCR | Tysons Corner | DOCSIS CMTS/CCAP | POInt | Yes | No | CMTS VA NVA TCR CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-06-04 | 2020-07-15 |  | SN-0048 | 2020-02-06 | Chg
34601 | CB Transport - New Router Manchester PE - MAN - Optics | NE | CON | MAN | Manchester | CB - Metro Core | POInt | Yes | No | CBMC NE CON MAN Optics Only for Cisco T5 Augment POR20_V2 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-06-15 | 2020-07-15
39225 | CCAP blades_ NCV | SE | GCT | NCV | Niceville | DOCSIS CMTS/CCAP | POInt | Yes | No | CMTS SE GCT NCV CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-07-06 | 2020-07-15 |  | SN-0048 | 2020-02-06 | Chg
34619 | CB Transport - New Router Bentonville - BVL - Card Add | CE | NWA | BVL | Bentonville | CB - Metro Core | POInt | Yes | No | CBMC CE ARK BVL Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-15 | 2020-07-15
34619 | CB Transport - New Router Bentonville - FAY - Optics | CE | NWA | FAY | Fayetteville | CB - Metro Core | POInt | Yes | No | CBMC CE ARK FAY Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-06-15 | 2020-07-15
75792 | Monitoring and Analytics - VEO Process Analytics | COR | COR | ATL | Atlanta | Voice Monitoring and Analytics | POInt | Yes | No | VMA CO -CO ATL Proactive Alerting Alignment POR20 | Labor | Data collection for Analytics of VEO Dev, trblsht | 1 | 2020-06-25 | 2020-07-15 |  | SB-0013 | 2020-01-30 | Chg
74648 | RPHY MRTR-New-LTF-CIN-DPA-5200 (100G DPIC) | VA | HRD | LTF | Lightfoot | R PHY | POInt | Yes | Yes | R PHY VA HRD LTF RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-07-15 | 2020-08-31 | SN-0606 | 2020-05-22
34619 | CB Transport - New Router North - BLV - Optics | CE | OMA | BLV | Bellevue | CB - Metro Core | POInt | Yes | Yes | CBMC CE OMA BLV Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-06-15 | 2020-07-15
44876 | MTCH CE OKC MOO Signal Rewire Augment POR20 | CE | OKC | MOO | Moore | MTC HE - Hub Signaling | POInt | Yes | No | MTCH CE OKC MOO Signal Rewire Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-05-06 | 2020-07-15 | 2020-08-15 | SN-0368 | 2020-04-10
34616 | CB Transport - New Router Irish Lane - NOR - Optics | CE | OKC | NOR | Norman | CB - Metro Core | POInt | Yes | Yes | CBMC CE OKC NOR Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-06-15 | 2020-07-15
34972 | CFG NWT HV-CFG GEN GROW PROJECT - MEDIUM | CE | KAN | NWT | Newton | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE KAN NWT HV-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-07-01 | 2020-07-15
34972 | CFG SOU RK-CFG GEN GROW PROJECT - MEDIUM | CE | OMA | SOU | South (OM) | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OMA SOU BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-07-01 | 2020-07-15
34623 | CB Transport - New Router Fowler - MCD - Optics | SW | ARZ | MCD | McDowell | CB - Metro Core | POInt | Yes | Yes | CBMC SW ARZ MCD Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-05-15 | 2020-07-15
34970 | CFG CHD BD-CFG GEN GROW PROJECT - LARGE | SW | ARZ | CHD | Chandler | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ CHD BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-03-01 | 2020-07-15
34970 | CFG CHD IV-CFG GEN GROW PROJECT - MEDIUM | SW | ARZ | CHD | Chandler | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ CHD BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-07-01 | 2020-07-15
75245 | RPHY MRTR-New-WIC-CIN-DPA-5200 (100G DPIC) | CE | KAN | WIC | Wichita | R PHY | POInt | Yes | Yes | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-07-15 | 2020-08-31 | SN-0612 | 2020-05-29 | Chg
34601 | CLVDBSRA02.RI.CL.COX.NET-ROUTER | NE | CLE | CLV | Cleveland | CB - Metro Core | POInt | Yes | Yes | CBMC NE CLE CLV ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-07-15 |  | SN-0144 | 2020-02-06 | Chg
34623 | CB Transport - New Router Fowler - FWL - Optics | SW | ARZ | FWL | Fowler | CB - Metro Core | POInt | Yes | Yes | CBMC SW ARZ FWL Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-05-22 | 2020-07-15
34970 | CFG PNL GN-CFG GEN GROW PROJECT - LARGE | SW | ARZ | PNL | Pinal County | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ PNL GN-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-02-01 | 2020-07-15
34970 | CFG PNL HV-CFG GEN GROW PROJECT - MEDIUM | SW | ARZ | PNL | Pinal County | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ PNL GN-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-06-01 | 2020-07-15
34623 | MCDLSYSA01-ROUTER | SW | ARZ | MCD | McDowell | CB - Metro Core | POInt | Yes | Yes | CBMC SW ARZ MCD ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-04-15 | 2020-07-15 |  | SN-0144 | 2020-02-06 | Chg
34841 | CCAP blades_ NOE | SE | NOR | NOE | New Orleans East | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SE NOR NOE CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-07-06 | 2020-07-15 |  | SN-0048 | 2020-02-06 | Chg
34623 | CB Transport - New Router Fowler - CHD - Optics | SW | ARZ | CHD | Chandler | CB - Metro Core | POInt | Yes | Yes | CBMC SW ARZ CHD Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-05-15 | 2020-07-15
34970 | CFG DGL RC-CFG GEN GROW PROJECT - SMALL | SW | ARZ | DGL | Douglas | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ DGL RC-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-03-01 | 2020-07-15
34970 | CFG SSC AC-CFG GEN GROW PROJECT - LARGE | SW | ARZ | SSC | South Scottsdale | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ SSC GN-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-01-01 | 2020-07-15
34970 | CFG SSC GN-CFG GEN GROW PROJECT - LARGE | SW | ARZ | SSC | South Scottsdale | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ SSC GN-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-02-01 | 2020-07-15
34619 | CB Transport - New Router North - ONA - Optics | CE | OMA | ONA | North (OM) | CB - Metro Core | POInt | Yes | Yes | CBMC CE OMA ONA Optics Only for Cisco T5 Augment POR20_V2 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-06-15 | 2020-07-15
34619 | CB Transport - New Router Irish Lane - OKC - Optics | CE | OKC | OKC | OKC MTC | CB - Metro Core | POInt | Yes | Yes | CBMC CE OKC OKC Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-06-15 | 2020-07-15
34970 | CFG BEN RC-CFG GEN GROW PROJECT - SMALL | SW | ARZ | BEN | Benson with (Insite tower) | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ BEN RC-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-03-01 | 2020-07-15
34970 | CFG TUC RC-CFG GEN GROW PROJECT - SMALL | SW | ARZ | TUC | Tucson | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ TUC BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-03-01 | 2020-07-15
74648 | RPHY MRTR-New-FBG-CIN-DPA-5200 (100G DPIC) | VA | NVA | FBG | Fredericksburg | R PHY | POInt | Yes | Yes | R PHY VA NVA FBG RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-07-15 | 2020-08-31 | SN-0606 | 2020-05-22
34970 | CFG TEN RC-CFG GEN GROW PROJECT - SMALL | SW | LAS | TEN | Tenaya | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW LAS TEN HV-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-03-01 | 2020-07-15
34970 | CFG TEN HV-CFG GEN GROW PROJECT - MEDIUM | SW | LAS | TEN | Tenaya | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW LAS TEN HV-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-06-01 | 2020-07-15
34604 | CB Transport - New Router St Martinville - STM - Card Add | SE | LFY | STM | St. Martinville | CB - Metro Core | POInt | Yes | Yes | CBMC SE LFY STM Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-15 | 2020-07-15
34970 | CFG ERN RC-CFG GEN GROW PROJECT - SMALL | SW | LAS | ERN | Ernest May | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW LAS ERN RC-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-03-01 | 2020-07-15
34619 | CB Transport - New Router North - OMM - Optics | CE | OMA | OMM | Omaha | CB - Metro Core | POInt | Yes | Yes | CBMC CE OMA OMM Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-06-15 | 2020-07-15
34685 | CCAP blades_ FBG | VA | NVA | FBG | Fredericksburg | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS VA NVA FBG CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-06-04 | 2020-07-15 |  | SN-0048 | 2020-02-06 | Chg
75245 | RPHY MRTR-New-CLH-CIN MGMT2-2K | CE | OKC | CLH | County Line | R PHY | POInt | Yes | Yes | R PHY CE OKC CLH RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-15 | 2020-08-31 | SN-0487 | 2020-05-12 | New
75245 | RPHY MRTR-New-CLH-CIN-Nokia-OCML2 | CE | OKC | CLH | County Line | R PHY | POInt | Yes | Yes | R PHY CE OKC CLH RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-05-15 | 2020-07-15 | 2020-08-31 | SN-0487 | 2020-05-12 | New
34972 | CFG WES RK-CFG GEN GROW PROJECT - MEDIUM | CE | OMA | WES | West (OM) | Critical Facilities (Grow) | POInt | Yes | Yes | CFG CE OMA WES BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-07-01 | 2020-07-15
34841 | CCAP blades_ CLR 2 | SE | NOR | CLR | Metairie | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SE NOR CLR CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-07-06 | 2020-07-15 |  | SN-0048 | 2020-02-06 | Chg
34690 | CCAP blades_ SSP | CE | NWA | SSP | Siloam Springs | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE NWA SSP CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-07-06 | 2020-07-15 |  | SN-0048 | 2020-02-06 | Chg
34619 | CB Transport - New Router Irish Lane - ILH - Optics | CE | OKC | ILH | Irish Lane | CB - Metro Core | POInt | Yes | Yes | CBMC CE OKC ILH Optics Only for Cisco T5 Augment POR20_V2 | Card & Optics | Optics Only for Cisco T5 | 3 | 2020-06-15 | 2020-07-15
34970 | CFG WCG BS-CFG GEN GROW PROJECT - MEDIUM | SW | ARZ | WCG | Wickenburg | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ WCG BS-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-06-01 | 2020-07-15
34623 | Ernest May-OCML-IXR | SW | LAS | ERN | Ernest May | CB - Metro Core | POInt | Yes | Yes | CBMC SW LAS ERN OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-07-20 | 2020-09-30 | SN-0819 | 2020-08-14 | Chg
34623 | Aliante-OCML-IXR | SW | LAS | ALI | Aliante | CB - Metro Core | POInt | Yes | Yes | CBMC SW LAS ALI OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-07-20 |  | SN-0586 | 2020-05-14 | Chg
34976 | CFG NE RHD LNC RK-CFG Deployment POR20 | NE | RHD | LNC | Lincoln | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE RHD LNC RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-07-14 | 2020-07-20 |  | SN-0411 | 2020-03-27
59522 | R PHY_CCAP_ALI_CBR8 Chassis-1 | SW | LAS | ALI | Aliante | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS ALI RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-04-20 | 2020-07-20 | 2020-07-20 | SN-0550 | 2020-05-12 | New
34623 | Buckeye-OCML-IXR | SW | ARZ | BUK | Buckeye | CB - Metro Core | POInt | Yes | Yes | CBMC SW ARZ BUK OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-07-20 |  | SN-0586 | 2020-05-14 | Chg
34604 | PNSCBSRA02.PN.AT-ROUTER | SE | GCT | PNS | Pensacola with (Insite tower) | CB - Metro Core | POInt | Yes | Yes | CBMC SE GCT PNS ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-06-15 | 2020-07-20 |  | SN-0586 | 2020-05-14 | Chg
34623 | Bell-OCML-IXR | SW | ARZ | BEL | Bell | CB - Metro Core | POInt | Yes | Yes | CBMC SW ARZ BEL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-07-20 |  | SN-0586 | 2020-05-14 | Chg
76106 | ServiceNow DDR | COR | COR | DDR | Duke Drive | Data Center Network Health | POInt | Yes | No | DCNH COR COR DDR ServiceNow POR20 | Labor | No Equipment | 1 |  | 2020-07-20 |  | SN-0129 | 2020-02-06 | New
75655 | Arbor 13 | VA | ROA | RON | Roanoke | Arbor DDoS | POInt | Yes | No | DDoS VA ROA RON Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-04-21 | 2020-07-20 | 2020-08-03 | SN-0172 | 2020-01-10 | Chg
75658 | VA-RON-1x ExtraHop EDA6200 (Dell R640) | VA | ROA | RON | Roanoke | Visibility Architecture | POInt | Yes | No | VIA VA ROA RON Visibility Architecture Gear Deployment POR20 | Chassis | 1x ExtraHop EDA6200 (Dell R640) | 1 | 2020-05-05 | 2020-07-20 | 2020-08-03 | SN-0169 | 2020-02-06 | Chg
75658 | VA-RON-1x Juniper EX4600 | VA | ROA | RON | Roanoke | Visibility Architecture | POInt | Yes | No | VIA VA ROA RON Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-05-05 | 2020-07-20 | 2020-08-03 | SN-0169 | 2020-02-06 | Chg
75658 | VA-RON-1x Dell R640 | VA | ROA | RON | Roanoke | Visibility Architecture | POInt | Yes | No | VIA VA ROA RON Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 1 | 2020-05-05 | 2020-07-20 | 2020-08-03 | SN-0169 | 2020-02-06 | Chg
76106 | ELK SRVR DDR | COR | COR | DDR | Duke Drive | Data Center Network Health | POInt | Yes | No | DCNH COR COR DDR ELK SERVER DEPLOYMENT POR20 | Labor | No Equipment | 1 |  | 2020-07-20 |  | SN-0129 | 2020-02-06 | New
76104 | DCFWLC DDR SRX4100 | COR | COR | DDR | Duke Drive | Data Center Firewall Lifecycle | POInt | Yes | No | DCFWLC COR COR DDR SRX4100 DEPLOYMNET POR20 | Labor | No Equipment | 8 | 2020-06-20 | 2020-07-20 | 2020-10-20 | SN-0685 | 2020-06-17 | Chg
75645 | CGN Replacement 13 | SW | ARZ | CHD | Chandler | Data Center Capacity | POInt | Yes | No | DTC SW ARZ CHD CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-02-22 | 2020-07-22 |  | SN-0554 | 2020-05-13 | Chg
75645 | CGN Replacement 14 | VA | ROA | RON | Roanoke | Data Center Capacity | POInt | Yes | No | DTC VA ROA RON CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-04-01 | 2020-07-23 |  | SN-0554 | 2020-05-13 | Chg
34608 | Norfolk-OCML-IXR | VA | HRD | NRF | Norfolk | CB - Metro Core | POInt | Yes | Yes | CBMC VA HRD NRF OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-07-30 |  | SN-0701 | 2020-07-02 | Chg
78091 | HY CA SAN ALP Voice HDT Decom POR20 | CA | SAN | ALP | Alpine | Voice Decom and Refortification | POInt | Yes | Yes | VCDR CA SAN ALP Voice HDT Decom POR20 v2 | Labor | No Equipment | 1 | 2020-04-01 | 2020-07-30 |  | SN-1080 | 2020-11-20
34608 | FRFYVA0631W-ROUTER | VA | NVA | FLK | Fair Lakes | CB - Metro Core | POInt | Yes | Yes | CBMC VA NVA FLK ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-07-30 |  | SN-0701 | 2020-07-02 | Chg
34619 | MTC-OCML-IXR | CE | OKC | OKC | OKC MTC | CB - Metro Core | POInt | Yes | Yes | CBMC CE OKC OKC OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-07-30 |  | SN-0701 | 2020-07-02 | Chg
78099 | HY SW ARZ VSA Voice HDT Decom POR20 | SW | ARZ | VSA | Vistancia | Voice Decom and Refortification | POInt | Yes | Yes | VCDR SW ARZ VSA Voice HDT Decom POR20 | Labor | No Equipment | 2 | 2020-05-07 | 2020-07-30 |  | SN-1080 | 2020-11-20
34619 | CB Transport - New Router Braden - TUL - Card Add | CE | TUL | TUL | Tulsa | CB - Metro Core | POInt | Yes | Yes | CBMC CE TUL TUL Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-02-15 | 2020-07-30 |  | SN-0701 | 2020-07-02 | Chg
34619 | CB Transport - New Router Garnett, Downtown (TUL) - TUL - Card Add | CE | TUL | TUL | Tulsa | CB - Metro Core | POInt | Yes | Yes | CBMC CE TUL TUL Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-03-15 | 2020-07-30 |  | SN-0701 | 2020-07-02 | Chg
34608 | NRFLVAJTBSRA7750-1-ROUTER | VA | HRD | NRF | Norfolk | CB - Metro Core | POInt | Yes | Yes | CBMC VA HRD NRF ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-03-15 | 2020-07-30 |  | SN-0701 | 2020-07-02 | Chg
34944 | MTRN-ORG-T5-Augment | CA | ORG | ORG | Orange | Metro Transport | POInt | Yes | Yes | MTRN CA ORG ORG T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | SN-0562 | 2020-05-12 | New
59850 | RPHY MRTR-New-DNP-CIN-RPA-5110 | CA | ORG | DNP | Dana Point | R PHY | POInt | Yes | Yes | R PHY CA ORG DNP RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 6 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0487 | 2020-05-12 | New
35011 | Metro OTN-DRA-Ciena 6500 S14 | VA | NVA | DRA | Dranesville | Metro Transport | POInt | Yes | Yes | MTRN VA NVA DRA OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | SN-0639 | 2020-06-05 | Chg
35011 | Metro OTN-DRA-Ciena 6500 S2 | VA | NVA | DRA | Dranesville | Metro Transport | POInt | Yes | Yes | MTRN VA NVA DRA OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-02-17 | 2020-07-31 | 2020-08-31 | SN-0639 | 2020-06-05 | Chg
35177 | MRTR OOB-New-RHL-OOB Server | VA | NVA | RHL | Rose Hill | Metro Routers | POInt | Yes | Yes | MRTR VA NVA RHL OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-05-01 | 2020-07-31 | 2020-10-31 | SN-0158 | 2020-02-06 | Chg
34948 | Metro OTN-LPL-Ciena 6500 S14 | SE | NOR | LPL | Lapalco | Metro Transport | POInt | Yes | Yes | MTRN SE NOR LPL OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | SN-0665 | 2020-06-14 | Chg
34948 | Metro OTN-LPL-Ciena 6500 S2 | SE | NOR | LPL | Lapalco | Metro Transport | POInt | Yes | Yes | MTRN SE NOR LPL OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | SN-0665 | 2020-06-14 | Chg
34948 | Metro OTN-STB-Ciena 6500 S14 | SE | NOR | STB | St. Bernard | Metro Transport | POInt | Yes | Yes | MTRN SE NOR STB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | SN-0665 | 2020-06-14 | Chg
34948 | Metro OTN-STB-Ciena 6500 S2 | SE | NOR | STB | St. Bernard | Metro Transport | POInt | Yes | Yes | MTRN SE NOR STB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | SN-0665 | 2020-06-14 | Chg
59744 | RPHY MRTR-Growth-MSA-CIN-Nokia-OCML | SW | ARZ | MSA | Mesa | R PHY | POInt | Yes | Yes | R PHY SW ARZ MSA RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 36 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0601 | 2020-05-22 | Chg
59744 | RPHY MRTR-Growth-MSA-CIN-RPA2-5110 | SW | ARZ | MSA | Mesa | R PHY | POInt | Yes | Yes | R PHY SW ARZ MSA RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 15 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0606 | 2020-05-22 | Chg
59744 | RPHY MRTR-Growth-MSA-CIN-Nokia2-OCML | SW | ARZ | MSA | Mesa | R PHY | POInt | Yes | Yes | R PHY SW ARZ MSA RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 50 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0608 | 2020-05-23 | Chg
59744 | RPHY MRTR-New-MSA-CIN MGMT-2K | SW | ARZ | MSA | Mesa | R PHY | POInt | Yes | Yes | R PHY SW ARZ MSA RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 5 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0606 | 2020-05-22 | Chg
34947 | MTRN-HEN- T5-05 | SW | LAS | HEN | Henderson | Metro Transport | POInt | Yes | Yes | MTRN SW LAS HEN T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | SN-0562 | 2020-05-12 | New
59744 | RPHY MRTR-New-VSA-CIN-RPA2-5110 | SW | ARZ | VSA | Vistancia | R PHY | POInt | Yes | Yes | R PHY SW ARZ VSA RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 3 | 2020-05-15 | 2020-07-31 | 2020-07-31 | SN-0487 | 2020-05-12 | New
35173 | MRTR SLR-New-TEN-Nexus Th-2248 | SW | LAS | TEN | Tenaya | Metro Routers | POInt | Yes | Yes | MRTR SW LAS TEN Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-07-31 | SN-0616 | 2020-05-29 | New
59744 | RPHY MRTR-New-BUK-CIN-RPA-5110 | SW | ARZ | BUK | Buckeye | R PHY | POInt | Yes | Yes | R PHY SW ARZ BUK RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 5 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0487 | 2020-05-12 | New
35177 | MRTR OOB-New-GCR-OOB Server | VA | NVA | GCR | Gunston | Metro Routers | POInt | Yes | Yes | MRTR VA NVA GCR OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-05-01 | 2020-07-31 | 2020-10-31 | SN-0158 | 2020-02-06 | Chg
59850 | RPHY MRTR-Growth-RSM-CIN-RPA-5110 | CA | ORG | RSM | Rancho Santa Margarita | R PHY | POInt | Yes | Yes | R PHY CA ORG RSM RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 6 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0606 | 2020-05-22 | Chg
35010 | Metro OTN-NOR-Ciena 6500 S14 | CE | OKC | NOR | Norman | Metro Transport | POInt | Yes | Yes | MTRN CE OKC NOR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | SN-0639 | 2020-06-05 | Chg
35010 | Metro OTN-NOR-Ciena 6500 S2 | CE | OKC | NOR | Norman | Metro Transport | POInt | Yes | Yes | MTRN CE OKC NOR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 4 | 2020-02-17 | 2020-07-31 | 2020-08-31 | SN-0639 | 2020-06-05 | Chg
59850 | RPHY MRTR-Growth-RSM-CIN-DPA-5200 | CA | ORG | RSM | Rancho Santa Margarita | R PHY | POInt | Yes | Yes | R PHY CA ORG RSM RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0487 | 2020-05-12 | New
59850 | RPHY MRTR-New-AVJ-CIN MGMT-2K | CA | ORG | RSM | Rancho Santa Margarita | R PHY | POInt | Yes | Yes | R PHY CA ORG RSM RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0606 | 2020-05-22 | New
35010 | Metro OTN-WLH-Ciena 6500 S14 | CE | OKC | WLH | Waterloo | Metro Transport | POInt | Yes | Yes | MTRN CE OKC WLH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | SN-0639 | 2020-06-05 | Chg
35010 | Metro OTN-WLH-Ciena 6500 S2 | CE | OKC | WLH | Waterloo | Metro Transport | POInt | Yes | Yes | MTRN CE OKC WLH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-07-31 | 2020-08-31 | SN-0639 | 2020-06-05 | Chg
59744 | RPHY MRTR-New-TUC-CIN-RPA-5110 | SW | ARZ | TUC | Tucson | R PHY | POInt | Yes | Yes | R PHY SW ARZ TUC RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 9 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0606 | 2020-05-22 | Chg
59744 | RPHY MRTR-New-TUC-CIN-DPA-5200 | SW | ARZ | TUC | Tucson | R PHY | POInt | Yes | Yes | R PHY SW ARZ TUC RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0606 | 2020-05-22 | Chg
34944 | MTRN-CHU- T5-02 | CA | SAN | CHU | Chula Vista | Metro Transport | POInt | Yes | Yes | MTRN CA SAN CHU T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | SN-0562 | 2020-05-12 | New
35011 | MTRN-OCN- T5-02 | VA | HRD | OCN | Oceana | Metro Transport | POInt | Yes | Yes | MTRN VA HRD OCN T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | SN-0562 | 2020-05-12 | New
59850 | RPHY MRTR-New-ELC-CIN-ATX-OCML2 | CA | SAN | ELC | El Cajon | R PHY | POInt | Yes | Yes | R PHY CA SAN ELC RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0606 | 2020-05-22 | Chg
59850 | RPHY MRTR-New-ELC-CIN-DPA-5200 | CA | SAN | ELC | El Cajon | R PHY | POInt | Yes | Yes | R PHY CA SAN ELC RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 6 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0487 | 2020-05-12 | New
59850 | RPHY MRTR-New-ELC-CIN-RPA-5110 | CA | SAN | ELC | El Cajon | R PHY | POInt | Yes | Yes | R PHY CA SAN ELC RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0606 | 2020-05-22 | Chg
59850 | RPHY MRTR-New-ELC-CIN MGMT-2K | CA | SAN | ELC | El Cajon | R PHY | POInt | Yes | Yes | R PHY CA SAN ELC RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0487 | 2020-05-12 | New
34619 | CNBFBSRA01-ROUTER | CE | OMA | CBL | Council Bluffs | CB - Metro Core | POInt | Yes | Yes | CBMC CE OMA CBL ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-03-15 | 2020-07-31 |  | SN-0686 | 2020-06-22 | Chg
34949 | Metro OTN-MAN-Ciena 6500 S32 | NE | CON | MAN | Manchester | Metro Transport | POInt | Yes | Yes | MTRN NE CON MAN OTN Deployment POR20 | Chassis | 1x Ciena 6500 S32 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | SN-0639 | 2020-06-05 | Chg
34949 | Metro OTN-MAN-Ciena 6500 S2 | NE | CON | MAN | Manchester | Metro Transport | POInt | Yes | Yes | MTRN NE CON MAN OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 4 | 2020-02-17 | 2020-07-31 | 2020-08-31 | SN-0639 | 2020-06-05 | Chg
34604 | GAINBSRA02.GA.AT-ROUTER | SE | GAN | GNS | Gainesville | CB - Metro Core | POInt | Yes | Yes | CBMC SE GAN GNS ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-03-15 | 2020-07-31 |  | SN-0737 | 2020-07-10 | Chg
35177 | MRTR OOB-New-DRA-OOB Server | VA | NVA | DRA | Dranesville | Metro Routers | POInt | Yes | Yes | MRTR VA NVA DRA OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-05-01 | 2020-07-31 | 2020-10-31 | SN-0158 | 2020-02-06 | Chg
59850 | RPHY MRTR-New-PWY-CIN-RPA-5110 | CA | SAN | PWY | Poway | R PHY | POInt | Yes | Yes | R PHY CA SAN PWY RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0487 | 2020-05-12 | New
59744 | RPHY MRTR-New-PNL-CIN-RPA-5110 | SW | ARZ | PNL | Pinal County | R PHY | POInt | Yes | Yes | R PHY SW ARZ PNL RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0487 | 2020-05-12 | New
34946 | Metro OTN-FWB-Ciena 6500 S14 | SE | GCT | FWB | Ft. Walton Beach with (Insite tower) | Metro Transport | POInt | Yes | Yes | MTRN SE GCT FWB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | SN-0665 | 2020-06-14 | Chg
34946 | Metro OTN-FWB-Ciena 6500 S2 | SE | GCT | FWB | Ft. Walton Beach with (Insite tower) | Metro Transport | POInt | Yes | Yes | MTRN SE GCT FWB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | SN-0665 | 2020-06-14 | Chg
59850 | RPHY MRTR-New-VST-CIN-RPA-5110 | CA | SAN | VST | Vista | R PHY | POInt | Yes | Yes | R PHY CA SAN VST RPHY Metro Augment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 8 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0606 | 2020-05-22 | Chg
59850 | RPHY MRTR-New-VST-CIN-ATX-OCML2 | CA | SAN | VST | Vista | R PHY | POInt | Yes | Yes | R PHY CA SAN VST RPHY Metro Augment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0606 | 2020-05-22 | Chg
59850 | RPHY MRTR-New-VST-CIN MGMT-2K | CA | SAN | VST | Vista | R PHY | POInt | Yes | Yes | R PHY CA SAN VST RPHY Metro Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0487 | 2020-05-12 | New
34622 | FED1BPRA01-ROUTER | CA | SAN | FED | Federal | CB - Metro Core | POInt | Yes | Yes | CBMC CA SAN FED ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-07-31 |  | SN-0654 | 2020-06-14 | Chg
34946 | Metro OTN-DES-Ciena 6500 S14 | SE | GCT | DES | Destin | Metro Transport | POInt | Yes | Yes | MTRN SE GCT DES OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | SN-0665 | 2020-06-14 | Chg
34946 | Metro OTN-DES-Ciena 6500 S2 | SE | GCT | DES | Destin | Metro Transport | POInt | Yes | Yes | MTRN SE GCT DES OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | SN-0665 | 2020-06-14 | Chg
34949 | Metro OTN-SFD-Ciena 6500 S14 | NE | CON | SFD | Stafford | Metro Transport | POInt | Yes | Yes | MTRN NE CON SFD OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | SN-0639 | 2020-06-05 | Chg
34949 | Metro OTN-SFD-Ciena 6500 S2 | NE | CON | SFD | Stafford | Metro Transport | POInt | Yes | Yes | MTRN NE CON SFD OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-07-31 | 2020-08-31 | SN-0639 | 2020-06-05 | Chg
34622 | ELCNBPRA01-ROUTER | CA | SAN | ELC | El Cajon | CB - Metro Core | POInt | Yes | Yes | CBMC CA SAN ELC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 1 | 2020-01-15 | 2020-07-31 |  | SN-0618 | 2020-06-05 | Chg
34622 | ELCNEWAA02-ROUTER | CA | SAN | ELC | El Cajon | CB - Metro Core | POInt | Yes | Yes | CBMC CA SAN ELC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 1 | 2020-02-15 | 2020-07-31 |  | SN-0618 | 2020-06-05 | Chg
34944 | MTRN-ELC- T5-02 | CA | SAN | ELC | El Cajon | Metro Transport | POInt | Yes | Yes | MTRN CA SAN ELC T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | SN-0562 | 2020-05-12 | New
59522 | CBR8 Chassis-3 | SW | LAS | OSB | Oso Blanca | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-05-01 | 2020-07-31 | 2020-07-31 | SN-0550 | 2020-05-12 | Chg
75245 | RPHY MRTR-New-WES-CIN-NOKIA-OCML | CE | OMA | WES | West (OM) | R PHY | POInt | Yes | Yes | R PHY CE OMA WES RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2021-03-31 | SN-0487 | 2020-05-12 | New
59744 | RPHY MRTR-New-OSB-CIN-RPA2-5110 | SW | LAS | OSB | Oso Blanca | R PHY | POInt | Yes | Yes | R PHY SW LAS OSB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 14 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0487 | 2020-05-12 | New
59744 | RPHY MRTR-New-OSB-CIN MGMT2-2K | SW | LAS | OSB | Oso Blanca | R PHY | POInt | Yes | Yes | R PHY SW LAS OSB RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 6 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0606 | 2020-05-22 | Chg
59744 | RPHY MRTR-New-OSB-CIN-ATX-OCML | SW | LAS | OSB | Oso Blanca | R PHY | POInt | Yes | Yes | R PHY SW LAS OSB RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 60 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0606 | 2020-05-22 | New
59850 | RPHY MRTR-New-OCE-CIN-ATX-OCML2 | CA | SAN | OCE | Oceanside | R PHY | POInt | Yes | Yes | R PHY CA SAN OCE RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0487 | 2020-05-12 | New
59850 | RPHY MRTR-New-OCE-RPA-5110 | CA | SAN | OCE | Oceanside | R PHY | POInt | Yes | Yes | R PHY CA SAN OCE RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 6 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0487 | 2020-05-12 | New
59850 | RPHY MRTR-New-OCE-CIN-RPA-5110 | CA | SAN | OCE | Oceanside | R PHY | POInt | Yes | Yes | R PHY CA SAN OCE RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 6 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0606 | 2020-05-22 | New
59850 | RPHY MRTR-New-OCE-CIN MGMT-2K | CA | SAN | OCE | Oceanside | R PHY | POInt | Yes | Yes | R PHY CA SAN OCE RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0606 | 2020-05-22 | New
35011 | Metro OTN-FST-Ciena 6500 S2 | VA | NVA | FST | Fairfax Station | Metro Transport | POInt | Yes | Yes | MTRN VA NVA FST OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-07-31 | 2020-08-31 | SN-0639 | 2020-06-05 | Chg
35011 | Metro OTN-FST-Ciena 6500 S14 | VA | NVA | FST | Fairfax Station | Metro Transport | POInt | Yes | Yes | MTRN VA NVA FST OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | SN-0639 | 2020-06-05 | Chg
34948 | Metro OTN-KNN-Ciena 6500 S14 | SE | NOR | KNN | Kenner | Metro Transport | POInt | Yes | Yes | MTRN SE NOR KNN OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | SN-0665 | 2020-06-14 | Chg
34948 | Metro OTN-KNN-Ciena 6500 S2 | SE | NOR | KNN | Kenner | Metro Transport | POInt | Yes | Yes | MTRN SE NOR KNN OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | SN-0665 | 2020-06-14 | Chg
35010 | Metro OTN-NEH-Ciena 6500 S14 | CE | OKC | NEH | North East | Metro Transport | POInt | Yes | Yes | MTRN CE OKC NEH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | SN-0639 | 2020-06-05 | Chg
35010 | Metro OTN-NEH-Ciena 6500 S2 | CE | OKC | NEH | North East | Metro Transport | POInt | Yes | Yes | MTRN CE OKC NEH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-07-31 | 2020-08-31 | SN-0639 | 2020-06-05 | Chg
34946 | Metro OTN-NCV-Ciena 6500 S14 | SE | GCT | NCV | Niceville | Metro Transport | POInt | Yes | Yes | MTRN SE GCT NCV OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | SN-0665 | 2020-06-14 | Chg
34946 | Metro OTN-NCV-Ciena 6500 S2 | SE | GCT | NCV | Niceville | Metro Transport | POInt | Yes | Yes | MTRN SE GCT NCV OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | SN-0665 | 2020-06-14 | Chg
59744 | RPHY MRTR-New-MCD-CIN-RPA-5110 | SW | ARZ | MCD | McDowell | R PHY | POInt | Yes | Yes | R PHY SW ARZ MCD RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0487 | 2020-05-12 | New
34949 | Metro OTN-ENF-Ciena 6500 S2 | NE | CON | ENF | Enfield | Metro Transport | POInt | Yes | Yes | MTRN NE CON ENF OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-02-17 | 2020-07-31 | 2020-08-31 | SN-0639 | 2020-06-05 | Chg
34949 | Metro OTN-ENF-Ciena 6500 S14 | NE | CON | ENF | Enfield | Metro Transport | POInt | Yes | Yes | MTRN NE CON ENF OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | SN-0639 | 2020-06-05 | Chg
34946 | Metro OTN-GRY-Ciena 6500 S14 | SE | MGA | GRY | Gray | Metro Transport | POInt | Yes | Yes | MTRN SE MGA GRY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | SN-0665 | 2020-06-14 | Chg
34946 | Metro OTN-GRY-Ciena 6500 S2 | SE | MGA | GRY | Gray | Metro Transport | POInt | Yes | Yes | MTRN SE MGA GRY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | SN-0665 | 2020-06-14 | Chg
75246 | R PHY_CCAP_SPC_RPHY CCAP Licenses_Q2 NC Video | SE | BTR | SPC | Pecue | R PHY | POInt | Yes | Yes | R PHY SE BTR SPC RPHY - CCAP Initial Deployment POR20 | License | CCAP license | 136 | 2020-03-30 | 2020-07-31 | 2020-07-31 | SN-0742 | 2020-07-10 | Chg
75246 | R PHY_CCAP_SPC_OTDR_1 | SE | BTR | SPC | Pecue | R PHY | POInt | Yes | Yes | R PHY SE BTR SPC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-07-31 |  | SN-0742 | 2020-07-10 | Chg
75246 | R PHY_CCAP_SPC_Boundary_Clocks_44119 | SE | BTR | SPC | Pecue | R PHY | POInt | Yes | Yes | R PHY SE BTR SPC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-03-05 | 2020-07-31 | 2020-07-31 | SN-0742 | 2020-07-10 | Chg
75246 | R PHY_CCAP_SPC_RPHY Bundled Solution V3_44119 | SE | BTR | SPC | Pecue | R PHY | POInt | Yes | Yes | R PHY SE BTR SPC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-03-05 | 2020-07-31 | 2020-07-31 | SN-0742 | 2020-07-10 | Chg
35177 | MRTR SLR-New-VBC-SLR-ASR9906 | VA | HRD | VBC | Virginia Beach | Metro Routers | POInt | Yes | Yes | MRTR VA HRD VBC SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-12-31 | SN-1037 | 2020-11-06 | Chg
35177 | MRTR SLR-New-OCN-SLR-ASR9906 | VA | HRD | OCN | Oceana | Metro Routers | POInt | Yes | Yes | MRTR VA HRD OCN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-12-31 | SN-1037 | 2020-11-06 | Chg
34948 | Metro OTN-ALG-Ciena 6500 S14 | SE | NOR | ALG | Algiers | Metro Transport | POInt | Yes | Yes | MTRN SE NOR ALG OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | SN-0665 | 2020-06-14 | Chg
34948 | Metro OTN-ALG-Ciena 6500 S2 | SE | NOR | ALG | Algiers | Metro Transport | POInt | Yes | Yes | MTRN SE NOR ALG OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | SN-0665 | 2020-06-14 | Chg
59850 | RPHY MRTR-Growth-CHU-CIN-RPA2-5110 | CA | SAN | CHU | Chula Vista | R PHY | POInt | Yes | Yes | R PHY CA SAN CHU RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 9 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0606 | 2020-05-22 | Chg
59850 | RPHY MRTR-New-CHU-CIN-ATX-OCML2 | CA | SAN | CHU | Chula Vista | R PHY | POInt | Yes | Yes | R PHY CA SAN CHU RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0606 | 2020-05-22 | Chg
59850 | RPHY MRTR-New-CHU-CIN MGMT-2K | CA | SAN | CHU | Chula Vista | R PHY | POInt | Yes | Yes | R PHY CA SAN CHU RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0487 | 2020-05-12 | New
74648 | RPHY MRTR-New-FBG-CIN-RPA-5110 | VA | NVA | FBG | Fredericksburg | R PHY | POInt | Yes | Yes | R PHY VA NVA FBG RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0487 | 2020-05-12 | Chg
74648 | RPHY MRTR-Growth-FBG-CIN MGMT-2K | VA | NVA | FBG | Fredericksburg | R PHY | POInt | Yes | Yes | R PHY VA NVA FBG RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0487 | 2020-05-12 | Chg
74648 | RPHY MRTR-New-FBG-CIN-ATX-OCML | VA | NVA | FBG | Fredericksburg | R PHY | POInt | Yes | Yes | R PHY VA NVA FBG RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0612 | 2020-05-29 | New
59744 | RPHY MRTR-New-SSC-CIN-RPA-5110 | SW | ARZ | SSC | South Scottsdale | R PHY | POInt | Yes | Yes | R PHY SW ARZ SSC RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 8 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0487 | 2020-05-12 | New
34949 | Metro OTN-MER-Ciena 6500 S14 | NE | CON | MER | Meriden | Metro Transport | POInt | Yes | Yes | MTRN NE CON MER OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | SN-0639 | 2020-06-05 | Chg
34949 | Metro OTN-MER-Ciena 6500 S2 | NE | CON | MER | Meriden | Metro Transport | POInt | Yes | Yes | MTRN NE CON MER OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-07-31 | 2020-08-31 | SN-0639 | 2020-06-05 | Chg
35173 | MRTR SLR-New-HEN-Nexus Th-2248 | SW | LAS | HEN | Henderson | Metro Routers | POInt | Yes | Yes | MRTR SW LAS HEN Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-07-31 | SN-0616 | 2020-05-29 | New
35175 | MRTR SLR-New-PRV-SLR-ASR9906 | NE | RHD | PRV | Providence | Metro Routers | POInt | Yes | Yes | MRTR NE RHD PRV SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-12-31 | SN-1037 | 2020-11-06 | New
35177 | MRTR OOB-New-FST-OOB Server | VA | NVA | FST | Fairfax Station | Metro Routers | POInt | Yes | Yes | MRTR VA NVA FST OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-05-01 | 2020-07-31 | 2020-10-31 | SN-0158 | 2020-02-06 | Chg
59744 | RPHY MRTR-New-ERN-CIN-MGMT-2K | SW | LAS | ERN | Ernest May | R PHY | POInt | Yes | Yes | R PHY SW LAS ERN RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 3 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0606 | 2020-05-22 | New
75842 | CA SAN CHU Backbone Growth Edge Augment POR20 | CA | SAN | CHU | Chula Vista | MTC Fiber and Rack Management | POInt | Yes | Yes | MVFM CA SAN CHU OSP Migration Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-05-06 | 2020-07-31 | 2020-07-31 | SN-0793 | 2020-08-20 | Chg
34944 | MTRN-FED- T5-02 | CA | SAN | FED | Federal | Metro Transport | POInt | Yes | Yes | MTRN CA SAN FED T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | SN-0562 | 2020-05-12 | New
34944 | MTRN-FED- T5-03 | CA | SAN | FED | Federal | Metro Transport | POInt | Yes | Yes | MTRN CA SAN FED T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | SN-0562 | 2020-05-12 | New
35173 | MRTR SLR-New-ERN-Nexus Th-2248 | SW | LAS | ERN | Ernest May | Metro Routers | POInt | Yes | Yes | MRTR SW LAS ERN Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-07-31 | SN-0616 | 2020-05-29 | New
34946 | Metro OTN-WRB-Ciena 6500 S14 | SE | MGA | WRB | Warner Robins | Metro Transport | POInt | Yes | Yes | MTRN SE MGA WRB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | SN-0665 | 2020-06-14 | Chg
34946 | Metro OTN-WRB-Ciena 6500 S2 | SE | MGA | WRB | Warner Robins | Metro Transport | POInt | Yes | Yes | MTRN SE MGA WRB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | SN-0665 | 2020-06-14 | Chg
59850 | RPHY MRTR-New-IRV-CIN-RPA2-5110 | CA | ORG | IRV | Irvine | R PHY | POInt | Yes | Yes | R PHY CA ORG IRV RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 6 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0487 | 2020-05-12 | New
35177 | MRTR OOB-New-FLK-OOB Server | VA | NVA | FLK | Fair Lakes | Metro Routers | POInt | Yes | Yes | MRTR VA NVA FLK OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-05-01 | 2020-07-31 | 2020-10-31 | SN-0158 | 2020-02-06 | Chg
34949 | Metro OTN-GLB-Ciena 6500 S2 | NE | CON | GLB | Glastonbury | Metro Transport | POInt | Yes | Yes | MTRN NE CON GLB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-07-31 | 2020-08-31 | SN-0639 | 2020-06-05 | Chg
34949 | Metro OTN-GLB-Ciena 6500 S14 | NE | CON | GLB | Glastonbury | Metro Transport | POInt | Yes | Yes | MTRN NE CON GLB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | SN-0639 | 2020-06-05 | Chg
34947 | MTRN-T5-BLU-01 | SW | LAS | BLU | Blue Diamond | Metro Transport | POInt | Yes | Yes | MTRN SW LAS BLU T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | SN-0562 | 2020-05-12 | New
34945 | MTRN-OMM- T5-01 | CE | OMA | OMM | Omaha | Metro Transport | POInt | Yes | Yes | MTRN CE OMA OMM T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | SN-0562 | 2020-05-12 | New
59850 | RPHY MRTR-New-AVJ-CIN-RPA2-5110 | CA | ORG | AVJ | Aliso Viejo | R PHY | POInt | Yes | Yes | R PHY CA ORG AVJ RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 16 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0606 | 2020-05-22 | Chg
59850 | RPHY MRTR-New-AVJ-CIN-ATX-OCML2 | CA | ORG | AVJ | Aliso Viejo | R PHY | POInt | Yes | Yes | R PHY CA ORG AVJ RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0487 | 2020-05-12 | New
34948 | Metro OTN-LUL-Ciena 6500 S14 | SE | NOR | LUL | Luling | Metro Transport | POInt | Yes | Yes | MTRN SE NOR LUL OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | SN-0665 | 2020-06-14 | Chg
34948 | Metro OTN-LUL-Ciena 6500 S2 | SE | NOR | LUL | Luling | Metro Transport | POInt | Yes | Yes | MTRN SE NOR LUL OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | SN-0665 | 2020-06-14 | Chg
34944 | MTRN-RSM- T5-03 | CA | ORG | RSM | Rancho Santa Margarita | Metro Transport | POInt | Yes | Yes | MTRN CA ORG RSM T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | SN-0562 | 2020-05-12 | New
35169 | MRTR SLR-New-DGL-SLR-ASR9906 | SW | ARZ | DGL | Douglas | Metro Routers | POInt | Yes | Yes | MRTR SW ARZ DGL SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-12-31 | SN-1037 | 2020-11-06 | New
34948 | Metro OTN-CLR-Ciena 6500 S14 | SE | NOR | CLR | Metairie | Metro Transport | POInt | Yes | Yes | MTRN SE NOR CLR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | SN-0665 | 2020-06-14 | Chg
34948 | Metro OTN-CLR-Ciena 6500 S2 | SE | NOR | CLR | Metairie | Metro Transport | POInt | Yes | Yes | MTRN SE NOR CLR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | SN-0665 | 2020-06-14 | Chg
34622 | CB Transport - New Router Escondido - ESC - Optics | CA | SAN | ESC | Escondido | CB - Metro Core | POInt | Yes | Yes | CBMC CA SAN ESC Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-03-15 | 2020-07-31 |  | SN-0701 | 2020-07-02 | Chg
59744 | RPHY MRTR-New-VLY-CIN-RPA-5110 | SW | LAS | VLY | Valley | R PHY | POInt | Yes | Yes | R PHY SW LAS VLY RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0487 | 2020-05-12 | New
59744 | RPHY MRTR-New-ALI-CIN-RPA-5110 | SW | LAS | ALI | Aliante | R PHY | POInt | Yes | Yes | R PHY SW LAS ALI RPHY Metro Augment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 5 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0606 | 2020-05-22 | Chg
35173 | MRTR SLR-New-BLU-Nexus Th-2248 | SW | LAS | BLU | Blue Diamond | Metro Routers | POInt | Yes | Yes | MRTR SW LAS BLU Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-07-31 | SN-0616 | 2020-05-29 | New
74548 | R PHY_CCAP_LTF_RPHY Bundled Solution V3_44119 | VA | HRD | LTF | Lightfoot | R PHY | POInt | Yes | Yes | R PHY VA HRD LTF RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-04-28 | 2020-07-31 |  | SN-0605 | 2020-05-22 | Chg
74548 | R PHY_CCAP_LTF_Boundary_Clocks_44119 | VA | HRD | LTF | Lightfoot | R PHY | POInt | Yes | Yes | R PHY VA HRD LTF RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-05-31 | 2020-07-31 |  | SN-0605 | 2020-05-22 | Chg
34949 | Metro OTN-RKH-Ciena 6500 S14 | NE | CON | RKH | Rocky Hill | Metro Transport | POInt | Yes | Yes | MTRN NE CON RKH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | SN-0639 | 2020-06-05 | Chg
34949 | Metro OTN-RKH-Ciena 6500 S2 | NE | CON | RKH | Rocky Hill | Metro Transport | POInt | Yes | Yes | MTRN NE CON RKH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-07-31 | 2020-08-31 | SN-0639 | 2020-06-05 | Chg
34948 | Metro OTN-NOE-Ciena 6500 S14 | SE | NOR | NOE | New Orleans East | Metro Transport | POInt | Yes | Yes | MTRN SE NOR NOE OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | SN-0665 | 2020-06-14 | Chg
34948 | Metro OTN-NOE-Ciena 6500 S2 | SE | NOR | NOE | New Orleans East | Metro Transport | POInt | Yes | Yes | MTRN SE NOR NOE OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | SN-0665 | 2020-06-14 | Chg
59744 | RPHY MRTR-New-NSC-CIN-RPA-5110 | SW | ARZ | NSC | North Scottsdale | R PHY | POInt | Yes | Yes | R PHY SW ARZ NSC RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0487 | 2020-05-12 | New
59744 | RPHY MRTR-New-CHD-CIN-RPA-5110 | SW | ARZ | CHD | Chandler | R PHY | POInt | Yes | Yes | R PHY SW ARZ CHD RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 8 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0606 | 2020-05-22 | Chg
59744 | RPHY MRTR-New-CHD-CIN-Nokia-OCML2 | SW | ARZ | CHD | Chandler | R PHY | POInt | Yes | Yes | R PHY SW ARZ CHD RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 40 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0487 | 2020-05-12 | New
59744 | RPHY MRTR-New-CHD-CIN-DPA-5200 | SW | ARZ | CHD | Chandler | R PHY | POInt | Yes | Yes | R PHY SW ARZ CHD RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0487 | 2020-05-12 | New
59744 | RPHY MRTR-New-CHD-CIN MGMT-2K | SW | ARZ | CHD | Chandler | R PHY | POInt | Yes | Yes | R PHY SW ARZ CHD RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0606 | 2020-05-22 | Chg
34948 | Metro OTN-DST-Ciena 6500 S14 | SE | NOR | DST | Destrehan | Metro Transport | POInt | Yes | Yes | MTRN SE NOR DST OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | SN-0665 | 2020-06-14 | Chg
34948 | Metro OTN-DST-Ciena 6500 S2 | SE | NOR | DST | Destrehan | Metro Transport | POInt | Yes | Yes | MTRN SE NOR DST OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | SN-0665 | 2020-06-14 | Chg
75245 | RPHY MRTR-New-WIC-CIN-NOKIA-OCML | CE | KAN | WIC | Wichita | R PHY | POInt | Yes | Yes | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 20 | 2020-05-15 | 2020-07-31 | 2020-09-30 | SN-0612 | 2020-05-29 | Chg
75245 | RPHY MRTR-New-WIC-CIN-RPA-5110 | CE | KAN | WIC | Wichita | R PHY | POInt | Yes | Yes | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 5 | 2020-05-15 | 2020-07-31 | 2020-09-30 | SN-0612 | 2020-05-29 | Chg
59744 | RPHY MRTR-New-FWL-CIN-RPA-5110 | SW | ARZ | FWL | Fowler | R PHY | POInt | Yes | Yes | R PHY SW ARZ FWL RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 8 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0606 | 2020-05-22 | Chg
59744 | RPHY MRTR-New-FWL-CIN-Nokia-OCML2 | SW | ARZ | FWL | Fowler | R PHY | POInt | Yes | Yes | R PHY SW ARZ FWL RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 20 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0487 | 2020-05-12 | New
59744 | RPHY MRTR-New-FWL-CIN MGMT-2K | SW | ARZ | FWL | Fowler | R PHY | POInt | Yes | Yes | R PHY SW ARZ FWL RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0606 | 2020-05-22 | Chg
35175 | MRTR SLR-New-PTH-SLR-ASR9906 | NE | RHD | PTH | Portsmouth (RI) | Metro Routers | POInt | Yes | Yes | MRTR NE RHD PTH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-01 | 2020-07-31 | 2020-09-30 | SN-0555 | 2020-05-12 | Chg
34947 | MTRN-VLY- T5-01 | SW | LAS | VLY | Valley | Metro Transport | POInt | Yes | Yes | MTRN SW LAS VLY T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | SN-0562 | 2020-05-12
35177 | MRTR OOB-New-TCR-OOB Server | VA | NVA | TCR | Tysons Corner | Metro Routers | POInt | Yes | Yes | MRTR VA NVA TCR OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-05-01 | 2020-07-31 | 2020-10-31 | SN-0158 | 2020-02-06 | Chg
34946 | Metro OTN-HLT-Ciena 6500 S14 | SE | MGA | HLT | Holt | Metro Transport | POInt | Yes | Yes | MTRN SE MGA HLT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | SN-0665 | 2020-06-14 | Chg
34946 | Metro OTN-HLT-Ciena 6500 S2 | SE | MGA | HLT | Holt | Metro Transport | POInt | Yes | Yes | MTRN SE MGA HLT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | SN-0665 | 2020-06-14 | Chg
34947 | MTRN-OSB- T5-02 | SW | LAS | OSB | Oso Blanca | Metro Transport | POInt | Yes | Yes | MTRN SW LAS OSB DWDM Deployment POR19 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | SN-0562 | 2020-05-12 | New
34623 | SSCTSYSA01-ROUTER | SW | ARZ | SSC | South Scottsdale | CB - Metro Core | POInt | Yes | Yes | CBMC SW ARZ SSC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-06-15 | 2020-07-31 |  | SN-0618 | 2020-06-05 | Chg
59850 | RPHY MRTR-New-SAB-CIN MGMT-2K | CA | SAB | SAB | Santa Barbara | R PHY | POInt | Yes | Yes | R PHY CA SAB SAB RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 12 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0487 | 2020-05-12 | Chg
59850 | RPHY MRTR-New-SAB-CIN-DPA-5200 (100G DPIC) | CA | SAB | SAB | Santa Barbara | R PHY | POInt | Yes | Yes | R PHY CA SAB SAB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0487 | 2020-05-12 | Chg
59850 | RPHY MRTR-New-SAB-CIN-RPA-5110 | CA | SAB | SAB | Santa Barbara | R PHY | POInt | Yes | Yes | R PHY CA SAB SAB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 24 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0487 | 2020-05-12 | Chg
59850 | RPHY MRTR-New-SAB-CIN-ATX-OCML | CA | SAB | SAB | Santa Barbara | R PHY | POInt | Yes | Yes | R PHY CA SAB SAB RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 100 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0606 | 2020-05-22 | Chg
59850 | RPHY MRTR-New-FED-CIN-ATX-OCML2 | CA | SAN | FED | Federal | R PHY | POInt | Yes | Yes | R PHY CA SAN FED RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0606 | 2020-05-22 | Chg
59850 | RPHY MRTR-New-FED-CIN-RPA-5110 | CA | SAN | FED | Federal | R PHY | POInt | Yes | Yes | R PHY CA SAN FED RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 14 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0606 | 2020-05-22 | Chg
59850 | RPHY MRTR-New-FED-CIN-DPA-5200 | CA | SAN | FED | Federal | R PHY | POInt | Yes | Yes | R PHY CA SAN FED RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0487 | 2020-05-12 | New
59850 | RPHY MRTR-New-FED-CIN MGMT-2K | CA | SAN | FED | Federal | R PHY | POInt | Yes | Yes | R PHY CA SAN FED RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0487 | 2020-05-12 | New
34949 | Metro OTN-STN-Ciena 6500 S14 | NE | CON | STN | Southington | Metro Transport | POInt | Yes | Yes | MTRN NE CON STN OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | SN-0639 | 2020-06-05 | Chg
34949 | Metro OTN-STN-Ciena 6500 S2 | NE | CON | STN | Southington | Metro Transport | POInt | Yes | Yes | MTRN NE CON STN OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-02-17 | 2020-07-31 | 2020-08-31 | SN-0639 | 2020-06-05 | Chg
59745 | R PHY_CCAP_ELC_RPHY Bundled Solution V3_43937 | CA | SAN | ELC | El Cajon | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN ELC RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-05-01 | 2020-07-31 | 2020-07-31 | SN-0550 | 2020-05-12 | Chg
59850 | RPHY MRTR-New-ORG-CIN-RPA-5110 | CA | ORG | ORG | Orange | R PHY | POInt | Yes | Yes | R PHY CA ORG ORG RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0487 | 2020-05-12 | New
35172 | MRTR SLR-New-MCN-SLR-ASR9906 | SE | MGA | MCN | Macon | Metro Routers | POInt | Yes | Yes | MRTR SE MGA MCN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-12-31 | SN-1037 | 2020-11-06 | New
35177 | MRTR OOB-New-MFD-OOB Server | VA | NVA | MFD | Merrifield | Metro Routers | POInt | Yes | Yes | MRTR VA NVA MFD OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 4 | 2020-05-01 | 2020-07-31 | 2020-10-31 | SN-0158 | 2020-02-06 | Chg
34943 | MTRN-FWL- T5-02 | SW | ARZ | FWL | Fowler | Metro Transport | POInt | Yes | Yes | MTRN SW ARZ FWL T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | SN-0562 | 2020-05-12
74648 | RPHY MRTR-New-VBC-CIN-ATX-OCML | VA | HRD | VBC | Virginia Beach | R PHY | POInt | Yes | No | R PHY VA HRD VBC R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 24 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0487 | 2020-05-12 | New
34642 | BWM OKC DOCSIS Expansion 96 MHz | CE | OKC | CHO | Choctaw | Bandwidth Management | POInt | Yes | No | BWM CE OKC CHO DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-31 | 2020-10-30 | SN-0558 | 2020-05-12 | New
59850 | RPHY MRTR-New-PAV2-CIN-RPA-5110 | CA | ORG | PAV | Palos Verdes | R PHY | POInt | Yes | No | R PHY CA ORG PAV R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 5 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0487 | 2020-05-12 | New
59850 | RPHY MRTR-New-PAV-CIN-ATX-OCML2 | CA | ORG | PAV | Palos Verdes | R PHY | POInt | Yes | No | R PHY CA ORG PAV R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0487 | 2020-05-12 | New
59850 | RPHY MRTR-New-PAV-CIN MGMT-2K | CA | ORG | PAV | Palos Verdes | R PHY | POInt | Yes | No | R PHY CA ORG PAV R PHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0487 | 2020-05-12 | New
59744 | RPHY MRTR-New-TEN-CIN-RPA-5110 | SW | LAS | TEN | Tenaya | R PHY | POInt | Yes | No | R PHY SW LAS TEN R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 15 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0606 | 2020-05-22 | Chg
59744 | RPHY MRTR-New-TEN-CIN-ATX-OCML | SW | LAS | TEN | Tenaya | R PHY | POInt | Yes | No | R PHY SW LAS TEN R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0487 | 2020-05-12 | New
59744 | RPHY MRTR-New-TEN-CIN MGMT-2K | SW | LAS | TEN | Tenaya | R PHY | POInt | Yes | No | R PHY SW LAS TEN R PHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 3 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0606 | 2020-05-22 | Chg
75788 | CDN Deploy 12 | CE | KAN | WIC | Wichita | CDN | POInt | Yes | No | CDN CE KAN WIC Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-06-01 | 2020-07-31 | 2020-08-14 | SN-0285 | 2020-02-24 | Chg
59744 | RPHY MRTR-New-BLU-CIN-RPA2-5110 | SW | LAS | BLU | Blue Diamond | R PHY | POInt | Yes | No | R PHY SW LAS BLU R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 8 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0606 | 2020-05-22 | Chg
59744 | RPHY MRTR-New-AVJ-CIN MGMT2-2K | SW | LAS | BLU | Blue Diamond | R PHY | POInt | Yes | No | R PHY SW LAS BLU R PHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0606 | 2020-05-22 | Chg
59744 | RPHY MRTR-New-BLU-CIN-ATX-OCML2 | SW | LAS | BLU | Blue Diamond | R PHY | POInt | Yes | No | R PHY SW LAS BLU R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 40 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0606 | 2020-05-22 | New
75663 | V2B SE NAT AT2 Terrestrial Mezzanine Contribution Augment POR20 | COR | NAT | AT2 | Atlanta - Equinix (cage 50015) | V2B | POInt | Yes | No | V2B SE NAT AT2 Terrestrial Mezzanine Contribution Augment POR20 | Labor | Contribution | 1 | 2020-06-06 | 2020-07-31 | 2020-12-31 | SN-0801 | 2020-07-31 | Chg
78067 | SolutionIP | SW | LAS | TEN | Tenaya | Hospitality Network | POInt | Yes | No | HN SW LAS TEN SolutionIP Server Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-07-31 |  | SB-0196 | 2020-08-14 | Chg
59744 | RPHY MRTR-New-PEO-CIN-RPA2-5110 | SW | ARZ | PEO | Peoria | R PHY | POInt | Yes | No | R PHY SW ARZ PEO R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 8 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0606 | 2020-05-22 | Chg
59744 | RPHY MRTR-New-PEO-CIN-Nokia2-OCML | SW | ARZ | PEO | Peoria | R PHY | POInt | Yes | No | R PHY SW ARZ PEO R PHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 20 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0487 | 2020-05-12 | New
59744 | RPHY MRTR-New-PEO-CIN MGMT-2K | SW | ARZ | PEO | Peoria | R PHY | POInt | Yes | No | R PHY SW ARZ PEO R PHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0606 | 2020-05-22 | Chg
75844 | NE CON STN ALU Nokia Fiber Augment POR20 | NE | CON | STN | Southington | MTC Fiber and Rack Management | POInt | Yes | No | MVFM NE CON STN ALU Nokia Fiber Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-07-31 | 2020-08-20 | SN-0793 | 2020-08-20 | Chg
35175 | MRTR SLR-New-EXT-SLR-ASR9906 | NE | RHD | EXT | Exeter | Metro Routers | POInt | Yes | Yes | MRTR NE RHD EXT SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-01 | 2020-07-31 | 2020-10-31 | SN-0555 | 2020-05-12 | Chg
34947 | MTRN-TEN- T5-05 | SW | LAS | TEN | Tenaya | Metro Transport | POInt | Yes | Yes | MTRN SW LAS TEN T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | SN-0562 | 2020-05-12 | New
34622 | El Cajon-OCML-IXR | CA | SAN | ELC | El Cajon | CB - Metro Core | POInt | Yes | Yes | CBMC CA SAN ELC OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-07-31 |  | SN-0618 | 2020-06-05 | Chg
59850 | RPHY MRTR-New-ESC-CIN-RPA-5110 | CA | SAN | ESC | Escondido | R PHY | POInt | Yes | Yes | R PHY CA SAN ESC RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0606 | 2020-05-22 | Chg
59850 | RPHY MRTR-New-ESC-CIN-ATX-OCML | CA | SAN | ESC | Escondido | R PHY | POInt | Yes | Yes | R PHY CA SAN ESC RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 20 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0487 | 2020-05-12 | New
59850 | RPHY MRTR-New-ESC-CIN MGMT-2K | CA | SAN | ESC | Escondido | R PHY | POInt | Yes | Yes | R PHY CA SAN ESC RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0487 | 2020-05-12 | New
35177 | MRTR SLR-New-CHS-SLR-ASR9906 | VA | HRD | CHS | Chesapeake | Metro Routers | POInt | Yes | Yes | MRTR VA HRD CHS SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-12-31 | SN-1037 | 2020-11-06 | Chg
35173 | MRTR NCS-Growth-ALI-CIN- 2K | SW | LAS | ALI | Aliante | Metro Routers | POInt | Yes | Yes | MRTR SW LAS ALI Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0608 | 2020-05-23 | New
35173 | MRTR NCS-Growth-ALI-Nexus Th- 2248 | SW | LAS | ALI | Aliante | Metro Routers | POInt | Yes | Yes | MRTR SW LAS ALI Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-07-31 | SN-0616 | 2020-05-29 | New
34943 | MTRN-TUC- T5-02 | SW | ARZ | TUC | Tucson | Metro Transport | POInt | Yes | Yes | MTRN SW ARZ TUC T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | SN-0562 | 2020-05-12 | New
35173 | MRTR NCS-Growth-VLY-CIN- 2K | SW | LAS | VLY | Valley | Metro Routers | POInt | Yes | Yes | MRTR SW LAS VLY Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0608 | 2020-05-23 | New
35173 | MRTR NCS-Nexus Th-VLY-2248 | SW | LAS | VLY | Valley | Metro Routers | POInt | Yes | Yes | MRTR SW LAS VLY Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-07-31 | SN-0616 | 2020-05-29 | New
34948 | Metro OTN-MCY-Ciena 6500 S14 | SE | NOR | MCY | Mid-City | Metro Transport | POInt | Yes | Yes | MTRN SE NOR MCY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | SN-0665 | 2020-06-14 | Chg
34948 | Metro OTN-MCY-Ciena 6500 S2 | SE | NOR | MCY | Mid-City | Metro Transport | POInt | Yes | Yes | MTRN SE NOR MCY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-04-15 | 2020-07-31 | 2020-09-30 | SN-0665 | 2020-06-14 | Chg
34949 | Metro OTN-GRB-Ciena 6500 S2 | NE | CON | GRB | Granby | Metro Transport | POInt | Yes | Yes | MTRN NE CON GRB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-07-31 | 2020-08-31 | SN-0639 | 2020-06-05 | Chg
34949 | Metro OTN-GRB-Ciena 6500 S14 | NE | CON | GRB | Granby | Metro Transport | POInt | Yes | Yes | MTRN NE CON GRB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | SN-0639 | 2020-06-05 | Chg
78101 | HY VA HRD PTM Voice HDT Decom POR20 | VA | HRD | PTM | Portsmouth (VA) | Voice Decom and Refortification | POInt | Yes | Yes | VCDR VA HRD PTM Voice HDT Decom POR20 | Labor | No Equipment | 1 | 2020-05-20 | 2020-07-31 |  | SN-0697 | 2020-07-10 | Chg
34946 | Metro OTN-CRV-Ciena 6500 S14 | SE | GCT | CRV | Crestview | Metro Transport | POInt | Yes | Yes | MTRN SE GCT CRV OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | SN-0665 | 2020-06-14 | Chg
34946 | Metro OTN-CRV-Ciena 6500 S2 | SE | GCT | CRV | Crestview | Metro Transport | POInt | Yes | Yes | MTRN SE GCT CRV OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | SN-0665 | 2020-06-14 | Chg
35177 | MRTR SLR-New-NWP-SLR-ASR9906 | VA | HRD | NWP | Newport News | Metro Routers | POInt | Yes | Yes | MRTR VA HRD NWP SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-12-31 | SN-1037 | 2020-11-06 | Chg
34619 | sr01.bra.tul.ok-ROUTER | CE | TUL | BRD | Braden | CB - Metro Core | POInt | Yes | Yes | CBMC CE TUL BRD ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-07-31 |  | SN-0686 | 2020-06-22 | Chg
34642 | BWM OKC DOCSIS Expansion 192 MHz | CE | OKC | CHO | Choctaw | Bandwidth Management | POInt | Yes | No | BWM CE OKC CHO DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-31 | 2021-01-20 | SN-0558 | 2020-05-12 | New
74648 | RPHY MRTR-New-LTF-CIN-RPA-5110 | VA | HRD | LTF | Lightfoot | R PHY | POInt | Yes | Yes | R PHY VA HRD LTF RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0487 | 2020-05-12 | Chg
75245 | RPHY MRTR-New-ONA-CIN-NOKIA-OCML | CE | OMA | ONA | North (OM) | R PHY | POInt | Yes | Yes | R PHY CE OMA ONA RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2021-03-31 | SN-0786 | 2020-07-27 | Chg
59744 | RPHY MRTR-New-BEL-CIN-RPA-5110 | SW | ARZ | BEL | Bell | R PHY | POInt | Yes | Yes | R PHY SW ARZ BEL RPHY Metro Augment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 8 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0606 | 2020-05-22 | Chg
59744 | RPHY MRTR-New-BEL-CIN MGMT-2K | SW | ARZ | BEL | Bell | R PHY | POInt | Yes | Yes | R PHY SW ARZ BEL RPHY Metro Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0606 | 2020-05-22 | Chg
75243 | RPHY MRTR-New-SPC-CIN-ATX-OCML | SE | BTR | SPC | Pecue | R PHY | POInt | Yes | Yes | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0741 | 2020-07-10 | Chg
75243 | RPHY MRTR-New-SPC-CIN Exfo-Switch | SE | BTR | SPC | Pecue | R PHY | POInt | Yes | Yes | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-07-31 | 2020-06-30 | SN-0741 | 2020-07-10 | Chg
75243 | RPHY MRTR-Growth-SPC-CIN MGMT-2K | SE | BTR | SPC | Pecue | R PHY | POInt | Yes | Yes | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-02-15 | 2020-07-31 | 2020-06-30 | SN-0741 | 2020-07-10 | Chg
75243 | RPHY MRTR-New-SPC-CIN-DPA-5200 (100G DPIC) | SE | BTR | SPC | Pecue | R PHY | POInt | Yes | Yes | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-02-15 | 2020-07-31 | 2020-06-30 | SN-0741 | 2020-07-10 | Chg
75243 | RPHY MRTR-New-SPC-CIN-RPA-5110 | SE | BTR | SPC | Pecue | R PHY | POInt | Yes | Yes | R PHY SE BTR SPC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-06-30 | SN-0741 | 2020-07-10 | Chg
74648 | RPHY MRTR-New-LTF-CIN-ATX-OCML | VA | HRD | LTF | Lightfoot | R PHY | POInt | Yes | Yes | R PHY VA HRD LTF RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0612 | 2020-05-29 | New
74648 | RPHY MRTR-Growth-LTF-CIN MGMT-2K | VA | HRD | LTF | Lightfoot | R PHY | POInt | Yes | Yes | R PHY VA HRD LTF RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0487 | 2020-05-12 | Chg
78067 | CPI Segment | SW | LAS | TEN | Tenaya | Hospitality Network | POInt | Yes | No | HN SW LAS TEN CPI Segment Augment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-07-31 |  | SB-0196 | 2020-08-14 | Chg
59850 | RPHY MRTR-New-DWN-CIN-RPA-5110 | CA | SAN | DWN | Downtown | R PHY | POInt | Yes | No | R PHY CA SAN DWN R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 9 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0606 | 2020-05-22 | Chg
59850 | RPHY MRTR-New-DWN-CIN-ATX-OCML2 | CA | SAN | DWN | Downtown | R PHY | POInt | Yes | No | R PHY CA SAN DWN R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0606 | 2020-05-22 | Chg
59850 | RPHY MRTR-New-DWN-CIN MGMT-2K | CA | SAN | DWN | Downtown | R PHY | POInt | Yes | No | R PHY CA SAN DWN R PHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-15 | SN-0487 | 2020-05-12 | New
59744 | RPHY MRTR-New-HEN-CIN-RPA2-5110 | SW | LAS | HEN | Henderson | R PHY | POInt | Yes | No | R PHY SW LAS HEN R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 9 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0606 | 2020-05-22 | Chg
59744 | RPHY MRTR-New-HEN-CIN-ATX-OCML2 | SW | LAS | HEN | Henderson | R PHY | POInt | Yes | No | R PHY SW LAS HEN R PHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0487 | 2020-05-12 | New
59744 | RPHY MRTR-New-HEN-CIN-DPA-5110 | SW | LAS | HEN | Henderson | R PHY | POInt | Yes | No | R PHY SW LAS HEN R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0487 | 2020-05-12 | New
59744 | RPHY MRTR-New-HEN-CIN MGMT-2K | SW | LAS | HEN | Henderson | R PHY | POInt | Yes | No | R PHY SW LAS HEN R PHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-08-31 | SN-0606 | 2020-05-22 | Chg
44875 | MTCH SE MGA WRB RPHY Test Rack Deployment POR20 | SE | MGA | WRB | Warner Robins | MTC HE - Hub Signaling | POInt | Yes | No | MTCH SE MGA WRB RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-06-06 | 2020-08-01 |  | SN-0219 | 2020-04-03
54571 | CFS SE NOR DST SC-CFS Augment POR20 | SE | NOR | DST | Destrehan | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE NOR DST SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE BTR STC SC-CFS Augment POR20 | SE | BTR | STC | St. Charles | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE BTR STC SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-01 |  | SB-0023 | 2020-01-30 | New
75860 | FI SW LAS OSB Oso Blanca Integration POR20 | SW | LAS | OSB | Oso Blanca | Facilities Integration | POInt | Yes | No | FI SW LAS OSB Oso Blanca Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling | 1 | 2020-05-01 | 2020-08-01 |  | SN-0374 | 2020-03-19 | Chg
35172 | MRTR NCS-Growth-FWB-100G Grow | SE | GCT | FWB | Ft. Walton Beach with (Insite tower) | Metro Routers | POInt | Yes | Yes | MRTR SE MGA WRB 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-07-01 | 2020-08-01 | 2020-09-30 | SN-0158 | 2020-02-06 | New
54572 | CFS VA HRD VBC BS-CFS Augment POR20 | VA | HRD | VBC | Virginia Beach | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD VBC BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-01 |  | SB-0023 | 2020-01-30 | New
75645 | CGN Replacement 16 | SE | GAN | GNS | Gainesville | Data Center Capacity | POInt | Yes | No | DTC SE GAN GNS CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-04-01 | 2020-08-05 |  | SN-0554 | 2020-05-13 | Chg
75655 | Arbor 18 | NE | RHD | PRV | Providence | Arbor DDoS | POInt | Yes | No | DDoS NE RHD PRV Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-06-26 | 2020-08-10 | 2020-08-24 | SN-0107 | 2020-02-06 | Chg
75658 | VA-VBC-1x Dell R640 | VA | HRD | VBC | Virginia Beach | Visibility Architecture | POInt | Yes | No | VIA VA HRD VBC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 4 | 2020-05-26 | 2020-08-10 | 2020-08-24 | SN-0169 | 2020-02-06 | Chg
75658 | VA-VBC-1x Juniper EX4600 | VA | HRD | VBC | Virginia Beach | Visibility Architecture | POInt | Yes | No | VIA VA HRD VBC Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-05-26 | 2020-08-10 | 2020-08-24 | SN-0169 | 2020-02-06 | Chg
75658 | VA-NRF-1x Dell R640 | VA | HRD | NRF | Norfolk | Visibility Architecture | POInt | Yes | No | VIA VA HRD NRF Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 4 | 2020-05-26 | 2020-08-10 | 2020-08-24 | SN-0169 | 2020-02-06 | Chg
75658 | VA-NRF-1x Juniper EX4600 | VA | HRD | NRF | Norfolk | Visibility Architecture | POInt | Yes | No | VIA VA HRD NRF Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-05-26 | 2020-08-10 | 2020-08-24 | SN-0169 | 2020-02-06 | Chg
75655 | Arbor 6 | COR | NAT | DA1/2 | Dallas (cage 373/2210) | Arbor DDoS | POInt | Yes | No | DDoS SW NAT DA1 Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-07-10 | 2020-08-12 | 2020-09-11 | SN-0220 | 2020-02-03 | Chg
34644 | BWM KAN DOCSIS Expansion 192 MHz | CE | KAN | CFV | Coffeyville | Bandwidth Management | POInt | Yes | No | BWM CE KAN CFV DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-14 | 2022-01-14 | SN-0558 | 2020-05-12 | New
34644 | BWM NWA DOCSIS Expansion 96 MHz | CE | NWA | BVL | Bentonville | Bandwidth Management | POInt | Yes | No | BWM CE NWA BVL DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-14 | 2021-04-01 | SN-0558 | 2020-05-12 | New
34644 | BWM NWA DOCSIS Expansion 192 MHz | CE | NWA | BVL | Bentonville | Bandwidth Management | POInt | Yes | No | BWM CE NWA BVL DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-14 | 2022-01-14 | SN-0558 | 2020-05-12 | New
34644 | BWM KAN DOCSIS Expansion 96 MHz | CE | KAN | CFV | Coffeyville | Bandwidth Management | POInt | Yes | No | BWM CE KAN CFV DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-14 | 2021-04-01 | SN-0558 | 2020-05-12 | New
34635 | BWM ROA DOCSIS Expansion 192 MHz | VA | ROA | RON | Roanoke | Bandwidth Management | POInt | Yes | No | BWM VA ROA RON DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-14 | 2023-01-30 | SN-0558 | 2020-05-12 | New
34635 | BWM ROA DOCSIS Expansion 96 MHz | VA | ROA | RON | Roanoke | Bandwidth Management | POInt | Yes | No | BWM VA ROA RON DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-14 | 2022-10-03 | SN-0558 | 2020-05-12 | New
34642 | BWM SUN DOCSIS Expansion 96 MHz | CE | SUN | SVI | Sun Valley | Bandwidth Management | POInt | Yes | No | BWM CE SUN SVI DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-14 | 2021-04-01 | SN-0558 | 2020-05-12 | New
34642 | BWM SUN DOCSIS Expansion 192 MHz | CE | SUN | SVI | Sun Valley | Bandwidth Management | POInt | Yes | No | BWM CE SUN SVI DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-14 | 2021-04-01 | SN-0558 | 2020-05-12 | New
44923 | MTCH CA SAN ELC Dish Upgrades Deployment POR20 | CA | SAN | ELC | El Cajon | MTC HE - Hub Signaling | POInt | Yes | No | MTCH CA SAN ELC Dish Upgrades Deployment POR20 | Labor | TVRO | 1 | 2020-08-31 | 2020-08-15 |  | SN-0852 | 2020-08-20 | Chg
75738 | MTCH DV6000 Replacement Deployment POR20 | COR | COR | ATL | Atlanta | MTC HE - Hub Signaling | POInt | Yes | No | MTCH CO COR ATL DV6000 Replacement Deployment POR20 | Chassis | Artel transceiver (3 RU) | 1 | 2020-08-06 | 2020-08-15
75663 | V2B COR COR DVY 4K UHD HDR Content Augment POR20 | COR | COR | DVY | Deer Valley | V2B | POInt | Yes | No | V2B COR COR DVY 4k UHD HDR Content Augment POR20 | Chassis | 4K UHD HDR | 1 | 2020-07-06 | 2020-08-15 | 2020-12-15
75663 | V2B CA SAN ELC 4K UHD HDR Content Augment POR20 | CA | SAN | ELC | El Cajon | V2B | POInt | Yes | No | V2B CA SAN ELC 4k UHD HDR Content Augment POR20 | Chassis | 4K UHD HDR | 1 | 2020-06-06 | 2020-08-15 | 2020-12-15
75699 | MTCS COR COR P6L Lab APEX3000 Deployment POR20 | COR | COR | P6L | P6 Lab | MTC - Servers and Software | POInt | Yes | No | MTCS CO COR P6L Lab APEX3000 Deployment POR20 | Chassis | APEX3000 | 1 | 2020-07-06 | 2020-08-15 | 2020-09-15
74648 | RPHY MRTR-New-LTF-CIN Exfo-Switch | VA | HRD | LTF | Lightfoot | R PHY | POInt | Yes | Yes | R PHY VA HRD LTF RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
59744 | RPHY MRTR-New-BEL-CIN Exfo-Switch | SW | ARZ | BEL | Bell | R PHY | POInt | Yes | Yes | R PHY SW ARZ BEL RPHY Metro Augment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 7 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
75245 | RPHY MRTR-New-ONA-CIN Exfo-Switch | CE | OMA | ONA | North (OM) | R PHY | POInt | Yes | Yes | R PHY CE OMA ONA RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
74648 | RPHY MRTR-New-PRA-CIN Exfo-Switch | VA | HRD | PRA | Princess Anne | R PHY | POInt | Yes | Yes | R PHY VA HRD PRA RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
75243 | RPHY MRTR-New-LFY-CIN Exfo-Switch | SE | LFY | LFY | Lafayette | R PHY | POInt | Yes | Yes | R PHY SE LFY LFY RPHY Metro Initial Deployment POR19 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
75245 | RPHY MRTR-New-QNC-CIN Exfo-Switch | CE | TUL | QNC | Quincy | R PHY | POInt | Yes | Yes | R PHY CE TUL QNC RPHY Metro Initial Deployment POR19 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
74648 | RPHY MRTR-New-CHS-CIN Exfo-Switch2 | VA | HRD | CHS | Chesapeake | R PHY | POInt | Yes | Yes | R PHY VA HRD CHS RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 |  | SN-0741 | 2020-07-10 | New
75244 | RPHY MRTR-New-PTH-CIN Exfo-Switch | NE | RHD | PTH | Portsmouth (RI) | R PHY | POInt | Yes | Yes | R PHY NE RHD PTH RPHY Metro Initial Deployment POR19 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
59850 | RPHY MRTR-New-ESC-CIN Exfo-Switch | CA | SAN | ESC | Escondido | R PHY | POInt | Yes | Yes | R PHY CA SAN ESC RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 3 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
75245 | RPHY MRTR-New-SOU-CIN Exfo-Switch | CE | OMA | SOU | South (OM) | R PHY | POInt | Yes | Yes | R PHY CE OMA SOU RPHY Metro Initial Deployment POR19 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
74648 | RPHY MRTR-New-NRF-CIN Exfo-Switch | VA | HRD | NRF | Norfolk | R PHY | POInt | Yes | No | R PHY VA HRD NRF R PHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
59850 | RPHY MRTR-New-AVJ-CIN Exfo-Switch | CA | ORG | AVJ | Aliso Viejo | R PHY | POInt | Yes | No | R PHY CA ORG AVJ R PHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 13 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
34616 | CB Transport - New Router Norman - NOR - Card Add | CE | OKC | NOR | Norman | CB - Metro Core | POInt | Yes | No | CBMC CE OKC NOR Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-07-15 | 2020-08-15 |  | SN-0701 | 2020-07-02 | Chg
34616 | CB Transport - New Router Moore - NOR - Card Add | CE | OKC | NOR | Norman | CB - Metro Core | POInt | Yes | No | CBMC CE OKC NOR Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-07-15 | 2020-08-15
34616 | CB Transport - New Router Northeast - NOR - Card Add | CE | OKC | NOR | Norman | CB - Metro Core | POInt | Yes | No | CBMC CE OKC NOR Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-07-15 | 2020-08-15 |  | SN-0701 | 2020-07-02 | Chg
74648 | RPHY MRTR-New-VBC-CIN Exfo-Switch | VA | HRD | VBC | Virginia Beach | R PHY | POInt | Yes | No | R PHY VA HRD VBC R PHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 2 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
75738 | MTCH All Channels Automation Deployment POR20 | COR | COR | ATL | Atlanta | MTC HE - Hub Signaling | POInt | Yes | No | MTCH CO COR ATL All Channels Automation Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-08-06 | 2020-08-15
59744 | RPHY MRTR-New-PEO-CIN Exfo-Switch | SW | ARZ | PEO | Peoria | R PHY | POInt | Yes | No | R PHY SW ARZ PEO R PHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 6 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
59850 | RPHY MRTR-New-IRV-CIN Exfo-Switch | CA | ORG | IRV | Irvine | R PHY | POInt | Yes | No | R PHY CA ORG IRV R PHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 7 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
44926 | MTCH NE RHD LNC RF Passive Splitter Deployment POR20 | NE | RHD | LNC | Lincoln | MTC HE - Hub Signaling | POInt | Yes | No | MTCH NE RHD LNC RF Passive Splitter Deployment POR20 | Chassis | 8-way splitter | 1 | 2020-07-06 | 2020-08-15 | 2020-09-15
75663 | V2B COR COR DVY 4K UHD HDR Monitoring Augment POR20 | COR | COR | DVY | Deer Valley | V2B | POInt | Yes | No | V2B COR COR DVY 4k UHD HDR Monitoring Augment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-06 | 2020-08-15 | 2020-12-15
75663 | V2B COR COR DDR 4K UHD HDR Content Augment POR20 | COR | COR | DDR | Duke Drive | V2B | POInt | Yes | No | V2B COR COR DDR 4k UHD HDR Content Augment POR20 | Chassis | 4K UHD HDR | 1 | 2020-07-06 | 2020-08-15 | 2020-12-15
59744 | RPHY MRTR-New-TEN-CLH Exfo-Switch | SW | LAS | TEN | Tenaya | R PHY | POInt | Yes | No | R PHY SW LAS TEN R PHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 5 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
75838 | SW LAS BLU Cabling Refortification Augment POR20 | SW | LAS | BLU | Blue Diamond | MTC Fiber and Rack Management | POInt | Yes | No | MVFM SW LAS BLU Cabling Refortification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-07-06 | 2020-08-15 | 2020-08-30 | SN-0793 | 2020-08-20 | Chg
74648 | RPHY MRTR-New-RON-CIN Exfo-Switch | VA | ROA | RON | Roanoke | R PHY | POInt | Yes | Yes | R PHY VA ROA RON RPHY Metro Initial Deployment POR19 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
74648 | RPHY MRTR-New-NWP-CIN-RPA-5110 | VA | HRD | NWP | Newport News | R PHY | POInt | Yes | Yes | R PHY VA HRD NWP RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-08-15 | 2020-08-31 | SN-0741 | 2020-07-10 | Chg
74648 | RPHY MRTR-New-NWP-CIN-ATX-OCML | VA | HRD | NWP | Newport News | R PHY | POInt | Yes | Yes | R PHY VA HRD NWP RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-08-15 | 2020-08-31 | SN-0741 | 2020-07-10 | Chg
74648 | RPHY MRTR-New-NWP-CIN MGMT-2K | VA | HRD | NWP | Newport News | R PHY | POInt | Yes | Yes | R PHY VA HRD NWP RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-08-15 | 2020-08-31 | SN-0741 | 2020-07-10 | Chg
74648 | RPHY MRTR-New-NWP-CIN Exfo-Switch | VA | HRD | NWP | Newport News | R PHY | POInt | Yes | Yes | R PHY VA HRD NWP RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 4 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
59744 | RPHY MRTR-New-VLY-CIN Exfo-Switch | SW | LAS | VLY | Valley | R PHY | POInt | Yes | Yes | R PHY SW LAS VLY RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 4 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
75245 | RPHY MRTR-New-WLK-CIN Exfo-Switch | CE | OKC | WLK | Walker Hub | R PHY | POInt | Yes | Yes | R PHY CE OKC WLK RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
34619 | CB Transport - New Router Moore - OKC - Card Add | CE | OKC | OKC | OKC MTC | CB - Metro Core | POInt | Yes | Yes | CBMC CE OKC OKC Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-07-15 | 2020-08-15 |  | SN-0419 | 2020-04-02 | Chg
75245 | RPHY MRTR-New-YAL-CIN Exfo-Switch | CE | TUL | YAL | Yale | R PHY | POInt | Yes | Yes | R PHY CE TUL YAL RPHY Metro Augment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
59744 | RPHY MRTR-New-HEN-CLH Exfo-Switch | SW | LAS | HEN | Henderson | R PHY | POInt | Yes | Yes | R PHY SW LAS HEN RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 9 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
59850 | RPHY MRTR-New-PAV-CIN Exfo-Switch | CA | ORG | PAV | Palos Verdes | R PHY | POInt | Yes | Yes | R PHY CA ORG PAV RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 4 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
59744 | RPHY MRTR-New-ERN-CLH Exfo-Switch | SW | LAS | ERN | Ernest May | R PHY | POInt | Yes | Yes | R PHY SW LAS ERN RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 8 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
59744 | RPHY MRTR-New-ALI-CIN Exfo-Switch | SW | LAS | ALI | Aliante | R PHY | POInt | Yes | Yes | R PHY SW LAS ALI RPHY Metro Augment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 4 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
75243 | RPHY MRTR-New-MCY-CIN Exfo-Switch | SE | NOR | MCY | Mid-City | R PHY | POInt | Yes | Yes | R PHY SE NOR MCY RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
54569 | CFS CHU HV-CFS GEN SUSTAIN PROJECT - MEDIUM | CA | SAN | CHU | Chula Vista | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS CA SAN CHU HV-CFS Augment POR20 | Critical Facilities | GEN SUSTAIN PROJECT - MEDIUM | 1 | 2020-02-01 | 2020-08-15
59744 | RPHY MRTR-New-CHD-CIN Exfo-Switch | SW | ARZ | CHD | Chandler | R PHY | POInt | Yes | Yes | R PHY SW ARZ CHD RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 12 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
59744 | RPHY MRTR-New-NSC-CIN Exfo-Switch | SW | ARZ | NSC | North Scottsdale | R PHY | POInt | Yes | Yes | R PHY SW ARZ NSC RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 2 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
59850 | RPHY MRTR-New-ORG-CIN Exfo-Switch | CA | ORG | ORG | Orange | R PHY | POInt | Yes | Yes | R PHY CA ORG ORG RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 5 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
59850 | RPHY MRTR-New-SAB-CIN Exfo-Switch | CA | SAB | SAB | Santa Barbara | R PHY | POInt | Yes | Yes | R PHY CA SAB SAB RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 10 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
59850 | RPHY MRTR-New-FED-CIN Exfo-Switch | CA | SAN | FED | Federal | R PHY | POInt | Yes | Yes | R PHY CA SAN FED RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 9 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
59850 | RPHY MRTR-New-DWN-CIN Exfo-Switch | CA | SAN | DWN | Downtown | R PHY | POInt | Yes | Yes | R PHY CA SAN DWN RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 6 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
34616 | CB Transport - New Router Moore - OKC - Chassis Add | CE | OKC | OKC | OKC MTC | CB - Metro Core | POInt | Yes | Yes | CBMC CE OKC OKC Optics Only for Cisco T5 Augment POR20_V2 | Chassis | 1x Cisco M6 Transport Chassis | 1 | 2020-07-15 | 2020-08-15 |  | SN-0144 | 2020-02-06 | Chg
59744 | RPHY MRTR-New-BLU-CIN Exfo-Switch | SW | LAS | BLU | Blue Diamond | R PHY | POInt | Yes | Yes | R PHY SW LAS BLU RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 7 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
59744 | RPHY MRTR-New-FWL-CIN Exfo-Switch | SW | ARZ | FWL | Fowler | R PHY | POInt | Yes | Yes | R PHY SW ARZ FWL RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 8 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
59744 | RPHY MRTR-New-SSC-CIN Exfo-Switch | SW | ARZ | SSC | South Scottsdale | R PHY | POInt | Yes | Yes | R PHY SW ARZ SSC RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 5 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
74648 | RPHY MRTR-New-FBG-CIN Exfo-Switch | VA | NVA | FBG | Fredericksburg | R PHY | POInt | Yes | Yes | R PHY VA NVA FBG RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
34623 | CB Transport - New Router Tenaya - TEN - Optics | SW | LAS | TEN | Tenaya | CB - Metro Core | POInt | Yes | Yes | CBMC SW LAS TEN Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-06-01 | 2020-08-15
34970 | CFG TUC BD-CFG GEN GROW PROJECT - LARGE | SW | ARZ | TUC | Tucson | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ TUC BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-03-01 | 2020-08-15
59850 | RPHY MRTR-New-CHU-CIN Exfo-Switch | CA | SAN | CHU | Chula Vista | R PHY | POInt | Yes | Yes | R PHY CA SAN CHU RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 7 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
74648 | RPHY MRTR-New-PTM-CIN Exfo-Switch2 | VA | HRD | PTM | Portsmouth (VA) | R PHY | POInt | Yes | Yes | R PHY VA HRD PTM RPHY Metro Augment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 |  | SN-0741 | 2020-07-10 | New
59744 | RPHY MRTR-New-MCD-CIN Exfo-Switch | SW | ARZ | MCD | McDowell | R PHY | POInt | Yes | Yes | R PHY SW ARZ MCD RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 2 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
75245 | RPHY MRTR-New-BVL-CIN Exfo-Switch | CE | NWA | BVL | Bentonville | R PHY | POInt | Yes | Yes | R PHY CE NWA BVL RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
75245 | RPHY MRTR-New-ELK-CIN Exfo-Switch | CE | OMA | ELK | Elkhorn | R PHY | POInt | Yes | Yes | R PHY CE OMA ELK RPHY Metro Augment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
74648 | RPHY MRTR-New-OCN-CIN Exfo-Switch | VA | HRD | OCN | Oceana | R PHY | POInt | Yes | Yes | R PHY VA HRD OCN RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
59850 | RPHY MRTR-New-OCE-CIN Exfo-Switch | CA | SAN | OCE | Oceanside | R PHY | POInt | Yes | Yes | R PHY CA SAN OCE RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 4 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
59744 | RPHY MRTR-New-OSB-CIN Exfo-Switch | SW | LAS | OSB | Oso Blanca | R PHY | POInt | Yes | Yes | R PHY SW LAS OSB RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 6 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
75245 | RPHY MRTR-New-WES-CIN Exfo-Switch | CE | OMA | WES | West (OM) | R PHY | POInt | Yes | Yes | R PHY CE OMA WES RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
75245 | RPHY MRTR-New-OKC-CIN Exfo-Switch | CE | OKC | OKC | OKC MTC | R PHY | POInt | Yes | Yes | R PHY CE OKC OKC RPHY Metro Augment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
34619 | CB Transport - New Router Northeast - NEH - Optics | CE | OKC | NEH | North East | CB - Metro Core | POInt | Yes | Yes | CBMC CE OKC NEH Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 3 | 2020-07-15 | 2020-08-15
75245 | RPHY MRTR-New-FAY-CIN Exfo-Switch | CE | NWA | FAY | Fayetteville | R PHY | POInt | Yes | Yes | R PHY CE NWA FAY RPHY Metro Augment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
34623 | CB Transport - New Router Tenaya - HEN - Optics | SW | LAS | HEN | Henderson | CB - Metro Core | POInt | Yes | Yes | CBMC SW LAS HEN Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-06-01 | 2020-08-15
34619 | CB Transport - New Router Moore - MOO - Optics | CE | OKC | MOO | Moore | CB - Metro Core | POInt | Yes | Yes | CBMC CE OKC MOO Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-07-15 | 2020-08-15
59850 | RPHY MRTR-New-VST-CIN Exfo-Switch | CA | SAN | VST | Vista | R PHY | POInt | Yes | Yes | R PHY CA SAN VST RPHY Metro Augment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 6 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
59850 | RPHY MRTR-New-PWY-CIN Exfo-Switch | CA | SAN | PWY | Poway | R PHY | POInt | Yes | Yes | R PHY CA SAN PWY RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 3 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
59744 | RPHY MRTR-New-PNL-CIN Exfo-Switch | SW | ARZ | PNL | Pinal County | R PHY | POInt | Yes | Yes | R PHY SW ARZ PNL RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 2 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
59850 | RPHY MRTR-New-ELC-CIN Exfo-Switch | CA | SAN | ELC | El Cajon | R PHY | POInt | Yes | Yes | R PHY CA SAN ELC RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 5 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
59744 | RPHY MRTR-New-TUC-CIN Exfo-Switch | SW | ARZ | TUC | Tucson | R PHY | POInt | Yes | Yes | R PHY SW ARZ TUC RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 4 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
75245 | RPHY MRTR-New-BAR-CIN Exfo-Switch | CE | TUL | BAR | Broken Arrow | R PHY | POInt | Yes | Yes | R PHY CE TUL BAR RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
59850 | RPHY MRTR-New-RSM-CIN Exfo-Switch | CA | ORG | RSM | Rancho Santa Margarita | R PHY | POInt | Yes | Yes | R PHY CA ORG RSM RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 5 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
59744 | RPHY MRTR-New-BUK-CIN Exfo-Switch | SW | ARZ | BUK | Buckeye | R PHY | POInt | Yes | Yes | R PHY SW ARZ BUK RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 2 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
75245 | RPHY MRTR-New-CLH-CIN Exfo-Switch | CE | OKC | CLH | County Line | R PHY | POInt | Yes | Yes | R PHY CE OKC CLH RPHY Metro Initial Deployment POR19 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
59744 | RPHY MRTR-New-VSA-CIN Exfo-Switch | SW | ARZ | VSA | Vistancia | R PHY | POInt | Yes | Yes | R PHY SW ARZ VSA RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
59744 | RPHY MRTR-New-MSA-CIN Exfo-Switch | SW | ARZ | MSA | Mesa | R PHY | POInt | Yes | Yes | R PHY SW ARZ MSA RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 18 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
59850 | RPHY MRTR-New-DNP-CIN Exfo-Switch | CA | ORG | DNP | Dana Point | R PHY | POInt | Yes | Yes | R PHY CA ORG DNP RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 5 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
75245 | RPHY MRTR-New-OWA-CIN Exfo-Switch | CE | TUL | OWA | Owasso | R PHY | POInt | Yes | Yes | R PHY CE TUL OWA RPHY Metro Initial Deployment POR19 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-08-15 | 2020-08-15 | SN-0606 | 2020-05-22 | New
39256 | BWM_GLB_VIDEO SG_2020 DOCSIS node split-based Video SG | NE | CON | GLB | Glastonbury | Bandwidth Management | POInt | Yes | No | BWM NE CON GLB VIDEO SG Augment POR20 v2 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-17 | 2020-11-13 | SN-0426 | 2020-04-10 | Chg
75645 | CGN Replacement 17 | SE | MGA | MCN | Macon | Data Center Capacity | POInt | Yes | No | DTC SE MGA MCN CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-04-01 | 2020-08-18 |  | SN-0554 | 2020-05-13 | Chg
75645 | CGN Replacement 18 | CE | TUL | TUL | Tulsa | Data Center Capacity | POInt | Yes | No | DTC CE TUL TUL CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-04-15 | 2020-08-19 |  | SN-0554 | 2020-05-13 | Chg
34976 | CFG NE RHD CRN RK-CFG Deployment POR20 | NE | RHD | CRN | Cranston | Critical Facilities (Grow) | POInt | Yes | Yes | CFG NE RHD CRN RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-08-03 | 2020-08-20 |  | SN-0411 | 2020-03-27
34619 | CB Transport - New Router Johnson - FAY - Optics | CE | NWA | FAY | Fayetteville | CB - Metro Core | POInt | Yes | Yes | CBMC CE NWA FAY Optics Only for Cisco T5 Augment POR20_V2 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-05-15 | 2020-08-20 |  | SN-0586 | 2020-05-14 | Chg
34638 | BWM_STC_MSSA_Spectrum Phase II Start | SE | BTR | STC | St. Charles | Bandwidth Management | POInt | Yes | No | BWM SE BTR STC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | SN-0703 | 2020-06-30 | Chg
34638 | BWM_GNZ_MSSA_Spectrum Phase II Start | SE | BTR | GNZ | Gonzales | Bandwidth Management | POInt | Yes | No | BWM SE BTR GNZ MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | SN-0703 | 2020-06-30 | Chg
34638 | BWM_ELM_MSSA_Spectrum Phase II Start | SE | NOR | ELM | Elmwood | Bandwidth Management | POInt | Yes | No | BWM SE NOR ELM MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-24 | 2020-09-15 | SN-0703 | 2020-06-30 | Chg
34638 | BWM_NOE_MSSA_Spectrum Phase II Start | SE | NOR | NOE | New Orleans East | Bandwidth Management | POInt | Yes | No | BWM SE NOR NOE MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-24 | 2020-09-15 | SN-0703 | 2020-06-30 | Chg
34642 | BWM_NEH_MSSA_Spectrum Phase II Start | CE | OKC | NEH | North East | Bandwidth Management | POInt | Yes | No | BWM CE OKC NEH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | SN-0703 | 2020-06-30 | Chg
34638 | BWM_NIB_MSSA_Spectrum Phase II Start | SE | LFY | NIB | New Iberia | Bandwidth Management | POInt | Yes | No | BWM SE LFY NIB MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | SN-0703 | 2020-06-30 | Chg
34642 | BWM_NOR_MSSA_Spectrum Phase II Start | CE | OKC | NOR | Norman | Bandwidth Management | POInt | Yes | No | BWM CE OKC NOR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | SN-0703 | 2020-06-30 | Chg
39256 | BWM_ENF_MSSA_Spectrum Phase II Start | NE | CON | ENF | Enfield | Bandwidth Management | POInt | Yes | No | BWM NE CON ENF MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-27 | SN-0703 | 2020-06-30 | Chg
34638 | BWM_LFY_MSSA_Spectrum Phase II Start | SE | LFY | LFY | Lafayette | Bandwidth Management | POInt | Yes | No | BWM SE LFY LFY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | SN-0703 | 2020-06-30 | Chg
34638 | BWM_DVL_MSSA_Spectrum Phase II Start | SE | BTR | DVL | Donaldsonville | Bandwidth Management | POInt | Yes | No | BWM SE BTR DVL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | SN-0703 | 2020-06-30 | Chg
39256 | BWM_GLB_MSSA_Spectrum Phase II Start | NE | CON | GLB | Glastonbury | Bandwidth Management | POInt | Yes | No | BWM NE CON GLB MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-27 | SN-0703 | 2020-06-30 | Chg
34642 | BWM_NCH_MSSA_Spectrum Phase II Start | CE | OKC | NCH | North Central | Bandwidth Management | POInt | Yes | No | BWM CE OKC NCH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | SN-0703 | 2020-06-30 | Chg
39256 | BWM_SFD_MSSA_Spectrum Phase II Start | NE | CON | SFD | Stafford | Bandwidth Management | POInt | Yes | No | BWM NE CON SFD MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-27 | SN-0703 | 2020-06-30 | Chg
34642 | BWM_CHO_MSSA_Spectrum Phase II Start | CE | OKC | CHO | Choctaw | Bandwidth Management | POInt | Yes | No | BWM CE OKC CHO MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | SN-0703 | 2020-06-30 | Chg
34638 | BWM_STM_MSSA_Spectrum Phase II Start | SE | LFY | STM | St. Martinville | Bandwidth Management | POInt | Yes | No | BWM SE LFY STM MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | SN-0703 | 2020-06-30 | Chg
39256 | BWM_RKH_MSSA_Spectrum Phase II Start | NE | CON | RKH | Rocky Hill | Bandwidth Management | POInt | Yes | No | BWM NE CON RKH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-27 | SN-0703 | 2020-06-30 | Chg
34638 | BWM_LUL_MSSA_Spectrum Phase II Start | SE | NOR | LUL | Luling | Bandwidth Management | POInt | Yes | No | BWM SE NOR LUL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-24 | 2020-09-15 | SN-0703 | 2020-06-30 | Chg
34638 | BWM_BTR_MSSA_Spectrum Phase II Start | SE | BTR | BTR | Baton Rouge | Bandwidth Management | POInt | Yes | No | BWM SE BTR BTR MSSA _Labor Only_Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | SN-0703 | 2020-06-30 | Chg
34642 | BWM_WLH_MSSA_Spectrum Phase II Start | CE | OKC | WLH | Waterloo | Bandwidth Management | POInt | Yes | No | BWM CE OKC WLH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | SN-0703 | 2020-06-30 | Chg
34638 | BWM_FRK_MSSA_Spectrum Phase II Start | SE | LFY | FRK | Franklin | Bandwidth Management | POInt | Yes | No | BWM SE LFY FRK MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | SN-0703 | 2020-06-30 | Chg
34638 | BWM_ALG_MSSA_Spectrum Phase II Start | SE | NOR | ALG | Algiers | Bandwidth Management | POInt | Yes | No | BWM SE NOR ALG MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-24 | 2020-09-15 | SN-0703 | 2020-06-30 | Chg
39256 | BWM_STN_MSSA_Spectrum Phase II Start | NE | CON | STN | Southington | Bandwidth Management | POInt | Yes | No | BWM NE CON STN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-27 | SN-0703 | 2020-06-30 | Chg
34638 | BWM_STB_MSSA_Spectrum Phase II Start | SE | NOR | STB | St. Bernard | Bandwidth Management | POInt | Yes | No | BWM SE NOR STB MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-24 | 2020-09-15 | SN-0703 | 2020-06-30 | Chg
34638 | BWM_NTH_MSSA_Spectrum Phase II Start | SE | BTR | NTH | Baker | Bandwidth Management | POInt | Yes | No | BWM SE BTR NTH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | SN-0703 | 2020-06-30 | Chg
34642 | BWM_ELR_MSSA_Spectrum Phase II Start | CE | OKC | ELR | El Reno | Bandwidth Management | POInt | Yes | No | BWM CE OKC ELR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | SN-0703 | 2020-06-30 | Chg
34642 | BWM_SEH_MSSA_Spectrum Phase II Start | CE | OKC | SEH | South East | Bandwidth Management | POInt | Yes | No | BWM CE OKC SEH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | SN-0703 | 2020-06-30 | Chg
34638 | BWM_DNS_MSSA_Spectrum Phase II Start | SE | BTR | DNS | Denham Springs | Bandwidth Management | POInt | Yes | No | BWM SE BTR DNS MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | SN-0703 | 2020-06-30 | Chg
34642 | BWM_ILH_MSSA_Spectrum Phase II Start | CE | OKC | ILH | Irish Lane | Bandwidth Management | POInt | Yes | No | BWM CE OKC ILH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | SN-0703 | 2020-06-30 | Chg
34638 | BWM_PLQ_MSSA_Spectrum Phase II Start | SE | BTR | PLQ | Plaquemine | Bandwidth Management | POInt | Yes | No | BWM SE BTR PLQ MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | SN-0703 | 2020-06-30 | Chg
34638 | BWM_CRW_MSSA_Spectrum Phase II Start | SE | LFY | CRW | Crowley | Bandwidth Management | POInt | Yes | No | BWM SE LFY CRW MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | SN-0703 | 2020-06-30 | Chg
34642 | BWM_WEH_MSSA_Spectrum Phase II Start | CE | OKC | WEH | West (OKC) | Bandwidth Management | POInt | Yes | No | BWM CE OKC WEH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | SN-0703 | 2020-06-30 | Chg
34638 | BWM_LPL_MSSA_Spectrum Phase II Start | SE | NOR | LPL | Lapalco | Bandwidth Management | POInt | Yes | No | BWM SE NOR LPL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-24 | 2020-09-15 | SN-0703 | 2020-06-30 | Chg
34638 | BWM_ERW_MSSA_Spectrum Phase II Start | SE | BTR | ERW | Erwinville | Bandwidth Management | POInt | Yes | No | BWM SE BTR ERW MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | SN-0703 | 2020-06-30 | Chg
34642 | BWM_OKC_MSSA_Spectrum Phase II Start | CE | OKC | OKC | OKC MTC | Bandwidth Management | POInt | Yes | No | BWM CE OKC OKC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | SN-0703 | 2020-06-30 | Chg
39256 | BWM_MER_MSSA_Spectrum Phase II Start | NE | CON | MER | Meriden | Bandwidth Management | POInt | Yes | No | BWM NE CON MER MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-27 | SN-0703 | 2020-06-30 | Chg
34642 | BWM_MOO_MSSA_Spectrum Phase II Start | CE | OKC | MOO | Moore | Bandwidth Management | POInt | Yes | No | BWM CE OKC MOO MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | SN-0703 | 2020-06-30 | Chg
34638 | BWM_SPC_MSSA_Spectrum Phase II Start | SE | BTR | SPC | Pecue | Bandwidth Management | POInt | Yes | No | BWM SE BTR SPC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | SN-0703 | 2020-06-30 | Chg
34642 | BWM_WLK_MSSA_Spectrum Phase II Start | CE | OKC | WLK | Walker Hub | Bandwidth Management | POInt | Yes | No | BWM CE OKC WLK MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | SN-0703 | 2020-06-30 | Chg
34642 | BWM_MWC_MSSA_Spectrum Phase II Start | CE | OKC | MWC | Midwest City | Bandwidth Management | POInt | Yes | No | BWM CE OKC MWC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | SN-0703 | 2020-06-30 | Chg
34638 | BWM_KNN_MSSA_Spectrum Phase II Start | SE | NOR | KNN | Kenner | Bandwidth Management | POInt | Yes | No | BWM SE NOR KNN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-24 | 2020-09-15 | SN-0703 | 2020-06-30 | Chg
34638 | BWM_CLR_MSSA_Spectrum Phase II Start | SE | NOR | CLR | Metairie | Bandwidth Management | POInt | Yes | No | BWM SE NOR CLR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-24 | 2020-09-15 | SN-0703 | 2020-06-30 | Chg
34638 | BWM_MCY_MSSA_Spectrum Phase II Start | SE | NOR | MCY | Mid-City | Bandwidth Management | POInt | Yes | No | BWM SE NOR MCY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-24 | 2020-09-15 | SN-0703 | 2020-06-30 | Chg
39256 | BWM_GRB_MSSA_Spectrum Phase II Start | NE | CON | GRB | Granby | Bandwidth Management | POInt | Yes | No | BWM NE CON GRB MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-27 | SN-0703 | 2020-06-30 | Chg
39256 | BWM_MAN_MSSA_Spectrum Phase II Start | NE | CON | MAN | Manchester | Bandwidth Management | POInt | Yes | No | BWM NE CON MAN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-27 | SN-0703 | 2020-06-30 | Chg
34642 | BWM_SRH_MSSA_Spectrum Phase II Start | CE | OKC | SRH | Sara Road | Bandwidth Management | POInt | Yes | No | BWM CE OKC SRH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | SN-0703 | 2020-06-30 | Chg
59745 | R PHY_CCAP_IRV_RPHY CCAP Licenses-1 | CA | ORG | IRV | Irvine | RSPD - CCAP | POInt | Yes | No | R PHY CA ORG IRV RPHY CCAP Augment POR20 | License | CCAP license | 390 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
59745 | R PHY_CCAP_AVJ_RPHY CCAP Licenses_1 | CA | ORG | AVJ | Aliso Viejo | RSPD - CCAP | POInt | Yes | No | R PHY CA ORG AVJ RPHY CCAP Augment POR20 | License | CCAP license | 1014 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
75738 | MTCH SE NAT AT2 Tektronix Upgrade Deployment POR20 | COR | NAT | AT2 | Atlanta - Equinix (cage 50015) | MTC HE - Hub Signaling | POInt | Yes | No | MTCH SE NAT AT2 MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | SN-0692 | 2020-06-30 | Chg
75187 | R PHY_CCAP_YAL_RPHY CCAP Licenses_1 | CE | TUL | YAL | Yale | R PHY | POInt | Yes | No | R PHY CE TUL YAL RPHY CCAP Augment POR20 | License | CCAP license | 207 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
59745 | R PHY_CCAP_ORG_RPHY CCAP Licenses-1 | CA | ORG | ORG | Orange | RSPD - CCAP | POInt | Yes | No | R PHY CA ORG ORG RPHY CCAP Augment POR20 | License | CCAP license | 494 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
75187 | R PHY_CCAP_OWA_RPHY CCAP Licenses_1 | CE | TUL | OWA | Owasso | R PHY | POInt | Yes | No | R PHY CE TUL OWA RPHY CCAP Augment POR20 | License | CCAP license | 26 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
59745 | R PHY_CCAP_DNP_RPHY CCAP Licenses-1 | CA | ORG | DNP | Dana Point | RSPD - CCAP | POInt | Yes | No | R PHY CA ORG DNP RPHY CCAP Augment POR20 | License | CCAP license | 182 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
34619 | sr01.wlh.okc.ok-ROUTER | CE | OKC | WLH | Waterloo | CB - Metro Core | POInt | Yes | Yes | CBMC CE OKC WLH ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-08-30 |  | SN-0796 | 2020-07-31 | Chg
75246 | R PHY_CCAP_MCY_RPHY CCAP Licenses_1 | SE | NOR | MCY | Mid-City | R PHY | POInt | Yes | Yes | R PHY SE NOR MCY RPHY CCAP Augment POR20 | License | CCAP license | 26 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
74548 | R PHY_CCAP_PTM_RPHY CCAP Licenses-1 | VA | HRD | PTM | Portsmouth (VA) | R PHY | POInt | Yes | Yes | R PHY VA HRD PTM RPHY CCAP Augment POR20 | License | CCAP license | 173 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
34619 | sr01.gar.tul.ok-ROUTER | CE | TUL | GAR | Garnett | CB - Metro Core | POInt | Yes | Yes | CBMC CE TUL GAR ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-04-15 | 2020-08-30 |  | SN-0796 | 2020-07-31 | Chg
44923 | MTCH CA SAN ELC MPEG4 Tektronix Upgrade Deployment POR20 | CA | SAN | ELC | El Cajon | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH CA SAN ELC MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 4 | 2020-07-15 | 2020-08-30 | 2020-09-30 | SN-0692 | 2020-06-30 | Chg
59745 | R PHY_CCAP_PWY_RPHY CCAP Licenses-1 | CA | SAN | PWY | Poway | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN PWY RPHY CCAP Deployment POR20 | License | CCAP license | 156 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_MCD_RPHY CCAP Licenses-1 | SW | ARZ | MCD | McDowell | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ MCD RPHY CCAP Deployment POR20 | License | CCAP license | 303 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
34619 | KSCYBSRA99-ROUTER | COR | NAT | KCY | Kansas City (1102 Grand) | CB - Metro Core | POInt | Yes | Yes | CBMC CE KAN KCY ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-05 | 2020-08-30 |  | SN-0796 | 2020-07-31 | Chg
44876 | MTCH CE SUN SVI Tektronix Upgrade Deployment POR20 | CE | SUN | SVI | Sun Valley | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH CE SUN SVI MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | SN-0692 | 2020-06-30 | Chg
59522 | R PHY_CCAP_TUC_RPHY CCAP Licenses-1 | SW | ARZ | TUC | Tucson | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ TUC RPHY CCAP Deployment POR20 | License | CCAP license | 78 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
44924 | MTCH SW LAS HEN MPEG4 Tektronix Upgrade Deployment POR20 | SW | LAS | HEN | Henderson | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH SW LAS HEN MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 2 | 2020-08-07 | 2020-08-30 | 2020-09-30 | SN-0852 | 2020-08-20 | Chg
75187 | R PHY_CCAP_BAR_RPHY CCAP Licenses_1 | CE | TUL | BAR | Broken Arrow | R PHY | POInt | Yes | Yes | R PHY CE TUL BAR RPHY CCAP Deployment POR20 | License | CCAP license | 78 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_PEO_RPHY CCAP Licenses-1 | SW | ARZ | PEO | Peoria | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ PEO RPHY CCAP Deployment POR20 | License | CCAP license | 468 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
44876 | MTCH CE OMA OMM MPEG4 Tektronix Upgrade Deployment POR20 | CE | OMA | OMM | Omaha | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH CE OMA OMM MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 3 | 2020-07-15 | 2020-08-30 | 2020-09-30 | SN-0692 | 2020-06-30 | Chg
59745 | R PHY_CCAP_VST_RPHY Unbundled Solution V2_44027 | CA | SAN | VST | Vista | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN VST RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 3 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | Chg
44927 | MTCH VA ROA RON Tektronix Upgrade Deployment POR20 | VA | ROA | RON | Roanoke | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH VA ROA RON MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-08-07 | 2020-08-30 | 2020-09-30 | SN-0800 | 2020-07-31 | Chg
34619 | South-OCML-IXR | CE | OMA | SOU | South (OM) | CB - Metro Core | POInt | Yes | Yes | CBMC CE OMA SOU OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-08-30 |  | SN-0796 | 2020-07-31 | Chg
74548 | R PHY_CCAP_PRA_RPHY CCAP Licenses-1 | VA | HRD | PRA | Princess Anne | R PHY | POInt | Yes | Yes | R PHY VA HRD PRA RPHY CCAP Augment POR20 | License | CCAP license | 52 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
44876 | MTCH CE TUL TUL Tektronix Upgrade Deployment POR20 | CE | TUL | TUL | Tulsa | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH CE TUL TUL MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 2 | 2020-07-15 | 2020-08-30 | 2020-09-30 | SN-0692 | 2020-06-30 | Chg
44923 | MTCH CA SAN CHU Tektronix Upgrade Deployment POR20 | CA | SAN | CHU | Chula Vista | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH CA SAN CHU MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | SN-0692 | 2020-06-30 | Chg
44923 | MTCH CA ORG RSM Tektronix Upgrade Deployment POR20 | CA | ORG | RSM | Rancho Santa Margarita | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH CA ORG RSM MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | SN-0692 | 2020-06-30 | Chg
74548 | R PHY_CCAP_NRF_RPHY CCAP Licenses-1 | VA | HRD | NRF | Norfolk | R PHY | POInt | Yes | Yes | R PHY VA HRD NRF RPHY CCAP Augment POR20 | License | CCAP license | 52 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
75187 | R PHY_CCAP_OKC_RPHY CCAP Licenses_1 | CE | OKC | OKC | OKC MTC | R PHY | POInt | Yes | Yes | R PHY CE OKC OKC RPHY CCAP Augment POR20 | License | CCAP license | 26 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_PNL_RPHY CCAP Licenses-1 | SW | ARZ | PNL | Pinal County | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ PNL RPHY CCAP Deployment POR20 | License | CCAP license | 26 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
59745 | R PHY_CCAP_CHU_RPHY CCAP Licenses-1 | CA | SAN | CHU | Chula Vista | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN CHU RPHY CCAP Deployment POR20 | License | CCAP license | 546 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
75246 | R PHY_CCAP_SPC_RPHY CCAP Licenses_1 | SE | BTR | SPC | Pecue | R PHY | POInt | Yes | Yes | R PHY SE BTR SPC RPHY - CCAP Initial Deployment POR20 | License | CCAP license | 69 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
44923 | MTCH CA SAB SAB Tektronix Upgrade Deployment POR20 | CA | SAB | SAB | Santa Barbara | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH CA SAB SAB MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | SN-0692 | 2020-06-30 | Chg
44926 | MTCH NE CLE CLV Tektronix Upgrade Deployment POR20 | NE | CLE | CLV | Cleveland | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH NE CLE CLV MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | SN-0692 | 2020-06-30 | Chg
59522 | R PHY_CCAP_FWL_RPHY CCAP Licenses-1 | SW | ARZ | FWL | Fowler | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ FWL RPHY CCAP Deployment POR20 | License | CCAP license | 597 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_MSA_RPHY CCAP Licenses-1 | SW | ARZ | MSA | Mesa | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ MSA RPHY CCAP Deployment POR20 | License | CCAP license | 3020 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
44927 | MTCH VA HRD VBC Tektronix Upgrade Deployment POR20 | VA | HRD | VBC | Virginia Beach | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH VA HRD VBC MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | SN-0692 | 2020-06-30 | Chg
44925 | MTCH SW ARZ CHD MPEG4 Tektronix Upgrade Deployment POR20 | SW | ARZ | CHD | Chandler | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH SW ARZ CHD MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | SN-0692 | 2020-06-30 | Chg
44875 | MTCH SE NOR ELM Tektronix Upgrade Deployment POR20 | SE | NOR | ELM | Elmwood | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH SE NOR ELM MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-08-07 | 2020-08-30 | 2020-09-30 | SN-0800 | 2020-07-31 | Chg
59745 | R PHY_CCAP_FED_RPHY CCAP Licenses-1 | CA | SAN | FED | Federal | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN FED RPHY CCAP Deployment POR20 | License | CCAP license | 459 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
74548 | R PHY_CCAP_VBC_RPHY CCAP Licenses-1 | VA | HRD | VBC | Virginia Beach | R PHY | POInt | Yes | Yes | R PHY VA HRD VBC RPHY CCAP Augment POR20 | License | CCAP license | 458 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
34619 | Local - MTC-OCML-IXR | CE | TUL | TUL | Tulsa | CB - Metro Core | POInt | Yes | Yes | CBMC CE TUL TUL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-08-30 |  | SN-0796 | 2020-07-31 | Chg
34619 | Broken Arrow-OCML-IXR | CE | TUL | BAR | Broken Arrow | CB - Metro Core | POInt | Yes | Yes | CBMC CE TUL BAR OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-08-30 |  | SN-0796 | 2020-07-31 | Chg
44876 | MTCH CE ARK NWA MPEG4 Tektronix Upgrade Deployment POR20 | CE | NWA | NWA | Johnson | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH CE NWA NWA MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | SN-0692 | 2020-06-30 | Chg
59745 | R PHY_CCAP_ELC_RPHY Unbundled Solution V2_44027 | CA | SAN | ELC | El Cajon | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN ELC RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 2 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | Chg
75246 | R PHY_CCAP_CLR_RPHY CCAP Licenses_1 | SE | NOR | CLR | Metairie | R PHY | POInt | Yes | Yes | R PHY SE NOR CLR RPHY - CCAP Initial Deployment POR20 | License | CCAP license | 1014 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
44876 | MTCH CE KAN WIC MPEG4 Tektronix Upgrade Deployment POR20 | CE | KAN | WIC | Wichita | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH CE KAN WIC MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 2 | 2020-07-15 | 2020-08-30 | 2020-09-30 | SN-0692 | 2020-06-30 | Chg
44927 | MTCH VA NVA MFD Tektronix Upgrade Deployment POR20 | VA | NVA | MFD | Merrifield | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH VA NVA MFD MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-08-07 | 2020-08-30 | 2020-09-30 | SN-0800 | 2020-07-31 | Chg
59522 | R PHY_CCAP_CHD_RPHY CCAP Licenses-1 | SW | ARZ | CHD | Chandler | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ CHD RPHY CCAP Deployment POR20 | License | CCAP license | 866 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
75187 | R PHY_CCAP_FAY_RPHY CCAP Licenses_1 | CE | NWA | FAY | Fayetteville | R PHY | POInt | Yes | Yes | R PHY CE NWA FAY RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
44876 | MTCH CE OKC OKC Tektronix Upgrade Deployment POR20 | CE | OKC | OKC | OKC MTC | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH CE OKC OKC MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 2 | 2020-07-15 | 2020-08-30 | 2020-09-30 | SN-0692 | 2020-06-30 | Chg
44926 | MTCH NE CON MAN Tektronix Upgrade Deployment POR20 | NE | CON | MAN | Manchester | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH NE CON MAN MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | SN-0692 | 2020-06-30 | Chg
75187 | R PHY_CCAP_TUL_RPHY CCAP Licenses_1 | CE | TUL | TUL | Tulsa | R PHY | POInt | Yes | Yes | R PHY CE TUL TUL RPHY CCAP Deployment POR20 | License | CCAP license | 2165 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
44875 | MTCH SE GCT PNS Tektronix Upgrade Deployment POR20 | SE | GCT | PNS | Pensacola with (Insite tower) | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH SE GCT PNS MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | SN-0692 | 2020-06-30 | Chg
44875 | MTCH SE LFY LFY Tektronix Upgrade Deployment POR20 | SE | LFY | LFY | Lafayette | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH SE LFY LFY MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | SN-0692 | 2020-06-30 | Chg
59522 | R PHY_CCAP_NSC_RPHY CCAP Licenses-1 | SW | ARZ | NSC | North Scottsdale | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ NSC RPHY CCAP Deployment POR20 | License | CCAP license | 26 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_BUK_RPHY CCAP Licenses-1 | SW | ARZ | BUK | Buckeye | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ BUK RPHY CCAP Deployment POR20 | License | CCAP license | 78 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_ERN_RPHY CCAP Licenses-1 | SW | LAS | ERN | Ernest May | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | License | CCAP license | 624 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
44875 | MTCH SE GAN GNS Tektronix Upgrade Deployment POR20 | SE | GAN | GNS | Gainesville | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH SE GAN GNS MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-08-07 | 2020-08-30 | 2020-09-30 | SN-0800 | 2020-07-31 | Chg
74548 | R PHY_CCAP_CHS_RPHY CCAP Licenses-1 | VA | HRD | CHS | Chesapeake | R PHY | POInt | Yes | Yes | R PHY VA HRD CHS RPHY CCAP Augment POR20 | License | CCAP license | 121 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
59745 | R PHY_CCAP_ESC_RPHY CCAP Licenses-1 | CA | SAN | ESC | Escondido | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN ESC RPHY CCAP Deployment POR20 | License | CCAP license | 233 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
59745 | R PHY_CCAP_DWN_RPHY CCAP Licenses-1 | CA | SAN | DWN | Downtown | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN DWN RPHY CCAP Deployment POR20 | License | CCAP license | 234 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
44926 | MTCH NE RHD WWK Tektronix Upgrade Deployment POR20 | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH NE RHD WWK MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 2 | 2020-07-15 | 2020-08-30 | 2020-09-30 | SN-0692 | 2020-06-30 | Chg
35169 | MRTR NCS-Growth-ALI-100G Grow | SW | LAS | ALI | Aliante | Metro Routers | POInt | Yes | Yes | MRTR SW ARZ MSA 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-07-01 | 2020-08-30 | 2020-09-30 | SN-0158 | 2020-02-06 | New
59522 | R PHY_CCAP_BEL_RPHY CCAP Licenses-1 | SW | ARZ | BEL | Bell | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ BEL RPHY CCAP Deployment POR20 | License | CCAP license | 632 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
44875 | MTCH SE MGA MCN Tektronix Upgrade Deployment POR20 | SE | MGA | MCN | Macon | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH SE MGA MCN MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 2 | 2020-07-15 | 2020-08-30 | 2020-09-30 | SN-0692 | 2020-06-30 | Chg
59522 | R PHY_CCAP_SSC_RPHY CCAP Licenses-1 | SW | ARZ | SSC | South Scottsdale | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ SSC RPHY CCAP Deployment POR20 | License | CCAP license | 906 | 2020-07-15 | 2020-08-30 | 2020-08-30 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_SSC_OTDR_1 | SW | ARZ | SSC | South Scottsdale | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ SSC RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
35174 | MRTR SLR-New-LFY-SLR-ASR9906 | SE | LFY | LFY | Lafayette | Metro Routers | POInt | Yes | Yes | MRTR SE LFY LFY SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-08-31 | 2020-12-31 | SN-0662 | 2020-06-14 | Chg
34623 | Chandler-OCML-IXR | SW | ARZ | CHD | Chandler | CB - Metro Core | POInt | Yes | Yes | CBMC SW ARZ CHD OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-08-31 |  | SN-0618 | 2020-06-05 | Chg
59522 | R PHY_CCAP_BEL_OTDR_1 | SW | ARZ | BEL | Bell | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ BEL RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
59745 | R PHY_CCAP_RSM_OTDR_1 | CA | ORG | RSM | Rancho Santa Margarita | RSPD - CCAP | POInt | Yes | Yes | R PHY CA ORG RSM RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
75187 | R PHY_CCAP_BVL_OTDR_1 | CE | NWA | BVL | Bentonville | R PHY | POInt | Yes | Yes | R PHY CE NWA BVL RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
59745 | R PHY_CCAP_DWN_OTDR_1 | CA | SAN | DWN | Downtown | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN DWN RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
34622 | CB Transport - New Router Chula Vista - ELC - Optics | CA | SAN | ELC | El Cajon | CB - Metro Core | POInt | Yes | Yes | CBMC CA SAN ELC Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-06-15 | 2020-08-31 |  | SN-0796 | 2020-07-31 | Chg
34601 | ENFDBSPA01.CT.RI-ROUTER | NE | CON | ENF | Enfield | CB - Metro Core | POInt | Yes | Yes | CBMC NE CON ENF ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 1 | 2020-01-15 | 2020-08-31 |  | SN-0944 | 2020-09-25 | Chg
34622 | CB Transport - New Router Chula Vista - FED - Optics | CA | SAN | FED | Federal | CB - Metro Core | POInt | Yes | Yes | CBMC CA SAN FED Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-06-15 | 2020-08-31 |  | SN-0796 | 2020-07-31 | Chg
74548 | R PHY_CCAP_CHS_OTDR_1 | VA | HRD | CHS | Chesapeake | R PHY | POInt | Yes | Yes | R PHY VA HRD CHS RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
59522 | R PHY_CCAP_BUK_OTDR_1 | SW | ARZ | BUK | Buckeye | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ BUK RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
59522 | R PHY_CCAP_ERN_OTDR_1 | SW | LAS | ERN | Ernest May | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
59522 | R PHY_CCAP_NSC_OTDR_1 | SW | ARZ | NSC | North Scottsdale | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ NSC RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
59522 | R PHY_CCAP_BLU_OTDR_1 | SW | LAS | BLU | Blue Diamond | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS BLU RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
59522 | R PHY_CCAP_CHD_OTDR_1 | SW | ARZ | CHD | Chandler | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ CHD RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
75187 | R PHY_CCAP_FAY_OTDR_1 | CE | NWA | FAY | Fayetteville | R PHY | POInt | Yes | Yes | R PHY CE NWA FAY RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
74548 | R PHY_CCAP_LTF_OTDR_1 | VA | HRD | LTF | Lightfoot | R PHY | POInt | Yes | Yes | R PHY VA HRD LTF RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
75246 | R PHY_CCAP_CLR_RPHY CCAP Licenses_Q2 NC Video | SE | NOR | CLR | Metairie | R PHY | POInt | Yes | Yes | R PHY SE NOR CLR RPHY - CCAP Initial Deployment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-08-31 | 2020-07-31 | SN-0811 | 2020-08-07 | Chg
75246 | R PHY_CCAP_CLR_OTDR_1 | SE | NOR | CLR | Metairie | R PHY | POInt | Yes | Yes | R PHY SE NOR CLR RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-15 | 2020-08-31 |  | SN-0811 | 2020-08-07 | Chg
75246 | R PHY_CCAP_CLR_RPHY Bundled Solution V3_44119 | SE | NOR | CLR | Metairie | R PHY | POInt | Yes | Yes | R PHY SE NOR CLR RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-01-15 | 2020-08-31 |  | SN-0811 | 2020-08-07 | Chg
75246 | R PHY_CCAP_CLR_Boundary_Clocks_44119 | SE | NOR | CLR | Metairie | R PHY | POInt | Yes | Yes | R PHY SE NOR CLR RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-01-15 | 2020-08-31 |  | SN-0811 | 2020-08-07 | Chg
59745 | R PHY_CCAP_OCE_OTDR_1 | CA | SAN | OCE | Oceanside | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN OCE RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
59745 | R PHY_CCAP_ELC_OTDR_1 | CA | SAN | ELC | El Cajon | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN ELC RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
34604 | BTRGLA741AW-24BTRMTC7750X01-ROUTER | SE | BTR | BTR | Baton Rouge | CB - Metro Core | POInt | Yes | Yes | CBMC SE BTR BTR ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-08-31 |  | SN-0618 | 2020-06-05 | Chg
74548 | R PHY_CCAP_NWP_OTDR_1 | VA | HRD | NWP | Newport News | R PHY | POInt | Yes | Yes | R PHY VA HRD NWP RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
74548 | R PHY_CCAP_VBC_OTDR_1 | VA | HRD | VBC | Virginia Beach | R PHY | POInt | Yes | Yes | R PHY VA HRD VBC RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
34622 | CB Transport - New Router Downtown (SD) - DWN - Optics | CA | SAN | DWN | Downtown | CB - Metro Core | POInt | Yes | Yes | CBMC CA SAN DWN Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-06-15 | 2020-08-31 |  | SN-0819 | 2020-08-14 | Chg
59522 | R PHY_CCAP_VLY_RPHY Unbundled Solution V2_44027 | SW | LAS | VLY | Valley | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS VLY RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 2 | 2020-07-15 | 2020-08-31 | 2020-08-31 | SN-0550 | 2020-05-12 | Chg
59522 | R PHY_CCAP_VLY_OTDR_1 | SW | LAS | VLY | Valley | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS VLY RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
34622 | CB Transport - New Router Chula Vista - CHU - Optics | CA | SAN | CHU | Chula Vista | CB - Metro Core | POInt | Yes | Yes | CBMC CA SAN CHU Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-06-15 | 2020-08-31 |  | SN-0796 | 2020-07-31 | Chg
59745 | R PHY_CCAP_FED_OTDR_1 | CA | SAN | FED | Federal | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN FED RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
35175 | NEXUS-GRB-3048-02 | NE | CON | GRB | Granby | Metro Routers | POInt | Yes | Yes | MRTR NE CON GRB Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 | 2020-07-01 | 2020-08-31 | 2020-09-30 | SN-0555 | 2020-05-12 | New
35175 | NEXUS-GRB-93108-02 | NE | CON | GRB | Granby | Metro Routers | POInt | Yes | Yes | MRTR NE CON GRB Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 2 | 2020-07-01 | 2020-08-31 | 2020-09-30 | SN-0555 | 2020-05-12 | New
35175 | NEXUS-GRB-93180-02 | NE | CON | GRB | Granby | Metro Routers | POInt | Yes | Yes | MRTR NE CON GRB Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-07-01 | 2020-08-31 | 2020-09-30 | SN-0555 | 2020-05-12 | New
75243 | RPHY MRTR-Growth-CLR-CIN MGMT-2K | SE | NOR | CLR | Metairie | R PHY | POInt | Yes | Yes | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-01-15 | 2020-08-31 | 2020-06-30 | SN-0810 | 2020-08-07 | Chg
75243 | RPHY MRTR-New-CLR-CIN-ATX-OCML | SE | NOR | CLR | Metairie | R PHY | POInt | Yes | Yes | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 40 | 2020-05-15 | 2020-08-31 | 2020-06-30 | SN-0810 | 2020-08-07 | Chg
75243 | RPHY MRTR-New-CLR-CIN-Exfo-Optical Switch | SE | NOR | CLR | Metairie | R PHY | POInt | Yes | Yes | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 4 | 2020-05-15 | 2020-08-31 | 2020-06-30 | SN-0810 | 2020-08-07 | Chg
75243 | RPHY MRTR-New-CLR-CIN-DPA-5200 (100G DPIC) | SE | NOR | CLR | Metairie | R PHY | POInt | Yes | Yes | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-01-15 | 2020-08-31 | 2020-06-30 | SN-0810 | 2020-08-07 | Chg
75243 | RPHY MRTR-New-CLR-CIN-RPA-5110 | SE | NOR | CLR | Metairie | R PHY | POInt | Yes | Yes | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-01-15 | 2020-08-31 | 2020-06-30 | SN-0810 | 2020-08-07 | Chg
75243 | RPHY MRTR-New-CLR-CIN-RPA2-5110 | SE | NOR | CLR | Metairie | R PHY | POInt | Yes | Yes | R PHY SE NOR CLR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 8 | 2020-05-15 | 2020-08-31 | 2020-08-31 | SN-0810 | 2020-08-07 | Chg
59522 | R PHY_CCAP_MSA_OTDR_1 | SW | ARZ | MSA | Mesa | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ MSA RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
59522 | R PHY_CCAP_FWL_OTDR_1 | SW | ARZ | FWL | Fowler | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ FWL RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
74548 | R PHY_CCAP_FBG_RPHY Bundled Solution V3_44119 | VA | NVA | FBG | Fredericksburg | R PHY | POInt | Yes | Yes | R PHY VA NVA FBG RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-05-01 | 2020-08-31 |  | SN-0605 | 2020-05-22 | Chg
74548 | R PHY_CCAP_FBG_Boundary_Clocks_44119 | VA | NVA | FBG | Fredericksburg | R PHY | POInt | Yes | Yes | R PHY VA NVA FBG RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-05-15 | 2020-08-31 |  | SN-0605 | 2020-05-22 | Chg
74548 | R PHY_CCAP_FBG_D9485_44119 | VA | NVA | FBG | Fredericksburg | R PHY | POInt | Yes | Yes | R PHY VA NVA FBG RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-05-01 | 2020-08-31 |  | SN-0605 | 2020-05-22 | Chg
74548 | R PHY_CCAP_FBG_OTDR_1 | VA | NVA | FBG | Fredericksburg | R PHY | POInt | Yes | Yes | R PHY VA NVA FBG RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
59522 | R PHY_CCAP_ALI_OTDR_1 | SW | LAS | ALI | Aliante | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS ALI RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
34601 | MNCHBSPA01.CT.RI-ROUTER | NE | CON | MAN | Manchester | CB - Metro Core | POInt | Yes | Yes | CBMC NE CON MAN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 1 | 2020-01-15 | 2020-08-31 |  | SN-0782 | 2020-07-27 | Chg
59745 | R PHY_CCAP_CHU_OTDR_1 | CA | SAN | CHU | Chula Vista | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN CHU RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
75187 | R PHY_CCAP_QNC_OTDR_1 | CE | TUL | QNC | Quincy | R PHY | POInt | Yes | Yes | R PHY CE TUL QNC RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
59522 | R PHY_CCAP_PNL_OTDR_1 | SW | ARZ | PNL | Pinal County | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ PNL RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
59744 | RPHY MRTR-New-OSB-CIN MGMT-2K | SW | LAS | OSB | Oso Blanca | R PHY | POInt | Yes | Yes | R PHY SW LAS OSB RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-02-05 | 2020-08-31 | 2020-08-31 | SN-0640 | 2020-06-06 | Chg
59744 | RPHY MRTR-New-OSB-CIN-DPA-5200 (100G DPIC) | SW | LAS | OSB | Oso Blanca | R PHY | POInt | Yes | Yes | R PHY SW LAS OSB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-02-05 | 2020-08-31 | 2020-08-31 | SN-0640 | 2020-06-06 | Chg
59744 | RPHY MRTR-New-OSB-CIN-RPA-5110 | SW | LAS | OSB | Oso Blanca | R PHY | POInt | Yes | Yes | R PHY SW LAS OSB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-02-05 | 2020-08-31 | 2020-08-31 | SN-0640 | 2020-06-06 | Chg
59522 | R PHY_CCAP_TEN_OTDR_1 | SW | LAS | TEN | Tenaya | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
75187 | R PHY_CCAP_OKC_OTDR_1 | CE | OKC | OKC | OKC MTC | R PHY | POInt | Yes | Yes | R PHY CE OKC OKC RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
74548 | R PHY_CCAP_NRF_OTDR_1 | VA | HRD | NRF | Norfolk | R PHY | POInt | Yes | Yes | R PHY VA HRD NRF RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
74548 | R PHY_CCAP_OCN_OTDR_1 | VA | HRD | OCN | Oceana | R PHY | POInt | Yes | Yes | R PHY VA HRD OCN RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
34604 | Abbeville-OCML-IXR | SE | LFY | ABV | Abbeville | CB - Metro Core | POInt | Yes | Yes | CBMC SE LFY ABV OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-08-31 |  | SN-0771 | 2020-07-20 | Chg
34623 | S Scottsdale-OCML-IXR | SW | ARZ | SSC | South Scottsdale | CB - Metro Core | POInt | Yes | Yes | CBMC SW ARZ SSC OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-08-31 |  | SN-0796 | 2020-07-31 | Chg
59522 | R PHY_CCAP_OSB_OTDR_1 | SW | LAS | OSB | Oso Blanca | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
75246 | R PHY_CCAP_LFY_OTDR_1 | SE | LFY | LFY | Lafayette | R PHY | POInt | Yes | Yes | R PHY SE LFY LFY RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
75187 | R PHY_CCAP_ELK_OTDR_1 | CE | OMA | ELK | Elkhorn | R PHY | POInt | Yes | Yes | R PHY CE OMA ELK RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
74548 | R PHY_CCAP_PRA_OTDR_1 | VA | HRD | PRA | Princess Anne | R PHY | POInt | Yes | Yes | R PHY VA HRD PRA RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
59745 | R PHY_CCAP_VST_OTDR_1 | CA | SAN | VST | Vista | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN VST RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
75245 | RPHY MRTR-Growth-BAR-CIN-RPA-5110 | CE | TUL | BAR | Broken Arrow | R PHY | POInt | Yes | Yes | R PHY CE TUL BAR RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 3 | 2020-01-01 | 2020-08-31 | 2020-08-31 | SN-0612 | 2020-05-29 | Chg
75187 | R PHY_CCAP_BAR_OTDR_1 | CE | TUL | BAR | Broken Arrow | R PHY | POInt | Yes | Yes | R PHY CE TUL BAR RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
78091 | VCDR CA SAN FED Voice HDT Decom POR20 | CA | SAN | FED | Federal | Voice Decom and Refortification | POInt | Yes | Yes | VCDR CA SAN FED Voice HDT Decom POR20 | Labor | No Equipment | 12 | 2020-04-21 | 2020-08-31 |  | SN-0496 | 2020-04-29 | New
59522 | R PHY_CCAP_PEO_OTDR_1 | SW | ARZ | PEO | Peoria | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ PEO RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
59522 | R PHY_CCAP_TUC_OTDR_1 | SW | ARZ | TUC | Tucson | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ TUC RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
59522 | R PHY_CCAP_HEN_OTDR_1 | SW | LAS | HEN | Henderson | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS HEN RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
75187 | R PHY_CCAP_ONA_OTDR_1 | CE | OMA | ONA | North (OM) | R PHY | POInt | Yes | Yes | R PHY CE OMA ONA RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
59522 | R PHY_CCAP_MCD_OTDR_1 | SW | ARZ | MCD | McDowell | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ MCD RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
34623 | PEORSYSA01-ROUTER | SW | ARZ | PEO | Peoria | CB - Metro Core | POInt | Yes | Yes | CBMC SW ARZ PEO ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-03-15 | 2020-08-31 |  | SN-0618 | 2020-06-05 | Chg
59745 | R PHY_CCAP_PWY_OTDR_1 | CA | SAN | PWY | Poway | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN PWY RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
75187 | R PHY_CCAP_WLK_OTDR_1 | CE | OKC | WLK | Walker Hub | R PHY | POInt | Yes | Yes | R PHY CE OKC WLK RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
35174 | MRTR SLR-New-ABV-SLR-ASR9906 | SE | LFY | ABV | Abbeville | Metro Routers | POInt | Yes | Yes | MRTR SE LFY ABV SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-08-31 | 2020-12-31 | SN-0662 | 2020-06-14 | Chg
34608 | RONLVA3100W-A702317750-ROUTER | VA | ROA | RON | Roanoke | CB - Metro Core | POInt | Yes | Yes | CBMC VA ROA RON ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-08-31 |  | SN-0782 | 2020-07-27 | Chg
74548 | R PHY_CCAP_PTM_OTDR_1 | VA | HRD | PTM | Portsmouth (VA) | R PHY | POInt | Yes | Yes | R PHY VA HRD PTM RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
75246 | R PHY_CCAP_MCY_OTDR_1 | SE | NOR | MCY | Mid-City | R PHY | POInt | Yes | Yes | R PHY SE NOR MCY RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
75187 | R PHY_CCAP_CLH_OTDR_1 | CE | OKC | CLH | County Line | R PHY | POInt | Yes | Yes | R PHY CE OKC CLH RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
34636 | BWM_FWB_MSSA_Spectrum Phase II Start | SE | GCT | FWB | Ft. Walton Beach with (Insite tower) | Bandwidth Management | POInt | Yes | No | BWM SE GCT FWB MSSA Augment POR20 v2 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-09-02 | SN-0703 | 2020-06-30 | Chg
34642 | BWM_SOU_MSSA_Spectrum Phase II Start | CE | OMA | SOU | South (OM) | Bandwidth Management | POInt | Yes | No | BWM CE OMA SOU MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-09-10 | SN-0703 | 2020-06-30 | Chg
75788 | CDN Deploy 25 | COR | COR | DDR | Duke Drive | CDN | POInt | Yes | No | CDN CO -CO DDR Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 4 | 2020-02-01 | 2020-08-31 | 2020-09-15 | SN-0803 | 2020-08-07 | Chg
34636 | BWM_PNS_MSSA_Spectrum Phase II Start | SE | GCT | PNS | Pensacola with (Insite tower) | Bandwidth Management | POInt | Yes | No | BWM SE GCT PNS MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-09-02 | SN-0703 | 2020-06-30 | Chg
75658 | VA-MCN-1x Juniper EX4600 | SE | MGA | MCN | Macon | Visibility Architecture | POInt | Yes | No | VIA SE MGA MCN Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-07-01 | 2020-08-31 | 2020-09-14 | SN-0094 | 2020-02-06 | Chg
34642 | BWM_CBL_MSSA_Spectrum Phase II Start | CE | OMA | CBL | Council Bluffs | Bandwidth Management | POInt | Yes | No | BWM CE OMA CBL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-09-10 | SN-0703 | 2020-06-30 | Chg
44926 | MTCH NE RHD LNC HFC Receiver Deployment POR20 | NE | RHD | LNC | Lincoln | MTC HE - Hub Signaling | POInt | Yes | No | MTCH NE RHD LNC HFC Receiver Deployment POR20 | Chassis | Receiver (1 RU) | 1 | 2020-07-06 | 2020-08-31 |  | SN-0021 | 2020-02-06 | Chg
75655 | Arbor 12 | SE | MGA | MCN | Macon | Arbor DDoS | POInt | Yes | No | DDoS SE MGA MCN Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-07-17 | 2020-08-31 | 2020-09-14 | SN-0107 | 2020-02-06 | Chg
34642 | BWM_ONA_MSSA_Spectrum Phase II Start | CE | OMA | ONA | North (OM) | Bandwidth Management | POInt | Yes | No | BWM CE OMA ONA MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-09-10 | SN-0703 | 2020-06-30 | Chg
75187 | R PHY_CCAP_SOU_OTDR_1 | CE | OMA | SOU | South (OM) | R PHY | POInt | Yes | No | R PHY CE OMA SOU RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
59745 | R PHY_CCAP_PAV_OTDR_1 | CA | ORG | PAV | Palos Verdes | RSPD - CCAP | POInt | Yes | No | R PHY CA ORG PAV RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
59745 | R PHY_CCAP_DNP_OTDR_1 | CA | ORG | DNP | Dana Point | RSPD - CCAP | POInt | Yes | No | R PHY CA ORG DNP RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
34636 | BWM_CRV_MSSA_Spectrum Phase II Start | SE | GCT | CRV | Crestview | Bandwidth Management | POInt | Yes | No | BWM SE GCT CRV MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-09-02 | SN-0703 | 2020-06-30 | Chg
75187 | R PHY_CCAP_OWA_OTDR_1 | CE | TUL | OWA | Owasso | R PHY | POInt | Yes | No | R PHY CE TUL OWA RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
59745 | R PHY_CCAP_ORG_OTDR_1 | CA | ORG | ORG | Orange | RSPD - CCAP | POInt | Yes | No | R PHY CA ORG ORG RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
75187 | R PHY_CCAP_YAL_OTDR_1 | CE | TUL | YAL | Yale | R PHY | POInt | Yes | No | R PHY CE TUL YAL RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
34636 | BWM_DES_MSSA_Spectrum Phase II Start | SE | GCT | DES | Destin | Bandwidth Management | POInt | Yes | No | BWM SE GCT DES MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-09-02 | SN-0703 | 2020-06-30 | Chg
34642 | BWM_WES_MSSA_Spectrum Phase II Start | CE | OMA | WES | West (OM) | Bandwidth Management | POInt | Yes | No | BWM CE OMA WES MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-09-10 | SN-0703 | 2020-06-30 | Chg
34642 | BWM_ELK_MSSA_Spectrum Phase II Start | CE | OMA | ELK | Elkhorn | Bandwidth Management | POInt | Yes | No | BWM CE OMA ELK MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-09-10 | SN-0703 | 2020-06-30 | Chg
34642 | BWM_BLV_MSSA_Spectrum Phase II Start | CE | OMA | BLV | Bellevue | Bandwidth Management | POInt | Yes | No | BWM CE OMA BLV MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-09-10 | SN-0703 | 2020-06-30 | Chg
75844 | NE CLE CLV Meet Me Rack Augment POR20 | NE | CLE | CLV | Cleveland | MTC Fiber and Rack Management | POInt | Yes | No | MVFM NE CLE CLV Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-06-08 | 2020-08-31 | 2020-09-30 | SN-0793 | 2020-08-20 | Chg
75788 | CDN Deploy 22 | SE | MGA | MCN | Macon | CDN | POInt | Yes | No | CDN SE MGA MCN Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-07-01 | 2020-08-31 | 2020-09-14 | SN-0803 | 2020-08-07 | Chg
75758 | Upgrade Prod E-XMS Systems to 5.7.5 | COR | COR | ATL | Atlanta | Voice Monitoring and Analytics | POInt | Yes | No | VMA CO -CO ATL Empirix Life Cycle Deployment POR20 | Labor | Other | 1 | 2020-07-10 | 2020-08-31 |  | SB-0140 | 2020-05-28 | Chg
59745 | R PHY_CCAP_AVJ_OTDR_1 | CA | ORG | AVJ | Aliso Viejo | RSPD - CCAP | POInt | Yes | No | R PHY CA ORG AVJ RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
59745 | R PHY_CCAP_IRV_OTDR_1 | CA | ORG | IRV | Irvine | RSPD - CCAP | POInt | Yes | No | R PHY CA ORG IRV RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-08-31 |  | SN-0605 | 2020-05-22 | New
75658 | VA-PRV-1x Juniper EX4600 | NE | RHD | PRV | Providence | Visibility Architecture | POInt | Yes | No | VIA NE RHD PRV Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-07-01 | 2020-08-31 | 2020-08-24 | SN-0094 | 2020-02-06 | Chg
34636 | BWM_NCV_MSSA_Spectrum Phase II Start | SE | GCT | NCV | Niceville | Bandwidth Management | POInt | Yes | No | BWM SE GCT NCV MSSA Augment POR20 v3 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-09-02 | SN-0703 | 2020-06-30 | Chg
44876 | MTCH CE OMA BLV RPHY Test Rack Deployment POR20 | CE | OMA | BLV | Bellevue | MTC HE - Hub Signaling | POInt | Yes | No | MTCH CE OMA BLV RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-07-06 | 2020-09-01 |  | SN-0219 | 2020-04-03
54571 | CFS SE GCT PNS HV-CFS Augment POR20 | SE | GCT | PNS | Pensacola with (Insite tower) | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE GCT PNS HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-09-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE NOR CLR BS-CFS Augment POR20 | SE | NOR | CLR | Metairie | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE NOR CLR BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-09-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE GAN GNS SC-CFS Augment POR20 | SE | GAN | GNS | Gainesville | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE GAN GNS SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-09-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE MGA GRY SC-CFS Augment POR20 | SE | MGA | GRY | Gray | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE MGA GRY SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-09-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE LFY STM BS-CFS Augment POR20 | SE | LFY | STM | St. Martinville | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE LFY STM BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-09-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE NOR LUL SC-CFS Augment POR20 | SE | NOR | LUL | Luling | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE NOR LUL SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-09-01 |  | SB-0023 | 2020-01-30 | New
46161 | MRTH-FWL-93180-01 | SW | ARZ | FWL | Fowler | Metro Nexus Thunder | POInt | Yes | Yes | MNEX SW ARZ FWL Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 4 | 2020-01-20 | 2020-09-01 | 2020-11-12 | SB-0237 | 2020-11-06 | Chg
46161 | MRTH-FWL-2248-01 | SW | ARZ | FWL | Fowler | Metro Nexus Thunder | POInt | Yes | Yes | MNEX SW ARZ FWL Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 9 | 2020-01-20 | 2020-09-01 | 2020-11-12 | SB-0237 | 2020-11-06 | Chg
46161 | MRTH-TUC-93180-01 | SW | ARZ | TUC | Tucson | Metro Nexus Thunder | POInt | Yes | Yes | MNEX SW ARZ TUC Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 4 | 2020-01-20 | 2020-09-01 | 2020-12-08 | SB-0237 | 2020-11-06 | Chg
46161 | MRTH-TUC-2248-01 | SW | ARZ | TUC | Tucson | Metro Nexus Thunder | POInt | Yes | Yes | MNEX SW ARZ TUC Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 7 | 2020-01-20 | 2020-09-01 | 2020-12-08 | SB-0237 | 2020-11-06 | Chg
75645 | CGN Replacement 15 | SE | GCT | PNS | Pensacola with (Insite tower) | Data Center Capacity | POInt | Yes | No | DTC SE GCT PNS CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-04-01 | 2020-09-02 |  | SN-0856 | 2020-08-21 | Chg
75645 | CGN Replacement 8 | CE | KAN | WIC | Wichita | Data Center Capacity | POInt | Yes | No | DTC CE KAN WIC CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-01-18 | 2020-09-08 |  | SN-0784 | 2020-07-27 | Chg
75788 | CDN Deploy 21 | SW | ARZ | FWL | Fowler | CDN | POInt | Yes | No | CDN SW ARZ FWL Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-06-01 | 2020-09-13 | 2020-09-30 | SN-0803 | 2020-08-07 | Chg
34635 | BWM_FBG_MSSA_Spectrum Phase II Start | VA | NVA | FBG | Fredericksburg | Bandwidth Management | POInt | Yes | No | BWM VA NVA FBG MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-09-16 | SN-0703 | 2020-06-30 | Chg
34635 | BWM_TCR_MSSA_Spectrum Phase II Start | VA | NVA | TCR | Tysons Corner | Bandwidth Management | POInt | Yes | No | BWM VA NVA TCR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-06-01 | 2020-09-14 | 2020-09-16 | SN-0703 | 2020-06-30 | Chg
34635 | BWM_FLK_MSSA_Spectrum Phase II Start | VA | NVA | FLK | Fair Lakes | Bandwidth Management | POInt | Yes | No | BWM VA NVA FLK MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-09-16 | SN-0703 | 2020-06-30 | Chg
34635 | BWM_GCR_MSSA_Spectrum Phase II Start | VA | NVA | GCR | Gunston | Bandwidth Management | POInt | Yes | No | BWM VA NVA GCR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-09-16 | SN-0703 | 2020-06-30 | Chg
34635 | BWM_FST_MSSA_Spectrum Phase II Start | VA | NVA | FST | Fairfax Station | Bandwidth Management | POInt | Yes | No | BWM VA NVA FST MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-09-16 | SN-0703 | 2020-06-30 | Chg
34635 | BWM_RHL_MSSA_Spectrum Phase II Start | VA | NVA | RHL | Rose Hill | Bandwidth Management | POInt | Yes | No | BWM VA NVA RHL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-09-16 | SN-0703 | 2020-06-30 | Chg
34635 | BWM_MFD_MSSA_Spectrum Phase II Start | VA | NVA | MFD | Merrifield | Bandwidth Management | POInt | Yes | No | BWM VA NVA MFD MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-09-16 | SN-0703 | 2020-06-30 | Chg
34623 | CB Transport - New Router Chandler/McDowellCORA - MCD - Card Add | SW | ARZ | MCD | McDowell | CB - Metro Core | POInt | Yes | No | CBMC SW ARZ MCD Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-07-24 | 2020-09-15
34619 | CB Transport - New Router Quincy - TUL - Optics | CE | TUL | TUL | Tulsa | CB - Metro Core | POInt | Yes | No | CBMC CE TUL TUL Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-08-15 | 2020-09-15
75844 | NE CON GRB VAM Splitter Augment POR20 | NE | CON | GRB | Granby | MTC Fiber and Rack Management | POInt | Yes | No | MVFM NE CON GRB Fiber Bay Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-09-07 | 2020-09-15 | 2020-09-15
34638 | BWM_CLR_VIDEO SG_2020 DOCSIS node split-based Video SG | SE | NOR | CLR | Metairie | Bandwidth Management | POInt | Yes | No | BWM SE NOR CLR Video SG Augment POR20 v3 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-15 | 2020-09-15
75651 | PTX Add 3 | VA | ROA | RON | Roanoke | Backbone | POInt | Yes | No | BBCAP VA ROA RON PTX10 Deployment POR20 | Chassis | 1x Juniper PTX10K Chassis | 2 | 2020-05-18 | 2020-09-15 |  | SN-0785 | 2020-07-27 | Chg
34638 | BWM_ABV_MSSA_Spectrum Phase II Start | SE | LFY | ABV | Abbeville | Bandwidth Management | POInt | Yes | No | BWM SE LFY ABV Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-08-01 | 2020-09-15 | 2020-09-15 | SN-0587 | 2020-05-14 | Chg
39256 | BWM_LNC_VIDEO SG_2020 DOCSIS node split-based Video SG | NE | RHD | LNC | Lincoln | Bandwidth Management | POInt | Yes | No | BWM NE RHD LNC VIDEO SG Augment POR20 v3 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-15 | 2020-09-15
75663 | V2B COR COR DDR Executive Channel Augment POR20 | COR | COR | DDR | Duke Drive | V2B | POInt | Yes | No | V2B COR COR DDR Executive Channel Augment POR20 | Card & Optics | Exec Channel | 1 | 2020-08-06 | 2020-09-15 | 2020-10-15
34616 | CB Transport - New Router Midwest City - NOR - Card Add | CE | OKC | NOR | Norman | CB - Metro Core | POInt | Yes | No | CBMC CE OKC NOR Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-08-15 | 2020-09-15 |  | SN-0419 | 2020-04-02 | Chg
34642 | BWM_DTN_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | TUL | DTN | Downtown (TUL) | Bandwidth Management | POInt | Yes | No | BWM CE TUL DTN Video SG Augment POR20 v3 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-15 | 2020-09-15
34642 | BWM_WES_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | OMA | WES | West (OM) | Bandwidth Management | POInt | Yes | No | BWM CE OMA WES VIDEO SG Augment POR20 v4 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-15 | 2020-09-15
34642 | BWM_BLV_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | OMA | BLV | Bellevue | Bandwidth Management | POInt | Yes | No | BWM CE OMA BLV VIDEO SG Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-15 | 2020-09-15
39256 | BWM_PTH_VIDEO SG_2020 DOCSIS node split-based Video SG | NE | RHD | PTH | Portsmouth (RI) | Bandwidth Management | POInt | Yes | No | BWM NE RHD PTH VIDEO SG Augment POR20 v3 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-15 | 2020-09-15
34636 | BWM_HLT_VIDEO SG_2020 DOCSIS node split-based Video SG | SE | MGA | HLT | Holt | Bandwidth Management | POInt | Yes | No | BWM SE MGA HLT Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-15 | 2020-09-15
39256 | BWM_PAW_VIDEO SG_2020 DOCSIS node split-based Video SG I | NE | RHD | PAW | Pawtucket | Bandwidth Management | POInt | Yes | No | BWM NE RHD PAW VIDEO SG Augment POR20 v3 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-15 | 2020-09-15
34945 | Metro OTN-CNY-Ciena 6500 S14 | CE | KAN | CNY | Cheney | Metro Transport | POInt | Yes | Yes | MTRN CE KAN CNY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-07-15 | 2020-09-15 | 2020-11-15 | SN-0161 | 2020-02-18 | Chg
34945 | Metro OTN-CNY-Ciena 6500 S2 | CE | KAN | CNY | Cheney | Metro Transport | POInt | Yes | Yes | MTRN CE KAN CNY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-07-15 | 2020-09-15 | 2020-11-15 | SN-0161 | 2020-02-18 | Chg
34970 | CFG MSA BS-CFG GEN GROW PROJECT - MEDIUM | SW | ARZ | MSA | Mesa | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ MSA HV-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-08-01 | 2020-09-15
34970 | CFG MSA HV-CFG GEN GROW PROJECT - MEDIUM | SW | ARZ | MSA | Mesa | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ MSA HV-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-08-01 | 2020-09-15
34619 | CB Transport - New Router Midwest City - OKC - Optics | CE | OKC | OKC | OKC MTC | CB - Metro Core | POInt | Yes | Yes | CBMC CE OKC OKC Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-08-15 | 2020-09-15
34970 | CFG CHD BS-CFG GEN GROW PROJECT - MEDIUM | SW | ARZ | CHD | Chandler | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ CHD BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-08-01 | 2020-09-15
34970 | CFG CHD DC-CFG GEN GROW PROJECT - MEDIUM | SW | ARZ | CHD | Chandler | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ CHD BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-07-01 | 2020-09-15
34619 | FAYTBSRA01-ROUTER | CE | NWA | FAY | Fayetteville | CB - Metro Core | POInt | Yes | Yes | CBMC CE NWA FAY ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-06-15 | 2020-09-15 |  | SN-0144 | 2020-02-06 | Chg
34623 | CB Transport - New Router Chandler/McDowellCORA - CHD - Card Add | SW | ARZ | CHD | Chandler | CB - Metro Core | POInt | Yes | Yes | CBMC SW ARZ CHD Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-08-15 | 2020-09-15
34619 | CB Transport - New Router Quincy - BAR - Optics | CE | TUL | BAR | Broken Arrow | CB - Metro Core | POInt | Yes | Yes | CBMC CE TUL BAR Optics Only for Cisco T5 Augment POR20 v1 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-08-15 | 2020-09-15
34608 | FRED-OCML-IXR | VA | NVA | FBG | Fredericksburg | CB - Metro Core | POInt | Yes | Yes | CBMC VA NVA FBG OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-06-15 | 2020-09-15
34619 | CB Transport - New Router Midwest City - MWC - Optics | CE | OKC | MWC | Midwest City | CB - Metro Core | POInt | Yes | Yes | CBMC CE OKC MWC Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 3 | 2020-08-15 | 2020-09-15
44876 | MTCH SE MGA MCN MPEG4 vDCM Install Deployment POR20 | SE | MGA | MCN | Macon | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH SE MGA MCN MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-03-31 | 2020-09-15 | 2021-01-15 | SN-0227 | 2020-03-30 | Chg
75645 | CGN Replacement 3 | CA | ORG | RSM | Rancho Santa Margarita | Data Center Capacity | POInt | Yes | No | DTC CA ORG RSM CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2019-12-15 | 2020-09-16 |  | SN-0784 | 2020-07-27 | Chg
75645 | CGN Replacement 19 | CE | NWA | NWA | Johnson | Data Center Capacity | POInt | Yes | No | DTC CE NWA NWA CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-04-15 | 2020-09-16 |  | SN-0784 | 2020-07-27 | Chg
34638 | BWM NOR DOCSIS Expansion 192 MHz | SE | NOR | ALG | Algiers | Bandwidth Management | POInt | Yes | No | BWM SE NOR ALG DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-09-16 | 2022-12-01 | SN-0558 | 2020-05-12 | New
34638 | BWM NOR DOCSIS Expansion 96 MHz | SE | NOR | ALG | Algiers | Bandwidth Management | POInt | Yes | No | BWM SE NOR ALG DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-09-16 | 2022-04-01 | SN-0558 | 2020-05-12 | New
39225 | CCAP blades_ GNS 1 | SE | GAN | GNS | Gainesville | DOCSIS CMTS/CCAP | POInt | Yes | No | CMTS SE GAN GNS CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-08-20 | 2020-09-20 |  | SN-0799 | 2020-07-31 | Chg
34683 | CCAP blades_ STN | NE | CON | STN | Southington | DOCSIS CMTS/CCAP | POInt | Yes | No | CMTS NE CON STN CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-08-20 | 2020-09-20 |  | SN-0799 | 2020-07-31 | Chg
34683 | CCAP blades_ RKH | NE | CON | RKH | Rocky Hill | DOCSIS CMTS/CCAP | POInt | Yes | No | CMTS NE CON RKH CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-08-20 | 2020-09-20 |  | SN-0799 | 2020-07-31 | Chg
34687 | CCAP blades_ NOR 2 | CE | OKC | NOR | Norman | DOCSIS CMTS/CCAP | POInt | Yes | No | CMTS CE OKC NOR CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-08-20 | 2020-09-20 |  | SN-0799 | 2020-07-31 | Chg
34685 | CCAP blades_ TCR 2 | VA | NVA | TCR | Tysons Corner | DOCSIS CMTS/CCAP | POInt | Yes | No | CMTS VA NVA TCR CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-08-20 | 2020-09-20 |  | SN-0799 | 2020-07-31 | Chg
34683 | CCAP blades_ LNC | NE | RHD | LNC | Lincoln | DOCSIS CMTS/CCAP | POInt | Yes | No | CMTS NE RHD LNC CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-08-20 | 2020-09-20 |  | SN-0799 | 2020-07-31 | Chg
34687 | CCAP blades_ BRD 1 | CE | TUL | BRD | Braden | DOCSIS CMTS/CCAP | POInt | Yes | No | CMTS CE TUL BRD CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-08-20 | 2020-09-20 |  | SN-0799 | 2020-07-31 | Chg
39225 | CCAP blades_ HLT | SE | MGA | HLT | Holt | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS SE MGA HLT CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-08-20 | 2020-09-20 |  | SN-0799 | 2020-07-31 | Chg
75655 | Arbor 16 | CE | NWA | NWA | Johnson | Arbor DDoS | POInt | Yes | No | DDoS CE NWA NWA Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-08-07 | 2020-09-21 | 2020-10-05 | SN-0107 | 2020-02-06 | Chg
75645 | CGN Replacement 2 | CE | OMA | OMM | Omaha | Data Center Capacity | POInt | Yes | No | DTC CE OMA OMM CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2019-12-08 | 2020-09-22 |  | SN-0856 | 2020-08-21 | Chg
78099 | VCDR SW ARZ PEO Voice HDT Decom POR20 | SW | ARZ | PEO | Peoria | Voice Decom and Refortification | POInt | Yes | Yes | VCDR SW ARZ PEO Voice HDT Decom POR20 | Labor | No Equipment | 40 | 2020-08-04 | 2020-09-22 |  | SN-0940 | 2020-09-25 | Chg
75655 | Arbor 15 | CE | TUL | TUL | Tulsa | Arbor DDoS | POInt | Yes | No | DDoS CE TUL TUL Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-08-14 | 2020-09-28 | 2020-10-12 | SN-0107 | 2020-02-06 | Chg
75788 | CDN Deploy 15 | VA | HRD | NRF | Norfolk | CDN | POInt | Yes | No | CDN VA HRD NRF Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 1 | 2020-07-01 | 2020-09-29 | 2020-10-13 | SN-0285 | 2020-02-24 | Chg
75788 | CDN Deploy 16 | VA | HRD | VBC | Virginia Beach | CDN | POInt | Yes | No | CDN VA HRD VBC Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 1 | 2020-07-01 | 2020-09-29 | 2020-10-13 | SN-0285 | 2020-02-24 | Chg
39256 | BWM_CLV_VIDEO SG_2020 DOCSIS node split-based Video SG | NE | CLE | CLV | Cleveland | Bandwidth Management | POInt | Yes | No | BWM NE CLE CLV VIDEO SG Augment POR20 v2 | Labor | No Equipment | 1 |  | 2020-09-30 | 2020-09-30 | SN-0245 | 2020-02-24 | Chg
44926 | MTCH NE RHD WWK Innotrans Unit Deployment POR20 | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | MTC HE - Hub Signaling | POInt | Yes | No | MTCH NE RHD WWK Innotrans Unit Deployment POR20 | Critical Facilities | MTC Hub Signaling | 4 | 2020-07-31 | 2020-09-30 | 2020-10-31 | SN-0852 | 2020-08-20 | Chg
75788 | CDN Deploy 27 | SW | ARZ | MSA | Mesa | CDN | POInt | Yes | No | CDN SW ARZ MSA Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-10-15 | SN-0803 | 2020-08-07 | Chg
59744 | RPHY MRTR-New-OSNAP-ERN | SW | LAS | ERN | Ernest May | R PHY | POInt | Yes | Yes | R PHY SW LAS ERN Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0487 | 2020-05-12 | New
35177 | MRTR SLR-New-NRF-SLR-ASR9906 | VA | HRD | NRF | Norfolk | Metro Routers | POInt | Yes | Yes | MRTR VA HRD NRF SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0158 | 2020-02-06 | Chg
34623 | North West-OCML-IXR | SW | LAS | TEN | Tenaya | CB - Metro Core | POInt | Yes | Yes | CBMC SW LAS TEN OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-09-30 |  | SN-0771 | 2020-07-20 | Chg
35170 | MRTR SLR-New-SAB-SLR-ASR9906 | CA | SAB | SAB | Santa Barbara | Metro Routers | POInt | Yes | Yes | MRTR CA SAB SAB SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-05 | 2020-09-30 | 2020-12-31 | SN-0158 | 2020-02-06 | Chg
78093 | VCDR CE SUN SVI Voice DMS Gateway Decom POR20 | CE | SUN | SVI | Sun Valley | Voice Decom and Refortification | POInt | Yes | Yes | VCDR CE SUN SVI Voice DMS Gateway Decom POR20 | Labor | No Equipment | 2 | 2020-05-31 | 2020-09-30 |  | SN-0644 | 2020-06-15 | Chg
59850 | RPHY MRTR-New-OSNAP-PWY | CA | SAN | PWY | Poway | R PHY | POInt | Yes | Yes | R PHY CA SAN PWY Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0487 | 2020-05-12 | New
59744 | RPHY MRTR-New-OSNAP-OSB | SW | LAS | OSB | Oso Blanca | R PHY | POInt | Yes | Yes | R PHY SW LAS OSB Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0487 | 2020-05-12 | New
59744 | RPHY MRTR-New-OSNAP-MCD | SW | ARZ | MCD | McDowell | R PHY | POInt | Yes | Yes | R PHY SW ARZ MCD Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0487 | 2020-05-12 | New
34945 | Metro OTN-HUT-Ciena 6500 S14 | CE | KAN | HUT | Hutchinson | Metro Transport | POInt | Yes | Yes | MTRN CE KAN HUT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-07-15 | 2020-09-30 | 2020-11-01 | SN-0161 | 2020-02-18 | Chg
34945 | Metro OTN-HUT-Ciena 6500 S2 | CE | KAN | HUT | Hutchinson | Metro Transport | POInt | Yes | Yes | MTRN CE KAN HUT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-11-01 | SN-0161 | 2020-02-18 | Chg
34604 | SOUTH BATON ROUGE-OCML-IXR | SE | BTR | SPC | Pecue | CB - Metro Core | POInt | Yes | Yes | CBMC SE BTR SPC OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-10-01 | 2020-09-30 |  | SN-0986 | 2020-10-14 | Chg
35177 | MRTR SLR-New-PRA-SLR-ASR9906 | VA | HRD | PRA | Princess Anne | Metro Routers | POInt | Yes | Yes | MRTR VA HRD PRA SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0158 | 2020-02-06 | Chg
59744 | RPHY MRTR-New-OSNAP-FWL | SW | ARZ | FWL | Fowler | R PHY | POInt | Yes | Yes | R PHY SW ARZ FWL Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0487 | 2020-05-12 | New
35172 | MRTR SLR-New-PNS-SLR-ASR9906 | SE | GCT | PNS | Pensacola with (Insite tower) | Metro Routers | POInt | Yes | Yes | MRTR SE GCT PNS SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | SN-0662 | 2020-06-14 | Chg
35176 | MRTR SLR-New-QNC-SLR-ASR9906 | CE | TUL | QNC | Quincy | Metro Routers | POInt | Yes | Yes | MRTR CE TUL QNC SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-09-30 | 2020-09-30 | SN-0638 | 2020-06-05 | Chg
35173 | MRTR SW LAS VLY 100G Grow Augment POR20 | SW | LAS | VLY | Valley | Metro Routers | POInt | Yes | Yes | MRTR SW LAS VLY 100G Grow Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0555 | 2020-05-12 | New
59744 | RPHY MRTR-New-OSNAP-BEL | SW | ARZ | BEL | Bell | R PHY | POInt | Yes | Yes | R PHY SW ARZ BEL Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0487 | 2020-05-12 | New
34604 | MACNBSRA01.mc.at.cox.net-ROUTER | SE | MGA | MCN | Macon | CB - Metro Core | POInt | Yes | Yes | CBMC SE MGA MCN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-03-15 | 2020-09-30 |  | SN-0618 | 2020-06-05 | Chg
35176 | MRTR OOB-New-WEH-OOB Server | CE | OKC | WEH | West (OKC) | Metro Routers | POInt | Yes | Yes | MRTR CE OKC WEH OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0158 | 2020-02-06 | Chg
59744 | RPHY MRTR-New-OSNAP-MSA | SW | ARZ | MSA | Mesa | R PHY | POInt | Yes | Yes | R PHY SW ARZ MSA Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0487 | 2020-05-12 | New
35170 | MRTR NCS-Growth-DWN-NCS Line Card | CA | SAN | DWN | Downtown | Metro Routers | POInt | Yes | Yes | MRTR CA SAN DWN NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-05 | 2020-09-30 | 2020-12-31 | SN-0555 | 2020-05-12 | New
75788 | CDN Deploy 20 | SW | ARZ | TUC | Tucson | CDN | POInt | Yes | No | CDN SW ARZ TUC Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-06-01 | 2020-09-30 | 2020-10-15 | SN-0803 | 2020-08-07 | Chg
35169 | MRTR NCS-Growth-FWL-NCS Line Card | SW | ARZ | FWL | Fowler | Metro Routers | POInt | Yes | No | MRTR SW ARZ FWL NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
44926 | MTCH NE RHD PAW HFC Receiver Deployment POR20 | NE | RHD | PAW | Pawtucket | MTC HE - Hub Signaling | POInt | Yes | No | MTCH NE RHD PAW HFC Receiver Deployment POR20 | Chassis | Receiver (1 RU) | 1 | 2020-07-06 | 2020-09-30 |  | SN-0607 | 2020-05-28 | Chg
78067 | Solarwinds | SW | LAS | TEN | Tenaya | Hospitality Network | POInt | Yes | No | HN SW LAS TEN Solarwinds Augment POR20 | Labor | No Equipment | 1 | 2020-08-01 | 2020-09-30 |  | SB-0108 | 2020-04-24 | New
34604 | Metairie-OCML-IXR | SE | NOR | CLR | Metairie | CB - Metro Core | POInt | Yes | No | CBMC SE GLA CLR OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-10-01 | 2020-09-30 |  | SN-0819 | 2020-08-14 | Chg
75244 | RPHY MRTR-New-PRV-CIN-ATX-OCML | NE | RHD | PRV | Providence | R PHY | POInt | Yes | No | R PHY NE RHD PRV RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-09-30 | 2020-10-31 | SN-0640 | 2020-06-06 | Chg
34635 | BWM_TCR_VIDEO SG_2020 DOCSIS node split-based Video SG | VA | NVA | TCR | Tysons Corner | Bandwidth Management | POInt | Yes | No | BWM VA NVA TCR Video SG Augment POR20 v2 | Labor | No Equipment | 1 |  | 2020-09-30 | 2020-09-30 | SN-0245 | 2020-02-24 | Chg
75658 | VA-TUL-1x Juniper EX4600 | CE | TUL | TUL | Tulsa | Visibility Architecture | POInt | Yes | No | VIA CE TUL TUL Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-08-01 | 2020-09-30 | 2020-10-12 | SN-0094 | 2020-02-06 | Chg
44926 | MTCH NE RHD PAW RF Passive Splitter Deployment POR20 | NE | RHD | PAW | Pawtucket | MTC HE - Hub Signaling | POInt | Yes | No | MTCH NE RHD PAW RF Passive Splitter Deployment POR20 | Chassis | 8-way splitter | 1 | 2020-07-06 | 2020-09-30 |  | SN-0607 | 2020-05-28 | Chg
44926 | MTCH NE CLE CLV Innotrans Unit Deployment POR20 | NE | CLE | CLV | Cleveland | MTC HE - Hub Signaling | POInt | Yes | No | MTCH NE CLE CLV Innotrans Unit Deployment POR20 | Critical Facilities | MTC Hub Signaling | 4 | 2020-07-31 | 2020-09-30 | 2020-10-31 | SN-0852 | 2020-08-20 | Chg
75788 | CDN Deploy 18 | SW | ARZ | BEL | Bell | CDN | POInt | Yes | No | CDN SW ARZ BEL Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-05-01 | 2020-09-30 | 2020-10-15 | SN-0803 | 2020-08-07 | Chg
44926 | MTCH NE CON MAN Innotrans Unit Deployment POR20 | NE | CON | MAN | Manchester | MTC HE - Hub Signaling | POInt | Yes | No | MTCH NE CON MAN Innotrans Unit Deployment POR20 | Critical Facilities | MTC Hub Signaling | 4 | 2020-07-31 | 2020-09-30 | 2020-10-31 | SN-0852 | 2020-08-20 | Chg
75658 | VA-NWA-1x Juniper EX4600 | CE | NWA | NWA | Johnson | Visibility Architecture | POInt | Yes | No | VIA CE NWA NWA Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-08-01 | 2020-09-30 | 2020-10-05 | SN-0094 | 2020-02-06 | Chg
34642 | BWM_SVI_MSSA_Spectrum Phase II Start | CE | SUN | SVI | Sun Valley | Bandwidth Management | POInt | Yes | No | BWM CE SUN SVI MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | SN-0195 | 2020-01-24 | Chg
78091 | VCDR CA SAB SAB Voice Gateway Decom POR20 | CA | SAB | SAB | Santa Barbara | Voice Decom and Refortification | POInt | Yes | Yes | VCDR CA SAB SAB Voice Gateway Decom POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 |  | SN-1080 | 2020-11-20
35176 | MRTR OOB-New-SAP-OOB Server | CE | TUL | SAP | Sapulpa | Metro Routers | POInt | Yes | Yes | MRTR CE TUL SAP OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0158 | 2020-02-06 | Chg
34608 | CB Transport - New Router Fredericksburg - FLK - Optics | VA | NVA | FLK | Fair Lakes | CB - Metro Core | POInt | Yes | Yes | CBMC VA NVA FLK Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-07-15 | 2020-09-30 |  | SN-0934 | 2020-09-18 | Chg
35175 | MRTR SLR-New-PAW-SLR-ASR9906 | NE | RHD | PAW | Pawtucket | Metro Routers | POInt | Yes | Yes | MRTR NE RHD PAW SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2021-01-31 | SN-0662 | 2020-06-14 | Chg
35169 | MRTR NCS-Growth-ERN-100G Grow | SW | LAS | ERN | Ernest May | Metro Routers | POInt | Yes | Yes | MRTR SW ARZ MSA 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-08-01 | 2020-09-30 | 2020-10-30 | SN-0158 | 2020-02-06 | New
34945 | Metro OTN-DCY2-Ciena 6500 S14 | CE | KAN | DCY | Dodge City | Metro Transport | POInt | Yes | Yes | MTRN CE KAN DCY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-07-15 | 2020-09-30 | 2020-11-30 | SN-0161 | 2020-02-18 | Chg
34945 | Metro OTN-DCY2-Ciena 6500 S2 | CE | KAN | DCY | Dodge City | Metro Transport | POInt | Yes | Yes | MTRN CE KAN DCY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-07-15 | 2020-09-30 | 2020-11-30 | SN-0161 | 2020-02-18 | Chg
34945 | Metro OTN-DCY-Ciena 6500 S14 | CE | KAN | DCY | Dodge City | Metro Transport | POInt | Yes | Yes | MTRN CE KAN DCY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-07-15 | 2020-09-30 | 2020-11-30 | SN-0161 | 2020-02-18 | Chg
34945 | Metro OTN-DCY-Ciena 6500 S2 | CE | KAN | DCY | Dodge City | Metro Transport | POInt | Yes | Yes | MTRN CE KAN DCY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-11-30 | SN-0161 | 2020-02-18 | Chg
35175 | NEXUS-GLB-3048-02 | NE | CON | GLB | Glastonbury | Metro Routers | POInt | Yes | Yes | MRTR NE CON GLB Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 | 2020-07-01 | 2020-09-30 | 2020-09-30 | SN-0555 | 2020-05-12 | New
59744 | RPHY MRTR-New-OSNAP-BUK | SW | ARZ | BUK | Buckeye | R PHY | POInt | Yes | Yes | R PHY SW ARZ BUK Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0487 | 2020-05-12 | New
59744 | RPHY MRTR-New-OSNAP-PEO | SW | ARZ | PEO | Peoria | R PHY | POInt | Yes | Yes | R PHY SW ARZ PEO Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0487 | 2020-05-12 | New
74648 | RPHY MRTR-New-RON-CIN-RPA-5110 | VA | ROA | RON | Roanoke | R PHY | POInt | Yes | Yes | R PHY VA ROA RON RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-09-30 | 2020-09-30 | SN-0640 | 2020-06-06 | Chg
35174 | MRTR SLR-New-MCY-SLR-ASR9906 | SE | NOR | MCY | Mid-City | Metro Routers | POInt | Yes | Yes | MRTR SE NOR MCY SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-09-30 | 2020-12-31 | SN-0662 | 2020-06-14 | Chg
35177 | MRTR NCS-Growth-OCN-NCS Line Card | VA | HRD | OCN | Oceana | Metro Routers | POInt | Yes | Yes | MRTR VA HRD OCN 100G Grow Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0555 | 2020-05-12 | New
35185 | MRTR OOB-New-SAB-OOB Server | CA | SAB | SAB | Santa Barbara | MTC Admin | POInt | Yes | Yes | MRTR CA SAB SAB OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0158 | 2020-02-06 | New
35176 | MRTR SLR-New-OKC-SLR-ASR9906 | CE | OKC | OKC | OKC MTC | Metro Routers | POInt | Yes | Yes | MRTR CE OKC OKC SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-09-30 | 2020-09-30 | SN-0638 | 2020-06-05 | Chg
75245 | RPHY MRTR-New-GAR-CIN-NOKIA-OCML | CE | TUL | GAR | Garnett | R PHY | POInt | Yes | Yes | R PHY CE TUL GAR RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-05-15 | 2020-09-30 | 2020-09-30 | SN-0710 | 2020-06-26 | Chg
75246 | R PHY_CCAP_WRB_Boundary_Clocks_44119 | SE | MGA | WRB | Warner Robins | R PHY | POInt | Yes | Yes | R PHY SE MGA WRB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-04-15 | 2020-09-30 |  | SN-0811 | 2020-08-07 | Chg
75246 | R PHY_CCAP_WRB_RPHY Bundled Solution V3_44119 | SE | MGA | WRB | Warner Robins | R PHY | POInt | Yes | Yes | R PHY SE MGA WRB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-07-10 | 2020-09-30 | 2020-09-30 | SN-0811 | 2020-08-07 | Chg
75246 | R PHY_CCAP_WRB_OTDR_1 | SE | MGA | WRB | Warner Robins | R PHY | POInt | Yes | Yes | R PHY SE MGA WRB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-06-10 | 2020-09-30 |  | SN-0811 | 2020-08-07 | Chg
34623 | NWSTCORA01.LV.LV.COX.NET | SW | LAS | TEN | Tenaya | CB - Metro Core | POInt | Yes | Yes | CBMC SW LAS TEN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 1 | 2020-01-15 | 2020-09-30 |  | SN-0771 | 2020-07-20 | Chg
75243 | RPHY MRTR-Growth-PNS-CIN MGMT-2K | SE | GCT | PNS | Pensacola with (Insite tower) | R PHY | POInt | Yes | Yes | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-01-01 | 2020-09-30 | 2020-07-31 | SN-0881 | 2020-08-28 | Chg
75243 | RPHY MRTR-New-PNS-CIN-DPA-5200 (100G DPIC) | SE | GCT | PNS | Pensacola with (Insite tower) | R PHY | POInt | Yes | Yes | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-01-05 | 2020-09-30 |  | SN-0881 | 2020-08-28 | Chg
75243 | RPHY MRTR-New-PNS-CIN-RPA-5110 | SE | GCT | PNS | Pensacola with (Insite tower) | R PHY | POInt | Yes | Yes | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-01-05 | 2020-09-30 | 2020-07-31 | SN-0881 | 2020-08-28 | Chg
75243 | RPHY MRTR-New-PNS-CIN-ATX-OCML | SE | GCT | PNS | Pensacola with (Insite tower) | R PHY | POInt | Yes | Yes | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-05-15 | 2020-09-30 | 2020-07-31 | SN-0881 | 2020-08-28 | Chg
75243 | RPHY MRTR-New-PNS-CIN Exfo-Switch | SE | GCT | PNS | Pensacola with (Insite tower) | R PHY | POInt | Yes | Yes | R PHY SE GCT PNS RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-09-30 | 2020-07-31 | SN-0881 | 2020-08-28 | Chg
59850 | RPHY MRTR-New-OSNAP-CHU | CA | SAN | CHU | Chula Vista | R PHY | POInt | Yes | Yes | R PHY CA SAN CHU Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0487 | 2020-05-12 | New
59850 | RPHY MRTR-New-OSNAP-DNP | CA | ORG | DNP | Dana Point | R PHY | POInt | Yes | Yes | R PHY CA ORG DNP Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0487 | 2020-05-12 | New
35176 | MRTR NCS-Growth-IND-NCS Line Card | CE | TUL | IND | Indianapolis | Metro Routers | POInt | Yes | Yes | MRTR CE TUL IND NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
59744 | RPHY MRTR-New-OSNAP-CHD | SW | ARZ | CHD | Chandler | R PHY | POInt | Yes | Yes | R PHY SW ARZ CHD Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0487 | 2020-05-12 | New
34623 | OSO BLANCA-OCML-IXR | SW | LAS | OSB | Oso Blanca | CB - Metro Core | POInt | Yes | Yes | CBMC SW LAS OSB OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-09-30 |  | SN-0701 | 2020-07-02 | Chg
35175 | NEXUS-EXT-3048-01 | NE | RHD | EXT | Exeter | Metro Routers | POInt | Yes | Yes | MRTR NE RHD EXT Metro Nexus Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-30 | 2020-09-30 | SN-0555 | 2020-05-12 | New
35172 | NEXUS-PNS-2248-02 | SE | GCT | PNS | Pensacola with (Insite tower) | Metro Routers | POInt | Yes | Yes | MRTR SE GCT PNS Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2021-03-30 | SN-1037 | 2020-11-06 | Chg
35172 | NEXUS-PNS-2248-01 | SE | GCT | PNS | Pensacola with (Insite tower) | Metro Routers | POInt | Yes | Yes | MRTR SE GCT PNS Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-09-30 | SN-0555 | 2020-05-12 | New
35177 | MRTR SLR-New-PRM-SLR-ASR9906 | VA | HRD | PTM | Portsmouth (VA) | Metro Routers | POInt | Yes | Yes | MRTR VA HRD PTM SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0158 | 2020-02-06 | Chg
35173 | MRTR NCS-Growth-ERN-NCS Line Card | SW | LAS | ERN | Ernest May | Metro Routers | POInt | Yes | Yes | MRTR SW LAS ERN NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
35174 | MRTR SLR-New-ELM-SLR-ASR9906 | SE | NOR | ELM | Elmwood | Metro Routers | POInt | Yes | Yes | MRTR SE NOR ELM SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | SN-0662 | 2020-06-14 | Chg
35175 | NEXUS-WWK-2248-01 | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | Metro Routers | POInt | Yes | Yes | MRTR NE RHD WWK Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 16 | 2020-07-01 | 2020-09-30 | 2020-09-30 | SN-0555 | 2020-05-12 | New
35175 | NEXUS-WWK-3048-02 | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | Metro Routers | POInt | Yes | Yes | MRTR NE RHD WWK Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 3 | 2020-07-01 | 2020-09-30 | 2020-09-30 | SN-0555 | 2020-05-12 | New
35175 | NEXUS-WWK-93108-02 | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | Metro Routers | POInt | Yes | Yes | MRTR NE RHD WWK Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 6 | 2020-07-01 | 2020-09-30 | 2020-09-30 | SN-0555 | 2020-05-12 | New
35175 | NEXUS-WWK-93180-02 | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | Metro Routers | POInt | Yes | Yes | MRTR NE RHD WWK Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 12 | 2020-07-01 | 2020-09-30 | 2020-09-30 | SN-0555 | 2020-05-12 | New
34623 | TUCSSYSA01-ROUTER | SW | ARZ | TUC | Tucson | CB - Metro Core | POInt | Yes | Yes | CBMC SW ARZ TUC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-09-30 |  | SN-0771 | 2020-07-20 | Chg
35169 | MRTR NCS-Growth-MCD-NCS Line Card | SW | ARZ | MCD | McDowell | Metro Routers | POInt | Yes | Yes | MRTR SW ARZ MCD NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
35175 | NEXUS-BUR-93180-02 | NE | RHD | BUR | Burrillville | Metro Routers | POInt | Yes | Yes | MRTR NE RHD BUR Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-09-30 | SN-0555 | 2020-05-12 | New
35175 | NEXUS-BUR-3048-02 | NE | RHD | BUR | Burrillville | Metro Routers | POInt | Yes | Yes | MRTR NE RHD BUR Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-09-30 | SN-0555 | 2020-05-12 | New
35175 | NEXUS-BUR-93108-02 | NE | RHD | BUR | Burrillville | Metro Routers | POInt | Yes | Yes | MRTR NE RHD BUR Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-09-30 | SN-0555 | 2020-05-12 | New
35176 | MRTR SLR-New-WLK-SLR-ASR9906 | CE | OKC | WLK | Walker Hub | Metro Routers | POInt | Yes | Yes | MRTR CE OKC WLK SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-09-30 | 2020-09-30 | SN-0638 | 2020-06-05 | Chg
34945 | Metro OTN-GBD-Ciena 6500 S2 | CE | KAN | GBD | Great Bend | Metro Transport | POInt | Yes | Yes | MTRN CE KAN GBD OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-11-30 | SN-0161 | 2020-02-18 | Chg
34945 | Metro OTN-GBD-Ciena 6500 S32 | CE | KAN | GBD | Great Bend | Metro Transport | POInt | Yes | Yes | MTRN CE KAN GBD OTN Deployment POR20 | Chassis | 1x Ciena 6500 S32 Chassis | 1 | 2020-07-15 | 2020-09-30 | 2020-11-30 | SN-0161 | 2020-02-18 | Chg
34623 | E Mesa-OCML-IXR | SW | ARZ | MSA | Mesa | CB - Metro Core | POInt | Yes | Yes | CBMC SW ARZ MSA OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-09-30 |  | SN-0771 | 2020-07-20 | Chg
78334 | NR HEN MTC 48 Node Cell | SW | LAS | HEN | Henderson | MTC 48 Node Cell | POInt | Yes | Yes | NR SW LAS HEN MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-09-30 | 2020-09-30 | SN-0854 | 2020-08-21 | Chg
35171 | MRTR OOB-New-SOU-OOB Server | CE | OMA | SOU | South (OM) | Metro Routers | POInt | Yes | Yes | MRTR CE OMA SOU OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0158 | 2020-02-06 | Chg
59744 | RPHY MRTR-New-OSNAP-ALI | SW | LAS | ALI | Aliante | R PHY | POInt | Yes | Yes | R PHY SW LAS ALI Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0487 | 2020-05-12 | New
75246 | R PHY_CCAP_PNS_Boundary_Clocks_44119 | SE | GCT | PNS | Pensacola with (Insite tower) | R PHY | POInt | Yes | Yes | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-01-16 | 2020-09-30 |  | SN-0879 | 2020-08-28 | Chg
75246 | R PHY_CCAP_PNS_D9485_44119 | SE | GCT | PNS | Pensacola with (Insite tower) | R PHY | POInt | Yes | Yes | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-03-15 | 2020-09-30 |  | SN-0879 | 2020-08-28 | Chg
75246 | R PHY_CCAP_PNS_RPHY CCAP Licenses_Q2 NC Video | SE | GCT | PNS | Pensacola with (Insite tower) | R PHY | POInt | Yes | Yes | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | License | CCAP license | 136 | 2020-03-30 | 2020-09-30 | 2020-09-30 | SN-0879 | 2020-08-28 | Chg
75246 | R PHY_CCAP_PNS_OTDR_1 | SE | GCT | PNS | Pensacola with (Insite tower) | R PHY | POInt | Yes | Yes | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-09-30 |  | SN-0879 | 2020-08-28 | Chg
75246 | R PHY_CCAP_PNS_RPHY Bundled Solution V3_44119 | SE | GCT | PNS | Pensacola with (Insite tower) | R PHY | POInt | Yes | Yes | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-01-07 | 2020-09-30 | 2020-09-30 | SN-0879 | 2020-08-28 | Chg
75246 | CCAP Licenses | SE | GCT | PNS | Pensacola with (Insite tower) | R PHY | POInt | Yes | Yes | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | License | License Activation | 138 | 2020-04-15 | 2020-09-30 |  | SN-0879 | 2020-08-28 | Chg
75246 | R PHY_CCAP_PNS_RPHY CCAP Licenses_1 | SE | GCT | PNS | Pensacola with (Insite tower) | R PHY | POInt | Yes | Yes | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | License | CCAP license | 69 | 2020-07-15 | 2020-09-30 | 2020-09-30 | SN-0879 | 2020-08-28 | Chg
35174 | MRTR SLR-New-LUL-SLR-ASR9906 | SE | NOR | LUL | Luling | Metro Routers | POInt | Yes | Yes | MRTR SE NOR LUL SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | SN-0662 | 2020-06-14 | Chg
75243 | RPHY MRTR-New-WRB-CIN MGMT-2K | SE | MGA | WRB | Warner Robins | R PHY | POInt | Yes | Yes | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-04-01 | 2020-09-30 | 2020-07-31 | SN-0810 | 2020-08-07 | Chg
75243 | RPHY MRTR-New-WRB-CIN-Exfo-Optical Switch | SE | MGA | WRB | Warner Robins | R PHY | POInt | Yes | Yes | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-04-05 | 2020-09-30 | 2020-07-31 | SN-0810 | 2020-08-07 | Chg
75243 | RPHY MRTR-New-WRB-CIN-DPA-5200 (100G DPIC) | SE | MGA | WRB | Warner Robins | R PHY | POInt | Yes | Yes | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-04-01 | 2020-09-30 | 2020-07-31 | SN-0810 | 2020-08-07 | Chg
75243 | RPHY MRTR-New-WRB-CIN-RPA-5110 | SE | MGA | WRB | Warner Robins | R PHY | POInt | Yes | Yes | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-04-01 | 2020-09-30 | 2020-07-31 | SN-0810 | 2020-08-07 | Chg
75243 | RPHY MRTR-New-WRB-CIN-ATX-OCML | SE | MGA | WRB | Warner Robins | R PHY | POInt | Yes | Yes | R PHY SE MGA WRB RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-04-05 | 2020-09-30 | 2020-07-31 | SN-0810 | 2020-08-07 | Chg
35175 | NEXUS-MAN-3048-02 | NE | CON | MAN | Manchester | Metro Routers | POInt | Yes | Yes | MRTR NE CON MAN Metro Nexus Augment POR20 | Labor | No Equipment | 3 | 2020-07-01 | 2020-09-30 | 2020-09-30 | SN-0555 | 2020-05-12 | New
35175 | NEXUS-MAN-93108-02 | NE | CON | MAN | Manchester | Metro Routers | POInt | Yes | Yes | MRTR NE CON MAN Metro Nexus Augment POR20 | Labor | No Equipment | 6 | 2020-07-01 | 2020-09-30 | 2020-09-30 | SN-0555 | 2020-05-12 | New
35175 | NEXUS-MAN-93180-02 | NE | CON | MAN | Manchester | Metro Routers | POInt | Yes | Yes | MRTR NE CON MAN Metro Nexus Augment POR20 | Labor | No Equipment | 12 | 2020-07-01 | 2020-09-30 | 2020-09-30 | SN-0555 | 2020-05-12 | New
35169 | MRTR NCS-Growth-FWL-100G Grow | SW | ARZ | FWL | Fowler | Metro Routers | POInt | Yes | Yes | MRTR SW ARZ FWL 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-07-01 | 2020-09-30 | 2021-03-31 | SN-0158 | 2020-02-06 | Chg
59744 | RPHY MRTR-New-OSNAP-BLU | SW | LAS | BLU | Blue Diamond | R PHY | POInt | Yes | Yes | R PHY SW LAS BLU Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0487 | 2020-05-12 | New
78334 | NR BLU MTC 48 Node Cell | SW | LAS | BLU | Blue Diamond | MTC 48 Node Cell | POInt | Yes | Yes | NR SW LAS BLU MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-09-30 | 2020-09-30 | SN-0854 | 2020-08-21 | Chg
35176 | MRTR SLR-New-TUL-SLR-ASR9906 | CE | TUL | TUL | Tulsa | Metro Routers | POInt | Yes | Yes | MRTR CE TUL TUL SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-09-30 | 2020-09-30 | SN-0638 | 2020-06-05 | Chg
35176 | MRTR OOB-New-SHE-OOB Server | CE | OKC | SEH | South East | Metro Routers | POInt | Yes | Yes | MRTR CE OKC SEH OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0158 | 2020-02-06 | Chg
34608 | CB Transport - New Router Fredericksburg - MFD - Optics | VA | NVA | MFD | Merrifield | CB - Metro Core | POInt | Yes | Yes | CBMC VA NVA MFD Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 5 | 2020-07-15 | 2020-09-30 |  | SN-0934 | 2020-09-18 | Chg
35171 | MRTR OOB-New-WES-OOB Server | CE | OMA | WES | West (OM) | Metro Routers | POInt | Yes | Yes | MRTR CE OMA WES OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0158 | 2020-02-06 | Chg
35176 | MRTR OOB-New-BRD-OOB Server | CE | TUL | BRD | Braden | Metro Routers | POInt | Yes | Yes | MRTR CE TUL BRD OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0158 | 2020-02-06 | Chg
35171 | MRTR OOB-New-OMM-OOB Server | CE | OMA | OMM | Omaha | Metro Routers | POInt | Yes | Yes | MRTR CE OMA OMM OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0158 | 2020-02-06 | Chg
78334 | NR ALI MTC 48 Node Cell | SW | LAS | ALI | Aliante | MTC 48 Node Cell | POInt | Yes | Yes | NR SW LAS ALI MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-09-30 | 2020-09-30 | SN-0854 | 2020-08-21 | Chg
35173 | MRTR NCS-Growth-TEN-NCS Line Card | SW | LAS | TEN | Tenaya | Metro Routers | POInt | Yes | Yes | MRTR SW LAS TEN NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
35172 | NEXUS-GNS-93108-01 | SE | GAN | GNS | Gainesville | Metro Routers | POInt | Yes | Yes | MRTR SE GAN GNS Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-09-30 | SN-0555 | 2020-05-12 | New
35172 | NEXUS-GNS-2248-01 | SE | GAN | GNS | Gainesville | Metro Routers | POInt | Yes | Yes | MRTR SE GAN GNS Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-09-30 | SN-0555 | 2020-05-12 | New
34619 | Quincy-OCML-IXR | CE | TUL | QNC | Quincy | CB - Metro Core | POInt | Yes | Yes | CBMC CE TUL QNC OCML_IXR -R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-09-30 |  | SN-0934 | 2020-09-18 | Chg
34623 | South East-OCML-IXR | SW | LAS | HEN | Henderson | CB - Metro Core | POInt | Yes | Yes | CBMC SW LAS HEN OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-09-30 |  | SN-0701 | 2020-07-02 | Chg
35177 | MRTR SLR-New-FBG-SLR-ASR9906 | VA | NVA | FBG | Fredericksburg | Metro Routers | POInt | Yes | Yes | MRTR VA NVA FBG SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
78334 | NR VLY MTC 48 Node Cell | SW | LAS | VLY | Valley | MTC 48 Node Cell | POInt | Yes | Yes | NR SW LAS VLY MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-09-30 | 2020-09-30 | SN-0854 | 2020-08-21 | Chg
35175 | MRTR SLR-New-MER-SLR-ASR9906 | NE | CON | MER | Meriden | Metro Routers | POInt | Yes | Yes | MRTR NE CON MER SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2021-01-31 | SN-0662 | 2020-06-14 | Chg
35174 | MRTR SLR-New-KNN-SLR-ASR9906 | SE | NOR | KNN | Kenner | Metro Routers | POInt | Yes | Yes | MRTR SE NOR KNN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | SN-0662 | 2020-06-14 | Chg
59850 | RPHY MRTR-New-OSNAP-ORG | CA | ORG | ORG | Orange | R PHY | POInt | Yes | Yes | R PHY CA ORG ORG Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0487 | 2020-05-12 | New
78334 | NR TEN MTC 48 Node Cell | SW | LAS | TEN | Tenaya | MTC 48 Node Cell | POInt | Yes | Yes | NR SW LAS TEN MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-09-30 | 2020-09-30 | SN-0854 | 2020-08-21 | Chg
34623 | Fowler-OCML-IXR | SW | ARZ | FWL | Fowler | CB - Metro Core | POInt | Yes | Yes | CBMC SW ARZ FWL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-09-30 |  | SN-0796 | 2020-07-31 | Chg
35175 | MRTR SLR-New-BUR-SLR-ASR9906 | NE | RHD | BUR | Burrillville | Metro Routers | POInt | Yes | Yes | MRTR NE RHD BUR SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2021-01-31 | SN-0662 | 2020-06-14 | Chg
34619 | BLVUBSRA01-ROUTER | CE | OMA | BLV | Bellevue | CB - Metro Core | POInt | Yes | Yes | CBMC CE OMA BLV ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-25 | 2020-09-30 |  | SN-0934 | 2020-09-18 | Chg
59744 | RPHY MRTR-New-OSNAP-PNL | SW | ARZ | PNL | Pinal County | R PHY | POInt | Yes | Yes | R PHY SW ARZ PNL Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0487 | 2020-05-12 | New
78334 | NR ERN MTC 48 Node Cell | SW | LAS | ERN | Ernest May | MTC 48 Node Cell | POInt | Yes | Yes | NR SW LAS ERN MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-09-30 | 2020-09-30 | SN-0854 | 2020-08-21 | Chg
35175 | MRTR SLR-New-STN-SLR-ASR9906 | NE | CON | STN | Southington | Metro Routers | POInt | Yes | Yes | MRTR NE CON STN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2021-03-31 | SN-0662 | 2020-06-14 | Chg
35176 | MRTR SLR-New-OWA-SLR-ASR9906 | CE | TUL | OWA | Owasso | Metro Routers | POInt | Yes | Yes | MRTR CE TUL OWA SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-01 | 2020-09-30 | 2020-09-30 | SN-0638 | 2020-06-05
35177 | NEXUS-PTM-2248-01 | VA | HRD | PTM | Portsmouth (VA) | Metro Routers | POInt | Yes | Yes | MRTR VA HRD PTM Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-07-15 | 2020-09-30 | 2020-09-30 | SN-0588 | 2020-05-14 | Chg
59744 | RPHY MRTR-New-OSNAP-SSC | SW | ARZ | SSC | South Scottsdale | R PHY | POInt | Yes | Yes | R PHY SW ARZ SSC Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0487 | 2020-05-12 | New
59850 | RPHY MRTR-New-OSNAP-ELC | CA | SAN | ELC | El Cajon | R PHY | POInt | Yes | Yes | R PHY CA SAN ELC Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0487 | 2020-05-12 | New
75187 | R PHY_CCAP_FTS_Boundary_Clocks_44119 | CE | NWA | FTS | Fort Smith | R PHY | POInt | Yes | Yes | R PHY CE NWA FTS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-05-15 | 2020-09-30 | 2020-09-30 | SN-0899 | 2020-09-11 | Chg
75187 | R PHY_CCAP_FTS_RPHY Bundled Solution V3_44119 | CE | NWA | FTS | Fort Smith | R PHY | POInt | Yes | Yes | R PHY CE NWA FTS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-09-18 | 2020-09-30 | 2020-09-30 | SN-0899 | 2020-09-11 | Chg
75187 | R PHY_CCAP_FTS_OTDR_1 | CE | NWA | FTS | Fort Smith | R PHY | POInt | Yes | Yes | R PHY CE NWA FTS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-09-30 |  | SN-0899 | 2020-09-11 | Chg
59850 | RPHY MRTR-New-OSNAP-DWN | CA | SAN | DWN | Downtown | R PHY | POInt | Yes | Yes | R PHY CA SAN DWN Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0487 | 2020-05-12 | New
35169 | MRTR NCS-Growth-TUC-NCS Line Card | SW | ARZ | TUC | Tucson | Metro Routers | POInt | Yes | Yes | MRTR SW ARZ TUC NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
35177 | MRTR SLR-New-LTF-SLR-ASR9906 | VA | HRD | LTF | Lightfoot | Metro Routers | POInt | Yes | Yes | MRTR VA HRD LTF SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
35177 | MRTR NCS-Growth-NWP-100G Grow | VA | HRD | NWP | Newport News | Metro Routers | POInt | Yes | Yes | MRTR VA HRD NWP 100G Grow Augment POR20 | Card & Optics | 100G Grow | 1 | 2020-07-01 | 2020-09-30 | 2021-03-31 | SN-0158 | 2020-02-06 | Chg
59744 | RPHY MRTR-New-OSNAP-TUC | SW | ARZ | TUC | Tucson | R PHY | POInt | Yes | Yes | R PHY SW ARZ TUC Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0487 | 2020-05-12 | New
35170 | MRTR NCS-New-SAB-NCS-5504-250 Sup Card | CA | SAB | SAB | Santa Barbara | Metro Routers | POInt | Yes | Yes | MRTR CA SAB SAB NCS Deployment POR20 | Card & Optics | NCS-5504-250 Sup Card | 2 | 2020-07-05 | 2020-09-30 | 2020-12-31 | SN-0158 | 2020-02-06 | Chg
35170 | MRTR NCS-Growth-SAB-NCS Line Card | CA | SAB | SAB | Santa Barbara | Metro Routers | POInt | Yes | Yes | MRTR CA SAB SAB NCS Deployment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-05 | 2020-09-30 | 2020-12-31 | SN-0158 | 2020-02-06 | Chg
35175 | MRTR SLR-New-CLV-SLR-ASR9906 | NE | CLE | CLV | Cleveland | Metro Routers | POInt | Yes | Yes | MRTR NE CLE CLV SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
34623 | South West-OCML-IXR | SW | LAS | BLU | Blue Diamond | CB - Metro Core | POInt | Yes | Yes | CBMC SW LAS BLU OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-09-30 | 2020-09-30 | SN-0944 | 2020-09-25 | Chg
34623 | SESTCORA01.LV.LV.COX.NET-ROUTER | SW | LAS | HEN | Henderson | CB - Metro Core | POInt | Yes | Yes | CBMC SW LAS HEN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 1 | 2020-01-15 | 2020-09-30 |  | SN-0771 | 2020-07-20 | Chg
78091 | HY CA ORG DNP Voice HDT Decom POR20 | CA | ORG | DNP | Dana Point | Voice Decom and Refortification | POInt | Yes | Yes | VCDR CA ORG DNP Voice HDT Decom POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 |  | SN-1080 | 2020-11-20
59850 | RPHY MRTR-New-OSNAP-VST | CA | SAN | VST | Vista | R PHY | POInt | Yes | Yes | R PHY CA SAN VST Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0487 | 2020-05-12 | New
35169 | MRTR NCS-Growth-CHD-NCS Line Card 2 | SW | ARZ | CHD | Chandler | Metro Routers | POInt | Yes | Yes | MRTR SW ARZ CHD NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0555 | 2020-05-12 | New
59850 | RPHY MRTR-New-OSNAP-ESC | CA | SAN | ESC | Escondido | R PHY | POInt | Yes | Yes | R PHY CA SAN ESC Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0487 | 2020-05-12 | New
59850 | RPHY MRTR-New-OSNAP-PAV | CA | ORG | PAV | Palos Verdes | R PHY | POInt | Yes | Yes | R PHY CA ORG PAV Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0487 | 2020-05-12 | New
59850 | RPHY MRTR-New-OSNAP-AVJ | CA | ORG | AVJ | Aliso Viejo | R PHY | POInt | Yes | Yes | R PHY CA ORG AVJ Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0487 | 2020-05-12 | New
75243 | RPHY MRTR-New-BTR-CIN MGMT-2K | SE | BTR | BTR | Baton Rouge | R PHY | POInt | Yes | Yes | R PHY SE BTR BTR RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-09-30 |  | SN-0881 | 2020-08-28 | Chg
75243 | RPHY MRTR-New-BTR-CIN-DPA-5200 | SE | BTR | BTR | Baton Rouge | R PHY | POInt | Yes | Yes | R PHY SE BTR BTR RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-09-30 |  | SN-0881 | 2020-08-28 | Chg
75243 | RPHY MRTR-New-BTR-CIN-RPA-5110 | SE | BTR | BTR | Baton Rouge | R PHY | POInt | Yes | Yes | R PHY SE BTR BTR RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-09-30 |  | SN-0881 | 2020-08-28 | Chg
75243 | RPHY MRTR-New-BTR-CIN-ATX-OCML | SE | BTR | BTR | Baton Rouge | R PHY | POInt | Yes | Yes | R PHY SE BTR BTR RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-09-30 |  | SN-0881 | 2020-08-28 | Chg
75243 | RPHY MRTR-New-BTR-CIN-Exfo-Switch | SE | BTR | BTR | Baton Rouge | R PHY | POInt | Yes | Yes | R PHY SE BTR BTR RPHY Metro Initial Deployment POR19 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-06-15 | 2020-09-30 |  | SN-0881 | 2020-08-28 | Chg
59744 | RPHY MRTR-New-OSNAP-HEN | SW | LAS | HEN | Henderson | R PHY | POInt | Yes | Yes | R PHY SW LAS HEN Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0487 | 2020-05-12 | New
59850 | RPHY MRTR-New-OSNAP-FED | CA | SAN | FED | Federal | R PHY | POInt | Yes | Yes | R PHY CA SAN FED Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0487 | 2020-05-12 | New
35175 | NEXUS-RKH-3048-02 | NE | CON | RKH | Rocky Hill | Metro Routers | POInt | Yes | Yes | MRTR NE CON RKH Metro Nexus Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-30 | 2020-09-30 | SN-0555 | 2020-05-12 | New
34945 | Metro OTN-GCY-Ciena 6500 S14 | CE | KAN | GDY | Garden City | Metro Transport | POInt | Yes | Yes | MTRN CE KAN GDY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-07-15 | 2020-09-30 | 2020-11-30 | SN-0161 | 2020-02-18 | Chg
34945 | Metro OTN-GCY-Ciena 6500 S2 | CE | KAN | GDY | Garden City | Metro Transport | POInt | Yes | Yes | MTRN CE KAN GDY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-11-30 | SN-0161 | 2020-02-18 | Chg
34945 | Metro OTN-KLY-Ciena 6500 S14 | CE | KAN | KLY | Kinsley | Metro Transport | POInt | Yes | Yes | MTRN CE KAN KLY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-07-15 | 2020-09-30 | 2020-11-30 | SN-0161 | 2020-02-18 | Chg
34945 | Metro OTN-KLY-Ciena 6500 S2 | CE | KAN | KLY | Kinsley | Metro Transport | POInt | Yes | Yes | MTRN CE KAN KLY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-11-30 | SN-0161 | 2020-02-18 | Chg
34619 | sr01.sap.tul.ok-ROUTER | CE | TUL | SAP | Sapulpa | CB - Metro Core | POInt | Yes | Yes | CBMC CE TUL SAP ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-04-15 | 2020-09-30 |  | SN-0934 | 2020-09-18 | Chg
34623 | Pinal County-OCML-IXR | SW | ARZ | PNL | Pinal County | CB - Metro Core | POInt | Yes | Yes | CBMC SW ARZ PNL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-09-30 |  | SN-0701 | 2020-07-02 | Chg
59744 | RPHY MRTR-New-OSNAP-TEN | SW | LAS | TEN | Tenaya | R PHY | POInt | Yes | Yes | R PHY SW LAS TEN Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0487 | 2020-05-12 | New
34945 | Metro OTN-NWT-Ciena 6500 S14 | CE | KAN | NWT | Newton | Metro Transport | POInt | Yes | Yes | MTRN CE KAN NWT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-07-15 | 2020-09-30 | 2020-11-30 | SN-0161 | 2020-02-18 | Chg
34945 | Metro OTN-NWT-Ciena 6500 S2 | CE | KAN | NWT | Newton | Metro Transport | POInt | Yes | Yes | MTRN CE KAN NWT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-11-30 | SN-0161 | 2020-02-18 | Chg
75246 | R PHY_CCAP_BTR_OTDR_1 | SE | BTR | BTR | Baton Rouge | R PHY | POInt | Yes | Yes | R PHY SE BTR BTR RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-07-20 | 2020-09-30 |  | SN-0879 | 2020-08-28 | Chg
35176 | MRTR SLR-New-YAL-SLR-ASR9906 | CE | TUL | YAL | Yale | Metro Routers | POInt | Yes | Yes | MRTR CE TUL YAL SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-09-30 | 2020-09-30 | SN-0638 | 2020-06-05 | Chg
75246 | R PHY_CCAP_BTR_RPHY CCAP Licenses_1 | SE | BTR | BTR | Baton Rouge | R PHY | POInt | Yes | Yes | R PHY SE BTR BTR RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-07-15 | 2020-09-30 | 2020-09-30 | SN-0879 | 2020-08-28 | Chg
75246 | R PHY_CCAP_BTR_RPHY CCAP Licenses_Q2 NC Video | SE | BTR | BTR | Baton Rouge | R PHY | POInt | Yes | Yes | R PHY SE BTR BTR RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-09-30 | 2020-09-30 | SN-0879 | 2020-08-28 | Chg
75246 | R PHY_CCAP_BTR_RPHY Unbundled Solution V2_43947 | SE | BTR | BTR | Baton Rouge | R PHY | POInt | Yes | Yes | R PHY SE BTR BTR RPHY CCAP Augment POR20 | License | License Activation | 1 | 2020-03-01 | 2020-09-30 |  | SN-0879 | 2020-08-28 | Chg
35176 | MRTR OOB-New-ELR-OOB Server | CE | OKC | ELR | El Reno | Metro Routers | POInt | Yes | Yes | MRTR CE OKC ELR OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 3 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0158 | 2020-02-06 | Chg
59850 | RPHY MRTR-New-OSNAP-IRV | CA | ORG | IRV | Irvine | R PHY | POInt | Yes | Yes | R PHY CA ORG IRV Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0487 | 2020-05-12 | New
78334 | NR MSA MTC 48 Node Cell | SW | ARZ | MSA | Mesa | MTC 48 Node Cell | POInt | Yes | Yes | NR SW ARZ MSA MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-09-30 | 2020-09-30 | SN-0854 | 2020-08-21 | Chg
34604 | BTRILA572AW-24STHHUB7750X02-ROUTER | SE | BTR | SPC | Pecue | CB - Metro Core | POInt | Yes | Yes | CBMC SE BTR SPC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-04-15 | 2020-09-30 |  | SN-0618 | 2020-06-05 | Chg
34604 | WARNER ROBINS-OCML-IXR | SE | MGA | WRB | Warner Robins | CB - Metro Core | POInt | Yes | Yes | CBMC SE MGA WRB OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-10-01 | 2020-09-30 |  | SN-0819 | 2020-08-14 | Chg
59850 | RPHY MRTR-New-OSNAP-RSM | CA | ORG | RSM | Rancho Santa Margarita | R PHY | POInt | Yes | Yes | R PHY CA ORG RSM Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0487 | 2020-05-12 | New
34945 | Metro OTN-WIC-Ciena 6500 S2 | CE | KAN | WIC | Wichita | Metro Transport | POInt | Yes | Yes | MTRN CE KAN WIC OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-11-30 | SN-0161 | 2020-02-18 | Chg
59744 | RPHY MRTR-New-OSNAP-NSC | SW | ARZ | NSC | North Scottsdale | R PHY | POInt | Yes | Yes | R PHY SW ARZ NSC Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0487 | 2020-05-12 | New
34623 | North East-OCML-IXR | SW | LAS | VLY | Valley | CB - Metro Core | POInt | Yes | Yes | CBMC SW LAS VLY OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-12 | 2020-09-30 |  | SN-0771 | 2020-07-20 | Chg
35170 | MRTR NCS-Growth-FED-NCS Line Card | CA | SAN | FED | Federal | Metro Routers | POInt | Yes | Yes | MRTR CA SAN FED 100G Grow Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-05 | 2020-09-30 | 2020-12-31 | SN-0555 | 2020-05-12 | New
34619 | Fayetteville-OCML-IXR | CE | NWA | FAY | Fayetteville | CB - Metro Core | POInt | Yes | Yes | CBMC CE NWA FAY OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-09-30 |  | SN-0934 | 2020-09-18 | Chg
35174 | MRTR SLR-New-CLR-SLR-ASR9906 | SE | NOR | CLR | Metairie | Metro Routers | POInt | Yes | Yes | MRTR SE NOR CLR SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | SN-0662 | 2020-06-14 | Chg
75246 | R PHY_CCAP_BTR_CBR8-1 | SE | BTR | BTR | Baton Rouge | R PHY | POInt | Yes | Yes | R PHY SE BTR BTR RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-09-30 |  | SN-0879 | 2020-08-28 | Chg
75246 | R PHY_CCAP_BTR_Boundary_Clocks-1 | SE | BTR | BTR | Baton Rouge | R PHY | POInt | Yes | Yes | R PHY SE BTR BTR RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-09-30 |  | SN-0879 | 2020-08-28 | Chg
34945 | Metro OTN-PRT-Ciena 6500 S14 | CE | KAN | PRT | Pratt | Metro Transport | POInt | Yes | Yes | MTRN CE KAN PRT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-07-15 | 2020-09-30 | 2020-11-30 | SN-0161 | 2020-02-18 | Chg
34945 | Metro OTN-PRT-Ciena 6500 S2 | CE | KAN | PRT | Pratt | Metro Transport | POInt | Yes | Yes | MTRN CE KAN PRT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-11-30 | SN-0161 | 2020-02-18 | Chg
35175 | NEXUS-SCT-93108-02 | NE | RHD | SCT | Scituate | Metro Routers | POInt | Yes | Yes | MRTR NE RHD SCT Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-09-30 | SN-0555 | 2020-05-12 | New
35175 | NEXUS-SCT-93180-02 | NE | RHD | SCT | Scituate | Metro Routers | POInt | Yes | Yes | MRTR NE RHD SCT Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-09-30 | SN-0555 | 2020-05-12 | New
35175 | NEXUS-SCT-3048-02 | NE | RHD | SCT | Scituate | Metro Routers | POInt | Yes | Yes | MRTR NE RHD SCT Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 | 2020-07-01 | 2020-09-30 | 2020-09-30 | SN-0555 | 2020-05-12 | New
35175 | MRTR SLR-New-WWK-SLR-ASR9906 | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | Metro Routers | POInt | Yes | Yes | MRTR NE RHD WWK SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2021-03-31 | SN-0662 | 2020-06-14 | Chg
59850 | RPHY MRTR-New-OSNAP-OCE | CA | SAN | OCE | Oceanside | R PHY | POInt | Yes | Yes | R PHY CA SAN OCE Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0487 | 2020-05-12 | New
34623 | Tucson-OCML-IXR | SW | ARZ | TUC | Tucson | CB - Metro Core | POInt | Yes | Yes | CBMC SW ARZ TUC OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-09-30 | 2020-09-30 | SN-0944 | 2020-09-25 | Chg
35175 | NEXUS-RMD-3048-02 | NE | RHD | RMD | Richmond (RI) | Metro Routers | POInt | Yes | Yes | MRTR NE RHD RMD Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 | 2020-07-01 | 2020-09-30 | 2020-09-30 | SN-0555 | 2020-05-12 | New
78334 | NR FWL MTC 48 Node Cell | SW | ARZ | FWL | Fowler | MTC 48 Node Cell | POInt | Yes | Yes | NR SW ARZ FWL MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-09-30 | 2020-09-30 | SN-0854 | 2020-08-21 | Chg
78336 | NR GDY Q3 MTC 48 Node Cell | CE | KAN | GDY | Garden City | MTC 48 Node Cell | POInt | Yes | Yes | NR CE KAN GDY MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-30 | 2020-09-30 | SN-0854 | 2020-08-21 | Chg
59744 | RPHY MRTR-New-OSNAP-VLY | SW | LAS | VLY | Valley | R PHY | POInt | Yes | Yes | R PHY SW LAS VLY Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | SN-0487 | 2020-05-12 | New
35174 | MRTR SLR-New-LPL-SLR-ASR9906 | SE | NOR | LPL | Lapalco | Metro Routers | POInt | Yes | Yes | MRTR SE NOR LPL SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | SN-0662 | 2020-06-14 | Chg
34619 | sr01.owh.tul.ok-ROUTER | CE | TUL | OWA | Owasso | CB - Metro Core | POInt | Yes | Yes | CBMC CE TUL OWA ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-04-15 | 2020-09-30 |  | SN-0934 | 2020-09-18 | Chg
34619 | Yale-OCML-IXR | CE | TUL | YAL | Yale | CB - Metro Core | POInt | Yes | Yes | CBMC CE TUL YAL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-09-30 |  | SN-0934 | 2020-09-18 | Chg
54572 | CFS VA HRD PTM DC-CFS Augment POR20 - 2 | VA | HRD | PTM | Portsmouth (VA) | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD PTM DC-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-10-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE NOR KNN HV-CFS Augment POR20 | SE | NOR | KNN | Kenner | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE NOR KNN HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-10-01 |  | SB-0023 | 2020-01-30 | New
54572 | CFS VA NVA RHL DC-CFS Augment POR20 | VA | NVA | RHL | Rose Hill | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA NVA RHL DC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-10-01 |  | SB-0023 | 2020-01-30 | New
54572 | CFS VA HRD NRF GN-CFS Augment POR20 | VA | HRD | NRF | Norfolk | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS VA HRD NRF GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-10-01 |  | SB-0023 | 2020-01-30 | New
54571 | CFS SE BTR ERW HV-CFS Augment POR20 | SE | BTR | ERW | Erwinville | Critical Facilities Sustaining (Field) | POInt | Yes | Yes | CFS SE BTR ERW HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-10-01 |  | SB-0023 | 2020-01-30 | New
34970 | CFG SW ARZ MSA BS-CFG Deployment POR20 | SW | ARZ | MSA | Mesa | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ MSA BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-10-01 |  | SB-0023 | 2020-01-30 | New
34604 | MACNGAWH1AW-HOLTBSRA01-ROUTER | SE | MGA | HLT | Holt | CB - Metro Core | POInt | Yes | Yes | CBMC SE MGA HLT ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-07-15 | 2020-10-01 |  | SN-0144 | 2020-02-06 | Chg
46161 | MRTH-GVA-93180-01 | SW | ARZ | GVA | Green Valley | Metro Nexus Thunder | POInt | Yes | Yes | MNEX SW ARZ GVA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 2 | 2020-04-20 | 2020-10-01 | 2020-12-14 | SB-0237 | 2020-11-06 | Chg
46161 | MRTH-GVA-2248-01 | SW | ARZ | GVA | Green Valley | Metro Nexus Thunder | POInt | Yes | Yes | MNEX SW ARZ GVA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-04-20 | 2020-10-01 | 2020-12-14 | SB-0237 | 2020-11-06 | Chg
44876 | MTCH CE OKC MWC RPHY Test Rack Deployment POR20 | CE | OKC | MWC | Midwest City | MTC HE - Hub Signaling | POInt | Yes | No | MTCH CE OKC MWC RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-08-06 | 2020-10-01 |  | SN-0219 | 2020-04-03
44876 | MTCH CE OMA WES RPHY Test Rack Deployment POR20 | CE | OMA | WES | West (OM) | MTC HE - Hub Signaling | POInt | Yes | No | MTCH CE OMA WES RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-08-06 | 2020-10-01 |  | SN-0219 | 2020-04-03
74548 | R PHY_CCAP_MFD_Grand_Master_Clocks_44119 | VA | NVA | MFD | Merrifield | R PHY CCAP | POInt | Yes | No | R PHY VA NVA MFD RPHY - CCAP Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2020-07-15 | 2020-10-01 |  | SN-0097 | 2020-02-06 | New
46161 | MRTH-VSA-93180-01 | SW | ARZ | VSA | Vistancia | Metro Nexus Thunder | POInt | Yes | Yes | MNEX SW ARZ VSA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 2 | 2020-04-20 | 2020-10-01 | 2020-12-08 | SB-0237 | 2020-11-06 | Chg
46161 | MRTH-VSA-2248-01 | SW | ARZ | VSA | Vistancia | Metro Nexus Thunder | POInt | Yes | Yes | MNEX SW ARZ VSA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-04-20 | 2020-10-01 | 2020-12-08 | SB-0237 | 2020-11-06 | Chg
46161 | MRTH-SVA-93180-01 | SW | ARZ | SVA | Sierra Vista | Metro Nexus Thunder | POInt | Yes | Yes | MNEX SW ARZ SVA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 2 | 2020-07-20 | 2020-10-13 | 2020-11-19 | SB-0237 | 2020-11-06 | Chg
46161 | MRTH-SVA-2248-01 | SW | ARZ | SVA | Sierra Vista | Metro Nexus Thunder | POInt | Yes | Yes | MNEX SW ARZ SVA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-07-20 | 2020-10-13 | 2020-11-19 | SB-0237 | 2020-11-06 | Chg
75788 | CDN Deploy 23 | SW | LAS | BLU | Blue Diamond | CDN | POInt | Yes | No | CDN SW LAS BLU Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-07-01 | 2020-10-13 | 2020-10-30 | SN-0803 | 2020-08-07 | Chg
46161 | MRTH-CSG-93180-01 | SW | ARZ | CSG | Casa Grande | Metro Nexus Thunder | POInt | Yes | Yes | MNEX SW ARZ CSG Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 2 | 2020-01-20 | 2020-10-13 | 2020-11-11 | SB-0237 | 2020-11-06 | Chg
46161 | MRTH-CSG-2248-01 | SW | ARZ | CSG | Casa Grande | Metro Nexus Thunder | POInt | Yes | Yes | MNEX SW ARZ CSG Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-01-20 | 2020-10-13 | 2020-11-11 | SB-0237 | 2020-11-06 | Chg
75788 | CDN Deploy 14 | SE | GAN | GNS | Gainesville | CDN | POInt | Yes | No | CDN SE GAN GNS Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-08-01 | 2020-10-14 | 2020-11-01 | SN-0803 | 2020-08-07 | Chg
34683 | CCAP blades_ CRN | NE | RHD | CRN | Cranston | DOCSIS CMTS/CCAP | POInt | Yes | No | CMTS NE RHD CRN CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-10-05 | 2020-10-15
75663 | V2B COR COR ATL StratOS New Objectives Augment POR20 | COR | COR | ATL | Atlanta | V2B | POInt | Yes | No | V2B COR COR ATL StratOS New Objectives Augment POR20 | Labor | StratOS | 2 | 2020-09-15 | 2020-10-15 | 2020-12-31 | SN-0901 | 2020-09-11 | Chg
34683 | CCAP blades_ PRV | NE | RHD | PRV | Providence | DOCSIS CMTS/CCAP | POInt | Yes | No | CMTS NE RHD PRV CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 2 | 2020-10-05 | 2020-10-15 |  | SN-0048 | 2020-02-06 | Chg
75663 | V2B COR COR DDR SD Copy Retirement Decom POR20 | COR | COR | DDR | Duke Drive | V2B | POInt | Yes | No | V2B COR COR DDR SD Copy Retirement Decom POR20 | Labor | Config of encoders and monitors | 1 | 2020-09-08 | 2020-10-15 | 2020-11-15 | SN-0708 | 2020-06-30 | Chg
75663 | V2B COR COR ATL Executive Channel Augment POR20 | COR | COR | ATL | Atlanta | V2B | POInt | Yes | No | V2B COR COR ATL Executive Channel Augment POR20 | Card & Optics | Exec Channel | 2 | 2020-09-15 | 2020-10-15 | 2020-11-15 | SN-0901 | 2020-09-11 | Chg
34687 | CCAP blades_ ONA 2 | CE | OMA | ONA | North (OM) | DOCSIS CMTS/CCAP | POInt | Yes | No | CMTS CE OMA ONA CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-10-05 | 2020-10-15 |  | SN-0048 | 2020-02-06 | Chg
75663 | V2B CA SAN ELC Media H264 HEVC Alignment POR20 | CA | SAN | ELC | El Cajon | V2B | POInt | Yes | No | V2B CA SAN ELC Media H264 HEVC Alignment POR20 | Card & Optics | UCS blades and config | 1 | 2020-09-15 | 2020-10-15 | 2020-11-15 | SN-0901 | 2020-09-11 | Chg
44923 | MTCH CA SAN ELC MPEG4 vDCM Install Deployment POR20 | CA | SAN | ELC | El Cajon | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH CA SAN ELC MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 4 | 2020-03-06 | 2020-10-15 | 2021-03-15 | SN-0575 | 2020-05-14 | Chg
34619 | OMHNBSRA01-ROUTER | CE | OMA | ONA | North (OM) | CB - Metro Core | POInt | Yes | Yes | CBMC CE OMA ONA ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-07-15 | 2020-10-15 |  | SN-0144 | 2020-02-06 | Chg
34619 | CB Transport - New Router South (OM) - BLV - Optics | CE | OMA | BLV | Bellevue | CB - Metro Core | POInt | Yes | Yes | CBMC CE OMA BLV Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-09-15 | 2020-10-15
39225 | CCAP blades_ GNS 2 | SE | GAN | GNS | Gainesville | DOCSIS CMTS/CCAP | POInt | Yes | No | CMTS SE GAN GNS CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-10-05 | 2020-10-15 |  | SN-0048 | 2020-02-06 | Chg
34690 | CCAP blades_ NWA | CE | NWA | NWA | Johnson | DOCSIS CMTS/CCAP | POInt | Yes | No | CMTS CE NWA NWA CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-10-05 | 2020-10-15
59745 | R PHY_CCAP_PAV_CBR8_2 | CA | ORG | PAV | Palos Verdes | RSPD - CCAP | POInt | Yes | No | R PHY CA ORG PAV RPHY CCAP Augment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-07-15 | 2020-10-15 |  | SN-0605 | 2020-05-22 | New
34683 | CCAP blades_ PAW | NE | RHD | PAW | Pawtucket | DOCSIS CMTS/CCAP | POInt | Yes | No | CMTS NE RHD PAW CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 2 | 2020-10-05 | 2020-10-15 |  | SN-0048 | 2020-02-06 | Chg
75663 | V2B CA SAN ELC SD Copy Retirement Decom POR20 | CA | SAN | ELC | El Cajon | V2B | POInt | Yes | No | V2B CA SAN ELC SD Copy Retirement Decom POR20 | Labor | Config of encoders and monitors | 1 | 2020-09-08 | 2020-10-15 | 2020-11-15 | SN-0708 | 2020-06-30 | Chg
75663 | V2B COR COR DDR Media H264 HEVC Alignment POR20 | COR | COR | DDR | Duke Drive | V2B | POInt | Yes | No | V2B COR COR DDR Media H264 HEVC Alignment POR20 | Standard | H264 HEVC | 1 | 2020-09-15 | 2020-10-15 | 2020-11-15 | SN-0901 | 2020-09-11 | Chg
34690 | CCAP blades_ NWT | CE | KAN | NWT | Newton | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE KAN NWT CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-10-05 | 2020-10-15 |  | SN-0048 | 2020-02-06 | Chg
34623 | CB Transport - New Router Aliante - ALI - Optics | SW | LAS | ALI | Aliante | CB - Metro Core | POInt | Yes | Yes | CBMC SW LAS ALI Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-08-03 | 2020-10-15
34619 | CB Transport - New Router South (OM) - SOU - Optics | CE | OMA | SOU | South (OM) | CB - Metro Core | POInt | Yes | Yes | CBMC CE OMA SOU Optics Only for Cisco T5 Augment POR20_V2 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-09-15 | 2020-10-15
59745 | R PHY_CCAP_RSM_RPHY Bundled Solution V3_44119 | CA | ORG | RSM | Rancho Santa Margarita | RSPD - CCAP | POInt | Yes | Yes | R PHY CA ORG RSM RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-09-18 | 2020-10-15 | 2020-10-15 | SN-0899 | 2020-09-11 | Chg
34685 | CCAP blades_ NKT | VA | HRD | NKT | New Kent | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS VA HRD NKT CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-09-01 | 2020-10-15 |  | SN-0048 | 2020-02-06 | Chg
59522 | R PHY_CCAP_BLU_CBR8 Chassis_1 | SW | LAS | BLU | Blue Diamond | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS BLU RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-09-28 | 2020-10-15 | 2020-10-15 | SN-0959 | 2020-09-25 | Chg
59745 | R PHY_CCAP_OCE_RPHY Unbundled Solution V2_44120 | CA | SAN | OCE | Oceanside | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN OCE RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-07-15 | 2020-10-15 | 2020-10-15 | SN-0550 | 2020-05-12 | New
34687 | CCAP blades_ ELK | CE | OMA | ELK | Elkhorn | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE OMA ELK CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-10-05 | 2020-10-15 |  | SN-0048 | 2020-02-06 | Chg
34622 | CV1XEWAA01-ROUTER | CA | SAN | CHU | Chula Vista | CB - Metro Core | POInt | Yes | Yes | CBMC CA SAN CHU ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-07-15 | 2020-10-15 |  | SN-0144 | 2020-02-06 | Chg
74548 | R PHY_CCAP_NWP_CBR8 Line Card_1 | VA | HRD | NWP | Newport News | R PHY | POInt | Yes | Yes | R PHY VA HRD NWP RPHY CCAP Augment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 3 | 2020-07-15 | 2020-10-15 | 2020-10-15 | SN-0550 | 2020-05-12 | New
34970 | CFG CHD HV-CFG GEN GROW PROJECT - LARGE | SW | ARZ | CHD | Chandler | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ CHD BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-09-01 | 2020-10-15
34687 | CCAP blades_ OKC 2 | CE | OKC | OKC | OKC MTC | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE OKC OKC CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-10-05 | 2020-10-15 |  | SN-0048 | 2020-02-06 | Chg
34690 | CCAP blades_ JCY | CE | KAN | JCY | Junction City | DOCSIS CMTS/CCAP | POInt | Yes | Yes | CMTS CE KAN JCY CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-10-05 | 2020-10-15
59522 | R PHY_CCAP_HEN_RPHY Bundled Solution V3_44119 | SW | LAS | HEN | Henderson | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS HEN RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-09-04 | 2020-10-15 | 2020-10-15 | SN-0899 | 2020-09-11 | Chg
34619 | CB Transport - New Router South (OM) - OMM - Optics | CE | OMA | OMM | Omaha | CB - Metro Core | POInt | Yes | Yes | CBMC CE OMA OMM Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-09-15 | 2020-10-15
59522 | R PHY_CCAP_ALI_RPHY Bundled Solution V3_44027 | SW | LAS | ALI | Aliante | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS ALI RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-07-15 | 2020-10-15 | 2020-10-15 | SN-0550 | 2020-05-12 | Chg
59522 | R PHY_CCAP_TEN_CBR8 Line Card_1 | SW | LAS | TEN | Tenaya | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 5 | 2020-07-15 | 2020-10-15 | 2020-10-15 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_OCE_CBR8 Line Card_1 | SW | LAS | OSB | Oso Blanca | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 5 | 2020-07-15 | 2020-10-15 | 2020-10-15 | SN-0550 | 2020-05-12 | New
34623 | CB Transport - New Router Aliante - HEN - Optics | SW | LAS | HEN | Henderson | CB - Metro Core | POInt | Yes | Yes | CBMC SW LAS HEN Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-08-03 | 2020-10-15
34970 | CFG MCD BS-CFG GEN GROW PROJECT - MEDIUM | SW | ARZ | MCD | McDowell | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ MCD BS-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-09-01 | 2020-10-15
34623 | CB Transport - New Router Aliante - TEN - Optics | SW | LAS | TEN | Tenaya | CB - Metro Core | POInt | Yes | Yes | CBMC SW LAS TEN Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-08-03 | 2020-10-15
44927 | MTCH VA ROA RON Inca 8VSB Deployment POR19 | VA | ROA | RON | Roanoke | MTC HE - Hub Signaling | POInt | Yes | No | MTCH VA ROA RON Inca 8VSB Deployment POR19 | Critical Facilities | MTC Hub Signaling | 1 | 2020-10-07 | 2020-10-16 | 2020-11-30 | SN-0970 | 2020-10-02 | Chg
44927 | MTCH VA HRD VBC Inca 8VSB Deployment POR19 | VA | HRD | VBC | Virginia Beach | MTC HE - Hub Signaling | POInt | Yes | No | MTCH VA HRD VBC Inca 8VSB Deployment POR19 | Critical Facilities | MTC Hub Signaling | 1 | 2020-10-07 | 2020-10-16 | 2020-11-30 | SN-0970 | 2020-10-02 | Chg
75655 | Arbor 25 | COR | COR | DVY | Deer Valley | Arbor DDoS | POInt | Yes | No | DDoS CO COR DVY Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 10 | 2020-07-28 | 2020-10-26 | 2020-11-09 | SN-0107 | 2020-02-06 | Chg
46161 | MRTH-MSA-93180-01 | SW | ARZ | MSA | Mesa | Metro Nexus Thunder | POInt | Yes | Yes | MNEX SW ARZ MSA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 6 | 2020-03-20 | 2020-10-26 | 2020-12-15 | SB-0237 | 2020-11-06 | Chg
46161 | MRTH-MSA-2248-01 | SW | ARZ | MSA | Mesa | Metro Nexus Thunder | POInt | Yes | Yes | MNEX SW ARZ MSA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 9 | 2020-03-20 | 2020-10-26 | 2020-12-15 | SB-0237 | 2020-11-06 | Chg
46161 | MRTH-BEN-93180-01 | SW | ARZ | BEN | Benson with (Insite tower) | Metro Nexus Thunder | POInt | Yes | Yes | MNEX SW ARZ BEN Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 2 | 2020-07-15 | 2020-10-28 | 2020-11-19 | SB-0237 | 2020-11-06 | Chg
46161 | MRTH-BEN-2248-01 | SW | ARZ | BEN | Benson with (Insite tower) | Metro Nexus Thunder | POInt | Yes | Yes | MNEX SW ARZ BEN Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-07-27 | 2020-10-28 | 2020-11-19 | SB-0237 | 2020-11-06 | Chg
78099 | VCDR SE NOR NOE Voice HDT Decom POR20 | SE | NOR | NOE | New Orleans East | Voice Decom and Refortification | POInt | Yes | Yes | VCDR SE NOR NOE Voice HDT Decom POR20 | Labor | No Equipment | 1 | 2020-03-31 | 2020-10-30 |  | SN-0644 | 2020-06-15 | Chg
78336 | NR ONA MTC 48 Node Cell | CE | OMA | ONA | North (OM) | MTC 48 Node Cell | POInt | Yes | Yes | NR CE OMA ONA MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-15 | 2020-10-30 | 2020-10-30 | SN-0946 | 2020-09-25 | Chg
78336 | NR ONA Q3 MTC 48 Node Cell | CE | OMA | ONA | North (OM) | MTC 48 Node Cell | POInt | Yes | Yes | NR CE OMA ONA MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-10-30 | 2020-10-30 | SN-0946 | 2020-09-25 | Chg
78336 | NR HUT Q3 MTC 48 Node Cell | CE | KAN | HUT | Hutchinson | MTC 48 Node Cell | POInt | Yes | Yes | NR CE KAN HUT MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-10-30 | 2020-10-30 | SN-0946 | 2020-09-25 | Chg
78336 | NR WES Q4 MTC 48 Node Cell | CE | OMA | WES | West (OM) | MTC 48 Node Cell | POInt | Yes | Yes | NR CE OMA WES MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-09-30 | 2020-10-30 | 2020-10-30 | SN-0946 | 2020-09-25 | Chg
75187 | R PHY_CCAP_ONA_Boundary_Clocks | CE | OMA | ONA | North (OM) | R PHY | POInt | Yes | Yes | R PHY CE OMA ONA RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-07-15 | 2020-10-30 |  | SN-0725 | 2020-07-02 | New
78336 | NR BVL MTC 48 Node Cell | CE | NWA | BVL | Bentonville | MTC 48 Node Cell | POInt | Yes | Yes | NR CE NWA BVL MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-15 | 2020-10-30 | 2020-10-30 | SN-0946 | 2020-09-25 | Chg
75246 | R PHY_CCAP_LUL_CBR8-1 | SE | NOR | LUL | Luling | R PHY | POInt | Yes | Yes | R PHY SE NOR LUL RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-10-30 |  | SN-0605 | 2020-05-22 | Chg
75246 | R PHY_CCAP_LUL_Boundary_Clocks-1 | SE | NOR | LUL | Luling | R PHY | POInt | Yes | Yes | R PHY SE NOR LUL RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-10-30 |  | SN-0605 | 2020-05-22 | Chg
78336 | NR BLV MTC 48 Node Cell | CE | OMA | BLV | Bellevue | MTC 48 Node Cell | POInt | Yes | Yes | NR CE OMA BLV MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-15 | 2020-10-30 | 2020-10-30 | SN-0946 | 2020-09-25 | Chg
75187 | R PHY_CCAP_WES_Boundary_Clocks | CE | OMA | WES | West (OM) | R PHY | POInt | Yes | Yes | R PHY CE OMA WES RPHY - CCAP Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-07-15 | 2020-10-30 |  | SN-0725 | 2020-07-02 | New
75187 | R PHY_CCAP_WIC_Boundary_Clocks_44119 | CE | KAN | WIC | Wichita | R PHY | POInt | Yes | Yes | R PHY CE KAN WIC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-05-15 | 2020-10-30 |  | SN-0613 | 2020-05-29 | Chg
75187 | R PHY_CCAP_WIC_Grand_Master_Clocks_44119 | CE | KAN | WIC | Wichita | R PHY | POInt | Yes | Yes | R PHY CE KAN WIC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2020-05-15 | 2020-10-30 |  | SN-0613 | 2020-05-29 | Chg
75187 | R PHY_CCAP_WIC_RPHY Bundled Solution V3_44119 | CE | KAN | WIC | Wichita | R PHY | POInt | Yes | Yes | R PHY CE KAN WIC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-05-26 | 2020-10-30 | 2020-10-30 | SN-0613 | 2020-05-29 | Chg
75187 | R PHY_CCAP_WIC_OTDR_1 | CE | KAN | WIC | Wichita | R PHY | POInt | Yes | Yes | R PHY CE KAN WIC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-07-20 | 2020-10-30 |  | SN-0637 | 2020-06-05 | New
78336 | NR WIC MTC 48 Node Cell | CE | KAN | WIC | Wichita | MTC 48 Node Cell | POInt | Yes | Yes | NR CE KAN WIC MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-15 | 2020-10-30 | 2020-10-30 | SN-0946 | 2020-09-25 | Chg
78336 | NR WIC Q3 MTC 48 Node Cell | CE | KAN | WIC | Wichita | MTC 48 Node Cell | POInt | Yes | Yes | NR CE KAN WIC MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-10-30 | 2020-10-30 | SN-0946 | 2020-09-25 | Chg
78332 | NR SAB Q4 MTC 48 Node Cell | CA | SAB | SAB | Santa Barbara | MTC 48 Node Cell | POInt | Yes | Yes | NR CA SAB SAB MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-10-01 | 2020-10-30 | 2020-10-30 | SN-0854 | 2020-08-21 | Chg
75246 | R PHY_CCAP_LUL_OTDR_1 | SE | NOR | LUL | Luling | R PHY | POInt | Yes | Yes | R PHY SE NOR LUL RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-07-20 | 2020-10-30 |  | SN-0637 | 2020-06-05 | New
78336 | NR NWA Q3 MTC 48 Node Cell | CE | NWA | NWA | Johnson | MTC 48 Node Cell | POInt | Yes | Yes | NR CE NWA NWA MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-10-30 | 2020-10-30 | SN-0946 | 2020-09-25 | Chg
75187 | R PHY_CCAP_BLV_RPHY Bundled Solution V3_44119 | CE | OMA | BLV | Bellevue | R PHY | POInt | Yes | Yes | R PHY CE OMA BLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-04-28 | 2020-10-30 | 2020-10-30 | SN-0613 | 2020-05-29 | Chg
75187 | R PHY_CCAP_BLV_Boundary_Clocks_44119 | CE | OMA | BLV | Bellevue | R PHY | POInt | Yes | Yes | R PHY CE OMA BLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-04-15 | 2020-10-30 |  | SN-0613 | 2020-05-29 | Chg
75187 | R PHY_CCAP_BLV_OTDR_1 | CE | OMA | BLV | Bellevue | R PHY | POInt | Yes | Yes | R PHY CE OMA BLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-07-20 | 2020-10-30 |  | SN-0637 | 2020-06-05 | New
78336 | NR TOP Q3 MTC 48 Node Cell | CE | KAN | TOP | Topeka | MTC 48 Node Cell | POInt | Yes | No | NR CE KAN TOP MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-10-30 | 2020-10-30 | SN-0946 | 2020-09-25 | Chg
44927 | MTCH VA HRD NKT Inca 8VSB Deployment POR19 | VA | HRD | NKT | New Kent | MTC HE - Hub Signaling | POInt | Yes | No | MTCH VA HRD NKT Inca 8VSB Deployment POR19 | Critical Facilities | MTC Hub Signaling | 1 | 2020-10-07 | 2020-10-30 | 2020-11-30 | SN-0970 | 2020-10-02 | Chg
75187 | R PHY_CCAP_TUL_OTDR_1 | CE | TUL | TUL | Tulsa | R PHY | POInt | Yes | No | R PHY CE TUL TUL R PHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-10-30 |  | SN-0613 | 2020-05-29 | Chg
75187 | R PHY_CCAP_TUL_RPHY Bundled Solution V3_43945 | CE | TUL | TUL | Tulsa | R PHY | POInt | Yes | No | R PHY CE TUL TUL R PHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-05-26 | 2020-10-30 | 2020-10-30 | SN-0613 | 2020-05-29 | Chg
78336 | NR BLV Q3 MTC 48 Node Cell | CE | OMA | BLV | Bellevue | MTC 48 Node Cell | POInt | Yes | No | NR CE OMA BLV MTC 48 Node Cell Augment POR20_0 | Labor | No Equipment | 1 | 2020-07-01 | 2020-10-30 | 2020-10-30 | SN-0946 | 2020-09-25 | Chg
78336 | NR MPN Q3 MTC 48 Node Cell | CE | KAN | MPN | McPherson | MTC 48 Node Cell | POInt | Yes | Yes | NR CE KAN MPN MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-10-30 | 2020-10-30 | SN-0946 | 2020-09-25 | Chg
78336 | NR ELK MTC 48 Node Cell | CE | OMA | ELK | Elkhorn | MTC 48 Node Cell | POInt | Yes | Yes | NR CE OMA ELK MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-15 | 2020-10-30 | 2020-10-30 | SN-0946 | 2020-09-25 | Chg
78336 | NR ELK Q3 MTC 48 Node Cell | CE | OMA | ELK | Elkhorn | MTC 48 Node Cell | POInt | Yes | Yes | NR CE OMA ELK MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-10-30 | 2020-10-30 | SN-0946 | 2020-09-25 | Chg
35169 | MRTR AAR-New-PEO-NEW-AAR | SW | ARZ | PEO | Peoria | Metro Routers | POInt | Yes | Yes | MRTR SW ARZ PEO AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
35169 | MRTR AAR-New-TEN-NEW-AAR | SW | LAS | TEN | Tenaya | Metro Routers | POInt | Yes | Yes | MRTR SW LAS TEN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
35176 | MRTR AAR-New-CLR-NEW-AAR | SE | NOR | CLR | Metairie | Metro Routers | POInt | Yes | Yes | MRTR SE NOR CLR AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0662 | 2020-06-14 | Chg
35176 | MRTR AAR-New-MCY-NEW-AAR | SE | NOR | MCY | Mid-City | Metro Routers | POInt | Yes | Yes | MRTR SE NOR MCY AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0662 | 2020-06-14 | Chg
35170 | MRTR AAR-New-CHU-NEW-AAR | CA | SAN | CHU | Chula Vista | Metro Routers | POInt | Yes | Yes | MRTR CA SAN CHU AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
35173 | MRTR AAR-New-ERN-NEW-AAR | SW | LAS | ERN | Ernest May | Metro Routers | POInt | Yes | Yes | MRTR SW LAS ERN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
35172 | MRTR OOB-New-MCN-OOB Server | SE | MGA | MCN | Macon | Metro Routers | POInt | Yes | Yes | MRTR SE MGA MCN OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-31 | 2020-10-31 | 2020-11-30 | SN-0864 | 2020-08-21 | New
35171 | MRTR AAR-New-BAR-NEW-AAR | CE | TUL | BAR | Broken Arrow | Metro Routers | POInt | Yes | Yes | MRTR CE TUL BAR AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
78340 | NR CRV MTC 48 Node Cell | SE | GCT | CRV | Crestview | MTC 48 Node Cell | POInt | Yes | Yes | NR SE GCT CRV MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-15 | 2020-10-31 | 2020-10-31 | SN-0594 | 2020-05-20 | New
35172 | MRTR OOB-New-NOE-OOB Server | SE | NOR | NOE | New Orleans East | Metro Routers | POInt | Yes | Yes | MRTR SE NOR NOE OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-31 | 2020-10-31 | 2020-11-30 | SN-0864 | 2020-08-21 | New
75830 | Metaswitch 4.3.4 Upgrade CB | COR | COR | ATL | Atlanta | Voice Network Upgrades | POInt | Yes | No | VNU CO -CO ATL Metaswitch Lifecycle Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-05 | 2020-10-31 | 2020-04-15 | SB-0162 | 2020-06-30 | Chg
75830 | Metaswitch DSP Cards | COR | COR | ATL | Atlanta | Voice Network Upgrades | POInt | Yes | No | VNU CO -CO ATL Metaswitch Lifecycle Deployment POR20 | Labor | Other | 1 | 2020-05-01 | 2020-10-31 | 2020-07-26 | SB-0162 | 2020-06-30 | Chg
35170 | MRTR AAR-New-VST-NEW-AAR | CA | SAN | VST | Vista | Metro Routers | POInt | Yes | Yes | MRTR CA SAN VST AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
34623 | N Scottsdale-OCML-IXR | SW | ARZ | NSC | North Scottsdale | CB - Metro Core | POInt | Yes | Yes | CBMC SW ARZ NSC OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-10-31 |  | SN-0934 | 2020-09-18 | Chg
75788 | CDN Deploy 5 | VA | NVA | MFD | Merrifield | CDN | POInt | Yes | No | CDN VA NVA MFD Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 4 | 2020-08-01 | 2020-10-31 | 2020-11-13 | SN-0285 | 2020-02-24 | Chg
75788 | CDN Deploy 30 | COR | COR | DDR | Duke Drive | CDN | POInt | Yes | No | CDN CO -CO DDR VHST Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 6 | 2020-05-10 | 2020-10-31 | 2020-11-14 | SN-0803 | 2020-08-07 | Chg
77906 | HY COR COR DDR Voice BTS Decom POR19 | COR | COR | DDR | Duke Drive | Voice Decom and Refortification | POInt | Yes | No | VCDR COR COR DDR Voice BTS Decom POR19 | Labor | No Equipment | 1 | 2020-07-01 | 2020-10-31 |  | SN-0610 | 2020-05-29 | Chg
75788 | CDN Deploy 28 | SW | ARZ | CHD | Chandler | CDN | POInt | Yes | No | CDN SW ARZ CHD VHST Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 3 | 2020-05-01 | 2020-10-31 | 2020-11-15 | SN-0803 | 2020-08-07 | Chg
35171 | MRTR AAR-New-ONA-NEW-AAR | CE | OMA | ONA | North (OM) | Metro Routers | POInt | Yes | No | MRTR CE OMA ONA AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0939 | 2020-09-18
75788 | CDN Deploy 29 | CA | SAN | FED | Federal | CDN | POInt | Yes | No | CDN CA SAN FED VHST Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 3 | 2020-05-01 | 2020-10-31 | 2020-11-30 | SN-0803 | 2020-08-07 | Chg
44926 | MTCH NE RHD PTH RF Passive Splitter Deployment POR20 | NE | RHD | PTH | Portsmouth (RI) | MTC HE - Hub Signaling | POInt | Yes | No | MTCH NE RHD PTH RF Passive Splitter Deployment POR20 | Chassis | 8-way splitter | 1 | 2020-09-06 | 2020-10-31 |  | SN-0021 | 2020-02-06 | Chg
35170 | MRTR AAR-New-OCE-NEW-AAR | CA | SAN | OCE | Oceanside | Metro Routers | POInt | Yes | No | MRTR CA SAN OCE AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
77906 | HY COR COR P6L Voice BTS Decom POR19 | COR | COR | P6L | P6 Lab | Voice Decom and Refortification | POInt | Yes | No | VCDR COR COR P6L Voice BTS Decom POR19 | Labor | No Equipment | 1 | 2020-07-06 | 2020-10-31 |  | SN-0610 | 2020-05-29 | Chg
35176 | MRTR AAR-New-LFY-NEW-AAR | SE | LFY | LFY | Lafayette | Metro Routers | POInt | Yes | Yes | MRTR SE LFY LFY AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0662 | 2020-06-14 | Chg
74548 | R PHY_CCAP_RON_CBR8-1 | VA | ROA | RON | Roanoke | R PHY | POInt | Yes | Yes | R PHY VA ROA RON RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-10-31 |  | SN-0879 | 2020-08-28 | Chg
74548 | R PHY_CCAP_RON_Boundary_Clocks-1 | VA | ROA | RON | Roanoke | R PHY | POInt | Yes | Yes | R PHY VA ROA RON RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-10-31 |  | SN-0879 | 2020-08-28 | Chg
35171 | MRTR AAR-New-SOU-NEW-AAR | CE | OMA | SOU | South (OM) | Metro Routers | POInt | Yes | Yes | MRTR CE OMA SOU AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0939 | 2020-09-18
35171 | MRTR AAR-New-DBY-NEW-AAR | CE | KAN | DBY | Derby | Metro Routers | POInt | Yes | Yes | MRTR CE KAN DBY AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
35169 | MRTR AAR-New-NSC-NEW-AAR | SW | ARZ | NSC | North Scottsdale | Metro Routers | POInt | Yes | Yes | MRTR SW ARZ NSC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
35170 | MRTR AAR-New-ESC-NEW-AAR | CA | SAN | ESC | Escondido | Metro Routers | POInt | Yes | Yes | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
35176 | MRTR AAR-New-PNS-NEW-AAR | SE | GCT | PNS | Pensacola with (Insite tower) | Metro Routers | POInt | Yes | Yes | MRTR SE GCT PNS AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0662 | 2020-06-14 | Chg
35169 | MRTR SLR-New-PEO-NEW-SLR | SW | ARZ | PEO | Peoria | Metro Routers | POInt | Yes | Yes | MRTR SW ARZ PEO SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | New
35171 | MRTR AAR-New-BVL-NEW-AAR | CE | NWA | BVL | Bentonville | Metro Routers | POInt | Yes | Yes | MRTR CE NWA BVL AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
75246 | R PHY_CCAP_LUL_RPHY CCAP Licenses_Q2 NC Video | SE | NOR | LUL | Luling | R PHY | POInt | Yes | Yes | R PHY SE NOR LUL RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-10-31 | 2020-10-31 | SN-0605 | 2020-05-22 | Chg
35169 | MRTR AAR-New-BUK-NEW-AAR | SW | ARZ | BUK | Buckeye | Metro Routers | POInt | Yes | Yes | MRTR SW ARZ BUK AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
59745 | R PHY_CCAP_ESC_OTDR_1 | CA | SAN | ESC | Escondido | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN ESC RPHY CCAP Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-07-20 | 2020-10-31 |  | SN-0637 | 2020-06-05 | New
35177 | MRTR AAR-New-OCN-NEW-AAR | VA | HRD | OCN | Oceana | Metro Routers | POInt | Yes | Yes | MRTR VA HRD OCN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
35173 | MRTR AAR-New-ALI-NEW-AAR | SW | LAS | ALI | Aliante | Metro Routers | POInt | Yes | Yes | MRTR SW LAS ALI AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
35170 | MRTR AAR-New-ELC-NEW-AAR | CA | SAN | ELC | El Cajon | Metro Routers | POInt | Yes | Yes | MRTR CA SAN ELC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
35169 | MRTR AAR-New-CHD-NEW-AAR | SW | ARZ | CHD | Chandler | Metro Routers | POInt | Yes | Yes | MRTR SW ARZ CHD AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
75243 | RPHY MRTR-New-LUL-CIN MGMT-2K | SE | NOR | LUL | Luling | R PHY | POInt | Yes | Yes | R PHY SE NOR LUL RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-10-31 | 2020-10-31 | SN-0612 | 2020-05-29 | Chg
75243 | RPHY MRTR-New-LUL-CIN-DPA-5200 | SE | NOR | LUL | Luling | R PHY | POInt | Yes | Yes | R PHY SE NOR LUL RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-10-31 | 2020-10-31 | SN-0612 | 2020-05-29 | Chg
75243 | RPHY MRTR-New-LUL-CIN-RPA-5110 | SE | NOR | LUL | Luling | R PHY | POInt | Yes | Yes | R PHY SE NOR LUL RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-10-31 | 2020-10-31 | SN-0612 | 2020-05-29 | Chg
75243 | RPHY MRTR-New-LUL-CIN-ATX-OCML | SE | NOR | LUL | Luling | R PHY | POInt | Yes | Yes | R PHY SE NOR LUL RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-10-31 | 2020-10-31 | SN-0612 | 2020-05-29 | Chg
78095 | VCDR NE CLE CLV Voice Gateway Decom POR20 | NE | CLE | CLV | Cleveland | Voice Decom and Refortification | POInt | Yes | Yes | VCDR NE CLE CLV Voice Gateway Decom POR20 | Labor | No Equipment | 1 | 2020-06-30 | 2020-10-31 |  | SN-1080 | 2020-11-20
78340 | NR NTH MTC 48 Node Cell | SE | BTR | NTH | Baker | MTC 48 Node Cell | POInt | Yes | Yes | NR SE BTR NTH MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-15 | 2020-10-31 | 2020-10-31 | SN-0594 | 2020-05-20 | New
75245 | RPHY MRTR-New-TUL-CIN-RPA2-5110 | CE | TUL | TUL | Tulsa | R PHY | POInt | Yes | Yes | R PHY CE TUL TUL RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 10 | 2020-05-15 | 2020-10-31 | 2020-10-31 | SN-0612 | 2020-05-29 | Chg
75245 | RPHY MRTR-New-TUL-CIN-Nokia-OCML2 | CE | TUL | TUL | Tulsa | R PHY | POInt | Yes | Yes | R PHY CE TUL TUL RPHY Metro Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 50 | 2020-05-15 | 2020-10-31 | 2020-10-31 | SN-0612 | 2020-05-29 | Chg
75245 | RPHY MRTR-New-TUL-CIN MGMT2-2K | CE | TUL | TUL | Tulsa | R PHY | POInt | Yes | Yes | R PHY CE TUL TUL RPHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 3 | 2020-05-15 | 2020-10-31 | 2020-10-31 | SN-0612 | 2020-05-29 | Chg
75245 | RPHY MRTR-New-TUL-CIN Exfo-Switch | CE | TUL | TUL | Tulsa | R PHY | POInt | Yes | Yes | R PHY CE TUL TUL RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 6 | 2020-05-31 | 2020-10-31 | 2020-10-31 | SN-0710 | 2020-06-26 | Chg
35169 | MRTR AAR-New-PNL-NEW-AAR | SW | ARZ | PNL | Pinal County | Metro Routers | POInt | Yes | Yes | MRTR SW ARZ PNL AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
35173 | MRTR AAR-New-VLY-NEW-AAR | SW | LAS | VLY | Valley | Metro Routers | POInt | Yes | Yes | MRTR SW LAS VLY AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-11-30 | SN-0555 | 2020-05-12
75243 | RPHY MRTR-New-ABV-CIN MGMT-2K | SE | LFY | ABV | Abbeville | R PHY | POInt | Yes | Yes | R PHY SE LFY ABV RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-10-31 | 2020-09-30 | SN-0900 | 2020-09-11 | Chg
75243 | RPHY MRTR-New-ABV-CIN-DPA-5200 | SE | LFY | ABV | Abbeville | R PHY | POInt | Yes | Yes | R PHY SE LFY ABV RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-10-31 | 2020-09-30 | SN-0900 | 2020-09-11 | Chg
75243 | RPHY MRTR-New-ABV-CIN-RPA-5110 | SE | LFY | ABV | Abbeville | R PHY | POInt | Yes | Yes | R PHY SE LFY ABV RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-10-31 | 2020-09-30 | SN-0900 | 2020-09-11 | Chg
75243 | RPHY MRTR-New-ABV-CIN-ATX-OCML | SE | LFY | ABV | Abbeville | R PHY | POInt | Yes | Yes | R PHY SE LFY ABV RPHY Metro Initial Deployment POR19 | Chassis | OCML - ATX OCML RACK KIT | 12 | 2019-11-15 | 2020-10-31 | 2020-09-30 | SN-0900 | 2020-09-11 | Chg
35170 | MRTR AAR-New-DWN-NEW-AAR | CA | SAN | DWN | Downtown | Metro Routers | POInt | Yes | Yes | MRTR CA SAN DWN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
59745 | R PHY_CCAP_SAB_Boundary_Clocks_43936 | CA | SAB | SAB | Santa Barbara | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-04-15 | 2020-10-31 |  | SN-0637 | 2020-06-05 | Chg
59745 | R PHY_CCAP_STB_D9485_43936 | CA | SAB | SAB | Santa Barbara | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-02-15 | 2020-10-31 |  | SN-0637 | 2020-06-05 | Chg
59745 | R PHY_CCAP_SAB_Grand_Master_Clocks_43936 | CA | SAB | SAB | Santa Barbara | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2020-04-15 | 2020-10-31 |  | SN-0637 | 2020-06-05 | Chg
59745 | R PHY_CCAP_SAB_RPHY Bundled Solution V3_43966 | CA | SAB | SAB | Santa Barbara | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 3 | 2020-05-27 | 2020-10-31 | 2020-10-31 | SN-0637 | 2020-06-05 | Chg
59745 | R PHY_CCAP_SAB_OTDR_1 | CA | SAB | SAB | Santa Barbara | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAB SAB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-06-15 | 2020-10-31 |  | SN-0637 | 2020-06-05 | Chg
35169 | MRTR AAR-New-FWL-NEW-AAR | SW | ARZ | FWL | Fowler | Metro Routers | POInt | Yes | Yes | MRTR SW ARZ FWL AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
78099 | VCDR SW ARZ MCD Voice HDT Decom POR20 | SW | ARZ | MCD | McDowell | Voice Decom and Refortification | POInt | Yes | Yes | VCDR SW ARZ MCD Voice HDT Decom POR20 | Labor | No Equipment | 12 | 2020-08-04 | 2020-10-31 |  | SN-1080 | 2020-11-20
35177 | MRTR AAR-New-NRF-NEW-AAR | VA | HRD | NRF | Norfolk | Metro Routers | POInt | Yes | Yes | MRTR VA HRD NRF AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
35172 | MRTR OOB-New-SPC-OOB Server | SE | BTR | SPC | Pecue | Metro Routers | POInt | Yes | Yes | MRTR SE BTR SPC OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-31 | 2020-10-31 | 2020-11-30 | SN-0864 | 2020-08-21 | New
35172 | MRTR OOB-New-WRB-OOB Server | SE | MGA | WRB | Warner Robins | Metro Routers | POInt | Yes | Yes | MRTR SE MGA WRB OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-31 | 2020-10-31 | 2020-11-30 | SN-0864 | 2020-08-21 | New
35171 | MRTR AAR-New-BLV-NEW-AAR | CE | OMA | BLV | Bellevue | Metro Routers | POInt | Yes | Yes | MRTR CE OMA BLV AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0939 | 2020-09-18
35170 | MRTR AAR-New-RSM-NEW-AAR | CA | ORG | RSM | Rancho Santa Margarita | Metro Routers | POInt | Yes | Yes | MRTR CA ORG RSM AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0638 | 2020-06-05 | Chg
35169 | MRTR AAR-New-BLU-NEW-AAR | SW | LAS | BLU | Blue Diamond | Metro Routers | POInt | Yes | Yes | MRTR SW LAS BLU AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
35169 | MRTR AAR-New-BEL-NEW-AAR | SW | ARZ | BEL | Bell | Metro Routers | POInt | Yes | Yes | MRTR SW ARZ BEL AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
75245 | RPHY MRTR-Growth-WIC-CIN MGMT-2K | CE | KAN | WIC | Wichita | R PHY | POInt | Yes | Yes | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-04-01 | 2020-10-31 | 2020-10-31 | SN-0612 | 2020-05-29 | Chg
75245 | RPHY MRTR-New-WIC-CIN Exfo-Switch | CE | KAN | WIC | Wichita | R PHY | POInt | Yes | Yes | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 2 | 2020-05-15 | 2020-10-31 | 2020-10-31 | SN-0612 | 2020-05-29 | Chg
35171 | MRTR AAR-New-FAY-NEW-AAR | CE | NWA | FAY | Fayetteville | Metro Routers | POInt | Yes | Yes | MRTR CE NWA FAY AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
35177 | MRTR AAR-New-NWP-NEW-AAR | VA | HRD | NWP | Newport News | Metro Routers | POInt | Yes | Yes | MRTR VA HRD NWP AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
35169 | MRTR AAR-New-MSA-NEW-AAR | SW | ARZ | MSA | Mesa | Metro Routers | POInt | Yes | Yes | MRTR SW ARZ MSA AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
35176 | MRTR AAR-New-WRB-NEW-AAR | SE | MGA | WRB | Warner Robins | Metro Routers | POInt | Yes | Yes | MRTR SE MGA WRB AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0662 | 2020-06-14 | Chg
35176 | MRTR AAR-New-LPL-NEW-AAR | SE | NOR | LPL | Lapalco | Metro Routers | POInt | Yes | Yes | MRTR SE NOR LPL AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0662 | 2020-06-14 | Chg
78097 | VCDR SE NOR STB Voice HDT Decom POR20 | SE | NOR | STB | St. Bernard | Voice Decom and Refortification | POInt | Yes | Yes | VCDR SE NOR STB Voice HDT Decom POR20 | Labor | No Equipment | 6 | 2020-03-31 | 2020-10-31 |  | SN-0697 | 2020-07-10 | Chg
35169 | MRTR AAR-New-SSC-NEW-AAR | SW | ARZ | SSC | South Scottsdale | Metro Routers | POInt | Yes | Yes | MRTR SW ARZ SSC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
78097 | VCDR SE NOR ALG Voice HDT Decom POR20 | SE | NOR | ALG | Algiers | Voice Decom and Refortification | POInt | Yes | Yes | VCDR SE NOR ALG Voice HDT Decom POR20 | Labor | No Equipment | 1 |  | 2020-10-31 |  | SN-0697 | 2020-07-10 | Chg
75245 | RPHY MRTR-Growth-BLV-CIN MGMT-2K | CE | OMA | BLV | Bellevue | R PHY | POInt | Yes | Yes | R PHY CE OMA BLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-10-31 | 2020-10-31 | SN-0612 | 2020-05-29 | Chg
75245 | RPHY MRTR-New-BLV-CIN-DPA-5200 (100G DPIC) | CE | OMA | BLV | Bellevue | R PHY | POInt | Yes | Yes | R PHY CE OMA BLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-10-31 | 2020-10-31 | SN-0612 | 2020-05-29 | Chg
75245 | RPHY MRTR-New-BLV-CIN-RPA-5110 | CE | OMA | BLV | Bellevue | R PHY | POInt | Yes | Yes | R PHY CE OMA BLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-04-01 | 2020-10-31 | 2020-10-31 | SN-0612 | 2020-05-29 | Chg
75245 | RPHY MRTR-New-BLV-CIN-Nokia-OCML | CE | OMA | BLV | Bellevue | R PHY | POInt | Yes | Yes | R PHY CE OMA BLV RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-05-15 | 2020-10-31 | 2020-10-31 | SN-0612 | 2020-05-29 | Chg
75245 | RPHY MRTR-New-BLV-CIN Exfo-Switch | CE | OMA | BLV | Bellevue | R PHY | POInt | Yes | Yes | R PHY CE OMA BLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-10-31 | 2020-10-31 | SN-0612 | 2020-05-29 | Chg
74548 | R PHY_CCAP_RON_RPHY CCAP Licenses-1 | VA | ROA | RON | Roanoke | R PHY | POInt | Yes | Yes | R PHY VA ROA RON RPHY CCAP Augment POR20 | License | CCAP license | 621 | 2020-07-15 | 2020-10-31 | 2020-10-31 | SN-0879 | 2020-08-28 | Chg
34619 | CB Transport - New Router Quincy - QNC - Optics | CE | TUL | QNC | Quincy | CB - Metro Core | POInt | Yes | Yes | CBMC CE TUL QNC Optics Only for Cisco T5 Augment POR20_V2 | Card & Optics | Optics Only for Cisco T5 | 3 | 2020-08-15 | 2020-10-31 |  | SN-0986 | 2020-10-14 | Chg
74548 | R PHY_CCAP_RON_RPHY CCAP Licenses_Q2 NC Video | VA | ROA | RON | Roanoke | R PHY | POInt | Yes | Yes | R PHY VA ROA RON RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-10-31 | 2020-10-31 | SN-0879 | 2020-08-28 | Chg
74548 | R PHY_CCAP_RON_OTDR_1 | VA | ROA | RON | Roanoke | R PHY | POInt | Yes | Yes | R PHY VA ROA RON RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-10-31 |  | SN-0879 | 2020-08-28 | Chg
75246 | R PHY_CCAP_ABV_RPHY CCAP Licenses_Q2 NC Video | SE | LFY | ABV | Abbeville | R PHY | POInt | Yes | Yes | R PHY SE LFY ABV RPHY CCAP Augment POR20 | License | CCAP license | 816 | 2020-03-30 | 2020-10-31 | 2020-10-31 | SN-0899 | 2020-09-11 | Chg
75246 | R PHY_CCAP_ABV_OTDR_1 | SE | LFY | ABV | Abbeville | R PHY | POInt | Yes | Yes | R PHY SE LFY ABV RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-07-20 | 2020-10-31 |  | SN-0899 | 2020-09-11 | Chg
35175 | NEXUS-PAR-93180-01 | NE | CLE | PAR | Parma | Metro Routers | POInt | Yes | Yes | MRTR NE CLE PAR Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 6 | 2020-08-01 | 2020-10-31 | 2020-12-31 | SN-0662 | 2020-06-14 | New
35175 | NEXUS-PAR-2248-01 | NE | CLE | PAR | Parma | Metro Routers | POInt | Yes | Yes | MRTR NE CLE PAR Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 8 | 2020-08-01 | 2020-10-31 | 2020-12-31 | SN-0662 | 2020-06-14 | New
35172 | MRTR OOB-New-LUL-OOB Server | SE | NOR | LUL | Luling | Metro Routers | POInt | Yes | Yes | MRTR SE NOR LUL OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-31 | 2020-10-31 | 2020-11-30 | SN-0864 | 2020-08-21 | New
35172 | MRTR OOB-New-LPL-OOB Server | SE | NOR | LPL | Lapalco | Metro Routers | POInt | Yes | Yes | MRTR SE NOR LPL OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-31 | 2020-10-31 | 2020-11-30 | SN-0864 | 2020-08-21 | New
35176 | MRTR AAR-New-BTR-NEW-AAR | SE | BTR | BTR | Baton Rouge | Metro Routers | POInt | Yes | Yes | MRTR SE BTR BTR AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0662 | 2020-06-14 | Chg
35176 | MRTR AAR-New-ELM-NEW-AAR | SE | NOR | ELM | Elmwood | Metro Routers | POInt | Yes | Yes | MRTR SE NOR ELM AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0662 | 2020-06-14 | Chg
35172 | MRTR OOB-New-CLR-OOB Server | SE | NOR | CLR | Metairie | Metro Routers | POInt | Yes | Yes | MRTR SE NOR CLR OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-31 | 2020-10-31 | 2020-11-30 | SN-0864 | 2020-08-21 | New
35172 | MRTR OOB-New-FWB-OOB Server | SE | GCT | FWB | Ft. Walton Beach with (Insite tower) | Metro Routers | POInt | Yes | Yes | MRTR SE GCT FWB OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-31 | 2020-10-31 | 2020-11-30 | SN-0864 | 2020-08-21 | New
35175 | MRTR OOB-New-PAR-OOB Server | NE | CLE | PAR | Parma | Metro Routers | POInt | Yes | Yes | MRTR NE CLE PAR OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-08-01 | 2020-10-31 | 2020-12-31 | SN-0662 | 2020-06-14 | New
35177 | MRTR AAR-New-PRA-NEW-AAR | VA | HRD | PRA | Princess Anne | Metro Routers | POInt | Yes | Yes | MRTR VA HRD PRA AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
35169 | MRTR AAR-New-MCD-NEW-AAR | SW | ARZ | MCD | McDowell | Metro Routers | POInt | Yes | Yes | MRTR SW ARZ MCD AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
78099 | VCDR SW ARZ MSA Voice HDT Decom POR20 | SW | ARZ | MSA | Mesa | Voice Decom and Refortification | POInt | Yes | Yes | VCDR SW ARZ MSA Voice HDT Decom POR20 | Labor | No Equipment | 1 |  | 2020-10-31 |  | SN-1080 | 2020-11-20
35171 | MRTR AAR-New-TUL-NEW-AAR | CE | TUL | TUL | Tulsa | Metro Routers | POInt | Yes | Yes | MRTR CE TUL TUL AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
35171 | MRTR AAR-New-ELK-NEW-AAR | CE | OMA | ELK | Elkhorn | Metro Routers | POInt | Yes | Yes | MRTR CE OMA ELK AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
35169 | MRTR AAR-New-TUC-NEW-AAR | SW | ARZ | TUC | Tucson | Metro Routers | POInt | Yes | Yes | MRTR SW ARZ TUC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
35176 | MRTR OOB-New-CHO-OOB Server | CE | OKC | CHO | Choctaw | Metro Routers | POInt | Yes | Yes | MRTR CE OKC CHO OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-08-05 | 2020-10-31 | 2021-04-30 | SN-0158 | 2020-02-06 | Chg
35176 | MRTR OOB-New-CLH-OOB Server | CE | OKC | CLH | County Line | Metro Routers | POInt | Yes | Yes | MRTR CE OKC CLH OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-08-05 | 2020-10-31 | 2021-04-30 | SN-0158 | 2020-02-06 | Chg
35177 | MRTR AAR-New-FBG-NEW-AAR | VA | NVA | FBG | Fredericksburg | Metro Routers | POInt | Yes | Yes | MRTR VA NVA FBG AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
35177 | MRTR AAR-New-LTF-NEW-AAR | VA | HRD | LTF | Lightfoot | Metro Routers | POInt | Yes | Yes | MRTR VA HRD LTF AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
35169 | MRTR SLR-New-SSC-NEW-SLR | SW | ARZ | SSC | South Scottsdale | Metro Routers | POInt | Yes | Yes | MRTR SW ARZ SSC SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | New
35177 | MRTR AAR-New-PTM-NEW-AAR | VA | HRD | PTM | Portsmouth (VA) | Metro Routers | POInt | Yes | Yes | MRTR VA HRD PTM AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
75246 | R PHY_CCAP_ABV_CBR8-1 | SE | LFY | ABV | Abbeville | R PHY | POInt | Yes | Yes | R PHY SE LFY ABV RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-10-31 |  | SN-0899 | 2020-09-11 | Chg
75246 | R PHY_CCAP_ABV_Boundary_Clocks-1 | SE | LFY | ABV | Abbeville | R PHY | POInt | Yes | Yes | R PHY SE LFY ABV RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-10-31 |  | SN-0899 | 2020-09-11 | Chg
35171 | MRTR AAR-New-WES-NEW-AAR | CE | OMA | WES | West (OM) | Metro Routers | POInt | Yes | Yes | MRTR CE OMA WES AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0939 | 2020-09-18
35177 | MRTR AAR-New-VBC-NEW-AAR | VA | HRD | VBC | Virginia Beach | Metro Routers | POInt | Yes | Yes | MRTR VA HRD VBC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | SN-0555 | 2020-05-12 | Chg
75246 | R PHY_CCAP_PRV_CBR8_1 | NE | RHD | PRV | Providence | R PHY | POInt | Yes | Yes | R PHY NE RHD PRV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-04-28 | 2020-11-01 | 2020-11-01 | SN-0958 | 2020-09-25 | Chg
75246 | R PHY_CCAP_PRV_Boundary Clock_2 | NE | RHD | PRV | Providence | R PHY | POInt | Yes | Yes | R PHY NE RHD PRV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-05-30 | 2020-11-01 |  | SN-0958 | 2020-09-25 | Chg
75246 | R PHY_CCAP_PRV_OTDR_1 | NE | RHD | PRV | Providence | R PHY | POInt | Yes | Yes | R PHY NE RHD PRV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-11-01 |  | SN-0958 | 2020-09-25 | Chg
44876 | MTCH CE OKC NEH RPHY Test Rack Deployment POR20 | CE | OKC | NEH | North East | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH CE OKC NEH RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-09-06 | 2020-11-01 |  | SN-0219 | 2020-04-03
44876 | MTCH CE TUL GAR RPHY Test Rack Deployment POR20 | CE | TUL | GAR | Garnett | MTC HE - Hub Signaling | POInt | Yes | No | MTCH CE TUL GAR RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-09-06 | 2020-11-01 |  | SN-0219 | 2020-04-03
44876 | MTCH CE NWA FTS RPHY Test Rack Deployment POR20 | CE | NWA | FTS | Fort Smith | MTC HE - Hub Signaling | POInt | Yes | No | MTCH CE NWA FTS RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-09-06 | 2020-11-01 |  | SN-0219 | 2020-04-03
44876 | MTCH CE OMA ONA RPHY Test Rack Deployment POR20 | CE | OMA | ONA | North (OM) | MTC HE - Hub Signaling | POInt | Yes | No | MTCH CE OMA ONA RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-09-06 | 2020-11-01 |  | SN-0219 | 2020-04-03
44876 | MTCH CE KAN WIC RPHY Test Rack Deployment POR20 | CE | KAN | WIC | Wichita | MTC HE - Hub Signaling | POInt | Yes | No | MTCH CE KAN WIC RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-09-06 | 2020-11-01 |  | SN-0219 | 2020-04-03
75247 | R PHY_CCAP_PRV_GMC1 | NE | RHD | PRV | Providence | R PHY | POInt | Yes | No | R PHY NE RHD PRV RPHY CCAP Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2019-11-15 | 2020-11-01 |  | SN-0958 | 2020-09-25 | Chg
75244 | RPHY MRTR-New-PRV-CIN-RPA-5110 | NE | RHD | PRV | Providence | R PHY | POInt | Yes | No | R PHY NE RHD PRV RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-11-01 | 2020-08-31 | SN-0842 | 2020-08-14 | Chg
75244 | RPHY MRTR-New-PRV-CIN MGMT-2K | NE | RHD | PRV | Providence | R PHY | POInt | Yes | No | R PHY NE RHD PRV RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-11-01 | 2020-08-31 | SN-0842 | 2020-08-14 | Chg
75244 | RPHY MRTR-New-PRV-CIN Exfo-Switch | NE | RHD | PRV | Providence | R PHY | POInt | Yes | No | R PHY NE RHD PRV RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-11-01 | 2020-08-15 | SN-0842 | 2020-08-14 | Chg
46161 | MRTH-MCD-93180-01 | SW | ARZ | MCD | McDowell | Metro Nexus Thunder | POInt | Yes | Yes | MNEX SW ARZ MCD Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 4 | 2020-07-20 | 2020-11-03 | 2020-12-10 | SB-0237 | 2020-11-06 | Chg
46161 | MRTH-MCD-2248-01 | SW | ARZ | MCD | McDowell | Metro Nexus Thunder | POInt | Yes | Yes | MNEX SW ARZ MCD Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 6 | 2020-07-20 | 2020-11-03 | 2020-12-10 | SB-0237 | 2020-11-06 | Chg
34638 | BWM BTR DOCSIS Expansion 96 MHz | SE | BTR | BTR | Baton Rouge | Bandwidth Management | POInt | Yes | No | BWM SE BTR BTR DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-11-13 | 2022-07-01 | SN-0558 | 2020-05-12 | New
34638 | BWM LFY DOCSIS Expansion 96 MHz | SE | LFY | LFY | Lafayette | Bandwidth Management | POInt | Yes | No | BWM SE LFY LFY DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-11-13 | 2022-07-01 | SN-0558 | 2020-05-12 | New
34638 | BWM LFY DOCSIS Expansion 192 MHz | SE | LFY | LFY | Lafayette | Bandwidth Management | POInt | Yes | No | BWM SE LFY LFY DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-11-13 | 2021-04-01 | SN-0558 | 2020-05-12 | New
75788 | CDN Deploy 6 | VA | NVA | MFD | Merrifield | CDN | POInt | Yes | No | CDN VA NVA MFD Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-08-01 | 2020-11-13 | 2020-11-30 | SN-0803 | 2020-08-07 | Chg
39256 | BWM CON DOCSIS Expansion 96 MHz | NE | CON | ENF | Enfield | Bandwidth Management | POInt | Yes | No | BWM NE CON ENF DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-11-13 | 2021-10-01 | SN-0558 | 2020-05-12 | New
34638 | BWM BTR DOCSIS Expansion 192 MHz | SE | BTR | BTR | Baton Rouge | Bandwidth Management | POInt | Yes | No | BWM SE BTR BTR DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-11-13 | 2022-12-01 | SN-0558 | 2020-05-12 | New
34642 | BWM OMA DOCSIS Expansion 96 MHz | CE | OMA | BLV | Bellevue | Bandwidth Management | POInt | Yes | No | BWM CE OMA BLV DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-11-13 | 2021-01-06 | SN-0558 | 2020-05-12 | New
34642 | BWM OMA DOCSIS Expansion 192 MHz | CE | OMA | BLV | Bellevue | Bandwidth Management | POInt | Yes | No | BWM CE OMA BLV DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-11-13 | 2021-10-01 | SN-0558 | 2020-05-12 | New
39256 | BWM CON DOCSIS Expansion 192 MHz | NE | CON | ENF | Enfield | Bandwidth Management | POInt | Yes | No | BWM NE CON ENF DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-11-13 | 2022-07-01 | SN-0558 | 2020-05-12 | New
78456 | FI CA ORG ORG Orange Integration POR20 | CA | ORG | ORG | Orange | Facilities Integration | POInt | Yes | No | FI CA ORG ORG Orange Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling | 1 | 2020-04-08 | 2020-11-15 |  | SN-0440 | 2020-04-10 | Chg
75187 | R PHY_CCAP_TUL_RPHY CCAP Licenses-1 | CE | TUL | TUL | Tulsa | R PHY | POInt | Yes | No | R PHY CE TUL TUL R PHY CCAP Deployment POR20 | License | CCAP license | 2319 | 2020-10-15 | 2020-11-15 | 2020-11-15 | SN-0550 | 2020-05-12 | New
75187 | R PHY_CCAP_OWA_RPHY CCAP Licenses-1 | CE | TUL | OWA | Owasso | R PHY | POInt | Yes | No | R PHY CE TUL OWA RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-10-15 | 2020-11-15 | 2020-11-15 | SN-0550 | 2020-05-12 | New
75663 | V2B COR COR DDR Ops Facility Tools Augment POR20 | COR | COR | DDR | Duke Drive | V2B | POInt | Yes | No | V2B COR COR DDR Ops Facility Tools Augment POR20 | Labor | Other | 1 | 2020-02-06 | 2020-11-15 | 2020-12-15 | SN-0430 | 2020-04-10 | Chg
75187 | R PHY_CCAP_YAL_RPHY CCAP Licenses-1 | CE | TUL | YAL | Yale | R PHY | POInt | Yes | No | R PHY CE TUL YAL RPHY CCAP Augment POR20 | License | CCAP license | 190 | 2020-10-15 | 2020-11-15 | 2020-11-15 | SN-0550 | 2020-05-12 | New
75187 | R PHY_CCAP_SOU_RPHY CCAP Licenses-1 | CE | OMA | SOU | South (OM) | R PHY | POInt | Yes | No | R PHY CE OMA SOU RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-10-15 | 2020-11-15 | 2020-11-15 | SN-0550 | 2020-05-12 | New
75187 | R PHY_CCAP_CLH_RPHY CCAP Licenses-1 | CE | OKC | CLH | County Line | R PHY | POInt | Yes | Yes | R PHY CE OKC CLH RPHY CCAP Augment POR20 | License | CCAP license | 52 | 2020-10-15 | 2020-11-15 | 2020-11-15 | SN-0550 | 2020-05-12 | New
74548 | R PHY_CCAP_PTM_RPHY CCAP Licenses-2 | VA | HRD | PTM | Portsmouth (VA) | R PHY | POInt | Yes | Yes | R PHY VA HRD PTM RPHY CCAP Augment POR20 | License | CCAP license | 52 | 2020-10-15 | 2020-11-15 | 2020-11-15 | SN-0550 | 2020-05-12 | New
35169 | MRTR NCS-Growth-MCD-100G Grow | SW | ARZ | MCD | McDowell | Metro Routers | POInt | Yes | Yes | MRTR SW ARZ MCD 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-09-01 | 2020-11-15 | 2020-12-31 | SN-0588 | 2020-05-14 | Chg
59522 | R PHY_CCAP_MCD_RPHY CCAP Licenses-2 | SW | ARZ | MCD | McDowell | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ MCD RPHY CCAP Deployment POR20 | License | CCAP license | 104 | 2020-10-15 | 2020-11-15 | 2020-11-15 | SN-0550 | 2020-05-12 | New
75187 | R PHY_CCAP_WLK_RPHY CCAP Licenses-1 | CE | OKC | WLK | Walker Hub | R PHY | POInt | Yes | Yes | R PHY CE OKC WLK RPHY CCAP Augment POR20 | License | CCAP license | 26 | 2020-10-15 | 2020-11-15 | 2020-11-15 | SN-0550 | 2020-05-12 | New
34616 | sr01.nor.okc.ok-ROUTER | CE | OKC | NOR | Norman | CB - Metro Core | POInt | Yes | Yes | CBMC CE OKC NOR ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-08-15 | 2020-11-15 |  | SN-0144 | 2020-02-06 | Chg
59522 | R PHY_CCAP_FWL_RPHY CCAP Licenses-2 | SW | ARZ | FWL | Fowler | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ FWL RPHY CCAP Deployment POR20 | License | CCAP license | 390 | 2020-10-15 | 2020-11-15 | 2020-11-15 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_MSA_RPHY CCAP Licenses-2 | SW | ARZ | MSA | Mesa | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ MSA RPHY CCAP Deployment POR20 | License | CCAP license | 2196 | 2020-10-15 | 2020-11-15 | 2020-11-15 | SN-0813 | 2020-08-12 | Chg
34619 | sr01.neh.okc.ok-ROUTER | CE | OKC | NEH | North East | CB - Metro Core | POInt | Yes | Yes | CBMC CE OKC NEH ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-08-15 | 2020-11-15 |  | SN-0144 | 2020-02-06 | Chg
75187 | R PHY_CCAP_QNC_RPHY CCAP Licenses-1 | CE | TUL | QNC | Quincy | R PHY | POInt | Yes | Yes | R PHY CE TUL QNC RPHY CCAP Augment POR20 | License | CCAP license | 242 | 2020-10-15 | 2020-11-15 | 2020-11-15 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_PNL_RPHY CCAP Licenses-2 | SW | ARZ | PNL | Pinal County | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ PNL RPHY CCAP Deployment POR20 | License | CCAP license | 26 | 2020-10-15 | 2020-11-15 | 2020-11-15 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_OSB_RPHY CCAP Licenses-1 | SW | LAS | OSB | Oso Blanca | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS OSB RPHY CCAP Initial Deployment POR20 | License | CCAP license | 260 | 2020-10-15 | 2020-11-15 | 2020-11-15 | SN-0605 | 2020-05-22 | Chg
75187 | R PHY_CCAP_OKC_RPHY CCAP Licenses-1 | CE | OKC | OKC | OKC MTC | R PHY | POInt | Yes | Yes | R PHY CE OKC OKC RPHY CCAP Augment POR20 | License | CCAP license | 286 | 2020-10-15 | 2020-11-15 | 2020-11-15 | SN-0550 | 2020-05-12 | New
74548 | R PHY_CCAP_NRF_RPHY CCAP Licenses-2 | VA | HRD | NRF | Norfolk | R PHY | POInt | Yes | Yes | R PHY VA HRD NRF RPHY CCAP Augment POR20 | License | CCAP license | 416 | 2020-10-15 | 2020-11-15 | 2020-11-15 | SN-0550 | 2020-05-12 | New
74548 | R PHY_CCAP_OCN_RPHY CCAP Licenses-1 | VA | HRD | OCN | Oceana | R PHY | POInt | Yes | Yes | R PHY VA HRD OCN RPHY CCAP Augment POR20 | License | CCAP license | 78 | 2020-10-15 | 2020-11-15 | 2020-11-15 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_ALI_RPHY CCAP Licenses-1 | SW | LAS | ALI | Aliante | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS ALI RPHY CCAP Deployment POR20 | License | CCAP license | 882 | 2020-10-15 | 2020-11-15 | 2020-11-15 | SN-0550 | 2020-05-12 | New
75187 | R PHY_CCAP_BAR_RPHY CCAP Licenses-2 | CE | TUL | BAR | Broken Arrow | R PHY | POInt | Yes | Yes | R PHY CE TUL BAR RPHY CCAP Deployment POR20 | License | CCAP license | 182 | 2020-10-15 | 2020-11-15 | 2020-11-15 | SN-0550 | 2020-05-12 | New
75246 | R PHY_CCAP_BTR_RPHY CCAP Licenses-2 | SE | BTR | BTR | Baton Rouge | R PHY | POInt | Yes | Yes | R PHY SE BTR BTR RPHY CCAP Augment POR20 | License | CCAP license | 69 | 2020-10-15 | 2020-11-15 | 2020-11-15 | SN-0879 | 2020-08-28 | Chg
59522 | R PHY_CCAP_PEO_RPHY CCAP Licenses-2 | SW | ARZ | PEO | Peoria | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ PEO RPHY CCAP Deployment POR20 | License | CCAP license | 234 | 2020-10-15 | 2020-11-15 | 2020-11-15 | SN-0550 | 2020-05-12 | New
35169 | MRTR NCS-Growth-TUC-100G Grow | SW | ARZ | TUC | Tucson | Metro Routers | POInt | Yes | Yes | MRTR SW ARZ TUC 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-09-01 | 2020-11-15 | 2020-11-15 | SN-0099 | 2020-02-06 | Chg
59522 | R PHY_CCAP_TUC_RPHY CCAP Licenses-2 | SW | ARZ | TUC | Tucson | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ TUC RPHY CCAP Deployment POR20 | License | CCAP license | 329 | 2020-10-15 | 2020-11-15 | 2020-11-15 | SN-0550 | 2020-05-12 | New
74548 | R PHY_CCAP_RON_RPHY CCAP Licenses-2 | VA | ROA | RON | Roanoke | R PHY | POInt | Yes | Yes | R PHY VA ROA RON RPHY CCAP Augment POR20 | License | CCAP license | 552 | 2020-10-15 | 2020-11-15 | 2020-11-15 | SN-0550 | 2020-05-12 | New
75187 | R PHY_CCAP_GAR_RPHY CCAP Licenses-1 | CE | TUL | GAR | Garnett | R PHY | POInt | Yes | Yes | R PHY CE TUL GAR RPHY - CCAP Initial Deployment POR20 | License | CCAP license | 26 | 2020-10-15 | 2020-11-15 | 2020-11-15 | SN-0550 | 2020-05-12 | New
75246 | R PHY_CCAP_LFY_RPHY CCAP Licenses-1 | SE | LFY | LFY | Lafayette | R PHY | POInt | Yes | Yes | R PHY SE LFY LFY RPHY CCAP Augment POR20 | License | CCAP license | 138 | 2020-10-15 | 2020-11-15 | 2020-11-15 | SN-0550 | 2020-05-12 | New
75187 | R PHY_CCAP_ELK_RPHY CCAP Licenses-1 | CE | OMA | ELK | Elkhorn | R PHY | POInt | Yes | Yes | R PHY CE OMA ELK RPHY CCAP Augment POR20 | License | CCAP license | 414 | 2020-10-15 | 2020-11-15 | 2020-11-15 | SN-0550 | 2020-05-12 | New
74548 | R PHY_CCAP_PRA_RPHY CCAP Licenses-2 | VA | HRD | PRA | Princess Anne | R PHY | POInt | Yes | Yes | R PHY VA HRD PRA RPHY CCAP Augment POR20 | License | CCAP license | 78 | 2020-10-15 | 2020-11-15 | 2020-11-15 | SN-0550 | 2020-05-12 | New
59745 | R PHY_CCAP_ESC_RPHY CCAP Licenses-2 | CA | SAN | ESC | Escondido | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN ESC RPHY CCAP Deployment POR20 | License | CCAP license | 78 | 2020-10-15 | 2020-11-15 | 2020-11-15 | SN-0550 | 2020-05-12 | New
74548 | R PHY_CCAP_CHS_RPHY CCAP Licenses-2 | VA | HRD | CHS | Chesapeake | R PHY | POInt | Yes | Yes | R PHY VA HRD CHS RPHY CCAP Augment POR20 | License | CCAP license | 78 | 2020-10-15 | 2020-11-15 | 2020-11-15 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_BUK_RPHY CCAP Licenses-2 | SW | ARZ | BUK | Buckeye | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ BUK RPHY CCAP Deployment POR20 | License | CCAP license | 26 | 2020-10-15 | 2020-11-15 | 2020-11-15 | SN-0550 | 2020-05-12 | New
44876 | MTCH CE OKC TUL MPEG4 vDCM Install Deployment POR20 | CE | TUL | TUL | Tulsa | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH CE TUL TUL MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-06-06 | 2020-11-15 | 2021-03-15 | SN-0575 | 2020-05-14 | Chg
59522 | R PHY_CCAP_NSC_RPHY CCAP Licenses-2 | SW | ARZ | NSC | North Scottsdale | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ NSC RPHY CCAP Deployment POR20 | License | CCAP license | 52 | 2020-10-15 | 2020-11-15 | 2020-11-15 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_BEL_RPHY CCAP Licenses-2 | SW | ARZ | BEL | Bell | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ BEL RPHY CCAP Deployment POR20 | License | CCAP license | 1011 | 2020-10-15 | 2020-11-15 | 2020-11-15 | SN-0550 | 2020-05-12 | New
44876 | MTCH CE OMA OMM MPEG4 vDCM Install Deployment POR20 | CE | OMA | OMM | Omaha | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH CE OMA OMM MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-05-06 | 2020-11-15 | 2021-03-15 | SN-0227 | 2020-03-30 | Chg
59522 | R PHY_CCAP_SSC_RPHY CCAP Licenses- | SW | ARZ | SSC | South Scottsdale | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ SSC RPHY CCAP Deployment POR20 | License | CCAP license | 830 | 2020-10-15 | 2020-11-15 | 2020-11-15 | SN-0550 | 2020-05-12 | New
35169 | MRTR NCS-Growth-CHD-100G Grow | SW | ARZ | CHD | Chandler | Metro Routers | POInt | Yes | Yes | MRTR SW ARZ CHD 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-09-01 | 2020-11-15 | 2020-12-31 | SN-0588 | 2020-05-14 | Chg
75187 | R PHY_CCAP_BVL_RPHY CCAP Licenses-1 | CE | NWA | BVL | Bentonville | R PHY | POInt | Yes | Yes | R PHY CE NWA BVL RPHY CCAP Augment POR20 | License | CCAP license | 416 | 2020-10-15 | 2020-11-15 | 2020-11-15 | SN-0550 | 2020-05-12 | New
34970 | CFG CHD HV-CFG GEN GROW PROJECT - MEDIUM | SW | ARZ | CHD | Chandler | Critical Facilities (Grow) | POInt | Yes | Yes | CFG SW ARZ CHD BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-10-01 | 2020-11-15
59745 | R PHY_CCAP_FED_RPHY CCAP Licenses-2 | CA | SAN | FED | Federal | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN FED RPHY CCAP Deployment POR20 | License | CCAP license | 598 | 2020-10-15 | 2020-11-15 | 2020-11-15 | SN-0813 | 2020-08-12 | Chg
75245 | RPHY MRTR-Growth-FTS-CIN MGMT-2K | CE | NWA | FTS | Fort Smith | R PHY | POInt | Yes | Yes | R PHY CE NWA FTS RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-04-01 | 2020-11-20 | 2020-09-30 | SN-0900 | 2020-09-11 | Chg
75245 | RPHY MRTR-New-FTS-CIN-DPA-5200 (100G DPIC) | CE | NWA | FTS | Fort Smith | R PHY | POInt | Yes | Yes | R PHY CE NWA FTS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-11-20 | 2020-09-30 | SN-0900 | 2020-09-11 | Chg
75245 | RPHY MRTR-New-FTS-CIN-RPA-5110 | CE | NWA | FTS | Fort Smith | R PHY | POInt | Yes | Yes | R PHY CE NWA FTS RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-11-20 | 2020-09-30 | SN-0900 | 2020-09-11 | Chg
75245 | RPHY MRTR-New-FTS-CIN-Nokia-OCML | CE | NWA | FTS | Fort Smith | R PHY | POInt | Yes | Yes | R PHY CE NWA FTS RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-05-15 | 2020-11-20 | 2020-09-30 | SN-0900 | 2020-09-11 | Chg
75245 | RPHY MRTR-New-FTS-CIN Exfo-Switch | CE | NWA | FTS | Fort Smith | R PHY | POInt | Yes | Yes | R PHY CE NWA FTS RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-11-20 | 2020-09-30 | SN-0900 | 2020-09-11 | Chg
78334 | NR BEL MTC 48 Node Cell | SW | ARZ | BEL | Bell | MTC 48 Node Cell | POInt | Yes | Yes | NR SW ARZ BEL MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-11-30 | 2020-11-30 | SN-0946 | 2020-09-25 | Chg
35170 | MRTR AAR-New-PAV-NEW-AAR | CA | ORG | PAV | Palos Verdes | Metro Routers | POInt | Yes | Yes | MRTR CA ORG PAV AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | SN-0750 | 2020-07-15 | Chg
35170 | MRTR AAR-New-ORG-NEW-AAR | CA | ORG | ORG | Orange | Metro Routers | POInt | Yes | Yes | MRTR CA ORG ORG AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 1 | 2020-09-01 | 2020-11-30 | 2020-12-31 | SN-0750 | 2020-07-15 | New
35175 | MRTR SLR-New-PAW-AAR-ASR9906 | NE | RHD | PAW | Pawtucket | Metro Routers | POInt | Yes | Yes | MRTR NE RHD PAW AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-15 | 2020-11-30 | 2020-12-30 | SN-1037 | 2020-11-06 | Chg
75245 | RPHY MRTR-New-GAR-CIN Exfo-Switch | CE | TUL | GAR | Garnett | R PHY | POInt | Yes | Yes | R PHY CE TUL GAR RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 2 | 2020-05-31 | 2020-11-30 | 2020-11-30 | SN-0612 | 2020-05-29 | Chg
75245 | RPHY MRTR-Growth-GAR-CIN MGMT-2K | CE | TUL | GAR | Garnett | R PHY | POInt | Yes | Yes | R PHY CE TUL GAR RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-05-15 | 2020-11-30 | 2020-11-30 | SN-0612 | 2020-05-29 | Chg
75245 | RPHY MRTR-New-GAR-CIN-DPA-5200 (100G DPIC) | CE | TUL | GAR | Garnett | R PHY | POInt | Yes | Yes | R PHY CE TUL GAR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-11-30 | 2020-11-30 | SN-0612 | 2020-05-29 | Chg
75245 | RPHY MRTR-New-GAR-CIN-RPA-5110 | CE | TUL | GAR | Garnett | R PHY | POInt | Yes | Yes | R PHY CE TUL GAR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-11-30 | 2020-11-30 | SN-0612 | 2020-05-29 | Chg
34619 | TOPEBSRA01-ROUTER | CE | KAN | TOP | Topeka | CB - Metro Core | POInt | Yes | Yes | CBMC CE KAN TOP ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-05-15 | 2020-11-30 |  | SN-1049 | 2020-11-13 | Chg
35176 | MRTR OOB-New-MWC-OOB Server | CE | OKC | MWC | Midwest City | Metro Routers | POInt | Yes | Yes | MRTR CE OKC MWC OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-09-05 | 2020-11-30 | 2021-02-28 | SN-0158 | 2020-02-06 | Chg
78334 | NR SSC MTC 48 Node Cell | SW | ARZ | SSC | South Scottsdale | MTC 48 Node Cell | POInt | Yes | Yes | NR SW ARZ SSC MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-11-30 | 2020-11-30 | SN-0946 | 2020-09-25 | Chg
78097 | VCDR SE NOR LPL Voice HDT Decom POR20 | SE | NOR | LPL | Lapalco | Voice Decom and Refortification | POInt | Yes | Yes | VCDR SE NOR LPL Voice HDT Decom POR20 | Labor | No Equipment | 1 |  | 2020-11-30 |  | SN-0697 | 2020-07-10 | New
78334 | NR BUK MTC 48 Node Cell | SW | ARZ | BUK | Buckeye | MTC 48 Node Cell | POInt | Yes | Yes | NR SW ARZ BUK MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-11-30 | 2020-11-30 | SN-0946 | 2020-09-25 | Chg
35169 | MRTR NCS-Growth-PEO-NCS Line Card | SW | ARZ | PEO | Peoria | Metro Routers | POInt | Yes | Yes | MRTR SW ARZ PEO NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-09-01 | 2020-11-30 | 2021-02-28 | SN-0158 | 2020-02-06 | Chg
35176 | MRTR SLR-New-SAP-AAR-ASR9906 | CE | TUL | SAP | Sapulpa | Metro Routers | POInt | Yes | Yes | MRTR CE TUL SAP AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-15 | 2020-11-30 | 2020-12-31 | SN-1037 | 2020-11-06 | Chg
35171 | MRTR AAR-New-DTN-NEW-AAR | CE | TUL | DTN | Downtown (TUL) | Metro Routers | POInt | Yes | Yes | MRTR CE TUL DTN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | SN-0651 | 2020-06-14 | New
34608 | CB Transport - New Router Village - NRF - Optics | VA | HRD | NRF | Norfolk | CB - Metro Core | POInt | Yes | Yes | CBMC VA HRD NRF Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-02-15 | 2020-11-30 |  | SN-0934 | 2020-09-18 | Chg
34608 | CB Transport - New Router Greenbrier - NRF - Optics | VA | HRD | NRF | Norfolk | CB - Metro Core | POInt | Yes | Yes | CBMC VA HRD NRF Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-03-15 | 2020-11-30 |  | SN-0934 | 2020-09-18 | Chg
35170 | MRTR SLR-New-PWY-SLR-ASR9906 | CA | SAN | PWY | Poway | Metro Routers | POInt | Yes | Yes | MRTR CA SAN PWY SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | SN-0866 | 2020-08-21
78334 | NR TUC MTC 48 Node Cell | SW | ARZ | TUC | Tucson | MTC 48 Node Cell | POInt | Yes | Yes | NR SW ARZ TUC MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-11-30 | 2020-11-30 | SN-0946 | 2020-09-25 | Chg
35171 | MRTR AAR-New-YAL-NEW-AAR | CE | TUL | YAL | Yale | Metro Routers | POInt | Yes | Yes | MRTR CE TUL YAL AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | SN-0651 | 2020-06-14 | New
35171 | MRTR OOB-New-WIC-OOB Server | CE | KAN | WIC | Wichita | Metro Routers | POInt | Yes | Yes | MRTR CE KAN WIC OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-09-05 | 2020-11-30 | 2021-02-28 | SN-0158 | 2020-02-06 | Chg
78334 | NR NSC MTC 48 Node Cell | SW | ARZ | NSC | North Scottsdale | MTC 48 Node Cell | POInt | Yes | Yes | NR SW ARZ NSC MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-11-30 | 2020-11-30 | SN-0946 | 2020-09-25 | Chg
78097 | HY SE GAN GNS Voice BTS Gateway Decom POR19 | SE | GAN | GNS | Gainesville | Voice Decom and Refortification | POInt | Yes | Yes | VCDR SE GAN GNS Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 | 2020-05-04 | 2020-11-30 |  | SN-0697 | 2020-07-10 | Chg
35171 | MRTR AAR-New-FTS-NEW-AAR | CE | NWA | FTS | Fort Smith | Metro Routers | POInt | Yes | Yes | MRTR CE NWA FTS AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | SN-0651 | 2020-06-14 | New
35176 | MRTR AAR-New-WLK-NEW-AAR | CE | OKC | WLK | Walker Hub | Metro Routers | POInt | Yes | Yes | MRTR CE OKC WLK AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | SN-0651 | 2020-06-14
35176 | MRTR AAR-New-OKC-NEW-AAR | CE | OKC | OKC | OKC MTC | Metro Routers | POInt | Yes | Yes | MRTR CE OKC OKC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | SN-0651 | 2020-06-14
35171 | MRTR AAR-New-GAR-NEW-AAR | CE | TUL | GAR | Garnett | Metro Routers | POInt | Yes | Yes | MRTR CE TUL GAR AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | SN-0651 | 2020-06-14 | New
35170 | MRTR AAR-New-FED-NEW-AAR | CA | SAN | FED | Federal | Metro Routers | POInt | Yes | Yes | MRTR CA SAN FED AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | SN-0651 | 2020-06-14
75187 | R PHY_CCAP_MWC_Boundary_Clocks_44119 | CE | OKC | MWC | Midwest City | R PHY | POInt | Yes | Yes | R PHY CE OKC MWC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-05-10 | 2020-11-30 |  | SN-0613 | 2020-05-29 | Chg
75187 | R PHY_CCAP_MWC_D9485_44119 | CE | OKC | MWC | Midwest City | R PHY | POInt | Yes | Yes | R PHY CE OKC MWC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-04-15 | 2020-11-30 |  | SN-0613 | 2020-05-29 | Chg
75187 | R PHY_CCAP_MWC_RPHY Bundled Solution V3_44119 | CE | OKC | MWC | Midwest City | R PHY | POInt | Yes | Yes | R PHY CE OKC MWC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-04-28 | 2020-11-30 | 2020-11-30 | SN-0613 | 2020-05-29 | Chg
75187 | R PHY_CCAP_MWC_OTDR_1 | CE | OKC | MWC | Midwest City | R PHY | POInt | Yes | Yes | R PHY CE OKC MWC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-07-20 | 2020-11-30 |  | SN-0637 | 2020-06-05 | New
78334 | NR VSA MTC 48 Node Cell | SW | ARZ | VSA | Vistancia | MTC 48 Node Cell | POInt | Yes | Yes | NR SW ARZ VSA MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-11-30 | 2020-11-30 | SN-0946 | 2020-09-25 | Chg
35170 | MRTR AAR-New-PWY-NEW-AAR | CA | SAN | PWY | Poway | Metro Routers | POInt | Yes | Yes | MRTR CA SAN PWY AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | SN-0651 | 2020-06-14
75187 | R PHY_CCAP_GAR_Boundary_Clocks_44119 | CE | TUL | GAR | Garnett | R PHY | POInt | Yes | Yes | R PHY CE TUL GAR RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-07-05 | 2020-11-30 |  | SN-0613 | 2020-05-29 | Chg
75187 | R PHY_CCAP_GAR_RPHY Bundled Solution V3_44119 | CE | TUL | GAR | Garnett | R PHY | POInt | Yes | Yes | R PHY CE TUL GAR RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-07-15 | 2020-11-30 | 2020-11-30 | SN-0613 | 2020-05-29 | Chg
75187 | R PHY_CCAP_GAR_OTDR_1 | CE | TUL | GAR | Garnett | R PHY | POInt | Yes | Yes | R PHY CE TUL GAR RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-07-20 | 2020-11-30 |  | SN-0637 | 2020-06-05 | New
34608 | CB Transport - New Router Newport News - NWP - Optics | VA | HRD | NWP | Newport News | CB - Metro Core | POInt | Yes | Yes | CBMC VA HRD NWP Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-02-15 | 2020-11-30 |  | SN-0934 | 2020-09-18 | Chg
35171 | MRTR OOB-New-FTS-OOB Server | CE | NWA | FTS | Fort Smith | Metro Routers | POInt | Yes | Yes | MRTR CE NWA FTS OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-09-01 | 2020-11-30 | 2021-02-28 | SN-0158 | 2020-02-06 | Chg
75245 | RPHY MRTR-Growth-MWC-CIN MGMT-2K | CE | OKC | MWC | Midwest City | R PHY | POInt | Yes | Yes | R PHY CE OKC MWC RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-04-01 | 2020-11-30 | 2020-11-30 | SN-0612 | 2020-05-29 | Chg
75245 | RPHY MRTR-New-MWC-CIN-DPA-5200 (100G DPIC) | CE | OKC | MWC | Midwest City | R PHY | POInt | Yes | Yes | R PHY CE OKC MWC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-11-30 | 2020-11-30 | SN-0612 | 2020-05-29 | Chg
75245 | RPHY MRTR-New-MWC-CIN-RPA-5110 | CE | OKC | MWC | Midwest City | R PHY | POInt | Yes | Yes | R PHY CE OKC MWC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-05-15 | 2020-11-30 | 2020-11-30 | SN-0612 | 2020-05-29 | Chg
75245 | RPHY MRTR-New-MWC-CIN Exfo-Switch | CE | OKC | MWC | Midwest City | R PHY | POInt | Yes | Yes | R PHY CE OKC MWC RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 2 | 2020-05-31 | 2020-11-30 | 2020-11-30 | SN-0612 | 2020-05-29 | Chg
75245 | RPHY MRTR-New-MWC-CIN-Nokia-OCML | CE | OKC | MWC | Midwest City | R PHY | POInt | Yes | Yes | R PHY CE OKC MWC RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 20 | 2020-05-15 | 2020-11-30 | 2020-11-30 | SN-0612 | 2020-05-29 | Chg
35170 | MRTR AAR-New-DNP-NEW-AAR | CA | ORG | DNP | Dana Point | Metro Routers | POInt | Yes | Yes | MRTR CA ORG DNP AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | SN-0651 | 2020-06-14
35170 | MRTR AAR-New-AVJ-NEW-AAR | CA | ORG | AVJ | Aliso Viejo | Metro Routers | POInt | Yes | Yes | MRTR CA ORG AVJ AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | SN-0651 | 2020-06-14
35170 | MRTR AAR-New-SAB-NEW-AAR | CA | SAB | SAB | Santa Barbara | Metro Routers | POInt | Yes | Yes | MRTR CA SAB SAB AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-15 | 2020-11-30 | 2020-12-31 | SN-0750 | 2020-07-15 | New
35176 | MRTR SLR-New-IND-AAR-ASR9906 | CE | TUL | IND | Indianapolis | Metro Routers | POInt | Yes | Yes | MRTR CE TUL IND AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-15 | 2020-11-30 | 2020-12-31 | SN-1037 | 2020-11-06 | Chg
34944 | Photonic-OTN-HHH-M15 | CA | SAN | FED | Federal | Metro Transport | POInt | Yes | Yes | MTRN CA SAN ALP DWDM Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | SN-0805 | 2020-08-07
34944 | Photonic-OTN-HHH-M6 | CA | SAN | FED | Federal | Metro Transport | POInt | Yes | Yes | MTRN CA SAN ALP DWDM Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | SN-0805 | 2020-08-07
78097 | VCDR SE NOR MCY Voice HDT Decom POR20 | SE | NOR | MCY | Mid-City | Voice Decom and Refortification | POInt | Yes | Yes | VCDR SE NOR MCY Voice HDT Decom POR20 | Labor | No Equipment | 1 |  | 2020-11-30 |  | SN-0697 | 2020-07-10 | New
35171 | MRTR AAR-New-OWA-NEW-AAR | CE | TUL | OWA | Owasso | Metro Routers | POInt | Yes | Yes | MRTR CE TUL OWA AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-15 | 2020-11-30 | 2020-12-31 | SN-0750 | 2020-07-15
34623 | SESTA01.LV.LV.COX.NET-ROUTER | SW | LAS | HEN | Henderson | CB - Metro Core | POInt | Yes | Yes | CBMC SW LAS HEN ROUTER-7750 SR-7s Deployment POR20 v2 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-08-01 | 2020-11-30 |  | SN-0611 | 2020-05-29 | New
78093 | HY CE OMA ONA Voice HDT Decom POR20 | CE | OMA | ONA | North (OM) | Voice Decom and Refortification | POInt | Yes | Yes | VCDR CE OMA ONA Voice HDT Decom POR20 | Labor | No Equipment | 17 | 2020-08-03 | 2020-11-30 |  | SN-0697 | 2020-07-10 | Chg
78334 | NR PEO MTC 48 Node Cell | SW | ARZ | PEO | Peoria | MTC 48 Node Cell | POInt | Yes | Yes | NR SW ARZ PEO MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-11-30 | 2020-11-30 | SN-0946 | 2020-09-25 | Chg
35172 | MRTR AAR-New-SPC-NEW-AAR | SE | BTR | SPC | Pecue | Metro Routers | POInt | Yes | Yes | MRTR SE BTR SPC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | SN-0651 | 2020-06-14 | New
35171 | MRTR SLR-New-DTN-SLR-ASR9906 | CE | TUL | DTN | Downtown (TUL) | Metro Routers | POInt | Yes | Yes | MRTR CE TUL DTN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | SN-1037 | 2020-11-06
35171 | MRTR OOB-New-ONA-OOB Server | CE | OMA | ONA | North (OM) | Metro Routers | POInt | Yes | Yes | MRTR CE OMA ONA OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-09-01 | 2020-11-30 | 2021-02-28 | SN-0158 | 2020-02-06 | Chg
78101 | Voice HDT Decom POR20 | VA | HRD | NKT | New Kent | Voice Decom and Refortification | POInt | Yes | Yes | VCDR VA HRD NKT Voice HDT Decom POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-11-30 |  | SN-0644 | 2020-06-15 | Chg
35171 | MRTR AAR-New-BRD-NEW-AAR | CE | TUL | BRD | Braden | Metro Routers | POInt | Yes | Yes | MRTR CE TUL BRD AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-15 | 2020-11-30 | 2020-12-31 | SN-0750 | 2020-07-15
78334 | NR MCD MTC 48 Node Cell | SW | ARZ | MCD | McDowell | MTC 48 Node Cell | POInt | Yes | Yes | NR SW ARZ MCD MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-11-30 | 2020-11-30 | SN-0946 | 2020-09-25 | Chg
35171 | MRTR AAR-New-QNC-NEW-AAR | CE | TUL | QNC | Quincy | Metro Routers | POInt | Yes | Yes | MRTR CE TUL QNC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | SN-0651 | 2020-06-14
78334 | NR PNL MTC 48 Node Cell | SW | ARZ | PNL | Pinal County | MTC 48 Node Cell | POInt | Yes | Yes | NR SW ARZ PNL MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-11-30 | 2020-11-30 | SN-0946 | 2020-09-25 | Chg
78338 | NR MAN MTC 48 Node Cell | NE | CON | MAN | Manchester | MTC 48 Node Cell | POInt | Yes | Yes | NR NE CON MAN MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-10-15 | 2020-11-30 | 2020-11-30 | SN-0946 | 2020-09-25 | New
35176 | MRTR OOB-New-GAR-OOB Server | CE | TUL | GAR | Garnett | Metro Routers | POInt | Yes | Yes | MRTR CE TUL GAR OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-09-05 | 2020-11-30 | 2021-02-28 | SN-0158 | 2020-02-06 | Chg
35177 | MRTR AAR-New-CHS-NEW-AAR | VA | HRD | CHS | Chesapeake | Metro Routers | POInt | Yes | Yes | MRTR VA HRD CHS AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | SN-0651 | 2020-06-14 | New
35176 | MRTR OOB-New-CLA-OOB Server | CE | TUL | CLA | Claremore | Metro Routers | POInt | Yes | Yes | MRTR CE TUL CLA OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-09-05 | 2020-11-30 | 2021-02-28 | SN-0158 | 2020-02-06 | Chg
78334 | NR CHD MTC 48 Node Cell | SW | ARZ | CHD | Chandler | MTC 48 Node Cell | POInt | Yes | Yes | NR SW ARZ CHD MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-11-30 | 2020-11-30 | SN-0946 | 2020-09-25 | Chg
35176 | MRTR SLR-New-CLA-AAR-ASR9906 | CE | TUL | CLA | Claremore | Metro Routers | POInt | Yes | Yes | MRTR CE TUL CLA AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-15 | 2020-11-30 | 2020-12-31 | SN-1037 | 2020-11-06 | Chg
35176 | MRTR OOB-New-MOO-OOB Server | CE | OKC | MOO | Moore | Metro Routers | POInt | Yes | Yes | MRTR CE OKC MOO OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-09-05 | 2020-11-30 | 2021-02-28 | SN-0158 | 2020-02-06 | Chg
78093 | HY CE KAN DCY Voice POI Decom POR20 | CE | KAN | DCY | Dodge City | Voice Decom and Refortification | POInt | Yes | No | VCDR CE KAN DCY Voice POI Decom POR20 | Labor | No Equipment | 1 | 2020-07-06 08:00 | 2020-11-30 |  | PB-0001 | 2019-12-20 | New
44925 | MTCH SW ARZ BEL Fiber Management Augment POR19 | SW | ARZ | BEL | Bell | MTC HE - Hub Signaling | POInt | Yes | No | MTCH SW ARZ BEL Fiber Management Augment POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-11-30 | 2020-11-30 | SN-0938 | 2020-09-25 | Chg
34608 | CB Transport - New Router Village - VBC - Optics | VA | HRD | VBC | Virginia Beach | CB - Metro Core | POInt | Yes | Yes | CBMC VA HRD VBC Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-02-15 | 2020-11-30 |  | SN-0934 | 2020-09-18 | Chg
35169 | MRTR SLR-New-HEN-AAR-ASR9906 | SW | LAS | HEN | Henderson | Metro Routers | POInt | Yes | No | MRTR SW LAS HEN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-15 | 2020-11-30 | 2020-12-31 | SN-0750 | 2020-07-15 | New
35169 | MRTR NCS-Growth-MSA-NCS Line Card | SW | ARZ | MSA | Mesa | Metro Routers | POInt | Yes | No | MRTR SW ARZ MSA NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-09-01 | 2020-11-30 | 2021-02-28 | SN-0158 | 2020-02-06 | Chg
75520 | SPLUNK Licenses | COR | COR | DDR | Duke Drive | Voice Capacity | POInt | Yes | No | VCAP CO -CO DDR Voice Capacity Augment POR20 | License | License procurement | 20 | 2020-05-25 | 2020-11-30 |  | SB-0235 | 2020-10-23 | Chg
35170 | MRTR AAR-New-IRV-NEW-AAR | CA | ORG | IRV | Irvine | Metro Routers | POInt | Yes | No | MRTR CA SAN OCE AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | SN-0651 | 2020-06-14
34644 | BWM_TOP_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | KAN | TOP | Topeka | Bandwidth Management | POInt | Yes | No | BWM CE KAN TOP VIDEO SG Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-01 |  | SN-0195 | 2020-01-24 | Chg
75850 | FI NE CLE CLV Parma Integration POR20 | NE | CLE | CLV | Cleveland | Facilities Integration | POInt | Yes | No | FI NE CLE CLV Parma Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling | 1 | 2020-04-06 | 2020-12-01 |  | SN-0704 | 2020-06-26 | Chg
34638 | BWM_NOE_VIDEO SG_2020 DOCSIS node split-based Video SG I | SE | NOR | NOE | New Orleans East | Bandwidth Management | POInt | Yes | No | BWM SE NOR NOE Video SG Augment POR20 v3 | Labor | No Equipment | 1 |  | 2020-12-01 | 2020-12-01 | SN-0195 | 2020-01-24 | Chg
34761 | BWM_PNL_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | PNL | Pinal County | Bandwidth Management | POInt | Yes | No | BWM SW ARZ PNL DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | SN-0143 | 2020-02-06 | Chg
34761 | BWM_VSA_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | VSA | Vistancia | Bandwidth Management | POInt | Yes | No | BWM SW ARZ VSA DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | SN-0143 | 2020-02-06 | Chg
34761 | BWM_CSG_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | CSG | Casa Grande | Bandwidth Management | POInt | Yes | No | BWM SW ARZ CSG DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | SN-0143 | 2020-02-06 | Chg
34761 | BWM_BEL_DGS_Spectrum Phase III 192 MHZv2 | SW | ARZ | BEL | Bell | Bandwidth Management | POInt | Yes | No | BWM SW ARZ BEL DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | SN-0143 | 2020-02-06 | Chg
34761 | BWM_SVA_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | SVA | Sierra Vista | Bandwidth Management | POInt | Yes | No | BWM SW ARZ SVA DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | SN-0143 | 2020-02-06 | Chg
34761 | BWM_WKB_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | WCG | Wickenburg | Bandwidth Management | POInt | Yes | No | BWM SW ARZ WCG DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | SN-0473 | 2020-04-17 | Chg
34761 | BWM_MSA_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | MSA | Mesa | Bandwidth Management | POInt | Yes | No | BWM SW ARZ MSA DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | SN-0143 | 2020-02-06 | Chg
34761 | BWM_BEN_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | BEN | Benson with (Insite tower) | Bandwidth Management | POInt | Yes | No | BWM SW ARZ BEN DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | SN-0143 | 2020-02-06 | Chg
34761 | BWM_BUK_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | BUK | Buckeye | Bandwidth Management | POInt | Yes | No | BWM SW ARZ BUK DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | SN-0143 | 2020-02-06 | Chg
34761 | BWM_PEO_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | PEO | Peoria | Bandwidth Management | POInt | Yes | No | BWM SW ARZ PEO DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | SN-0143 | 2020-02-06 | Chg
34761 | BWM_SSC_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | SSC | South Scottsdale | Bandwidth Management | POInt | Yes | No | BWM SW ARZ SSC DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | SN-0143 | 2020-02-06 | Chg
34761 | BWM_GVA_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | GVA | Green Valley | Bandwidth Management | POInt | Yes | No | BWM SW ARZ GVA DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | SN-0143 | 2020-02-06 | Chg
34761 | BWM_CHD_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | CHD | Chandler | Bandwidth Management | POInt | Yes | No | BWM SW ARZ CHD DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | SN-0143 | 2020-02-06 | Chg
34761 | BWM_MCD_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | MCD | McDowell | Bandwidth Management | POInt | Yes | No | BWM SW ARZ MCD DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | SN-0143 | 2020-02-06 | Chg
34761 | BWM_NSC_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | NSC | North Scottsdale | Bandwidth Management | POInt | Yes | No | BWM SW ARZ NSC DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | SN-0143 | 2020-02-06 | Chg
34761 | BWM_TUC_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | TUC | Tucson | Bandwidth Management | POInt | Yes | No | BWM SW ARZ TUC DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | SN-0143 | 2020-02-06 | Chg
34761 | BWM_FWL_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | FWL | Fowler | Bandwidth Management | POInt | Yes | No | BWM SW ARZ FWL DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | SN-0143 | 2020-02-06 | Chg
34761 | BWM_DGL_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | DGL | Douglas | Bandwidth Management | POInt | Yes | No | BWM SW ARZ DGL DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | SN-0143 | 2020-02-06 | Chg
34635 | BWM NVA DOCSIS Expansion 192 MHz | VA | NVA | DRA | Dranesville | Bandwidth Management | POInt | Yes | No | BWM VA NVA DRA DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-10 | 2021-10-03 | SN-0558 | 2020-05-12 | New
34635 | BWM NVA DOCSIS Expansion 96 MHz | VA | NVA | DRA | Dranesville | Bandwidth Management | POInt | Yes | No | BWM VA NVA DRA DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-10 | 2020-10-03 | SN-0558 | 2020-05-12 | New
44927 | MTCH VA NVA FST Inca 8VSB Deployment POR19 | VA | NVA | FST | Fairfax Station | MTC HE - Hub Signaling | POInt | Yes | No | MTCH VA NVA FST Inca 8VSB Deployment POR19 | Critical Facilities | MTC Hub Signaling | 1 | 2020-10-07 | 2020-12-11 | 2020-12-11 | SN-0970 | 2020-10-02 | Chg
78093 | VCDR CE NWA FTS Voice Gateway Decom POR20 | CE | NWA | FTS | Fort Smith | Voice Decom and Refortification | POInt | Yes | Yes | VCDR CE NWA FTS Voice Gateway Decom POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-11 |  | SN-0697 | 2020-07-10 | Chg
75788 | CDN Deploy 19 | SW | ARZ | PEO | Peoria | CDN | POInt | Yes | No | CDN SW ARZ PEO Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-07-01 | 2020-12-14 | 2020-12-30 | SN-0803 | 2020-08-07 | Chg
34636 | BWM_CRV_VIDEO SG_2020 DOCSIS node split-based Video SG | SE | GCT | CRV | Crestview | Bandwidth Management | POInt | Yes | No | BWM SE GCT CRV Video SG Augment POR20 v2 | Labor | No Equipment | 1 | 2020-10-01 | 2020-12-15 | 2020-12-15
34642 | BWM_TUL_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | TUL | TUL | Tulsa | Bandwidth Management | POInt | Yes | No | BWM CE TUL TUL VIDEO SG Augment POR20 v4 | Labor | No Equipment | 1 | 2020-10-01 | 2020-12-15 | 2020-12-15
34644 | BWM_GDY_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | KAN | GDY | Garden City | Bandwidth Management | POInt | Yes | No | BWM CE KAN GDY Video SG Augment POR20 v3 | Labor | No Equipment | 1 | 2020-10-01 | 2020-12-15 | 2020-12-15
75686 | WIFI Standardization | COR | COR | ATL | Atlanta | Wifi | POInt | Yes | No | WFI COR COR ATL WIFI STANDARDIZATION ALIGNMENT POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-12-15
34642 | BWM_SOU_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | OMA | SOU | South (OM) | Bandwidth Management | POInt | Yes | No | BWM CE OMA SOU VIDEO SG Augment POR20 v5 | Labor | No Equipment | 1 | 2020-10-01 | 2020-12-15 | 2020-12-15
75645 | CGN Replacement 20 | NE | CLE | CLV | Cleveland | Data Center Capacity | POInt | Yes | No | DTC NE CLE CLV CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-08-30 | 2020-12-15 |  | SN-0963 | 2020-10-02 | Chg
34644 | BWM_HUT_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | KAN | HUT | Hutchinson | Bandwidth Management | POInt | Yes | No | BWM CE KAN HUT Video SG Augment POR20 v3 | Labor | No Equipment | 1 | 2020-10-01 | 2020-12-15 | 2020-12-15
75693 | Wifi Lifecycle | COR | COR | ATL | Atlanta | Wifi | POInt | Yes | No | WFI COR COR ATL WIFI LIFECYCLE ALIGNMENT POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-12-15
75645 | CGN Replacement 9 | SE | NOR | ELM | Elmwood | Data Center Capacity | POInt | Yes | No | DTC SE NOR ELM CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-01-25 | 2020-12-15 |  | SN-0902 | 2020-09-18 | Chg
75688 | WiFi Trial | COR | COR | ATL | Atlanta | Wifi | POInt | Yes | No | WFI COR COR ATL WIFI TRIAL ALIGNMENT POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-12-15
75651 | PTX Add 6 | CE | TUL | TUL | Tulsa | Backbone | POInt | Yes | No | BBCAP CE TUL TUL PTX10 Deployment POR20 | Chassis | 1x Juniper PTX10K Chassis | 2 | 2020-09-05 | 2020-12-15 |  | SN-1034 | 2020-10-30 | Chg
75651 | MX2010 | NE | CLE | CLV | Cleveland | Backbone | POInt | Yes | No | BBCAP NE CLE CLV MX2010 Deployment POR20 | Chassis | 1x Juniper MX2010 Chassis | 2 | 2020-07-01 | 2020-12-15 |  | SN-0964 | 2020-10-02 | Chg
75788 | CDN Deploy 26 | NE | CLE | CLV | Cleveland | CDN | POInt | Yes | No | CDN NE CLE CLV Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-10-01 | 2020-12-15 | 2020-12-31 | SN-0966 | 2020-10-02 | Chg
75645 | CGN Replacement 11 | NE | RHD | PRV | Providence | Data Center Capacity | POInt | Yes | No | DTC NE RHD PRV CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-02-08 | 2020-12-15 |  | SN-0902 | 2020-09-18 | Chg
78457 | FI CA SAB SAB Santa Barbara Integration POR20 | CA | SAB | SAB | Santa Barbara | Facilities Integration | POInt | Yes | No | FI CA SAB SAB Santa Barbara Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling | 1 | 2020-07-06 | 2020-12-15 |  | SN-0440 | 2020-04-10 | Chg
39256 | BWM_MER_VIDEO SG_2020 DOCSIS node split-based Video SG | NE | CON | MER | Meriden | Bandwidth Management | POInt | Yes | No | BWM NE CON MER VIDEO SG Augment POR20 v2 | Labor | No Equipment | 1 | 2020-10-01 | 2020-12-15 | 2020-12-15
44926 | MTCH NE CLE CLV Replace Tektronix Upgrade Decom POR19 | NE | CLE | CLV | Cleveland | MTC HE - Hub Signaling | POInt | Yes | No | MTCH NE CLE CLV Replace Tektronix Upgrade Decom POR19 | Chassis | Tektronix Sentry | 1 | 2020-11-15 | 2020-12-15 | 2021-01-15 | SN-0575 | 2020-05-14 | Chg
75830 | Metaswitch 4.6 Upgrade CB | COR | COR | ATL | Atlanta | Voice Network Upgrades | POInt | Yes | No | VNU CO -CO ATL Metaswitch Lifecycle Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-08-15 | 2020-12-15 | 2020-12-15 | SB-0047 | 2020-01-31 | New
39256 | BWM_RKH_VIDEO SG_2020 DOCSIS node split-based Video SG | NE | CON | RKH | Rocky Hill | Bandwidth Management | POInt | Yes | No | BWM NE CON RKH VIDEO SG Augment POR20 v3 | Labor | No Equipment | 1 | 2020-10-01 | 2020-12-15 | 2020-12-15
34642 | BWM_BRD_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | TUL | BRD | Braden | Bandwidth Management | POInt | Yes | No | BWM CE TUL BRD Video SG Augment POR20 v3 | Labor | No Equipment | 1 | 2020-10-01 | 2020-12-15 | 2020-12-15
35177 | MRTR OOB-New-FBG-OOB Server | VA | NVA | FBG | Fredericksburg | Metro Routers | POInt | Yes | Yes | MRTR VA NVA FBG OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-10-01 | 2020-12-15 | 2020-12-15
39256 | BWM_ENF_VIDEO SG_2020 DOCSIS node split-based Video SG | NE | CON | ENF | Enfield | Bandwidth Management | POInt | Yes | No | BWM NE CON ENF VIDEO SG Augment POR20 v3 | Labor | No Equipment | 1 | 2020-10-01 | 2020-12-15 | 2020-12-15
39256 | BWM_CRN_VIDEO SG_2020 DOCSIS node split-based Video SG | NE | RHD | CRN | Cranston | Bandwidth Management | POInt | Yes | No | BWM NE RHD CRN VIDEO SG Augment POR20 v3 | Labor | No Equipment | 1 | 2020-10-01 | 2020-12-15 | 2020-12-15
75647 | Nokia 1830 Add 12 | NE | CLE | CLV | Cleveland | C4 & C4B Transport Network | POInt | Yes | No | C4B NE CLE CLV Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis | 8 | 2020-07-01 | 2020-12-15 |  | SN-0965 | 2020-10-02 | Chg
39256 | BWM_PAW_VIDEO SG_2020 DOCSIS node split-based Video SG | NE | RHD | PAW | Pawtucket | Bandwidth Management | POInt | Yes | No | BWM NE RHD PAW VIDEO SG Augment POR20 v3 | Labor | No Equipment | 1 | 2020-10-01 | 2020-12-15 | 2020-12-15
75665 | UC App SW Upgrade 1 | COR | COR | ATL | Atlanta | Voice Network Upgrades | POInt | Yes | No | VNU CO -CO ATL UC App Upgrade Deployment POR20 | Labor | Certify and deploy updated UC App SW. | 4 | 2020-09-08 | 2020-12-15 |  | SB-0013 | 2020-01-30 | Chg
75658 | VA-CLV-1x Juniper EX4600 | NE | CLE | CLV | Cleveland | Visibility Architecture | POInt | Yes | No | VIA NE CLE CLV Visibility Architecture Gear Deployment POR20 | Chassis | 1x Juniper EX4600 Chassis | 1 | 2020-06-01 | 2020-12-15 | 2020-12-31 | SN-0967 | 2020-10-02 | Chg
75658 | VA-CLV-1x Niagra PT-3225 | NE | CLE | CLV | Cleveland | Visibility Architecture | POInt | Yes | No | VIA NE CLE CLV Visibility Architecture Gear Deployment POR20 | Chassis | 1x Niagra PT-3225 Chassis | 4 | 2020-06-30 | 2020-12-15 | 2020-12-31 | SN-0967 | 2020-10-02 | Chg
75658 | VA-CLV-1x Arista DCS-7280CR2A-60-F | NE | CLE | CLV | Cleveland | Visibility Architecture | POInt | Yes | No | VIA NE CLE CLV Visibility Architecture Gear Deployment POR20 | Chassis | 1x Arista DCS-7280CR2-60 Chassis | 1 | 2020-07-31 | 2020-12-15 | 2020-12-31 | SN-0967 | 2020-10-02 | Chg
75658 | VA-CLV-1x Dell R640 | NE | CLE | CLV | Cleveland | Visibility Architecture | POInt | Yes | No | VIA NE CLE CLV Visibility Architecture Gear Deployment POR20 | Chassis | 1x Dell R640 Chassis | 3 | 2020-06-30 | 2020-12-15 | 2020-12-31 | SN-0967 | 2020-10-02 | Chg
34619 | OMHSBSRA01-ROUTER | CE | OMA | SOU | South (OM) | CB - Metro Core | POInt | Yes | Yes | CBMC CE OMA SOU ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-10-15 | 2020-12-15 |  | SN-0144 | 2020-02-06 | Chg
44876 | MTCH CE OKC OKC MPEG4 vDCM Install Deployment POR20 | CE | OKC | OKC | OKC MTC | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH CE OKC OKC MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-05-06 | 2020-12-15 | 2021-03-15 | SN-0227 | 2020-03-30 | Chg
35173 | MRTR OOB-New-VLY-OOB Server | SW | LAS | VLY | Valley | Metro Routers | POInt | Yes | Yes | MRTR SW LAS VLY OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-10-01 | 2020-12-15 | 2020-12-15
39251 | BWM_FED_DGS_Spectrum Phase III 96 MHZ | CA | SAN | FED | Federal | Bandwidth Management | POInt | Yes | No | BWM CA SAN FED DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | SN-0330 | 2020-03-27
34761 | BWM_ALI_DGS_Spectrum Phase III 96 MHZ | SW | LAS | ALI | Aliante | Bandwidth Management | POInt | Yes | No | BWM SW LAS ALI DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | SN-0330 | 2020-03-27
34761 | BWM_CEN_DGS_Spectrum Phase III 96 MHZ | SW | LAS | CEN | Central | Bandwidth Management | POInt | Yes | No | BWM SW LAS CEN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | SN-0330 | 2020-03-27
34761 | BWM_VLY_DGS_Spectrum Phase III 96 MHZ | SW | LAS | VLY | Valley | Bandwidth Management | POInt | Yes | No | BWM SW LAS VLY DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | SN-0330 | 2020-03-27
34761 | BWM_BLU_DGS_Spectrum Phase III 96 MHZ | SW | LAS | BLU | Blue Diamond | Bandwidth Management | POInt | Yes | No | BWM SW LAS BLU DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | SN-0330 | 2020-03-27
39251 | BWM_CHU_DGS_Spectrum Phase II 96 MHZv2 | CA | SAN | CHU | Chula Vista | Bandwidth Management | POInt | Yes | No | BWM CA SAN CHU DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | SN-0330 | 2020-03-27
39251 | BWM_ELC_DGS_Spectrum Phase III 96 MHZ | CA | SAN | ELC | El Cajon | Bandwidth Management | POInt | Yes | No | BWM CA SAN ELC DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | SN-0330 | 2020-03-27
34761 | BWM_TEN_DGS_Spectrum Phase III 96 MHZ | SW | LAS | TEN | Tenaya | Bandwidth Management | POInt | Yes | No | BWM SW LAS TEN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | SN-0330 | 2020-03-27
39251 | BWM_DWN_DGS_Spectrum Phase II 96 MHZ | CA | SAN | DWN | Downtown | Bandwidth Management | POInt | Yes | No | BWM CA SAN DWN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | SN-0330 | 2020-03-27
39251 | BWM_OCE_DGS_Spectrum Phase II 96 MHZv2 | CA | SAN | OCE | Oceanside | Bandwidth Management | POInt | Yes | No | BWM CA SAN OCE DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | SN-0330 | 2020-03-27
39251 | BWM_ESC_DGS_Spectrum Phase II 96 MHZ | CA | SAN | ESC | Escondido | Bandwidth Management | POInt | Yes | No | BWM CA SAN ESC DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | SN-0330 | 2020-03-27
39251 | BWM_ALP_DGS_Spectrum Phase III_96 MHZv2 | CA | SAN | ALP | Alpine | Bandwidth Management | POInt | Yes | No | BWM CA SAN ALP DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | SN-0330 | 2020-03-27
34761 | BWM_ERN_DGS_Spectrum Phase III 96 MHZ | SW | LAS | ERN | Ernest May | Bandwidth Management | POInt | Yes | No | BWM SW LAS ERN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | SN-0330 | 2020-03-27
39251 | BWM_PWY_DGS_Spectrum Phase III 96 MHZ | CA | SAN | PWY | Poway | Bandwidth Management | POInt | Yes | No | BWM CA SAN PWY DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | SN-0330 | 2020-03-27
34761 | BWM_VST_DGS_Spectrum Phase II 96 MHZv2 | CA | SAN | VST | Vista | Bandwidth Management | POInt | Yes | No | BWM CA SAN VST DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | SN-0330 | 2020-03-27
34761 | BWM_HEN_DGS_Spectrum Phase III 96 MHZ | SW | LAS | HEN | Henderson | Bandwidth Management | POInt | Yes | No | BWM SW LAS HEN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | SN-0330 | 2020-03-27
75187 | R PHY_CCAP_YAL_CBR8-1 | CE | TUL | YAL | Yale | R PHY | POInt | Yes | Yes | R PHY CE TUL YAL RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2019-11-15 | 2020-12-20 | 2020-12-20 | SN-0637 | 2020-06-05 | Chg
75187 | R PHY_CCAP_YAL_Boundary_Clocks-1 | CE | TUL | YAL | Yale | R PHY | POInt | Yes | Yes | R PHY CE TUL YAL RPHY CCAP Initial Deployment POR19 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2019-11-15 | 2020-12-20 | 2020-12-20 | SN-0637 | 2020-06-05 | Chg
34945 | Photonic-OTN-BER-M15 | CE | NWA | BER | Berryville | Metro Transport | POInt | Yes | Yes | MTRN CE NWA BER DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34945 | Photonic-OTN-BER-M6 | CE | NWA | BER | Berryville | Metro Transport | POInt | Yes | Yes | MTRN CE NWA BER DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34947 | Photonic-OTN-LV1-ERN-M15 | SW | LAS | ERN | Ernest May | Metro Transport | POInt | Yes | Yes | MTRN SW LAS ERN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34947 | MTRN-T5-ERN-01 | SW | LAS | ERN | Ernest May | Metro Transport | POInt | Yes | Yes | MTRN SW LAS ERN DWDM-OLS Deployment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34947 | Photonic-OTN-LV1-ERN-M6 | SW | LAS | ERN | Ernest May | Metro Transport | POInt | Yes | Yes | MTRN SW LAS ERN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 3 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34947 | Photonic-OTN-LV1-BLU-M15 | SW | LAS | BLU | Blue Diamond | Metro Transport | POInt | Yes | Yes | MTRN SW LAS BLU DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34947 | Photonic-OTN-LV1-BLU-M6 | SW | LAS | BLU | Blue Diamond | Metro Transport | POInt | Yes | Yes | MTRN SW LAS BLU DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34945 | Photonic-OTN-III-M15 | CE | NWA | FAY | Fayetteville | Metro Transport | POInt | Yes | Yes | MTRN CE NWA FAY Evansville DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 1 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34945 | Photonic-OTN-III-M6 | CE | NWA | FAY | Fayetteville | Metro Transport | POInt | Yes | Yes | MTRN CE NWA FAY Evansville DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34944 | Photonic-OTN-ELC-M15 | CA | SAN | ELC | El Cajon | Metro Transport | POInt | Yes | Yes | MTRN CA SAN ELC DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 5 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34944 | Photonic-OTN-ELC-M6 | CA | SAN | ELC | El Cajon | Metro Transport | POInt | Yes | Yes | MTRN CA SAN ELC DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 6 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
75838 | MVFM SW LAS OSB OCML DLX40 Augment POR20 | SW | LAS | OSB | Oso Blanca | MTC Fiber and Rack Management | POInt | Yes | Yes | MVFM SW LAS OSB OCML DLX40 Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-09-22 | 2020-12-30 | 2020-12-30 | SN-0968 | 2020-10-02 | Chg
34944 | Photonic-OTN-EEE-M15 | CA | SAN | VST | Vista | Metro Transport | POInt | Yes | Yes | MTRN CA SAN VST AIS OTN_OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34944 | Photonic-OTN-EEE-M6 | CA | SAN | VST | Vista | Metro Transport | POInt | Yes | Yes | MTRN CA SAN VST AIS OTN_OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34944 | Photonic-OTN-PWY-M15 | CA | SAN | PWY | Poway | Metro Transport | POInt | Yes | Yes | MTRN CA SAN PWY DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34944 | Photonic-OTN-PWY-M6 | CA | SAN | PWY | Poway | Metro Transport | POInt | Yes | Yes | MTRN CA SAN PWY DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34944 | MTRN-PWY-T5 | CA | SAN | PWY | Poway | Metro Transport | POInt | Yes | Yes | MTRN CA SAN PWY DWDM-OLS Deployment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34947 | Photonic-OTN-LV1-TEN-M15 | SW | LAS | TEN | Tenaya | Metro Transport | POInt | Yes | Yes | MTRN SW LAS TEN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 4 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34947 | Photonic-OTN-LV1-TEN-M6 | SW | LAS | TEN | Tenaya | Metro Transport | POInt | Yes | Yes | MTRN SW LAS TEN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 3 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34945 | Photonic-OTN-VBN-M15 | CE | NWA | VBN | Van Buren | Metro Transport | POInt | Yes | Yes | MTRN CE NWA VBN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34945 | Photonic-OTN-VBN-M6 | CE | NWA | VBN | Van Buren | Metro Transport | POInt | Yes | Yes | MTRN CE NWA VBN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34947 | Photonic-OTN-LV1-HEN-M15 | SW | LAS | HEN | Henderson | Metro Transport | POInt | Yes | Yes | MTRN SW LAS HEN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 4 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34947 | Photonic-OTN-LV1-HEN-M6 | SW | LAS | HEN | Henderson | Metro Transport | POInt | Yes | Yes | MTRN SW LAS HEN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 4 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34947 | Photonic-OTN-LV1-VLY-M15 | SW | LAS | VLY | Valley | Metro Transport | POInt | Yes | Yes | MTRN SW LAS VLY DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34947 | Photonic-OTN-LV1-VLY-M6 | SW | LAS | VLY | Valley | Metro Transport | POInt | Yes | Yes | MTRN SW LAS VLY DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34944 | Photonic-OTN-CHU-M15 | CA | SAN | CHU | Chula Vista | Metro Transport | POInt | Yes | Yes | MTRN CA SAN CHU DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34944 | Photonic-OTN-CHU-M6 | CA | SAN | CHU | Chula Vista | Metro Transport | POInt | Yes | Yes | MTRN CA SAN CHU DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34945 | Photonic-OTN-FTS-M15 | CE | NWA | FTS | Fort Smith | Metro Transport | POInt | Yes | Yes | MTRN CE NWA FTS DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34945 | Photonic-OTN-FTS-M6 | CE | NWA | FTS | Fort Smith | Metro Transport | POInt | Yes | Yes | MTRN CE NWA FTS DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34945 | Photonic-OTN-JJJ-M15 | CE | NWA | FAY | Fayetteville | Metro Transport | POInt | Yes | Yes | MTRN CE NWA FAY Kingston DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34945 | Photonic-OTN-JJJ-M6 | CE | NWA | FAY | Fayetteville | Metro Transport | POInt | Yes | Yes | MTRN CE NWA FAY Kingston DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 1 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34945 | Photonic-OTN-SSP-M15 | CE | NWA | SSP | Siloam Springs | Metro Transport | POInt | Yes | Yes | MTRN CE NWA SSP DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34945 | Photonic-OTN-SSP-M6 | CE | NWA | SSP | Siloam Springs | Metro Transport | POInt | Yes | Yes | MTRN CE NWA SSP DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34945 | Photonic-OTN-BVL-M15 | CE | NWA | BVL | Bentonville | Metro Transport | POInt | Yes | Yes | MTRN CE NWA BVL DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34945 | Photonic-OTN-BVL-M6 | CE | NWA | BVL | Bentonville | Metro Transport | POInt | Yes | Yes | MTRN CE NWA BVL DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 3 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34944 | Photonic-OTN-FED-M15 | CA | SAN | FED | Federal | Metro Transport | POInt | Yes | Yes | MTRN CA SAN FED DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 4 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34944 | Photonic-OTN-FED-M6 | CA | SAN | FED | Federal | Metro Transport | POInt | Yes | Yes | MTRN CA SAN FED DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 4 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34945 | Photonic-OTN-NWA-M15 | CE | NWA | NWA | Johnson | Metro Transport | POInt | Yes | Yes | MTRN CE NWA NWA DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 3 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34945 | Photonic-OTN-NWA-M6 | CE | NWA | NWA | Johnson | Metro Transport | POInt | Yes | Yes | MTRN CE NWA NWA DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 4 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34945 | Photonic-OTN-FAY-M15 | CE | NWA | FAY | Fayetteville | Metro Transport | POInt | Yes | Yes | MTRN CE NWA FAY DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34945 | Photonic-OTN-FAY-M6 | CE | NWA | FAY | Fayetteville | Metro Transport | POInt | Yes | Yes | MTRN CE NWA FAY DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 3 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34945 | Photonic-OTN-HRN-M15 | CE | NWA | HRN | Harrison | Metro Transport | POInt | Yes | Yes | MTRN CE NWA HRN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34945 | Photonic-OTN-HRN-M6 | CE | NWA | HRN | Harrison | Metro Transport | POInt | Yes | Yes | MTRN CE NWA HRN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34947 | Photonic-OTN-LV2-ALI-M15 | SW | LAS | ALI | Aliante | Metro Transport | POInt | Yes | Yes | MTRN SW LAS ALI DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34947 | Photonic-OTN-LV2-ALI-M6 | SW | LAS | ALI | Aliante | Metro Transport | POInt | Yes | Yes | MTRN SW LAS ALI DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34947 | MTRN-ALI- T5-03 | SW | LAS | ALI | Aliante | Metro Transport | POInt | Yes | Yes | MTRN SW LAS ALI DWDM-OLS Deployment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34944 | Photonic-OTN-VST-M15 | CA | SAN | VST | Vista | Metro Transport | POInt | Yes | Yes | MTRN CA SAN VST DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34944 | Photonic-OTN-VST-M6 | CA | SAN | VST | Vista | Metro Transport | POInt | Yes | Yes | MTRN CA SAN VST DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
75788 | CDN Deploy 24 | CA | SAN | CHU | Chula Vista | CDN | POInt | Yes | No | CDN CA SAN CHU Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-10-01 | 2020-12-30 | 2021-01-13 | SN-0285 | 2020-02-24 | New
34944 | Photonic-OTN-OCE-M15 | CA | SAN | OCE | Oceanside | Metro Transport | POInt | Yes | Yes | MTRN CA SAN OCE DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34944 | Photonic-OTN-OCE-M6 | CA | SAN | OCE | Oceanside | Metro Transport | POInt | Yes | Yes | MTRN CA SAN OCE DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34944 | Photonic-OTN-DWN-M15 | CA | SAN | DWN | Downtown | Metro Transport | POInt | Yes | Yes | MTRN CA SAN DWN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34944 | Photonic-OTN-DWN-M6 | CA | SAN | DWN | Downtown | Metro Transport | POInt | Yes | Yes | MTRN CA SAN DWN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34944 | Photonic-OTN-ESC-M15 | CA | SAN | ESC | Escondido | Metro Transport | POInt | Yes | Yes | MTRN CA SAN ESC DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34944 | Photonic-OTN-ESC-M6 | CA | SAN | ESC | Escondido | Metro Transport | POInt | Yes | Yes | MTRN CA SAN ESC DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34944 | Photonic-OTN-FFF-M15 | CA | SAN | FED | Federal | Metro Transport | POInt | Yes | Yes | MTRN CA SAN FED EdgeConnex OTN_OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 1 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
34944 | Photonic-OTN-FFF-M6 | CA | SAN | FED | Federal | Metro Transport | POInt | Yes | Yes | MTRN CA SAN FED EdgeConnex OTN_OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | SN-0953 | 2020-09-25 | Chg
35715 | MRTR AAR-New-WWK-NEW-AAR | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | Metro Routers | POInt | Yes | Yes | MRTR NE RHD WWK AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | SN-0158 | 2020-02-06 | Chg
59744 | RPHY MRTR-New-BEL-CIN Nokia-OCML | SW | ARZ | BEL | Bell | R PHY | POInt | Yes | Yes | R PHY SW ARZ BEL RPHY Metro Augment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 36 | 2020-01-01 | 2020-12-31 | 2020-12-31 | SN-0640 | 2020-06-06 | Chg
59744 | RPHY MRTR-New-BEL-CIN Nokia-OCML2 | SW | ARZ | BEL | Bell | R PHY | POInt | Yes | Yes | R PHY SW ARZ BEL RPHY Metro Augment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 20 | 2020-05-15 | 2020-12-31 | 2020-12-31 | SN-0640 | 2020-06-06 | Chg
35011 | MTRN-NWP- T5-01 | VA | HRD | NWP | Newport News | Metro Transport | POInt | Yes | Yes | MTRN VA HRD NWP T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-12-31 | 2020-12-31 | SN-0639 | 2020-06-05 | Chg
59745 | R PHY_CCAP_PWY_CBR8_1 | CA | SAN | PWY | Poway | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN PWY RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-10-15 | 2020-12-31 | 2020-12-31 | SN-0550 | 2020-05-12 | New
78097 | HY SE GCT PNS Voice BTS Gateway Decom POR19 | SE | GCT | PNS | Pensacola with (Insite tower) | Voice Decom and Refortification | POInt | Yes | Yes | VCDR SE GCT PNS Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 | 2020-07-06 | 2020-12-31 |  | SN-0697 | 2020-07-10 | Chg
35176 | MRTR OOB-New-DTN-OOB Server | CE | TUL | DTN | Downtown (TUL) | Metro Routers | POInt | Yes | Yes | MRTR CE TUL DTN OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-10-01 03:01 | 2020-12-31 | 2021-03-31 | SN-0158 | 2020-02-06 | Chg
75804 | Delivery Expansion - Delivery Service Expansion | COR | COR | ATL | Atlanta | Voice Network Upgrades | POInt | Yes | No | VNU CO -CO ATL ODI and SD WAN Infra Env Alignment POR20 | Labor | Build additional Dev environments. | 1 | 2020-07-10 | 2020-12-31 |  | SB-0162 | 2020-06-30 | Chg
75663 | V2B CA SAN ELC Platform Refresh Augment POR20 | CA | SAN | ELC | El Cajon | V2B | POInt | Yes | No | V2B CA SAN ELC Platform Refresh Augment POR20 | Card & Optics | Replace UCS blades | 24 | 2020-11-15 | 2020-12-31 | 2020-12-31 | SN-1015 | 2020-10-16 | Chg
59745 | R PHY_CCAP_PAV_CBR8_1 | CA | ORG | PAV | Palos Verdes | RSPD - CCAP | POInt | Yes | No | R PHY CA ORG PAV RPHY CCAP Augment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-10-15 | 2020-12-31 | 2020-12-31 | SN-0550 | 2020-05-12 | New
75846 | SE GAN GNS Meet Me Rack Augment POR20 | SE | GAN | GNS | Gainesville | MTC Fiber and Rack Management | POInt | Yes | No | MVFM SE GAN GNS Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-12-04 | 2020-12-31 | 2020-12-31 | SN-1087 | 2020-11-20 | Chg
78408 | HN Hosts | COR | COR | DDR | Duke Drive | Hospitality Network | POInt | Yes | No | HN COR COR DDR HN Hosts Augment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-12-31 |  | SB-0252 | 2020-11-19 | Chg
77906 | Voice Decom Back Office | COR | COR | ATL | Atlanta | Voice Decom and Refortification | POInt | Yes | No | VCDR COR COR ATL Backoffice Systems Decom POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-12-31 |  | SN-0610 | 2020-05-29 | New
34608 | CB Transport - New Router Princess Anne - VBC - Optics | VA | HRD | VBC | Virginia Beach | CB - Metro Core | POInt | Yes | Yes | CBMC VA HRD VBC Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-09-15 | 2020-12-31 |  | SN-1049 | 2020-11-13 | Chg
34608 | CB Transport - New Router Portsmouth - VBC - Optics | VA | HRD | VBC | Virginia Beach | CB - Metro Core | POInt | Yes | Yes | CBMC VA HRD VBC Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-06-15 | 2020-12-31 |  | SN-1049 | 2020-11-13 | Chg
78101 | HY VA HRD LTF Voice HDT Decom POR19 | VA | HRD | LTF | Lightfoot | Voice Decom and Refortification | POInt | Yes | Yes | VCDR VA HRD LTF Voice HDT Decom POR19 | Labor | No Equipment | 1 | 2020-04-10 | 2020-12-31 |  | SN-0697 | 2020-07-10 | Chg
75751 | Static IP PBX Migrations to Metaswitch | COR | COR | ATL | Atlanta | Voice Obsolescence | POInt | Yes | No | VOBS CO -CO ATL SBC Metaswitch Migration Deployment POR20 | Labor | Continue ACME SBC to Metaswitch migration | 30 | 2020-01-10 | 2020-12-31 |  | SB-0164 | 2020-06-30 | Chg
75663 | V2B COR COR DDR Platform Refresh Augment POR20 | COR | COR | DDR | Duke Drive | V2B | POInt | Yes | No | V2B COR COR DDR Platform Refresh Augment POR20 | Card & Optics | Replace UCS blades | 24 | 2020-11-15 | 2020-12-31 | 2020-12-31 | SN-1015 | 2020-10-16 | Chg
75246 | R PHY_CCAP_CLV_Boundary_Clocks_44119 | NE | CLE | CLV | Cleveland | R PHY | POInt | Yes | No | R PHY NE CLE CLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-07-15 | 2020-12-31 |  | SN-0843 | 2020-08-15 | Chg
75246 | R PHY_CCAP_CLV_Grand_Master_Clocks_44119 | NE | CLE | CLV | Cleveland | R PHY | POInt | Yes | No | R PHY NE CLE CLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2020-07-15 | 2020-12-31 |  | SN-0843 | 2020-08-15 | Chg
75246 | R PHY_CCAP_CLV_CBR8_3 | NE | CLE | CLV | Cleveland | R PHY | POInt | Yes | No | R PHY NE CLE CLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 4 | 2020-10-09 | 2020-12-31 |  | SN-0959 | 2020-09-25 | Chg
75246 | R PHY_CCAP_CLV_OTDR_1 | NE | CLE | CLV | Cleveland | R PHY | POInt | Yes | No | R PHY NE CLE CLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-07-20 | 2020-12-31 |  | SN-0843 | 2020-08-15 | Chg
77906 | Voice Decom Ericson | COR | COR | ATL | Atlanta | Voice Decom and Refortification | POInt | Yes | No | VCDR COR COR ATL Ericsson SOW Backoffice Systems Decom POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-12-31 |  | SN-0610 | 2020-05-29 | New
75643 | Sonus LD Migration | COR | COR | ATL | Atlanta | Voice Obsolescence | POInt | Yes | No | VOBS CO -CO ATL Sonus routing Deployment POR20 | Labor | Migrate Long Distance routing off of Sonus SBC | 1 | 2020-01-10 | 2020-12-31 | 2020-09-15 | SB-0164 | 2020-06-30 | Chg
75187 | R PHY_CCAP_TUL_CBR8_2 | CE | TUL | TUL | Tulsa | R PHY | POInt | Yes | No | R PHY CE TUL TUL R PHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-09-22 | 2020-12-31 |  | SN-0899 | 2020-09-11 | Chg
59745 | R PHY_CCAP_ORG_CBR8_1 | CA | ORG | ORG | Orange | RSPD - CCAP | POInt | Yes | No | R PHY CA ORG ORG RPHY CCAP Augment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-10-15 | 2020-12-31 | 2020-12-31 | SN-0550 | 2020-05-12 | New
78408 | Granite Automation | COR | COR | ATL | Atlanta | Hospitality Network | POInt | Yes | No | HN COR COR ATL HN Granite Automation Deployment POR20 | Labor | No Equipment | 1 | 2020-06-01 | 2020-12-31 |  | SB-0252 | 2020-11-19 | Chg
59522 | R PHY_CCAP_ERN_CBR8_1 | SW | LAS | ERN | Ernest May | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS ERN RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 2 | 2020-10-15 | 2020-12-31 | 2020-12-31 | SN-0550 | 2020-05-12 | New
34608 | CB Transport - New Router Newport News - NRF - Card Add | VA | HRD | NRF | Norfolk | CB - Metro Core | POInt | Yes | Yes | CBMC VA HRD NRF Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-02-15 | 2020-12-31 |  | SN-1049 | 2020-11-13 | Chg
35176 | MRTR OOB-New-SRH-OOB Server | CE | OKC | SRH | Sara Road | Metro Routers | POInt | Yes | Yes | MRTR CE OKC SRH OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-10-05 | 2020-12-31 | 2021-03-31 | SN-0158 | 2020-02-06 | Chg
75245 | RPHY MRTR-New-GAR-CIN-RPA25110 | CE | TUL | GAR | Garnett | R PHY | POInt | Yes | Yes | R PHY CE TUL GAR RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-10-01 | 2020-12-31 |  | SN-0722 | 2020-07-15 | New
59522 | R PHY_CCAP_BLU_CBR8_1 | SW | LAS | BLU | Blue Diamond | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS BLU RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-11-02 | 2020-12-31 | 2020-12-31 | SN-0899 | 2020-09-11 | Chg
35176 | MRTR OOB-New-IND-OOB Server | CE | TUL | IND | Indianapolis | Metro Routers | POInt | Yes | Yes | MRTR CE TUL IND NCS Augment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-10-05 | 2020-12-31 | 2021-03-31 | SN-1037 | 2020-11-06 | Chg
75243 | RPHY MRTR-New-OSNAP-CLR | SE | NOR | CLR | Metairie | R PHY | POInt | Yes | Yes | R PHY SE NOR CLR Rphy Metro OSNAP Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 1 | 2020-10-01 | 2020-12-31 |  | SN-0786 | 2020-07-27 | New
75245 | RPHY MRTR-New-BAR-CIN-RPA2-5110 | CE | TUL | BAR | Broken Arrow | R PHY | POInt | Yes | Yes | R PHY CE TUL BAR RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-10-01 | 2020-12-31 |  | SN-0722 | 2020-07-15 | New
75245 | RPHY MRTR-New-BAR-CIN MGMT2-2K | CE | TUL | BAR | Broken Arrow | R PHY | POInt | Yes | Yes | R PHY CE TUL BAR RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-10-01 | 2020-12-31 |  | SN-0722 | 2020-07-15 | New
75245 | RPHY MRTR-New-BAR-CIN-Nokia3-OCML | CE | TUL | BAR | Broken Arrow | R PHY | POInt | Yes | Yes | R PHY CE TUL BAR RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-10-01 | 2020-12-31 |  | SN-0722 | 2020-07-15 | New
75245 | RPHY MRTR-New-TUL-CIN-RPA3-5110 | CE | TUL | TUL | Tulsa | R PHY | POInt | Yes | Yes | R PHY CE TUL TUL RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 3 | 2020-10-01 | 2020-12-31 |  | SN-0722 | 2020-07-15 | New
34608 | CB Transport - New Router Portsmouth - PTM - Optics | VA | HRD | PTM | Portsmouth (VA) | CB - Metro Core | POInt | Yes | Yes | CBMC VA HRD PTM Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-06-15 | 2020-12-31 |  | SN-1049 | 2020-11-13 | Chg
59745 | R PHY_CCAP_DWN_CBR8_1 | CA | SAN | DWN | Downtown | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN DWN RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 2 | 2020-10-15 | 2020-12-31 | 2020-12-31 | SN-0550 | 2020-05-12 | New
35715 | MRTR AAR-New-STN-NEW-AAR | NE | CON | STN | Southington | Metro Routers | POInt | Yes | Yes | MRTR NE CON STN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | SN-0158 | 2020-02-06 | Chg
78091 | VCDR CA SAN ELC Voice HDT Decom POR19 | CA | SAN | ELC | El Cajon | Voice Decom and Refortification | POInt | Yes | Yes | VCDR CA SAN ELC Voice HDT Decom POR19 | Labor | No Equipment | 1 |  | 2020-12-31 |  | SN-0818 | 2020-08-12 | Chg
59745 | R PHY_CCAP_RSM_CBR8_1 | CA | ORG | RSM | Rancho Santa Margarita | RSPD - CCAP | POInt | Yes | Yes | R PHY CA ORG RSM RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 5 | 2020-10-15 | 2020-12-31 | 2020-12-31 | SN-0550 | 2020-05-12 | New
35171 | MRTR NCS-Growth-ELK-100G Grow | CE | OMA | ELK | Elkhorn | Metro Routers | POInt | Yes | Yes | MRTR CE OMA ELK 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | SN-0158 | 2020-02-06 | Chg
78093 | VCDR CE OKC WEH Voice HDT Decom POR20 | CE | OKC | WEH | West (OKC) | Voice Decom and Refortification | POInt | Yes | Yes | VCDR CE OKC WEH Voice HDT Decom POR20 | Labor | No Equipment | 4 | 2020-07-17 | 2020-12-31 |  | SN-0783 | 2020-07-27 | New
35176 | MRTR VSR-New-OKC-VSR-ASR9906 | CE | OKC | OKC | OKC MTC | Metro Routers | POInt | Yes | Yes | MRTR CE OKC OKC VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-01 | 2020-12-31 | 2021-03-31 | SN-0555 | 2020-05-12 | Chg
78097 | HY SE BTR BTR Voice BTS Gateway Decom POR19 | SE | BTR | BTR | Baton Rouge | Voice Decom and Refortification | POInt | Yes | Yes | VCDR SE BTR BTR Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 | 2020-07-06 | 2020-12-31 |  | SN-0697 | 2020-07-10 | Chg
59745 | R PHY_CCAP_OCE_CBR8_1 | CA | SAN | OCE | Oceanside | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN OCE RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-10-15 | 2020-12-31 | 2020-12-31 | SN-0550 | 2020-05-12 | New
75246 | R PHY_CCAP_CLR_CBR8_1 | SE | NOR | CLR | Metairie | R PHY | POInt | Yes | Yes | R PHY SE NOR CLR RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-10-15 | 2020-12-31 | 2020-12-31 | SN-0550 | 2020-05-12 | New
35171 | MRTR SLR-New-FTS-SLR-ASR9906 | CE | NWA | FTS | Fort Smith | Metro Routers | POInt | Yes | Yes | MRTR CE NWA FTS SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-15 | 2020-12-31 | 2020-12-31 | SN-0638 | 2020-06-05 | Chg
78095 | VCDR NE RHD PTH Voice HDT Decom POR20 | NE | RHD | PTH | Portsmouth (RI) | Voice Decom and Refortification | POInt | Yes | Yes | VCDR NE RHD PTH Voice HDT Decom POR20 | Labor | No Equipment | 1 | 2020-07-20 | 2020-12-31 |  | SN-0783 | 2020-07-27 | New
59522 | R PHY_CCAP_CHD_CBR8_1 | SW | ARZ | CHD | Chandler | RSPD - CCAP | POInt | Yes | Yes | R PHY SW ARZ CHD RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 5 | 2020-10-15 | 2020-12-31 | 2020-12-31 | SN-0550 | 2020-05-12 | New
78097 | VCDR SE NOR DST Voice HDT Decom POR20 | SE | NOR | DST | Destrehan | Voice Decom and Refortification | POInt | Yes | Yes | VCDR SE NOR DST Voice HDT Decom POR20 | Labor | No Equipment | 1 | 2020-07-15 | 2020-12-31 |  | SN-0783 | 2020-07-27 | New
75245 | RPHY MRTR-New-BVL-CIN-Nokia3-OCML | CE | NWA | BVL | Bentonville | R PHY | POInt | Yes | Yes | R PHY CE NWA BVL RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-10-01 | 2020-12-31 |  | SN-0722 | 2020-07-15 | New
75245 | RPHY MRTR-New-BVL-CIN-RPA2-5110 | CE | NWA | BVL | Bentonville | R PHY | POInt | Yes | Yes | R PHY CE NWA BVL RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-10-01 | 2020-12-31 |  | SN-0722 | 2020-07-15 | New
75245 | RPHY MRTR-New-BVL-CIN MGMT2-2K | CE | NWA | BVL | Bentonville | R PHY | POInt | Yes | Yes | R PHY CE NWA BVL RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-10-01 | 2020-12-31 |  | SN-0722 | 2020-07-15 | New
35171 | MRTR SLR-New-HRN-SLR-ASR9906 | CE | NWA | HRN | Harrison | Metro Routers | POInt | Yes | Yes | MRTR CE NWA HRN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-05 | 2020-12-31 | 2020-12-31 | SN-0638 | 2020-06-05 | Chg
34608 | CB Transport - New Router Princess Anne - NRF - Optics | VA | HRD | NRF | Norfolk | CB - Metro Core | POInt | Yes | Yes | CBMC VA HRD NRF Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-09-15 | 2020-12-31 |  | SN-1049 | 2020-11-13 | Chg
34608 | CB Transport - New Router Portsmouth - NRF - Optics | VA | HRD | NRF | Norfolk | CB - Metro Core | POInt | Yes | Yes | CBMC VA HRD NRF Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-06-15 | 2020-12-31 |  | SN-1049 | 2020-11-13 | Chg
78093 | VCDR CE KAN WIC Voice HDT Decom POR20 | CE | KAN | WIC | Wichita | Voice Decom and Refortification | POInt | Yes | Yes | VCDR CE KAN WIC Voice HDT Decom POR20 | Labor | No Equipment | 19 | 2020-07-15 | 2020-12-31 |  | SN-0783 | 2020-07-27 | New
59745 | R PHY_CCAP_ELC_CBR8_1 | CA | SAN | ELC | El Cajon | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN ELC RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-10-15 | 2020-12-31 | 2020-12-31 | SN-0550 | 2020-05-12 | New
74548 | R PHY_CCAP_NWP_CBR8_1 | VA | HRD | NWP | Newport News | R PHY | POInt | Yes | Yes | R PHY VA HRD NWP RPHY CCAP Augment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 2 | 2020-10-15 | 2020-12-31 | 2020-12-31 | SN-0550 | 2020-05-12 | New
59522 | R PHY_CCAP_VLY_CBR8_1 | SW | LAS | VLY | Valley | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS VLY RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-10-15 | 2020-12-31 | 2020-12-31 | SN-0550 | 2020-05-12 | New
74548 | R PHY_CCAP_VBC_CBR8_1 | VA | HRD | VBC | Virginia Beach | R PHY | POInt | Yes | Yes | R PHY VA HRD VBC RPHY CCAP Augment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 1 | 2020-10-15 | 2020-12-31 | 2020-12-31 | SN-0550 | 2020-05-12 | New
75245 | RPHY MRTR-Growth-WIC-CIN MGMT2-2K | CE | KAN | WIC | Wichita | R PHY | POInt | Yes | Yes | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-10-01 | 2020-12-31 |  | SN-0722 | 2020-07-15 | New
75245 | RPHY MRTR-New-WIC2-CIN-RPA2-5110 | CE | KAN | WIC | Wichita | R PHY | POInt | Yes | Yes | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-10-01 | 2020-12-31 |  | SN-0722 | 2020-07-15 | New
75245 | RPHY MRTR-New-WIC-CIN Exfo-Switch2 | CE | KAN | WIC | Wichita | R PHY | POInt | Yes | Yes | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-10-01 | 2020-12-31 |  | SN-0722 | 2020-07-15 | New
75245 | RPHY MRTR-New-WIC-CIN-NOKIA-OCML2 | CE | KAN | WIC | Wichita | R PHY | POInt | Yes | Yes | R PHY CE KAN WIC RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-10-01 | 2020-12-31 |  | SN-0722 | 2020-07-15 | New
75245 | RPHY MRTR-New-ELK-CIN-RPA2-5110 | CE | OMA | ELK | Elkhorn | R PHY | POInt | Yes | Yes | R PHY CE OMA ELK RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-10-01 | 2020-12-31 |  | SN-0722 | 2020-07-15 | New
75245 | RPHY MRTR-New-ELK-CIN MGMT2-2K | CE | OMA | ELK | Elkhorn | R PHY | POInt | Yes | Yes | R PHY CE OMA ELK RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-10-01 | 2020-12-31 |  | SN-0722 | 2020-07-15 | New
75245 | RPHY MRTR-New-ELK-CIN-Nokia3-OCML | CE | OMA | ELK | Elkhorn | R PHY | POInt | Yes | Yes | R PHY CE OMA ELK RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-10-01 | 2020-12-31 |  | SN-0722 | 2020-07-15 | New
34608 | CB Transport - New Router Princess Anne - PRA - Optics | VA | HRD | PRA | Princess Anne | CB - Metro Core | POInt | Yes | Yes | CBMC VA HRD PRA Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-09-15 | 2020-12-31 |  | SN-1049 | 2020-11-13 | Chg
78093 | HY SE NOR KNN Voice HDT Decom POR19 | SE | NOR | KNN | Kenner | Voice Decom and Refortification | POInt | Yes | Yes | VCDR SE NOR KNN Voice HDT Decom POR20 | Labor | No Equipment | 7 | 2020-03-31 | 2020-12-31 |  | SN-0818 | 2020-08-12 | Chg
78101 | HY VA HRD HCK Voice HDT Decom POR19 | VA | HRD | HCK | Hickory | Voice Decom and Refortification | POInt | Yes | Yes | VCDR VA HRD HCK Voice HDT Decom POR20 | Labor | No Equipment | 1 | 2020-05-14 | 2020-12-31 |  | SN-0884 | 2020-09-02 | Chg
75247 | R PHY_CCAP_PTH_OTDR_1 | NE | RHD | PTH | Portsmouth (RI) | R PHY | POInt | Yes | Yes | R PHY NE RHD PTH RPHY CCAP Augment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-05-30 | 2020-12-31 |  | SN-0958 | 2020-09-25 | Chg
75245 | RPHY MRTR-New-BVL-CIN Exfo-Switch2 | CE | NWA | BVL | Bentonville | R PHY | POInt | Yes | Yes | R PHY CE NWA BVL RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-10-01 | 2020-12-31 |  | SN-0722 | 2020-07-15 | New
78093 | HY CE NWA HRN Voice POI Decom POR20 | CE | NWA | HRN | Harrison | Voice Decom and Refortification | POInt | Yes | Yes | VCDR CE NWA HRN Voice POI Decom POR20 | Labor | No Equipment | 1 |  | 2020-12-31 |  | SN-0697 | 2020-07-10 | Chg
75244 | RPHY MRTR-Growth-CLV-CIN MGMT-2K | NE | CLE | CLV | Cleveland | R PHY | POInt | Yes | Yes | R PHY NE CLE CLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 16 | 2020-08-01 | 2020-12-31 | 2020-12-31 | SN-0662 | 2020-06-14 | Chg
75244 | RPHY MRTR-New-CLV-CIN-DPA-5200 (100G DPIC) | NE | CLE | CLV | Cleveland | R PHY | POInt | Yes | Yes | R PHY NE CLE CLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 4 | 2020-08-01 | 2020-12-31 | 2020-12-31 | SN-0662 | 2020-06-14 | Chg
75244 | RPHY MRTR-New-CLV-CIN-RPA-5110 | NE | CLE | CLV | Cleveland | R PHY | POInt | Yes | Yes | R PHY NE CLE CLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 32 | 2020-08-01 | 2020-12-31 | 2020-12-31 | SN-0662 | 2020-06-14 | Chg
75244 | RPHY MRTR-New-CLV-CIN-ATX-OCML | NE | CLE | CLV | Cleveland | R PHY | POInt | Yes | Yes | R PHY NE CLE CLV RPHY Metro Initial Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 160 | 2020-08-01 | 2020-12-31 | 2020-12-31 | SN-0662 | 2020-06-14 | New
75244 | RPHY MRTR-New-CLV-CIN-Exfo-Optical Switch | NE | CLE | CLV | Cleveland | R PHY | POInt | Yes | Yes | R PHY NE CLE CLV RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2870 64 Port Optical Switch | 16 | 2020-08-01 | 2020-12-31 | 2020-12-31 | SN-0662 | 2020-06-14 | New
78101 | HY VA HRD GBR Voice HDT Decom POR19 | VA | HRD | GBR | Greenbrier | Voice Decom and Refortification | POInt | Yes | Yes | VCDR VA HRD GBR Voice HDT Decom POR19 | Labor | No Equipment | 1 | 2020-06-08 | 2020-12-31 |  | SN-0884 | 2020-09-02 | Chg
34619 | BNVLBSRA01-ROUTER | CE | NWA | BVL | Bentonville | CB - Metro Core | POInt | Yes | Yes | CBMC CE NWA BVL ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-07-15 | 2020-12-31 |  | SN-1049 | 2020-11-13 | Chg
59522 | R PHY_CCAP_TEN_CBR8_1 | SW | LAS | TEN | Tenaya | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS TEN RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-10-15 | 2020-12-31 | 2020-12-31 | SN-0550 | 2020-05-12 | New
75245 | RPHY MRTR-New-ELK-CIN Exfo-Switch2 | CE | OMA | ELK | Elkhorn | R PHY | POInt | Yes | Yes | R PHY CE OMA ELK RPHY Metro Augment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-10-01 | 2020-12-31 |  | SN-0722 | 2020-07-15 | New
75187 | R PHY_CCAP_NEH_Boundary_Clocks_44119 | CE | OKC | NEH | North East | R PHY | POInt | Yes | Yes | R PHY CE OKC NEH RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-10-05 | 2020-12-31 |  | SN-0605 | 2020-05-22 | Chg
75187 | R PHY_CCAP_NEH_CBR8_1 | CE | OKC | NEH | North East | R PHY | POInt | Yes | Yes | R PHY CE OKC NEH RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-10-15 | 2020-12-31 | 2020-12-31 | SN-0550 | 2020-05-12 | New
75187 | R PHY_CCAP_NEH_OTDR_1 | CE | OKC | NEH | North East | R PHY | POInt | Yes | Yes | R PHY CE OKC NEH RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Exfo FG-750 OTDR Chassis | 1 | 2020-07-31 | 2020-12-31 |  | SN-0637 | 2020-06-05 | New
75245 | RPHY MRTR-New-OKC-CIN-RPA2-5110 | CE | OKC | OKC | OKC MTC | R PHY | POInt | Yes | Yes | R PHY CE OKC OKC RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-10-01 | 2020-12-31 |  | SN-0722 | 2020-07-15 | New
75245 | RPHY MRTR-New-OKC-CIN MGMT2-2K | CE | OKC | OKC | OKC MTC | R PHY | POInt | Yes | Yes | R PHY CE OKC OKC RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-10-01 | 2020-12-31 |  | SN-0722 | 2020-07-15 | New
75245 | RPHY MRTR-New-OKC-CIN-Nokia3-OCML | CE | OKC | OKC | OKC MTC | R PHY | POInt | Yes | Yes | R PHY CE OKC OKC RPHY Metro Initial Deployment POR19 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-10-01 | 2020-12-31 |  | SN-0722 | 2020-07-15 | New
35177 | MRTR VSR-New-NRF-VSR-ASR9906 | VA | HRD | VBC | Virginia Beach | Metro Routers | POInt | Yes | Yes | MRTR VA HRD VBC VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-01 | 2020-12-31 | 2021-03-31 | SN-1037 | 2020-11-06 | Chg
75245 | RPHY MRTR-Growth-NEH-CIN MGMT-2K | CE | OKC | NEH | North East | R PHY | POInt | Yes | Yes | R PHY CE OKC NEH RPHY Metro Initial Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-12-31 | 2020-12-31 | SN-0612 | 2020-05-29 | Chg
75245 | RPHY MRTR-New-NEH-CIN-DPA-5200 (100G DPIC) | CE | OKC | NEH | North East | R PHY | POInt | Yes | Yes | R PHY CE OKC NEH RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-05-15 | 2020-12-31 | 2020-12-31 | SN-0612 | 2020-05-29 | Chg
75245 | RPHY MRTR-New-NEH-CIN Exfo-Switch | CE | OKC | NEH | North East | R PHY | POInt | Yes | Yes | R PHY CE OKC NEH RPHY Metro Initial Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-05-31 | 2020-12-31 | 2020-12-31 | SN-0612 | 2020-05-29 | Chg
75245 | RPHY MRTR-New-NEH-CIN-NOKIA-OCML | CE | OKC | NEH | North East | R PHY | POInt | Yes | Yes | R PHY CE OKC NEH RPHY Metro Initial Deployment POR20 | Chassis | OCML - NOKIA OCML RACK KIT | 10 | 2020-05-15 | 2020-12-31 | 2020-12-31 | SN-0612 | 2020-05-29 | Chg
75245 | RPHY MRTR-New-NEH-CIN-RPA-5110 | CE | OKC | NEH | North East | R PHY | POInt | Yes | Yes | R PHY CE OKC NEH RPHY Metro Initial Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2020-12-31 | 2020-12-31 | SN-0612 | 2020-05-29 | Chg
34608 | CB Transport - New Router Newport News - VBC - Card Add | VA | HRD | VBC | Virginia Beach | CB - Metro Core | POInt | Yes | Yes | CBMC VA HRD VBC Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-02-15 | 2020-12-31 |  | SN-1049 | 2020-11-13 | Chg
75245 | RPHY MRTR-New-OKC-CIN Exfo-Switch2 | CE | OKC | OKC | OKC MTC | R PHY | POInt | Yes | Yes | R PHY CE OKC OKC RPHY Metro Augment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-10-01 | 2020-12-31 |  | SN-0722 | 2020-07-15 | New
35174 | MRTR VSR-New-MCN-VSR-ASR9906 | SE | MGA | MCN | Macon | Metro Routers | POInt | Yes | Yes | MRTR SE MGA MCN VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-01 | 2020-12-31 | 2021-03-31 | SN-0555 | 2020-05-12 | Chg
78101 | HY VA HRD GLO Voice HDT Decom POR19 | VA | HRD | GLO | Gloucester | Voice Decom and Refortification | POInt | Yes | Yes | VCDR VA HRD GLO Voice HDT Decom POR19 | Labor | No Equipment | 1 | 2020-04-10 | 2020-12-31 |  | SN-0818 | 2020-08-12 | Chg
35715 | MRTR AAR-New-CLV-NEW-AAR | NE | CLE | CLV | Cleveland | Metro Routers | POInt | Yes | Yes | MRTR NE CLE CLV AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | SN-0158 | 2020-02-06 | Chg
59745 | R PHY_CCAP_VST_CBR8_1 | CA | SAN | VST | Vista | RSPD - CCAP | POInt | Yes | Yes | R PHY CA SAN VST RPHY CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-10-15 | 2020-12-31 | 2020-12-31 | SN-0550 | 2020-05-12 | New
75245 | RPHY MRTR-New-BAR-CIN Exfo-Switch2 | CE | TUL | BAR | Broken Arrow | R PHY | POInt | Yes | Yes | R PHY CE TUL BAR RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-10-01 | 2020-12-31 |  | SN-0722 | 2020-07-15 | New
59522 | R PHY_CCAP_HEN_CBR8_1 | SW | LAS | HEN | Henderson | RSPD - CCAP | POInt | Yes | Yes | R PHY SW LAS HEN RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 3 | 2020-10-15 | 2020-12-31 | 2020-12-31 | SN-0550 | 2020-05-12 | New
78101 | HY VA ROA RON Voice BTS Gateway Decom POR19 | VA | ROA | RON | Roanoke | Voice Decom and Refortification | POInt | Yes | Yes | VCDR VA ROA RON Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 | 2020-07-06 | 2020-12-31 |  | SN-0697 | 2020-07-10 | Chg
34608 | CB Transport - New Router Fredericksburg - FBG - Optics | VA | NVA | FBG | Fredericksburg | CB - Metro Core | POInt | Yes | Yes | CBMC VA NVA FBG Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-07-15 | 2020-12-31 |  | SN-1049 | 2020-11-13 | Chg
78097 | HY SE LFY LFY Voice BTS Gateway Decom POR19 | SE | LFY | LFY | Lafayette | Voice Decom and Refortification | POInt | Yes | Yes | VCDR SE LFY LFY Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 | 2020-07-06 | 2020-12-31 |  | SN-0697 | 2020-07-10 | Chg
46161 | MRTH-SSC-93180-01 | SW | ARZ | SSC | South Scottsdale | Metro Nexus Thunder | POInt | Yes | Yes | MNEX SW ARZ SSC Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 4 | 2020-01-20 | 2021-01-15 | 2021-02-04 | SB-0237 | 2020-11-06 | Chg
46161 | MRTH-PEO-93180-01 | SW | ARZ | PEO | Peoria | Metro Nexus Thunder | POInt | Yes | Yes | MNEX SW ARZ PEO Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 6 | 2020-04-20 | 2021-01-15 | 2021-01-29 | SB-0237 | 2020-11-06 | Chg
46161 | MRTH-PEO-2248-01 | SW | ARZ | PEO | Peoria | Metro Nexus Thunder | POInt | Yes | Yes | MNEX SW ARZ PEO Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 8 | 2020-04-20 | 2021-01-15 | 2021-01-29 | SB-0237 | 2020-11-06 | Chg
46161 | MRTH-SSC-2248-01 | SW | ARZ | SSC | South Scottsdale | Metro Nexus Thunder | POInt | Yes | Yes | MNEX SW ARZ SSC Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-01-20 | 2021-01-16 | 2021-02-04 | SB-0237 | 2020-11-06 | Chg
46161 | MRTH-DGL-2248-01 | SW | ARZ | DGL | Douglas | Metro Nexus Thunder | POInt | Yes | Yes | MNEX SW ARZ DGL Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-07-14 | 2021-01-20 | 2021-01-29 | SB-0237 | 2020-11-06 | Chg
46161 | MRTH-DGL-93180-01 | SW | ARZ | DGL | Douglas | Metro Nexus Thunder | POInt | Yes | Yes | MNEX SW ARZ DGL Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 2 | 2020-07-14 | 2021-01-21 | 2021-01-30 | SB-0237 | 2020-11-06 | Chg
75792 | Monitoring and Analytics - Proactive Alerting | COR | COR | ATL | Atlanta | Voice Monitoring and Analytics | POInt | Yes | No | VMA CO -CO ATL Proactive Alerting Alignment POR20 | Labor | Adding Proactive Alerting. | 1 | 2020-03-25 | 2021-01-30 |  | SB-0128 | 2020-05-13 | Chg
75663 | V2B CE ARK NWA Market Blackout Control Deployment POR20 | CE | NWA | NWA | Johnson | V2B | POInt | Yes | No | V2B CE NWA NWA V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-12-06 | 2021-01-31 | 2021-02-28 | SN-0501 | 2020-05-05 | Chg
75663 | V2B VA HRD VBC Market Blackout Control Deployment POR20 | VA | HRD | VBC | Virginia Beach | V2B | POInt | Yes | No | V2B VA HRD VBC V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-12-06 | 2021-01-31 | 2021-02-28 | SN-0501 | 2020-05-05 | Chg
75663 | V2B CE OKC OKC Market Blackout Control Deployment POR20 | CE | OKC | OKC | OKC MTC | V2B | POInt | Yes | No | V2B CE OKC OKC V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-12-06 | 2021-01-31 | 2021-02-28 | SN-0501 | 2020-05-05 | Chg
75663 | V2B NE CLE CLV Market Blackout Control Deployment POR20 | NE | CLE | CLV | Cleveland | V2B | POInt | Yes | No | V2B NE CLE CLV V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-12-06 | 2021-01-31 | 2021-02-28 | SN-0501 | 2020-05-05 | Chg
75663 | V2B CE OKC TUL Market Blackout Control Deployment POR20 | CE | TUL | TUL | Tulsa | V2B | POInt | Yes | No | V2B CE TUL TUL V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-12-06 | 2021-01-31 | 2021-02-28 | SN-0501 | 2020-05-05 | Chg
75663 | V2B VA NVA MFD Market Blackout Control Deployment POR20 | VA | NVA | MFD | Merrifield | V2B | POInt | Yes | No | V2B VA NVA MFD V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-12-06 | 2021-01-31 | 2021-02-28 | SN-0501 | 2020-05-05 | Chg
75663 | V2B VA ROA RON Market Blackout Control Deployment POR20 | VA | ROA | RON | Roanoke | V2B | POInt | Yes | No | V2B VA ROA RON V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-12-06 | 2021-01-31 | 2021-02-28 | SN-0501 | 2020-05-05 | Chg
75663 | V2B NE CON MAN Market Blackout Control Deployment POR20 | NE | CON | MAN | Manchester | V2B | POInt | Yes | No | V2B NE CON MAN V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-12-06 | 2021-01-31 | 2021-02-28 | SN-0501 | 2020-05-05 | Chg
75663 | V2B NE RHD WWK Market Blackout Control Deployment POR20 | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | V2B | POInt | Yes | No | V2B NE RHD WWK V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-12-06 | 2021-01-31 | 2021-02-28 | SN-0501 | 2020-05-05 | Chg
75663 | V2B CE OMA OMM Market Blackout Control Deployment POR20 | CE | OMA | OMM | Omaha | V2B | POInt | Yes | No | V2B CE OMA OMM V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-12-06 | 2021-01-31 | 2021-02-28 | SN-0501 | 2020-05-05 | Chg
75663 | V2B CE KAN WIC Market Blackout Control Deployment POR20 | CE | KAN | WIC | Wichita | V2B | POInt | Yes | No | V2B CE KAN WIC V2B Market Blackout Control Deployment POR20 | Chassis | Virtual IRD (1 RU server) | 2 | 2020-12-06 | 2021-01-31 | 2021-02-28 | SN-0501 | 2020-05-05 | Chg
78097 | HY SE MGA MCN Voice BTS Gateway Decom POR19 | SE | MGA | MCN | Macon | Voice Decom and Refortification | POInt | Yes | Yes | VCDR SE MGA MCN Voice BTS Gateway Decom POR19 | Labor | No Equipment | 1 | 2020-06-01 | 2021-01-31 |  | SN-0697 | 2020-07-10 | Chg
44876 | MTCH CE ARK NWA MPEG4 vDCM Install Deployment POR20 | CE | NWA | NWA | Johnson | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH CE NWA NWA MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-03-06 | 2021-02-15 | 2021-06-15 | SN-0227 | 2020-03-30 | Chg
44876 | MTCH CE KAN WIC MPEG4 vDCM Install Deployment POR20 | CE | KAN | WIC | Wichita | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH CE KAN WIC MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 4 | 2020-04-15 | 2021-02-15 | 2021-05-15 | SN-0227 | 2020-03-30 | Chg
34622 | SNTBBSRA01-ROUTER | CA | SAB | SAB | Santa Barbara | CB - Metro Core | POInt | Yes | Yes | CBMC CA SAB SAB ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-07-20 | 2021-02-21 |  | SN-1049 | 2020-11-13 | Chg
78091 | HY CA SAN ELC Voice DMS Decom POR20 | CA | SAN | ELC | El Cajon | Voice Decom and Refortification | POInt | Yes | Yes | VCDR CA SAN ELC Voice El Cajon DMS Decom POR19 | Labor | DMS-500 switch decom | 1 | 2019-10-06 | 2021-02-28 |  | SN-0697 | 2020-07-10 | Chg
78093 | HY CE KAN TOP Voice POI Decom POR20 | CE | KAN | TOP | Topeka | Voice Decom and Refortification | POInt | Yes | No | VCDR CE KAN TOP Voice POI Decom POR20 | Labor | No Equipment | 2 | 2020-07-06 | 2021-02-28 |  | SN-0697 | 2020-07-10 | Chg
78093 | HY CE KAN HWTHKSXA Voice POI Decom POR20 | CE | KAN | WIC | Wichita | Voice Decom and Refortification | POInt | Yes | No | VCDR CE KAN HWTHKSXA Voice POI Decom POR20 | Labor | No Equipment | 3 | 2020-07-06 08:00 | 2021-02-28 |  | SN-0697 | 2020-07-10 | Chg
78093 | HY CE KAN SAL Voice POI Decom POR20 | CE | KAN | SAL | Salina | Voice Decom and Refortification | POInt | Yes | No | VCDR CE KAN SAL Voice POI Decom POR20 | Labor | No Equipment | 1 | 2020-07-06 08:00 | 2021-02-28 |  | SN-0697 | 2020-07-10 | Chg
78093 | HY CE KAN MNT Voice POI Decom POR20 | CE | KAN | MNT | Manhattan | Voice Decom and Refortification | POInt | Yes | No | VCDR CE KAN MNT Voice POI Decom POR20 | Labor | No Equipment | 1 | 2020-07-06 08:00 | 2021-02-28 |  | SN-0697 | 2020-07-10 | Chg
78093 | HY CE KAN HUT Voice POI Decom POR20 | CE | KAN | HUT | Hutchinson | Voice Decom and Refortification | POInt | Yes | No | VCDR CE KAN HUT Voice POI Decom POR20 | Labor | No Equipment | 1 | 2020-07-06 08:00 | 2021-02-28 |  | SN-0697 | 2020-07-10 | Chg
78093 | HY CE KAN PSN Voice POI Decom POR20 | CE | KAN | PSN | Parsons | Voice Decom and Refortification | POInt | Yes | No | VCDR CE KAN PSN Voice POI Decom POR20 | Labor | No Equipment | 1 | 2020-07-06 08:00 | 2021-02-28 |  | SN-0697 | 2020-07-10 | Chg
78099 | VCDR SW ARZ CHD Voice DMS 2 Decom POR20 | SW | ARZ | CHD | Chandler | Voice Decom and Refortification | POInt | Yes | Yes | VCDR SW ARZ CHD Voice DMS 2 Decom POR20 | Labor | No Equipment | 1 | 2020-09-30 | 2021-02-28 |  | SN-0697 | 2020-07-10 | Chg
35171 | MRTR SLR-New-FAY-SLR-ASR9906 | CE | NWA | FAY | Fayetteville | Metro Routers | POInt | Yes | Yes | MRTR CE NWA FAY SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-05 | 2021-02-28 | 2021-02-28 | SN-0638 | 2020-06-05 | Chg
44927 | MTCH VA HRD VBC MPEG4 vDCM Install Deployment POR20 | VA | HRD | VBC | Virginia Beach | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH VA HRD VBC MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-11-15 | 2021-02-28 | 2021-04-30 | SN-0693 | 2020-06-30 | Chg
78093 | VCDR CE KAN JCY Voice POI Decom POR20 | CE | KAN | JCY | Junction City | Voice Decom and Refortification | POInt | Yes | Yes | VCDR CE KAN JCY Voice POI Decom POR20 | Labor | No Equipment | 1 |  | 2021-02-28 |  | SN-0697 | 2020-07-10 | Chg
35176 | MRTR SLR-New-BAR-SLR-ASR9906 | CE | TUL | BAR | Broken Arrow | Metro Routers | POInt | Yes | Yes | MRTR CE TUL BAR SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-05 | 2021-02-28 | 2021-02-28 | SN-0638 | 2020-06-05 | Chg
78091 | VCDR CA SAN ELC Voice Cypress DMS Decom POR20 | CA | SAN | ELC | El Cajon | Voice Decom and Refortification | POInt | Yes | Yes | VCDR CA SAN ELC Voice Cypress DMS Decom POR20 | Labor | No Equipment | 1 | 2020-09-25 | 2021-02-28 |  | SN-0644 | 2020-06-15 | Chg
44875 | MTCH SE GCT PNS MPEG4 vDCM Install Deployment POR20 | SE | GCT | PNS | Pensacola with (Insite tower) | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH SE GCT PNS MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-11-15 | 2021-02-28 | 2021-04-30 | SN-0693 | 2020-06-30 | Chg
78093 | HY CE TUL TULSOKTB Voice POI Decom POR19 | CE | TUL | TUL | Tulsa | Voice Decom and Refortification | POInt | Yes | Yes | VCDR CE TUL TULSOKTB Voice POI Decom POR20 | Labor | No Equipment | 1 |  | 2021-03-02 |  | SN-0850 | 2020-08-20 | Chg
78093 | HY CE KAN WIC Voice DMS Decom POR20 | CE | KAN | WIC | Wichita | Voice Decom and Refortification | POInt | Yes | No | VCDR CE KAN WIC Voice DMS Decom POR20 | Labor | No Equipment | 1 |  | 2021-03-03 |  | SN-0423 | 2020-04-10 | Chg
44925 | MTCH SW ARZ CHD MPEG4 vDCM Install Deployment POR20 | SW | ARZ | CHD | Chandler | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH SW ARZ CHD MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 4 | 2020-10-15 | 2021-03-15 | 2021-05-15 | SN-0693 | 2020-06-30 | Chg
44924 | MTCH SW LAS HEN MPEG4 vDCM Install Deployment POR20 | SW | LAS | HEN | Henderson | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH SW LAS HEN MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-03-06 | 2021-03-15 | 2021-06-15 | SN-0227 | 2020-03-30 | Chg
35171 | MRTR SLR-New-BVL-SLR-ASR9906 | CE | NWA | BVL | Bentonville | Metro Routers | POInt | Yes | Yes | MRTR CE NWA BVL SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2021-03-31 | 2021-03-31 | SN-0638 | 2020-06-05 | Chg
75243 | RPHY MRTR-Growth-MCY-CIN-RPA2-5110 | SE | NOR | MCY | Mid-City | R PHY | POInt | Yes | Yes | R PHY SE NOR MCY RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-12-01 | 2021-03-31 |  | SN-0909 | 2020-09-25 | New
75243 | RPHY MRTR-New-MCY-CIN Exfo-Switch2 | SE | NOR | MCY | Mid-City | R PHY | POInt | Yes | Yes | R PHY SE NOR MCY RPHY Metro Deployment POR20 | Chassis | 1x Exfo M-OTAU-NS2869 48 Port Optical Switch | 1 | 2020-12-01 | 2021-03-31 |  | SN-0909 | 2020-09-25 | New
75243 | RPHY MRTR-New-MCY-CIN-ATX-OCML2 | SE | NOR | MCY | Mid-City | R PHY | POInt | Yes | Yes | R PHY SE NOR MCY RPHY Metro Deployment POR20 | Chassis | OCML - ATX OCML RACK KIT | 10 | 2020-12-01 | 2021-03-31 |  | SN-0909 | 2020-09-25 | New
78101 | HY VA-HRD-CHS Voice DMS Decom POR19 | VA | HRD | CHS | Chesapeake | Voice Decom and Refortification | POInt | Yes | Yes | VCDR VA HRD CHS Voice DMS Decom POR19 | Labor | No Equipment | 1 |  | 2021-03-31 |  | SN-0697 | 2020-07-10 | Chg
35171 | MRTR SLR-New-DBY-SLR-ASR9906 | CE | KAN | DBY | Derby | Metro Routers | POInt | Yes | Yes | MRTR CE KAN DBY SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2021-03-31 | 2021-03-31 | SN-0638 | 2020-06-05 | Chg
78097 | Voice SE NOR CLR Voice HDT Decom POR20 | SE | NOR | CLR | Metairie | Voice Decom and Refortification | POInt | Yes | Yes | VCDR SE NOR CLR Voice HDT Decom POR20 | Labor | No Equipment | 1 | 2020-06-01 | 2021-03-31 |  | SN-1002 | 2020-10-15 | Chg
74648 | RPHY MRTR-New-NRF-CIN MGMT-2K | VA | HRD | NRF | Norfolk | R PHY | POInt | Yes | Yes | R PHY VA HRD NRF RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2021-03-31 | 2021-03-31 | SN-0640 | 2020-06-06 | Chg
74648 | RPHY MRTR-New-NRF-CIN-DPA-5200 | VA | HRD | NRF | Norfolk | R PHY | POInt | Yes | Yes | R PHY VA HRD NRF RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2021-03-31 | 2021-03-31 | SN-0640 | 2020-06-06 | Chg
74648 | RPHY MRTR-New-NRF-CIN-RPA-5110 | VA | HRD | NRF | Norfolk | R PHY | POInt | Yes | Yes | R PHY VA HRD NRF RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2021-03-31 | 2021-03-31 | SN-0640 | 2020-06-06 | Chg
35173 | MRTR NCS-Growth-HEN-NCS Line Card | SW | LAS | HEN | Henderson | Metro Routers | POInt | Yes | Yes | MRTR SW LAS HEN NCS Augment POR20 | Card & Optics | NCS Line Card | 4 | 2020-01-01 03:01 | 2021-03-31 | 2021-03-31 | SN-0638 | 2020-06-05 | Chg
75245 | RPHY MRTR-New-CLH-CIN-RPA2-5110 | CE | OKC | CLH | County Line | R PHY | POInt | Yes | Yes | R PHY CE OKC CLH RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-05-15 | 2021-03-31 | 2021-03-31 | SN-0640 | 2020-06-06 | Chg
75798 | BroadSoft R23 Upgrade 1 | COR | COR | ATL | Atlanta | Voice Network Upgrades | POInt | Yes | No | VNU CO -CO ATL BroadSoft LifeCycle Deployment POR20 | Labor | Upgrade BroadSoft SW to Release 23 | 1 | 2020-03-06 | 2021-03-31 |  | SB-0193 | 2020-08-14 | Chg
35176 | MRTR SLR-New-GAR-SLR-ASR9906 | CE | TUL | GAR | Garnett | Metro Routers | POInt | Yes | Yes | MRTR CE TUL GAR SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2021-03-31 | 2021-03-31 | SN-0638 | 2020-06-05 | Chg
44926 | MTCH NE RHD WWK MPEG4 vDCM Install Deployment POR20 | NE | RHD | WWK | West Warwick w/ Insite tower Cox antennas | MTC HE - Hub Signaling | POInt | Yes | Yes | MTCH NE RHD WWK MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 4 | 2020-11-15 | 2021-04-15 | 2021-07-15 | SN-0950 | 2020-09-25 | Chg
78093 | HY CE KAN WIC Voice HDT Decom POR20 | CE | KAN | WIC | Wichita | Voice Decom and Refortification | POInt | Yes | No | VCDR CE KAN WIC Voice HDT Decom POR20 | Labor | No Equipment | 1 |  | 2021-05-05 |  | SN-0423 | 2020-04-10 | Chg
78091 | VCDR CA SAN CHU Voice HDT Decom POR20 | CA | SAN | CHU | Chula Vista | Voice Decom and Refortification | POInt | Yes | Yes | VCDR CA SAN CHU Voice HDT Decom POR20 | Labor | No Equipment | 22 | 2020-07-01 | 2021-06-30 |  | SN-0697 | 2020-07-10 | New
78099 | VCDR SW ARZ SSC Voice HDT Decom POR20 | SW | ARZ | SSC | South Scottsdale | Voice Decom and Refortification | POInt | Yes | Yes | VCDR SW ARZ SSC Voice HDT Decom POR20 | Labor | No Equipment | 2 | 2020-07-17 | 2021-06-30 |  | SN-0783 | 2020-07-27 | New
78091 | VCDR CA SAN ESC Voice HDT Decom POR20 | CA | SAN | ESC | Escondido | Voice Decom and Refortification | POInt | Yes | Yes | VCDR CA SAN ESC Voice HDT Decom POR20 | Labor | No Equipment | 3 | 2020-07-01 | 2021-06-30 |  | SN-0697 | 2020-07-10 | New
34636 | BWM GCT DOCSIS Expansion 192 MHz | SE | GCT | CRV | Crestview | Bandwidth Management | POInt | Yes | No | BWM SE GCT CRV DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2021-10-01 | 2022-07-01 | SN-0558 | 2020-05-12 | New
34636 | BWM GCT DOCSIS Expansion 96 MHz | SE | GCT | CRV | Crestview | Bandwidth Management | POInt | Yes | No | BWM SE GCT CRV DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2021-10-01 | 2021-12-01 | SN-0558 | 2020-05-12 | New
78091 | VCDR CA SAN VST Voice HDT Decom POR20 | CA | SAN | VST | Vista | Voice Decom and Refortification | POInt | Yes | Yes | VCDR CA SAN VST Voice HDT Decom POR20 | Labor | No Equipment | 15 | 2020-07-01 | 2021-12-01 |  | SN-0697 | 2020-07-10 | New
78091 | VCDR CA SAN OCE Voice HDT Decom POR20 | CA | SAN | OCE | Oceanside | Voice Decom and Refortification | POInt | Yes | Yes | VCDR CA SAN OCE Voice HDT Decom POR20 | Labor | No Equipment | 12 | 2020-07-01 | 2021-12-01 |  | SN-0697 | 2020-07-10 | New

## POR Log
EquipPlan Identifier | Reg | Mkt | Loc | Program | EPSProject_Nm | Kit Type | Kit Name | Kit Qty | NeedBy Date | Activation Month | Migration Month | Plan Status | Line Type | Action | CR | CR Type | CR_Status | CR_Eff_Dt | CR Description
Arbor 19 | CA | ORG | RSM | Arbor DDoS | DDoS CA ORG RSM Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-01-06 | 2020-04-05 | 2020-04-20 | Active | EP
Arbor 19 | CA | ORG | RSM | Arbor DDoS | DDoS CA ORG RSM Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-01-06 | 2020-04-05 | 2020-04-20 | Active | Log | Upd | SN-0107 | Schedule Change | Approved | 2020-02-06 10:50 | POR updates to align 2020 Arbor deployment to updated VIA schedule (CR-0094)
Arbor 24 | CE | OKC | OKC | Arbor DDoS | DDoS CE OKC OKC Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-01-24 | 2020-03-09 | 2020-03-23 | Active | EP
Arbor 24 | CE | OKC | OKC | Arbor DDoS | DDoS CE OKC OKC Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-01-24 | 2020-03-09 | 2020-03-23 | Active | Log | Upd | SN-0107 | Schedule Change | Approved | 2020-02-06 10:50 | POR updates to align 2020 Arbor deployment to updated VIA schedule (CR-0094)
Arbor 20 | CE | OMA | OMM | Arbor DDoS | DDoS CE OMA OMM Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-03-26 | 2020-05-25 | 2020-06-08 | Active | EP
Arbor 20 | CE | OMA | OMM | Arbor DDoS | DDoS CE OMA OMM Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-03-26 | 2020-05-25 | 2020-06-08 | Active | Log | Upd | SN-0107 | Schedule Change | Approved | 2020-02-06 10:50 | POR updates to align 2020 Arbor deployment to updated VIA schedule (CR-0094)
Arbor 5 | COR | NAT | AT1 | Arbor DDoS | DDoS SE NAT AT1 Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-01-01 | 2020-02-26 | 2020-03-27 | Active | EP
Arbor 5 | COR | NAT | AT1 | Arbor DDoS | DDoS SE NAT AT1 Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-01-01 | 2020-02-26 | 2020-03-27 | Active | Log | Upd | SN-0122 | Schedule Change | Approved | 2020-02-06 10:58 | Pulling licensing acquisition to January Aligns material budget for Dell servers to the updated vTMS deployment schedule Updated based on the new quotes for different facility power types and distributes remaining across facilitiesfor ancillary and optics
Arbor 21 | SE | BTR | BTR | Arbor DDoS | DDoS SE BTR BTR Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-01-13 | 2020-03-02 | 2020-03-16 | Active | EP
Arbor 21 | SE | BTR | BTR | Arbor DDoS | DDoS SE BTR BTR Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-01-13 | 2020-03-02 | 2020-03-16 | Active | Log | Upd | SN-0107 | Schedule Change | Approved | 2020-02-06 10:50 | POR updates to align 2020 Arbor deployment to updated VIA schedule (CR-0094)
Arbor 8 | SW | ARZ | CHD | Arbor DDoS | DDoS SW ARZ CHD Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-01-13 | 2020-04-12 | 2020-05-11 | Active | EP
Arbor 8 | SW | ARZ | CHD | Arbor DDoS | DDoS SW ARZ CHD Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-01-13 | 2020-04-12 | 2020-05-11 | Active | Log | Upd | SN-0107 | Schedule Change | Approved | 2020-02-06 10:50 | POR updates to align 2020 Arbor deployment to updated VIA schedule (CR-0094)
Arbor 9 | SW | ARZ | MCD | Arbor DDoS | DDoS SW ARZ MCD Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-01-13 | 2020-04-12 | 2020-05-11 | Active | EP
Arbor 9 | SW | ARZ | MCD | Arbor DDoS | DDoS SW ARZ MCD Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-01-13 | 2020-04-12 | 2020-05-11 | Active | Log | Upd | SN-0107 | Schedule Change | Approved | 2020-02-06 10:50 | POR updates to align 2020 Arbor deployment to updated VIA schedule (CR-0094)
Arbor 17 | VA | NVA | MFD | Arbor DDoS | DDoS VA NVA MFD Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-03-10 | 2020-06-08 | 2020-06-22 | Active | EP
Arbor 17 | VA | NVA | MFD | Arbor DDoS | DDoS VA NVA MFD Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-03-10 | 2020-06-08 | 2020-06-22 | Active | Log | Upd | SN-0107 | Schedule Change | Approved | 2020-02-06 10:50 | POR updates to align 2020 Arbor deployment to updated VIA schedule (CR-0094)
Arbor 23 | CE | KAN | WIC | Arbor DDoS | DDoS CE KAN WIC Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-01-31 | 2020-03-16 | 2020-03-30 | Active | EP
Arbor 23 | CE | KAN | WIC | Arbor DDoS | DDoS CE KAN WIC Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-01-31 | 2020-03-16 | 2020-03-30 | Active | Log | Upd | SN-0107 | Schedule Change | Approved | 2020-02-06 10:50 | POR updates to align 2020 Arbor deployment to updated VIA schedule (CR-0094)
Arbor 1 | COR | NAT | LA1 | Arbor DDoS | DDoS CA NAT LA1 Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-02-28 | 2020-03-31 | 2020-04-30 | Active | EP
Arbor 1 | COR | NAT | LA1 | Arbor DDoS | DDoS CA NAT LA1 Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-01-31 | 2020-03-31 | 2020-04-30 | Active | Log | Upd | SN-0122 | Schedule Change | Approved | 2020-02-06 10:58 | Pulling licensing acquisition to January Aligns material budget for Dell servers to the updated vTMS deployment schedule Updated based on the new quotes for different facility power types and distributes remaining across facilitiesfor ancillary and optics
Arbor 1 | COR | NAT | LA1 | Arbor DDoS | DDoS CA NAT LA1 Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-02-28 | 2020-03-31 | 2020-04-30 | Active | Log | Upd | SN-0220 | Schedule Change | Approved | 2020-02-03 16:49 | Correcting misalignment back to POI and confirmed plan No financial changes
Arbor 18 | NE | RHD | PRV | Arbor DDoS | DDoS NE RHD PRV Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-06-26 | 2020-08-10 | 2020-08-24 | Active | EP
Arbor 18 | NE | RHD | PRV | Arbor DDoS | DDoS NE RHD PRV Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-06-26 | 2020-08-10 | 2020-08-24 | Active | Log | Upd | SN-0107 | Schedule Change | Approved | 2020-02-06 10:50 | POR updates to align 2020 Arbor deployment to updated VIA schedule (CR-0094)
Arbor 22 | SE | NOR | ELM | Arbor DDoS | DDoS SE NOR ELM Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-01-17 | 2020-03-02 | 2020-03-16 | Active | EP
Arbor 22 | SE | NOR | ELM | Arbor DDoS | DDoS SE NOR ELM Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-01-17 | 2020-03-02 | 2020-03-16 | Active | Log | Upd | SN-0107 | Schedule Change | Approved | 2020-02-06 10:50 | POR updates to align 2020 Arbor deployment to updated VIA schedule (CR-0094)
Arbor 16 | CE | NWA | NWA | Arbor DDoS | DDoS CE NWA NWA Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-08-07 | 2020-09-21 | 2020-10-05 | Active | EP
Arbor 16 | CE | NWA | NWA | Arbor DDoS | DDoS CE NWA NWA Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-08-07 | 2020-09-21 | 2020-10-05 | Active | Log | Upd | SN-0107 | Schedule Change | Approved | 2020-02-06 10:50 | POR updates to align 2020 Arbor deployment to updated VIA schedule (CR-0094)
Arbor 15 | CE | TUL | TUL | Arbor DDoS | DDoS CE TUL TUL Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-08-14 | 2020-09-28 | 2020-10-12 | Active | EP
Arbor 15 | CE | TUL | TUL | Arbor DDoS | DDoS CE TUL TUL Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-08-14 | 2020-09-28 | 2020-10-12 | Active | Log | Upd | SN-0107 | Schedule Change | Approved | 2020-02-06 10:50 | POR updates to align 2020 Arbor deployment to updated VIA schedule (CR-0094)
Arbor 7 | COR | NAT | DC2/6 | Arbor DDoS | DDoS VA NAT DC2 Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-04-23 | 2020-05-23 | 2020-06-21 | Active | EP
Arbor 7 | COR | NAT | DC2/6 | Arbor DDoS | DDoS VA NAT DC2 Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-06-27 | 2020-08-26 | 2020-09-25 | Active | Log | Upd | SN-0122 | Schedule Change | Approved | 2020-02-06 10:58 | Pulling licensing acquisition to January Aligns material budget for Dell servers to the updated vTMS deployment schedule Updated based on the new quotes for different facility power types and distributes remaining across facilitiesfor ancillary and optics
Arbor 7 | COR | NAT | DC2/6 | Arbor DDoS | DDoS VA NAT DC2 Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-04-23 | 2020-05-23 | 2020-06-21 | Active | Log | Upd | SN-0220 | Schedule Change | Approved | 2020-02-03 16:49 | Correcting misalignment back to POI and confirmed plan No financial changes
Arbor 3 | COR | NAT | CH1 | Arbor DDoS | DDoS CE NAT CH1 Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-04-24 | 2020-05-27 | 2020-06-26 | Active | EP
Arbor 3 | COR | NAT | CH2 | Arbor DDoS | DDoS CE NAT CH1 Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-03-28 | 2020-05-27 | 2020-06-26 | Active | Log | Upd | SN-0122 | Schedule Change | Approved | 2020-02-06 10:58 | Pulling licensing acquisition to January Aligns material budget for Dell servers to the updated vTMS deployment schedule Updated based on the new quotes for different facility power types and distributes remaining across facilitiesfor ancillary and optics
Arbor 3 | COR | NAT | CH1 | Arbor DDoS | DDoS CE NAT CH1 Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-04-24 | 2020-05-27 | 2020-06-26 | Active | Log | Upd | SN-0220 | Schedule Change | Approved | 2020-02-03 16:49 | Correcting misalignment back to POI and confirmed plan No financial changes
Arbor 6 | COR | NAT | DA1/2 | Arbor DDoS | DDoS SW NAT DA1 Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-07-10 | 2020-08-12 | 2020-09-11 | Active | EP
Arbor 6 | COR | NAT | DA1/2 | Arbor DDoS | DDoS SW NAT DA1 Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-06-13 | 2020-08-12 | 2020-09-11 | Active | Log | Upd | SN-0122 | Schedule Change | Approved | 2020-02-06 10:58 | Pulling licensing acquisition to January Aligns material budget for Dell servers to the updated vTMS deployment schedule Updated based on the new quotes for different facility power types and distributes remaining across facilitiesfor ancillary and optics
Arbor 6 | COR | NAT | DA1/2 | Arbor DDoS | DDoS SW NAT DA1 Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-07-10 | 2020-08-12 | 2020-09-11 | Active | Log | Upd | SN-0220 | Schedule Change | Approved | 2020-02-03 16:49 | Correcting misalignment back to POI and confirmed plan No financial changes
Arbor 25 | COR | COR | DVY | Arbor DDoS | DDoS CO COR DVY Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 10 | 2020-07-28 | 2020-10-26 | 2020-11-09 | Active | EP
Arbor 25 | COR | COR | DVY | Arbor DDoS | DDoS CO COR DVY Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 10 | 2020-07-28 | 2020-10-26 | 2020-11-09 | Active | Log | Upd | SN-0107 | Schedule Change | Approved | 2020-02-06 10:50 | POR updates to align 2020 Arbor deployment to updated VIA schedule (CR-0094)
Arbor 4 | COR | NAT | NY1 | Arbor DDoS | DDoS NE NAT NY1 Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-04-17 | 2020-05-20 | 2020-06-19 | Active | EP
Arbor 4 | COR | NAT | NY1 | Arbor DDoS | DDoS NE NAT NY1 Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-03-21 | 2020-05-20 | 2020-06-19 | Active | Log | Upd | SN-0122 | Schedule Change | Approved | 2020-02-06 10:58 | Pulling licensing acquisition to January Aligns material budget for Dell servers to the updated vTMS deployment schedule Updated based on the new quotes for different facility power types and distributes remaining across facilitiesfor ancillary and optics
Arbor 4 | COR | NAT | NY1 | Arbor DDoS | DDoS NE NAT NY1 Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-04-17 | 2020-05-20 | 2020-06-19 | Active | Log | Upd | SN-0220 | Schedule Change | Approved | 2020-02-03 16:49 | Correcting misalignment back to POI and confirmed plan No financial changes
Arbor 2 | COR | NAT | SV5 | Arbor DDoS | DDoS CA NAT SV5 Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-06-12 | 2020-07-05 | 2020-08-14 | Active | EP
Arbor 2 | COR | NAT | SV5 | Arbor DDoS | DDoS CA NAT SV5 Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-05-06 | 2020-07-05 | 2020-08-14 | Active | Log | New | SN-0122 | Schedule Change | Approved | 2020-02-06 10:58 | Pulling licensing acquisition to January Aligns material budget for Dell servers to the updated vTMS deployment schedule Updated based on the new quotes for different facility power types and distributes remaining across facilitiesfor ancillary and optics
Arbor 2 | COR | NAT | SV5 | Arbor DDoS | DDoS CA NAT SV5 Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-06-12 | 2020-07-05 | 2020-08-14 | Active | Log | Upd | SN-0220 | Schedule Change | Approved | 2020-02-03 16:49 | Correcting misalignment back to POI and confirmed plan No financial changes
Arbor 10 | NE | CLE | CLV | Arbor DDoS | DDoS NE CLE CLV Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-05-22 | 2020-07-06 | 2020-07-20 | Active | EP
Arbor 10 | NE | CLE | CLV | Arbor DDoS | DDoS NE CLE CLV Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-05-22 | 2020-07-06 | 2020-07-20 | Active | Log | Upd | SN-0107 | Schedule Change | Approved | 2020-02-06 10:50 | POR updates to align 2020 Arbor deployment to updated VIA schedule (CR-0094)
Arbor 11 | SE | GAN | GNS | Arbor DDoS | DDoS SE GAN GNS Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-01-10 | 2020-02-24 | 2020-03-09 | Active | EP
Arbor 11 | SE | GAN | GNS | Arbor DDoS | DDoS SE GAN GNS Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-01-10 | 2020-02-24 | 2020-03-09 | Active | Log | Upd | SN-0107 | Schedule Change | Approved | 2020-02-06 10:50 | POR updates to align 2020 Arbor deployment to updated VIA schedule (CR-0094)
Arbor 14 | SE | GCT | PNS | Arbor DDoS | DDoS SE GCT PNS Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-05-15 | 2020-06-29 | 2020-07-13 | Active | EP
Arbor 14 | SE | GCT | PNS | Arbor DDoS | DDoS SE GCT PNS Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-05-15 | 2020-06-29 | 2020-07-13 | Active | Log | Upd | SN-0107 | Schedule Change | Approved | 2020-02-06 10:50 | POR updates to align 2020 Arbor deployment to updated VIA schedule (CR-0094)
Arbor 12 | SE | MGA | MCN | Arbor DDoS | DDoS SE MGA MCN Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-07-17 | 2020-08-31 | 2020-09-14 | Active | EP
Arbor 12 | SE | MGA | MCN | Arbor DDoS | DDoS SE MGA MCN Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-07-17 | 2020-08-31 | 2020-09-14 | Active | Log | Upd | SN-0107 | Schedule Change | Approved | 2020-02-06 10:50 | POR updates to align 2020 Arbor deployment to updated VIA schedule (CR-0094)
Arbor 13 | VA | ROA | RON | Arbor DDoS | DDoS VA ROA RON Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-04-21 | 2020-07-20 | 2020-08-03 | Active | EP
Arbor 13 | VA | ROA | RON | Arbor DDoS | DDoS VA ROA RON Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-06-26 | 2020-08-10 | 2020-08-24 | Active | Log | Upd | SN-0107 | Schedule Change | Approved | 2020-02-06 10:50 | POR updates to align 2020 Arbor deployment to updated VIA schedule (CR-0094)
Arbor 13 | VA | ROA | RON | Arbor DDoS | DDoS VA ROA RON Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 1 | 2020-04-21 | 2020-07-20 | 2020-08-03 | Active | Log | Upd | SN-0172 | Schedule Change | Approved | 2020-01-10 15:11 | Due to FEO timeline constraints for turnaround between receiving, installing, and activating equipment, the schedule for the VA deployments need adjusting Due to ongoing SCM negotiations funding for licenses will need to push from January
PTX Add 5 | CE | NWA | NWA | Backbone | BBCAP CE NWA NWA PTX10 Deployment POR20 | Chassis | 1x Juniper PTX10K Chassis |  |  |  |  | Deleted | EP
PTX Add 5 | CE | NWA | NWA | Backbone | BBCAP CE NWA NWA PTX10 Deployment POR20 | Chassis | 1x Juniper PTX10K Chassis |  |  |  |  | Deleted | Log | Del | SN-0533 | COVID-19 Related | Approved | 2020-05-08 14:26 | Submitting this CR to update the Backbone Capacity program POR against deferrals CR submitted earlier for financial changes
PTX Add 6 | CE | TUL | TUL | Backbone | BBCAP CE TUL TUL PTX10 Deployment POR20 | Chassis | 1x Juniper PTX10K Chassis | 2 | 2020-09-05 | 2020-12-15 |  | Active | EP
PTX Add 6 | CE | TUL | TUL | Backbone | BBCAP CE TUL TUL PTX10 Deployment POR20 | Chassis | 1x Juniper PTX10K Chassis | 2 | 2020-09-05 | 2020-11-15 |  | Active | Log | Upd | SN-0049 | New | Approved | 2020-02-06 10:21 | Updating the Market, TLA names in the POR to align with EPS projects
PTX Add 6 | CE | TUL | TUL | Backbone | BBCAP CE TUL TUL PTX10 Deployment POR20 | Chassis | 1x Juniper PTX10K Chassis | 2 | 2020-09-05 | 2020-12-15 |  | Active | Log | Upd | SN-1034 | Schedule Change | Approved | 2020-10-30 10:21 | Due limited burn in after power availability and delay in fiber order being rescheduled for December
PTX Add 7 | NE | CLE | CLV | Backbone | BBCAP NE CLE CLV PTX10 Deployment POR20 | Chassis | 1x Juniper PTX10K Chassis |  |  |  |  | Deleted | EP
PTX Add 7 | NE | CLE | CLV | Backbone | BBCAP NE CLE CLV PTX10 Deployment POR20 | Chassis | 1x Juniper PTX10K Chassis | 2 | 2020-08-01 | 2020-10-31 |  | Deleted | Log | Upd | SN-0265 | True up | Approved | 2020-02-14 15:54 | Overall Capex variance of ~ 16K favorable mainly due to lesser labor numbers Adjusting in out months Opex variance of ~ 24K being adjusted from out months
PTX Add 7 | NE | CLE | CLV | Backbone | BBCAP NE CLE CLV PTX10 Deployment POR20 | Chassis | 1x Juniper PTX10K Chassis | 2 | 2020-07-10 | 2020-10-31 |  | Deleted | Log | Upd | SN-0448 | True up | Approved | 2020-04-17 16:30 | Overall Capex variance of 1,902 Material variance ~ 28K as taxes against one of the PO didn t hit March Labor variance due to multiple activities related to PTX installs and capacity enhancement activities due to current situation
PTX Add 7 | NE | CLE | CLV | Backbone | BBCAP NE CLE CLV PTX10 Deployment POR20 | Chassis | 1x Juniper PTX10K Chassis | 2 | 2020-07-10 | 2020-11-30 |  | Deleted | Log | Upd | SN-0483 | Schedule Change | Approved | 2020-04-24 14:36 | Pushing 346K to May because the Juniper PTX10K chassis intiailly planned for April receipt have been delyaed and will now be delivered in May Also updating POR for Cleveland activation date change
PTX Add 7 | NE | CLE | CLV | Backbone | BBCAP NE CLE CLV PTX10 Deployment POR20 | Chassis | 1x Juniper PTX10K Chassis |  |  |  |  | Deleted | Log | Del | SN-0533 | COVID-19 Related | Approved | 2020-05-08 14:26 | Submitting this CR to update the Backbone Capacity program POR against deferrals CR submitted earlier for financial changes
PTX Add FOA | SE | GAN | GNS | Backbone | BBCAP SE GAN GNS PTX10 Deployment POR20 | Chassis | 1x Juniper PTX10K Chassis | 2 | 2020-03-14 | 2020-06-22 |  | Active | EP
PTX Add FOA | SE | GAN | GNS | Backbone | BBCAP SE GAN GNS PTX10 Deployment POR20 | Chassis | 1x Juniper PTX10K Chassis | 2 | 2020-03-14 | 2020-06-22 |  | Active | Log | Upd | SN-0549 | True up | Approved | 2020-05-13 11:44 | April capex variance of 66K unfavorable mainly due to high IHL as there are multiple activities going on to meet the capacity demand due to Covid19 Also re aligning the Capex funds based on the updated plan and funds requirement per month
PTX Add 2 | SE | GCT | PNS | Backbone | BBCAP SE GCT PNS PTX10 Deployment POR20 | Chassis | 1x Juniper PTX10K Chassis | 2 | 2020-04-23 | 2020-07-15 |  | Active | EP
PTX Add 2 | SE | GCT | PNS | Backbone | BBCAP SE GCT PNS PTX10 Deployment POR20 | Chassis | 1x Juniper PTX10K Chassis | 2 | 2020-04-23 | 2020-07-15 |  | Active | Log | Upd | SN-0448 | True up | Approved | 2020-04-17 16:30 | Overall Capex variance of 1,902 Material variance ~ 28K as taxes against one of the PO didn t hit March Labor variance due to multiple activities related to PTX installs and capacity enhancement activities due to current situation
PTX Add 4 | SE | MGA | MCN | Backbone | BBCAP SE MGA MCN PTX10 Deployment POR20 | Chassis | 1x Juniper PTX10K Chassis |  |  |  |  | Deleted | EP
PTX Add 4 | SE | MGA | MCN | Backbone | BBCAP SE MGA MCN PTX10 Deployment POR20 | Chassis | 1x Juniper PTX10K Chassis | 2 | 2020-06-08 | 2020-09-15 |  | Deleted | Log | Upd | SN-0448 | True up | Approved | 2020-04-17 16:30 | Overall Capex variance of 1,902 Material variance ~ 28K as taxes against one of the PO didn t hit March Labor variance due to multiple activities related to PTX installs and capacity enhancement activities due to current situation
PTX Add 4 | SE | MGA | MCN | Backbone | BBCAP SE MGA MCN PTX10 Deployment POR20 | Chassis | 1x Juniper PTX10K Chassis |  |  |  |  | Deleted | Log | Del | SN-0533 | COVID-19 Related | Approved | 2020-05-08 14:26 | Submitting this CR to update the Backbone Capacity program POR against deferrals CR submitted earlier for financial changes
PTX Add 3 | VA | ROA | RON | Backbone | BBCAP VA ROA RON PTX10 Deployment POR20 | Chassis | 1x Juniper PTX10K Chassis | 2 | 2020-05-18 | 2020-09-15 |  | Active | EP
PTX Add 3 | VA | ROA | RON | Backbone | BBCAP VA ROA RON PTX10 Deployment POR20 | Chassis | 1x Juniper PTX10K Chassis | 2 | 2020-05-18 | 2020-08-18 |  | Active | Log | Upd | SN-0347 | True up | Approved | 2020-03-12 11:44 | Capex variance of ~ 19K Material variance due to non-receipt of PTX10K and high labor charges due to reclass of labor from Opex to Capex charged incorrectly in Jan Reclass resulted in Opex credit that is distributed in out months as required
PTX Add 3 | VA | ROA | RON | Backbone | BBCAP VA ROA RON PTX10 Deployment POR20 | Chassis | 1x Juniper PTX10K Chassis | 2 | 2020-05-18 | 2020-09-15 |  | Active | Log | Upd | SN-0785 | Schedule Change | Approved | 2020-07-27 09:30 | PTX migration date updates for Roanoke
MX2010 | NE | CLE | CLV | Backbone | BBCAP NE CLE CLV MX2010 Deployment POR20 | Chassis | 1x Juniper MX2010 Chassis | 2 | 2020-07-01 | 2020-12-15 |  | Active | EP
MX2010 | NE | CLE | CLV | Backbone | BBCAP NE CLE CLV MX2010 Deployment POR20 | Chassis | 1x Juniper MX2010 Chassis | 2 | 2020-07-01 | 2020-08-31 |  | Active | Log | New | SN-0622 | Schedule Change | Approved | 2020-06-05 14:51 | CR to update POR with addition of Cleveland Parma Backbone equipment install project CR to manage financials was already submitted and approved so no impact to financials
MX2010 | NE | CLE | CLV | Backbone | BBCAP NE CLE CLV MX2010 Deployment POR20 | Chassis | 1x Juniper MX2010 Chassis | 2 | 2020-07-01 | 2020-12-15 |  | Active | Log | Upd | SN-0964 | Schedule Change | Approved | 2020-10-02 09:33 | Bacbone MX2010 migration date updates for Cleveland
BWM_SAB_VIDEO SG_2020 DOCSIS node split-based Video SG | CA | SAB | SAB | Bandwidth Management | BWM CA SAB SAB VIDEO SG Augment POR20 | Labor | No Equipment | 4 | 2019-10-01 | 2020-03-15 | 2020-03-01 | Active | EP
BWM_SAB_VIDEO SG_2020 DOCSIS node split-based Video SG | CA | SAB | SAB | Bandwidth Management | BWM CA SAB SAB VIDEO SG Augment POR20 | Labor | No Equipment | 4 | 2019-10-01 | 2020-03-15 | 2020-03-01 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_BVL_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | NWA | BVL | Bandwidth Management | BWM CE NWA BVL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-06-15 | 2020-06-24 | Active | EP
BWM_BVL_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | NWA | BVL | Bandwidth Management | BWM CE NWA BVL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_BVL_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | NWA | BVL | Bandwidth Management | BWM CE NWA BVL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-06-15 | 2020-08-14 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_BVL_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | NWA | BVL | Bandwidth Management | BWM CE NWA BVL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-06-15 | 2020-06-24 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_NWA_VIDEO SG_2020 DOCSIS node split-based Video SG I | CE | NWA | NWA | Bandwidth Management | BWM CE NWA NWA MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-24 | Active | EP
BWM_NWA_VIDEO SG_2020 DOCSIS node split-based Video SG I | CE | NWA | NWA | Bandwidth Management | BWM CE NWA NWA MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_NWA_VIDEO SG_2020 DOCSIS node split-based Video SG I | CE | NWA | NWA | Bandwidth Management | BWM CE NWA NWA MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_NWA_VIDEO SG_2020 DOCSIS node split-based Video SG I | CE | NWA | NWA | Bandwidth Management | BWM CE NWA NWA MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-08-14 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_NWA_VIDEO SG_2020 DOCSIS node split-based Video SG I | CE | NWA | NWA | Bandwidth Management | BWM CE NWA NWA MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-24 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_PSN_VIDEO SG_2020 DOCSIS node split-based Video SG I | CE | KAN | PSN | Bandwidth Management | BWM CE KAN PSN VIDEO SG Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | EP
BWM_OKC_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | OKC | OKC | Bandwidth Management | BWM CE OKC OKC VIDEO SG Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | EP
BWM_BLV_VIDEO SG_2020 DOCSIS node split-based Video SG I | CE | OMA | BLV | Bandwidth Management | BWM CE OMA BLV Video SG Augment POR20 1 | Labor | No Equipment | 1 |  | 2020-06-30 | 2020-06-30 | Active | EP
BWM_BLV_VIDEO SG_2020 DOCSIS node split-based Video SG I | CE | OMA | BLV | Bandwidth Management | BWM CE OMA BLV Video SG Augment POR20 1 | Labor | No Equipment | 1 |  | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0245 | Schedule Change | Approved | 2020-02-24 12:37 | 59 projects were made inactive on CR SN-0195 in error, I m reactivating these projects and VSG submited an revised plan 14 VSG projects removed and shifting some dates for the remaining projects
BWM_TUL_VIDEO SG_2020 DOCSIS node split-based Video SG I Dup1 | CE | OMA | ELK | Bandwidth Management | BWM CE OMA ONA VIDEO SG Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_TUL_VIDEO SG_2020 DOCSIS node split-based Video SG I Dup1 | CE | OMA | ELK | Bandwidth Management | BWM CE OMA ONA VIDEO SG Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0245 | Schedule Change | Approved | 2020-02-24 12:37 | 59 projects were made inactive on CR SN-0195 in error, I m reactivating these projects and VSG submited an revised plan 14 VSG projects removed and shifting some dates for the remaining projects
BWM_WES_VIDEO SG_2020 DOCSIS node split-based Video SG I | CE | OMA | WES | Bandwidth Management | BWM CE OMA WES Video SG Augment POR20 1 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_WES_VIDEO SG_2020 DOCSIS node split-based Video SG I | CE | OMA | WES | Bandwidth Management | BWM CE OMA WES Video SG Augment POR20 1 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0413 | New | Approved | 2020-04-02 09:42 | Remove three VSG projects that were removed via manual POR, but also needs to be removed from process and DB
BWM_WES_VIDEO SG_2020 DOCSIS node split-based Video SG I | CE | OMA | WES | Bandwidth Management | BWM CE OMA WES Video SG Augment POR20 1 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_MAN_VIDEO SG_2020 DOCSIS node split-based Video SG Dup | NE | CON | MAN | Bandwidth Management | BWM NE CON MAN Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Deleted | EP
BWM_NRF_VIDEO SG_2020 DOCSIS node split-based Video SG | VA | HRD | NRF | Bandwidth Management | BWM VA HRD NRF MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-05-20 | Active | EP
BWM_NRF_VIDEO SG_2020 DOCSIS node split-based Video SG | VA | HRD | NRF | Bandwidth Management | BWM VA HRD NRF MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-05-20 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_PRA_VIDEO SG_2020 DOCSIS node split-based Video SG | VA | HRD | PRA | Bandwidth Management | BWM VA HRD PRA VIDEO SG Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_PRA_VIDEO SG_2020 DOCSIS node split-based Video SG | VA | HRD | PRA | Bandwidth Management | BWM VA HRD PRA VIDEO SG Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0245 | Schedule Change | Approved | 2020-02-24 12:37 | 59 projects were made inactive on CR SN-0195 in error, I m reactivating these projects and VSG submited an revised plan 14 VSG projects removed and shifting some dates for the remaining projects
BWM_MFD_VIDEO SG_2020 DOCSIS node split-based Video SG | VA | NVA | MFD | Bandwidth Management | BWM VA NVA MFD Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | EP
BWM_RON_VIDEO SG_2020 DOCSIS node split-based Video SG | VA | ROA | RON | Bandwidth Management | BWM VA ROA RON Video SG Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_RON_VIDEO SG_2020 DOCSIS node split-based Video SG | VA | ROA | RON | Bandwidth Management | BWM VA ROA RON Video SG Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0245 | Schedule Change | Approved | 2020-02-24 12:37 | 59 projects were made inactive on CR SN-0195 in error, I m reactivating these projects and VSG submited an revised plan 14 VSG projects removed and shifting some dates for the remaining projects
BWM _CHS_MSSA_Spectrum Phase II Start | VA | HRD | CHS | Bandwidth Management | BWM VA HRD CHS MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-05-20 | Active | EP
BWM _CHS_MSSA_Spectrum Phase II Start | VA | HRD | CHS | Bandwidth Management | BWM VA HRD CHS MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-30 | 2020-03-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM _CHS_MSSA_Spectrum Phase II Start | VA | HRD | CHS | Bandwidth Management | BWM VA HRD CHS MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-06-05 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM _CHS_MSSA_Spectrum Phase II Start | VA | HRD | CHS | Bandwidth Management | BWM VA HRD CHS MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-05-20 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_GLO_MSSA_Spectrum Phase II Start | VA | HRD | GLO | Bandwidth Management | BWM VA HRD GLO MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-05-20 | Active | EP
BWM_GLO_MSSA_Spectrum Phase II Start | VA | HRD | GLO | Bandwidth Management | BWM VA HRD GLO MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-30 | 2020-03-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_GLO_MSSA_Spectrum Phase II Start | VA | HRD | GLO | Bandwidth Management | BWM VA HRD GLO MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-06-05 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_GLO_MSSA_Spectrum Phase II Start | VA | HRD | GLO | Bandwidth Management | BWM VA HRD GLO MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-05-20 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_GNS_MSSA_Spectrum Phase II Start | SE | GAN | GNS | Bandwidth Management | BWM SE GAN GNS MSSA_Labor Only_Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-30 | 2020-03-30 | Active | EP
BWM_GNS_MSSA_Spectrum Phase II Start | SE | GAN | GNS | Bandwidth Management | BWM SE GAN GNS MSSA_Labor Only_Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-30 | 2020-03-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_HCK_MSSA_Spectrum Phase II Start | VA | HRD | HCK | Bandwidth Management | BWM VA HRD HCK MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-03-16 | 2020-05-20 | Active | EP
BWM_HCK_MSSA_Spectrum Phase II Start | VA | HRD | HCK | Bandwidth Management | BWM VA HRD HCK MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-30 | 2020-03-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_HCK_MSSA_Spectrum Phase II Start | VA | HRD | HCK | Bandwidth Management | BWM VA HRD HCK MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-06-05 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_HCK_MSSA_Spectrum Phase II Start | VA | HRD | HCK | Bandwidth Management | BWM VA HRD HCK MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-03-16 | 2020-05-20 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_LTF_MSSA_Spectrum Phase II Start | VA | HRD | LTF | Bandwidth Management | BWM VA HRD LTF MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-05-20 | Active | EP
BWM_LTF_MSSA_Spectrum Phase II Start | VA | HRD | LTF | Bandwidth Management | BWM VA HRD LTF MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_LTF_MSSA_Spectrum Phase II Start | VA | HRD | LTF | Bandwidth Management | BWM VA HRD LTF MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-03-16 | 2020-06-05 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_LTF_MSSA_Spectrum Phase II Start | VA | HRD | LTF | Bandwidth Management | BWM VA HRD LTF MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-03-16 | 2020-06-05 | Active | Log | Upd | SN-0587 | New | Approved | 2020-05-14 16:37 | Updated 12 Need by dates
BWM_LTF_MSSA_Spectrum Phase II Start | VA | HRD | LTF | Bandwidth Management | BWM VA HRD LTF MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-05-20 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_NRF_MSSA_Spectrum Phase II Start | VA | HRD | NRF | Bandwidth Management | BWM VA HRD NRF MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-05-20 | Active | EP
BWM_NRF_MSSA_Spectrum Phase II Start | VA | HRD | NRF | Bandwidth Management | BWM VA HRD NRF MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-30 | 2020-03-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_NRF_MSSA_Spectrum Phase II Start | VA | HRD | NRF | Bandwidth Management | BWM VA HRD NRF MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-06-05 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_NRF_MSSA_Spectrum Phase II Start | VA | HRD | NRF | Bandwidth Management | BWM VA HRD NRF MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-05-20 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_NWP_MSSA_Spectrum Phase II Start | VA | HRD | NWP | Bandwidth Management | BWM VA HRD NWP MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-05-20 | Active | EP
BWM_NWP_MSSA_Spectrum Phase II Start | VA | HRD | NWP | Bandwidth Management | BWM VA HRD NWP MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-30 | 2020-03-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_NWP_MSSA_Spectrum Phase II Start | VA | HRD | NWP | Bandwidth Management | BWM VA HRD NWP MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-06-05 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_NWP_MSSA_Spectrum Phase II Start | VA | HRD | NWP | Bandwidth Management | BWM VA HRD NWP MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-05-20 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_OCN_MSSA_Spectrum Phase II Start | VA | HRD | OCN | Bandwidth Management | BWM VA HRD OCN MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-05-20 | Active | EP
BWM_OCN_MSSA_Spectrum Phase II Start | VA | HRD | OCN | Bandwidth Management | BWM VA HRD OCN MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-30 | 2020-03-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_OCN_MSSA_Spectrum Phase II Start | VA | HRD | OCN | Bandwidth Management | BWM VA HRD OCN MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-06-05 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_OCN_MSSA_Spectrum Phase II Start | VA | HRD | OCN | Bandwidth Management | BWM VA HRD OCN MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-05-20 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_PRA_MSSA_Spectrum Phase II Start | VA | HRD | PRA | Bandwidth Management | BWM VA HRD PRA MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-05-20 | Active | EP
BWM_PRA_MSSA_Spectrum Phase II Start | VA | HRD | PRA | Bandwidth Management | BWM VA HRD PRA MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-30 | 2020-03-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_PRA_MSSA_Spectrum Phase II Start | VA | HRD | PRA | Bandwidth Management | BWM VA HRD PRA MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-06-05 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_PRA_MSSA_Spectrum Phase II Start | VA | HRD | PRA | Bandwidth Management | BWM VA HRD PRA MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-05-20 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_PTM_MSSA_Spectrum Phase II Start | VA | HRD | PTM | Bandwidth Management | BWM VA HRD PTM MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-05-20 | Active | EP
BWM_PTM_MSSA_Spectrum Phase II Start | VA | HRD | PTM | Bandwidth Management | BWM VA HRD PTM MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-30 | 2020-03-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_PTM_MSSA_Spectrum Phase II Start | VA | HRD | PTM | Bandwidth Management | BWM VA HRD PTM MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-06-05 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_PTM_MSSA_Spectrum Phase II Start | VA | HRD | PTM | Bandwidth Management | BWM VA HRD PTM MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-05-20 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_VBC_MSSA_Spectrum Phase II Start | VA | HRD | VBC | Bandwidth Management | BWM VA HRD VBC MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-05-20 | Active | EP
BWM_VBC_MSSA_Spectrum Phase II Start | VA | HRD | VBC | Bandwidth Management | BWM VA HRD VBC MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-30 | 2020-03-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_VBC_MSSA_Spectrum Phase II Start | VA | HRD | VBC | Bandwidth Management | BWM VA HRD VBC MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-06-05 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_VBC_MSSA_Spectrum Phase II Start | VA | HRD | VBC | Bandwidth Management | BWM VA HRD VBC MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-05-20 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_AVJ_ MSSA_Spectrum Phase II Start | CA | ORG | AVJ | Bandwidth Management | BWM CA ORG AVJ MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-01-27 | 2020-03-13 | Active | EP
BWM_AVJ_ MSSA_Spectrum Phase II Start | CA | ORG | AVJ | Bandwidth Management | BWM CA ORG AVJ MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2019-10-22 | 2019-04-20 |  | Active | Log | New | SN-0055 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_AVJ_ MSSA_Spectrum Phase II Start | CA | ORG | AVJ | Bandwidth Management | BWM CA ORG AVJ MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_AVJ_ MSSA_Spectrum Phase II Start | CA | ORG | AVJ | Bandwidth Management | BWM CA ORG AVJ MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-01-27 | 2020-03-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_AVJ_ MSSA_Spectrum Phase II Start | CA | ORG | AVJ | Bandwidth Management | BWM CA ORG AVJ MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-01-27 | 2020-03-13 | Active | Log | Upd | SN-0587 | New | Approved | 2020-05-14 16:37 | Updated 12 Need by dates
BWM_IRV_MSSA_Spectrum Phase II Start | CA | ORG | IRV | Bandwidth Management | BWM CA ORG IRV MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-01-27 | 2020-03-13 | Active | EP
BWM_IRV_MSSA_Spectrum Phase II Start | CA | ORG | IRV | Bandwidth Management | BWM CA ORG IRV MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2019-09-20 |  | Active | Log | New | SN-0055 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_IRV_MSSA_Spectrum Phase II Start | CA | ORG | IRV | Bandwidth Management | BWM CA ORG IRV MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_IRV_MSSA_Spectrum Phase II Start | CA | ORG | IRV | Bandwidth Management | BWM CA ORG IRV MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-01-27 | 2020-03-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_IRV_MSSA_Spectrum Phase II Start | CA | ORG | IRV | Bandwidth Management | BWM CA ORG IRV MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-01-27 | 2020-03-13 | Active | Log | Upd | SN-0587 | New | Approved | 2020-05-14 16:37 | Updated 12 Need by dates
BWM_ORG_MSSA_Spectrum Phase II Start | CA | ORG | ORG | Bandwidth Management | BWM CA ORG ORG MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-01-27 | 2020-03-13 | Active | EP
BWM_ORG_MSSA_Spectrum Phase II Start | CA | ORG | ORG | Bandwidth Management | BWM CA ORG ORG MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2019-04-20 |  | Active | Log | New | SN-0055 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_ORG_MSSA_Spectrum Phase II Start | CA | ORG | ORG | Bandwidth Management | BWM CA ORG ORG MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_ORG_MSSA_Spectrum Phase II Start | CA | ORG | ORG | Bandwidth Management | BWM CA ORG ORG MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-01-27 | 2020-03-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_ORG_MSSA_Spectrum Phase II Start | CA | ORG | ORG | Bandwidth Management | BWM CA ORG ORG MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-01-27 | 2020-03-13 | Active | Log | Upd | SN-0587 | New | Approved | 2020-05-14 16:37 | Updated 12 Need by dates
BWM_PAV_MSSA_Spectrum Phase II Start | CA | ORG | PAV | Bandwidth Management | BWM CA ORG PAV MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-01-27 | 2020-03-13 | Active | EP
BWM_PAV_MSSA_Spectrum Phase II Start | CA | ORG | PAV | Bandwidth Management | BWM CA ORG PAV MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2019-04-20 |  | Active | Log | New | SN-0055 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_PAV_MSSA_Spectrum Phase II Start | CA | ORG | PAV | Bandwidth Management | BWM CA ORG PAV MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_PAV_MSSA_Spectrum Phase II Start | CA | ORG | PAV | Bandwidth Management | BWM CA ORG PAV MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-01-27 | 2020-03-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_PAV_MSSA_Spectrum Phase II Start | CA | ORG | PAV | Bandwidth Management | BWM CA ORG PAV MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-01-27 | 2020-03-13 | Active | Log | Upd | SN-0587 | New | Approved | 2020-05-14 16:37 | Updated 12 Need by dates
BWM_RSM_MSSA_Spectrum Phase II Start | CA | ORG | RSM | Bandwidth Management | BWM CA ORG RSM MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-01-27 | 2020-03-13 | Active | EP
BWM_RSM_MSSA_Spectrum Phase II Start | CA | ORG | RSM | Bandwidth Management | BWM CA ORG RSM MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2019-09-20 |  | Active | Log | New | SN-0055 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_RSM_MSSA_Spectrum Phase II Start | CA | ORG | RSM | Bandwidth Management | BWM CA ORG RSM MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_RSM_MSSA_Spectrum Phase II Start | CA | ORG | RSM | Bandwidth Management | BWM CA ORG RSM MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-01-27 | 2020-03-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_RSM_MSSA_Spectrum Phase II Start | CA | ORG | RSM | Bandwidth Management | BWM CA ORG RSM MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-01-27 | 2020-03-13 | Active | Log | Upd | SN-0587 | New | Approved | 2020-05-14 16:37 | Updated 12 Need by dates
BWM_DNP_MSSA_Spectrum Phase II Start | CA | ORG | DNP | Bandwidth Management | BWM CA ORG DNP MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-01-27 | 2020-03-13 | Active | EP
BWM_DNP_MSSA_Spectrum Phase II Start | CA | ORG | DNP | Bandwidth Management | BWM CA ORG DNP MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2019-09-20 |  | Active | Log | New | SN-0055 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_DNP_MSSA_Spectrum Phase II Start | CA | ORG | DNP | Bandwidth Management | BWM CA ORG DNP MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_DNP_MSSA_Spectrum Phase II Start | CA | ORG | DNP | Bandwidth Management | BWM CA ORG DNP MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-01-27 | 2020-03-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_DNP_MSSA_Spectrum Phase II Start | CA | ORG | DNP | Bandwidth Management | BWM CA ORG DNP MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-01-27 | 2020-03-13 | Active | Log | Upd | SN-0587 | New | Approved | 2020-05-14 16:37 | Updated 12 Need by dates
BWM_BRD_VIDEO SG_2020 DOCSIS node split-based Video SG Calculations per facility | CE | OMA | ELK | Bandwidth Management | BWM CE OMA ONA VIDEO SG Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_BRD_VIDEO SG_2020 DOCSIS node split-based Video SG Calculations per facility | CE | OMA | ELK | Bandwidth Management | BWM CE OMA ONA VIDEO SG Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0413 | New | Approved | 2020-04-02 09:42 | Remove three VSG projects that were removed via manual POR, but also needs to be removed from process and DB
BWM_QNC_MSSA_Spectrum Phase II Start | CE | TUL | QNC | Bandwidth Management | BWM CE TUL QNC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-06-11 | Active | EP
BWM_QNC_MSSA_Spectrum Phase II Start | CE | TUL | QNC | Bandwidth Management | BWM CE TUL QNC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_QNC_MSSA_Spectrum Phase II Start | CE | TUL | QNC | Bandwidth Management | BWM CE TUL QNC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-07-31 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_QNC_MSSA_Spectrum Phase II Start | CE | TUL | QNC | Bandwidth Management | BWM CE TUL QNC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-07-31 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_QNC_MSSA_Spectrum Phase II Start | CE | TUL | QNC | Bandwidth Management | BWM CE TUL QNC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-06-11 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_SAP_MSSA_Spectrum Phase II Start | CE | TUL | SAP | Bandwidth Management | BWM CE TUL SAP MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-06-11 | Active | EP
BWM_SAP_MSSA_Spectrum Phase II Start | CE | TUL | SAP | Bandwidth Management | BWM CE TUL SAP MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_SAP_MSSA_Spectrum Phase II Start | CE | TUL | SAP | Bandwidth Management | BWM CE TUL SAP MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-07-31 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_SAP_MSSA_Spectrum Phase II Start | CE | TUL | SAP | Bandwidth Management | BWM CE TUL SAP MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-07-31 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_SAP_MSSA_Spectrum Phase II Start | CE | TUL | SAP | Bandwidth Management | BWM CE TUL SAP MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-06-11 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_TUL_MSSA_Spectrum Phase II Start | CE | TUL | TUL | Bandwidth Management | BWM CE TUL TUL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-06-11 | Active | EP
BWM_TUL_MSSA_Spectrum Phase II Start | CE | TUL | TUL | Bandwidth Management | BWM CE TUL TUL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_TUL_MSSA_Spectrum Phase II Start | CE | TUL | TUL | Bandwidth Management | BWM CE TUL TUL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-07-31 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_TUL_MSSA_Spectrum Phase II Start | CE | TUL | TUL | Bandwidth Management | BWM CE TUL TUL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-07-31 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_TUL_MSSA_Spectrum Phase II Start | CE | TUL | TUL | Bandwidth Management | BWM CE TUL TUL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-06-11 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_ENF_VIDEO SG_2020 DOCSIS node split-based Video SG | NE | CON | ENF | Bandwidth Management | BWM NE CON ENF VIDEO SG Augment POR20 v3 | Labor | No Equipment | 1 | 2020-10-01 | 2020-12-15 | 2020-12-15 | Active | EP
BWM_GLB_MSSA_Spectrum Phase II Start | NE | CON | GLB | Bandwidth Management | BWM NE CON GLB MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-27 | Active | EP
BWM_GLB_MSSA_Spectrum Phase II Start | NE | CON | GLB | Bandwidth Management | BWM NE CON GLB MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_GLB_MSSA_Spectrum Phase II Start | NE | CON | GLB | Bandwidth Management | BWM NE CON GLB MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_GLB_MSSA_Spectrum Phase II Start | NE | CON | GLB | Bandwidth Management | BWM NE CON GLB MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-11-13 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_GLB_MSSA_Spectrum Phase II Start | NE | CON | GLB | Bandwidth Management | BWM NE CON GLB MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-27 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_GLB_VIDEO SG_2020 DOCSIS node split-based Video SG | NE | CON | GLB | Bandwidth Management | BWM NE CON GLB VIDEO SG Augment POR20 v2 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-17 | 2020-11-13 | Active | EP
BWM_GLB_VIDEO SG_2020 DOCSIS node split-based Video SG | NE | CON | GLB | Bandwidth Management | BWM NE CON GLB VIDEO SG Augment POR20 v2 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_GRB_MSSA_Spectrum Phase II Start | NE | CON | GRB | Bandwidth Management | BWM NE CON GRB MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-27 | Active | EP
BWM_GRB_MSSA_Spectrum Phase II Start | NE | CON | GRB | Bandwidth Management | BWM NE CON GRB MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_GRB_MSSA_Spectrum Phase II Start | NE | CON | GRB | Bandwidth Management | BWM NE CON GRB MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_GRB_MSSA_Spectrum Phase II Start | NE | CON | GRB | Bandwidth Management | BWM NE CON GRB MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-11-13 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_GRB_MSSA_Spectrum Phase II Start | NE | CON | GRB | Bandwidth Management | BWM NE CON GRB MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-27 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_MAN_MSSA_Spectrum Phase II Start | NE | CON | MAN | Bandwidth Management | BWM NE CON MAN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-27 | Active | EP
BWM_MAN_MSSA_Spectrum Phase II Start | NE | CON | MAN | Bandwidth Management | BWM NE CON MAN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_MAN_MSSA_Spectrum Phase II Start | NE | CON | MAN | Bandwidth Management | BWM NE CON MAN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_MAN_MSSA_Spectrum Phase II Start | NE | CON | MAN | Bandwidth Management | BWM NE CON MAN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-11-13 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_MAN_MSSA_Spectrum Phase II Start | NE | CON | MAN | Bandwidth Management | BWM NE CON MAN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-27 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_MAN_VIDEO SG_2020 DOCSIS node split-based Video SG | NE | CON | MAN | Bandwidth Management | BWM NE CON MAN Video SG Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-01 | 2020-03-01 | Active | EP
BWM_MAN_VIDEO SG_2020 DOCSIS node split-based Video SG | NE | CON | MAN | Bandwidth Management | BWM NE CON MAN Video SG Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-01 | 2020-03-01 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_MER_MSSA_Spectrum Phase II Start | NE | CON | MER | Bandwidth Management | BWM NE CON MER MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-27 | Active | EP
BWM_MER_MSSA_Spectrum Phase II Start | NE | CON | MER | Bandwidth Management | BWM NE CON MER MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_MER_MSSA_Spectrum Phase II Start | NE | CON | MER | Bandwidth Management | BWM NE CON MER MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_MER_MSSA_Spectrum Phase II Start | NE | CON | MER | Bandwidth Management | BWM NE CON MER MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-11-13 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_MER_MSSA_Spectrum Phase II Start | NE | CON | MER | Bandwidth Management | BWM NE CON MER MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-27 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_MER_VIDEO SG_2020 DOCSIS node split-based Video SG | NE | CON | MER | Bandwidth Management | BWM NE CON MER VIDEO SG Augment POR20 v2 | Labor | No Equipment | 1 | 2020-10-01 | 2020-12-15 | 2020-12-15 | Active | EP
BWM_RKH_MSSA_Spectrum Phase II Start | NE | CON | RKH | Bandwidth Management | BWM NE CON RKH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-27 | Active | EP
BWM_RKH_MSSA_Spectrum Phase II Start | NE | CON | RKH | Bandwidth Management | BWM NE CON RKH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_RKH_MSSA_Spectrum Phase II Start | NE | CON | RKH | Bandwidth Management | BWM NE CON RKH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-11-13 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_RKH_MSSA_Spectrum Phase II Start | NE | CON | RKH | Bandwidth Management | BWM NE CON RKH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-27 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_RKH_VIDEO SG_2020 DOCSIS node split-based Video SG | NE | CON | RKH | Bandwidth Management | BWM NE CON RKH VIDEO SG Augment POR20 v3 | Labor | No Equipment | 1 | 2020-10-01 | 2020-12-15 | 2020-12-15 | Active | EP
BWM_STN_MSSA_Spectrum Phase II Start | NE | CON | STN | Bandwidth Management | BWM NE CON STN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-27 | Active | EP
BWM_STN_MSSA_Spectrum Phase II Start | NE | CON | STN | Bandwidth Management | BWM NE CON STN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_STN_MSSA_Spectrum Phase II Start | NE | CON | STN | Bandwidth Management | BWM NE CON STN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-11-13 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_STN_MSSA_Spectrum Phase II Start | NE | CON | STN | Bandwidth Management | BWM NE CON STN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-27 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_SFD_MSSA_Spectrum Phase II Start | NE | CON | SFD | Bandwidth Management | BWM NE CON SFD MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-27 | Active | EP
BWM_SFD_MSSA_Spectrum Phase II Start | NE | CON | SFD | Bandwidth Management | BWM NE CON SFD MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_SFD_MSSA_Spectrum Phase II Start | NE | CON | SFD | Bandwidth Management | BWM NE CON SFD MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-11-13 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_SFD_MSSA_Spectrum Phase II Start | NE | CON | SFD | Bandwidth Management | BWM NE CON SFD MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-27 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_BUR_MSSA_Spectrum Phase II Start | NE | RHD | BUR | Bandwidth Management | BWM NE RHD BUR MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-07-08 | Active | EP
BWM_BUR_MSSA_Spectrum Phase II Start | NE | RHD | BUR | Bandwidth Management | BWM NE RHD BUR MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_BUR_MSSA_Spectrum Phase II Start | NE | RHD | BUR | Bandwidth Management | BWM NE RHD BUR MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_BUR_MSSA_Spectrum Phase II Start | NE | RHD | BUR | Bandwidth Management | BWM NE RHD BUR MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-08-28 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_BUR_MSSA_Spectrum Phase II Start | NE | RHD | BUR | Bandwidth Management | BWM NE RHD BUR MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-07-08 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_BUR_DGS_Spectrum Phase III_48 MHZ | NE | RHD | BUR | Bandwidth Management | BWM NE RHD BUR DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_BUR_DGS_Spectrum Phase III_48 MHZ | NE | RHD | BUR | Bandwidth Management | BWM NE RHD BUR DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_BUR_DGS_Spectrum Phase III_48 MHZ | NE | RHD | BUR | Bandwidth Management | BWM NE RHD BUR DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_WLH_MSSA_Spectrum Phase II Start | CE | OKC | WLH | Bandwidth Management | BWM CE OKC WLH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | Active | EP
BWM_WLH_MSSA_Spectrum Phase II Start | CE | OKC | WLH | Bandwidth Management | BWM CE OKC WLH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_WLH_MSSA_Spectrum Phase II Start | CE | OKC | WLH | Bandwidth Management | BWM CE OKC WLH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_WLH_MSSA_Spectrum Phase II Start | CE | OKC | WLH | Bandwidth Management | BWM CE OKC WLH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-10-23 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_WLH_MSSA_Spectrum Phase II Start | CE | OKC | WLH | Bandwidth Management | BWM CE OKC WLH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_WLH_DGS_Spectrum Phase III_48 MHZ | CE | OKC | WLH | Bandwidth Management | BWM CE OKC WLH DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_WLH_DGS_Spectrum Phase III_48 MHZ | CE | OKC | WLH | Bandwidth Management | BWM CE OKC WLH DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_WLH_DGS_Spectrum Phase III_48 MHZ | CE | OKC | WLH | Bandwidth Management | BWM CE OKC WLH DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_WLH_DGS_Spectrum Phase III_96 MHZ | CE | OKC | WLH | Bandwidth Management | BWM CE OKC WLH DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_WLH_DGS_Spectrum Phase III_96 MHZ | CE | OKC | WLH | Bandwidth Management | BWM CE OKC WLH DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_WLH_DGS_Spectrum Phase III_96 MHZ | CE | OKC | WLH | Bandwidth Management | BWM CE OKC WLH DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_WEH_MSSA_Spectrum Phase II Start | CE | OKC | WEH | Bandwidth Management | BWM CE OKC WEH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | Active | EP
BWM_WEH_MSSA_Spectrum Phase II Start | CE | OKC | WEH | Bandwidth Management | BWM CE OKC WEH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_WEH_MSSA_Spectrum Phase II Start | CE | OKC | WEH | Bandwidth Management | BWM CE OKC WEH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_WEH_MSSA_Spectrum Phase II Start | CE | OKC | WEH | Bandwidth Management | BWM CE OKC WEH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-10-23 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_WEH_MSSA_Spectrum Phase II Start | CE | OKC | WEH | Bandwidth Management | BWM CE OKC WEH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_WEH_DGS_Spectrum Phase III_48 MHZ | CE | OKC | WEH | Bandwidth Management | BWM CE OKC WEH DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_WEH_DGS_Spectrum Phase III_48 MHZ | CE | OKC | WEH | Bandwidth Management | BWM CE OKC WEH DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_WEH_DGS_Spectrum Phase III_48 MHZ | CE | OKC | WEH | Bandwidth Management | BWM CE OKC WEH DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_WEH_DGS_Spectrum Phase III_96 MHZ | CE | OKC | WEH | Bandwidth Management | BWM CE OKC WEH DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_WEH_DGS_Spectrum Phase III_96 MHZ | CE | OKC | WEH | Bandwidth Management | BWM CE OKC WEH DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_WEH_DGS_Spectrum Phase III_96 MHZ | CE | OKC | WEH | Bandwidth Management | BWM CE OKC WEH DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_YAL_MSSA_Spectrum Phase II Start | CE | TUL | YAL | Bandwidth Management | BWM CE TUL YAL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-06-11 | Active | EP
BWM_YAL_MSSA_Spectrum Phase II Start | CE | TUL | YAL | Bandwidth Management | BWM CE OKC WEH MSSA Augment POR20 v4 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_YAL_MSSA_Spectrum Phase II Start | CE | TUL | YAL | Bandwidth Management | BWM CE TUL YAL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-07-31 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_YAL_MSSA_Spectrum Phase II Start | CE | TUL | YAL | Bandwidth Management | BWM CE TUL YAL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-07-31 | Active | Log | Upd | SN-0473 | New | Approved | 2020-04-17 16:09 | 4 projects are showing the incorrect project name on the POR, making the correction on this CR
BWM_YAL_MSSA_Spectrum Phase II Start | CE | TUL | YAL | Bandwidth Management | BWM CE TUL YAL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-07-31 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_YAL_MSSA_Spectrum Phase II Start | CE | TUL | YAL | Bandwidth Management | BWM CE TUL YAL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-06-11 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_ENF_MSSA_Spectrum Phase II Start | NE | CON | ENF | Bandwidth Management | BWM NE CON ENF MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-27 | Active | EP
BWM_ENF_MSSA_Spectrum Phase II Start | NE | CON | ENF | Bandwidth Management | BWM NE CON ENF MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_ENF_MSSA_Spectrum Phase II Start | NE | CON | ENF | Bandwidth Management | BWM NE CON ENF MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_ENF_MSSA_Spectrum Phase II Start | NE | CON | ENF | Bandwidth Management | BWM NE CON ENF MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-11-13 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_ENF_MSSA_Spectrum Phase II Start | NE | CON | ENF | Bandwidth Management | BWM NE CON ENF MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-27 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_CRN_MSSA_Spectrum Phase II Start | NE | RHD | CRN | Bandwidth Management | BWM NE RHD CRN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-07-08 | Active | EP
BWM_CRN_MSSA_Spectrum Phase II Start | NE | RHD | CRN | Bandwidth Management | BWM NE RHD CRN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_CRN_MSSA_Spectrum Phase II Start | NE | RHD | CRN | Bandwidth Management | BWM NE RHD CRN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_CRN_MSSA_Spectrum Phase II Start | NE | RHD | CRN | Bandwidth Management | BWM NE RHD CRN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-08-28 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_CRN_MSSA_Spectrum Phase II Start | NE | RHD | CRN | Bandwidth Management | BWM NE RHD CRN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-07-08 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_CRN_DGS_Spectrum Phase III_48 MHZ | NE | RHD | CRN | Bandwidth Management | BWM NE RHD CRN DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_CRN_DGS_Spectrum Phase III_48 MHZ | NE | RHD | CRN | Bandwidth Management | BWM NE RHD CRN DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_CRN_DGS_Spectrum Phase III_48 MHZ | NE | RHD | CRN | Bandwidth Management | BWM NE RHD CRN DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_CRN_VIDEO SG_2020 DOCSIS node split-based Video SG | NE | RHD | CRN | Bandwidth Management | BWM NE RHD CRN VIDEO SG Augment POR20 v3 | Labor | No Equipment | 1 | 2020-10-01 | 2020-12-15 | 2020-12-15 | Active | EP
BWM_EXT_MSSA_Spectrum Phase II Start | NE | RHD | EXT | Bandwidth Management | BWM NE RHD EXT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-07-08 | Active | EP
BWM_EXT_MSSA_Spectrum Phase II Start | NE | RHD | EXT | Bandwidth Management | BWM NE RHD EXT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_EXT_MSSA_Spectrum Phase II Start | NE | RHD | EXT | Bandwidth Management | BWM NE RHD EXT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_EXT_MSSA_Spectrum Phase II Start | NE | RHD | EXT | Bandwidth Management | BWM NE RHD EXT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-08-28 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_EXT_MSSA_Spectrum Phase II Start | NE | RHD | EXT | Bandwidth Management | BWM NE RHD EXT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-07-08 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_EXT_DGS_Spectrum Phase III_48 MHZ | NE | RHD | EXT | Bandwidth Management | BWM NE RHD EXT DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_EXT_DGS_Spectrum Phase III_48 MHZ | NE | RHD | EXT | Bandwidth Management | BWM NE RHD EXT DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_EXT_DGS_Spectrum Phase III_48 MHZ | NE | RHD | EXT | Bandwidth Management | BWM NE RHD EXT DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_LNC_MSSA_Spectrum Phase II Start | NE | RHD | LNC | Bandwidth Management | BWM NE RHD LNC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-07-08 | Active | EP
BWM_LNC_MSSA_Spectrum Phase II Start | NE | RHD | LNC | Bandwidth Management | BWM NE RHD LNC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_LNC_MSSA_Spectrum Phase II Start | NE | RHD | LNC | Bandwidth Management | BWM NE RHD LNC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_LNC_MSSA_Spectrum Phase II Start | NE | RHD | LNC | Bandwidth Management | BWM NE RHD LNC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-08-28 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_LNC_MSSA_Spectrum Phase II Start | NE | RHD | LNC | Bandwidth Management | BWM NE RHD LNC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-07-08 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_LNC_DGS_Spectrum Phase III_48 MHZ | NE | RHD | LNC | Bandwidth Management | BWM NE RHD LNC DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_LNC_DGS_Spectrum Phase III_48 MHZ | NE | RHD | LNC | Bandwidth Management | BWM NE RHD LNC DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_LNC_DGS_Spectrum Phase III_48 MHZ | NE | RHD | LNC | Bandwidth Management | BWM NE RHD LNC DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_LNC_VIDEO SG_2020 DOCSIS node split-based Video SG | NE | RHD | LNC | Bandwidth Management | BWM NE RHD LNC VIDEO SG Augment POR20 v3 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-15 | 2020-09-15 | Active | EP
BWM_PAW_MSSA_Spectrum Phase II Start | NE | RHD | PAW | Bandwidth Management | BWM NE RHD PAW MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-07-08 | Active | EP
BWM_PAW_MSSA_Spectrum Phase II Start | NE | RHD | PAW | Bandwidth Management | BWM NE RHD PAW MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_PAW_MSSA_Spectrum Phase II Start | NE | RHD | PAW | Bandwidth Management | BWM NE RHD PAW MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_PAW_MSSA_Spectrum Phase II Start | NE | RHD | PAW | Bandwidth Management | BWM NE RHD PAW MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-08-28 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_PAW_MSSA_Spectrum Phase II Start | NE | RHD | PAW | Bandwidth Management | BWM NE RHD PAW MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-07-08 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_PAW_DGS_Spectrum Phase III_48 MHZ | NE | RHD | PAW | Bandwidth Management | BWM NE RHD PAW DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_PAW_DGS_Spectrum Phase III_48 MHZ | NE | RHD | PAW | Bandwidth Management | BWM NE RHD PAW DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_PAW_DGS_Spectrum Phase III_48 MHZ | NE | RHD | PAW | Bandwidth Management | BWM NE RHD PAW DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_PAW_VIDEO SG_2020 DOCSIS node split-based Video SG | NE | RHD | PAW | Bandwidth Management | BWM NE RHD PAW VIDEO SG Augment POR20 v3 | Labor | No Equipment | 1 | 2020-10-01 | 2020-12-15 | 2020-12-15 | Active | EP
BWM_PTH_MSSA_Spectrum Phase II Start | NE | RHD | PTH | Bandwidth Management | BWM NE RHD PTH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-07-08 | Active | EP
BWM_PTH_MSSA_Spectrum Phase II Start | NE | RHD | PTH | Bandwidth Management | BWM NE RHD PTH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_PTH_MSSA_Spectrum Phase II Start | NE | RHD | PTH | Bandwidth Management | BWM NE RHD PTH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_PTH_MSSA_Spectrum Phase II Start | NE | RHD | PTH | Bandwidth Management | BWM NE RHD PTH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-08-28 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_PTH_MSSA_Spectrum Phase II Start | NE | RHD | PTH | Bandwidth Management | BWM NE RHD PTH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-07-08 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_PTH_DGS_Spectrum Phase III_48 MHZ | NE | RHD | PTH | Bandwidth Management | BWM NE RHD PTH DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_PTH_DGS_Spectrum Phase III_48 MHZ | NE | RHD | PTH | Bandwidth Management | BWM NE RHD PTH DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_PTH_DGS_Spectrum Phase III_48 MHZ | NE | RHD | PTH | Bandwidth Management | BWM NE RHD PTH DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_PTH_VIDEO SG_2020 DOCSIS node split-based Video SG | NE | RHD | PTH | Bandwidth Management | BWM NE RHD PTH VIDEO SG Augment POR20 v3 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-15 | 2020-09-15 | Active | EP
BWM_PRV_MSSA_Spectrum Phase II Start | NE | RHD | PRV | Bandwidth Management | BWM NE RHD PRV MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-07-08 | Active | EP
BWM_PRV_MSSA_Spectrum Phase II Start | NE | RHD | PRV | Bandwidth Management | BWM NE RHD PRV MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_PRV_MSSA_Spectrum Phase II Start | NE | RHD | PRV | Bandwidth Management | BWM NE RHD PRV MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_PRV_MSSA_Spectrum Phase II Start | NE | RHD | PRV | Bandwidth Management | BWM NE RHD PRV MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-08-28 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_PRV_MSSA_Spectrum Phase II Start | NE | RHD | PRV | Bandwidth Management | BWM NE RHD PRV MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-07-08 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_PRV_DGS_Spectrum Phase III_48 MHZ | NE | RHD | PRV | Bandwidth Management | BWM NE RHD PRV DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_PRV_DGS_Spectrum Phase III_48 MHZ | NE | RHD | PRV | Bandwidth Management | BWM NE RHD PRV DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_PRV_DGS_Spectrum Phase III_48 MHZ | NE | RHD | PRV | Bandwidth Management | BWM NE RHD PRV DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_YAL_DGS_Spectrum Phase III_48 MHZ | CE | TUL | YAL | Bandwidth Management | BWM CE TUL YAL DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_YAL_DGS_Spectrum Phase III_48 MHZ | CE | TUL | YAL | Bandwidth Management | BWM CE TUL YAL DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_YAL_DGS_Spectrum Phase III_48 MHZ | CE | TUL | YAL | Bandwidth Management | BWM CE TUL YAL DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_YAL_DGS_Spectrum Phase III_96 MHZ | CE | TUL | YAL | Bandwidth Management | BWM CE TUL YAL DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_YAL_DGS_Spectrum Phase III_96 MHZ | CE | TUL | YAL | Bandwidth Management | BWM CE TUL YAL DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_YAL_DGS_Spectrum Phase III_96 MHZ | CE | TUL | YAL | Bandwidth Management | BWM CE TUL YAL DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_BLV_MSSA_Spectrum Phase II Start | CE | OMA | BLV | Bandwidth Management | BWM CE OMA BLV MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-09-10 | Active | EP
BWM_BLV_MSSA_Spectrum Phase II Start | CE | OMA | BLV | Bandwidth Management | BWM CE OMA BLV MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_BLV_MSSA_Spectrum Phase II Start | CE | OMA | BLV | Bandwidth Management | BWM CE OMA BLV MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_BLV_MSSA_Spectrum Phase II Start | CE | OMA | BLV | Bandwidth Management | BWM CE OMA BLV MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-08-31 | 2020-11-13 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_BLV_MSSA_Spectrum Phase II Start | CE | OMA | BLV | Bandwidth Management | BWM CE OMA BLV MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-09-10 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_BLV_DGS_Spectrum Phase III_48 MHZ | CE | OMA | BLV | Bandwidth Management | BWM CE OMA BLV DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_BLV_DGS_Spectrum Phase III_48 MHZ | CE | OMA | BLV | Bandwidth Management | BWM CE OMA BLV DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_BLV_DGS_Spectrum Phase III_48 MHZ | CE | OMA | BLV | Bandwidth Management | BWM CE OMA BLV DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_BLV_DGS_Spectrum Phase III_96 MHZ | CE | OMA | BLV | Bandwidth Management | BWM CE OMA BLV DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_BLV_DGS_Spectrum Phase III_96 MHZ | CE | OMA | BLV | Bandwidth Management | BWM CE OMA BLV DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_BLV_DGS_Spectrum Phase III_96 MHZ | CE | OMA | BLV | Bandwidth Management | BWM CE OMA BLV DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_BLV_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | OMA | BLV | Bandwidth Management | BWM CE OMA BLV VIDEO SG Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-15 | 2020-09-15 | Active | EP
BWM_CBL_MSSA_Spectrum Phase II Start | CE | OMA | CBL | Bandwidth Management | BWM CE OMA CBL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-09-10 | Active | EP
BWM_CBL_MSSA_Spectrum Phase II Start | CE | OMA | CBL | Bandwidth Management | BWM CE OMA CBL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_CBL_MSSA_Spectrum Phase II Start | CE | OMA | CBL | Bandwidth Management | BWM CE OMA CBL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_CBL_MSSA_Spectrum Phase II Start | CE | OMA | CBL | Bandwidth Management | BWM CE OMA CBL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-11-13 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_CBL_MSSA_Spectrum Phase II Start | CE | OMA | CBL | Bandwidth Management | BWM CE OMA CBL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-09-10 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_CBL_DGS_Spectrum Phase III_48 MHZ | CE | OMA | CBL | Bandwidth Management | BWM CE OMA CBL DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_CBL_DGS_Spectrum Phase III_48 MHZ | CE | OMA | CBL | Bandwidth Management | BWM CE OMA CBL DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_CBL_DGS_Spectrum Phase III_48 MHZ | CE | OMA | CBL | Bandwidth Management | BWM CE OMA CBL DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_CBL_DGS_Spectrum Phase III_96 MHZ | CE | OMA | CBL | Bandwidth Management | BWM CE OMA CBL DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_CBL_DGS_Spectrum Phase III_96 MHZ | CE | OMA | CBL | Bandwidth Management | BWM CE OMA CBL DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_CBL_DGS_Spectrum Phase III_96 MHZ | CE | OMA | CBL | Bandwidth Management | BWM CE OMA CBL DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_ELK_MSSA_Spectrum Phase II Start | CE | OMA | ELK | Bandwidth Management | BWM CE OMA ELK MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-09-10 | Active | EP
BWM_ELK_MSSA_Spectrum Phase II Start | CE | OMA | ELK | Bandwidth Management | BWM CE OMA ELK MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_ELK_MSSA_Spectrum Phase II Start | CE | OMA | ELK | Bandwidth Management | BWM CE OMA ELK MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_ELK_MSSA_Spectrum Phase II Start | CE | OMA | ELK | Bandwidth Management | BWM CE OMA ELK MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-11-13 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_ELK_MSSA_Spectrum Phase II Start | CE | OMA | ELK | Bandwidth Management | BWM CE OMA ELK MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-09-10 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_ELK_DGS_Spectrum Phase III_48 MHZ | CE | OMA | ELK | Bandwidth Management | BWM CE OMA ELK DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_ELK_DGS_Spectrum Phase III_48 MHZ | CE | OMA | ELK | Bandwidth Management | BWM CE OMA ELK DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_ELK_DGS_Spectrum Phase III_48 MHZ | CE | OMA | ELK | Bandwidth Management | BWM CE OMA ELK DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_ELK_DGS_Spectrum Phase III_96 MHZ | CE | OMA | ELK | Bandwidth Management | BWM CE OMA ELK DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_ELK_DGS_Spectrum Phase III_96 MHZ | CE | OMA | ELK | Bandwidth Management | BWM CE OMA ELK DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_ELK_DGS_Spectrum Phase III_96 MHZ | CE | OMA | ELK | Bandwidth Management | BWM CE OMA ELK DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_ONA_MSSA_Spectrum Phase II Start | CE | OMA | ONA | Bandwidth Management | BWM CE OMA ONA MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-09-10 | Active | EP
BWM_ONA_MSSA_Spectrum Phase II Start | CE | OMA | ONA | Bandwidth Management | BWM CE OMA ONA MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_ONA_MSSA_Spectrum Phase II Start | CE | OMA | ONA | Bandwidth Management | BWM CE OMA ONA MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_ONA_MSSA_Spectrum Phase II Start | CE | OMA | ONA | Bandwidth Management | BWM CE OMA ONA MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-11-13 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_ONA_MSSA_Spectrum Phase II Start | CE | OMA | ONA | Bandwidth Management | BWM CE OMA ONA MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-09-10 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_ONA_DGS_Spectrum Phase III_48 MHZ | CE | OMA | ONA | Bandwidth Management | BWM CE OMA ONA DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_ONA_DGS_Spectrum Phase III_48 MHZ | CE | OMA | ONA | Bandwidth Management | BWM CE OMA ONA DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_ONA_DGS_Spectrum Phase III_48 MHZ | CE | OMA | ONA | Bandwidth Management | BWM CE OMA ONA DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_ONA_DGS_Spectrum Phase III_96 MHZ | CE | OMA | ONA | Bandwidth Management | BWM CE OMA ONA DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_ONA_DGS_Spectrum Phase III_96 MHZ | CE | OMA | ONA | Bandwidth Management | BWM CE OMA ONA DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_ONA_DGS_Spectrum Phase III_96 MHZ | CE | OMA | ONA | Bandwidth Management | BWM CE OMA ONA DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_ONA_VIDEO SG_2020 DOCSIS node split-based Video SG Dup | CE | OMA | ONA | Bandwidth Management | BWM CE OMA ONA VIDEO SG Augment POR20 v4 | Labor | No Equipment | 1 | 2020-10-01 | 2020-12-15 | 2020-12-15 | Deleted | EP
BWM_ONA_VIDEO SG_2020 DOCSIS node split-based Video SG Dup1 | CE | OMA | ONA | Bandwidth Management | BWM CE OMA ONA VIDEO SG Augment POR20 v5 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_ONA_VIDEO SG_2020 DOCSIS node split-based Video SG Dup1 | CE | OMA | ONA | Bandwidth Management | BWM CE OMA ONA VIDEO SG Augment POR20 v5 | Labor | No Equipment | 1 |  | 2020-09-30 | 2020-09-30 | Deleted | Log | Upd | SN-0245 | Schedule Change | Approved | 2020-02-24 12:37 | 59 projects were made inactive on CR SN-0195 in error, I m reactivating these projects and VSG submited an revised plan 14 VSG projects removed and shifting some dates for the remaining projects
BWM_ONA_VIDEO SG_2020 DOCSIS node split-based Video SG Dup1 | CE | OMA | ONA | Bandwidth Management | BWM CE OMA ONA VIDEO SG Augment POR20 v5 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0413 | New | Approved | 2020-04-02 09:42 | Remove three VSG projects that were removed via manual POR, but also needs to be removed from process and DB
BWM_SOU_MSSA_Spectrum Phase II Start | CE | OMA | SOU | Bandwidth Management | BWM CE OMA SOU MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-09-10 | Active | EP
BWM_SOU_MSSA_Spectrum Phase II Start | CE | OMA | SOU | Bandwidth Management | BWM CE OMA SOU MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_SOU_MSSA_Spectrum Phase II Start | CE | OMA | SOU | Bandwidth Management | BWM CE OMA SOU MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_SOU_MSSA_Spectrum Phase II Start | CE | OMA | SOU | Bandwidth Management | BWM CE OMA SOU MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-11-13 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_SOU_MSSA_Spectrum Phase II Start | CE | OMA | SOU | Bandwidth Management | BWM CE OMA SOU MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-09-10 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_SOU_DGS_Spectrum Phase III_48 MHZ | CE | OMA | SOU | Bandwidth Management | BWM CE OMA SOU DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_SOU_DGS_Spectrum Phase III_48 MHZ | CE | OMA | SOU | Bandwidth Management | BWM CE OMA SOU DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_SOU_DGS_Spectrum Phase III_48 MHZ | CE | OMA | SOU | Bandwidth Management | BWM CE OMA SOU DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_SOU_DGS_Spectrum Phase III_96 MHZ | CE | OMA | SOU | Bandwidth Management | BWM CE OMA SOU DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_SOU_DGS_Spectrum Phase III_96 MHZ | CE | OMA | SOU | Bandwidth Management | BWM CE OMA SOU DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_SOU_DGS_Spectrum Phase III_96 MHZ | CE | OMA | SOU | Bandwidth Management | BWM CE OMA SOU DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_SOU_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | OMA | SOU | Bandwidth Management | BWM CE OMA SOU VIDEO SG Augment POR20 v5 | Labor | No Equipment | 1 | 2020-10-01 | 2020-12-15 | 2020-12-15 | Active | EP
BWM_SVI_MSSA_Spectrum Phase II Start | CE | SUN | SVI | Bandwidth Management | BWM CE SUN SVI MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | EP
BWM_SVI_MSSA_Spectrum Phase II Start | CE | SUN | SVI | Bandwidth Management | BWM CE SUN SVI MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_SVI_DGS_Spectrum Phase III_48 MHZ | CE | SUN | SVI | Bandwidth Management | BWM CE SUN SVI DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_SVI_DGS_Spectrum Phase III_48 MHZ | CE | SUN | SVI | Bandwidth Management | BWM CE SUN SVI DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_SVI_DGS_Spectrum Phase III_48 MHZ | CE | SUN | SVI | Bandwidth Management | BWM CE SUN SVI DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_SVI_DGS_Spectrum Phase III_96 MHZ | CE | SUN | SVI | Bandwidth Management | BWM CE SUN SVI DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_SVI_DGS_Spectrum Phase III_96 MHZ | CE | SUN | SVI | Bandwidth Management | BWM CE SUN SVI DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_SVI_DGS_Spectrum Phase III_96 MHZ | CE | SUN | SVI | Bandwidth Management | BWM CE SUN SVI DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_WES_MSSA_Spectrum Phase II Start | CE | OMA | WES | Bandwidth Management | BWM CE OMA WES MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-09-10 | Active | EP
BWM_WES_MSSA_Spectrum Phase II Start | CE | OMA | WES | Bandwidth Management | BWM CE OMA WES MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_WES_MSSA_Spectrum Phase II Start | CE | OMA | WES | Bandwidth Management | BWM CE OMA WES MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_WES_MSSA_Spectrum Phase II Start | CE | OMA | WES | Bandwidth Management | BWM CE OMA WES MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-11-13 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_WES_MSSA_Spectrum Phase II Start | CE | OMA | WES | Bandwidth Management | BWM CE OMA WES MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-09-10 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_WES_DGS_Spectrum Phase III_48 MHZ | CE | OMA | WES | Bandwidth Management | BWM CE OMA WES DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_WES_DGS_Spectrum Phase III_48 MHZ | CE | OMA | WES | Bandwidth Management | BWM CE OMA WES DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_WES_DGS_Spectrum Phase III_48 MHZ | CE | OMA | WES | Bandwidth Management | BWM CE OMA WES DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_WES_DGS_Spectrum Phase III_96 MHZ | CE | OMA | WES | Bandwidth Management | BWM CE OMA WES DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_WES_DGS_Spectrum Phase III_96 MHZ | CE | OMA | WES | Bandwidth Management | BWM CE OMA WES DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_WES_DGS_Spectrum Phase III_96 MHZ | CE | OMA | WES | Bandwidth Management | BWM CE OMA WES DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_WES_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | OMA | WES | Bandwidth Management | BWM CE OMA WES VIDEO SG Augment POR20 v4 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-15 | 2020-09-15 | Active | EP
BWM_CLV_MSSA_Spectrum Phase II Start | NE | CLE | CLV | Bandwidth Management | BWM NE CLE CLV MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-24 | 2020-06-10 | Active | EP
BWM_CLV_MSSA_Spectrum Phase II Start | NE | CLE | CLV | Bandwidth Management | BWM NE CLE CLV MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_CLV_MSSA_Spectrum Phase II Start | NE | CLE | CLV | Bandwidth Management | BWM NE CLE CLV MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_CLV_MSSA_Spectrum Phase II Start | NE | CLE | CLV | Bandwidth Management | BWM NE CLE CLV MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-08-14 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_CLV_MSSA_Spectrum Phase II Start | NE | CLE | CLV | Bandwidth Management | BWM NE CLE CLV MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-24 | 2020-06-10 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_CLV_VIDEO SG_2020 DOCSIS node split-based Video SG | NE | CLE | CLV | Bandwidth Management | BWM NE CLE CLV VIDEO SG Augment POR20 v2 | Labor | No Equipment | 1 |  | 2020-09-30 | 2020-09-30 | Active | EP
BWM_CLV_VIDEO SG_2020 DOCSIS node split-based Video SG | NE | CLE | CLV | Bandwidth Management | BWM NE CLE CLV VIDEO SG Augment POR20 v2 | Labor | No Equipment | 1 |  | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0245 | Schedule Change | Approved | 2020-02-24 12:37 | 59 projects were made inactive on CR SN-0195 in error, I m reactivating these projects and VSG submited an revised plan 14 VSG projects removed and shifting some dates for the remaining projects
BWM_OWA_MSSA_Spectrum Phase II Start | CE | TUL | OWA | Bandwidth Management | BWM CE TUL OWA MSSA Augment POR20 v2 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-06-11 | Active | EP
BWM_OWA_MSSA_Spectrum Phase II Start | CE | TUL | OWA | Bandwidth Management | BWM CE TUL OWA MSSA Augment POR20 v2 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_OWA_MSSA_Spectrum Phase II Start | CE | TUL | OWA | Bandwidth Management | BWM CE TUL OWA MSSA Augment POR20 v2 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-07-31 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_OWA_MSSA_Spectrum Phase II Start | CE | TUL | OWA | Bandwidth Management | BWM CE TUL OWA MSSA Augment POR20 v2 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-07-31 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_OWA_MSSA_Spectrum Phase II Start | CE | TUL | OWA | Bandwidth Management | BWM CE TUL OWA MSSA Augment POR20 v2 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-06-11 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_OWA_DGS_Spectrum Phase III_48 MHZ | CE | TUL | OWA | Bandwidth Management | BWM CE TUL OWA DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_OWA_DGS_Spectrum Phase III_48 MHZ | CE | TUL | OWA | Bandwidth Management | BWM CE TUL OWA DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_OWA_DGS_Spectrum Phase III_48 MHZ | CE | TUL | OWA | Bandwidth Management | BWM CE TUL OWA DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_OWA_DGS_Spectrum Phase III_96 MHZ | CE | TUL | OWA | Bandwidth Management | BWM CE TUL OWA DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_OWA_DGS_Spectrum Phase III_96 MHZ | CE | TUL | OWA | Bandwidth Management | BWM CE TUL OWA DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_OWA_DGS_Spectrum Phase III_96 MHZ | CE | TUL | OWA | Bandwidth Management | BWM CE TUL OWA DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_SEH_MSSA_Spectrum Phase II Start | CE | OKC | SEH | Bandwidth Management | BWM CE OKC SEH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | Active | EP
BWM_SEH_MSSA_Spectrum Phase II Start | CE | OKC | SEH | Bandwidth Management | BWM CE OKC SEH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_SEH_MSSA_Spectrum Phase II Start | CE | OKC | SEH | Bandwidth Management | BWM CE OKC SEH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_SEH_MSSA_Spectrum Phase II Start | CE | OKC | SEH | Bandwidth Management | BWM CE OKC SEH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-10-23 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_SEH_MSSA_Spectrum Phase II Start | CE | OKC | SEH | Bandwidth Management | BWM CE OKC SEH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_SEH_DGS_Spectrum Phase III_48 MHZ | CE | OKC | SEH | Bandwidth Management | BWM CE OKC SEH DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_SEH_DGS_Spectrum Phase III_48 MHZ | CE | OKC | SEH | Bandwidth Management | BWM CE OKC SEH DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_SEH_DGS_Spectrum Phase III_48 MHZ | CE | OKC | SEH | Bandwidth Management | BWM CE OKC SEH DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_SEH_DGS_Spectrum Phase III_96 MHZ | CE | OKC | SEH | Bandwidth Management | BWM CE OKC SEH DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_SEH_DGS_Spectrum Phase III_96 MHZ | CE | OKC | SEH | Bandwidth Management | BWM CE OKC SEH DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_SEH_DGS_Spectrum Phase III_96 MHZ | CE | OKC | SEH | Bandwidth Management | BWM CE OKC SEH DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_TUL_DGS_Spectrum Phase III_48 MHZ | CE | TUL | TUL | Bandwidth Management | BWM CE TUL TUL DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_TUL_DGS_Spectrum Phase III_48 MHZ | CE | TUL | TUL | Bandwidth Management | BWM CE TUL TUL DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_TUL_DGS_Spectrum Phase III_48 MHZ | CE | TUL | TUL | Bandwidth Management | BWM CE TUL TUL DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_TUL_DGS_Spectrum Phase III_96 MHZ | CE | TUL | TUL | Bandwidth Management | BWM CE TUL TUL DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_TUL_DGS_Spectrum Phase III_96 MHZ | CE | TUL | TUL | Bandwidth Management | BWM CE TUL TUL DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_TUL_DGS_Spectrum Phase III_96 MHZ | CE | TUL | TUL | Bandwidth Management | BWM CE TUL TUL DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_TUL_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | TUL | TUL | Bandwidth Management | BWM CE TUL TUL VIDEO SG Augment POR20 v4 | Labor | No Equipment | 1 | 2020-10-01 | 2020-12-15 | 2020-12-15 | Active | EP
BWM_WIC_DGS_Spectrum Phase III_96 MHZ | CE | KAN | WIC | Bandwidth Management | BWM CE KAN WIC DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_WIC_DGS_Spectrum Phase III_96 MHZ | CE | KAN | WIC | Bandwidth Management | BWM CE KAN WIC DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_WIC_DGS_Spectrum Phase III_96 MHZ | CE | KAN | WIC | Bandwidth Management | BWM CE KAN WIC DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_BRD_DGS_Spectrum Phase III_48 MHZ | CE | TUL | BRD | Bandwidth Management | BWM CE TUL BRD DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_BRD_DGS_Spectrum Phase III_48 MHZ | CE | TUL | BRD | Bandwidth Management | BWM CE TUL BRD DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_BRD_DGS_Spectrum Phase III_48 MHZ | CE | TUL | BRD | Bandwidth Management | BWM CE TUL BRD DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_BRD_DGS_Spectrum Phase III_96 MHZ | CE | TUL | BRD | Bandwidth Management | BWM CE TUL BRD DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_BRD_DGS_Spectrum Phase III_96 MHZ | CE | TUL | BRD | Bandwidth Management | BWM CE TUL BRD DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_BRD_DGS_Spectrum Phase III_96 MHZ | CE | TUL | BRD | Bandwidth Management | BWM CE TUL BRD DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_BRD_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | TUL | BRD | Bandwidth Management | BWM CE TUL BRD Video SG Augment POR20 v3 | Labor | No Equipment | 1 | 2020-10-01 | 2020-12-15 | 2020-12-15 | Active | EP
BWM_ELR_DGS_Spectrum Phase III_48 MHZ | CE | OKC | ELR | Bandwidth Management | BWM CE OKC ELR DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_ELR_DGS_Spectrum Phase III_48 MHZ | CE | OKC | ELR | Bandwidth Management | BWM CE OKC ELR DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_ELR_DGS_Spectrum Phase III_48 MHZ | CE | OKC | ELR | Bandwidth Management | BWM CE OKC ELR DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_ELR_DGS_Spectrum Phase III_96 MHZ | CE | OKC | ELR | Bandwidth Management | BWM CE OKC ELR DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_ELR_DGS_Spectrum Phase III_96 MHZ | CE | OKC | ELR | Bandwidth Management | BWM CE OKC ELR DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_ELR_DGS_Spectrum Phase III_96 MHZ | CE | OKC | ELR | Bandwidth Management | BWM CE OKC ELR DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_GAR_DGS_Spectrum Phase III_48 MHZ | CE | TUL | GAR | Bandwidth Management | BWM CE TUL GAR DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_GAR_DGS_Spectrum Phase III_48 MHZ | CE | TUL | GAR | Bandwidth Management | BWM CE TUL GAR DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_GAR_DGS_Spectrum Phase III_48 MHZ | CE | TUL | GAR | Bandwidth Management | BWM CE TUL GAR DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_GAR_DGS_Spectrum Phase III_96 MHZ | CE | TUL | GAR | Bandwidth Management | BWM CE TUL GAR DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_GAR_DGS_Spectrum Phase III_96 MHZ | CE | TUL | GAR | Bandwidth Management | BWM CE TUL GAR DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_GAR_DGS_Spectrum Phase III_96 MHZ | CE | TUL | GAR | Bandwidth Management | BWM CE TUL GAR DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_IND_DGS_Spectrum Phase III_48 MHZ | CE | TUL | IND | Bandwidth Management | BWM CE TUL IND DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_IND_DGS_Spectrum Phase III_48 MHZ | CE | TUL | IND | Bandwidth Management | BWM CE TUL IND DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_IND_DGS_Spectrum Phase III_48 MHZ | CE | TUL | IND | Bandwidth Management | BWM CE TUL IND DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_IND_DGS_Spectrum Phase III_96 MHZ | CE | TUL | IND | Bandwidth Management | BWM CE TUL IND DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_IND_DGS_Spectrum Phase III_96 MHZ | CE | TUL | IND | Bandwidth Management | BWM CE TUL IND DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_IND_DGS_Spectrum Phase III_96 MHZ | CE | TUL | IND | Bandwidth Management | BWM CE TUL IND DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_ILH_DGS_Spectrum Phase III_48 MHZ | CE | OKC | ILH | Bandwidth Management | BWM CE OKC ILH DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_ILH_DGS_Spectrum Phase III_48 MHZ | CE | OKC | ILH | Bandwidth Management | BWM CE OKC ILH DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_ILH_DGS_Spectrum Phase III_48 MHZ | CE | OKC | ILH | Bandwidth Management | BWM CE OKC ILH DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_ILH_MSSA_Spectrum Phase II Start | CE | OKC | ILH | Bandwidth Management | BWM CE OKC ILH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | Active | EP
BWM_ILH_MSSA_Spectrum Phase II Start | CE | OKC | ILH | Bandwidth Management | BWM CE OKC ILH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_ILH_MSSA_Spectrum Phase II Start | CE | OKC | ILH | Bandwidth Management | BWM CE OKC ILH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_ILH_MSSA_Spectrum Phase II Start | CE | OKC | ILH | Bandwidth Management | BWM CE OKC ILH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-10-23 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_ILH_MSSA_Spectrum Phase II Start | CE | OKC | ILH | Bandwidth Management | BWM CE OKC ILH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_ILH_DGS_Spectrum Phase III_96 MHZ | CE | OKC | ILH | Bandwidth Management | BWM CE OKC ILH DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_ILH_DGS_Spectrum Phase III_96 MHZ | CE | OKC | ILH | Bandwidth Management | BWM CE OKC ILH DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_ILH_DGS_Spectrum Phase III_96 MHZ | CE | OKC | ILH | Bandwidth Management | BWM CE OKC ILH DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_MWC_MSSA_Spectrum Phase II Start | CE | OKC | MWC | Bandwidth Management | BWM CE OKC MWC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | Active | EP
BWM_MWC_MSSA_Spectrum Phase II Start | CE | OKC | MWC | Bandwidth Management | BWM CE OKC MWC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_MWC_MSSA_Spectrum Phase II Start | CE | OKC | MWC | Bandwidth Management | BWM CE OKC MWC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_MWC_MSSA_Spectrum Phase II Start | CE | OKC | MWC | Bandwidth Management | BWM CE OKC MWC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-10-23 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_MWC_MSSA_Spectrum Phase II Start | CE | OKC | MWC | Bandwidth Management | BWM CE OKC MWC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_MWC_DGS_Spectrum Phase III_48 MHZ | CE | OKC | MWC | Bandwidth Management | BWM CE OKC MWC DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_MWC_DGS_Spectrum Phase III_48 MHZ | CE | OKC | MWC | Bandwidth Management | BWM CE OKC MWC DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_MWC_DGS_Spectrum Phase III_48 MHZ | CE | OKC | MWC | Bandwidth Management | BWM CE OKC MWC DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_GDY_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | KAN | GDY | Bandwidth Management | BWM CE KAN GDY Video SG Augment POR20 v3 | Labor | No Equipment | 1 | 2020-10-01 | 2020-12-15 | 2020-12-15 | Active | EP
BWM_GDY_DGS_Spectrum Phase III_96 MHZ | CE | KAN | GDY | Bandwidth Management | BWM CE KAN GDY DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_GDY_DGS_Spectrum Phase III_96 MHZ | CE | KAN | GDY | Bandwidth Management | BWM CE KAN GDY DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_GDY_DGS_Spectrum Phase III_96 MHZ | CE | KAN | GDY | Bandwidth Management | BWM CE KAN GDY DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_GDY_DGS_Spectrum Phase III_48 MHZ | CE | KAN | GDY | Bandwidth Management | BWM CE KAN GDY DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_GDY_DGS_Spectrum Phase III_48 MHZ | CE | KAN | GDY | Bandwidth Management | BWM CE KAN GDY DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_GDY_DGS_Spectrum Phase III_48 MHZ | CE | KAN | GDY | Bandwidth Management | BWM CE KAN GDY DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_FTS_DGS_Spectrum Phase III_96 MHZ | CE | NWA | FTS | Bandwidth Management | BWM CE NWA FTS DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_FTS_DGS_Spectrum Phase III_96 MHZ | CE | NWA | FTS | Bandwidth Management | BWM CE NWA FTS DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_FTS_DGS_Spectrum Phase III_96 MHZ | CE | NWA | FTS | Bandwidth Management | BWM CE NWA FTS DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_FTS_DGS_Spectrum Phase III_48 MHZ | CE | NWA | FTS | Bandwidth Management | BWM CE NWA FTS DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_FTS_DGS_Spectrum Phase III_48 MHZ | CE | NWA | FTS | Bandwidth Management | BWM CE NWA FTS DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_FTS_DGS_Spectrum Phase III_48 MHZ | CE | NWA | FTS | Bandwidth Management | BWM CE NWA FTS DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_FAY_DGS_Spectrum Phase III_96 MHZ | CE | NWA | FAY | Bandwidth Management | BWM CE NWA FAY DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_FAY_DGS_Spectrum Phase III_96 MHZ | CE | NWA | FAY | Bandwidth Management | BWM CE NWA FAY DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_FAY_DGS_Spectrum Phase III_96 MHZ | CE | NWA | FAY | Bandwidth Management | BWM CE NWA FAY DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_FAY_DGS_Spectrum Phase III_48 MHZ | CE | NWA | FAY | Bandwidth Management | BWM CE NWA FAY DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_FAY_DGS_Spectrum Phase III_48 MHZ | CE | NWA | FAY | Bandwidth Management | BWM CE NWA FAY DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_FAY_DGS_Spectrum Phase III_48 MHZ | CE | NWA | FAY | Bandwidth Management | BWM CE NWA FAY DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_DCY_DGS_Spectrum Phase III_96 MHZ | CE | KAN | DCY | Bandwidth Management | BWM CE KAN DCY DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_DCY_DGS_Spectrum Phase III_96 MHZ | CE | KAN | DCY | Bandwidth Management | BWM CE KAN DCY DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_DCY_DGS_Spectrum Phase III_96 MHZ | CE | KAN | DCY | Bandwidth Management | BWM CE KAN DCY DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_DCY_DGS_Spectrum Phase III_48 MHZ | CE | KAN | DCY | Bandwidth Management | BWM CE KAN DCY DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_DCY_DGS_Spectrum Phase III_48 MHZ | CE | KAN | DCY | Bandwidth Management | BWM CE KAN DCY DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_DCY_DGS_Spectrum Phase III_48 MHZ | CE | KAN | DCY | Bandwidth Management | BWM CE KAN DCY DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_DBY_DGS_Spectrum Phase III_96 MHZ | CE | KAN | DBY | Bandwidth Management | BWM CE KAN DBY DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_DBY_DGS_Spectrum Phase III_96 MHZ | CE | KAN | DBY | Bandwidth Management | BWM CE KAN DBY DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_DBY_DGS_Spectrum Phase III_96 MHZ | CE | KAN | DBY | Bandwidth Management | BWM CE KAN DBY DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_DBY_DGS_Spectrum Phase III_48 MHZ | CE | KAN | DBY | Bandwidth Management | BWM CE KAN DBY DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_DBY_DGS_Spectrum Phase III_48 MHZ | CE | KAN | DBY | Bandwidth Management | BWM CE KAN DBY DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_DBY_DGS_Spectrum Phase III_48 MHZ | CE | KAN | DBY | Bandwidth Management | BWM CE KAN DBY DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_CFV_DGS_Spectrum Phase III_96 MHZ | CE | KAN | CFV | Bandwidth Management | BWM CE KAN CFV DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_CFV_DGS_Spectrum Phase III_96 MHZ | CE | KAN | CFV | Bandwidth Management | BWM CE KAN CFV DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_CFV_DGS_Spectrum Phase III_96 MHZ | CE | KAN | CFV | Bandwidth Management | BWM CE KAN CFV DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_CFV_DGS_Spectrum Phase III_48 MHZ | CE | KAN | CFV | Bandwidth Management | BWM CE KAN CFV DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_CFV_DGS_Spectrum Phase III_48 MHZ | CE | KAN | CFV | Bandwidth Management | BWM CE KAN CFV DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_CFV_DGS_Spectrum Phase III_48 MHZ | CE | KAN | CFV | Bandwidth Management | BWM CE KAN CFV DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_BER_DGS_Spectrum Phase III_96 MHZ | CE | NWA | BER | Bandwidth Management | BWM CE NWA BER DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_BER_DGS_Spectrum Phase III_96 MHZ | CE | NWA | BER | Bandwidth Management | BWM CE NWA BER DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_BER_DGS_Spectrum Phase III_96 MHZ | CE | NWA | BER | Bandwidth Management | BWM CE NWA BER DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_BER_DGS_Spectrum Phase III_48 MHZ | CE | NWA | BER | Bandwidth Management | BWM CE NWA BER DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_BER_DGS_Spectrum Phase III_48 MHZ | CE | NWA | BER | Bandwidth Management | BWM CE NWA BER DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_BER_DGS_Spectrum Phase III_48 MHZ | CE | NWA | BER | Bandwidth Management | BWM CE NWA BER DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_BVL_DGS_Spectrum Phase III_96 MHZ | CE | NWA | BVL | Bandwidth Management | BWM CE NWA BVL DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_BVL_DGS_Spectrum Phase III_96 MHZ | CE | NWA | BVL | Bandwidth Management | BWM CE NWA BVL DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_BVL_DGS_Spectrum Phase III_96 MHZ | CE | NWA | BVL | Bandwidth Management | BWM CE NWA BVL DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_QNC_DGS_Spectrum Phase III_48 MHZ | CE | TUL | QNC | Bandwidth Management | BWM CE TUL QNC DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_QNC_DGS_Spectrum Phase III_48 MHZ | CE | TUL | QNC | Bandwidth Management | BWM CE TUL QNC DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_QNC_DGS_Spectrum Phase III_48 MHZ | CE | TUL | QNC | Bandwidth Management | BWM CE TUL QNC DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_QNC_DGS_Spectrum Phase III_96 MHZ | CE | TUL | QNC | Bandwidth Management | BWM CE TUL QNC DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_QNC_DGS_Spectrum Phase III_96 MHZ | CE | TUL | QNC | Bandwidth Management | BWM CE TUL QNC DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_QNC_DGS_Spectrum Phase III_96 MHZ | CE | TUL | QNC | Bandwidth Management | BWM CE TUL QNC DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_SAP_DGS_Spectrum Phase III_48 MHZ | CE | TUL | SAP | Bandwidth Management | BWM CE TUL SAP DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_SAP_DGS_Spectrum Phase III_48 MHZ | CE | TUL | SAP | Bandwidth Management | BWM CE TUL SAP DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_SAP_DGS_Spectrum Phase III_48 MHZ | CE | TUL | SAP | Bandwidth Management | BWM CE TUL SAP DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_SAP_DGS_Spectrum Phase III_96 MHZ | CE | TUL | SAP | Bandwidth Management | BWM CE TUL SAP DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_SAP_DGS_Spectrum Phase III_96 MHZ | CE | TUL | SAP | Bandwidth Management | BWM CE TUL SAP DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_SAP_DGS_Spectrum Phase III_96 MHZ | CE | TUL | SAP | Bandwidth Management | BWM CE TUL SAP DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_SRH_MSSA_Spectrum Phase II Start | CE | OKC | SRH | Bandwidth Management | BWM CE OKC SRH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | Active | EP
BWM_SRH_MSSA_Spectrum Phase II Start | CE | OKC | SRH | Bandwidth Management | BWM CE OKC SRH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_SRH_MSSA_Spectrum Phase II Start | CE | OKC | SRH | Bandwidth Management | BWM CE OKC SRH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_SRH_MSSA_Spectrum Phase II Start | CE | OKC | SRH | Bandwidth Management | BWM CE OKC SRH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-10-23 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_SRH_MSSA_Spectrum Phase II Start | CE | OKC | SRH | Bandwidth Management | BWM CE OKC SRH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_SRH_DGS_Spectrum Phase III_48 MHZ | CE | OKC | SRH | Bandwidth Management | BWM CE OKC SRH DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_SRH_DGS_Spectrum Phase III_48 MHZ | CE | OKC | SRH | Bandwidth Management | BWM CE OKC SRH DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_SRH_DGS_Spectrum Phase III_48 MHZ | CE | OKC | SRH | Bandwidth Management | BWM CE OKC SRH DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_SRH_DGS_Spectrum Phase III_96 MHZ | CE | OKC | SRH | Bandwidth Management | BWM CE OKC SRH DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_SRH_DGS_Spectrum Phase III_96 MHZ | CE | OKC | SRH | Bandwidth Management | BWM CE OKC SRH DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_SRH_DGS_Spectrum Phase III_96 MHZ | CE | OKC | SRH | Bandwidth Management | BWM CE OKC SRH DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_NWT_DGS_Spectrum Phase III_48 MHZ | CE | KAN | NWT | Bandwidth Management | BWM CE KAN NWT DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_NWT_DGS_Spectrum Phase III_48 MHZ | CE | KAN | NWT | Bandwidth Management | BWM CE KAN NWT DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_NWT_DGS_Spectrum Phase III_48 MHZ | CE | KAN | NWT | Bandwidth Management | BWM CE KAN NWT DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_NWT_DGS_Spectrum Phase III_96 MHZ | CE | KAN | NWT | Bandwidth Management | BWM CE KAN NWT DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_NWT_DGS_Spectrum Phase III_96 MHZ | CE | KAN | NWT | Bandwidth Management | BWM CE KAN NWT DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_NWT_DGS_Spectrum Phase III_96 MHZ | CE | KAN | NWT | Bandwidth Management | BWM CE KAN NWT DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_PIT_DGS_Spectrum Phase III_48 MHZ | CE | KAN | PIT | Bandwidth Management | BWM CE KAN PIT DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_PIT_DGS_Spectrum Phase III_48 MHZ | CE | KAN | PIT | Bandwidth Management | BWM CE KAN PIT DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_PIT_DGS_Spectrum Phase III_48 MHZ | CE | KAN | PIT | Bandwidth Management | BWM CE KAN PIT DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_PIT_DGS_Spectrum Phase III_96 MHZ | CE | KAN | PIT | Bandwidth Management | BWM CE KAN PIT DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_PIT_DGS_Spectrum Phase III_96 MHZ | CE | KAN | PIT | Bandwidth Management | BWM CE KAN PIT DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_PIT_DGS_Spectrum Phase III_96 MHZ | CE | KAN | PIT | Bandwidth Management | BWM CE KAN PIT DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_PRT_DGS_Spectrum Phase III_48 MHZ | CE | KAN | PRT | Bandwidth Management | BWM CE KAN PRT DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_PRT_DGS_Spectrum Phase III_48 MHZ | CE | KAN | PRT | Bandwidth Management | BWM CE KAN PRT DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_PRT_DGS_Spectrum Phase III_48 MHZ | CE | KAN | PRT | Bandwidth Management | BWM CE KAN PRT DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_PRT_DGS_Spectrum Phase III_96 MHZ | CE | KAN | PRT | Bandwidth Management | BWM CE KAN PRT DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_PRT_DGS_Spectrum Phase III_96 MHZ | CE | KAN | PRT | Bandwidth Management | BWM CE KAN PRT DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_PRT_DGS_Spectrum Phase III_96 MHZ | CE | KAN | PRT | Bandwidth Management | BWM CE KAN PRT DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_SAL_DGS_Spectrum Phase III_48 MHZ | CE | KAN | SAL | Bandwidth Management | BWM CE KAN SAL DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_SAL_DGS_Spectrum Phase III_48 MHZ | CE | KAN | SAL | Bandwidth Management | BWM CE KAN SAL DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_SAL_DGS_Spectrum Phase III_48 MHZ | CE | KAN | SAL | Bandwidth Management | BWM CE KAN SAL DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_SAL_DGS_Spectrum Phase III_96 MHZ | CE | KAN | SAL | Bandwidth Management | BWM CE KAN SAL DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_SAL_DGS_Spectrum Phase III_96 MHZ | CE | KAN | SAL | Bandwidth Management | BWM CE KAN SAL DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_SAL_DGS_Spectrum Phase III_96 MHZ | CE | KAN | SAL | Bandwidth Management | BWM CE KAN SAL DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_SSP_DGS_Spectrum Phase III_48 MHZ | CE | NWA | SSP | Bandwidth Management | BWM CE NWA SSP DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_SSP_DGS_Spectrum Phase III_48 MHZ | CE | NWA | SSP | Bandwidth Management | BWM CE NWA SSP DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_SSP_DGS_Spectrum Phase III_48 MHZ | CE | NWA | SSP | Bandwidth Management | BWM CE NWA SSP DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_SSP_DGS_Spectrum Phase III_96 MHZ | CE | NWA | SSP | Bandwidth Management | BWM CE NWA SSP DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_SSP_DGS_Spectrum Phase III_96 MHZ | CE | NWA | SSP | Bandwidth Management | BWM CE NWA SSP DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_SSP_DGS_Spectrum Phase III_96 MHZ | CE | NWA | SSP | Bandwidth Management | BWM CE NWA SSP DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_STR_DGS_Spectrum Phase III_48 MHZ | CE | KAN | STR | Bandwidth Management | BWM CE KAN STR DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_STR_DGS_Spectrum Phase III_48 MHZ | CE | KAN | STR | Bandwidth Management | BWM CE KAN STR DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_STR_DGS_Spectrum Phase III_48 MHZ | CE | KAN | STR | Bandwidth Management | BWM CE KAN STR DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_STR_DGS_Spectrum Phase III_96 MHZ | CE | KAN | STR | Bandwidth Management | BWM CE KAN STR DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_STR_DGS_Spectrum Phase III_96 MHZ | CE | KAN | STR | Bandwidth Management | BWM CE KAN STR DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_STR_DGS_Spectrum Phase III_96 MHZ | CE | KAN | STR | Bandwidth Management | BWM CE KAN STR DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_TOP_DGS_Spectrum Phase III_48 MHZ | CE | KAN | TOP | Bandwidth Management | BWM CE KAN TOP DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_TOP_DGS_Spectrum Phase III_48 MHZ | CE | KAN | TOP | Bandwidth Management | BWM CE KAN TOP DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_TOP_DGS_Spectrum Phase III_48 MHZ | CE | KAN | TOP | Bandwidth Management | BWM CE KAN TOP DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_TOP_DGS_Spectrum Phase III_96 MHZ | CE | KAN | TOP | Bandwidth Management | BWM CE KAN TOP DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_TOP_DGS_Spectrum Phase III_96 MHZ | CE | KAN | TOP | Bandwidth Management | BWM CE KAN TOP DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_TOP_DGS_Spectrum Phase III_96 MHZ | CE | KAN | TOP | Bandwidth Management | BWM CE KAN TOP DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_TOW_DGS_Spectrum Phase III_48 MHZ | CE | KAN | TOW | Bandwidth Management | BWM CE KAN TOW DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_TOW_DGS_Spectrum Phase III_48 MHZ | CE | KAN | TOW | Bandwidth Management | BWM CE KAN TOW DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_TOW_DGS_Spectrum Phase III_48 MHZ | CE | KAN | TOW | Bandwidth Management | BWM CE KAN TOW DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_TOW_DGS_Spectrum Phase III_96 MHZ | CE | KAN | TOW | Bandwidth Management | BWM CE KAN TOW DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_TOW_DGS_Spectrum Phase III_96 MHZ | CE | KAN | TOW | Bandwidth Management | BWM CE KAN TOW DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_TOW_DGS_Spectrum Phase III_96 MHZ | CE | KAN | TOW | Bandwidth Management | BWM CE KAN TOW DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_VBN_DGS_Spectrum Phase III_48 MHZ | CE | NWA | VBN | Bandwidth Management | BWM CE NWA VBN DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_VBN_DGS_Spectrum Phase III_48 MHZ | CE | NWA | VBN | Bandwidth Management | BWM CE NWA VBN DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_VBN_DGS_Spectrum Phase III_48 MHZ | CE | NWA | VBN | Bandwidth Management | BWM CE NWA VBN DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_VBN_DGS_Spectrum Phase III_96 MHZ | CE | NWA | VBN | Bandwidth Management | BWM CE NWA VBN DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_VBN_DGS_Spectrum Phase III_96 MHZ | CE | NWA | VBN | Bandwidth Management | BWM CE NWA VBN DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_VBN_DGS_Spectrum Phase III_96 MHZ | CE | NWA | VBN | Bandwidth Management | BWM CE NWA VBN DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_WIC_DGS_Spectrum Phase III_48 MHZ | CE | KAN | WIC | Bandwidth Management | BWM CE KAN WIC DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_WIC_DGS_Spectrum Phase III_48 MHZ | CE | KAN | WIC | Bandwidth Management | BWM CE KAN WIC DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_WIC_DGS_Spectrum Phase III_48 MHZ | CE | KAN | WIC | Bandwidth Management | BWM CE KAN WIC DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_BAR_DGS_Spectrum Phase III_48 MHZ | CE | TUL | BAR | Bandwidth Management | BWM CE TUL BAR DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_BAR_DGS_Spectrum Phase III_48 MHZ | CE | TUL | BAR | Bandwidth Management | BWM CE TUL BAR DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_BAR_DGS_Spectrum Phase III_48 MHZ | CE | TUL | BAR | Bandwidth Management | BWM CE TUL BAR DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_BAR_DGS_Spectrum Phase III_96 MHZ | CE | TUL | BAR | Bandwidth Management | BWM CE TUL BAR DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_BAR_DGS_Spectrum Phase III_96 MHZ | CE | TUL | BAR | Bandwidth Management | BWM CE TUL BAR DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_BAR_DGS_Spectrum Phase III_96 MHZ | CE | TUL | BAR | Bandwidth Management | BWM CE TUL BAR DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_BAR_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | TUL | BAR | Bandwidth Management | BWM CE TUL BAR Video SG Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_BAR_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | TUL | BAR | Bandwidth Management | BWM CE TUL BAR Video SG Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0245 | Schedule Change | Approved | 2020-02-24 12:37 | 59 projects were made inactive on CR SN-0195 in error, I m reactivating these projects and VSG submited an revised plan 14 VSG projects removed and shifting some dates for the remaining projects
BWM_CHO_MSSA_Spectrum Phase II Start | CE | OKC | CHO | Bandwidth Management | BWM CE OKC CHO MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | Active | EP
BWM_CHO_MSSA_Spectrum Phase II Start | CE | OKC | CHO | Bandwidth Management | BWM CE OKC CHO MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_CHO_MSSA_Spectrum Phase II Start | CE | OKC | CHO | Bandwidth Management | BWM CE OKC CHO MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_CHO_MSSA_Spectrum Phase II Start | CE | OKC | CHO | Bandwidth Management | BWM CE OKC CHO MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-10-23 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_CHO_MSSA_Spectrum Phase II Start | CE | OKC | CHO | Bandwidth Management | BWM CE OKC CHO MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_CHO_DGS_Spectrum Phase III_48 MHZ | CE | OKC | CHO | Bandwidth Management | BWM CE OKC CHO DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_CHO_DGS_Spectrum Phase III_48 MHZ | CE | OKC | CHO | Bandwidth Management | BWM CE OKC CHO DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_CHO_DGS_Spectrum Phase III_48 MHZ | CE | OKC | CHO | Bandwidth Management | BWM CE OKC CHO DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_CHO_DGS_Spectrum Phase III_96 MHZ | CE | OKC | CHO | Bandwidth Management | BWM CE OKC CHO DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_CHO_DGS_Spectrum Phase III_96 MHZ | CE | OKC | CHO | Bandwidth Management | BWM CE OKC CHO DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_CHO_DGS_Spectrum Phase III_96 MHZ | CE | OKC | CHO | Bandwidth Management | BWM CE OKC CHO DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_CLA_DGS_Spectrum Phase III_48 MHZ | CE | TUL | CLA | Bandwidth Management | BWM CE TUL CLA DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_CLA_DGS_Spectrum Phase III_48 MHZ | CE | TUL | CLA | Bandwidth Management | BWM CE TUL CLA DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_CLA_DGS_Spectrum Phase III_48 MHZ | CE | TUL | CLA | Bandwidth Management | BWM CE TUL CLA DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_CLA_DGS_Spectrum Phase III_96 MHZ | CE | TUL | CLA | Bandwidth Management | BWM CE TUL CLA DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_CLA_DGS_Spectrum Phase III_96 MHZ | CE | TUL | CLA | Bandwidth Management | BWM CE TUL CLA DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_CLA_DGS_Spectrum Phase III_96 MHZ | CE | TUL | CLA | Bandwidth Management | BWM CE TUL CLA DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_CLH_MSSA_Spectrum Phase II Start | CE | OKC | CLH | Bandwidth Management | BWM CE OKC CLH DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_CLH_MSSA_Spectrum Phase II Start | CE | OKC | CLH | Bandwidth Management | BWM CE OKC CLH DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_CLH_DGS_Spectrum Phase III_48 MHZ | CE | OKC | CLH | Bandwidth Management | BWM CE OKC CLH DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_CLH_DGS_Spectrum Phase III_48 MHZ | CE | OKC | CLH | Bandwidth Management | BWM CE OKC CLH DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_CLH_DGS_Spectrum Phase III_48 MHZ | CE | OKC | CLH | Bandwidth Management | BWM CE OKC CLH DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_CLH_DGS_Spectrum Phase III_96 MHZ | CE | OKC | CLH | Bandwidth Management | BWM CE OKC CLH DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_CLH_DGS_Spectrum Phase III_96 MHZ | CE | OKC | CLH | Bandwidth Management | BWM CE OKC CLH DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_CLH_DGS_Spectrum Phase III_96 MHZ | CE | OKC | CLH | Bandwidth Management | BWM CE OKC CLH DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_DTN_DGS_Spectrum Phase III_48 MHZ | CE | TUL | DTN | Bandwidth Management | BWM CE TUL DTN DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_DTN_DGS_Spectrum Phase III_48 MHZ | CE | TUL | DTN | Bandwidth Management | BWM CE TUL DTN DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_DTN_DGS_Spectrum Phase III_48 MHZ | CE | TUL | DTN | Bandwidth Management | BWM CE TUL DTN DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_DTN_DGS_Spectrum Phase III_96 MHZ | CE | TUL | DTN | Bandwidth Management | BWM CE TUL DTN DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_DTN_DGS_Spectrum Phase III_96 MHZ | CE | TUL | DTN | Bandwidth Management | BWM CE TUL DTN DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_DTN_DGS_Spectrum Phase III_96 MHZ | CE | TUL | DTN | Bandwidth Management | BWM CE TUL DTN DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_DTN_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | TUL | DTN | Bandwidth Management | BWM CE TUL DTN Video SG Augment POR20 v3 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-15 | 2020-09-15 | Active | EP
BWM_ELR_MSSA_Spectrum Phase II Start | CE | OKC | ELR | Bandwidth Management | BWM CE OKC ELR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | Active | EP
BWM_ELR_MSSA_Spectrum Phase II Start | CE | OKC | ELR | Bandwidth Management | BWM CE OKC ELR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_ELR_MSSA_Spectrum Phase II Start | CE | OKC | ELR | Bandwidth Management | BWM CE OKC ELR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_ELR_MSSA_Spectrum Phase II Start | CE | OKC | ELR | Bandwidth Management | BWM CE OKC ELR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-10-23 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_ELR_MSSA_Spectrum Phase II Start | CE | OKC | ELR | Bandwidth Management | BWM CE OKC ELR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_MWC_DGS_Spectrum Phase III_96 MHZ | CE | OKC | MWC | Bandwidth Management | BWM CE OKC MWC DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_MWC_DGS_Spectrum Phase III_96 MHZ | CE | OKC | MWC | Bandwidth Management | BWM CE OKC MWC DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_MWC_DGS_Spectrum Phase III_96 MHZ | CE | OKC | MWC | Bandwidth Management | BWM CE OKC MWC DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_MOO_MSSA_Spectrum Phase II Start | CE | OKC | MOO | Bandwidth Management | BWM CE OKC MOO MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | Active | EP
BWM_MOO_MSSA_Spectrum Phase II Start | CE | OKC | MOO | Bandwidth Management | BWM CE OKC MOO MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_MOO_MSSA_Spectrum Phase II Start | CE | OKC | MOO | Bandwidth Management | BWM CE OKC MOO MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_MOO_MSSA_Spectrum Phase II Start | CE | OKC | MOO | Bandwidth Management | BWM CE OKC MOO MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-10-23 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_MOO_MSSA_Spectrum Phase II Start | CE | OKC | MOO | Bandwidth Management | BWM CE OKC MOO MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_MOO_DGS_Spectrum Phase III_48 MHZ | CE | OKC | MOO | Bandwidth Management | BWM CE OKC MOO DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_MOO_DGS_Spectrum Phase III_48 MHZ | CE | OKC | MOO | Bandwidth Management | BWM CE OKC MOO DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_MOO_DGS_Spectrum Phase III_48 MHZ | CE | OKC | MOO | Bandwidth Management | BWM CE OKC MOO DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_MOO_DGS_Spectrum Phase III_96 MHZ | CE | OKC | MOO | Bandwidth Management | BWM CE OKC MOO DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_MOO_DGS_Spectrum Phase III_96 MHZ | CE | OKC | MOO | Bandwidth Management | BWM CE OKC MOO DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_MOO_DGS_Spectrum Phase III_96 MHZ | CE | OKC | MOO | Bandwidth Management | BWM CE OKC MOO DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_NOR_MSSA_Spectrum Phase II Start | CE | OKC | NOR | Bandwidth Management | BWM CE OKC NOR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | Active | EP
BWM_NOR_MSSA_Spectrum Phase II Start | CE | OKC | NOR | Bandwidth Management | BWM CE OKC NOR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_NOR_MSSA_Spectrum Phase II Start | CE | OKC | NOR | Bandwidth Management | BWM CE OKC NOR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_NOR_MSSA_Spectrum Phase II Start | CE | OKC | NOR | Bandwidth Management | BWM CE OKC NOR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-10-23 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_NOR_MSSA_Spectrum Phase II Start | CE | OKC | NOR | Bandwidth Management | BWM CE OKC NOR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_NOR_DGS_Spectrum Phase III_48 MHZ | CE | OKC | NOR | Bandwidth Management | BWM CE OKC NOR DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_NOR_DGS_Spectrum Phase III_48 MHZ | CE | OKC | NOR | Bandwidth Management | BWM CE OKC NOR DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_NOR_DGS_Spectrum Phase III_48 MHZ | CE | OKC | NOR | Bandwidth Management | BWM CE OKC NOR DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_NOR_DGS_Spectrum Phase III_96 MHZ | CE | OKC | NOR | Bandwidth Management | BWM CE OKC NOR DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_NOR_DGS_Spectrum Phase III_96 MHZ | CE | OKC | NOR | Bandwidth Management | BWM CE OKC NOR DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_NOR_DGS_Spectrum Phase III_96 MHZ | CE | OKC | NOR | Bandwidth Management | BWM CE OKC NOR DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_NCH_MSSA_Spectrum Phase II Start | CE | OKC | NCH | Bandwidth Management | BWM CE OKC NCH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | Active | EP
BWM_NCH_MSSA_Spectrum Phase II Start | CE | OKC | NCH | Bandwidth Management | BWM CE OKC NCH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_NCH_MSSA_Spectrum Phase II Start | CE | OKC | NCH | Bandwidth Management | BWM CE OKC NCH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_NCH_MSSA_Spectrum Phase II Start | CE | OKC | NCH | Bandwidth Management | BWM CE OKC NCH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-10-23 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_NCH_MSSA_Spectrum Phase II Start | CE | OKC | NCH | Bandwidth Management | BWM CE OKC NCH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_NCH_DGS_Spectrum Phase III_48 MHZ | CE | OKC | NCH | Bandwidth Management | BWM CE OKC NCH DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_NCH_DGS_Spectrum Phase III_48 MHZ | CE | OKC | NCH | Bandwidth Management | BWM CE OKC NCH DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_NCH_DGS_Spectrum Phase III_48 MHZ | CE | OKC | NCH | Bandwidth Management | BWM CE OKC NCH DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_NCH_DGS_Spectrum Phase III_96 MHZ | CE | OKC | NCH | Bandwidth Management | BWM CE OKC NCH DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_NCH_DGS_Spectrum Phase III_96 MHZ | CE | OKC | NCH | Bandwidth Management | BWM CE OKC NCH DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_NCH_DGS_Spectrum Phase III_96 MHZ | CE | OKC | NCH | Bandwidth Management | BWM CE OKC NCH DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_NEH_MSSA_Spectrum Phase II Start | CE | OKC | NEH | Bandwidth Management | BWM CE OKC NEH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | Active | EP
BWM_NEH_MSSA_Spectrum Phase II Start | CE | OKC | NEH | Bandwidth Management | BWM CE OKC NEH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_NEH_MSSA_Spectrum Phase II Start | CE | OKC | NEH | Bandwidth Management | BWM CE OKC NEH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_NEH_MSSA_Spectrum Phase II Start | CE | OKC | NEH | Bandwidth Management | BWM CE OKC NEH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-10-23 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_NEH_MSSA_Spectrum Phase II Start | CE | OKC | NEH | Bandwidth Management | BWM CE OKC NEH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_NEH_DGS_Spectrum Phase III_48 MHZ | CE | OKC | NEH | Bandwidth Management | BWM CE OKC NEH DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_NEH_DGS_Spectrum Phase III_48 MHZ | CE | OKC | NEH | Bandwidth Management | BWM CE OKC NEH DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_NEH_DGS_Spectrum Phase III_48 MHZ | CE | OKC | NEH | Bandwidth Management | BWM CE OKC NEH DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_NEH_DGS_Spectrum Phase III_96 MHZ | CE | OKC | NEH | Bandwidth Management | BWM CE OKC NEH DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_NEH_DGS_Spectrum Phase III_96 MHZ | CE | OKC | NEH | Bandwidth Management | BWM CE OKC NEH DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_NEH_DGS_Spectrum Phase III_96 MHZ | CE | OKC | NEH | Bandwidth Management | BWM CE OKC NEH DGS Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_OKC_MSSA_Spectrum Phase II Start | CE | OKC | OKC | Bandwidth Management | BWM CE OKC OKC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | Active | EP
BWM_OKC_MSSA_Spectrum Phase II Start | CE | OKC | OKC | Bandwidth Management | BWM CE OKC OKC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_OKC_MSSA_Spectrum Phase II Start | CE | OKC | OKC | Bandwidth Management | BWM CE OKC OKC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_OKC_MSSA_Spectrum Phase II Start | CE | OKC | OKC | Bandwidth Management | BWM CE OKC OKC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-10-23 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_OKC_MSSA_Spectrum Phase II Start | CE | OKC | OKC | Bandwidth Management | BWM CE OKC OKC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_MPN_DGS_Spectrum Phase III_48 MHZ | CE | KAN | MPN | Bandwidth Management | BWM CE KAN MPN DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_MPN_DGS_Spectrum Phase III_48 MHZ | CE | KAN | MPN | Bandwidth Management | BWM CE KAN MPN DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_MPN_DGS_Spectrum Phase III_48 MHZ | CE | KAN | MPN | Bandwidth Management | BWM CE KAN MPN DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_MNT_DGS_Spectrum Phase III_96 MHZ | CE | KAN | MNT | Bandwidth Management | BWM CE KAN MNT DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_MNT_DGS_Spectrum Phase III_96 MHZ | CE | KAN | MNT | Bandwidth Management | BWM CE KAN MNT DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_MNT_DGS_Spectrum Phase III_96 MHZ | CE | KAN | MNT | Bandwidth Management | BWM CE KAN MNT DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_MNT_DGS_Spectrum Phase III_48 MHZ | CE | KAN | MNT | Bandwidth Management | BWM CE KAN MNT DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_MNT_DGS_Spectrum Phase III_48 MHZ | CE | KAN | MNT | Bandwidth Management | BWM CE KAN MNT DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_MNT_DGS_Spectrum Phase III_48 MHZ | CE | KAN | MNT | Bandwidth Management | BWM CE KAN MNT DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_MPN_DGS_Spectrum Phase III_96 MHZ | CE | KAN | MPN | Bandwidth Management | BWM CE KAN MPN DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_MPN_DGS_Spectrum Phase III_96 MHZ | CE | KAN | MPN | Bandwidth Management | BWM CE KAN MPN DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_MPN_DGS_Spectrum Phase III_96 MHZ | CE | KAN | MPN | Bandwidth Management | BWM CE KAN MPN DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_JCY_DGS_Spectrum Phase III_96 MHZ | CE | KAN | JCY | Bandwidth Management | BWM CE KAN JCY DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_JCY_DGS_Spectrum Phase III_96 MHZ | CE | KAN | JCY | Bandwidth Management | BWM CE KAN JCY DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_JCY_DGS_Spectrum Phase III_96 MHZ | CE | KAN | JCY | Bandwidth Management | BWM CE KAN JCY DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_JCY_DGS_Spectrum Phase III_48 MHZ | CE | KAN | JCY | Bandwidth Management | BWM CE KAN JCY DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_JCY_DGS_Spectrum Phase III_48 MHZ | CE | KAN | JCY | Bandwidth Management | BWM CE KAN JCY DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_JCY_DGS_Spectrum Phase III_48 MHZ | CE | KAN | JCY | Bandwidth Management | BWM CE KAN JCY DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_NWA_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | NWA | NWA | Bandwidth Management | BWM CE NWA NWA Video SG Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_NWA_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | NWA | NWA | Bandwidth Management | BWM CE NWA NWA Video SG Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0245 | Schedule Change | Approved | 2020-02-24 12:37 | 59 projects were made inactive on CR SN-0195 in error, I m reactivating these projects and VSG submited an revised plan 14 VSG projects removed and shifting some dates for the remaining projects
BWM_NWA_DGS_Spectrum Phase III_96 MHZ | CE | NWA | NWA | Bandwidth Management | BWM CE NWA NWA DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_NWA_DGS_Spectrum Phase III_96 MHZ | CE | NWA | NWA | Bandwidth Management | BWM CE NWA NWA DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_NWA_DGS_Spectrum Phase III_96 MHZ | CE | NWA | NWA | Bandwidth Management | BWM CE NWA NWA DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_NWA_DGS_Spectrum Phase III_48 MHZ | CE | NWA | NWA | Bandwidth Management | BWM CE NWA NWA DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_NWA_DGS_Spectrum Phase III_48 MHZ | CE | NWA | NWA | Bandwidth Management | BWM CE NWA NWA DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_NWA_DGS_Spectrum Phase III_48 MHZ | CE | NWA | NWA | Bandwidth Management | BWM CE NWA NWA DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_OLA_DGS_Spectrum Phase III_96 MHZ | CE | KAN | OLA | Bandwidth Management | BWM CE KAN OLA DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_OLA_DGS_Spectrum Phase III_96 MHZ | CE | KAN | OLA | Bandwidth Management | BWM CE KAN OLA DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_OLA_DGS_Spectrum Phase III_96 MHZ | CE | KAN | OLA | Bandwidth Management | BWM CE KAN OLA DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_OLA_DGS_Spectrum Phase III_48 MHZ | CE | KAN | OLA | Bandwidth Management | BWM CE KAN OLA DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_OLA_DGS_Spectrum Phase III_48 MHZ | CE | KAN | OLA | Bandwidth Management | BWM CE KAN OLA DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_OLA_DGS_Spectrum Phase III_48 MHZ | CE | KAN | OLA | Bandwidth Management | BWM CE KAN OLA DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_HUT_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | KAN | HUT | Bandwidth Management | BWM CE KAN HUT Video SG Augment POR20 v3 | Labor | No Equipment | 1 | 2020-10-01 | 2020-12-15 | 2020-12-15 | Active | EP
BWM_HUT_DGS_Spectrum Phase III_96 MHZ | CE | KAN | HUT | Bandwidth Management | BWM CE KAN HUT DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_HUT_DGS_Spectrum Phase III_96 MHZ | CE | KAN | HUT | Bandwidth Management | BWM CE KAN HUT DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_HUT_DGS_Spectrum Phase III_96 MHZ | CE | KAN | HUT | Bandwidth Management | BWM CE KAN HUT DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_HUT_DGS_Spectrum Phase III_48 MHZ | CE | KAN | HUT | Bandwidth Management | BWM CE KAN HUT DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_HUT_DGS_Spectrum Phase III_48 MHZ | CE | KAN | HUT | Bandwidth Management | BWM CE KAN HUT DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_HUT_DGS_Spectrum Phase III_48 MHZ | CE | KAN | HUT | Bandwidth Management | BWM CE KAN HUT DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_HRN_DGS_Spectrum Phase III_96 MHZ | CE | NWA | HRN | Bandwidth Management | BWM CE NWA HRN DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_HRN_DGS_Spectrum Phase III_96 MHZ | CE | NWA | HRN | Bandwidth Management | BWM CE NWA HRN DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_HRN_DGS_Spectrum Phase III_96 MHZ | CE | NWA | HRN | Bandwidth Management | BWM CE NWA HRN DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_HRN_DGS_Spectrum Phase III_48 MHZ | CE | NWA | HRN | Bandwidth Management | BWM CE NWA HRN DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_HRN_DGS_Spectrum Phase III_48 MHZ | CE | NWA | HRN | Bandwidth Management | BWM CE NWA HRN DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_HRN_DGS_Spectrum Phase III_48 MHZ | CE | NWA | HRN | Bandwidth Management | BWM CE NWA HRN DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_GBD_DGS_Spectrum Phase III_96 MHZ | CE | KAN | GBD | Bandwidth Management | BWM CE KAN GBD DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_GBD_DGS_Spectrum Phase III_96 MHZ | CE | KAN | GBD | Bandwidth Management | BWM CE KAN GBD DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_GBD_DGS_Spectrum Phase III_96 MHZ | CE | KAN | GBD | Bandwidth Management | BWM CE KAN GBD DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_GBD_DGS_Spectrum Phase III_48 MHZ | CE | KAN | GBD | Bandwidth Management | BWM CE KAN GBD DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_GBD_DGS_Spectrum Phase III_48 MHZ | CE | KAN | GBD | Bandwidth Management | BWM CE KAN GBD DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_GBD_DGS_Spectrum Phase III_48 MHZ | CE | KAN | GBD | Bandwidth Management | BWM CE KAN GBD DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_BVL_DGS_Spectrum Phase III_48 MHZ | CE | NWA | BVL | Bandwidth Management | BWM CE NWA BVL DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_BVL_DGS_Spectrum Phase III_48 MHZ | CE | NWA | BVL | Bandwidth Management | BWM CE NWA BVL DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_BVL_DGS_Spectrum Phase III_48 MHZ | CE | NWA | BVL | Bandwidth Management | BWM CE NWA BVL DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_SAB_MSSA_Spectrum Phase II Start | CA | SAB | SAB | Bandwidth Management | BWM CA SAB SAB MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-15 | 2020-06-03 | Active | EP
BWM_SAB_MSSA_Spectrum Phase II Start | CA | SAB | SAB | Bandwidth Management | BWM CA SAB SAB MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2019-04-20 |  | Active | Log | New | SN-0055 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_SAB_MSSA_Spectrum Phase II Start | CA | SAB | SAB | Bandwidth Management | BWM CA SAB SAB MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_SAB_MSSA_Spectrum Phase II Start | CA | SAB | SAB | Bandwidth Management | BWM CA SAB SAB MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-07-13 | 2020-10-16 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_SAB_MSSA_Spectrum Phase II Start | CA | SAB | SAB | Bandwidth Management | BWM CA SAB SAB MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-15 | 2020-06-19 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_SAB_MSSA_Spectrum Phase II Start | CA | SAB | SAB | Bandwidth Management | BWM CA SAB SAB MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-15 | 2020-06-03 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_FLK_MSSA_Spectrum Phase II Start | VA | NVA | FLK | Bandwidth Management | BWM VA NVA FLK MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-09-16 | Active | EP
BWM_FLK_MSSA_Spectrum Phase II Start | VA | NVA | FLK | Bandwidth Management | BWM VA NVA FLK MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-30 | 2020-12-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_FLK_MSSA_Spectrum Phase II Start | VA | NVA | FLK | Bandwidth Management | BWM VA NVA FLK MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-12-30 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_FLK_MSSA_Spectrum Phase II Start | VA | NVA | FLK | Bandwidth Management | BWM VA NVA FLK MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-09-16 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_FLK_VIDEO SG_2020 DOCSIS node split-based Video SG | VA | NVA | FLK | Bandwidth Management | BWM VA NVA FLK Video SG Augment POR20 v2 | Labor | No Equipment | 1 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | EP
BWM_FST_MSSA_Spectrum Phase II Start | VA | NVA | FST | Bandwidth Management | BWM VA NVA FST MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-09-16 | Active | EP
BWM_FST_MSSA_Spectrum Phase II Start | VA | NVA | FST | Bandwidth Management | BWM VA NVA FST MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-30 | 2020-12-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_FST_MSSA_Spectrum Phase II Start | VA | NVA | FST | Bandwidth Management | BWM VA NVA FST MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-12-30 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_FST_MSSA_Spectrum Phase II Start | VA | NVA | FST | Bandwidth Management | BWM VA NVA FST MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-09-16 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_FBG_MSSA_Spectrum Phase II Start | VA | NVA | FBG | Bandwidth Management | BWM VA NVA FBG MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-09-16 | Active | EP
BWM_FBG_MSSA_Spectrum Phase II Start | VA | NVA | FBG | Bandwidth Management | BWM VA NVA FBG MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-30 | 2020-12-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_FBG_MSSA_Spectrum Phase II Start | VA | NVA | FBG | Bandwidth Management | BWM VA NVA FBG MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-12-30 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_FBG_MSSA_Spectrum Phase II Start | VA | NVA | FBG | Bandwidth Management | BWM VA NVA FBG MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-09-16 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_FBG_VIDEO SG_2020 DOCSIS node split-based Video SG | VA | NVA | FBG | Bandwidth Management | BWM VA NVA FBG Video SG Augment POR20 v2 | Labor | No Equipment | 1 |  | 2020-06-30 | 2020-06-30 | Active | EP
BWM_FBG_VIDEO SG_2020 DOCSIS node split-based Video SG | VA | NVA | FBG | Bandwidth Management | BWM VA NVA FBG Video SG Augment POR20 v2 | Labor | No Equipment | 1 |  | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0245 | Schedule Change | Approved | 2020-02-24 12:37 | 59 projects were made inactive on CR SN-0195 in error, I m reactivating these projects and VSG submited an revised plan 14 VSG projects removed and shifting some dates for the remaining projects
BWM_GCR_MSSA_Spectrum Phase II Start | VA | NVA | GCR | Bandwidth Management | BWM VA NVA GCR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-09-16 | Active | EP
BWM_GCR_MSSA_Spectrum Phase II Start | VA | NVA | GCR | Bandwidth Management | BWM VA NVA GCR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-30 | 2020-12-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_GCR_MSSA_Spectrum Phase II Start | VA | NVA | GCR | Bandwidth Management | BWM VA NVA GCR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-12-30 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_GCR_MSSA_Spectrum Phase II Start | VA | NVA | GCR | Bandwidth Management | BWM VA NVA GCR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-09-16 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_MFD_MSSA_Spectrum Phase II Start | VA | NVA | MFD | Bandwidth Management | BWM VA NVA MFD MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-09-16 | Active | EP
BWM_MFD_MSSA_Spectrum Phase II Start | VA | NVA | MFD | Bandwidth Management | BWM VA NVA MFD MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-30 | 2020-12-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_MFD_MSSA_Spectrum Phase II Start | VA | NVA | MFD | Bandwidth Management | BWM VA NVA MFD MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-12-30 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_MFD_MSSA_Spectrum Phase II Start | VA | NVA | MFD | Bandwidth Management | BWM VA NVA MFD MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-09-16 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_GLO_VIDEO SG_2020 DOCSIS node split-based Video SG | VA | HRD | GLO | Bandwidth Management | BWM VA HRD GLO Video SG Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 | 2020-06-30 | Active | EP
BWM_GLO_VIDEO SG_2020 DOCSIS node split-based Video SG | VA | HRD | GLO | Bandwidth Management | BWM VA HRD GLO Video SG Augment POR20 | Labor | No Equipment | 1 |  | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_GLO_VIDEO SG_2020 DOCSIS node split-based Video SG | VA | HRD | GLO | Bandwidth Management | BWM VA HRD GLO Video SG Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0245 | Schedule Change | Approved | 2020-02-24 12:37 | 59 projects were made inactive on CR SN-0195 in error, I m reactivating these projects and VSG submited an revised plan 14 VSG projects removed and shifting some dates for the remaining projects
BWM_NKT_MSSA_Spectrum Phase II Start | VA | HRD | NKT | Bandwidth Management | BWM VA HRD NKT MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-05-20 | Active | EP
BWM_NKT_MSSA_Spectrum Phase II Start | VA | HRD | NKT | Bandwidth Management | BWM VA HRD NKT MSSA Augment POR20 | Labor | No Equipment | 1 | 2029-10-01 | 2020-03-20 | 2020-03-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_NKT_MSSA_Spectrum Phase II Start | VA | HRD | NKT | Bandwidth Management | BWM VA HRD NKT MSSA Augment POR20 | Labor | No Equipment | 1 | 2029-10-01 | 2020-03-16 | 2020-06-05 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_NKT_MSSA_Spectrum Phase II Start | VA | HRD | NKT | Bandwidth Management | BWM VA HRD NKT MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-06-05 | Active | Log | Upd | SN-0587 | New | Approved | 2020-05-14 16:37 | Updated 12 Need by dates
BWM_NKT_MSSA_Spectrum Phase II Start | VA | HRD | NKT | Bandwidth Management | BWM VA HRD NKT MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-16 | 2020-05-20 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_NKT_VIDEO SG_2020 DOCSIS node split-based Video SG | VA | HRD | NKT | Bandwidth Management | BWM VA HRD NKT Video SG Augment POR20 v2 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | Active | EP
BWM_NKT_VIDEO SG_2020 DOCSIS node split-based Video SG | VA | HRD | NKT | Bandwidth Management | BWM VA HRD NKT Video SG Augment POR20 v2 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-30 | 2020-12-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_NKT_VIDEO SG_2020 DOCSIS node split-based Video SG | VA | HRD | NKT | Bandwidth Management | BWM VA HRD NKT Video SG Augment POR20 v2 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | Active | Log | Upd | SN-0245 | Schedule Change | Approved | 2020-02-24 12:37 | 59 projects were made inactive on CR SN-0195 in error, I m reactivating these projects and VSG submited an revised plan 14 VSG projects removed and shifting some dates for the remaining projects
BWM_RHL_MSSA_Spectrum Phase II Start | VA | NVA | RHL | Bandwidth Management | BWM VA NVA RHL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-09-16 | Active | EP
BWM_RHL_MSSA_Spectrum Phase II Start | VA | NVA | RHL | Bandwidth Management | BWM VA NVA RHL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-30 | 2020-12-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_RHL_MSSA_Spectrum Phase II Start | VA | NVA | RHL | Bandwidth Management | BWM VA NVA RHL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-12-30 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_RHL_MSSA_Spectrum Phase II Start | VA | NVA | RHL | Bandwidth Management | BWM VA NVA RHL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-09-16 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_TCR_MSSA_Spectrum Phase II Start | VA | NVA | TCR | Bandwidth Management | BWM VA NVA TCR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-06-01 | 2020-09-14 | 2020-09-16 | Active | EP
BWM_TCR_MSSA_Spectrum Phase II Start | VA | NVA | TCR | Bandwidth Management | BWM VA NVA TCR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-10-05 | 2020-09-14 | 2020-12-15 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_TCR_MSSA_Spectrum Phase II Start | VA | NVA | TCR | Bandwidth Management | BWM VA NVA TCR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-06-01 | 2020-09-14 | 2020-12-15 | Active | Log | Upd | SN-0587 | New | Approved | 2020-05-14 16:37 | Updated 12 Need by dates
BWM_TCR_MSSA_Spectrum Phase II Start | VA | NVA | TCR | Bandwidth Management | BWM VA NVA TCR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-06-01 | 2020-09-14 | 2020-09-16 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_TCR_VIDEO SG_2020 DOCSIS node split-based Video SG | VA | NVA | TCR | Bandwidth Management | BWM VA NVA TCR Video SG Augment POR20 v2 | Labor | No Equipment | 1 |  | 2020-09-30 | 2020-09-30 | Active | EP
BWM_TCR_VIDEO SG_2020 DOCSIS node split-based Video SG | VA | NVA | TCR | Bandwidth Management | BWM VA NVA TCR Video SG Augment POR20 v2 | Labor | No Equipment | 1 |  | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0245 | Schedule Change | Approved | 2020-02-24 12:37 | 59 projects were made inactive on CR SN-0195 in error, I m reactivating these projects and VSG submited an revised plan 14 VSG projects removed and shifting some dates for the remaining projects
BWM_OCL_MSSA_Spectrum Phase II Start | SE | GAN | OCL | Bandwidth Management | BWM SE GAN OCL MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-30 | 2020-03-30 | Active | EP
BWM_OCL_MSSA_Spectrum Phase II Start | SE | GAN | OCL | Bandwidth Management | BWM SE GAN OCL MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-31 | 2020-03-31 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_OCL_MSSA_Spectrum Phase II Start | SE | GAN | OCL | Bandwidth Management | BWM SE GAN OCL MSSA Augment POR20 | Labor | No Equipment | 1 | 2029-10-01 | 2020-03-30 | 2020-03-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_OCL_MSSA_Spectrum Phase II Start | SE | GAN | OCL | Bandwidth Management | BWM SE GAN OCL MSSA Augment POR20 | Labor | No Equipment | 1 | 2019-10-01 | 2020-03-30 | 2020-03-30 | Active | Log | Upd | SN-0587 | New | Approved | 2020-05-14 16:37 | Updated 12 Need by dates
BWM_OCL_VIDEO SG_2020 DOCSIS node split-based Video SG | SE | GAN | OCL | Bandwidth Management | BWM SE GAN OCL Video SG Augment POR20 v3 | Labor | No Equipment | 1 |  | 2020-06-30 | 2020-06-30 | Active | EP
BWM_OCL_VIDEO SG_2020 DOCSIS node split-based Video SG | SE | GAN | OCL | Bandwidth Management | BWM SE GAN OCL Video SG Augment POR20 v3 | Labor | No Equipment | 1 |  | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0245 | Schedule Change | Approved | 2020-02-24 12:37 | 59 projects were made inactive on CR SN-0195 in error, I m reactivating these projects and VSG submited an revised plan 14 VSG projects removed and shifting some dates for the remaining projects
BWM_GNS_DGS_Spectrum Phase III_48 MHZ | SE | GAN | GNS | Bandwidth Management | BWM SE GAN GNS DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_GNS_DGS_Spectrum Phase III_48 MHZ | SE | GAN | GNS | Bandwidth Management | BWM SE GAN GNS DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_GNS_DGS_Spectrum Phase III_48 MHZ | SE | GAN | GNS | Bandwidth Management | BWM SE GAN GNS DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_GNS_VIDEO SG_2020 DOCSIS node split-based Video SG | SE | GAN | GNS | Bandwidth Management | BWM SE GAN GNS Video SG Augment POR20 v4 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-15 | 2020-06-15 | Active | EP
BWM_PNS_MSSA_Spectrum Phase II Start | SE | GCT | PNS | Bandwidth Management | BWM SE GCT PNS MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-09-02 | Active | EP
BWM_PNS_MSSA_Spectrum Phase II Start | SE | GCT | PNS | Bandwidth Management | BWM SE GCT PNS MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_PNS_MSSA_Spectrum Phase II Start | SE | GCT | PNS | Bandwidth Management | BWM SE GCT PNS MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-01-27 | 2020-04-24 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_PNS_MSSA_Spectrum Phase II Start | SE | GCT | PNS | Bandwidth Management | BWM SE GCT PNS MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-11-13 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_PNS_MSSA_Spectrum Phase II Start | SE | GCT | PNS | Bandwidth Management | BWM SE GCT PNS MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-09-02 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_GRY_DGS_Spectrum Phase III_48 MHZ | SE | MGA | GRY | Bandwidth Management | BWM SE MGA GRY DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_GRY_DGS_Spectrum Phase III_48 MHZ | SE | MGA | GRY | Bandwidth Management | BWM SE MGA GRY DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_GRY_DGS_Spectrum Phase III_48 MHZ | SE | MGA | GRY | Bandwidth Management | BWM SE MGA GRY DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_MCN_DGS_Spectrum Phase III_48 MHZ | SE | MGA | MCN | Bandwidth Management | BWM SE MGA MCN DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_MCN_DGS_Spectrum Phase III_48 MHZ | SE | MGA | MCN | Bandwidth Management | BWM SE MGA MCN DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_MCN_DGS_Spectrum Phase III_48 MHZ | SE | MGA | MCN | Bandwidth Management | BWM SE MGA MCN DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_CRV_MSSA_Spectrum Phase II Start | SE | GCT | CRV | Bandwidth Management | BWM SE GCT CRV MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-09-02 | Active | EP
BWM_CRV_MSSA_Spectrum Phase II Start | SE | GCT | CRV | Bandwidth Management | BWM SE GCT CRV MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_CRV_MSSA_Spectrum Phase II Start | SE | GCT | CRV | Bandwidth Management | BWM SE GCT CRV MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-01-27 | 2020-04-24 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_CRV_MSSA_Spectrum Phase II Start | SE | GCT | CRV | Bandwidth Management | BWM SE GCT CRV MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-11-13 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_CRV_MSSA_Spectrum Phase II Start | SE | GCT | CRV | Bandwidth Management | BWM SE GCT CRV MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-09-02 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_CRV_VIDEO SG_2020 DOCSIS node split-based Video SG | SE | GCT | CRV | Bandwidth Management | BWM SE GCT CRV Video SG Augment POR20 v2 | Labor | No Equipment | 1 | 2020-10-01 | 2020-12-15 | 2020-12-15 | Active | EP
BWM_DES_MSSA_Spectrum Phase II Start | SE | GCT | DES | Bandwidth Management | BWM SE GCT DES MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-09-02 | Active | EP
BWM_DES_MSSA_Spectrum Phase II Start | SE | GCT | DES | Bandwidth Management | BWM SE GCT DES MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_DES_MSSA_Spectrum Phase II Start | SE | GCT | DES | Bandwidth Management | BWM SE GCT DES MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-01-27 | 2020-04-24 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_DES_MSSA_Spectrum Phase II Start | SE | GCT | DES | Bandwidth Management | BWM SE GCT DES MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-11-13 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_DES_MSSA_Spectrum Phase II Start | SE | GCT | DES | Bandwidth Management | BWM SE GCT DES MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-09-02 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_CRW_MSSA_Spectrum Phase II Start | SE | LFY | CRW | Bandwidth Management | BWM SE LFY CRW MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | Active | EP
BWM_CRW_MSSA_Spectrum Phase II Start | SE | LFY | CRW | Bandwidth Management | BWM SE LFY CRW MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_CRW_MSSA_Spectrum Phase II Start | SE | LFY | CRW | Bandwidth Management | BWM SE LFY CRW MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_CRW_MSSA_Spectrum Phase II Start | SE | LFY | CRW | Bandwidth Management | BWM SE LFY CRW MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-11-13 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_CRW_MSSA_Spectrum Phase II Start | SE | LFY | CRW | Bandwidth Management | BWM SE LFY CRW MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_CRW_DGS_Spectrum Phase III_48 MHZ | SE | LFY | CRW | Bandwidth Management | BWM SE LFY CRW DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_CRW_DGS_Spectrum Phase III_48 MHZ | SE | LFY | CRW | Bandwidth Management | BWM SE LFY CRW DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_CRW_DGS_Spectrum Phase III_48 MHZ | SE | LFY | CRW | Bandwidth Management | BWM SE LFY CRW DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_DNS_MSSA_Spectrum Phase II Start | SE | BTR | DNS | Bandwidth Management | BWM SE BTR DNS MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | Active | EP
BWM_DNS_MSSA_Spectrum Phase II Start | SE | BTR | DNS | Bandwidth Management | BWM SE BTR DNS MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_DNS_MSSA_Spectrum Phase II Start | SE | BTR | DNS | Bandwidth Management | BWM SE BTR DNS MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_DNS_MSSA_Spectrum Phase II Start | SE | BTR | DNS | Bandwidth Management | BWM SE BTR DNS MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-11-13 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_DNS_MSSA_Spectrum Phase II Start | SE | BTR | DNS | Bandwidth Management | BWM SE BTR DNS MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_DNS_DGS_Spectrum Phase III_48 MHZ | SE | BTR | DNS | Bandwidth Management | BWM SE BTR DNS DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_DNS_DGS_Spectrum Phase III_48 MHZ | SE | BTR | DNS | Bandwidth Management | BWM SE BTR DNS DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_DNS_DGS_Spectrum Phase III_48 MHZ | SE | BTR | DNS | Bandwidth Management | BWM SE BTR DNS DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_DVL_MSSA_Spectrum Phase II Start | SE | BTR | DVL | Bandwidth Management | BWM SE BTR DVL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | Active | EP
BWM_DVL_MSSA_Spectrum Phase II Start | SE | BTR | DVL | Bandwidth Management | BWM SE BTR DVL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_DVL_MSSA_Spectrum Phase II Start | SE | BTR | DVL | Bandwidth Management | BWM SE BTR DVL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_DVL_MSSA_Spectrum Phase II Start | SE | BTR | DVL | Bandwidth Management | BWM SE BTR DVL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-11-13 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_DVL_MSSA_Spectrum Phase II Start | SE | BTR | DVL | Bandwidth Management | BWM SE BTR DVL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_DVL_DGS_Spectrum Phase III_48 MHZ | SE | BTR | DVL | Bandwidth Management | BWM SE BTR DVL DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_DVL_DGS_Spectrum Phase III_48 MHZ | SE | BTR | DVL | Bandwidth Management | BWM SE BTR DVL DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_DVL_DGS_Spectrum Phase III_48 MHZ | SE | BTR | DVL | Bandwidth Management | BWM SE BTR DVL DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_ELM_MSSA_Spectrum Phase II Start | SE | NOR | ELM | Bandwidth Management | BWM SE NOR ELM MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-24 | 2020-09-15 | Active | EP
BWM_ELM_MSSA_Spectrum Phase II Start | SE | NOR | ELM | Bandwidth Management | BWM SE NOR ELM MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-30 | 2020-12-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_ELM_MSSA_Spectrum Phase II Start | SE | NOR | ELM | Bandwidth Management | BWM SE NOR ELM MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-10-09 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_ELM_MSSA_Spectrum Phase II Start | SE | NOR | ELM | Bandwidth Management | BWM SE NOR ELM MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-10-16 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_ELM_MSSA_Spectrum Phase II Start | SE | NOR | ELM | Bandwidth Management | BWM SE NOR ELM MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-24 | 2020-09-15 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_ELM_BAU SA_Spectrum Phase III | SE | NOR | ELM | Bandwidth Management | BWM SE NOR ELM BAU SA Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_ELM_BAU SA_Spectrum Phase III | SE | NOR | ELM | Bandwidth Management | BWM SE NOR ELM BAU SA Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0743 | New | Approved | 2020-07-10 10:14 | Removing SA SE NOR BAU projects which are duplicates of work being done in NOR for MSSA
BWM_ELM_VIDEO SG_2020 DOCSIS node split-based Video SG | SE | NOR | ELM | Bandwidth Management | BWM SE NOR ELM Video SG Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_ELM_VIDEO SG_2020 DOCSIS node split-based Video SG | SE | NOR | ELM | Bandwidth Management | BWM SE NOR ELM Video SG Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0245 | Schedule Change | Approved | 2020-02-24 12:37 | 59 projects were made inactive on CR SN-0195 in error, I m reactivating these projects and VSG submited an revised plan 14 VSG projects removed and shifting some dates for the remaining projects
BWM_ERW_MSSA_Spectrum Phase II Start | SE | BTR | ERW | Bandwidth Management | BWM SE BTR ERW MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | Active | EP
BWM_ERW_MSSA_Spectrum Phase II Start | SE | BTR | ERW | Bandwidth Management | BWM SE BTR ERW MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_ERW_MSSA_Spectrum Phase II Start | SE | BTR | ERW | Bandwidth Management | BWM SE BTR ERW MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_ERW_MSSA_Spectrum Phase II Start | SE | BTR | ERW | Bandwidth Management | BWM SE BTR ERW MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-11-13 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_ERW_MSSA_Spectrum Phase II Start | SE | BTR | ERW | Bandwidth Management | BWM SE BTR ERW MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_ERW_DGS_Spectrum Phase III_48 MHZ | SE | BTR | ERW | Bandwidth Management | BWM SE BTR ERW DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_ERW_DGS_Spectrum Phase III_48 MHZ | SE | BTR | ERW | Bandwidth Management | BWM SE BTR ERW DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_ERW_DGS_Spectrum Phase III_48 MHZ | SE | BTR | ERW | Bandwidth Management | BWM SE BTR ERW DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_FRK_MSSA_Spectrum Phase II Start | SE | LFY | FRK | Bandwidth Management | BWM SE LFY FRK MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | Active | EP
BWM_FRK_MSSA_Spectrum Phase II Start | SE | LFY | FRK | Bandwidth Management | BWM SE LFY FRK MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_FRK_MSSA_Spectrum Phase II Start | SE | LFY | FRK | Bandwidth Management | BWM SE LFY FRK MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_FRK_MSSA_Spectrum Phase II Start | SE | LFY | FRK | Bandwidth Management | BWM SE LFY FRK MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-11-13 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_FRK_MSSA_Spectrum Phase II Start | SE | LFY | FRK | Bandwidth Management | BWM SE LFY FRK MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_FRK_DGS_Spectrum Phase III_48 MHZ | SE | LFY | FRK | Bandwidth Management | BWM SE LFY FRK DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_FRK_DGS_Spectrum Phase III_48 MHZ | SE | LFY | FRK | Bandwidth Management | BWM SE LFY FRK DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_FRK_DGS_Spectrum Phase III_48 MHZ | SE | LFY | FRK | Bandwidth Management | BWM SE LFY FRK DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_GNZ_MSSA_Spectrum Phase II Start | SE | BTR | GNZ | Bandwidth Management | BWM SE BTR GNZ MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | Active | EP
BWM_GNZ_MSSA_Spectrum Phase II Start | SE | BTR | GNZ | Bandwidth Management | BWM SE BTR GNZ MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_GNZ_MSSA_Spectrum Phase II Start | SE | BTR | GNZ | Bandwidth Management | BWM SE BTR GNZ MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_GNZ_MSSA_Spectrum Phase II Start | SE | BTR | GNZ | Bandwidth Management | BWM SE BTR GNZ MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-11-13 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_GNZ_MSSA_Spectrum Phase II Start | SE | BTR | GNZ | Bandwidth Management | BWM SE BTR GNZ MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_LFY_DGS_Spectrum Phase III_48 MHZ | SE | LFY | LFY | Bandwidth Management | BWM SE LFY LFY DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_LFY_DGS_Spectrum Phase III_48 MHZ | SE | LFY | LFY | Bandwidth Management | BWM SE LFY LFY DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_LFY_DGS_Spectrum Phase III_48 MHZ | SE | LFY | LFY | Bandwidth Management | BWM SE LFY LFY DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_LPL_MSSA_Spectrum Phase II Start | SE | NOR | LPL | Bandwidth Management | BWM SE NOR LPL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-24 | 2020-09-15 | Active | EP
BWM_LPL_MSSA_Spectrum Phase II Start | SE | NOR | LPL | Bandwidth Management | BWM SE NOR LPL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-30 | 2020-12-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_LPL_MSSA_Spectrum Phase II Start | SE | NOR | LPL | Bandwidth Management | BWM SE NOR LPL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-10-09 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_LPL_MSSA_Spectrum Phase II Start | SE | NOR | LPL | Bandwidth Management | BWM SE NOR LPL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-10-16 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_LPL_MSSA_Spectrum Phase II Start | SE | NOR | LPL | Bandwidth Management | BWM SE NOR LPL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-24 | 2020-09-15 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_LPL_BAU SA_Spectrum Phase III | SE | NOR | LPL | Bandwidth Management | BWM SE NOR LPL BAU SA Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_LPL_BAU SA_Spectrum Phase III | SE | NOR | LPL | Bandwidth Management | BWM SE NOR LPL BAU SA Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0743 | New | Approved | 2020-07-10 10:14 | Removing SA SE NOR BAU projects which are duplicates of work being done in NOR for MSSA
BWM_LUL_MSSA_Spectrum Phase II Start | SE | NOR | LUL | Bandwidth Management | BWM SE NOR LUL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-24 | 2020-09-15 | Active | EP
BWM_LUL_MSSA_Spectrum Phase II Start | SE | NOR | LUL | Bandwidth Management | BWM SE NOR LUL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-30 | 2020-12-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_LUL_MSSA_Spectrum Phase II Start | SE | NOR | LUL | Bandwidth Management | BWM SE NOR LUL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-10-09 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_LUL_MSSA_Spectrum Phase II Start | SE | NOR | LUL | Bandwidth Management | BWM SE NOR LUL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-10-16 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_LUL_MSSA_Spectrum Phase II Start | SE | NOR | LUL | Bandwidth Management | BWM SE NOR LUL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-24 | 2020-09-15 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_LUL_BAU SA_Spectrum Phase III | SE | NOR | LUL | Bandwidth Management | BWM SE NOR LUL BAU SA Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_LUL_BAU SA_Spectrum Phase III | SE | NOR | LUL | Bandwidth Management | BWM SE NOR LUL BAU SA Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0743 | New | Approved | 2020-07-10 10:14 | Removing SA SE NOR BAU projects which are duplicates of work being done in NOR for MSSA
BWM_MCY_MSSA_Spectrum Phase II Start | SE | NOR | MCY | Bandwidth Management | BWM SE NOR MCY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-24 | 2020-09-15 | Active | EP
BWM_MCY_MSSA_Spectrum Phase II Start | SE | NOR | MCY | Bandwidth Management | BWM SE NOR MCY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-30 | 2020-12-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_MCY_MSSA_Spectrum Phase II Start | SE | NOR | MCY | Bandwidth Management | BWM SE NOR MCY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-10-09 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_MCY_MSSA_Spectrum Phase II Start | SE | NOR | MCY | Bandwidth Management | BWM SE NOR MCY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-10-16 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_MCY_MSSA_Spectrum Phase II Start | SE | NOR | MCY | Bandwidth Management | BWM SE NOR MCY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-24 | 2020-09-15 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_MCY_BAU SA_Spectrum Phase III | SE | NOR | MCY | Bandwidth Management | BWM SE NOR MCY BAU SA Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_MCY_BAU SA_Spectrum Phase III | SE | NOR | MCY | Bandwidth Management | BWM SE NOR MCY BAU SA Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0743 | New | Approved | 2020-07-10 10:14 | Removing SA SE NOR BAU projects which are duplicates of work being done in NOR for MSSA
BWM_NIB_MSSA_Spectrum Phase II Start | SE | LFY | NIB | Bandwidth Management | BWM SE LFY NIB MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | Active | EP
BWM_NIB_MSSA_Spectrum Phase II Start | SE | LFY | NIB | Bandwidth Management | BWM SE LFY NIB MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_NIB_MSSA_Spectrum Phase II Start | SE | LFY | NIB | Bandwidth Management | BWM SE LFY NIB MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_NIB_MSSA_Spectrum Phase II Start | SE | LFY | NIB | Bandwidth Management | BWM SE LFY NIB MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-11-13 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_NIB_MSSA_Spectrum Phase II Start | SE | LFY | NIB | Bandwidth Management | BWM SE LFY NIB MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_NIB_DGS_Spectrum Phase III_48 MHZ | SE | LFY | NIB | Bandwidth Management | BWM SE LFY NIB DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_NIB_DGS_Spectrum Phase III_48 MHZ | SE | LFY | NIB | Bandwidth Management | BWM SE LFY NIB DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_NIB_DGS_Spectrum Phase III_48 MHZ | SE | LFY | NIB | Bandwidth Management | BWM SE LFY NIB DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_NOE_MSSA_Spectrum Phase II Start | SE | NOR | NOE | Bandwidth Management | BWM SE NOR NOE MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-24 | 2020-09-15 | Active | EP
BWM_NOE_MSSA_Spectrum Phase II Start | SE | NOR | NOE | Bandwidth Management | BWM SE NOR NOE MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-30 | 2020-12-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_NOE_MSSA_Spectrum Phase II Start | SE | NOR | NOE | Bandwidth Management | BWM SE NOR NOE MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-10-09 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_NOE_MSSA_Spectrum Phase II Start | SE | NOR | NOE | Bandwidth Management | BWM SE NOR NOE MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-10-16 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_NOE_MSSA_Spectrum Phase II Start | SE | NOR | NOE | Bandwidth Management | BWM SE NOR NOE MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-24 | 2020-09-15 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_NOE_BAU SA_Spectrum Phase III | SE | NOR | NOE | Bandwidth Management | BWM SE NOR NOE BAU SA Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_NOE_BAU SA_Spectrum Phase III | SE | NOR | NOE | Bandwidth Management | BWM SE NOR NOE BAU SA Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0743 | New | Approved | 2020-07-10 10:14 | Removing SA SE NOR BAU projects which are duplicates of work being done in NOR for MSSA
BWM_NOE_VIDEO SG_2020 DOCSIS node split-based Video SG | SE | NOR | NOE | Bandwidth Management | BWM SE NOR NOE Video SG Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_NOE_VIDEO SG_2020 DOCSIS node split-based Video SG | SE | NOR | NOE | Bandwidth Management | BWM SE NOR NOE Video SG Augment POR20 v3 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-01 | Deleted | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_NOE_VIDEO SG_2020 DOCSIS node split-based Video SG | SE | NOR | NOE | Bandwidth Management | BWM SE NOR NOE Video SG Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0245 | Schedule Change | Approved | 2020-02-24 12:37 | 59 projects were made inactive on CR SN-0195 in error, I m reactivating these projects and VSG submited an revised plan 14 VSG projects removed and shifting some dates for the remaining projects
BWM_NTH_MSSA_Spectrum Phase II Start | SE | BTR | NTH | Bandwidth Management | BWM SE BTR NTH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | Active | EP
BWM_NTH_MSSA_Spectrum Phase II Start | SE | BTR | NTH | Bandwidth Management | BWM SE BTR NTH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_NTH_MSSA_Spectrum Phase II Start | SE | BTR | NTH | Bandwidth Management | BWM SE BTR NTH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_NTH_MSSA_Spectrum Phase II Start | SE | BTR | NTH | Bandwidth Management | BWM SE BTR NTH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-11-13 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_NTH_MSSA_Spectrum Phase II Start | SE | BTR | NTH | Bandwidth Management | BWM SE BTR NTH MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_NTH_DGS_Spectrum Phase III_48 MHZ | SE | BTR | NTH | Bandwidth Management | BWM SE BTR NTH DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_NTH_DGS_Spectrum Phase III_48 MHZ | SE | BTR | NTH | Bandwidth Management | BWM SE BTR NTH DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_NTH_DGS_Spectrum Phase III_48 MHZ | SE | BTR | NTH | Bandwidth Management | BWM SE BTR NTH DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_PLQ_MSSA_Spectrum Phase II Start | SE | BTR | PLQ | Bandwidth Management | BWM SE BTR PLQ MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | Active | EP
BWM_PLQ_MSSA_Spectrum Phase II Start | SE | BTR | PLQ | Bandwidth Management | BWM SE BTR PLQ MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_PLQ_MSSA_Spectrum Phase II Start | SE | BTR | PLQ | Bandwidth Management | BWM SE BTR PLQ MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_PLQ_MSSA_Spectrum Phase II Start | SE | BTR | PLQ | Bandwidth Management | BWM SE BTR PLQ MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-11-13 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_PLQ_MSSA_Spectrum Phase II Start | SE | BTR | PLQ | Bandwidth Management | BWM SE BTR PLQ MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_PLQ_DGS_Spectrum Phase III_48 MHZ | SE | BTR | PLQ | Bandwidth Management | BWM SE BTR PLQ DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_PLQ_DGS_Spectrum Phase III_48 MHZ | SE | BTR | PLQ | Bandwidth Management | BWM SE BTR PLQ DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_PLQ_DGS_Spectrum Phase III_48 MHZ | SE | BTR | PLQ | Bandwidth Management | BWM SE BTR PLQ DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_SPC_MSSA_Spectrum Phase II Start | SE | BTR | SPC | Bandwidth Management | BWM SE BTR SPC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | Active | EP
BWM_SPC_MSSA_Spectrum Phase II Start | SE | BTR | SPC | Bandwidth Management | BWM SE BTR SPC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_SPC_MSSA_Spectrum Phase II Start | SE | BTR | SPC | Bandwidth Management | BWM SE BTR SPC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_SPC_MSSA_Spectrum Phase II Start | SE | BTR | SPC | Bandwidth Management | BWM SE BTR SPC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-11-13 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_SPC_MSSA_Spectrum Phase II Start | SE | BTR | SPC | Bandwidth Management | BWM SE BTR SPC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_SPC_DGS_Spectrum Phase III_48 MHZ | SE | BTR | SPC | Bandwidth Management | BWM SE BTR SPC DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_SPC_DGS_Spectrum Phase III_48 MHZ | SE | BTR | SPC | Bandwidth Management | BWM SE BTR SPC DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_SPC_DGS_Spectrum Phase III_48 MHZ | SE | BTR | SPC | Bandwidth Management | BWM SE BTR SPC DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_STB_MSSA_Spectrum Phase II Start | SE | NOR | STB | Bandwidth Management | BWM SE NOR STB MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-24 | 2020-09-15 | Active | EP
BWM_STB_MSSA_Spectrum Phase II Start | SE | NOR | STB | Bandwidth Management | BWM SE NOR STB MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-30 | 2020-12-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_STB_MSSA_Spectrum Phase II Start | SE | NOR | STB | Bandwidth Management | BWM SE NOR STB MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-10-09 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_STB_MSSA_Spectrum Phase II Start | SE | NOR | STB | Bandwidth Management | BWM SE NOR STB MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-10-16 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_STB_MSSA_Spectrum Phase II Start | SE | NOR | STB | Bandwidth Management | BWM SE NOR STB MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-24 | 2020-09-15 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_STB_BAU SA_Spectrum Phase III | SE | NOR | STB | Bandwidth Management | BWM SE NOR STB BAU SA Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_STB_BAU SA_Spectrum Phase III | SE | NOR | STB | Bandwidth Management | BWM SE NOR STB BAU SA Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0743 | New | Approved | 2020-07-10 10:14 | Removing SA SE NOR BAU projects which are duplicates of work being done in NOR for MSSA
BWM_STC_MSSA_Spectrum Phase II Start | SE | BTR | STC | Bandwidth Management | BWM SE BTR STC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | Active | EP
BWM_STC_MSSA_Spectrum Phase II Start | SE | BTR | STC | Bandwidth Management | BWM SE BTR STC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_STC_MSSA_Spectrum Phase II Start | SE | BTR | STC | Bandwidth Management | BWM SE BTR STC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_STC_MSSA_Spectrum Phase II Start | SE | BTR | STC | Bandwidth Management | BWM SE BTR STC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-11-13 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_STC_MSSA_Spectrum Phase II Start | SE | BTR | STC | Bandwidth Management | BWM SE BTR STC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_STC_DGS_Spectrum Phase III_48 MHZ | SE | BTR | STC | Bandwidth Management | BWM SE BTR STC DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_STC_DGS_Spectrum Phase III_48 MHZ | SE | BTR | STC | Bandwidth Management | BWM SE BTR STC DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_STC_DGS_Spectrum Phase III_48 MHZ | SE | BTR | STC | Bandwidth Management | BWM SE BTR STC DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_STM_MSSA_Spectrum Phase II Start | SE | LFY | STM | Bandwidth Management | BWM SE LFY STM MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | Active | EP
BWM_STM_MSSA_Spectrum Phase II Start | SE | LFY | STM | Bandwidth Management | BWM SE LFY STM MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_STM_MSSA_Spectrum Phase II Start | SE | LFY | STM | Bandwidth Management | BWM SE LFY STM MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_STM_MSSA_Spectrum Phase II Start | SE | LFY | STM | Bandwidth Management | BWM SE LFY STM MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-11-13 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_STM_MSSA_Spectrum Phase II Start | SE | LFY | STM | Bandwidth Management | BWM SE LFY STM MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_ABV_MSSA_Spectrum Phase II Start | SE | LFY | ABV | Bandwidth Management | BWM SE LFY ABV Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-08-01 | 2020-09-15 | 2020-09-15 | Active | EP
BWM_ABV_MSSA_Spectrum Phase II Start | SE | LFY | ABV | Bandwidth Management | BWM SE LFY ABV Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-08-01 | 2020-09-15 | 2020-09-15 | Active | Log | Upd | SN-0587 | New | Approved | 2020-05-14 16:37 | Updated 12 Need by dates
BWM_ALG_MSSA_Spectrum Phase II Start | SE | NOR | ALG | Bandwidth Management | BWM SE NOR ALG MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-24 | 2020-09-15 | Active | EP
BWM_ALG_MSSA_Spectrum Phase II Start | SE | NOR | ALG | Bandwidth Management | BWM SE NOR ALG MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-30 | 2020-12-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_ALG_MSSA_Spectrum Phase II Start | SE | NOR | ALG | Bandwidth Management | BWM SE NOR ALG MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-10-09 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_ALG_MSSA_Spectrum Phase II Start | SE | NOR | ALG | Bandwidth Management | BWM SE NOR ALG MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-10-16 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_ALG_MSSA_Spectrum Phase II Start | SE | NOR | ALG | Bandwidth Management | BWM SE NOR ALG MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-24 | 2020-09-15 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_BTR_MSSA_Spectrum Phase II Start | SE | BTR | BTR | Bandwidth Management | BWM SE BTR BTR MSSA _Labor Only_Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | Active | EP
BWM_BTR_MSSA_Spectrum Phase II Start | SE | BTR | BTR | Bandwidth Management | BWM SE BTR BTR MSSA _Labor Only_Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_BTR_MSSA_Spectrum Phase II Start | SE | BTR | BTR | Bandwidth Management | BWM SE BTR BTR MSSA _Labor Only_Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_BTR_MSSA_Spectrum Phase II Start | SE | BTR | BTR | Bandwidth Management | BWM SE BTR BTR MSSA _Labor Only_Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-11-13 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_BTR_MSSA_Spectrum Phase II Start | SE | BTR | BTR | Bandwidth Management | BWM SE BTR BTR MSSA _Labor Only_Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_BTR_DGS_Spectrum Phase III_48 MHZ | SE | BTR | BTR | Bandwidth Management | BWM SE BTR BTR DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_BTR_DGS_Spectrum Phase III_48 MHZ | SE | BTR | BTR | Bandwidth Management | BWM SE BTR BTR DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_BTR_DGS_Spectrum Phase III_48 MHZ | SE | BTR | BTR | Bandwidth Management | BWM SE BTR BTR DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_CLR_MSSA_Spectrum Phase II Start | SE | NOR | CLR | Bandwidth Management | BWM SE NOR CLR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-24 | 2020-09-15 | Active | EP
BWM_CLR_MSSA_Spectrum Phase II Start | SE | NOR | CLR | Bandwidth Management | BWM SE NOR CLR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-30 | 2020-12-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_CLR_MSSA_Spectrum Phase II Start | SE | NOR | CLR | Bandwidth Management | BWM SE NOR CLR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-10-09 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_CLR_MSSA_Spectrum Phase II Start | SE | NOR | CLR | Bandwidth Management | BWM SE NOR CLR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-10-16 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_CLR_MSSA_Spectrum Phase II Start | SE | NOR | CLR | Bandwidth Management | BWM SE NOR CLR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-24 | 2020-09-15 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_GNZ_DGS_Spectrum Phase III_48 MHZ | SE | BTR | GNZ | Bandwidth Management | BWM SE BTR GNZ DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_GNZ_DGS_Spectrum Phase III_48 MHZ | SE | BTR | GNZ | Bandwidth Management | BWM SE BTR GNZ DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_GNZ_DGS_Spectrum Phase III_48 MHZ | SE | BTR | GNZ | Bandwidth Management | BWM SE BTR GNZ DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_KNN_MSSA_Spectrum Phase II Start | SE | NOR | KNN | Bandwidth Management | BWM SE NOR KNN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-24 | 2020-09-15 | Active | EP
BWM_KNN_MSSA_Spectrum Phase II Start | SE | NOR | KNN | Bandwidth Management | BWM SE NOR KNN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-30 | 2020-12-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_KNN_MSSA_Spectrum Phase II Start | SE | NOR | KNN | Bandwidth Management | BWM SE NOR KNN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-10-09 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_KNN_MSSA_Spectrum Phase II Start | SE | NOR | KNN | Bandwidth Management | BWM SE NOR KNN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-14 | 2020-10-16 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_KNN_MSSA_Spectrum Phase II Start | SE | NOR | KNN | Bandwidth Management | BWM SE NOR KNN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-24 | 2020-09-15 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_KNN_BAU SA_Spectrum Phase III | SE | NOR | KNN | Bandwidth Management | BWM SE NOR KNN BAU SA Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_KNN_BAU SA_Spectrum Phase III | SE | NOR | KNN | Bandwidth Management | BWM SE NOR KNN BAU SA Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0743 | New | Approved | 2020-07-10 10:14 | Removing SA SE NOR BAU projects which are duplicates of work being done in NOR for MSSA
BWM_LFY_MSSA_Spectrum Phase II Start | SE | LFY | LFY | Bandwidth Management | BWM SE LFY LFY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | Active | EP
BWM_LFY_MSSA_Spectrum Phase II Start | SE | LFY | LFY | Bandwidth Management | BWM SE LFY LFY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-09-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_LFY_MSSA_Spectrum Phase II Start | SE | LFY | LFY | Bandwidth Management | BWM SE LFY LFY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-09-01 | 2020-08-24 | 2020-11-13 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_LFY_MSSA_Spectrum Phase II Start | SE | LFY | LFY | Bandwidth Management | BWM SE LFY LFY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-24 | 2020-11-13 | Active | Log | Upd | SN-0587 | New | Approved | 2020-05-14 16:37 | Updated 12 Need by dates
BWM_LFY_MSSA_Spectrum Phase II Start | SE | LFY | LFY | Bandwidth Management | BWM SE LFY LFY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-08-26 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_STM_DGS_Spectrum Phase III_48 MHZ | SE | LFY | STM | Bandwidth Management | BWM SE LFY STM DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_STM_DGS_Spectrum Phase III_48 MHZ | SE | LFY | STM | Bandwidth Management | BWM SE LFY STM DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_STM_DGS_Spectrum Phase III_48 MHZ | SE | LFY | STM | Bandwidth Management | BWM SE LFY STM DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_SCT_MSSA_Spectrum Phase II Start | NE | RHD | SCT | Bandwidth Management | BWM NE RHD SCT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-07-08 | Active | EP
BWM_SCT_MSSA_Spectrum Phase II Start | NE | RHD | SCT | Bandwidth Management | BWM NE RHD SCT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_SCT_MSSA_Spectrum Phase II Start | NE | RHD | SCT | Bandwidth Management | BWM NE RHD SCT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_SCT_MSSA_Spectrum Phase II Start | NE | RHD | SCT | Bandwidth Management | BWM NE RHD SCT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-08-28 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_SCT_MSSA_Spectrum Phase II Start | NE | RHD | SCT | Bandwidth Management | BWM NE RHD SCT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-07-08 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_SCT_DGS_Spectrum Phase III_48 MHZ | NE | RHD | SCT | Bandwidth Management | BWM NE RHD SCT DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_SCT_DGS_Spectrum Phase III_48 MHZ | NE | RHD | SCT | Bandwidth Management | BWM NE RHD SCT DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_SCT_DGS_Spectrum Phase III_48 MHZ | NE | RHD | SCT | Bandwidth Management | BWM NE RHD SCT DGS Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_WWK_MSSA_Spectrum Phase II Start | NE | RHD | WWK | Bandwidth Management | BWM NE RHD WWK MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-07-08 | Active | EP
BWM_WWK_MSSA_Spectrum Phase II Start | NE | RHD | WWK | Bandwidth Management | BWM NE RHD WWK MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_WWK_MSSA_Spectrum Phase II Start | NE | RHD | WWK | Bandwidth Management | BWM NE RHD WWK MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_WWK_MSSA_Spectrum Phase II Start | NE | RHD | WWK | Bandwidth Management | BWM NE RHD WWK MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-08-28 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_WWK_MSSA_Spectrum Phase II Start | NE | RHD | WWK | Bandwidth Management | BWM NE RHD WWK MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-29 | 2020-07-08 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_IND_MSSA_Spectrum Phase II Start | CE | TUL | IND | Bandwidth Management | BWM CE TUL IND MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-06-11 | Active | EP
BWM_IND_MSSA_Spectrum Phase II Start | CE | TUL | IND | Bandwidth Management | BWM CE TUL IND MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_IND_MSSA_Spectrum Phase II Start | CE | TUL | IND | Bandwidth Management | BWM CE TUL IND MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-07-31 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_IND_MSSA_Spectrum Phase II Start | CE | TUL | IND | Bandwidth Management | BWM CE TUL IND MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-07-31 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_IND_MSSA_Spectrum Phase II Start | CE | TUL | IND | Bandwidth Management | BWM CE TUL IND MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-06-11 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_ONA_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | OKC | NOR | Bandwidth Management | BWM CE OKC NOR VIDEO SG Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-15 | 2020-06-15 | Active | EP
BWM_VBN_MSSA_Spectrum Phase II Start | CE | NWA | VBN | Bandwidth Management | BWM CE NWA VBN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-24 | Active | EP
BWM_VBN_MSSA_Spectrum Phase II Start | CE | NWA | VBN | Bandwidth Management | BWM CE NWA VBN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_VBN_MSSA_Spectrum Phase II Start | CE | NWA | VBN | Bandwidth Management | BWM CE NWA VBN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_VBN_MSSA_Spectrum Phase II Start | CE | NWA | VBN | Bandwidth Management | BWM CE NWA VBN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-08-14 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_VBN_MSSA_Spectrum Phase II Start | CE | NWA | VBN | Bandwidth Management | BWM CE NWA VBN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-24 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_GAR_MSSA_Spectrum Phase II Start | CE | TUL | GAR | Bandwidth Management | BWM CE TUL GAR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-06-11 | Active | EP
BWM_GAR_MSSA_Spectrum Phase II Start | CE | TUL | GAR | Bandwidth Management | BWM CE KAN WIC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_GAR_MSSA_Spectrum Phase II Start | CE | TUL | GAR | Bandwidth Management | BWM CE TUL GAR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-07-31 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_GAR_MSSA_Spectrum Phase II Start | CE | TUL | GAR | Bandwidth Management | BWM CE TUL GAR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-07-31 | Active | Log | Upd | SN-0473 | New | Approved | 2020-04-17 16:09 | 4 projects are showing the incorrect project name on the POR, making the correction on this CR
BWM_GAR_MSSA_Spectrum Phase II Start | CE | TUL | GAR | Bandwidth Management | BWM CE TUL GAR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-07-31 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_GAR_MSSA_Spectrum Phase II Start | CE | TUL | GAR | Bandwidth Management | BWM CE TUL GAR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-06-11 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_WIC_MSSA_Spectrum Phase II Start | CE | KAN | WIC | Bandwidth Management | BWM CE KAN WIC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | Active | EP
BWM_WIC_MSSA_Spectrum Phase II Start | CE | KAN | WIC | Bandwidth Management | BWM CE KAN WIC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_WIC_MSSA_Spectrum Phase II Start | CE | KAN | WIC | Bandwidth Management | BWM CE KAN WIC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_WIC_MSSA_Spectrum Phase II Start | CE | KAN | WIC | Bandwidth Management | BWM CE KAN WIC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-08-14 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_WIC_MSSA_Spectrum Phase II Start | CE | KAN | WIC | Bandwidth Management | BWM CE KAN WIC MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_WIC_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | KAN | WIC | Bandwidth Management | BWM CE KAN WIC VIDEO SG Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-15 | 2020-06-15 | Active | EP
BWM_BRD_MSSA_Spectrum Phase II Start | CE | TUL | BRD | Bandwidth Management | BWM CE TUL BRD MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-06-11 | Active | EP
BWM_BRD_MSSA_Spectrum Phase II Start | CE | TUL | BRD | Bandwidth Management | BWM CE TUL BRD MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_BRD_MSSA_Spectrum Phase II Start | CE | TUL | BRD | Bandwidth Management | BWM CE TUL BRD MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-07-31 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_BRD_MSSA_Spectrum Phase II Start | CE | TUL | BRD | Bandwidth Management | BWM CE TUL BRD MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-07-31 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_BRD_MSSA_Spectrum Phase II Start | CE | TUL | BRD | Bandwidth Management | BWM CE TUL BRD MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-06-11 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_BRD_VIDEO SG_2020 DOCSIS node split-based Video SG Calculations per facility Dup1 | CE | TUL | BRD | Bandwidth Management | BWM CE TUL BRD VIDEO SG Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-15 | 2020-09-15 | Deleted | EP
BWM_BAR_MSSA_Spectrum Phase II Start | CE | TUL | BAR | Bandwidth Management | BWM CE TUL BAR MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-06-11 | Active | EP
BWM_BAR_MSSA_Spectrum Phase II Start | CE | TUL | BAR | Bandwidth Management | BWM CE TUL BAR MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_BAR_MSSA_Spectrum Phase II Start | CE | TUL | BAR | Bandwidth Management | BWM CE TUL BAR MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-07-31 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_BAR_MSSA_Spectrum Phase II Start | CE | TUL | BAR | Bandwidth Management | BWM CE TUL BAR MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-07-31 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_BAR_MSSA_Spectrum Phase II Start | CE | TUL | BAR | Bandwidth Management | BWM CE TUL BAR MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-06-11 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_CLA_MSSA_Spectrum Phase II Start | CE | TUL | CLA | Bandwidth Management | BWM CE TUL CLA MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-06-11 | Active | EP
BWM_CLA_MSSA_Spectrum Phase II Start | CE | TUL | CLA | Bandwidth Management | BWM CE TUL CLA MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_CLA_MSSA_Spectrum Phase II Start | CE | TUL | CLA | Bandwidth Management | BWM CE TUL CLA MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-07-31 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_CLA_MSSA_Spectrum Phase II Start | CE | TUL | CLA | Bandwidth Management | BWM CE TUL CLA MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-07-31 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_CLA_MSSA_Spectrum Phase II Start | CE | TUL | CLA | Bandwidth Management | BWM CE TUL CLA MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-06-11 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_DTN_MSSA_Spectrum Phase II Start | CE | TUL | DTN | Bandwidth Management | BWM CE TUL DTN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-06-11 | Active | EP
BWM_DTN_MSSA_Spectrum Phase II Start | CE | TUL | DTN | Bandwidth Management | BWM CE TUL DTN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_DTN_MSSA_Spectrum Phase II Start | CE | TUL | DTN | Bandwidth Management | BWM CE TUL DTN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-07-31 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_DTN_MSSA_Spectrum Phase II Start | CE | TUL | DTN | Bandwidth Management | BWM CE TUL DTN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-07-31 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_DTN_MSSA_Spectrum Phase II Start | CE | TUL | DTN | Bandwidth Management | BWM CE TUL DTN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-08 | 2020-06-11 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_FTS_MSSA_Spectrum Phase II Start | CE | NWA | FTS | Bandwidth Management | BWM CE NWA FTS MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-24 | Active | EP
BWM_FTS_MSSA_Spectrum Phase II Start | CE | NWA | FTS | Bandwidth Management | BWM CE NWA FTS MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_FTS_MSSA_Spectrum Phase II Start | CE | NWA | FTS | Bandwidth Management | BWM CE NWA FTS MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_FTS_MSSA_Spectrum Phase II Start | CE | NWA | FTS | Bandwidth Management | BWM CE NWA FTS MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-08-14 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_FTS_MSSA_Spectrum Phase II Start | CE | NWA | FTS | Bandwidth Management | BWM CE NWA FTS MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-24 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_GDY_MSSA_Spectrum Phase II Start | CE | KAN | GDY | Bandwidth Management | BWM CE KAN GDY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | Active | EP
BWM_GDY_MSSA_Spectrum Phase II Start | CE | KAN | GDY | Bandwidth Management | BWM CE KAN GDY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_GDY_MSSA_Spectrum Phase II Start | CE | KAN | GDY | Bandwidth Management | BWM CE KAN GDY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_GDY_MSSA_Spectrum Phase II Start | CE | KAN | GDY | Bandwidth Management | BWM CE KAN GDY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-08-14 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_GDY_MSSA_Spectrum Phase II Start | CE | KAN | GDY | Bandwidth Management | BWM CE KAN GDY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_GBD_MSSA_Spectrum Phase II Start | CE | KAN | GBD | Bandwidth Management | BWM CE KAN GBD MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | Active | EP
BWM_GBD_MSSA_Spectrum Phase II Start | CE | KAN | GBD | Bandwidth Management | BWM CE KAN GBD MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_GBD_MSSA_Spectrum Phase II Start | CE | KAN | GBD | Bandwidth Management | BWM CE KAN GBD MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_GBD_MSSA_Spectrum Phase II Start | CE | KAN | GBD | Bandwidth Management | BWM CE KAN GBD MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-08-14 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_GBD_MSSA_Spectrum Phase II Start | CE | KAN | GBD | Bandwidth Management | BWM CE KAN GBD MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_HRN_MSSA_Spectrum Phase II Start | CE | NWA | HRN | Bandwidth Management | BWM CE NWA HRN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-24 | Active | EP
BWM_HRN_MSSA_Spectrum Phase II Start | CE | NWA | HRN | Bandwidth Management | BWM CE NWA HRN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_HRN_MSSA_Spectrum Phase II Start | CE | NWA | HRN | Bandwidth Management | BWM CE NWA HRN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_HRN_MSSA_Spectrum Phase II Start | CE | NWA | HRN | Bandwidth Management | BWM CE NWA HRN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-08-14 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_HRN_MSSA_Spectrum Phase II Start | CE | NWA | HRN | Bandwidth Management | BWM CE NWA HRN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-24 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_HUT_MSSA_Spectrum Phase II Start | CE | KAN | HUT | Bandwidth Management | BWM CE KAN HUT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | Active | EP
BWM_HUT_MSSA_Spectrum Phase II Start | CE | KAN | HUT | Bandwidth Management | BWM CE KAN HUT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_HUT_MSSA_Spectrum Phase II Start | CE | KAN | HUT | Bandwidth Management | BWM CE KAN HUT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_HUT_MSSA_Spectrum Phase II Start | CE | KAN | HUT | Bandwidth Management | BWM CE KAN HUT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-08-14 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_HUT_MSSA_Spectrum Phase II Start | CE | KAN | HUT | Bandwidth Management | BWM CE KAN HUT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_OLA_MSSA_Spectrum Phase II Start | CE | KAN | OLA | Bandwidth Management | BWM CE KAN OLA MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | Active | EP
BWM_OLA_MSSA_Spectrum Phase II Start | CE | KAN | OLA | Bandwidth Management | BWM CE KAN OLA MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_OLA_MSSA_Spectrum Phase II Start | CE | KAN | OLA | Bandwidth Management | BWM CE KAN OLA MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_OLA_MSSA_Spectrum Phase II Start | CE | KAN | OLA | Bandwidth Management | BWM CE KAN OLA MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-08-14 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_OLA_MSSA_Spectrum Phase II Start | CE | KAN | OLA | Bandwidth Management | BWM CE KAN OLA MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_NWA_MSSA_Spectrum Phase II Start | CE | NWA | NWA | Bandwidth Management | BWM CE NWA NWA MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-24 | Active | EP
BWM_NWA_MSSA_Spectrum Phase II Start | CE | NWA | NWA | Bandwidth Management | BWM CE NWA NWA MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_NWA_MSSA_Spectrum Phase II Start | CE | NWA | NWA | Bandwidth Management | BWM CE NWA NWA MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_NWA_MSSA_Spectrum Phase II Start | CE | NWA | NWA | Bandwidth Management | BWM CE NWA NWA MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-08-14 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_NWA_MSSA_Spectrum Phase II Start | CE | NWA | NWA | Bandwidth Management | BWM CE NWA NWA MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-24 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_JCY_MSSA_Spectrum Phase II Start | CE | KAN | JCY | Bandwidth Management | BWM CE KAN JCY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | Active | EP
BWM_JCY_MSSA_Spectrum Phase II Start | CE | KAN | JCY | Bandwidth Management | BWM CE KAN JCY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_JCY_MSSA_Spectrum Phase II Start | CE | KAN | JCY | Bandwidth Management | BWM CE KAN JCY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_JCY_MSSA_Spectrum Phase II Start | CE | KAN | JCY | Bandwidth Management | BWM CE KAN JCY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-08-14 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_JCY_MSSA_Spectrum Phase II Start | CE | KAN | JCY | Bandwidth Management | BWM CE KAN JCY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_MNT_MSSA_Spectrum Phase II Start | CE | KAN | MNT | Bandwidth Management | BWM CE KAN MNT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | Active | EP
BWM_MNT_MSSA_Spectrum Phase II Start | CE | KAN | MNT | Bandwidth Management | BWM CE KAN MNT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_MNT_MSSA_Spectrum Phase II Start | CE | KAN | MNT | Bandwidth Management | BWM CE KAN MNT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_MNT_MSSA_Spectrum Phase II Start | CE | KAN | MNT | Bandwidth Management | BWM CE KAN MNT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-08-14 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_MNT_MSSA_Spectrum Phase II Start | CE | KAN | MNT | Bandwidth Management | BWM CE KAN MNT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_MPN_MSSA_Spectrum Phase II Start | CE | KAN | MPN | Bandwidth Management | BWM CE KAN MPN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | Active | EP
BWM_MPN_MSSA_Spectrum Phase II Start | CE | KAN | MPN | Bandwidth Management | BWM CE KAN MPN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_MPN_MSSA_Spectrum Phase II Start | CE | KAN | MPN | Bandwidth Management | BWM CE KAN MPN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_MPN_MSSA_Spectrum Phase II Start | CE | KAN | MPN | Bandwidth Management | BWM CE KAN MPN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-08-14 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_MPN_MSSA_Spectrum Phase II Start | CE | KAN | MPN | Bandwidth Management | BWM CE KAN MPN MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_NWT_MSSA_Spectrum Phase II Start | CE | KAN | NWT | Bandwidth Management | BWM CE KAN NWT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | Active | EP
BWM_NWT_MSSA_Spectrum Phase II Start | CE | KAN | NWT | Bandwidth Management | BWM CE KAN NWT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_NWT_MSSA_Spectrum Phase II Start | CE | KAN | NWT | Bandwidth Management | BWM CE KAN NWT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_NWT_MSSA_Spectrum Phase II Start | CE | KAN | NWT | Bandwidth Management | BWM CE KAN NWT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-08-14 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_NWT_MSSA_Spectrum Phase II Start | CE | KAN | NWT | Bandwidth Management | BWM CE KAN NWT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_PSN_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | KAN | PSN | Bandwidth Management | BWM CE KAN PSN VIDEO SG Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-15 | 2020-06-15 | Active | EP
BWM_BVL_MSSA_Spectrum Phase II Start | CE | NWA | BVL | Bandwidth Management | BWM CE NWA BVL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-06 | 2020-06-15 | 2020-06-24 | Active | EP
BWM_BVL_MSSA_Spectrum Phase II Start | CE | NWA | BVL | Bandwidth Management | BWM CE NWA BVL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-06 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_BVL_MSSA_Spectrum Phase II Start | CE | NWA | BVL | Bandwidth Management | BWM CE NWA BVL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-06 | 2020-06-15 | 2020-08-14 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_BVL_MSSA_Spectrum Phase II Start | CE | NWA | BVL | Bandwidth Management | BWM CE NWA BVL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-06 | 2020-06-15 | 2020-06-24 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_BER_MSSA_Spectrum Phase II Start | CE | NWA | BER | Bandwidth Management | BWM CE NWA BER MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-24 | Active | EP
BWM_BER_MSSA_Spectrum Phase II Start | CE | NWA | BER | Bandwidth Management | BWM CE NWA BER MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_BER_MSSA_Spectrum Phase II Start | CE | NWA | BER | Bandwidth Management | BWM CE NWA BER MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_BER_MSSA_Spectrum Phase II Start | CE | NWA | BER | Bandwidth Management | BWM CE NWA BER MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-08-14 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_BER_MSSA_Spectrum Phase II Start | CE | NWA | BER | Bandwidth Management | BWM CE NWA BER MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-24 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_CFV_MSSA_Spectrum Phase II Start | CE | KAN | CFV | Bandwidth Management | BWM CE KAN CFV MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | Active | EP
BWM_CFV_MSSA_Spectrum Phase II Start | CE | KAN | CFV | Bandwidth Management | BWM CE KAN CFV MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_CFV_MSSA_Spectrum Phase II Start | CE | KAN | CFV | Bandwidth Management | BWM CE KAN CFV MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_CFV_MSSA_Spectrum Phase II Start | CE | KAN | CFV | Bandwidth Management | BWM CE KAN CFV MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-08-14 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_CFV_MSSA_Spectrum Phase II Start | CE | KAN | CFV | Bandwidth Management | BWM CE KAN CFV MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_DBY_MSSA_Spectrum Phase II Start | CE | KAN | DBY | Bandwidth Management | BWM CE KAN DBY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | Active | EP
BWM_DBY_MSSA_Spectrum Phase II Start | CE | KAN | DBY | Bandwidth Management | BWM CE KAN DBY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_DBY_MSSA_Spectrum Phase II Start | CE | KAN | DBY | Bandwidth Management | BWM CE KAN DBY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_DBY_MSSA_Spectrum Phase II Start | CE | KAN | DBY | Bandwidth Management | BWM CE KAN DBY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-08-14 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_DBY_MSSA_Spectrum Phase II Start | CE | KAN | DBY | Bandwidth Management | BWM CE KAN DBY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_DCY_MSSA_Spectrum Phase II Start | CE | KAN | DCY | Bandwidth Management | BWM CE KAN DCY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | Active | EP
BWM_DCY_MSSA_Spectrum Phase II Start | CE | KAN | DCY | Bandwidth Management | BWM CE KAN DCY MSSA Augment POR20 | Labor | No Equipment |  |  |  |  | Active | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_DCY_MSSA_Spectrum Phase II Start | CE | KAN | DCY | Bandwidth Management | BWM CE KAN DCY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_DCY_MSSA_Spectrum Phase II Start | CE | KAN | DCY | Bandwidth Management | BWM CE KAN DCY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_DCY_MSSA_Spectrum Phase II Start | CE | KAN | DCY | Bandwidth Management | BWM CE KAN DCY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-08-14 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_DCY_MSSA_Spectrum Phase II Start | CE | KAN | DCY | Bandwidth Management | BWM CE KAN DCY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_FAY_MSSA_Spectrum Phase II Start | CE | NWA | FAY | Bandwidth Management | BWM CE NWA FAY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-24 | Active | EP
BWM_FAY_MSSA_Spectrum Phase II Start | CE | NWA | FAY | Bandwidth Management | BWM CE NWA FAY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_FAY_MSSA_Spectrum Phase II Start | CE | NWA | FAY | Bandwidth Management | BWM CE NWA FAY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_FAY_MSSA_Spectrum Phase II Start | CE | NWA | FAY | Bandwidth Management | BWM CE NWA FAY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-08-14 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_FAY_MSSA_Spectrum Phase II Start | CE | NWA | FAY | Bandwidth Management | BWM CE NWA FAY MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-24 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_TOW_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | KAN | TOW | Bandwidth Management | BWM CE KAN TOW VIDEO SG Augment POR20 | Labor | No Equipment | 1 | 2020-01-16 | 2020-03-01 |  | Active | EP
BWM_TOW_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | KAN | TOW | Bandwidth Management | BWM CE KAN TOW VIDEO SG Augment POR20 | Labor | No Equipment | 1 | 2020-01-16 | 2020-03-01 |  | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_PRT_MSSA_Spectrum Phase II Start | CE | KAN | PRT | Bandwidth Management | BWM CE KAN PRT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-15 | 2020-06-25 | Active | EP
BWM_PRT_MSSA_Spectrum Phase II Start | CE | KAN | PRT | Bandwidth Management | BWM CE KAN PRT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_PRT_MSSA_Spectrum Phase II Start | CE | KAN | PRT | Bandwidth Management | BWM CE KAN PRT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_PRT_MSSA_Spectrum Phase II Start | CE | KAN | PRT | Bandwidth Management | BWM CE KAN PRT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-15 | 2020-08-14 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_PRT_MSSA_Spectrum Phase II Start | CE | KAN | PRT | Bandwidth Management | BWM CE KAN PRT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-15 | 2020-06-25 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_SAL_MSSA_Spectrum Phase II Start | CE | KAN | SAL | Bandwidth Management | BWM CE KAN SAL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-15 | 2020-06-25 | Active | EP
BWM_SAL_MSSA_Spectrum Phase II Start | CE | KAN | SAL | Bandwidth Management | BWM CE KAN SAL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_SAL_MSSA_Spectrum Phase II Start | CE | KAN | SAL | Bandwidth Management | BWM CE KAN SAL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_SAL_MSSA_Spectrum Phase II Start | CE | KAN | SAL | Bandwidth Management | BWM CE KAN SAL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-15 | 2020-08-14 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_SAL_MSSA_Spectrum Phase II Start | CE | KAN | SAL | Bandwidth Management | BWM CE KAN SAL MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-15 | 2020-06-25 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_SAL_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | KAN | SAL | Bandwidth Management | BWM CE KAN SAL VIDEO SG Augment POR20 | Labor | No Equipment | 1 | 2020-01-16 | 2020-03-01 |  | Active | EP
BWM_SAL_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | KAN | SAL | Bandwidth Management | BWM CE KAN SAL VIDEO SG Augment POR20 | Labor | No Equipment | 1 | 2020-01-16 | 2020-03-01 |  | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_SSP_MSSA_Spectrum Phase II Start | CE | NWA | SSP | Bandwidth Management | BWM CE NWA SSP MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-24 | Active | EP
BWM_SSP_MSSA_Spectrum Phase II Start | CE | NWA | SSP | Bandwidth Management | BWM CE NWA SSP MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_SSP_MSSA_Spectrum Phase II Start | CE | NWA | SSP | Bandwidth Management | BWM CE NWA SSP MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_SSP_MSSA_Spectrum Phase II Start | CE | NWA | SSP | Bandwidth Management | BWM CE NWA SSP MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-08-14 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_SSP_MSSA_Spectrum Phase II Start | CE | NWA | SSP | Bandwidth Management | BWM CE NWA SSP MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-24 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_STR_MSSA_Spectrum Phase II Start | CE | KAN | STR | Bandwidth Management | BWM CE KAN STR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | Active | EP
BWM_STR_MSSA_Spectrum Phase II Start | CE | KAN | STR | Bandwidth Management | BWM CE KAN STR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_STR_MSSA_Spectrum Phase II Start | CE | KAN | STR | Bandwidth Management | BWM CE KAN STR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_STR_MSSA_Spectrum Phase II Start | CE | KAN | STR | Bandwidth Management | BWM CE KAN STR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-08-14 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_STR_MSSA_Spectrum Phase II Start | CE | KAN | STR | Bandwidth Management | BWM CE KAN STR MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_TOP_MSSA_Spectrum Phase II Start | CE | KAN | TOP | Bandwidth Management | BWM CE KAN TOP MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | Active | EP
BWM_TOP_MSSA_Spectrum Phase II Start | CE | KAN | TOP | Bandwidth Management | BWM CE KAN TOP MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_TOP_MSSA_Spectrum Phase II Start | CE | KAN | TOP | Bandwidth Management | BWM CE KAN TOP MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_TOP_MSSA_Spectrum Phase II Start | CE | KAN | TOP | Bandwidth Management | BWM CE KAN TOP MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-08-14 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_TOP_MSSA_Spectrum Phase II Start | CE | KAN | TOP | Bandwidth Management | BWM CE KAN TOP MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_TOP_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | KAN | TOP | Bandwidth Management | BWM CE KAN TOP VIDEO SG Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-01 |  | Active | EP
BWM_TOP_VIDEO SG_2020 DOCSIS node split-based Video SG | CE | KAN | TOP | Bandwidth Management | BWM CE KAN TOP VIDEO SG Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-01 |  | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_TOW_MSSA_Spectrum Phase II Start | CE | KAN | TOW | Bandwidth Management | BWM CE KAN TOW MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | Active | EP
BWM_TOW_MSSA_Spectrum Phase II Start | CE | KAN | TOW | Bandwidth Management | BWM CE KAN TOW MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_TOW_MSSA_Spectrum Phase II Start | CE | KAN | TOW | Bandwidth Management | BWM CE KAN TOW MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_TOW_MSSA_Spectrum Phase II Start | CE | KAN | TOW | Bandwidth Management | BWM CE KAN TOW MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-08-14 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_TOW_MSSA_Spectrum Phase II Start | CE | KAN | TOW | Bandwidth Management | BWM CE KAN TOW MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_PIT_MSSA_Spectrum Phase II Start | CE | KAN | PIT | Bandwidth Management | BWM CE KAN PIT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | Active | EP
BWM_PIT_MSSA_Spectrum Phase II Start | CE | KAN | PIT | Bandwidth Management | BWM CE KAN PIT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_PIT_MSSA_Spectrum Phase II Start | CE | KAN | PIT | Bandwidth Management | BWM CE KAN PIT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-05-18 | 2020-08-14 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_PIT_MSSA_Spectrum Phase II Start | CE | KAN | PIT | Bandwidth Management | BWM CE KAN PIT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-08-14 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_PIT_MSSA_Spectrum Phase II Start | CE | KAN | PIT | Bandwidth Management | BWM CE KAN PIT MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-15 | 2020-06-25 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_LFY_VIDEO SG_2020 DOCSIS node split-based Video SG | SE | LFY | LFY | Bandwidth Management | BWM SE LFY LFY Video SG Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_LFY_VIDEO SG_2020 DOCSIS node split-based Video SG | SE | LFY | LFY | Bandwidth Management | BWM SE LFY LFY Video SG Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0245 | Schedule Change | Approved | 2020-02-24 12:37 | 59 projects were made inactive on CR SN-0195 in error, I m reactivating these projects and VSG submited an revised plan 14 VSG projects removed and shifting some dates for the remaining projects
BWM_MER_VIDEO SG_2020 DOCSIS node split-based Video SG I | NE | CON | MER | Bandwidth Management | BWM NE CON MER VIDEO SG Augment POR20 v2 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-15 | 2020-06-15 | Active | EP
BWM_PAW_VIDEO SG_2020 DOCSIS node split-based Video SG I | NE | RHD | PAW | Bandwidth Management | BWM NE RHD PAW VIDEO SG Augment POR20 v3 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-15 | 2020-09-15 | Active | EP
BWM_WES_VIDEO SG_2020 DOCSIS node split-based Video SG 2 | CE | OMA | WES | Bandwidth Management | BWM CE OMA WES VIDEO SG Augment POR20 v4 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_WES_VIDEO SG_2020 DOCSIS node split-based Video SG 2 | CE | OMA | WES | Bandwidth Management | BWM CE OMA WES VIDEO SG Augment POR20 v4 | Labor | No Equipment | 1 |  | 2020-08-01 | 2020-08-01 | Deleted | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_WES_VIDEO SG_2020 DOCSIS node split-based Video SG 2 | CE | OMA | WES | Bandwidth Management | BWM CE OMA WES VIDEO SG Augment POR20 v4 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0245 | Schedule Change | Approved | 2020-02-24 12:37 | 59 projects were made inactive on CR SN-0195 in error, I m reactivating these projects and VSG submited an revised plan 14 VSG projects removed and shifting some dates for the remaining projects
BWM_OKC_DGS_Spectrum Phase III_96 MHZ | CE | OKC | OKC | Bandwidth Management | BWM CE OKC OKC DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_OKC_DGS_Spectrum Phase III_96 MHZ | CE | OKC | OKC | Bandwidth Management | BWM CE OKC OKC DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_OKC_DGS_Spectrum Phase III_96 MHZ | CE | OKC | OKC | Bandwidth Management | BWM CE OKC OKC DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_TUL_VIDEO SG_2020 DOCSIS node split-based Video SG I Dup | CE | TUL | TUL | Bandwidth Management | BWM CE TUL TUL VIDEO SG Augment POR20 v4 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_TUL_VIDEO SG_2020 DOCSIS node split-based Video SG I Dup | CE | TUL | TUL | Bandwidth Management | BWM CE TUL TUL VIDEO SG Augment POR20 v4 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0245 | Schedule Change | Approved | 2020-02-24 12:37 | 59 projects were made inactive on CR SN-0195 in error, I m reactivating these projects and VSG submited an revised plan 14 VSG projects removed and shifting some dates for the remaining projects
BWM_WLK_MSSA_Spectrum Phase II Start | CE | OKC | WLK | Bandwidth Management | BWM CE OKC WLK MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | Active | EP
BWM_WLK_MSSA_Spectrum Phase II Start | CE | OKC | WLK | Bandwidth Management | BWM CE OKC WLK MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_WLK_MSSA_Spectrum Phase II Start | CE | OKC | WLK | Bandwidth Management | BWM CE OKC WLK MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-17 | 2020-11-13 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_WLK_MSSA_Spectrum Phase II Start | CE | OKC | WLK | Bandwidth Management | BWM CE OKC WLK MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-10-23 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_WLK_MSSA_Spectrum Phase II Start | CE | OKC | WLK | Bandwidth Management | BWM CE OKC WLK MSSA Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-24 | 2020-09-01 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_WLK_DGS_Spectrum Phase III_96 MHZ | CE | OKC | WLK | Bandwidth Management | BWM CE OKC WLK DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_WLK_DGS_Spectrum Phase III_96 MHZ | CE | OKC | WLK | Bandwidth Management | BWM CE OKC WLK DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_WLK_DGS_Spectrum Phase III_96 MHZ | CE | OKC | WLK | Bandwidth Management | BWM CE OKC WLK DGS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_NWA_VIDEO SG_2020 DOCSIS node split-based Video SG 2 Dup | CE | NWA | NWA | Bandwidth Management | BWM CE NWA NWA Video SG Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_NWA_VIDEO SG_2020 DOCSIS node split-based Video SG 2 Dup | CE | NWA | NWA | Bandwidth Management | BWM CE NWA NWA Video SG Augment POR20 v3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0245 | Schedule Change | Approved | 2020-02-24 12:37 | 59 projects were made inactive on CR SN-0195 in error, I m reactivating these projects and VSG submited an revised plan 14 VSG projects removed and shifting some dates for the remaining projects
BWM_GNS_VIDEO SG_2020 DOCSIS node split-based Video SG I | SE | GAN | GNS | Bandwidth Management | BWM SE GAN GNS Video SG Augment POR20 v2 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | Active | EP
BWM_GNS_VIDEO SG_2020 DOCSIS node split-based Video SG I | SE | GAN | GNS | Bandwidth Management | BWM SE GAN GNS Video SG Augment POR20 v2 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | Active | Log | Upd | SN-0245 | Schedule Change | Approved | 2020-02-24 12:37 | 59 projects were made inactive on CR SN-0195 in error, I m reactivating these projects and VSG submited an revised plan 14 VSG projects removed and shifting some dates for the remaining projects
BWM_CRV_VIDEO SG_2020 DOCSIS node split-based Video SG I | SE | GCT | CRV | Bandwidth Management | BWM SE GCT CRV Video SG Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_CRV_VIDEO SG_2020 DOCSIS node split-based Video SG I | SE | GCT | CRV | Bandwidth Management | BWM SE GCT CRV Video SG Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0245 | Schedule Change | Approved | 2020-02-24 12:37 | 59 projects were made inactive on CR SN-0195 in error, I m reactivating these projects and VSG submited an revised plan 14 VSG projects removed and shifting some dates for the remaining projects
BWM_NOE_VIDEO SG_2020 DOCSIS node split-based Video SG I | SE | NOR | NOE | Bandwidth Management | BWM SE NOR NOE Video SG Augment POR20 v3 | Labor | No Equipment | 1 |  | 2020-12-01 | 2020-12-01 | Active | EP
BWM_NOE_VIDEO SG_2020 DOCSIS node split-based Video SG I | SE | NOR | NOE | Bandwidth Management | BWM SE NOR NOE Video SG Augment POR20 v3 | Labor | No Equipment | 1 |  | 2020-12-01 | 2020-12-01 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_ALG_BAU SA_Spectrum Phase III | SE | NOR | ALG | Bandwidth Management | BWM SE NOR ALG BAU SA Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_ALG_BAU SA_Spectrum Phase III | SE | NOR | ALG | Bandwidth Management | BWM SE NOR ALG BAU SA Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0743 | New | Approved | 2020-07-10 10:14 | Removing SA SE NOR BAU projects which are duplicates of work being done in NOR for MSSA
BWM_CLR_BAU SA_Spectrum Phase III | SE | NOR | CLR | Bandwidth Management | BWM SE NOR CLR BAU SA Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_CLR_BAU SA_Spectrum Phase III | SE | NOR | CLR | Bandwidth Management | BWM SE NOR CLR BAU SA Augment POR20 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0743 | New | Approved | 2020-07-10 10:14 | Removing SA SE NOR BAU projects which are duplicates of work being done in NOR for MSSA
BWM_CLR_VIDEO SG_2020 DOCSIS node split-based Video SG | SE | NOR | CLR | Bandwidth Management | BWM SE NOR CLR Video SG Augment POR20 v3 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-15 | 2020-09-15 | Active | EP
BWM_FWB_MSSA_Spectrum Phase II Start | SE | GCT | FWB | Bandwidth Management | BWM SE GCT FWB MSSA Augment POR20 v2 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-09-02 | Active | EP
BWM_FWB_MSSA_Spectrum Phase II Start | SE | GCT | FWB | Bandwidth Management | BWM SE GCT FWB MSSA Augment POR20 v2 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_FWB_MSSA_Spectrum Phase II Start | SE | GCT | FWB | Bandwidth Management | BWM SE GCT FWB MSSA Augment POR20 v2 | Labor | No Equipment | 1 | 2020-04-01 | 2020-01-27 | 2020-04-24 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_FWB_MSSA_Spectrum Phase II Start | SE | GCT | FWB | Bandwidth Management | BWM SE GCT FWB MSSA Augment POR20 v2 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-11-13 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_FWB_MSSA_Spectrum Phase II Start | SE | GCT | FWB | Bandwidth Management | BWM SE GCT FWB MSSA Augment POR20 v2 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-09-02 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_NCV_MSSA_Spectrum Phase II Start | SE | GCT | NCV | Bandwidth Management | BWM SE GCT NCV MSSA Augment POR20 v3 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-09-02 | Active | EP
BWM_NCV_MSSA_Spectrum Phase II Start | SE | GCT | NCV | Bandwidth Management | BWM SE GCT NCV MSSA Augment POR20 v3 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_NCV_MSSA_Spectrum Phase II Start | SE | GCT | NCV | Bandwidth Management | BWM SE GCT NCV MSSA Augment POR20 v3 | Labor | No Equipment | 1 | 2020-04-01 | 2020-01-27 | 2020-04-24 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_NCV_MSSA_Spectrum Phase II Start | SE | GCT | NCV | Bandwidth Management | BWM SE GCT NCV MSSA Augment POR20 v3 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-11-13 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_NCV_MSSA_Spectrum Phase II Start | SE | GCT | NCV | Bandwidth Management | BWM SE GCT NCV MSSA Augment POR20 v3 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-09-02 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_HLT_VIDEO SG_2020 DOCSIS node split-based Video SG | SE | MGA | HLT | Bandwidth Management | BWM SE MGA HLT Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-15 | 2020-09-15 | Active | EP
BWM_WRB_VIDEO SG_2020 DOCSIS node split-based Video SG I | SE | MGA | WRB | Bandwidth Management | BWM SE MGA WRB Video SG Augment POR20 v2 | Labor | No Equipment | 1 | 2020-01-16 | 2020-06-30 | 2020-06-30 | Active | EP
BWM_WRB_VIDEO SG_2020 DOCSIS node split-based Video SG I | SE | MGA | WRB | Bandwidth Management | BWM SE MGA WRB Video SG Augment POR20 v2 | Labor | No Equipment | 1 | 2020-01-16 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_BRD_VIDEO SG_2020 DOCSIS node split-based Video SG Calculations per facility Dup | CE | TUL | BRD | Bandwidth Management | BWM CE TUL BRD VIDEO SG Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-20 | 2020-06-20 | Active | EP
BWM_BRD_VIDEO SG_2020 DOCSIS node split-based Video SG Calculations per facility Dup | CE | TUL | BRD | Bandwidth Management | BWM CE TUL BRD VIDEO SG Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-20 | 2020-06-20 | Active | Log | Upd | SN-0245 | Schedule Change | Approved | 2020-02-24 12:37 | 59 projects were made inactive on CR SN-0195 in error, I m reactivating these projects and VSG submited an revised plan 14 VSG projects removed and shifting some dates for the remaining projects
BWM_TUL_VIDEO SG_2020 DOCSIS node split-based Video SG I | CE | TUL | TUL | Bandwidth Management | BWM CE TUL TUL VIDEO SG Augment POR20 v4 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_TUL_VIDEO SG_2020 DOCSIS node split-based Video SG I | CE | TUL | TUL | Bandwidth Management | BWM CE TUL TUL VIDEO SG Augment POR20 v4 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0245 | Schedule Change | Approved | 2020-02-24 12:37 | 59 projects were made inactive on CR SN-0195 in error, I m reactivating these projects and VSG submited an revised plan 14 VSG projects removed and shifting some dates for the remaining projects
BWM_NWA_VIDEO SG_2020 DOCSIS node split-based Video SG 2 | CE | NWA | NWA | Bandwidth Management | BWM CE NWA NWA Video SG Augment POR20 v3 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | EP
BWM_NWA_VIDEO SG_2020 DOCSIS node split-based Video SG 2 | CE | NWA | NWA | Bandwidth Management | BWM CE NWA NWA Video SG Augment POR20 v3 | Labor | No Equipment | 1 | 2020-01-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_NCV_VIDEO SG_2020 DOCSIS node split-based Video SG | SE | GCT | NCV | Bandwidth Management | BWM SE GCT NCV Video SG Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_NCV_VIDEO SG_2020 DOCSIS node split-based Video SG | SE | GCT | NCV | Bandwidth Management | BWM SE GCT NCV Video SG Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_NCV_VIDEO SG_2020 DOCSIS node split-based Video SG | SE | GCT | NCV | Bandwidth Management | BWM SE GCT NCV Video SG Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0245 | Schedule Change | Approved | 2020-02-24 12:37 | 59 projects were made inactive on CR SN-0195 in error, I m reactivating these projects and VSG submited an revised plan 14 VSG projects removed and shifting some dates for the remaining projects
BWM_LFY_VIDEO SG_2020 DOCSIS node split-based Video SG Dup1 | SE | LFY | LFY | Bandwidth Management | BWM SE GLA LFY Video SG Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_LFY_VIDEO SG_2020 DOCSIS node split-based Video SG Dup1 | SE | LFY | LFY | Bandwidth Management | BWM SE GLA LFY Video SG Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_ALP_DGS_Spectrum Phase III_96MHZ | CA | SAN | ALP | Bandwidth Management | BWM SE GAN OCL MSSA Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_ALP_DGS_Spectrum Phase III_96MHZ | CA | SAN | ALP | Bandwidth Management | BWM SE GAN OCL MSSA Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_CHU_DGS_Spectrum Phase III 96 MHZ | CA | SAN | FED | Bandwidth Management | BWM CA SAN FED DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Deleted | EP
BWM_CHU_DGS_Spectrum Phase III 96 MHZ | CA | SAN | FED | Bandwidth Management | BWM CA SAN FED DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-04-30 | 2020-04-30 | Deleted | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_CHU_DGS_Spectrum Phase III 96 MHZ | CA | SAN | FED | Bandwidth Management | BWM CA SAN FED DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-30 | 2020-04-30 | Deleted | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_CHU_DGS_Spectrum Phase III 96 MHZ | CA | SAN | FED | Bandwidth Management | BWM CA SAN FED DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-08 | 2020-12-08 | Deleted | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_CHU_DGS_Spectrum Phase III 96 MHZ | CA | SAN | FED | Bandwidth Management | BWM CA SAN FED DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_DWN_DGS_Spectrum Phase III 96 MHZ | CA | SAN | ESC | Bandwidth Management | BWM CA SAN ESC DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Deleted | EP
BWM_DWN_DGS_Spectrum Phase III 96 MHZ | CA | SAN | ESC | Bandwidth Management | BWM CA SAN ESC DGS 192 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-04-30 | 2020-04-30 | Deleted | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_DWN_DGS_Spectrum Phase III 96 MHZ | CA | SAN | ESC | Bandwidth Management | BWM CA SAN ESC DGS 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-09-30 | 2020-09-30 | Deleted | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_DWN_DGS_Spectrum Phase III 96 MHZ | CA | SAN | ESC | Bandwidth Management | BWM CA SAN ESC DGS 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-08 | 2020-12-08 | Deleted | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_DWN_DGS_Spectrum Phase III 96 MHZ | CA | SAN | ESC | Bandwidth Management | BWM CA SAN ESC DGS 192 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_ELC_DGS_Spectrum Phase III 96 MHZ | CA | SAN | ELC | Bandwidth Management | BWM CA SAN ELC DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Active | EP
BWM_ELC_DGS_Spectrum Phase III 96 MHZ | CA | SAN | DWN | Bandwidth Management | BWM CA SAN DWN DGS 192 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-04-30 | 2020-04-30 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_ELC_DGS_Spectrum Phase III 96 MHZ | CA | SAN | DWN | Bandwidth Management | BWM CA SAN DWN DGS 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_ELC_DGS_Spectrum Phase III 96 MHZ | CA | SAN | DWN | Bandwidth Management | BWM CA SAN DWN DGS 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-08 | 2020-12-08 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_ELC_DGS_Spectrum Phase III 96 MHZ | CA | SAN | DWN | Bandwidth Management | BWM CA SAN DWN DGS 192 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Active | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_ELC_DGS_Spectrum Phase III 96 MHZ | CA | SAN | ELC | Bandwidth Management | BWM CA SAN ELC DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM_ESC_DGS_Spectrum Phase III 96 MHZ | CA | SAN | PWY | Bandwidth Management | BWM CA SAN PWY DGS 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-08 | 2020-12-08 | Deleted | EP
BWM_ESC_DGS_Spectrum Phase III 96 MHZ | CA | SAN | PWY | Bandwidth Management | BWM CA SAN PWY DGS 192 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-04-30 | 2020-04-30 | Deleted | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_ESC_DGS_Spectrum Phase III 96 MHZ | CA | SAN | PWY | Bandwidth Management | BWM CA SAN PWY DGS 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-09-30 | 2020-09-30 | Deleted | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_ESC_DGS_Spectrum Phase III 96 MHZ | CA | SAN | PWY | Bandwidth Management | BWM CA SAN PWY DGS 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-08 | 2020-12-08 | Deleted | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_ESC_DGS_Spectrum Phase III 96 MHZ | CA | SAN | PWY | Bandwidth Management | BWM CA SAN PWY DGS 192 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_FED_DGS_Spectrum Phase III 96 MHZ | CA | SAN | FED | Bandwidth Management | BWM CA SAN FED DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Active | EP
BWM_FED_DGS_Spectrum Phase III 96 MHZ | CA | SAN | ELC | Bandwidth Management | BWM CA SAN ELC DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-04-30 | 2020-04-30 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_FED_DGS_Spectrum Phase III 96 MHZ | CA | SAN | ELC | Bandwidth Management | BWM CA SAN ELC DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-30 | 2020-04-30 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_FED_DGS_Spectrum Phase III 96 MHZ | CA | SAN | ELC | Bandwidth Management | BWM CA SAN ELC DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-08 | 2020-12-08 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_FED_DGS_Spectrum Phase III 96 MHZ | CA | SAN | ELC | Bandwidth Management | BWM CA SAN ELC DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Active | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_FED_DGS_Spectrum Phase III 96 MHZ | CA | SAN | FED | Bandwidth Management | BWM CA SAN FED DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM_OCE_DGS_Spectrum Phase III 96 MHZ | CA | SAN | DWN | Bandwidth Management | BWM CA SAN DWN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Deleted | EP
BWM_OCE_DGS_Spectrum Phase III 96 MHZ | CA | SAN | DWN | Bandwidth Management | BWM CA SAN DWN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-04-30 | 2020-04-30 | Deleted | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_OCE_DGS_Spectrum Phase III 96 MHZ | CA | SAN | DWN | Bandwidth Management | BWM CA SAN DWN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-30 | 2020-04-30 | Deleted | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_OCE_DGS_Spectrum Phase III 96 MHZ | CA | SAN | DWN | Bandwidth Management | BWM CA SAN DWN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-08 | 2020-12-08 | Deleted | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_OCE_DGS_Spectrum Phase III 96 MHZ | CA | SAN | DWN | Bandwidth Management | BWM CA SAN DWN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_PWY_DGS_Spectrum Phase III 96 MHZ | CA | SAN | PWY | Bandwidth Management | BWM CA SAN PWY DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Active | EP
BWM_PWY_DGS_Spectrum Phase III 96 MHZ | CA | SAN | VST | Bandwidth Management | BWM CA SAN VST DGS 192 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-04-30 | 2020-04-30 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_PWY_DGS_Spectrum Phase III 96 MHZ | CA | SAN | PWY | Bandwidth Management | BWM CA SAN PWY DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-30 | 2020-04-30 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_PWY_DGS_Spectrum Phase III 96 MHZ | CA | SAN | PWY | Bandwidth Management | BWM CA SAN PWY DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-08 | 2020-12-08 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_PWY_DGS_Spectrum Phase III 96 MHZ | CA | SAN | PWY | Bandwidth Management | BWM CA SAN PWY DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Active | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_PWY_DGS_Spectrum Phase III 96 MHZ | CA | SAN | PWY | Bandwidth Management | BWM CA SAN PWY DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM_VST_DGS_Spectrum Phase III 96 MHZ | CA | SAN | VST | Bandwidth Management | BWM CA SAN VST DGS 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-08 | 2020-12-08 | Deleted | EP
BWM_VST_DGS_Spectrum Phase III 96 MHZ | CA | SAN | VST | Bandwidth Management | BWM CA SAN VST DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-04-30 | 2020-04-30 | Deleted | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_VST_DGS_Spectrum Phase III 96 MHZ | CA | SAN | VST | Bandwidth Management | BWM CA SAN VST DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-30 | 2020-04-30 | Deleted | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_VST_DGS_Spectrum Phase III 96 MHZ | CA | SAN | VST | Bandwidth Management | BWM CA SAN VST DGS 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-08 | 2020-12-08 | Deleted | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_VST_DGS_Spectrum Phase III 96 MHZ | CA | SAN | VST | Bandwidth Management | BWM CA SAN VST DGS 192 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_ALI_DGS_Spectrum Phase III 96 MHZ | SW | LAS | ALI | Bandwidth Management | BWM SW LAS ALI DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Active | EP
BWM_ALI_DGS_Spectrum Phase III 96 MHZ | SW | LAS | ALI | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-10-22 | 2020-03-31 | 2020-03-31 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_ALI_DGS_Spectrum Phase III 96 MHZ | SW | LAS | ALI | Bandwidth Management | BWM SW LAS ALI DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-31 | 2020-03-31 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_ALI_DGS_Spectrum Phase III 96 MHZ | SW | LAS | ALI | Bandwidth Management | BWM SW LAS ALI DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-08 | 2020-12-08 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_ALI_DGS_Spectrum Phase III 96 MHZ | SW | LAS | ALI | Bandwidth Management | BWM SW LAS ALI DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Active | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_ALI_DGS_Spectrum Phase III 96 MHZ | SW | LAS | ALI | Bandwidth Management | BWM SW LAS ALI DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM_BEL_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | BEL | Bandwidth Management | BWM SW ARZ BEL DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | EP
BWM_BEL_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | BEL | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2019-10-22 | 2020-01-31 | 2020-01-31 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_BEL_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | BEL | Bandwidth Management | BWM SW ARZ BEL DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-31 | 2020-01-31 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_BEL_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | BEL | Bandwidth Management | BWM SW ARZ BEL DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_BEN_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | BEN | Bandwidth Management | BWM SW ARZ BEN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | EP
BWM_BEN_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | BEN | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2019-10-22 | 2020-01-31 | 2020-01-31 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_BEN_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | BEN | Bandwidth Management | BWM SW ARZ BEN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-31 | 2020-01-31 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_BEN_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | BEN | Bandwidth Management | BWM SW ARZ BEN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_BLU_DGS_Spectrum Phase III 96 MHZ | SW | LAS | BLU | Bandwidth Management | BWM SW LAS BLU DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Active | EP
BWM_BLU_DGS_Spectrum Phase III 96 MHZ | SW | LAS | BLU | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-10-22 | 2020-03-31 | 2020-03-31 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_BLU_DGS_Spectrum Phase III 96 MHZ | SW | LAS | BLU | Bandwidth Management | BWM SW LAS BLU DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-31 | 2020-03-31 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_BLU_DGS_Spectrum Phase III 96 MHZ | SW | LAS | BLU | Bandwidth Management | BWM SW LAS BLU DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-08 | 2020-12-08 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_BLU_DGS_Spectrum Phase III 96 MHZ | SW | LAS | BLU | Bandwidth Management | BWM SW LAS BLU DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Active | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_BLU_DGS_Spectrum Phase III 96 MHZ | SW | LAS | BLU | Bandwidth Management | BWM SW LAS BLU DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM_BUK_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | BUK | Bandwidth Management | BWM SW ARZ BUK DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | EP
BWM_BUK_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | BUK | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2019-10-22 | 2020-01-31 | 2020-01-31 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_BUK_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | BUK | Bandwidth Management | BWM SW ARZ BUK DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-31 | 2020-01-31 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_BUK_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | BUK | Bandwidth Management | BWM SW ARZ BUK DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_CSG_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | CSG | Bandwidth Management | BWM SW ARZ CSG DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | EP
BWM_CSG_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | CSG | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2019-10-22 | 2020-01-31 | 2020-01-31 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_CSG_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | CSG | Bandwidth Management | BWM SW ARZ CSG DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-31 | 2020-01-31 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_CSG_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | CSG | Bandwidth Management | BWM SW ARZ CSG DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_CEN_DGS_Spectrum Phase III 96 MHZ | SW | LAS | CEN | Bandwidth Management | BWM SW LAS CEN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Active | EP
BWM_CEN_DGS_Spectrum Phase III 96 MHZ | SW | LAS | CEN | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-10-22 | 2020-03-31 | 2020-03-31 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_CEN_DGS_Spectrum Phase III 96 MHZ | SW | LAS | CEN | Bandwidth Management | BWM SW LAS CEN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-31 | 2020-03-31 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_CEN_DGS_Spectrum Phase III 96 MHZ | SW | LAS | CEN | Bandwidth Management | BWM SW LAS CEN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-08 | 2020-12-08 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_CEN_DGS_Spectrum Phase III 96 MHZ | SW | LAS | CEN | Bandwidth Management | BWM SW LAS CEN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Active | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_CEN_DGS_Spectrum Phase III 96 MHZ | SW | LAS | CEN | Bandwidth Management | BWM SW LAS CEN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM_CHD_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | CHD | Bandwidth Management | BWM SW ARZ CHD DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | EP
BWM_CHD_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | CHD | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2019-10-22 | 2020-01-31 | 2020-01-31 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_CHD_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | CHD | Bandwidth Management | BWM SW ARZ CHD DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-31 | 2020-01-31 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_CHD_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | CHD | Bandwidth Management | BWM SW ARZ CHD DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_DGL_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | DGL | Bandwidth Management | BWM SW ARZ DGL DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | EP
BWM_DGL_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | DGL | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2019-10-22 | 2020-01-31 | 2020-01-31 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_DGL_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | DGL | Bandwidth Management | BWM SW ARZ DGL DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-31 | 2020-01-31 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_DGL_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | DGL | Bandwidth Management | BWM SW ARZ DGL DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_ERN_DGS_Spectrum Phase III 96 MHZ | SW | LAS | ERN | Bandwidth Management | BWM SW LAS ERN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Active | EP
BWM_ERN_DGS_Spectrum Phase III 96 MHZ | SW | LAS | ERN | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-10-22 | 2020-03-31 | 2020-03-31 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_ERN_DGS_Spectrum Phase III 96 MHZ | SW | LAS | ERN | Bandwidth Management | BWM SW LAS ERN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-31 | 2020-03-31 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_ERN_DGS_Spectrum Phase III 96 MHZ | SW | LAS | ERN | Bandwidth Management | BWM SW LAS ERN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-08 | 2020-12-08 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_ERN_DGS_Spectrum Phase III 96 MHZ | SW | LAS | ERN | Bandwidth Management | BWM SW LAS ERN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Active | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_ERN_DGS_Spectrum Phase III 96 MHZ | SW | LAS | ERN | Bandwidth Management | BWM SW LAS ERN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM_FWL_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | FWL | Bandwidth Management | BWM SW ARZ FWL DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | EP
BWM_FWL_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | FWL | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2019-10-22 | 2020-01-31 | 2020-01-31 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_FWL_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | FWL | Bandwidth Management | BWM SW ARZ FWL DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-31 | 2020-01-31 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_FWL_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | FWL | Bandwidth Management | BWM SW ARZ FWL DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_GVA_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | GVA | Bandwidth Management | BWM SW ARZ GVA DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | EP
BWM_GVA_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | GVA | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2019-10-22 | 2020-01-31 | 2020-01-31 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_GVA_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | GVA | Bandwidth Management | BWM SW ARZ GVA DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-31 | 2020-01-31 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_GVA_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | GVA | Bandwidth Management | BWM SW ARZ GVA DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_HEN_DGS_Spectrum Phase III 96 MHZ | SW | LAS | HEN | Bandwidth Management | BWM SW LAS HEN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Active | EP
BWM_HEN_DGS_Spectrum Phase III 96 MHZ | SW | LAS | HEN | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-10-22 | 2020-03-31 | 2020-03-31 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_HEN_DGS_Spectrum Phase III 96 MHZ | SW | LAS | HEN | Bandwidth Management | BWM SW LAS HEN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-31 | 2020-03-31 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_HEN_DGS_Spectrum Phase III 96 MHZ | SW | LAS | HEN | Bandwidth Management | BWM SW LAS HEN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-08 | 2020-12-08 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_HEN_DGS_Spectrum Phase III 96 MHZ | SW | LAS | HEN | Bandwidth Management | BWM SW LAS HEN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Active | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_HEN_DGS_Spectrum Phase III 96 MHZ | SW | LAS | HEN | Bandwidth Management | BWM SW LAS HEN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM_MCD_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | MCD | Bandwidth Management | BWM SW ARZ MCD DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | EP
BWM_MCD_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | MCD | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2019-10-22 | 2020-01-31 | 2020-01-31 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_MCD_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | MCD | Bandwidth Management | BWM SW ARZ MCD DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-31 | 2020-01-31 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_MCD_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | MCD | Bandwidth Management | BWM SW ARZ MCD DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_MSA_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | MSA | Bandwidth Management | BWM SW ARZ MSA DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | EP
BWM_MSA_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | MSA | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2019-10-22 | 2020-01-31 | 2020-01-31 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_MSA_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | MSA | Bandwidth Management | BWM SW ARZ MSA DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-31 | 2020-01-31 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_MSA_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | MSA | Bandwidth Management | BWM SW ARZ MSA DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_NSC_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | NSC | Bandwidth Management | BWM SW ARZ NSC DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | EP
BWM_NSC_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | NSC | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2019-10-22 | 2020-01-31 | 2020-01-31 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_NSC_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | NSC | Bandwidth Management | BWM SW ARZ NSC DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-31 | 2020-01-31 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_NSC_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | NSC | Bandwidth Management | BWM SW ARZ NSC DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_PEO_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | PEO | Bandwidth Management | BWM SW ARZ PEO DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | EP
BWM_PEO_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | PEO | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2019-10-22 | 2020-01-31 | 2020-01-31 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_PEO_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | PEO | Bandwidth Management | BWM SW ARZ PEO DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-31 | 2020-01-31 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_PEO_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | PEO | Bandwidth Management | BWM SW ARZ PEO DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_PNL_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | PNL | Bandwidth Management | BWM SW ARZ PNL DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | EP
BWM_PNL_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | PNL | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2019-10-22 | 2020-01-31 | 2020-01-31 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_PNL_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | PNL | Bandwidth Management | BWM SW ARZ PNL DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-31 | 2020-01-31 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_PNL_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | PNL | Bandwidth Management | BWM SW ARZ PNL DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_SVA_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | SVA | Bandwidth Management | BWM SW ARZ SVA DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | EP
BWM_SVA_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | SVA | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2019-10-22 | 2020-01-31 | 2020-01-31 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_SVA_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | SVA | Bandwidth Management | BWM SW ARZ SVA DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-31 | 2020-01-31 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_SVA_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | SVA | Bandwidth Management | BWM SW ARZ SVA DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_SSC_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | SSC | Bandwidth Management | BWM SW ARZ SSC DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | EP
BWM_SSC_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | SSC | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2019-10-22 | 2020-01-31 | 2020-01-31 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_SSC_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | SSC | Bandwidth Management | BWM SW ARZ SSC DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-31 | 2020-01-31 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_SSC_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | SSC | Bandwidth Management | BWM SW ARZ SSC DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_TEN_DGS_Spectrum Phase III 96 MHZ | SW | LAS | TEN | Bandwidth Management | BWM SW LAS TEN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Active | EP
BWM_TEN_DGS_Spectrum Phase III 96 MHZ | SW | LAS | TEN | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-10-22 | 2020-03-31 | 2020-03-31 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_TEN_DGS_Spectrum Phase III 96 MHZ | SW | LAS | TEN | Bandwidth Management | BWM SW LAS TEN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-31 | 2020-03-31 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_TEN_DGS_Spectrum Phase III 96 MHZ | SW | LAS | TEN | Bandwidth Management | BWM SW LAS TEN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-08 | 2020-12-08 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_TEN_DGS_Spectrum Phase III 96 MHZ | SW | LAS | TEN | Bandwidth Management | BWM SW LAS TEN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Active | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_TEN_DGS_Spectrum Phase III 96 MHZ | SW | LAS | TEN | Bandwidth Management | BWM SW LAS TEN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM_TUC_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | TUC | Bandwidth Management | BWM SW ARZ TUC DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | EP
BWM_TUC_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | TUC | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2019-10-22 | 2020-01-31 | 2020-01-31 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_TUC_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | TUC | Bandwidth Management | BWM SW ARZ TUC DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-31 | 2020-01-31 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_TUC_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | TUC | Bandwidth Management | BWM SW ARZ TUC DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_VLY_DGS_Spectrum Phase III 96 MHZ | SW | LAS | VLY | Bandwidth Management | BWM SW LAS VLY DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Active | EP
BWM_VLY_DGS_Spectrum Phase III 96 MHZ | SW | LAS | VLY | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-10-22 | 2020-03-31 | 2020-03-31 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_VLY_DGS_Spectrum Phase III 96 MHZ | SW | LAS | VLY | Bandwidth Management | BWM SW LAS VLY DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-31 | 2020-03-31 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_VLY_DGS_Spectrum Phase III 96 MHZ | SW | LAS | VLY | Bandwidth Management | BWM SW LAS VLY DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-08 | 2020-12-08 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_VLY_DGS_Spectrum Phase III 96 MHZ | SW | LAS | VLY | Bandwidth Management | BWM SW LAS VLY DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Active | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_VLY_DGS_Spectrum Phase III 96 MHZ | SW | LAS | VLY | Bandwidth Management | BWM SW LAS VLY DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM_VSA_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | VSA | Bandwidth Management | BWM SW ARZ VSA DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | EP
BWM_VSA_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | VSA | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2019-10-22 | 2020-01-31 | 2020-01-31 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_VSA_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | VSA | Bandwidth Management | BWM SW ARZ VSA DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-31 | 2020-01-31 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_VSA_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | VSA | Bandwidth Management | BWM SW ARZ VSA DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_WKB_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | WCG | Bandwidth Management | BWM SW ARZ WCG DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | EP
BWM_WKB_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | WCG | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2019-10-22 | 2020-01-31 | 2020-01-31 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_WKB_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | WCG | Bandwidth Management | BWM SW ARZ WCG DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_WKB_DGS_Spectrum Phase III 96 MHZ | SW | ARZ | WCG | Bandwidth Management | BWM SW ARZ WCG DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | Log | Upd | SN-0473 | New | Approved | 2020-04-17 16:09 | 4 projects are showing the incorrect project name on the POR, making the correction on this CR
BWM_ALP_DGS_Spectrum Phase III_192 MHZv2 | CA | SAN | ALP | Bandwidth Management | BWM CA SAB SAB MSSA_Labor Only_ Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_ALP_DGS_Spectrum Phase III_192 MHZv2 | CA | SAN | ALP | Bandwidth Management | BWM CA SAB SAB MSSA_Labor Only_ Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_CHU_DGS_Spectrum Phase III 192 MHZV2 | CA | SAN | ELC | Bandwidth Management | BWM CA SAN ELC DGS 192 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_CHU_DGS_Spectrum Phase III 192 MHZV2 | CA | SAN | ELC | Bandwidth Management | BWM CA SAN ELC DGS 192 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Deleted | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_CHU_DGS_Spectrum Phase III 192 MHZV2 | CA | SAN | ELC | Bandwidth Management | BWM CA SAN ELC DGS 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-09-30 | 2020-09-30 | Deleted | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_CHU_DGS_Spectrum Phase III 192 MHZV2 | CA | SAN | ELC | Bandwidth Management | BWM CA SAN ELC DGS 192 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_DWN_DGS_Spectrum Phase III 192 MHZv2 | CA | SAN | CHU | Bandwidth Management | BWM CA SAN CHU DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Deleted | EP
BWM_DWN_DGS_Spectrum Phase III 192 MHZv2 | CA | SAN | CHU | Bandwidth Management | BWM CA SAN CHU DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Deleted | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_DWN_DGS_Spectrum Phase III 192 MHZv2 | CA | SAN | CHU | Bandwidth Management | BWM CA SAN CHU DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-30 | 2020-04-30 | Deleted | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_DWN_DGS_Spectrum Phase III 192 MHZv2 | CA | SAN | CHU | Bandwidth Management | BWM CA SAN CHU DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_ELC_DGS_Spectrum Phase III 192 MHZv2 | CA | SAN | OCE | Bandwidth Management | BWM CA SAN OCE DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Deleted | EP
BWM_ELC_DGS_Spectrum Phase III 192 MHZv2 | CA | SAN | OCE | Bandwidth Management | BWM CA SAN OCE DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Deleted | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_ELC_DGS_Spectrum Phase III 192 MHZv2 | CA | SAN | OCE | Bandwidth Management | BWM CA SAN OCE DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-30 | 2020-04-30 | Deleted | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_ELC_DGS_Spectrum Phase III 192 MHZv2 | CA | SAN | OCE | Bandwidth Management | BWM CA SAN OCE DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_ESC_DGS_Spectrum Phase III 192 MHZv2 | CA | SAN | ESC | Bandwidth Management | BWM CA SAN ESC DGS 192 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Deleted | EP
BWM_ESC_DGS_Spectrum Phase III 192 MHZv2 | CA | SAN | ESC | Bandwidth Management | BWM CA SAN ESC DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Deleted | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_ESC_DGS_Spectrum Phase III 192 MHZv2 | CA | SAN | ESC | Bandwidth Management | BWM CA SAN ESC DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-30 | 2020-04-30 | Deleted | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_ESC_DGS_Spectrum Phase III 192 MHZv2 | CA | SAN | ESC | Bandwidth Management | BWM CA SAN ESC DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_OCE_DGS_Spectrum Phase III 192 MHZv2 | CA | SAN | OCE | Bandwidth Management | BWM CA SAN OCE DGS 192 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_OCE_DGS_Spectrum Phase III 192 MHZv2 | CA | SAN | OCE | Bandwidth Management | BWM CA SAN OCE DGS 192 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Deleted | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_OCE_DGS_Spectrum Phase III 192 MHZv2 | CA | SAN | OCE | Bandwidth Management | BWM CA SAN OCE DGS 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-09-30 | 2020-09-30 | Deleted | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_OCE_DGS_Spectrum Phase III 192 MHZv2 | CA | SAN | OCE | Bandwidth Management | BWM CA SAN OCE DGS 192 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_PWY_DGS_Spectrum Phase III 192 MHZv2 | CA | SAN | FED | Bandwidth Management | BWM CA SAN FED DGS 192 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_PWY_DGS_Spectrum Phase III 192 MHZv2 | CA | SAN | FED | Bandwidth Management | BWM CA SAN FED DGS 192 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Deleted | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_PWY_DGS_Spectrum Phase III 192 MHZv2 | CA | SAN | FED | Bandwidth Management | BWM CA SAN FED DGS 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-09-30 | 2020-09-30 | Deleted | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_PWY_DGS_Spectrum Phase III 192 MHZv2 | CA | SAN | FED | Bandwidth Management | BWM CA SAN FED DGS 192 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_VST_DGS_Spectrum Phase III 192 MHZv2 | CA | SAN | PWY | Bandwidth Management | BWM CA SAN PWY DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Deleted | EP
BWM_VST_DGS_Spectrum Phase III 192 MHZv2 | CA | SAN | PWY | Bandwidth Management | BWM CA SAN PWY DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Deleted | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_VST_DGS_Spectrum Phase III 192 MHZv2 | CA | SAN | PWY | Bandwidth Management | BWM CA SAN PWY DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_ALI_DGS_Spectrum Phase III 192 MHZv2 | SW | LAS | ALI | Bandwidth Management | BWM SW LAS ALI DGS 192 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_ALI_DGS_Spectrum Phase III 192 MHZv2 | SW | LAS | ALI | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-08-31 | Deleted | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_ALI_DGS_Spectrum Phase III 192 MHZv2 | SW | LAS | ALI | Bandwidth Management | BWM SW LAS ALI DGS 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-31 | 2020-08-31 | Deleted | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_ALI_DGS_Spectrum Phase III 192 MHZv2 | SW | LAS | ALI | Bandwidth Management | BWM SW LAS ALI DGS 192 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_BEL_DGS_Spectrum Phase III 192 MHZv2 | SW | ARZ | BEL | Bandwidth Management | BWM SW ARZ BEL DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | EP
BWM_BEL_DGS_Spectrum Phase III 192 MHZv2 | SW | ARZ | BEL | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_BEL_DGS_Spectrum Phase III 192 MHZv2 | SW | ARZ | BEL | Bandwidth Management | BWM SW ARZ BEL DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_BEL_DGS_Spectrum Phase III 192 MHZv2 | SW | ARZ | BEL | Bandwidth Management | BWM SW ARZ BEL DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_BEN_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | BEN | Bandwidth Management | BWM SW ARZ BEN DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | EP
BWM_BEN_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | BEN | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_BEN_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | BEN | Bandwidth Management | BWM SW ARZ BEN DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_BEN_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | BEN | Bandwidth Management | BWM SW ARZ BEN DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_BLU_DGS_Spectrum Phase III 192 MHZv2 | SW | LAS | BLU | Bandwidth Management | BWM SW LAS BLU DGS 192 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_BLU_DGS_Spectrum Phase III 192 MHZv2 | SW | LAS | BLU | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-08-31 | Deleted | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_BLU_DGS_Spectrum Phase III 192 MHZv2 | SW | LAS | BLU | Bandwidth Management | BWM SW LAS BLU DGS 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-31 | 2020-08-31 | Deleted | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_BLU_DGS_Spectrum Phase III 192 MHZv2 | SW | LAS | BLU | Bandwidth Management | BWM SW LAS BLU DGS 192 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_BUK_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | BUK | Bandwidth Management | BWM SW ARZ BUK DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | EP
BWM_BUK_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | BUK | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_BUK_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | BUK | Bandwidth Management | BWM SW ARZ BUK DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_BUK_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | BUK | Bandwidth Management | BWM SW ARZ BUK DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_CSG_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | CSG | Bandwidth Management | BWM SW ARZ CSG DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | EP
BWM_CSG_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | CSG | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_CSG_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | CSG | Bandwidth Management | BWM SW ARZ CSG DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_CSG_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | CSG | Bandwidth Management | BWM SW ARZ CSG DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_CEN_DGS_Spectrum Phase III 192 MHZv2 | SW | LAS | CEN | Bandwidth Management | BWM SW LAS CEN DGS 192 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_CEN_DGS_Spectrum Phase III 192 MHZv2 | SW | LAS | CEN | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-08-31 | Deleted | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_CEN_DGS_Spectrum Phase III 192 MHZv2 | SW | LAS | CEN | Bandwidth Management | BWM SW LAS CEN DGS 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-31 | 2020-08-31 | Deleted | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_CEN_DGS_Spectrum Phase III 192 MHZv2 | SW | LAS | CEN | Bandwidth Management | BWM SW LAS CEN DGS 192 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_CHD_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | CHD | Bandwidth Management | BWM SW ARZ CHD DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | EP
BWM_CHD_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | CHD | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_CHD_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | CHD | Bandwidth Management | BWM SW ARZ CHD DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_CHD_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | CHD | Bandwidth Management | BWM SW ARZ CHD DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_DGL_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | DGL | Bandwidth Management | BWM SW ARZ DGL DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | EP
BWM_DGL_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | DGL | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_DGL_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | DGL | Bandwidth Management | BWM SW ARZ DGL DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_DGL_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | DGL | Bandwidth Management | BWM SW ARZ DGL DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_ERN_DGS_Spectrum Phase III 192 MHZv2 | SW | LAS | ERN | Bandwidth Management | BWM SW LAS ERN DGS 192 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_ERN_DGS_Spectrum Phase III 192 MHZv2 | SW | LAS | ERN | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-08-31 | Deleted | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_ERN_DGS_Spectrum Phase III 192 MHZv2 | SW | LAS | ERN | Bandwidth Management | BWM SW LAS ERN DGS 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-31 | 2020-08-31 | Deleted | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_ERN_DGS_Spectrum Phase III 192 MHZv2 | SW | LAS | ERN | Bandwidth Management | BWM SW LAS ERN DGS 192 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_FWL_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | FWL | Bandwidth Management | BWM SW ARZ FWL DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | EP
BWM_FWL_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | FWL | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_FWL_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | FWL | Bandwidth Management | BWM SW ARZ FWL DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_FWL_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | FWL | Bandwidth Management | BWM SW ARZ FWL DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_GVA_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | GVA | Bandwidth Management | BWM SW ARZ GVA DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | EP
BWM_GVA_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | GVA | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_GVA_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | GVA | Bandwidth Management | BWM SW ARZ GVA DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_GVA_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | GVA | Bandwidth Management | BWM SW ARZ GVA DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_HEN_DGS_Spectrum Phase III 192 MHZv2 | SW | LAS | HEN | Bandwidth Management | BWM SW LAS HEN DGS 192 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_HEN_DGS_Spectrum Phase III 192 MHZv2 | SW | LAS | HEN | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-08-31 | Deleted | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_HEN_DGS_Spectrum Phase III 192 MHZv2 | SW | LAS | HEN | Bandwidth Management | BWM SW LAS HEN DGS 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-31 | 2020-08-31 | Deleted | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_HEN_DGS_Spectrum Phase III 192 MHZv2 | SW | LAS | HEN | Bandwidth Management | BWM SW LAS HEN DGS 192 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_MCD_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | MCD | Bandwidth Management | BWM SW ARZ MCD DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | EP
BWM_MCD_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | MCD | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_MCD_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | MCD | Bandwidth Management | BWM SW ARZ MCD DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_MCD_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | MCD | Bandwidth Management | BWM SW ARZ MCD DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_MSA_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | MSA | Bandwidth Management | BWM SW ARZ MSA DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | EP
BWM_MSA_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | MSA | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_MSA_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | MSA | Bandwidth Management | BWM SW ARZ MSA DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_MSA_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | MSA | Bandwidth Management | BWM SW ARZ MSA DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_NSC_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | NSC | Bandwidth Management | BWM SW ARZ NSC DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | EP
BWM_NSC_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | NSC | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_NSC_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | NSC | Bandwidth Management | BWM SW ARZ NSC DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_NSC_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | NSC | Bandwidth Management | BWM SW ARZ NSC DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_PEO_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | PEO | Bandwidth Management | BWM SW ARZ PEO DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | EP
BWM_PEO_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | PEO | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_PEO_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | PEO | Bandwidth Management | BWM SW ARZ PEO DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_PEO_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | PEO | Bandwidth Management | BWM SW ARZ PEO DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_PNL_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | PNL | Bandwidth Management | BWM SW ARZ PNL DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | EP
BWM_PNL_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | PNL | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_PNL_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | PNL | Bandwidth Management | BWM SW ARZ PNL DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_PNL_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | PNL | Bandwidth Management | BWM SW ARZ PNL DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_SVA_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | SVA | Bandwidth Management | BWM SW ARZ SVA DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | EP
BWM_SVA_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | SVA | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_SVA_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | SVA | Bandwidth Management | BWM SW ARZ SVA DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_SVA_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | SVA | Bandwidth Management | BWM SW ARZ SVA DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_SSC_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | SSC | Bandwidth Management | BWM SW ARZ SSC DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | EP
BWM_SSC_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | SSC | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_SSC_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | SSC | Bandwidth Management | BWM SW ARZ SSC DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_SSC_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | SSC | Bandwidth Management | BWM SW ARZ SSC DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_TEN_DGS_Spectrum Phase III 192 MHZv2 | SW | LAS | TEN | Bandwidth Management | BWM SW LAS TEN DGS 192 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_TEN_DGS_Spectrum Phase III 192 MHZv2 | SW | LAS | TEN | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-08-31 | 2020-08-31 | Deleted | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_TEN_DGS_Spectrum Phase III 192 MHZv2 | SW | LAS | TEN | Bandwidth Management | BWM SW LAS TEN DGS 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-31 | 2020-08-31 | Deleted | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_TEN_DGS_Spectrum Phase III 192 MHZv2 | SW | LAS | TEN | Bandwidth Management | BWM SW LAS TEN DGS 192 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_TUC_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | TUC | Bandwidth Management | BWM SW ARZ TUC DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | EP
BWM_TUC_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | TUC | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_TUC_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | TUC | Bandwidth Management | BWM SW ARZ TUC DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_TUC_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | TUC | Bandwidth Management | BWM SW ARZ TUC DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_VLY_DGS_Spectrum Phase III 192 MHZPOR20 | SW | LAS | VLY | Bandwidth Management | BWM SW LAS VLY DGS 192 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_VLY_DGS_Spectrum Phase III 192 MHZPOR20 | SW | LAS | VLY | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-06-30 | 2020-06-30 | Deleted | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_VLY_DGS_Spectrum Phase III 192 MHZPOR20 | SW | LAS | VLY | Bandwidth Management | BWM SW LAS VLY DGS 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-31 | 2020-08-31 | Deleted | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_VLY_DGS_Spectrum Phase III 192 MHZPOR20 | SW | LAS | VLY | Bandwidth Management | BWM SW LAS VLY DGS 192 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_VSA_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | VSA | Bandwidth Management | BWM SW ARZ VSA DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | EP
BWM_VSA_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | VSA | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_VSA_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | VSA | Bandwidth Management | BWM SW ARZ VSA DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_VSA_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | VSA | Bandwidth Management | BWM SW ARZ VSA DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_WKB_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | WCG | Bandwidth Management | BWM SW ARZ WCG DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | EP
BWM_WKB_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | WCG | Bandwidth Management | BWM SW ARZ DGL Video SG Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_WKB_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | WCG | Bandwidth Management | BWM SW ARZ WCG DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_WKB_DGS_Spectrum Phase III 192 MHZPOR20 | SW | ARZ | WCG | Bandwidth Management | BWM SW ARZ WCG DOCSIS EXPANSION 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-04 | 2020-12-04 | Active | Log | Upd | SN-0473 | New | Approved | 2020-04-17 16:09 | 4 projects are showing the incorrect project name on the POR, making the correction on this CR
BWM_ALP_DGS_Spectrum Phase III_96 MHZv2 | CA | SAN | ALP | Bandwidth Management | BWM CA SAN ALP DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Active | EP
BWM_ALP_DGS_Spectrum Phase III_96 MHZv2 | CA | SAN | ALP | Bandwidth Management | BWM CA SAN ALP DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2019-10-22 | 2020-04-30 | 2020-04-30 | Active | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_ALP_DGS_Spectrum Phase III_96 MHZv2 | CA | SAN | ALP | Bandwidth Management | BWM CA SAN ALP DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-30 | 2020-04-30 | Active | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_ALP_DGS_Spectrum Phase III_96 MHZv2 | CA | SAN | ALP | Bandwidth Management | BWM CA SAN ALP DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-08 | 2020-12-08 | Active | Log | Upd | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
BWM_ALP_DGS_Spectrum Phase III_96 MHZv2 | CA | SAN | ALP | Bandwidth Management | BWM CA SAN ALP DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Active | Log | Del | SN-0195 | Schedule Change | Approved | 2020-01-24 14:40 | 4 VSG project need to be removed and 12 VSG projects needed to be added to POR per reviewing the updated January tracker Reviewing the MSSA Tracker one site needed to be added in ROA VSG 10 schedule chgs and MSSA 127 sch chgs 85 DGS 48MHZ projs deleted
BWM_ALP_DGS_Spectrum Phase III_96 MHZv2 | CA | SAN | ALP | Bandwidth Management | BWM CA SAN ALP DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM_FED_DGS_Spectrum Phase III 192 MHZv2 | CA | SAN | CHU | Bandwidth Management | BWM CA SAN CHU DGS 192 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
BWM_FED_DGS_Spectrum Phase III 192 MHZv2 | CA | SAN | CHU | Bandwidth Management | BWM CA SAN CHU DGS 192 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-09-30 | 2020-09-30 | Deleted | Log | New | SN-0030 | New | Canceled | 2019-10-29 19:36 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 34 96 MHz projects and 34 192 MHZ Docsis Expansion projects (3rd Block)
BWM_FED_DGS_Spectrum Phase III 192 MHZv2 | CA | SAN | CHU | Bandwidth Management | BWM CA SAN CHU DGS 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-09-30 | 2020-09-30 | Deleted | Log | Upd | SN-0063 | New | Approved | 2020-02-06 10:27 | Correcting start date on Project BWM SE GAN OCL MSSA Adding 33 96 MHz projects and 31 192 MHZ Docsis Expansion projects (3rd Block)
BWM_FED_DGS_Spectrum Phase III 192 MHZv2 | CA | SAN | CHU | Bandwidth Management | BWM CA SAN CHU DGS 192 MHz Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0143 | Scope Change | Approved | 2020-02-06 11:07 | DOCSIS expansion plan change removing 82 48MHz, 60 96 MHz (CE), 16 192MHz (LV CA) The 2020 plan will have 31 96 MHz and 18 192MHz projects for (SW and CA regions only) There are also schedule changes for these projects, moving from Q1 Q2 to Q3 Q4
NS SW LAS TEN 48 Node RF Rack Augment POR20 | SW | LAS | TEN | Bandwidth Management | NS SW LAS TEN 48 Node RF Rack Augment POR20 |  |  | 1 |  | 2020-04-15 |  | Deleted | EP
Narrowcast Video SA ORG-ORG 2018 | CA | ORG | ORG | Bandwidth Management | Narrowcast Video SA ORG-ORG 2018 |  |  | 1 |  | 2020-04-15 |  | Deleted | EP
BWM SW ARZ BEL MSSA _Labor Only_ Augment POR20 | SW | ARZ | BEL | Bandwidth Management | BWM SW ARZ BEL MSSA _Labor Only_ Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | EP
BWM SW ARZ BEL MSSA _Labor Only_ Augment POR20 | SW | ARZ | BEL | Bandwidth Management | BWM SW ARZ BEL MSSA _Labor Only_ Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM SW ARZ BEL MSSA _Labor Only_ Augment POR20 | SW | ARZ | BEL | Bandwidth Management | BWM SW ARZ BEL MSSA _Labor Only_ Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM SW ARZ BEN MSSA Augment POR20 | SW | ARZ | BEN | Bandwidth Management | BWM SW ARZ BEN MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | EP
BWM SW ARZ BEN MSSA Augment POR20 | SW | ARZ | BEN | Bandwidth Management | BWM SW ARZ BEN MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM SW ARZ BEN MSSA Augment POR20 | SW | ARZ | BEN | Bandwidth Management | BWM SW ARZ BEN MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM SW ARZ BUK MSSA Augment POR20 | SW | ARZ | BUK | Bandwidth Management | BWM SW ARZ BUK MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | EP
BWM SW ARZ BUK MSSA Augment POR20 | SW | ARZ | BUK | Bandwidth Management | BWM SW ARZ BUK MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM SW ARZ BUK MSSA Augment POR20 | SW | ARZ | BUK | Bandwidth Management | BWM SW ARZ BUK MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM SW ARZ CHD MSSA Augment POR20 | SW | ARZ | CHD | Bandwidth Management | BWM SW ARZ CHD MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | EP
BWM SW ARZ CHD MSSA Augment POR20 | SW | ARZ | CHD | Bandwidth Management | BWM SW ARZ CHD MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM SW ARZ CHD MSSA Augment POR20 | SW | ARZ | CHD | Bandwidth Management | BWM SW ARZ CHD MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM SW ARZ CSG MSSA Augment POR20 | SW | ARZ | CSG | Bandwidth Management | BWM SW ARZ CSG MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | EP
BWM SW ARZ CSG MSSA Augment POR20 | SW | ARZ | CSG | Bandwidth Management | BWM SW ARZ CSG MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM SW ARZ CSG MSSA Augment POR20 | SW | ARZ | CSG | Bandwidth Management | BWM SW ARZ CSG MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM SW ARZ DGL MSSA Augment POR20 | SW | ARZ | DGL | Bandwidth Management | BWM SW ARZ DGL MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | EP
BWM SW ARZ DGL MSSA Augment POR20 | SW | ARZ | DGL | Bandwidth Management | BWM SW ARZ DGL MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM SW ARZ DGL MSSA Augment POR20 | SW | ARZ | DGL | Bandwidth Management | BWM SW ARZ DGL MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM SW ARZ FWL MSSA Augment POR20 | SW | ARZ | FWL | Bandwidth Management | BWM SW ARZ FWL MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | EP
BWM SW ARZ FWL MSSA Augment POR20 | SW | ARZ | FWL | Bandwidth Management | BWM SW ARZ FWL MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM SW ARZ FWL MSSA Augment POR20 | SW | ARZ | FWL | Bandwidth Management | BWM SW ARZ FWL MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM SW ARZ GVA MSSA Augment POR20 | SW | ARZ | GVA | Bandwidth Management | BWM SW ARZ GVA MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | EP
BWM SW ARZ GVA MSSA Augment POR20 | SW | ARZ | GVA | Bandwidth Management | BWM SW ARZ GVA MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM SW ARZ GVA MSSA Augment POR20 | SW | ARZ | GVA | Bandwidth Management | BWM SW ARZ GVA MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM SW ARZ JMX MSSA Augment POR20 | SW | ARZ | JMX | Bandwidth Management | BWM SW ARZ JMX MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | EP
BWM SW ARZ JMX MSSA Augment POR20 | SW | ARZ | JMX | Bandwidth Management | BWM SW ARZ JMX MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM SW ARZ JMX MSSA Augment POR20 | SW | ARZ | JMX | Bandwidth Management | BWM SW ARZ JMX MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM SW ARZ MCD MSSA Augment POR20 | SW | ARZ | MCD | Bandwidth Management | BWM SW ARZ MCD MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | EP
BWM SW ARZ MCD MSSA Augment POR20 | SW | ARZ | MCD | Bandwidth Management | BWM SW ARZ MCD MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM SW ARZ MCD MSSA Augment POR20 | SW | ARZ | MCD | Bandwidth Management | BWM SW ARZ MCD MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM SW ARZ MSA MSSA Augment POR20 | SW | ARZ | MSA | Bandwidth Management | BWM SW ARZ MSA MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | EP
BWM SW ARZ MSA MSSA Augment POR20 | SW | ARZ | MSA | Bandwidth Management | BWM SW ARZ MSA MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM SW ARZ MSA MSSA Augment POR20 | SW | ARZ | MSA | Bandwidth Management | BWM SW ARZ MSA MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM SW ARZ NSC MSSA Augment POR20 | SW | ARZ | NSC | Bandwidth Management | BWM SW ARZ NSC MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | EP
BWM SW ARZ NSC MSSA Augment POR20 | SW | ARZ | NSC | Bandwidth Management | BWM SW ARZ NSC MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM SW ARZ NSC MSSA Augment POR20 | SW | ARZ | NSC | Bandwidth Management | BWM SW ARZ NSC MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM SW ARZ PEO MSSA Augment POR20 | SW | ARZ | PEO | Bandwidth Management | BWM SW ARZ PEO MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | EP
BWM SW ARZ PEO MSSA Augment POR20 | SW | ARZ | PEO | Bandwidth Management | BWM SW ARZ PEO MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM SW ARZ PEO MSSA Augment POR20 | SW | ARZ | PEO | Bandwidth Management | BWM SW ARZ PEO MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM SW ARZ PNL MSSA Augment POR20 | SW | ARZ | PNL | Bandwidth Management | BWM SW ARZ PNL MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | EP
BWM SW ARZ PNL MSSA Augment POR20 | SW | ARZ | PNL | Bandwidth Management | BWM SW ARZ PNL MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM SW ARZ PNL MSSA Augment POR20 | SW | ARZ | PNL | Bandwidth Management | BWM SW ARZ PNL MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM SW ARZ SSC MSSA Augment POR20 | SW | ARZ | SSC | Bandwidth Management | BWM SW ARZ SSC MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | EP
BWM SW ARZ SSC MSSA Augment POR20 | SW | ARZ | SSC | Bandwidth Management | BWM SW ARZ SSC MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM SW ARZ SSC MSSA Augment POR20 | SW | ARZ | SSC | Bandwidth Management | BWM SW ARZ SSC MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM SW ARZ TUC MSSA Augment POR20 | SW | ARZ | TUC | Bandwidth Management | BWM SW ARZ TUC MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | EP
BWM SW ARZ TUC MSSA Augment POR20 | SW | ARZ | TUC | Bandwidth Management | BWM SW ARZ TUC MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM SW ARZ TUC MSSA Augment POR20 | SW | ARZ | TUC | Bandwidth Management | BWM SW ARZ TUC MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM SW ARZ VAL MSSA Augment POR20 | SW | ARZ | VAL | Bandwidth Management | BWM SW ARZ VAL MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | EP
BWM SW ARZ VAL MSSA Augment POR20 | SW | ARZ | VAL | Bandwidth Management | BWM SW ARZ VAL MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM SW ARZ VAL MSSA Augment POR20 | SW | ARZ | VAL | Bandwidth Management | BWM SW ARZ VAL MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM SW ARZ SVA MSSA Augment POR20 | SW | ARZ | VSA | Bandwidth Management | BWM SW ARZ VSA MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | EP
BWM SW ARZ SVA MSSA Augment POR20 | SW | ARZ | VSA | Bandwidth Management | BWM SW ARZ VSA MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM SW ARZ SVA MSSA Augment POR20 | SW | ARZ | VSA | Bandwidth Management | BWM SW ARZ VSA MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM SW ARZ VSA MSSA Augment POR20 | SW | ARZ | VSA | Bandwidth Management | BWM SW ARZ VSA MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | EP
BWM SW ARZ VSA MSSA Augment POR20 | SW | ARZ | VSA | Bandwidth Management | BWM SW ARZ VSA MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM SW ARZ VSA MSSA Augment POR20 | SW | ARZ | VSA | Bandwidth Management | BWM SW ARZ VSA MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM SW ARZ WCG MSSA Augment POR20 | SW | ARZ | WCG | Bandwidth Management | BWM SW ARZ WCG MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | EP
BWM SW ARZ WCG MSSA Augment POR20 | SW | ARZ | WCG | Bandwidth Management | BWM SW ARZ WCG MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM SW ARZ WCG MSSA Augment POR20 | SW | ARZ | WCG | Bandwidth Management | BWM SW ARZ WCG MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM SW LAS ALI MSSA _Labor Only_ Augment POR20 | SW | LAS | ALI | Bandwidth Management | BWM SW LAS ALI MSSA _Labor Only_ Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | EP
BWM SW LAS ALI MSSA _Labor Only_ Augment POR20 | SW | LAS | ALI | Bandwidth Management | BWM SW LAS ALI MSSA _Labor Only_ Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM SW LAS ALI MSSA _Labor Only_ Augment POR20 | SW | LAS | ALI | Bandwidth Management | BWM SW LAS ALI MSSA _Labor Only_ Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM SW LAS AMI MSSA Augment POR20 | SW | LAS | AMI | Bandwidth Management | BWM SW LAS AMI MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | EP
BWM SW LAS AMI MSSA Augment POR20 | SW | LAS | AMI | Bandwidth Management | BWM SW LAS AMI MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM SW LAS AMI MSSA Augment POR20 | SW | LAS | AMI | Bandwidth Management | BWM SW LAS AMI MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM SW LAS BLU MSSA Augment POR20 | SW | LAS | BLU | Bandwidth Management | BWM SW LAS BLU MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | EP
BWM SW LAS BLU MSSA Augment POR20 | SW | LAS | BLU | Bandwidth Management | BWM SW LAS BLU MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM SW LAS BLU MSSA Augment POR20 | SW | LAS | BLU | Bandwidth Management | BWM SW LAS BLU MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM SW LAS BOC MSSA Augment POR20 | SW | LAS | BOC | Bandwidth Management | BWM SW LAS BOC MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | EP
BWM SW LAS BOC MSSA Augment POR20 | SW | LAS | BOC | Bandwidth Management | BWM SW LAS BOC MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM SW LAS BOC MSSA Augment POR20 | SW | LAS | BOC | Bandwidth Management | BWM SW LAS BOC MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM SW LAS CEN MSSA Augment POR20 | SW | LAS | CEN | Bandwidth Management | BWM SW LAS CEN MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | EP
BWM SW LAS CEN MSSA Augment POR20 | SW | LAS | CEN | Bandwidth Management | BWM SW LAS CEN MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM SW LAS CEN MSSA Augment POR20 | SW | LAS | CEN | Bandwidth Management | BWM SW LAS CEN MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM SW LAS ERN MSSA Augment POR20 | SW | LAS | ERN | Bandwidth Management | BWM SW LAS ERN MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | EP
BWM SW LAS ERN MSSA Augment POR20 | SW | LAS | ERN | Bandwidth Management | BWM SW LAS ERN MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM SW LAS ERN MSSA Augment POR20 | SW | LAS | ERN | Bandwidth Management | BWM SW LAS ERN MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM SW LAS HEN MSSA Augment POR20 | SW | LAS | HEN | Bandwidth Management | BWM SW LAS HEN MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | EP
BWM SW LAS HEN MSSA Augment POR20 | SW | LAS | HEN | Bandwidth Management | BWM SW LAS HEN MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM SW LAS HEN MSSA Augment POR20 | SW | LAS | HEN | Bandwidth Management | BWM SW LAS HEN MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM SW LAS OSB MSSA Augment POR20 | SW | LAS | OSB | Bandwidth Management | BWM SW LAS OSB MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | EP
BWM SW LAS OSB MSSA Augment POR20 | SW | LAS | OSB | Bandwidth Management | BWM SW LAS OSB MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM SW LAS OSB MSSA Augment POR20 | SW | LAS | OSB | Bandwidth Management | BWM SW LAS OSB MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM SW LAS TEN MSSA Augment POR20 | SW | LAS | TEN | Bandwidth Management | BWM SW LAS TEN MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | EP
BWM SW LAS TEN MSSA Augment POR20 | SW | LAS | TEN | Bandwidth Management | BWM SW LAS TEN MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM SW LAS TEN MSSA Augment POR20 | SW | LAS | TEN | Bandwidth Management | BWM SW LAS TEN MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM SW LAS VLY MSSA Augment POR20 | SW | LAS | VLY | Bandwidth Management | BWM SW LAS VLY MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | EP
BWM SW LAS VLY MSSA Augment POR20 | SW | LAS | VLY | Bandwidth Management | BWM SW LAS VLY MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-30 | 2020-03-30 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM SW LAS VLY MSSA Augment POR20 | SW | LAS | VLY | Bandwidth Management | BWM SW LAS VLY MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-15 | 2020-03-11 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_ALP_MSSA_Spectrum Phase II Start | CA | SAN | ALP | Bandwidth Management | BWM CA SAN ALP MSSA _Labor Only_ Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-10 | 2020-03-11 | Active | EP
BWM_ALP_MSSA_Spectrum Phase II Start | CA | SAN | ALP | Bandwidth Management | BWM CA SAN ALP MSSA _Labor Only_ Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 | 2020-07-01 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM_ALP_MSSA_Spectrum Phase II Start | CA | SAN | ALP | Bandwidth Management | BWM CA SAN ALP MSSA _Labor Only_ Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-10 | 2020-03-11 | Active | Log | Upd | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_CHU_DGS_Spectrum Phase II 96 MHZv2 | CA | SAN | CHU | Bandwidth Management | BWM CA SAN CHU DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Active | EP
BWM_CHU_DGS_Spectrum Phase II 96 MHZv2 | CA | SAN | CHU | Bandwidth Management | BWM CA SAN CHU DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM_OCE_DGS_Spectrum Phase II 96 MHZv2 | CA | SAN | OCE | Bandwidth Management | BWM CA SAN OCE DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Active | EP
BWM_OCE_DGS_Spectrum Phase II 96 MHZv2 | CA | SAN | OCE | Bandwidth Management | BWM CA SAN OCE DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM_VST_DGS_Spectrum Phase II 96 MHZv2 | CA | SAN | VST | Bandwidth Management | BWM CA SAN VST DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Active | EP
BWM_VST_DGS_Spectrum Phase II 96 MHZv2 | CA | SAN | VST | Bandwidth Management | BWM CA SAN VST DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM_DWN_DGS_Spectrum Phase II 96 MHZ | CA | SAN | DWN | Bandwidth Management | BWM CA SAN DWN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Active | EP
BWM_DWN_DGS_Spectrum Phase II 96 MHZ | CA | SAN | DWN | Bandwidth Management | BWM CA SAN DWN DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM_ESC_DGS_Spectrum Phase II 96 MHZ | CA | SAN | ESC | Bandwidth Management | BWM CA SAN ESC DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Active | EP
BWM_ESC_DGS_Spectrum Phase II 96 MHZ | CA | SAN | ESC | Bandwidth Management | BWM CA SAN ESC DOCSIS EXPANSION 96 MHz Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-18 | 2020-12-18 | Active | Log | Undel | SN-0330 | Schedule Change | Approved | 2020-03-27 15:11 | I attempted to reactivate these projects on CR SN-0245, but I did not follow the proper update method and they did not save once the CR was submitted
BWM_ROA_ MSSA_Spectrum Phase II Start | VA | ROA | RON | Bandwidth Management | BWM VA ROA RON MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-15 | 2020-06-18 | Active | EP
BWM_ROA_ MSSA_Spectrum Phase II Start | VA | ROA | RON | Bandwidth Management | BWM VA ROA RON MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 |  | 2020-05-18 | 2020-08-14 | Active | Log | Undel | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_ROA_ MSSA_Spectrum Phase II Start | VA | ROA | RON | Bandwidth Management | BWM VA ROA RON MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-15 | 2020-08-14 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM_ROA_ MSSA_Spectrum Phase II Start | VA | ROA | RON | Bandwidth Management | BWM VA ROA RON MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-06-15 | 2020-06-18 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM_MCN_MSSA_Spectrum Phase II Start | SE | MGA | MCN | Bandwidth Management | BWM SE MGA MCN MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-19 | 2020-03-11 | Active | EP
BWM_MCN_MSSA_Spectrum Phase II Start | SE | MGA | MCN | Bandwidth Management | BWM SE MGA MCN MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-19 | 2020-03-11 | Active | Log | Undel | SN-0426 | Schedule Change | Approved | 2020-04-10 15:22 | Adjusting SA dates to align with current SA Tracker, reactivated 2 MSSA projects (ROA MCN) and deleted 1 VSG project so it can be removed from DB (CE WES) POR changes only no financial impact
BWM_MCN_MSSA_Spectrum Phase II Start | SE | MGA | MCN | Bandwidth Management | BWM SE MGA MCN MSSA Augment POR20 | Labor | No Equipment | 1 |  | 2019-05-19 | 2020-03-11 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
| CA | SAN | ALP | Bandwidth Management | BWM CA SAN ALP SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment |  |  | 2020-05-31 | 2020-05-31 | Deleted | EP
BWM SA SAN COVID-19_ LABOR ONLY | CA | SAN | ALP | Bandwidth Management | BWM CA SAN ALP SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | EP
BWM SA SAN COVID-19_ LABOR ONLY | CA | SAN | ALP | Bandwidth Management | BWM CA SAN ALP SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0479 | COVID-19 Related | Approved | 2020-04-24 14:39 | BWM Adding 5th carrier to address impact of COVID 19 on the spectrum for all markets Taking 45K from IHL topside to cover SA COVID 19 IHL charges
BWM SA ORG COVID-19_ LABOR ONLY | CA | ORG | AVJ | Bandwidth Management | BWM CA ORG AVJ SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | EP
BWM SA ORG COVID-19_ LABOR ONLY | CA | ORG | AVJ | Bandwidth Management | BWM CA ORG AVJ SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0479 | COVID-19 Related | Approved | 2020-04-24 14:39 | BWM Adding 5th carrier to address impact of COVID 19 on the spectrum for all markets Taking 45K from IHL topside to cover SA COVID 19 IHL charges
BWM SA SAB COVID-19_ LABOR ONLY | CA | SAB | SAB | Bandwidth Management | BWM CA SAB SAB SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | EP
BWM SA SAB COVID-19_ LABOR ONLY | CA | SAB | SAB | Bandwidth Management | BWM CA SAB SAB SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0479 | COVID-19 Related | Approved | 2020-04-24 14:39 | BWM Adding 5th carrier to address impact of COVID 19 on the spectrum for all markets Taking 45K from IHL topside to cover SA COVID 19 IHL charges
BWM SA NWA COVID-19_ LABOR ONLY | CE | OMA | BLV | Bandwidth Management | BWM CE NWA BVL SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | EP
BWM SA NWA COVID-19_ LABOR ONLY | CE | OMA | BLV | Bandwidth Management | BWM CE NWA BVL SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0479 | COVID-19 Related | Approved | 2020-04-24 14:39 | BWM Adding 5th carrier to address impact of COVID 19 on the spectrum for all markets Taking 45K from IHL topside to cover SA COVID 19 IHL charges
BWM SA KAN COVID-19_ LABOR ONLY | CE | KAN | CFV | Bandwidth Management | BWM CE KAN CFV SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | EP
BWM SA KAN COVID-19_ LABOR ONLY | CE | KAN | CFV | Bandwidth Management | BWM CE KAN CFV SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0479 | COVID-19 Related | Approved | 2020-04-24 14:39 | BWM Adding 5th carrier to address impact of COVID 19 on the spectrum for all markets Taking 45K from IHL topside to cover SA COVID 19 IHL charges
BWM SA OKC COVID-19_ LABOR ONLY | CE | OKC | CHO | Bandwidth Management | BWM CE OKC CHO SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | EP
BWM SA OKC COVID-19_ LABOR ONLY | CE | OKC | CHO | Bandwidth Management | BWM CE OKC CHO SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0479 | COVID-19 Related | Approved | 2020-04-24 14:39 | BWM Adding 5th carrier to address impact of COVID 19 on the spectrum for all markets Taking 45K from IHL topside to cover SA COVID 19 IHL charges
BWM SA SUN COVID-19_ LABOR ONLY | CE | SUN | SVI | Bandwidth Management | BWM CE SUN SVI SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | EP
BWM SA SUN COVID-19_ LABOR ONLY | CE | SUN | SVI | Bandwidth Management | BWM CE SUN SVI SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0479 | COVID-19 Related | Approved | 2020-04-24 14:39 | BWM Adding 5th carrier to address impact of COVID 19 on the spectrum for all markets Taking 45K from IHL topside to cover SA COVID 19 IHL charges
BWM SA OMA COVID-19_ LABOR ONLY | CE | OMA | BLV | Bandwidth Management | BWM CE OMA BLV SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | EP
BWM SA OMA COVID-19_ LABOR ONLY | CE | OMA | BLV | Bandwidth Management | BWM CE OMA BLV SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0479 | COVID-19 Related | Approved | 2020-04-24 14:39 | BWM Adding 5th carrier to address impact of COVID 19 on the spectrum for all markets Taking 45K from IHL topside to cover SA COVID 19 IHL charges
BWM SA TUL COVID-19_ LABOR ONLY | CE | TUL | BAR | Bandwidth Management | BWM CE TUL BAR SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | EP
BWM SA TUL COVID-19_ LABOR ONLY | CE | TUL | BAR | Bandwidth Management | BWM CE TUL BAR SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0479 | COVID-19 Related | Approved | 2020-04-24 14:39 | BWM Adding 5th carrier to address impact of COVID 19 on the spectrum for all markets Taking 45K from IHL topside to cover SA COVID 19 IHL charges
BWM SA CLE COVID-19_ LABOR ONLY | NE | CLE | CLV | Bandwidth Management | BWM NE CLE CLV SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | EP
BWM SA CLE COVID-19_ LABOR ONLY | NE | CLE | CLV | Bandwidth Management | BWM NE CLE CLV SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0479 | COVID-19 Related | Approved | 2020-04-24 14:39 | BWM Adding 5th carrier to address impact of COVID 19 on the spectrum for all markets Taking 45K from IHL topside to cover SA COVID 19 IHL charges
BWM SA CON COVID-19_ LABOR ONLY | NE | CON | ENF | Bandwidth Management | BWM NE CON ENF SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | EP
BWM SA CON COVID-19_ LABOR ONLY | NE | CON | ENF | Bandwidth Management | BWM NE CON ENF SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0479 | COVID-19 Related | Approved | 2020-04-24 14:39 | BWM Adding 5th carrier to address impact of COVID 19 on the spectrum for all markets Taking 45K from IHL topside to cover SA COVID 19 IHL charges
BWM SA RHD COVID-19_ LABOR ONLY | NE | RHD | BUR | Bandwidth Management | BWM NE RHD BUR MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-29 | 2020-07-08 | Active | EP
BWM SA RHD COVID-19_ LABOR ONLY | NE | RHD | BUR | Bandwidth Management | BWM NE RHD BUR MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0479 | COVID-19 Related | Approved | 2020-04-24 14:39 | BWM Adding 5th carrier to address impact of COVID 19 on the spectrum for all markets Taking 45K from IHL topside to cover SA COVID 19 IHL charges
BWM SA RHD COVID-19_ LABOR ONLY | NE | RHD | BUR | Bandwidth Management | BWM NE RHD BUR MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-29 | 2020-08-28 | Active | Log | Upd | SN-0498 | Schedule Change | Approved | 2020-04-29 16:34 | Date changes for the following 11 spectrum alignment markets due to Peregrine plan changes: SAB TUL OMA KAN NWA OKC CLV RHD CON ROA GCT GLA majority of date changes are within same quarter most within same month no financial realignment required
BWM SA RHD COVID-19_ LABOR ONLY | NE | RHD | BUR | Bandwidth Management | BWM NE RHD BUR MSSA_Labor Only_ Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-29 | 2020-07-08 | Active | Log | Upd | SN-0703 | New | Approved | 2020-06-30 11:14 | Moving dollars from CORP PPM 75649 into the perspective regions for DOCSIS Expansion and VSG Also updating migration cutover dates for MSSA
BWM SA GAN COVID-19_ LABOR ONLY | SE | GAN | GNS | Bandwidth Management | BWM SE GAN GNS SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | EP
BWM SA GAN COVID-19_ LABOR ONLY | SE | GAN | GNS | Bandwidth Management | BWM SE GAN GNS SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0479 | COVID-19 Related | Approved | 2020-04-24 14:39 | BWM Adding 5th carrier to address impact of COVID 19 on the spectrum for all markets Taking 45K from IHL topside to cover SA COVID 19 IHL charges
BWM SA GCT COVID-19_ LABOR ONLY | SE | GCT | CRV | Bandwidth Management | BWM SE GCT CRV SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | EP
BWM SA GCT COVID-19_ LABOR ONLY | SE | GCT | CRV | Bandwidth Management | BWM SE GCT CRV SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0479 | COVID-19 Related | Approved | 2020-04-24 14:39 | BWM Adding 5th carrier to address impact of COVID 19 on the spectrum for all markets Taking 45K from IHL topside to cover SA COVID 19 IHL charges
BWM SA MGA COVID-19_ LABOR ONLY | SE | MGA | GRY | Bandwidth Management | BWM SE MGA GRY SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | EP
BWM SA MGA COVID-19_ LABOR ONLY | SE | MGA | GRY | Bandwidth Management | BWM SE MGA GRY SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0479 | COVID-19 Related | Approved | 2020-04-24 14:39 | BWM Adding 5th carrier to address impact of COVID 19 on the spectrum for all markets Taking 45K from IHL topside to cover SA COVID 19 IHL charges
BWM SA LFY COVID-19_ LABOR ONLY | SE | LFY | ABV | Bandwidth Management | BWM SE LFY ABV SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | EP
BWM SA LFY COVID-19_ LABOR ONLY | SE | LFY | ABV | Bandwidth Management | BWM SE LFY ABV SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0479 | COVID-19 Related | Approved | 2020-04-24 14:39 | BWM Adding 5th carrier to address impact of COVID 19 on the spectrum for all markets Taking 45K from IHL topside to cover SA COVID 19 IHL charges
BWM SA BTR COVID-19_ LABOR ONLY | SE | BTR | BTR | Bandwidth Management | BWM SE BTR BTR SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | EP
BWM SA BTR COVID-19_ LABOR ONLY | SE | BTR | BTR | Bandwidth Management | BWM SE BTR BTR SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0479 | COVID-19 Related | Approved | 2020-04-24 14:39 | BWM Adding 5th carrier to address impact of COVID 19 on the spectrum for all markets Taking 45K from IHL topside to cover SA COVID 19 IHL charges
BWM SA NOR COVID-19_ LABOR ONLY | SE | NOR | ALG | Bandwidth Management | BWM SE NOR ALN SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | EP
BWM SA NOR COVID-19_ LABOR ONLY | SE | NOR | ALG | Bandwidth Management | BWM SE NOR ALN SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0479 | COVID-19 Related | Approved | 2020-04-24 14:39 | BWM Adding 5th carrier to address impact of COVID 19 on the spectrum for all markets Taking 45K from IHL topside to cover SA COVID 19 IHL charges
BWM SA ARZ COVID-19_ LABOR ONLY | SW | ARZ | PNL | Bandwidth Management | BWM SW ARZ PNL SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | EP
BWM SA ARZ COVID-19_ LABOR ONLY | SW | ARZ | PNL | Bandwidth Management | BWM SW ARZ PNL SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0479 | COVID-19 Related | Approved | 2020-04-24 14:39 | BWM Adding 5th carrier to address impact of COVID 19 on the spectrum for all markets Taking 45K from IHL topside to cover SA COVID 19 IHL charges
BWM SA LAS COVID-19_ LABOR ONLY | SW | LAS | ALI | Bandwidth Management | BWM SW LAS ALI SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | EP
BWM SA LAS COVID-19_ LABOR ONLY | SW | LAS | ALI | Bandwidth Management | BWM SW LAS ALI SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0479 | COVID-19 Related | Approved | 2020-04-24 14:39 | BWM Adding 5th carrier to address impact of COVID 19 on the spectrum for all markets Taking 45K from IHL topside to cover SA COVID 19 IHL charges
BWM SA HRD COVID-19_ LABOR ONLY | VA | HRD | ALX | Bandwidth Management | BWM VA NVA DRA SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | EP
BWM SA HRD COVID-19_ LABOR ONLY | VA | HRD | ALX | Bandwidth Management | BWM VA NVA DRA SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0479 | COVID-19 Related | Approved | 2020-04-24 14:39 | BWM Adding 5th carrier to address impact of COVID 19 on the spectrum for all markets Taking 45K from IHL topside to cover SA COVID 19 IHL charges
BWM SA HRD COVID-19_ LABOR ONLY | VA | HRD | ALX | Bandwidth Management | BWM VA NVA DRA SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0587 | New | Approved | 2020-05-14 16:37 | Updated 12 Need by dates
BWM SA NVA COVID-19_ LABOR ONLY | VA | NVA | DRA | Bandwidth Management | BWM VA NVA DRA SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | EP
BWM SA NVA COVID-19_ LABOR ONLY | VA | NVA | DRA | Bandwidth Management | BWM VA NVA DRA SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0479 | COVID-19 Related | Approved | 2020-04-24 14:39 | BWM Adding 5th carrier to address impact of COVID 19 on the spectrum for all markets Taking 45K from IHL topside to cover SA COVID 19 IHL charges
BWM SA ROA COVID-19_ LABOR ONLY | VA | ROA | RON | Bandwidth Management | BWM VA ROA RON SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | EP
BWM SA ROA COVID-19_ LABOR ONLY | VA | ROA | RON | Bandwidth Management | BWM VA ROA RON SA COVID19 _LABOR ONLY Augment POR20 | Labor | No Equipment | 1 | 2020-04-21 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0479 | COVID-19 Related | Approved | 2020-04-24 14:39 | BWM Adding 5th carrier to address impact of COVID 19 on the spectrum for all markets Taking 45K from IHL topside to cover SA COVID 19 IHL charges
BWM ORG DOCSIS Expansion 192 MHz | CA | ORG | AVJ | Bandwidth Management | BWM CA ORG AVJ DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-12 | 2022-04-01 | Active | EP
BWM ORG DOCSIS Expansion 192 MHz | CA | ORG | AVJ | Bandwidth Management | BWM CA ORG AVJ DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-12 | 2022-04-01 | Active | Log | Upd | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM ORG DOCSIS Expansion 96 MHz | CA | ORG | AVJ | Bandwidth Management | BWM CA ORG AVJ DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-12 | 2022-04-01 | Active | EP
BWM ORG DOCSIS Expansion 96 MHz | CA | ORG | AVJ | Bandwidth Management | BWM CA ORG AVJ DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-12 | 2022-04-01 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM SAB DOCSIS Expansion 192 MHz | CA | SAB | SAB | Bandwidth Management | BWM CA SAB SAB DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-03 | 2023-10-05 | Active | EP
BWM SAB DOCSIS Expansion 192 MHz | CA | SAB | SAB | Bandwidth Management | BWM CA SAB SAB DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-03 | 2023-10-05 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM SAB DOCSIS Expansion 96 MHz | CA | SAB | SAB | Bandwidth Management | BWM CA SAB SAB DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-03 | 2022-10-03 | Active | EP
BWM SAB DOCSIS Expansion 96 MHz | CA | SAB | SAB | Bandwidth Management | BWM CA SAB SAB DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-03 | 2022-10-03 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM KAN DOCSIS Expansion 192 MHz | CE | KAN | CFV | Bandwidth Management | BWM CE KAN CFV DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-14 | 2022-01-14 | Active | EP
BWM KAN DOCSIS Expansion 192 MHz | CE | KAN | CFV | Bandwidth Management | BWM CE KAN CFV DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-14 | 2022-01-14 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM KAN DOCSIS Expansion 96 MHz | CE | KAN | CFV | Bandwidth Management | BWM CE KAN CFV DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-14 | 2021-04-01 | Active | EP
BWM KAN DOCSIS Expansion 96 MHz | CE | KAN | CFV | Bandwidth Management | BWM CE KAN CFV DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-14 | 2021-04-01 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM NWA DOCSIS Expansion 192 MHz | CE | NWA | BVL | Bandwidth Management | BWM CE NWA BVL DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-14 | 2022-01-14 | Active | EP
BWM NWA DOCSIS Expansion 192 MHz | CE | NWA | BVL | Bandwidth Management | BWM CE NWA BVL DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-14 | 2022-01-14 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM NWA DOCSIS Expansion 96 MHz | CE | NWA | BVL | Bandwidth Management | BWM CE NWA BVL DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-14 | 2021-04-01 | Active | EP
BWM NWA DOCSIS Expansion 96 MHz | CE | NWA | BVL | Bandwidth Management | BWM CE NWA BVL DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-14 | 2021-04-01 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM OKC DOCSIS Expansion 192 MHz | CE | OKC | CHO | Bandwidth Management | BWM CE OKC CHO DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-31 | 2021-01-20 | Active | EP
BWM OKC DOCSIS Expansion 192 MHz | CE | OKC | CHO | Bandwidth Management | BWM CE OKC CHO DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-31 | 2021-01-20 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM OKC DOCSIS Expansion 96 MHz | CE | OKC | CHO | Bandwidth Management | BWM CE OKC CHO DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-31 | 2020-10-30 | Active | EP
BWM OKC DOCSIS Expansion 96 MHz | CE | OKC | CHO | Bandwidth Management | BWM CE OKC CHO DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-31 | 2020-10-30 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM OMA DOCSIS Expansion 192 MHz | CE | OMA | BLV | Bandwidth Management | BWM CE OMA BLV DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-11-13 | 2021-10-01 | Active | EP
BWM OMA DOCSIS Expansion 192 MHz | CE | OMA | BLV | Bandwidth Management | BWM CE OMA BLV DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-11-13 | 2021-10-01 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM OMA DOCSIS Expansion 96 MHz | CE | OMA | BLV | Bandwidth Management | BWM CE OMA BLV DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-11-13 | 2021-01-06 | Active | EP
BWM OMA DOCSIS Expansion 96 MHz | CE | OMA | BLV | Bandwidth Management | BWM CE OMA BLV DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-11-13 | 2021-01-06 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM SUN DOCSIS Expansion 192 MHz | CE | SUN | SVI | Bandwidth Management | BWM CE SUN SVI DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-14 | 2021-04-01 | Active | EP
BWM SUN DOCSIS Expansion 192 MHz | CE | SUN | SVI | Bandwidth Management | BWM CE SUN SVI DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-14 | 2021-04-01 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM SUN DOCSIS Expansion 96 MHz | CE | SUN | SVI | Bandwidth Management | BWM CE SUN SVI DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-14 | 2021-04-01 | Active | EP
BWM SUN DOCSIS Expansion 96 MHz | CE | SUN | SVI | Bandwidth Management | BWM CE SUN SVI DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-14 | 2021-04-01 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM BRD DOCSIS Expansion 192 MHz | CE | TUL | BRD | Bandwidth Management | BWM CE TUL BRD DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-11 | 2020-10-15 | Active | EP
BWM BRD DOCSIS Expansion 192 MHz | CE | TUL | BRD | Bandwidth Management | BWM CE TUL BRD DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-11 | 2020-10-15 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM BAR DOCSIS Expansion 96 MHz | CE | TUL | BAR | Bandwidth Management | BWM CE TUL BAR DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-11 | 2021-10-01 | Active | EP
BWM BAR DOCSIS Expansion 96 MHz | CE | TUL | BAR | Bandwidth Management | BWM CE TUL BAR DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-11 | 2021-10-01 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM CLE DOCSIS Expansion 192 MHz | NE | CLE | CLV | Bandwidth Management | BWM NE CLE CLV DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-10 | 2021-10-01 | Active | EP
BWM CLE DOCSIS Expansion 192 MHz | NE | CLE | CLV | Bandwidth Management | BWM NE CLE CLV DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-10 | 2021-10-01 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM CLE DOCSIS Expansion 96 MHz | NE | CLE | CLV | Bandwidth Management | BWM NE CLE CLV DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-10 | 2022-10-03 | Active | EP
BWM CLE DOCSIS Expansion 96 MHz | NE | CLE | CLV | Bandwidth Management | BWM NE CLE CLV DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-10 | 2022-10-03 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM CON DOCSIS Expansion 192 MHz | NE | CON | ENF | Bandwidth Management | BWM NE CON ENF DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-11-13 | 2022-07-01 | Active | EP
BWM CON DOCSIS Expansion 192 MHz | NE | CON | ENF | Bandwidth Management | BWM NE CON ENF DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-11-13 | 2022-07-01 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM CON DOCSIS Expansion 96 MHz | NE | CON | ENF | Bandwidth Management | BWM NE CON ENF DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-11-13 | 2021-10-01 | Active | EP
BWM CON DOCSIS Expansion 96 MHz | NE | CON | ENF | Bandwidth Management | BWM NE CON ENF DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-11-13 | 2021-10-01 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM RHD DOCSIS Expansion 192 MHz | NE | RHD | CRN | Bandwidth Management | BWM NE RHD CRN DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-08 | 2022-04-01 | Active | EP
BWM RHD DOCSIS Expansion 192 MHz | NE | RHD | CRN | Bandwidth Management | BWM NE RHD CRN DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-08 | 2022-04-01 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM RHD DOCSIS Expansion 96 MHz | NE | RHD | PAW | Bandwidth Management | BWM NE RHD PAW DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-08 | 2021-07-01 | Active | EP
BWM RHD DOCSIS Expansion 96 MHz | NE | RHD | PAW | Bandwidth Management | BWM NE RHD PAW DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-08 | 2021-07-01 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM BTR DOCSIS Expansion 192 MHz | SE | BTR | BTR | Bandwidth Management | BWM SE BTR BTR DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-11-13 | 2022-12-01 | Active | EP
BWM BTR DOCSIS Expansion 192 MHz | SE | BTR | BTR | Bandwidth Management | BWM SE BTR BTR DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-11-13 | 2022-12-01 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM BTR DOCSIS Expansion 96 MHz | SE | BTR | BTR | Bandwidth Management | BWM SE BTR BTR DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-11-13 | 2022-07-01 | Active | EP
BWM BTR DOCSIS Expansion 96 MHz | SE | BTR | BTR | Bandwidth Management | BWM SE BTR BTR DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-11-13 | 2022-07-01 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM GCT DOCSIS Expansion 192 MHz | SE | GCT | CRV | Bandwidth Management | BWM SE GCT CRV DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2021-10-01 | 2022-07-01 | Active | EP
BWM GCT DOCSIS Expansion 192 MHz | SE | GCT | CRV | Bandwidth Management | BWM SE GCT CRV DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2021-10-01 | 2022-07-01 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM GCT DOCSIS Expansion 96 MHz | SE | GCT | CRV | Bandwidth Management | BWM SE GCT CRV DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2021-10-01 | 2021-12-01 | Active | EP
BWM GCT DOCSIS Expansion 96 MHz | SE | GCT | CRV | Bandwidth Management | BWM SE GCT CRV DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2021-10-01 | 2021-12-01 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM LFY DOCSIS Expansion 192 MHz | SE | LFY | LFY | Bandwidth Management | BWM SE LFY LFY DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-11-13 | 2021-04-01 | Active | EP
BWM LFY DOCSIS Expansion 192 MHz | SE | LFY | LFY | Bandwidth Management | BWM SE LFY LFY DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-11-13 | 2021-04-01 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM LFY DOCSIS Expansion 96 MHz | SE | LFY | LFY | Bandwidth Management | BWM SE LFY LFY DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-11-13 | 2022-07-01 | Active | EP
BWM LFY DOCSIS Expansion 96 MHz | SE | LFY | LFY | Bandwidth Management | BWM SE LFY LFY DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-11-13 | 2022-07-01 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM NOR DOCSIS Expansion 192 MHz | SE | NOR | ALG | Bandwidth Management | BWM SE NOR ALG DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-09-16 | 2022-12-01 | Active | EP
BWM NOR DOCSIS Expansion 192 MHz | SE | NOR | ALG | Bandwidth Management | BWM SE NOR ALG DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-09-16 | 2022-12-01 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM NOR DOCSIS Expansion 96 MHz | SE | NOR | ALG | Bandwidth Management | BWM SE NOR ALG DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-09-16 | 2022-04-01 | Active | EP
BWM NOR DOCSIS Expansion 96 MHz | SE | NOR | ALG | Bandwidth Management | BWM SE NOR ALG DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-09-16 | 2022-04-01 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM HRD DOCSIS Expansion 192 MHz | VA | HRD | CHS | Bandwidth Management | BWM VA HRD CHS DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-05-21 | 2022-04-01 | Active | EP
BWM HRD DOCSIS Expansion 192 MHz | VA | HRD | CHS | Bandwidth Management | BWM VA HRD CHS DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-05-21 | 2022-04-01 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM HRD DOCSIS Expansion 96 MHz | VA | HRD | CHS | Bandwidth Management | BWM VA HRD CHS DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-05-21 | 2021-07-01 | Active | EP
BWM HRD DOCSIS Expansion 96 MHz | VA | HRD | CHS | Bandwidth Management | BWM VA HRD CHS DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-05-21 | 2021-07-01 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM NVA DOCSIS Expansion 192 MHz | VA | NVA | DRA | Bandwidth Management | BWM VA NVA DRA DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-10 | 2021-10-03 | Active | EP
BWM NVA DOCSIS Expansion 192 MHz | VA | NVA | DRA | Bandwidth Management | BWM VA NVA DRA DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-10 | 2021-10-03 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM NVA DOCSIS Expansion 96 MHz | VA | NVA | DRA | Bandwidth Management | BWM VA NVA DRA DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-10 | 2020-10-03 | Active | EP
BWM NVA DOCSIS Expansion 96 MHz | VA | NVA | DRA | Bandwidth Management | BWM VA NVA DRA DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-12-10 | 2020-10-03 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM ROA DOCSIS Expansion 192 MHz | VA | ROA | RON | Bandwidth Management | BWM VA ROA RON DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-14 | 2023-01-30 | Active | EP
BWM ROA DOCSIS Expansion 192 MHz | VA | ROA | RON | Bandwidth Management | BWM VA ROA RON DOCSIS Expansion 192 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-14 | 2023-01-30 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
BWM ROA DOCSIS Expansion 96 MHz | VA | ROA | RON | Bandwidth Management | BWM VA ROA RON DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-14 | 2022-10-03 | Active | EP
BWM ROA DOCSIS Expansion 96 MHz | VA | ROA | RON | Bandwidth Management | BWM VA ROA RON DOCSIS Expansion 96 MHz Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-14 | 2022-10-03 | Active | Log | New | SN-0558 | New | Approved | 2020-05-12 18:00 | Adding projects for the SE NE VA CA Markets for DOCSIS Expansion to acitivity plan No financial impact these projects were made inactive and now are being re added with a new name DOCSIS Expansion replacing DSG projects
Nokia 1830 Add 1 | COR | NAT | LA1 | C4 & C4B Transport Network | C4B CA NAT LA1 Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis | 5 | 2019-11-10 | 2020-01-15 |  | Active | EP
Nokia 1830 Add 3 | CA | ORG | RSM | C4 & C4B Transport Network | C4B CA ORG RSM Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis | 5 |  | 2020-04-07 |  | Active | EP
Nokia 1830 Add 3 | CA | ORG | RSM | C4 & C4B Transport Network | C4B CA ORG RSM Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis | 5 |  | 2020-06-30 |  | Active | Log | Upd | SN-0198 | Scope Change | Canceled | 2020-01-23 15:32 | CR includes POR and finacial updates to reflect descoping of Nokia chassis installs at few sites We don t see need for new Nokia chassis at few locations now as against initial plan, so updating the POR accordingly and giving back related funds
Nokia 1830 Add 3 | CA | ORG | RSM | C4 & C4B Transport Network | C4B CA ORG RSM Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis | 5 |  | 2020-06-30 |  | Active | Log | Upd | SN-0229 | Scope Change | Approved | 2020-02-03 16:48 | CR includes POR updates to reflect descoping of Nokia chassis installs at few sites We don t see need for new Nokia chassis at few locations now as against initial plan, so updating the POR accordingly
Nokia 1830 Add 3 | CA | ORG | RSM | C4 & C4B Transport Network | C4B CA ORG RSM Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis | 5 |  | 2020-04-07 |  | Active | Log | Upd | SN-0551 | True up | Approved | 2020-05-13 11:44 | April Capex variance of 12K due to some ancillary charges hitting the budget Also realigning material funds as per updated plan for rest of the year Giving back IHL 500K to risk as we have sufficient IHL funds for rest of the year
Nokia 1830 Add 4 | COR | COR | ATL | C4 & C4B Transport Network | C4B SE-NAT-AT1 Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis |  |  |  |  | Deleted | EP
Nokia 1830 Add 4 | COR | COR | ATL | C4 & C4B Transport Network | C4B SE-NAT-AT1 Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis |  |  |  |  | Deleted | Log | Del | SN-0165 | Schedule Change | Approved | 2020-02-06 11:20 | Funds ~ 292K will need to be pushed from Jan to Feb as the vendors (Nokia and Ciena) will not be able to deliver the material in Jan Also, updating POR to reflect correct facility code
Nokia 1830 Add 2 | COR | NAT | DC2 | C4 & C4B Transport Network | C4B VA NAT DC2 Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis | 5 |  | 2020-02-28 |  | Active | EP
Nokia 1830 Add 2 | COR | NAT | DC2 | C4 & C4B Transport Network | C4B VA NAT DC2 Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis | 5 |  | 2020-02-28 |  | Active | Log | Upd | SN-0229 | Scope Change | Approved | 2020-02-03 16:48 | CR includes POR updates to reflect descoping of Nokia chassis installs at few sites We don t see need for new Nokia chassis at few locations now as against initial plan, so updating the POR accordingly
Nokia 1830 Add 8 | CE | KAN | WIC | C4 & C4B Transport Network | C4B CE KAN WIC Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis |  |  |  |  | Deleted | EP
Nokia 1830 Add 8 | CE | KAN | WIC | C4 & C4B Transport Network | C4B CE KAN WIC Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis |  |  |  |  | Deleted | Log | Del | SN-0198 | Scope Change | Canceled | 2020-01-23 15:32 | CR includes POR and finacial updates to reflect descoping of Nokia chassis installs at few sites We don t see need for new Nokia chassis at few locations now as against initial plan, so updating the POR accordingly and giving back related funds
Nokia 1830 Add 8 | CE | KAN | WIC | C4 & C4B Transport Network | C4B CE KAN WIC Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis |  |  |  |  | Deleted | Log | Del | SN-0229 | Scope Change | Approved | 2020-02-03 16:48 | CR includes POR updates to reflect descoping of Nokia chassis installs at few sites We don t see need for new Nokia chassis at few locations now as against initial plan, so updating the POR accordingly
Nokia 1830 Add 7 | CE | OKC | OKC | C4 & C4B Transport Network | C4B CE OKC OKC Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis |  |  |  |  | Deleted | EP
Nokia 1830 Add 7 | CE | OKC | OKC | C4 & C4B Transport Network | C4B CE OKC OKC Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis |  |  |  |  | Deleted | Log | Del | SN-0165 | Schedule Change | Approved | 2020-02-06 11:20 | Funds ~ 292K will need to be pushed from Jan to Feb as the vendors (Nokia and Ciena) will not be able to deliver the material in Jan Also, updating POR to reflect correct facility code
Nokia 1830 Add 5 | SW | ARZ | CHD | C4 & C4B Transport Network | C4B SW ARZ CHD Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis | 5 | 2020-02-01 | 2020-04-15 |  | Active | EP
Nokia 1830 Add 6 | SW | LAS | TEN | C4 & C4B Transport Network | C4B SW LAS TEN Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis | 5 | 2020-03-01 | 2020-05-22 |  | Active | EP
Nokia 1830 Add 6 | SW | LAS | TEN | C4 & C4B Transport Network | C4B SW LAS TEN Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis | 5 | 2020-03-01 | 2020-05-22 |  | Active | Log | Upd | SN-0551 | True up | Approved | 2020-05-13 11:44 | April Capex variance of 12K due to some ancillary charges hitting the budget Also realigning material funds as per updated plan for rest of the year Giving back IHL 500K to risk as we have sufficient IHL funds for rest of the year
Nokia PSI-M Add 3 | CA | ORG | RSM | C4 & C4B Transport Network | C4B CA ORG RSM Nokia 1830 PSI-M Augment POR20 | Chassis | 1x Nokia 1830 PSI-M Chassis |  |  |  |  | Deleted | EP
Nokia PSI-M Add 3 | CA | ORG | RSM | C4 & C4B Transport Network | C4B CA ORG RSM Nokia 1830 PSI-M Augment POR20 | Chassis | 1x Nokia 1830 PSI-M Chassis |  |  |  |  | Deleted | Log | Del | SN-0198 | Scope Change | Canceled | 2020-01-23 15:32 | CR includes POR and finacial updates to reflect descoping of Nokia chassis installs at few sites We don t see need for new Nokia chassis at few locations now as against initial plan, so updating the POR accordingly and giving back related funds
Nokia PSI-M Add 3 | CA | ORG | RSM | C4 & C4B Transport Network | C4B CA ORG RSM Nokia 1830 PSI-M Augment POR20 | Chassis | 1x Nokia 1830 PSI-M Chassis |  |  |  |  | Deleted | Log | Del | SN-0229 | Scope Change | Approved | 2020-02-03 16:48 | CR includes POR updates to reflect descoping of Nokia chassis installs at few sites We don t see need for new Nokia chassis at few locations now as against initial plan, so updating the POR accordingly
Nokia PSI-M Add 8 | CE | KAN | WIC | C4 & C4B Transport Network | C4B CE KAN WIC Nokia 1830 PSI-M Augment POR20 | Chassis | 1x Nokia 1830 PSI-M Chassis |  |  |  |  | Deleted | EP
Nokia PSI-M Add 8 | CE | KAN | WIC | C4 & C4B Transport Network | C4B CE KAN WIC Nokia 1830 PSI-M Augment POR20 | Chassis | 1x Nokia 1830 PSI-M Chassis |  |  |  |  | Deleted | Log | Del | SN-0198 | Scope Change | Canceled | 2020-01-23 15:32 | CR includes POR and finacial updates to reflect descoping of Nokia chassis installs at few sites We don t see need for new Nokia chassis at few locations now as against initial plan, so updating the POR accordingly and giving back related funds
Nokia PSI-M Add 8 | CE | KAN | WIC | C4 & C4B Transport Network | C4B CE KAN WIC Nokia 1830 PSI-M Augment POR20 | Chassis | 1x Nokia 1830 PSI-M Chassis |  |  |  |  | Deleted | Log | Del | SN-0229 | Scope Change | Approved | 2020-02-03 16:48 | CR includes POR updates to reflect descoping of Nokia chassis installs at few sites We don t see need for new Nokia chassis at few locations now as against initial plan, so updating the POR accordingly
Nokia PSI-M Add 2 | COR | NAT | DC2 | C4 & C4B Transport Network | C4B VA NAT DC2 Nokia 1830 PSI-M Augment POR20 | Chassis | 1x Nokia 1830 PSI-M Chassis |  |  |  |  | Deleted | EP
Nokia PSI-M Add 2 | COR | NAT | DC2 | C4 & C4B Transport Network | C4B VA NAT DC2 Nokia 1830 PSI-M Augment POR20 | Chassis | 1x Nokia 1830 PSI-M Chassis |  |  |  |  | Deleted | Log | Del | SN-0198 | Scope Change | Canceled | 2020-01-23 15:32 | CR includes POR and finacial updates to reflect descoping of Nokia chassis installs at few sites We don t see need for new Nokia chassis at few locations now as against initial plan, so updating the POR accordingly and giving back related funds
Nokia PSI-M Add 2 | COR | NAT | DC2 | C4 & C4B Transport Network | C4B VA NAT DC2 Nokia 1830 PSI-M Augment POR20 | Chassis | 1x Nokia 1830 PSI-M Chassis |  |  |  |  | Deleted | Log | Del | SN-0229 | Scope Change | Approved | 2020-02-03 16:48 | CR includes POR updates to reflect descoping of Nokia chassis installs at few sites We don t see need for new Nokia chassis at few locations now as against initial plan, so updating the POR accordingly
Nokia PSI-M Add 4 | COR | COR | ATL | C4 & C4B Transport Network | C4B SE-NAT-AT1 Nokia 1830 PSI-M Augment POR20 | Chassis | 1x Nokia 1830 PSI-M Chassis |  |  |  |  | Deleted | EP
Nokia PSI-M Add 4 | COR | COR | ATL | C4 & C4B Transport Network | C4B SE-NAT-AT1 Nokia 1830 PSI-M Augment POR20 | Chassis | 1x Nokia 1830 PSI-M Chassis |  |  |  |  | Deleted | Log | Del | SN-0165 | Schedule Change | Approved | 2020-02-06 11:20 | Funds ~ 292K will need to be pushed from Jan to Feb as the vendors (Nokia and Ciena) will not be able to deliver the material in Jan Also, updating POR to reflect correct facility code
Nokia PSI-M Add 7 | CE | OKC | OKC | C4 & C4B Transport Network | C4B SW-NAT-DA1 Nokia 1830 PSI-M Augment POR20 | Chassis | 1x Nokia 1830 PSI-M Chassis |  |  |  |  | Deleted | EP
Nokia PSI-M Add 7 | CE | OKC | OKC | C4 & C4B Transport Network | C4B SW-NAT-DA1 Nokia 1830 PSI-M Augment POR20 | Chassis | 1x Nokia 1830 PSI-M Chassis |  |  |  |  | Deleted | Log | Del | SN-0165 | Schedule Change | Approved | 2020-02-06 11:20 | Funds ~ 292K will need to be pushed from Jan to Feb as the vendors (Nokia and Ciena) will not be able to deliver the material in Jan Also, updating POR to reflect correct facility code
Nokia PSI-M FOA | COR | NAT | LA1 | C4 & C4B Transport Network | C4B CA NAT LA1 Nokia 1830 PSI-M Augment POR20 | Chassis | 1x Nokia 1830 PSI-M Chassis |  |  |  |  | Deleted | EP
Nokia PSI-M FOA | COR | NAT | LA1 | C4 & C4B Transport Network | C4B CA NAT LA1 Nokia 1830 PSI-M Augment POR20 | Chassis | 1x Nokia 1830 PSI-M Chassis |  |  |  |  | Deleted | Log | Del | SN-0198 | Scope Change | Canceled | 2020-01-23 15:32 | CR includes POR and finacial updates to reflect descoping of Nokia chassis installs at few sites We don t see need for new Nokia chassis at few locations now as against initial plan, so updating the POR accordingly and giving back related funds
Nokia PSI-M FOA | COR | NAT | LA1 | C4 & C4B Transport Network | C4B CA NAT LA1 Nokia 1830 PSI-M Augment POR20 | Chassis | 1x Nokia 1830 PSI-M Chassis |  |  |  |  | Deleted | Log | Del | SN-0229 | Scope Change | Approved | 2020-02-03 16:48 | CR includes POR updates to reflect descoping of Nokia chassis installs at few sites We don t see need for new Nokia chassis at few locations now as against initial plan, so updating the POR accordingly
Nokia PSI-M Add 5 | SW | ARZ | CHD | C4 & C4B Transport Network | C4B SW ARZ CHD Nokia 1830 PSI-M Augment POR20 | Chassis | 1x Nokia 1830 PSI-M Chassis |  |  |  |  | Deleted | EP
Nokia PSI-M Add 5 | SW | ARZ | CHD | C4 & C4B Transport Network | C4B SW ARZ CHD Nokia 1830 PSI-M Augment POR20 | Chassis | 1x Nokia 1830 PSI-M Chassis |  |  |  |  | Deleted | Log | Del | SN-0198 | Scope Change | Canceled | 2020-01-23 15:32 | CR includes POR and finacial updates to reflect descoping of Nokia chassis installs at few sites We don t see need for new Nokia chassis at few locations now as against initial plan, so updating the POR accordingly and giving back related funds
Nokia PSI-M Add 5 | SW | ARZ | CHD | C4 & C4B Transport Network | C4B SW ARZ CHD Nokia 1830 PSI-M Augment POR20 | Chassis | 1x Nokia 1830 PSI-M Chassis |  |  |  |  | Deleted | Log | Del | SN-0229 | Scope Change | Approved | 2020-02-03 16:48 | CR includes POR updates to reflect descoping of Nokia chassis installs at few sites We don t see need for new Nokia chassis at few locations now as against initial plan, so updating the POR accordingly
Nokia PSI-M Add 6 | SW | LAS | TEN | C4 & C4B Transport Network | C4B SW LAS TEN Nokia 1830 PSI-M Augment POR20 | Chassis | 1x Nokia 1830 PSI-M Chassis |  |  |  |  | Deleted | EP
Nokia PSI-M Add 6 | SW | LAS | TEN | C4 & C4B Transport Network | C4B SW LAS TEN Nokia 1830 PSI-M Augment POR20 | Chassis | 1x Nokia 1830 PSI-M Chassis |  |  |  |  | Deleted | Log | Del | SN-0198 | Scope Change | Canceled | 2020-01-23 15:32 | CR includes POR and finacial updates to reflect descoping of Nokia chassis installs at few sites We don t see need for new Nokia chassis at few locations now as against initial plan, so updating the POR accordingly and giving back related funds
Nokia PSI-M Add 6 | SW | LAS | TEN | C4 & C4B Transport Network | C4B SW LAS TEN Nokia 1830 PSI-M Augment POR20 | Chassis | 1x Nokia 1830 PSI-M Chassis |  |  |  |  | Deleted | Log | Del | SN-0229 | Scope Change | Approved | 2020-02-03 16:48 | CR includes POR updates to reflect descoping of Nokia chassis installs at few sites We don t see need for new Nokia chassis at few locations now as against initial plan, so updating the POR accordingly
Nokia PSI-M Add 9 | COR | NAT | DA1 | C4 & C4B Transport Network | C4B SW-NAT-DA1 Nokia 1830 PSI-M Augment POR20 | Chassis | 1x Nokia 1830 PSI-M Chassis | 2 | 2020-06-01 | 2020-08-15 |  | Deleted | EP
Nokia PSI-M Add 9 | COR | NAT | DA1 | C4 & C4B Transport Network | C4B SW-NAT-DA1 Nokia 1830 PSI-M Augment POR20 | Chassis | 1x Nokia 1830 PSI-M Chassis | 2 | 2020-06-01 | 2020-08-15 |  | Deleted | Log | New | SN-0165 | Schedule Change | Approved | 2020-02-06 11:20 | Funds ~ 292K will need to be pushed from Jan to Feb as the vendors (Nokia and Ciena) will not be able to deliver the material in Jan Also, updating POR to reflect correct facility code
Nokia PSI-M Add 9 | COR | NAT | DA1 | C4 & C4B Transport Network | C4B SW-NAT-DA1 Nokia 1830 PSI-M Augment POR20 | Chassis | 1x Nokia 1830 PSI-M Chassis |  |  |  |  | Deleted | Log | Del | SN-0198 | Scope Change | Canceled | 2020-01-23 15:32 | CR includes POR and finacial updates to reflect descoping of Nokia chassis installs at few sites We don t see need for new Nokia chassis at few locations now as against initial plan, so updating the POR accordingly and giving back related funds
Nokia PSI-M Add 9 | COR | NAT | DA1 | C4 & C4B Transport Network | C4B SW-NAT-DA1 Nokia 1830 PSI-M Augment POR20 | Chassis | 1x Nokia 1830 PSI-M Chassis |  |  |  |  | Deleted | Log | Del | SN-0229 | Scope Change | Approved | 2020-02-03 16:48 | CR includes POR updates to reflect descoping of Nokia chassis installs at few sites We don t see need for new Nokia chassis at few locations now as against initial plan, so updating the POR accordingly
Nokia 1830 Add 9 | COR | NAT | DA1 | C4 & C4B Transport Network | C4B CE OKC OKC Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis | 5 | 2020-03-01 | 2020-04-15 |  | Deleted | EP
Nokia 1830 Add 9 | COR | NAT | DA1 | C4 & C4B Transport Network | C4B CE OKC OKC Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis | 5 | 2020-03-01 | 2020-04-15 |  | Deleted | Log | New | SN-0165 | Schedule Change | Approved | 2020-02-06 11:20 | Funds ~ 292K will need to be pushed from Jan to Feb as the vendors (Nokia and Ciena) will not be able to deliver the material in Jan Also, updating POR to reflect correct facility code
Nokia 1830 Add 9 | COR | NAT | DA1 | C4 & C4B Transport Network | C4B CE OKC OKC Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis |  |  |  |  | Deleted | Log | Del | SN-0198 | Scope Change | Canceled | 2020-01-23 15:32 | CR includes POR and finacial updates to reflect descoping of Nokia chassis installs at few sites We don t see need for new Nokia chassis at few locations now as against initial plan, so updating the POR accordingly and giving back related funds
Nokia 1830 Add 9 | COR | NAT | DA1 | C4 & C4B Transport Network | C4B CE OKC OKC Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis |  |  |  |  | Deleted | Log | Del | SN-0229 | Scope Change | Approved | 2020-02-03 16:48 | CR includes POR updates to reflect descoping of Nokia chassis installs at few sites We don t see need for new Nokia chassis at few locations now as against initial plan, so updating the POR accordingly
Nokia PSI-M Add 10 | COR | NAT | AT1 | C4 & C4B Transport Network | C4B SE-NAT-AT1 Nokia 1830 PSI-M Augment POR20 | Chassis | 1x Nokia 1830 PSI-M Chassis | 2 | 2020-06-01 | 2020-07-15 |  | Deleted | EP
Nokia PSI-M Add 10 | COR | NAT | AT1 | C4 & C4B Transport Network | C4B SE-NAT-AT1 Nokia 1830 PSI-M Augment POR20 | Chassis | 1x Nokia 1830 PSI-M Chassis | 2 | 2020-06-01 | 2020-07-15 |  | Deleted | Log | New | SN-0165 | Schedule Change | Approved | 2020-02-06 11:20 | Funds ~ 292K will need to be pushed from Jan to Feb as the vendors (Nokia and Ciena) will not be able to deliver the material in Jan Also, updating POR to reflect correct facility code
Nokia PSI-M Add 10 | COR | NAT | AT1 | C4 & C4B Transport Network | C4B SE-NAT-AT1 Nokia 1830 PSI-M Augment POR20 | Chassis | 1x Nokia 1830 PSI-M Chassis |  |  |  |  | Deleted | Log | Del | SN-0198 | Scope Change | Canceled | 2020-01-23 15:32 | CR includes POR and finacial updates to reflect descoping of Nokia chassis installs at few sites We don t see need for new Nokia chassis at few locations now as against initial plan, so updating the POR accordingly and giving back related funds
Nokia PSI-M Add 10 | COR | NAT | AT1 | C4 & C4B Transport Network | C4B SE-NAT-AT1 Nokia 1830 PSI-M Augment POR20 | Chassis | 1x Nokia 1830 PSI-M Chassis |  |  |  |  | Deleted | Log | Del | SN-0229 | Scope Change | Approved | 2020-02-03 16:48 | CR includes POR updates to reflect descoping of Nokia chassis installs at few sites We don t see need for new Nokia chassis at few locations now as against initial plan, so updating the POR accordingly
Nokia 1830 Add 10 | COR | NAT | AT1 | C4 & C4B Transport Network | C4B SE-NAT-AT1 Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis | 5 | 2019-11-10 | 2020-01-15 |  | Active | EP
Nokia 1830 Add 10 | COR | NAT | AT1 | C4 & C4B Transport Network | C4B SE-NAT-AT1 Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis | 5 | 2019-11-10 | 2020-01-15 |  | Active | Log | New | SN-0165 | Schedule Change | Approved | 2020-02-06 11:20 | Funds ~ 292K will need to be pushed from Jan to Feb as the vendors (Nokia and Ciena) will not be able to deliver the material in Jan Also, updating POR to reflect correct facility code
Nokia 1830 Add 11 | CE | OKC | OKC | C4 & C4B Transport Network | C4B CE OKC OKC Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis | 5 |  | 2020-06-30 |  | Active | EP
Nokia 1830 Add 11 | CE | OKC | OKC | C4 & C4B Transport Network | C4B CE OKC OKC Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis | 5 | 2020-03-01 | 2020-06-30 |  | Active | Log | New | SN-0198 | Scope Change | Canceled | 2020-01-23 15:32 | CR includes POR and finacial updates to reflect descoping of Nokia chassis installs at few sites We don t see need for new Nokia chassis at few locations now as against initial plan, so updating the POR accordingly and giving back related funds
Nokia 1830 Add 11 | CE | OKC | OKC | C4 & C4B Transport Network | C4B CE OKC OKC Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis | 5 |  | 2020-06-30 |  | Active | Log | New | SN-0229 | Scope Change | Approved | 2020-02-03 16:48 | CR includes POR updates to reflect descoping of Nokia chassis installs at few sites We don t see need for new Nokia chassis at few locations now as against initial plan, so updating the POR accordingly
Nokia 1830 Add 12 | NE | CLE | CLV | C4 & C4B Transport Network | C4B NE CLE CLV Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis | 8 | 2020-07-01 | 2020-12-15 |  | Active | EP
Nokia 1830 Add 12 | NE | CLE | CLV | C4 & C4B Transport Network | C4B NE CLE CLV Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis | 8 | 2020-07-01 | 2020-08-31 |  | Active | Log | New | SN-0625 | Schedule Change | Approved | 2020-06-05 14:51 | CR to update POR with addition of Cleveland Parma C4 Transport equipment install project CR to manage financials was already submitted and approved so no impact to financials
Nokia 1830 Add 12 | NE | CLE | CLV | C4 & C4B Transport Network | C4B NE CLE CLV Nokia 1830-PSS Augment POR20 | Chassis | 1x Nokia 1830 PSS-16II Chassis | 8 | 2020-07-01 | 2020-12-15 |  | Active | Log | Upd | SN-0965 | Schedule Change | Approved | 2020-10-02 09:34 | C4 Nokia 1830 migration date updates for Cleveland
Aliso Viejo (AV)-OCML-IXR | CA | ORG | AVJ | CB - Metro Core | CBMC CA ORG AVJ OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | EP
Aliso Viejo (AV)-OCML-IXR | CA | ORG | AVJ | CB - Metro Core | CBMC CA ORG AVJ OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0132 | Schedule Change | Approved | 2020-02-06 11:03 | All IXR projects for CBMC In January were moved to March in order lighten January budget Financials have already been updated to reflect the change This is an adminstrative CR
Aliso Viejo (AV)-OCML-IXR | CA | ORG | AVJ | CB - Metro Core | CBMC CA ORG AVJ OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
Dana Point (DP)-OCML-IXR | CA | ORG | DNP | CB - Metro Core | CBMC CA ORG DNP OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | EP
Dana Point (DP)-OCML-IXR | CA | ORG | DNP | CB - Metro Core | CBMC CA ORG DNP OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0132 | Schedule Change | Approved | 2020-02-06 11:03 | All IXR projects for CBMC In January were moved to March in order lighten January budget Financials have already been updated to reflect the change This is an adminstrative CR
Dana Point (DP)-OCML-IXR | CA | ORG | DNP | CB - Metro Core | CBMC CA ORG DNP OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
Irvine (IR)-OCML-IXR | CA | ORG | IRV | CB - Metro Core | CBMC CA ORG IRV OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | EP
Irvine (IR)-OCML-IXR | CA | ORG | IRV | CB - Metro Core | CBMC CA ORG IRV OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0132 | Schedule Change | Approved | 2020-02-06 11:03 | All IXR projects for CBMC In January were moved to March in order lighten January budget Financials have already been updated to reflect the change This is an adminstrative CR
Irvine (IR)-OCML-IXR | CA | ORG | IRV | CB - Metro Core | CBMC CA ORG IRV OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
Orange (OR)-OCML-IXR | CA | ORG | ORG | CB - Metro Core | CBMC CA ORG ORG OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
Orange (OR)-OCML-IXR | CA | ORG | ORG | CB - Metro Core | CBMC CA ORG ORG OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Deleted | Log | Upd | SN-0132 | Schedule Change | Approved | 2020-02-06 11:03 | All IXR projects for CBMC In January were moved to March in order lighten January budget Financials have already been updated to reflect the change This is an adminstrative CR
Orange (OR)-OCML-IXR | CA | ORG | ORG | CB - Metro Core | CBMC CA ORG ORG OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Deleted | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
Orange (OR)-OCML-IXR | CA | ORG | ORG | CB - Metro Core | CBMC CA ORG ORG OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
Palos Verdes (PV)-OCML-IXR | CA | ORG | PAV | CB - Metro Core | CBMC CA ORG PAV OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | EP
Palos Verdes (PV)-OCML-IXR | CA | ORG | PAV | CB - Metro Core | CBMC CA ORG PAV OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0132 | Schedule Change | Approved | 2020-02-06 11:03 | All IXR projects for CBMC In January were moved to March in order lighten January budget Financials have already been updated to reflect the change This is an adminstrative CR
Palos Verdes (PV)-OCML-IXR | CA | ORG | PAV | CB - Metro Core | CBMC CA ORG PAV OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
CB Transport - New Router El Cajon - ELC - Optics | CA | SAN | ELC | CB - Metro Core | CBMC CA SAN ELC Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-01-15 | 2020-02-15 |  | Active | EP
CB Transport - New Router El Cajon - FED - Optics | CA | SAN | FED | CB - Metro Core | CBMC CA SAN FED Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-01-15 | 2020-02-15 |  | Active | EP
FED1EWAA03-100G CARD | CA | SAN | FED | CB - Metro Core | CBMC CA SAN FED 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 2 | 2020-02-15 | 2020-05-20 |  | Active | EP
FED1EWAA03-100G CARD | CA | SAN | FED | CB - Metro Core | CBMC CA SAN FED 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 2 | 2020-02-15 | 2020-03-15 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
FED1EWAA03-100G CARD | CA | SAN | FED | CB - Metro Core | CBMC CA SAN FED 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 2 | 2020-02-15 | 2020-04-15 |  | Active | Log | Upd | SN-0419 | Schedule Change | Approved | 2020-04-02 09:36 | Updates driven by field audit and material delays
FED1EWAA03-100G CARD | CA | SAN | FED | CB - Metro Core | CBMC CA SAN FED 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 2 | 2020-02-15 | 2020-05-20 |  | Active | Log | Upd | SN-0478 | Schedule Change | Approved | 2020-04-24 14:37 | Adjusting schedule dates across multpile PPMs
Bentonville-OCML-IXR | CE | NWA | BVL | CB - Metro Core | CBMC CE NWA BVL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
Bentonville-OCML-IXR | CE | NWA | BVL | CB - Metro Core | CBMC CE NWA BVL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Deleted | Log | Upd | SN-0132 | Schedule Change | Approved | 2020-02-06 11:03 | All IXR projects for CBMC In January were moved to March in order lighten January budget Financials have already been updated to reflect the change This is an adminstrative CR
Bentonville-OCML-IXR | CE | NWA | BVL | CB - Metro Core | CBMC CE NWA BVL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Deleted | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
Bentonville-OCML-IXR | CE | NWA | BVL | CB - Metro Core | CBMC CE NWA BVL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
Fayetteville-OCML-IXR | CE | NWA | FAY | CB - Metro Core | CBMC CE NWA FAY OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-09-30 |  | Active | EP
Fayetteville-OCML-IXR | CE | NWA | FAY | CB - Metro Core | CBMC CE ARK FAY Optics Only for Cisco T5 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0132 | Schedule Change | Approved | 2020-02-06 11:03 | All IXR projects for CBMC In January were moved to March in order lighten January budget Financials have already been updated to reflect the change This is an adminstrative CR
Fayetteville-OCML-IXR | CE | NWA | FAY | CB - Metro Core | CBMC CE NWA FAY OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
Fayetteville-OCML-IXR | CE | NWA | FAY | CB - Metro Core | CBMC CE NWA FAY OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
Fayetteville-OCML-IXR | CE | NWA | FAY | CB - Metro Core | CBMC CE NWA FAY OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-07-30 |  | Active | Log | Upd | SN-0701 | Schedule Change | Approved | 2020-07-02 11:45 | Pushing out activation dates in CE CA VA and SW due to equipment delays
Fayetteville-OCML-IXR | CE | NWA | FAY | CB - Metro Core | CBMC CE NWA FAY OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-08-30 |  | Active | Log | Upd | SN-0796 | Schedule Change | Approved | 2020-07-31 10:03 | Moving activation dates out for projects in the CA and SW regions due to various delays
Fayetteville-OCML-IXR | CE | NWA | FAY | CB - Metro Core | CBMC CE NWA FAY OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-09-30 |  | Active | Log | Upd | SN-0934 | Schedule Change | Approved | 2020-09-18 09:35 | Moving out activation dates due to delays
CB Transport - New Router Braden - BAR - Chassis Add | CE | TUL | BAR | CB - Metro Core | CBMC CE TUL BAR Cisco M6_M15 Chassis Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 1 | 2020-02-15 | 2020-05-20 |  | Active | EP
CB Transport - New Router Braden - BAR - Chassis Add | CE | TUL | BAR | CB - Metro Core | CBMC CE TUL BAR Cisco M6_M15 Chassis Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 1 | 2020-02-15 | 2020-03-30 |  | Active | Log | Upd | SN-0329 | Schedule Change | Approved | 2020-03-03 16:39 | Several pieces of material in Central Region were received in Feb vs the original Jan date Pushing the acitivation dates out to March to accodomate
CB Transport - New Router Braden - BAR - Chassis Add | CE | TUL | BAR | CB - Metro Core | CBMC CE TUL BAR Cisco M6_M15 Chassis Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 1 | 2020-02-15 | 2020-04-30 |  | Active | Log | Upd | SN-0386 | New | Approved | 2020-03-27 15:11 | Changes to activation dates in the CE region due to late equipment arrivals and installations
CB Transport - New Router Braden - BAR - Chassis Add | CE | TUL | BAR | CB - Metro Core | CBMC CE TUL BAR Cisco M6_M15 Chassis Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 1 | 2020-02-15 | 2020-05-20 |  | Active | Log | Upd | SN-0586 | Schedule Change | Approved | 2020-05-14 14:37 | Adjusting dates for CBMC POR Most of the changes are pushing activation dates out due to equipment delays
CB Transport - New Router Braden, Downtown (TUL) - BAR - Card Add | CE | TUL | BAR | CB - Metro Core | CBMC CE TUL BAR Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-02-15 | 2020-04-30 |  | Active | EP
CB Transport - New Router Braden, Downtown (TUL) - BAR - Card Add | CE | TUL | BAR | CB - Metro Core | CBMC CE TUL BAR Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-02-15 | 2020-03-30 |  | Active | Log | Upd | SN-0329 | Schedule Change | Approved | 2020-03-03 16:39 | Several pieces of material in Central Region were received in Feb vs the original Jan date Pushing the acitivation dates out to March to accodomate
CB Transport - New Router Braden, Downtown (TUL) - BAR - Card Add | CE | TUL | BAR | CB - Metro Core | CBMC CE TUL BAR Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-02-15 | 2020-04-30 |  | Active | Log | Upd | SN-0386 | New | Approved | 2020-03-27 15:11 | Changes to activation dates in the CE region due to late equipment arrivals and installations
BRAROKKA9CW-XR03.BA.TUL.OK-100G CARD | CE | TUL | BAR | CB - Metro Core | CBMC CE TUL BAR 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-02-15 | 2020-04-30 |  | Active | EP
BRAROKKA9CW-XR03.BA.TUL.OK-100G CARD | CE | TUL | BAR | CB - Metro Core | CBMC CE TUL BAR 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-02-15 | 2020-03-15 |  | Active | Log | Upd | SN-0064 | True up | Approved | 2020-02-06 10:27 | CBMC POR Updates for Central and Southwest
BRAROKKA9CW-XR03.BA.TUL.OK-100G CARD | CE | TUL | BAR | CB - Metro Core | CBMC CE TUL BAR 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-02-15 | 2020-04-30 |  | Active | Log | Upd | SN-0386 | New | Approved | 2020-03-27 15:11 | Changes to activation dates in the CE region due to late equipment arrivals and installations
BRAROKKA9DW-XR04.BA.TUL.OK-100G CARD | CE | TUL | BAR | CB - Metro Core | CBMC CE TUL BAR 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-02-15 | 2020-04-30 |  | Active | EP
BRAROKKA9DW-XR04.BA.TUL.OK-100G CARD | CE | TUL | BAR | CB - Metro Core | CBMC CE TUL BAR 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-02-15 | 2020-03-15 |  | Active | Log | Upd | SN-0064 | True up | Approved | 2020-02-06 10:27 | CBMC POR Updates for Central and Southwest
BRAROKKA9DW-XR04.BA.TUL.OK-100G CARD | CE | TUL | BAR | CB - Metro Core | CBMC CE TUL BAR 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-02-15 | 2020-04-30 |  | Active | Log | Upd | SN-0386 | New | Approved | 2020-03-27 15:11 | Changes to activation dates in the CE region due to late equipment arrivals and installations
xr01.ba.tul.ok-100G CARD | CE | TUL | BAR | CB - Metro Core | CBMC CE TUL BAR 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-02-15 | 2020-04-30 |  | Active | EP
xr01.ba.tul.ok-100G CARD | CE | TUL | BAR | CB - Metro Core | CBMC CE TUL BAR 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-01-15 | 2020-02-15 |  | Active | Log | Upd | SN-0064 | True up | Approved | 2020-02-06 10:27 | CBMC POR Updates for Central and Southwest
xr01.ba.tul.ok-100G CARD | CE | TUL | BAR | CB - Metro Core | CBMC CE TUL BAR 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-02-15 | 2020-03-30 |  | Active | Log | Upd | SN-0329 | Schedule Change | Approved | 2020-03-03 16:39 | Several pieces of material in Central Region were received in Feb vs the original Jan date Pushing the acitivation dates out to March to accodomate
xr01.ba.tul.ok-100G CARD | CE | TUL | BAR | CB - Metro Core | CBMC CE TUL BAR 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-02-15 | 2020-04-30 |  | Active | Log | Upd | SN-0386 | New | Approved | 2020-03-27 15:11 | Changes to activation dates in the CE region due to late equipment arrivals and installations
BRAROKKA9CW-XR03.BA.TUL.OK-SFM | CE | TUL | BAR | CB - Metro Core | CBMC CE TUL BAR SFM-7950 XRS-20 Augment POR20 | Card & Optics | Nokia SFM-7950 XRS-20/20e SFM2-SA | 8 | 2020-02-15 | 2020-04-30 |  | Active | EP
BRAROKKA9CW-XR03.BA.TUL.OK-SFM | CE | TUL | BAR | CB - Metro Core | CBMC CE TUL BAR SFM-7950 XRS-20 Augment POR20 | Card & Optics | Nokia SFM-7950 XRS-20/20e SFM2-SA | 8 | 2020-02-15 | 2020-03-30 |  | Active | Log | Upd | SN-0329 | Schedule Change | Approved | 2020-03-03 16:39 | Several pieces of material in Central Region were received in Feb vs the original Jan date Pushing the acitivation dates out to March to accodomate
BRAROKKA9CW-XR03.BA.TUL.OK-SFM | CE | TUL | BAR | CB - Metro Core | CBMC CE TUL BAR SFM-7950 XRS-20 Augment POR20 | Card & Optics | Nokia SFM-7950 XRS-20/20e SFM2-SA | 8 | 2020-02-15 | 2020-04-30 |  | Active | Log | Upd | SN-0386 | New | Approved | 2020-03-27 15:11 | Changes to activation dates in the CE region due to late equipment arrivals and installations
BRAROKKA9DW-XR04.BA.TUL.OK-SFM | CE | TUL | BAR | CB - Metro Core | CBMC CE TUL BAR SFM-7950 XRS-20 Augment POR20 | Card & Optics | Nokia SFM-7950 XRS-20/20e SFM2-SA | 8 | 2020-02-15 | 2020-04-30 |  | Active | EP
BRAROKKA9DW-XR04.BA.TUL.OK-SFM | CE | TUL | BAR | CB - Metro Core | CBMC CE TUL BAR SFM-7950 XRS-20 Augment POR20 | Card & Optics | Nokia SFM-7950 XRS-20/20e SFM2-SA | 8 | 2020-02-15 | 2020-03-30 |  | Active | Log | Upd | SN-0329 | Schedule Change | Approved | 2020-03-03 16:39 | Several pieces of material in Central Region were received in Feb vs the original Jan date Pushing the acitivation dates out to March to accodomate
BRAROKKA9DW-XR04.BA.TUL.OK-SFM | CE | TUL | BAR | CB - Metro Core | CBMC CE TUL BAR SFM-7950 XRS-20 Augment POR20 | Card & Optics | Nokia SFM-7950 XRS-20/20e SFM2-SA | 8 | 2020-02-15 | 2020-04-30 |  | Active | Log | Upd | SN-0386 | New | Approved | 2020-03-27 15:11 | Changes to activation dates in the CE region due to late equipment arrivals and installations
CB Transport - New Router Braden - BRD - Optics | CE | TUL | BRD | CB - Metro Core | CBMC CE TUL BRD Optics Only for Cisco T5 POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-01-15 | 2020-04-30 |  | Active | EP
CB Transport - New Router Braden - BRD - Optics | CE | TUL | BRD | CB - Metro Core | CBMC CE TUL BRD Optics Only for Cisco T5 POR20 | Card & Optics | Optics Only for Cisco T5 |  |  |  |  | Active | Log | Del | SN-0020 | New | Approved | 2020-02-06 09:59 | Cleaning up POR Deleting duplicate records from the POR No financials are attached to this CR
CB Transport - New Router Braden - BRD - Optics | CE | TUL | BRD | CB - Metro Core | CBMC CE TUL BRD Optics Only for Cisco T5 POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-01-15 | 2020-04-30 |  | Active | Log | Undel | SN-0386 | New | Approved | 2020-03-27 15:11 | Changes to activation dates in the CE region due to late equipment arrivals and installations
County Line STC-OCML-IXR | CE | OKC | CLH | CB - Metro Core | CBMC CE OKC CLH OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | EP
County Line STC-OCML-IXR | CE | OKC | CLH | CB - Metro Core | CBMC CE OKC CLH OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-01-01 | 2020-02-15 |  | Active | Log | Upd | SN-0064 | True up | Approved | 2020-02-06 10:27 | CBMC POR Updates for Central and Southwest
County Line STC-OCML-IXR | CE | OKC | CLH | CB - Metro Core | CBMC CE OKC CLH OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0132 | Schedule Change | Approved | 2020-02-06 11:03 | All IXR projects for CBMC In January were moved to March in order lighten January budget Financials have already been updated to reflect the change This is an adminstrative CR
County Line STC-OCML-IXR | CE | OKC | CLH | CB - Metro Core | CBMC CE OKC CLH OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
INDIANAPOLIS-OCML-IXR | CE | TUL | IND | CB - Metro Core | CBMC CE TUL IND OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
INDIANAPOLIS-OCML-IXR | CE | TUL | IND | CB - Metro Core | CBMC CE TUL IND OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Deleted | Log | Upd | SN-0132 | Schedule Change | Approved | 2020-02-06 11:03 | All IXR projects for CBMC In January were moved to March in order lighten January budget Financials have already been updated to reflect the change This is an adminstrative CR
INDIANAPOLIS-OCML-IXR | CE | TUL | IND | CB - Metro Core | CBMC CE TUL IND OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Deleted | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
INDIANAPOLIS-OCML-IXR | CE | TUL | IND | CB - Metro Core | CBMC CE TUL IND OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0782 | Schedule Change | Approved | 2020-07-27 09:31 | Adjusting activation dates due to equipment delays and removing POR records for deferred projects for CBMC
xr01.nor.okc.ok-100G CARD | CE | OKC | NOR | CB - Metro Core | CBMC CE OKC NOR 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-02-15 | 2020-03-30 |  | Active | EP
xr01.nor.okc.ok-100G CARD | CE | OKC | NOR | CB - Metro Core | CBMC CE OKC NOR 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-01-15 | 2020-02-15 |  | Active | Log | Upd | SN-0064 | True up | Approved | 2020-02-06 10:27 | CBMC POR Updates for Central and Southwest
xr01.nor.okc.ok-100G CARD | CE | OKC | NOR | CB - Metro Core | CBMC CE OKC NOR 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-02-15 | 2020-03-30 |  | Active | Log | Upd | SN-0329 | Schedule Change | Approved | 2020-03-03 16:39 | Several pieces of material in Central Region were received in Feb vs the original Jan date Pushing the acitivation dates out to March to accodomate
CB Transport - New Router Waterloo - NOR - Chassis Add | CE | OKC | NOR | CB - Metro Core | CBMC CE OKC NOR Cisco M6_M15 Chassis Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 1 | 2020-02-15 | 2020-03-30 |  | Active | EP
CB Transport - New Router Waterloo - NOR - Chassis Add | CE | OKC | NOR | CB - Metro Core | CBMC CE OKC NOR Cisco M6_M15 Chassis Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 1 | 2020-01-15 | 2020-02-15 |  | Active | Log | Upd | SN-0064 | True up | Approved | 2020-02-06 10:27 | CBMC POR Updates for Central and Southwest
CB Transport - New Router Waterloo - NOR - Chassis Add | CE | OKC | NOR | CB - Metro Core | CBMC CE OKC NOR Cisco M6_M15 Chassis Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 1 | 2020-02-15 | 2020-03-30 |  | Active | Log | Upd | SN-0329 | Schedule Change | Approved | 2020-03-03 16:39 | Several pieces of material in Central Region were received in Feb vs the original Jan date Pushing the acitivation dates out to March to accodomate
CB Transport - New Router Waterloo, Irish Lane - NOR - Card Add | CE | OKC | NOR | CB - Metro Core | CBMC CE OKC NOR Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-02-15 | 2020-03-30 |  | Active | EP
CB Transport - New Router Waterloo, Irish Lane - NOR - Card Add | CE | OKC | NOR | CB - Metro Core | CBMC CE OKC NOR Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-02-15 | 2020-03-30 |  | Active | Log | Upd | SN-0329 | Schedule Change | Approved | 2020-03-03 16:39 | Several pieces of material in Central Region were received in Feb vs the original Jan date Pushing the acitivation dates out to March to accodomate
CB Transport - New Router Waterloo - OKC - Card Add | CE | OKC | OKC | CB - Metro Core | CBMC CE OKC OKC Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-02-15 | 2020-03-30 |  | Active | EP
CB Transport - New Router Waterloo - OKC - Card Add | CE | OKC | OKC | CB - Metro Core | CBMC CE OKC OKC Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-02-15 | 2020-03-30 |  | Active | Log | Upd | SN-0329 | Schedule Change | Approved | 2020-03-03 16:39 | Several pieces of material in Central Region were received in Feb vs the original Jan date Pushing the acitivation dates out to March to accodomate
MTC-OCML-IXR | CE | OKC | OKC | CB - Metro Core | CBMC CE OKC OKC OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-07-30 |  | Active | EP
MTC-OCML-IXR | CE | OKC | OKC | CB - Metro Core | CBMC CE OKC OKC OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-01-01 | 2020-01-15 |  | Active | Log | Upd | SN-0064 | True up | Approved | 2020-02-06 10:27 | CBMC POR Updates for Central and Southwest
MTC-OCML-IXR | CE | OKC | OKC | CB - Metro Core | CBMC CE OKC OKC OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0132 | Schedule Change | Approved | 2020-02-06 11:03 | All IXR projects for CBMC In January were moved to March in order lighten January budget Financials have already been updated to reflect the change This is an adminstrative CR
MTC-OCML-IXR | CE | OKC | OKC | CB - Metro Core | CBMC CE OKC OKC OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
MTC-OCML-IXR | CE | OKC | OKC | CB - Metro Core | CBMC CE OKC OKC OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-07-30 |  | Active | Log | Upd | SN-0701 | Schedule Change | Approved | 2020-07-02 11:45 | Pushing out activation dates in CE CA VA and SW due to equipment delays
xr01.mtc.okc.ok-100G CARD | CE | OKC | OKC | CB - Metro Core | CBMC CE OKC OKC 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 3 | 2020-02-15 | 2020-03-30 |  | Active | EP
xr01.mtc.okc.ok-100G CARD | CE | OKC | OKC | CB - Metro Core | CBMC CE OKC OKC 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 3 | 2020-01-15 | 2020-02-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
xr01.mtc.okc.ok-100G CARD | CE | OKC | OKC | CB - Metro Core | CBMC CE OKC OKC 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 3 | 2020-02-15 | 2020-03-30 |  | Active | Log | Upd | SN-0329 | Schedule Change | Approved | 2020-03-03 16:39 | Several pieces of material in Central Region were received in Feb vs the original Jan date Pushing the acitivation dates out to March to accodomate
Quincy-OCML-IXR | CE | TUL | QNC | CB - Metro Core | CBMC CE TUL QNC OCML_IXR -R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-09-30 |  | Active | EP
Quincy-OCML-IXR | CE | TUL | QNC | CB - Metro Core | CBMC CE TUL QNC Optics Only for Cisco T5 Augment POR20_V2 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0132 | Schedule Change | Approved | 2020-02-06 11:03 | All IXR projects for CBMC In January were moved to March in order lighten January budget Financials have already been updated to reflect the change This is an adminstrative CR
Quincy-OCML-IXR | CE | TUL | QNC | CB - Metro Core | CBMC CE TUL QNC Optics Only for Cisco T5 Augment POR20_V2 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
Quincy-OCML-IXR | CE | TUL | QNC | CB - Metro Core | CBMC CE TUL QNC OCML_IXR -R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0419 | Schedule Change | Approved | 2020-04-02 09:36 | Updates driven by field audit and material delays
Quincy-OCML-IXR | CE | TUL | QNC | CB - Metro Core | CBMC CE TUL QNC OCML_IXR -R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-07-31 |  | Active | Log | Upd | SN-0686 | New | Approved | 2020-06-22 10:17 | POR clean up for the CE and SE regions Deleting duplicate entries and adusting activation months
Quincy-OCML-IXR | CE | TUL | QNC | CB - Metro Core | CBMC CE TUL QNC OCML_IXR -R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-08-30 |  | Active | Log | Upd | SN-0796 | Schedule Change | Approved | 2020-07-31 10:03 | Moving activation dates out for projects in the CA and SW regions due to various delays
Quincy-OCML-IXR | CE | TUL | QNC | CB - Metro Core | CBMC CE TUL QNC OCML_IXR -R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-09-30 |  | Active | Log | Upd | SN-0934 | Schedule Change | Approved | 2020-09-18 09:35 | Moving out activation dates due to delays
CB Transport - New Router Braden - TUL - Card Add | CE | TUL | TUL | CB - Metro Core | CBMC CE TUL TUL Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-02-15 | 2020-07-30 |  | Active | EP
CB Transport - New Router Braden - TUL - Card Add | CE | TUL | TUL | CB - Metro Core | CBMC CE TUL TUL Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-02-15 | 2020-03-30 |  | Active | Log | Upd | SN-0329 | Schedule Change | Approved | 2020-03-03 16:39 | Several pieces of material in Central Region were received in Feb vs the original Jan date Pushing the acitivation dates out to March to accodomate
CB Transport - New Router Braden - TUL - Card Add | CE | TUL | TUL | CB - Metro Core | CBMC CE TUL TUL Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-02-15 | 2020-04-30 |  | Active | Log | Upd | SN-0386 | New | Approved | 2020-03-27 15:11 | Changes to activation dates in the CE region due to late equipment arrivals and installations
CB Transport - New Router Braden - TUL - Card Add | CE | TUL | TUL | CB - Metro Core | CBMC CE TUL TUL Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-02-15 | 2020-07-30 |  | Active | Log | Upd | SN-0701 | Schedule Change | Approved | 2020-07-02 11:45 | Pushing out activation dates in CE CA VA and SW due to equipment delays
TULVOKFZ9DW-XR03.MTN.TUL.OK-100G CARD | CE | TUL | TUL | CB - Metro Core | CBMC CE TUL TUL 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 3 | 2020-02-15 | 2020-03-30 |  | Active | EP
TULVOKFZ9DW-XR03.MTN.TUL.OK-100G CARD | CE | TUL | TUL | CB - Metro Core | CBMC CE TUL TUL 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 3 | 2020-01-15 | 2020-02-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
TULVOKFZ9DW-XR03.MTN.TUL.OK-100G CARD | CE | TUL | TUL | CB - Metro Core | CBMC CE TUL TUL 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 3 | 2020-02-15 | 2020-03-30 |  | Active | Log | Upd | SN-0329 | Schedule Change | Approved | 2020-03-03 16:39 | Several pieces of material in Central Region were received in Feb vs the original Jan date Pushing the acitivation dates out to March to accodomate
Tulsa MTC-OCML-IXR | CE | TUL | TUL | CB - Metro Core | CBMC CE TUL TUL OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | EP
Tulsa MTC-OCML-IXR | CE | TUL | TUL | CB - Metro Core | CBMC CE TUL TUL OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-01-15 | 2020-03-15 |  | Active | Log | Upd | SN-0064 | True up | Approved | 2020-02-06 10:27 | CBMC POR Updates for Central and Southwest
Tulsa MTC-OCML-IXR | CE | TUL | TUL | CB - Metro Core | CBMC CE TUL TUL OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0132 | Schedule Change | Approved | 2020-02-06 11:03 | All IXR projects for CBMC In January were moved to March in order lighten January budget Financials have already been updated to reflect the change This is an adminstrative CR
Tulsa MTC-OCML-IXR | CE | TUL | TUL | CB - Metro Core | CBMC CE TUL TUL OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
CB Transport - New Router Waterloo - WLH - Optics | CE | OKC | WLH | CB - Metro Core | CBMC CE OKC WLH Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-02-15 | 2020-03-30 |  | Active | EP
CB Transport - New Router Waterloo - WLH - Optics | CE | OKC | WLH | CB - Metro Core | CBMC CE OKC WLH Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-02-15 | 2020-03-30 |  | Active | Log | Upd | SN-0329 | Schedule Change | Approved | 2020-03-03 16:39 | Several pieces of material in Central Region were received in Feb vs the original Jan date Pushing the acitivation dates out to March to accodomate
OKCMOKJN9AW-XR01.WLK.OKC.OK-100G CARD | CE | OKC | WLK | CB - Metro Core | CBMC CE OKC WLK 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 2 | 2020-02-15 | 2020-03-15 |  | Active | EP
OKCMOKJN9AW-XR01.WLK.OKC.OK-100G CARD | CE | OKC | WLK | CB - Metro Core | CBMC CE OKC WLK 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 2 | 2020-02-15 | 2020-03-15 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
Yale-OCML-IXR | CE | TUL | YAL | CB - Metro Core | CBMC CE TUL YAL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-09-30 |  | Active | EP
Yale-OCML-IXR | CE | TUL | YAL | CB - Metro Core | CBMC CE TUL YAL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0132 | Schedule Change | Approved | 2020-02-06 11:03 | All IXR projects for CBMC In January were moved to March in order lighten January budget Financials have already been updated to reflect the change This is an adminstrative CR
Yale-OCML-IXR | CE | TUL | YAL | CB - Metro Core | CBMC CE TUL YAL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
Yale-OCML-IXR | CE | TUL | YAL | CB - Metro Core | CBMC CE TUL YAL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-07-31 |  | Active | Log | Upd | SN-0686 | New | Approved | 2020-06-22 10:17 | POR clean up for the CE and SE regions Deleting duplicate entries and adusting activation months
Yale-OCML-IXR | CE | TUL | YAL | CB - Metro Core | CBMC CE TUL YAL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-08-30 |  | Active | Log | Upd | SN-0796 | Schedule Change | Approved | 2020-07-31 10:03 | Moving activation dates out for projects in the CA and SW regions due to various delays
Yale-OCML-IXR | CE | TUL | YAL | CB - Metro Core | CBMC CE TUL YAL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-09-30 |  | Active | Log | Upd | SN-0934 | Schedule Change | Approved | 2020-09-18 09:35 | Moving out activation dates due to delays
CB Transport - New Router Council Bluffs, North - BLV - Card Add | CE | OMA | BLV | CB - Metro Core | CBMC CE OMA BLV Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-02-15 | 2020-03-15 |  | Active | EP
CB Transport - New Router Bellevue - BLV - Chassis Add | CE | OMA | BLV | CB - Metro Core | CBMC CE OMA BLV Cisco M6_M15 Chassis Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-03-30 | 2020-04-30 |  | Active | EP
CB Transport - New Router Bellevue - BLV - Chassis Add | CE | OMA | BLV | CB - Metro Core | CBMC CE OMA BLV Cisco M6_M15 Chassis Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-03-30 | 2020-04-30 |  | Active | Log | Upd | SN-0326 | Schedule Change | Approved | 2020-03-02 16:19 | M6 Chassis for OMA BVL is delayed, moving from February into March Pushing
CB Transport - New Router Bellevue - BLV - Card Add | CE | OMA | BLV | CB - Metro Core | CBMC CE OMA BLV Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-02-15 | 2020-03-30 |  | Active | EP
CB Transport - New Router Bellevue - BLV - Card Add | CE | OMA | BLV | CB - Metro Core | CBMC CE OMA BLV Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-02-15 | 2020-03-30 |  | Active | Log | Upd | SN-0329 | Schedule Change | Approved | 2020-03-03 16:39 | Several pieces of material in Central Region were received in Feb vs the original Jan date Pushing the acitivation dates out to March to accodomate
CB Transport - New Router Council Bluffs - CBL - Optics | CE | OMA | CBL | CB - Metro Core | CBMC CE OMA CBL Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 3 | 2020-02-15 | 2020-03-15 |  | Active | EP
OMAJNEOT9DW-ELKHBSRA21-100G CARD | CE | OMA | ELK | CB - Metro Core | CBMC CE OMA ELK 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 2 | 2020-02-15 | 2020-03-15 |  | Active | EP
OMAJNEOT9DW-ELKHBSRA21-100G CARD | CE | OMA | ELK | CB - Metro Core | CBMC CE OMA ELK 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 2 | 2020-02-15 | 2020-03-15 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
CB Transport - New Router Council Bluffs - OMM - Optics | CE | OMA | OMM | CB - Metro Core | CBMC CE OMA OMM Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-02-15 | 2020-06-30 |  | Active | EP
CB Transport - New Router Council Bluffs - OMM - Optics | CE | OMA | OMM | CB - Metro Core | CBMC CE OMA OMM Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-02-15 | 2020-06-30 |  | Active | Log | Upd | SN-0386 | New | Approved | 2020-03-27 15:11 | Changes to activation dates in the CE region due to late equipment arrivals and installations
CB Transport - New Router Bellevue, Omaha MTC - OMM - Card Add | CE | OMA | OMM | CB - Metro Core | CBMC CE OMA OMM Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-02-15 | 2020-06-30 |  | Active | EP
CB Transport - New Router Bellevue, Omaha MTC - OMM - Card Add | CE | OMA | OMM | CB - Metro Core | CBMC CE OMA OMM Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-02-15 | 2020-03-30 |  | Active | Log | Upd | SN-0329 | Schedule Change | Approved | 2020-03-03 16:39 | Several pieces of material in Central Region were received in Feb vs the original Jan date Pushing the acitivation dates out to March to accodomate
CB Transport - New Router Bellevue, Omaha MTC - OMM - Card Add | CE | OMA | OMM | CB - Metro Core | CBMC CE OMA OMM Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-02-15 | 2020-06-30 |  | Active | Log | Upd | SN-0386 | New | Approved | 2020-03-27 15:11 | Changes to activation dates in the CE region due to late equipment arrivals and installations
South-OCML-IXR | CE | OMA | SOU | CB - Metro Core | CBMC CE OMA SOU OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-08-30 |  | Active | EP
South-OCML-IXR | CE | OMA | SOU | CB - Metro Core | CBMC CE OMA SOU Optics Only for Cisco T5 Augment POR20_V2 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0132 | Schedule Change | Approved | 2020-02-06 11:03 | All IXR projects for CBMC In January were moved to March in order lighten January budget Financials have already been updated to reflect the change This is an adminstrative CR
South-OCML-IXR | CE | OMA | SOU | CB - Metro Core | CBMC CE OMA SOU OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
South-OCML-IXR | CE | OMA | SOU | CB - Metro Core | CBMC CE OMA SOU OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
South-OCML-IXR | CE | OMA | SOU | CB - Metro Core | CBMC CE OMA SOU OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-07-31 |  | Active | Log | Upd | SN-0686 | New | Approved | 2020-06-22 10:17 | POR clean up for the CE and SE regions Deleting duplicate entries and adusting activation months
South-OCML-IXR | CE | OMA | SOU | CB - Metro Core | CBMC CE OMA SOU OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-08-30 |  | Active | Log | Upd | SN-0796 | Schedule Change | Approved | 2020-07-31 10:03 | Moving activation dates out for projects in the CA and SW regions due to various delays
CB Transport - New Router Enfield P - ENF - Card Add | NE | CON | ENF | CB - Metro Core | CBMC NE CON ENF Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-01 | 2020-06-30 |  | Active | EP
CB Transport - New Router Enfield P - ENF - Card Add | NE | CON | ENF | CB - Metro Core | CBMC NE CON ENF Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-01 | 2020-05-15 |  | Active | Log | Upd | SN-0419 | Schedule Change | Approved | 2020-04-02 09:36 | Updates driven by field audit and material delays
CB Transport - New Router Enfield P - ENF - Card Add | NE | CON | ENF | CB - Metro Core | CBMC NE CON ENF Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-01 | 2020-06-30 |  | Active | Log | Upd | SN-0618 | Schedule Change | Approved | 2020-06-05 14:52 | Removing deferred projects that still remain in the POR and moving out activation dates due to various equipment delays
CB Transport - New Router Enfield P, Manchester P - MAN - Card Add | NE | CON | MAN | CB - Metro Core | CBMC NE CON MAN Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-01 | 2020-06-30 |  | Active | EP
CB Transport - New Router Enfield P, Manchester P - MAN - Card Add | NE | CON | MAN | CB - Metro Core | CBMC NE CON MAN Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-01 | 2020-05-15 |  | Active | Log | Upd | SN-0419 | Schedule Change | Approved | 2020-04-02 09:36 | Updates driven by field audit and material delays
CB Transport - New Router Enfield P, Manchester P - MAN - Card Add | NE | CON | MAN | CB - Metro Core | CBMC NE CON MAN Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-01 | 2020-06-30 |  | Active | Log | Upd | SN-0618 | Schedule Change | Approved | 2020-06-05 14:52 | Removing deferred projects that still remain in the POR and moving out activation dates due to various equipment delays
CB Transport - New Router Manchester P - PRV - Optics | NE | RHD | PRV | CB - Metro Core | CBMC NE RHD PRV Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-01-01 | 2020-01-15 |  | Active | EP
CB Transport - New Router Richmond - PRV - Optics | NE | RHD | PRV | CB - Metro Core | CBMC NE RHD PRV Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-01-15 | 2020-02-15 |  | Active | EP
CB Transport - New Router Richmond - PRV - Optics | NE | RHD | PRV | CB - Metro Core |  | Card & Optics | Optics Only for Cisco T5 |  |  |  |  | Active | Log | Del | SN-0020 | New | Approved | 2020-02-06 09:59 | Cleaning up POR Deleting duplicate records from the POR No financials are attached to this CR
CB Transport - New Router Richmond - PRV - Optics | NE | RHD | PRV | CB - Metro Core | CBMC NE RHD PRV Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 |  | 2020-02-15 |  | Active | Log | New | SN-0131 | New | Approved | 2020-02-06 11:02 | 18 line items inadverntly were deleted from the POR
CB Transport - New Router Richmond - PRV - Optics | NE | RHD | PRV | CB - Metro Core | CBMC NE RHD PRV Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-01-15 | 2020-02-15 |  | Active | Log | Upd | SN-0309 | Schedule Change | Approved | 2020-03-02 16:17 | Audit of POR and making changed based on results
PROVBSPA01.RI.RI-SFM | NE | RHD | PRV | CB - Metro Core | CBMC NE RHD PRV SFM-7950 XRS-20 Augment POR20 | Card & Optics | Nokia SFM-7950 XRS-20/20e SFM2-SA | 8 | 2020-01-15 | 2020-05-15 |  | Active | EP
PROVBSPA01.RI.RI-SFM | NE | RHD | PRV | CB - Metro Core | CBMC NE RHD PRV SFM-7950 XRS-20 Augment POR20 | Card & Optics | Nokia SFM-7950 XRS-20/20e SFM2-SA | 8 | 2020-01-15 | 2020-05-15 |  | Active | Log | Upd | SN-0419 | Schedule Change | Approved | 2020-04-02 09:36 | Updates driven by field audit and material delays
PROVBSPA01.RI.RI-100G CARD | NE | RHD | PRV | CB - Metro Core | CBMC NE RHD PRV 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-01-15 | 2020-05-20 |  | Active | EP
PROVBSPA01.RI.RI-100G CARD | NE | RHD | PRV | CB - Metro Core | CBMC NE RHD PRV 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-01-15 | 2020-04-15 |  | Active | Log | Upd | SN-0419 | Schedule Change | Approved | 2020-04-02 09:36 | Updates driven by field audit and material delays
PROVBSPA01.RI.RI-100G CARD | NE | RHD | PRV | CB - Metro Core | CBMC NE RHD PRV 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-01-15 | 2020-05-20 |  | Active | Log | Upd | SN-0478 | Schedule Change | Approved | 2020-04-24 14:37 | Adjusting schedule dates across multpile PPMs
Portsmouth-OCML-IXR | NE | RHD | PTH | CB - Metro Core | CBMC NE RHD PTH OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | EP
Portsmouth-OCML-IXR | NE | RHD | PTH | CB - Metro Core | CBMC NE RHD PTH OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0132 | Schedule Change | Approved | 2020-02-06 11:03 | All IXR projects for CBMC In January were moved to March in order lighten January budget Financials have already been updated to reflect the change This is an adminstrative CR
Portsmouth-OCML-IXR | NE | RHD | PTH | CB - Metro Core | CBMC NE RHD PTH OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
CB Transport - New Router Richmond - RMD - Optics | NE | RHD | RMD | CB - Metro Core | CBMC NE RHD RMD Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 3 | 2020-01-15 | 2020-02-15 |  | Active | EP
CB Transport - New Router Richmond - WWK - Optics | NE | RHD | WWK | CB - Metro Core | CBMC NE RHD WWK Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-01-01 | 2020-02-15 |  | Active | EP
CB Transport - New Router Enfield P, Richmond - WWK - Card Add | NE | RHD | WWK | CB - Metro Core | CBMC NE RHD WWK Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-01 | 2020-06-30 |  | Active | EP
CB Transport - New Router Enfield P, Richmond - WWK - Card Add | NE | RHD | WWK | CB - Metro Core | CBMC NE RHD WWK Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-01 | 2020-05-15 |  | Active | Log | Upd | SN-0419 | Schedule Change | Approved | 2020-04-02 09:36 | Updates driven by field audit and material delays
CB Transport - New Router Enfield P, Richmond - WWK - Card Add | NE | RHD | WWK | CB - Metro Core | CBMC NE RHD WWK Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-01 | 2020-06-30 |  | Active | Log | Upd | SN-0618 | Schedule Change | Approved | 2020-06-05 14:52 | Removing deferred projects that still remain in the POR and moving out activation dates due to various equipment delays
WWCKBSPA01.RI.RI-100G CARD | NE | RHD | WWK | CB - Metro Core | CBMC NE RHD WWK 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-01-15 | 2020-05-20 |  | Active | EP
WWCKBSPA01.RI.RI-100G CARD | NE | RHD | WWK | CB - Metro Core | CBMC NE RHD WWK 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-01-15 | 2020-04-15 |  | Active | Log | Upd | SN-0419 | Schedule Change | Approved | 2020-04-02 09:36 | Updates driven by field audit and material delays
WWCKBSPA01.RI.RI-100G CARD | NE | RHD | WWK | CB - Metro Core | CBMC NE RHD WWK 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-01-15 | 2020-05-20 |  | Active | Log | Upd | SN-0478 | Schedule Change | Approved | 2020-04-24 14:37 | Adjusting schedule dates across multpile PPMs
WWCKBSPA01.RI.RI-SFM | NE | RHD | WWK | CB - Metro Core | CBMC NE RHD WWK SFM-7950 XRS-20 Augment POR20 | Card & Optics | Nokia SFM-7950 XRS-20/20e SFM2-SA | 8 | 2020-01-15 | 2020-05-15 |  | Active | EP
WWCKBSPA01.RI.RI-SFM | NE | RHD | WWK | CB - Metro Core | CBMC NE RHD WWK SFM-7950 XRS-20 Augment POR20 | Card & Optics | Nokia SFM-7950 XRS-20/20e SFM2-SA | 8 | 2020-01-15 | 2020-05-15 |  | Active | Log | Upd | SN-0419 | Schedule Change | Approved | 2020-04-02 09:36 | Updates driven by field audit and material delays
Abbeville-OCML-IXR | SE | LFY | ABV | CB - Metro Core | CBMC SE LFY ABV OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-08-31 |  | Active | EP
Abbeville-OCML-IXR | SE | LFY | ABV | CB - Metro Core | CBMC SE LFY ABV OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0132 | Schedule Change | Approved | 2020-02-06 11:03 | All IXR projects for CBMC In January were moved to March in order lighten January budget Financials have already been updated to reflect the change This is an adminstrative CR
Abbeville-OCML-IXR | SE | LFY | ABV | CB - Metro Core | CBMC SE LFY ABV OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
Abbeville-OCML-IXR | SE | LFY | ABV | CB - Metro Core | CBMC SE LFY ABV OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-07-31 |  | Active | Log | Upd | SN-0618 | Schedule Change | Approved | 2020-06-05 14:52 | Removing deferred projects that still remain in the POR and moving out activation dates due to various equipment delays
Abbeville-OCML-IXR | SE | LFY | ABV | CB - Metro Core | CBMC SE LFY ABV OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-08-31 |  | Active | Log | Upd | SN-0771 | Schedule Change | Approved | 2020-07-20 09:31 | Adjusting POR activation months in CE SE and SW due to impacts from equipment delays
CB Transport - New Router South - BTR - Optics | SE | BTR | BTR | CB - Metro Core | CBMC SE BTR BTR Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-01-01 | 2020-02-15 |  | Active | EP
CB Transport - New Router South - BTR - Optics | SE | BTR | BTR | CB - Metro Core |  | Card & Optics | Optics Only for Cisco T5 |  |  |  |  | Active | Log | Del | SN-0020 | New | Approved | 2020-02-06 09:59 | Cleaning up POR Deleting duplicate records from the POR No financials are attached to this CR
CB Transport - New Router South - BTR - Optics | SE | BTR | BTR | CB - Metro Core | CBMC SE BTR BTR Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 |  | 2020-01-01 |  | Active | Log | New | SN-0131 | New | Approved | 2020-02-06 11:02 | 18 line items inadverntly were deleted from the POR
CB Transport - New Router South - BTR - Optics | SE | BTR | BTR | CB - Metro Core | CBMC SE BTR BTR Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-01-01 | 2020-02-15 |  | Active | Log | Upd | SN-0309 | Schedule Change | Approved | 2020-03-02 16:17 | Audit of POR and making changed based on results
CB Transport - New Router St Charles - BTR - Optics | SE | BTR | BTR | CB - Metro Core | CBMC SE BTR BTR Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-01-01 | 2020-02-15 |  | Active | EP
CB Transport - New Router St Charles - BTR - Optics | SE | BTR | BTR | CB - Metro Core |  | Card & Optics | Optics Only for Cisco T5 |  |  |  |  | Active | Log | Del | SN-0020 | New | Approved | 2020-02-06 09:59 | Cleaning up POR Deleting duplicate records from the POR No financials are attached to this CR
CB Transport - New Router St Charles - BTR - Optics | SE | BTR | BTR | CB - Metro Core | CBMC SE BTR BTR Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 |  | 2020-01-01 |  | Active | Log | New | SN-0131 | New | Approved | 2020-02-06 11:02 | 18 line items inadverntly were deleted from the POR
CB Transport - New Router St Charles - BTR - Optics | SE | BTR | BTR | CB - Metro Core | CBMC SE BTR BTR Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-01-01 | 2020-02-15 |  | Active | Log | Upd | SN-0309 | Schedule Change | Approved | 2020-03-02 16:17 | Audit of POR and making changed based on results
CB Transport - New Router Donaldsonville - BTR - Optics | SE | BTR | BTR | CB - Metro Core | CBMC SE BTR BTR Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-01-01 | 2020-02-01 |  | Active | EP
CB Transport - New Router Lafayette - BTR - Optics | SE | BTR | BTR | CB - Metro Core | CBMC SE BTR BTR Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-01-01 | 2020-02-15 |  | Active | EP
CB Transport - New Router Lafayette - BTR - Optics | SE | BTR | BTR | CB - Metro Core |  | Card & Optics | Optics Only for Cisco T5 |  |  |  |  | Active | Log | Del | SN-0020 | New | Approved | 2020-02-06 09:59 | Cleaning up POR Deleting duplicate records from the POR No financials are attached to this CR
CB Transport - New Router Lafayette - BTR - Optics | SE | BTR | BTR | CB - Metro Core | CBMC SE BTR BTR Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 |  | 2020-01-01 |  | Active | Log | New | SN-0131 | New | Approved | 2020-02-06 11:02 | 18 line items inadverntly were deleted from the POR
CB Transport - New Router Lafayette - BTR - Optics | SE | BTR | BTR | CB - Metro Core | CBMC SE BTR BTR Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-01-01 | 2020-02-15 |  | Active | Log | Upd | SN-0309 | Schedule Change | Approved | 2020-03-02 16:17 | Audit of POR and making changed based on results
CB Transport - New Router North - BTR - Optics | SE | BTR | BTR | CB - Metro Core | CBMC SE BTR BTR Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-01-01 | 2020-02-15 |  | Active | EP
CB Transport - New Router North - BTR - Optics | SE | BTR | BTR | CB - Metro Core |  | Card & Optics | Optics Only for Cisco T5 |  |  |  |  | Active | Log | Del | SN-0020 | New | Approved | 2020-02-06 09:59 | Cleaning up POR Deleting duplicate records from the POR No financials are attached to this CR
CB Transport - New Router North - BTR - Optics | SE | BTR | BTR | CB - Metro Core | CBMC SE BTR BTR Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 |  | 2020-01-01 |  | Active | Log | New | SN-0131 | New | Approved | 2020-02-06 11:02 | 18 line items inadverntly were deleted from the POR
CB Transport - New Router North - BTR - Optics | SE | BTR | BTR | CB - Metro Core | CBMC SE BTR BTR Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-01-01 | 2020-02-15 |  | Active | Log | Upd | SN-0309 | Schedule Change | Approved | 2020-03-02 16:17 | Audit of POR and making changed based on results
BRX02-100G CARD | SE | BTR | BTR | CB - Metro Core | CBMC SE BTR BTR 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-01-15 | 2020-04-15 |  | Active | EP
BRX02-100G CARD | SE | BTR | BTR | CB - Metro Core | CBMC SE BTR BTR 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-01-15 | 2020-04-15 |  | Active | Log | Upd | SN-0419 | Schedule Change | Approved | 2020-04-02 09:36 | Updates driven by field audit and material delays
BRX02-SFM | SE | BTR | BTR | CB - Metro Core | CBMC SE BTR BTR SFM-7950 XRS-20 Augment POR20 | Card & Optics | Nokia SFM-7950 XRS-20/20e SFM2-SA | 16 | 2020-01-15 | 2020-02-15 |  | Active | EP
BRX02-SFM | SE | BTR | BTR | CB - Metro Core | CBMC SE BTR BTR SFM-7950 XRS-20 Augment POR20 | Card & Optics | Nokia SFM-7950 XRS-20/20e SFM2-SA | 16 | 2020-01-15 | 2020-02-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
BRX02-SFM | SE | BTR | BTR | CB - Metro Core | CBMC SE BTR BTR SFM-7950 XRS-20 Augment POR20 | Card & Optics | Nokia SFM-7950 XRS-20/20e SFM2-SA | 16 | 2020-01-15 | 2020-02-15 |  | Active | Log | Upd | SN-0419 | Schedule Change | Approved | 2020-04-02 09:36 | Updates driven by field audit and material delays
CB Transport - New Router BTR uplink, POY - ELM - Optics | SE | NOR | ELM | CB - Metro Core | CBMC SE NOR ELM Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-01-01 | 2020-01-15 |  | Active | EP
CB Transport - New Router New Orleans East - ELM - Optics | SE | NOR | ELM | CB - Metro Core | CBMC SE NOR ELM Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
HRHNLA061AW-100G CARD | SE | NOR | MCY | CB - Metro Core | CBMC SE NOR MCY 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA |  |  |  |  | Deleted | EP
HRHNLA061AW-100G CARD | SE | NOR | MCY | CB - Metro Core | CBMC SE NOR MCY 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA |  |  |  |  | Deleted | Log | Del | SN-0419 | Schedule Change | Approved | 2020-04-02 09:36 | Updates driven by field audit and material delays
HRHNLA061AW-SFM | SE | NOR | MCY | CB - Metro Core | CBMC SE NOR MCY SFM-7950 XRS-20 Augment POR20 | Card & Optics | Nokia SFM-7950 XRS-20/20e SFM2-SA | 8 | 2020-01-15 | 2020-04-15 |  | Active | EP
HRHNLA061AW-SFM | SE | NOR | MCY | CB - Metro Core | CBMC SE NOR MCY SFM-7950 XRS-20 Augment POR20 | Card & Optics | Nokia SFM-7950 XRS-20/20e SFM2-SA | 8 | 2020-01-15 | 2020-04-15 |  | Active | Log | Upd | SN-0419 | Schedule Change | Approved | 2020-04-02 09:36 | Updates driven by field audit and material delays
CB Transport - New Router Lafayette, St. Martinville - LFY - Card Add | SE | LFY | LFY | CB - Metro Core | CBMC SE LFY LFY Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-01 | 2020-01-15 |  | Active | EP
CB Transport - New Router St Martinville - LFY - Optics | SE | LFY | LFY | CB - Metro Core | CBMC SE LFY LFY Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-01-01 | 2020-02-01 |  | Active | EP
CB Transport - New Router St Martinville - LFY - Optics | SE | LFY | LFY | CB - Metro Core | CBMC SE LFY LFY Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-01-01 | 2020-02-01 |  | Active | Log | Upd | SN-0419 | Schedule Change | Approved | 2020-04-02 09:36 | Updates driven by field audit and material delays
St. Charles West-OCML-IXR | SE | NOR | LUL | CB - Metro Core | CBMC SE NOR LUL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | EP
St. Charles West-OCML-IXR | SE | NOR | LUL | CB - Metro Core | CBMC SE NOR LUL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0132 | Schedule Change | Approved | 2020-02-06 11:03 | All IXR projects for CBMC In January were moved to March in order lighten January budget Financials have already been updated to reflect the change This is an adminstrative CR
St. Charles West-OCML-IXR | SE | NOR | LUL | CB - Metro Core | CBMC SE NOR LUL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
MCTYCBPN01-100G CARD | SE | NOR | MCY | CB - Metro Core | CBMC SE NOR MCY 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 2 | 2020-01-15 | 2020-04-15 |  | Active | EP
MCTYCBPN01-100G CARD | SE | NOR | MCY | CB - Metro Core | CBMC SE NOR MCY 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 2 | 2020-01-15 | 2020-04-15 |  | Active | Log | Upd | SN-0419 | Schedule Change | Approved | 2020-04-02 09:36 | Updates driven by field audit and material delays
CB Transport - New Router New Orleans East - MCY - Card Add | SE | NOR | MCY | CB - Metro Core | CBMC SE NOR MCY Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CB Transport - New Router BTR uplink, POY - MCY - Optics | SE | NOR | MCY | CB - Metro Core | CBMC SE NOR MCY Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-01-01 | 2020-01-15 |  | Active | EP
Mid City-OCML-IXR | SE | NOR | MCY | CB - Metro Core | CBMC SE NOR MCY OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | EP
Mid City-OCML-IXR | SE | NOR | MCY | CB - Metro Core | CBMC SE NOR MCY OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0132 | Schedule Change | Approved | 2020-02-06 11:03 | All IXR projects for CBMC In January were moved to March in order lighten January budget Financials have already been updated to reflect the change This is an adminstrative CR
Mid City-OCML-IXR | SE | NOR | MCY | CB - Metro Core | CBMC SE NOR MCY OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
CB Transport - New Router New Orleans East - NOE - Optics | SE | NOR | NOE | CB - Metro Core | CBMC SE NOR NOE Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 3 | 2020-01-01 | 2020-01-15 |  | Active | EP
CB Transport - New Router South - SPC - Optics | SE | BTR | SPC | CB - Metro Core | CBMC SE BTR SPC Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-01-01 | 2020-03-01 |  | Active | EP
CB Transport - New Router Holt - MCN - Card Add | SE | MGA | MCN | CB - Metro Core | CBMC SE MGA MCN Optics Only for Cisco T5 Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 6 | 2020-01-20 | 2020-03-15 |  | Active | EP
CB Transport - New Router Holt - MCN - Card Add | SE | MGA | MCN | CB - Metro Core | CBMC SE MGA HLT Optics Only for Cisco T5 Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-20 | 2020-03-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
CB Transport - New Router Holt - MCN - Card Add | SE | MGA | MCN | CB - Metro Core | CBMC SE MGA MCN Optics Only for Cisco T5 Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 6 | 2020-01-20 | 2020-03-15 |  | Active | Log | Upd | SN-0419 | Schedule Change | Approved | 2020-04-02 09:36 | Updates driven by field audit and material delays
CB Transport - New Router Bell - BEL - Optics | SW | ARZ | BEL | CB - Metro Core | CBMC SW ARZ BEL Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-01-15 | 2020-02-15 |  | Active | EP
CB Transport - New Router Bell, Peoria - CHD - Card Add | SW | ARZ | CHD | CB - Metro Core | CBMC SW ARZ CHD Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-15 | 2020-02-15 |  | Active | EP
CB Transport - New Router Peoria - CHD - Optics | SW | ARZ | CHD | CB - Metro Core | CBMC SW ARZ CHD Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-01-17 | 2020-03-15 |  | Active | EP
CB Transport - New Router Tucson - CHD - Card Add | SW | ARZ | CHD | CB - Metro Core | CBMC SW ARZ CHD Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CB Transport - New Router Peoria - MCD - Card Add | SW | ARZ | MCD | CB - Metro Core | CBMC SW ARZ MCD Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-17 | 2020-03-15 |  | Active | EP
CB Transport - New Router Peoria - MCD - Card Add | SW | ARZ | MCD | CB - Metro Core | CBMC SW ARZ MCD Optics Only for Cisco T5 Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-17 | 2020-03-15 |  | Active | Log | Upd | SN-0064 | True up | Approved | 2020-02-06 10:27 | CBMC POR Updates for Central and Southwest
CB Transport - New Router Peoria - MCD - Card Add | SW | ARZ | MCD | CB - Metro Core | CBMC SW ARZ MCD Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-17 | 2020-03-15 |  | Active | Log | Upd | SN-0419 | Schedule Change | Approved | 2020-04-02 09:36 | Updates driven by field audit and material delays
CB Transport - New Router Bell - MCD - Optics | SW | ARZ | MCD | CB - Metro Core | CBMC SW ARZ MCD Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-01-01 | 2020-02-15 |  | Active | EP
CB Transport - New Router Tucson - MCD - Optics | SW | ARZ | MCD | CB - Metro Core | CBMC SW ARZ MCD Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-01-01 | 2020-01-15 |  | Active | EP
CB Transport - New Router Peoria - PEO - Card Add | SW | ARZ | PEO | CB - Metro Core | CBMC SW ARZ PEO Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-10 | 2020-03-15 |  | Active | EP
CB Transport - New Router Tucson - TUC - Card Add | SW | ARZ | TUC | CB - Metro Core | CBMC SW ARZ TUC Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-01 | 2020-01-15 |  | Active | EP
Aliante-OCML-IXR | SW | LAS | ALI | CB - Metro Core | CBMC SW LAS ALI OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-07-20 |  | Active | EP
Aliante-OCML-IXR | SW | LAS | ALI | CB - Metro Core | CBMC SW LAS ALI OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0132 | Schedule Change | Approved | 2020-02-06 11:03 | All IXR projects for CBMC In January were moved to March in order lighten January budget Financials have already been updated to reflect the change This is an adminstrative CR
Aliante-OCML-IXR | SW | LAS | ALI | CB - Metro Core | CBMC SW LAS ALI OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
Aliante-OCML-IXR | SW | LAS | ALI | CB - Metro Core | CBMC SW LAS ALI OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-07-20 |  | Active | Log | Upd | SN-0586 | Schedule Change | Approved | 2020-05-14 14:37 | Adjusting dates for CBMC POR Most of the changes are pushing activation dates out due to equipment delays
South East-OCML-IXR | SW | LAS | HEN | CB - Metro Core | CBMC SW LAS HEN OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-09-30 |  | Active | EP
South East-OCML-IXR | SW | LAS | HEN | CB - Metro Core | CBMC SW LAS HEN OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0132 | Schedule Change | Approved | 2020-02-06 11:03 | All IXR projects for CBMC In January were moved to March in order lighten January budget Financials have already been updated to reflect the change This is an adminstrative CR
South East-OCML-IXR | SW | LAS | HEN | CB - Metro Core | CBMC SW LAS HEN OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
South East-OCML-IXR | SW | LAS | HEN | CB - Metro Core | CBMC SW LAS HEN OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-07-20 |  | Active | Log | Upd | SN-0586 | Schedule Change | Approved | 2020-05-14 14:37 | Adjusting dates for CBMC POR Most of the changes are pushing activation dates out due to equipment delays
South East-OCML-IXR | SW | LAS | HEN | CB - Metro Core | CBMC SW LAS HEN OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-09-30 |  | Active | Log | Upd | SN-0701 | Schedule Change | Approved | 2020-07-02 11:45 | Pushing out activation dates in CE CA VA and SW due to equipment delays
North West-OCML-IXR | SW | LAS | TEN | CB - Metro Core | CBMC SW LAS TEN OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-09-30 |  | Active | EP
North West-OCML-IXR | SW | LAS | TEN | CB - Metro Core | CBMC SW LAS TEN OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0132 | Schedule Change | Approved | 2020-02-06 11:03 | All IXR projects for CBMC In January were moved to March in order lighten January budget Financials have already been updated to reflect the change This is an adminstrative CR
North West-OCML-IXR | SW | LAS | TEN | CB - Metro Core | CBMC SW LAS TEN OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
North West-OCML-IXR | SW | LAS | TEN | CB - Metro Core | CBMC SW LAS TEN OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-07-30 |  | Active | Log | Upd | SN-0701 | Schedule Change | Approved | 2020-07-02 11:45 | Pushing out activation dates in CE CA VA and SW due to equipment delays
North West-OCML-IXR | SW | LAS | TEN | CB - Metro Core | CBMC SW LAS TEN OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-09-30 |  | Active | Log | Upd | SN-0771 | Schedule Change | Approved | 2020-07-20 09:31 | Adjusting POR activation months in CE SE and SW due to impacts from equipment delays
NRFLVAJT8AW-A701JT7950-100G CARD | VA | HRD | NRF | CB - Metro Core | CBMC VA HRD NRF 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-01-15 | 2020-02-15 |  | Active | EP
CB Transport - New Router Village - NRF - Optics | VA | HRD | NRF | CB - Metro Core | CBMC VA HRD NRF Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-02-15 | 2020-11-30 |  | Active | EP
CB Transport - New Router Village - NRF - Optics | VA | HRD | NRF | CB - Metro Core | CBMC VA HRD NRF Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-02-15 | 2020-11-30 |  | Active | Log | Upd | SN-0934 | Schedule Change | Approved | 2020-09-18 09:35 | Moving out activation dates due to delays
CB Transport - New Router Newport News - NRF - Card Add | VA | HRD | NRF | CB - Metro Core | CBMC VA HRD NRF Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-02-15 | 2020-12-31 |  | Active | EP
CB Transport - New Router Newport News - NRF - Card Add | VA | HRD | NRF | CB - Metro Core | CBMC VA HRD NRF Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-02-15 | 2020-10-31 |  | Active | Log | Upd | SN-0934 | Schedule Change | Approved | 2020-09-18 09:35 | Moving out activation dates due to delays
CB Transport - New Router Newport News - NRF - Card Add | VA | HRD | NRF | CB - Metro Core | CBMC VA HRD NRF Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-02-15 | 2020-12-31 |  | Active | Log | Upd | SN-1049 | New | Approved | 2020-11-13 09:56 | Moving out activation dates for CBMC projects
CB Transport - New Router Newport News - NWP - Optics | VA | HRD | NWP | CB - Metro Core | CBMC VA HRD NWP Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-02-15 | 2020-11-30 |  | Active | EP
CB Transport - New Router Newport News - NWP - Optics | VA | HRD | NWP | CB - Metro Core | CBMC VA HRD NWP Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-02-15 | 2020-11-30 |  | Active | Log | Upd | SN-0934 | Schedule Change | Approved | 2020-09-18 09:35 | Moving out activation dates due to delays
CB Transport - New Router Village - VBC - Optics | VA | HRD | VBC | CB - Metro Core | CBMC VA HRD VBC Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-02-15 | 2020-11-30 |  | Active | EP
CB Transport - New Router Village - VBC - Optics | VA | HRD | VBC | CB - Metro Core | CBMC VA HRD VBC Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-02-15 | 2020-11-30 |  | Active | Log | Upd | SN-0934 | Schedule Change | Approved | 2020-09-18 09:35 | Moving out activation dates due to delays
CB Transport - New Router Newport News - VBC - Card Add | VA | HRD | VBC | CB - Metro Core | CBMC VA HRD VBC Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-02-15 | 2020-12-31 |  | Active | EP
CB Transport - New Router Newport News - VBC - Card Add | VA | HRD | VBC | CB - Metro Core | CBMC VA HRD VBC Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-02-15 | 2020-10-31 |  | Active | Log | Upd | SN-0934 | Schedule Change | Approved | 2020-09-18 09:35 | Moving out activation dates due to delays
CB Transport - New Router Newport News - VBC - Card Add | VA | HRD | VBC | CB - Metro Core | CBMC VA HRD VBC Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-02-15 | 2020-12-31 |  | Active | Log | Upd | SN-1049 | New | Approved | 2020-11-13 09:56 | Moving out activation dates for CBMC projects
VRBHVAZD8BW-A701JT7950-100G CARD | VA | HRD | VBC | CB - Metro Core | CBMC VA HRD VBC 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-01-15 | 2020-02-15 |  | Active | EP
FRFYVA0648W-100G CARD | VA | NVA | FLK | CB - Metro Core | CBMC VA NVA FLK 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-01-15 | 2020-02-15 |  | Active | EP
FLCHVA1948W-100G CARD | VA | NVA | MFD | CB - Metro Core | CBMC VA NVA MFD 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-01-15 | 2020-02-15 |  | Active | EP
BLVUBSRA99-ROUTER | CE | OMA | BLV | CB - Metro Core | CBMC CE OMA BLV ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-05 | 2020-04-15 |  | Active | EP
BLVUBSRA99-ROUTER | CE | OMA | BLV | CB - Metro Core | CBMC CE OMA BLV ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-05 | 2020-04-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
BLVUBSRA01-ROUTER | CE | OMA | BLV | CB - Metro Core | CBMC CE OMA BLV ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-25 | 2020-09-30 |  | Active | EP
BLVUBSRA01-ROUTER | CE | OMA | BLV | CB - Metro Core | CBMC CE OMA BLV ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-25 | 2020-05-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
BLVUBSRA01-ROUTER | CE | OMA | BLV | CB - Metro Core | CBMC CE OMA BLV ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-25 | 2020-08-31 |  | Active | Log | Upd | SN-0737 | Schedule Change | Approved | 2020-07-10 10:12 | Pushing out activation dates in the SER due to equipment delays Deleting duplicate record in CE and pushing out activation month due to site readiness delays
BLVUBSRA01-ROUTER | CE | OMA | BLV | CB - Metro Core | CBMC CE OMA BLV ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-25 | 2020-09-30 |  | Active | Log | Upd | SN-0934 | Schedule Change | Approved | 2020-09-18 09:35 | Moving out activation dates due to delays
BLVUBSRA02-ROUTER | CE | OMA | BLV | CB - Metro Core | CBMC CE OMA BLV ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
BLVUBSRA02-ROUTER | CE | OMA | BLV | CB - Metro Core | CBMC CE OMA BLV ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-25 | 2020-05-15 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
BLVUBSRA02-ROUTER | CE | OMA | BLV | CB - Metro Core | CBMC CE OMA BLV ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0737 | Schedule Change | Approved | 2020-07-10 10:12 | Pushing out activation dates in the SER due to equipment delays Deleting duplicate record in CE and pushing out activation month due to site readiness delays
CNBFBSRA02-ROUTER | CE | OMA | CBL | CB - Metro Core | CBMC CE OMA CBL ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
CNBFBSRA02-ROUTER | CE | OMA | CBL | CB - Metro Core | CBMC CE OMA CBL ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-03-15 | 2020-06-15 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
CNBFBSRA02-ROUTER | CE | OMA | CBL | CB - Metro Core | CBMC CE OMA CBL ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0686 | New | Approved | 2020-06-22 10:17 | POR clean up for the CE and SE regions Deleting duplicate entries and adusting activation months
CNBFBSRA01-ROUTER | CE | OMA | CBL | CB - Metro Core | CBMC CE OMA CBL ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-03-15 | 2020-07-31 |  | Active | EP
CNBFBSRA01-ROUTER | CE | OMA | CBL | CB - Metro Core | CBMC CE OMA CBL ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-03-15 | 2020-06-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
CNBFBSRA01-ROUTER | CE | OMA | CBL | CB - Metro Core | CBMC CE OMA CBL ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-03-15 | 2020-07-31 |  | Active | Log | Upd | SN-0686 | New | Approved | 2020-06-22 10:17 | POR clean up for the CE and SE regions Deleting duplicate entries and adusting activation months
MTC1BSRA99-ROUTER | CE | OMA | OMM | CB - Metro Core | CBMC CE OMA OMM ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-05 | 2020-06-30 |  | Active | EP
MTC1BSRA99-ROUTER | CE | OMA | OMM | CB - Metro Core | CBMC CE OMA OMM ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-05 | 2020-04-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
MTC1BSRA99-ROUTER | CE | OMA | OMM | CB - Metro Core | CBMC CE OMA OMM ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-05 | 2020-06-30 |  | Active | Log | Upd | SN-0386 | New | Approved | 2020-03-27 15:11 | Changes to activation dates in the CE region due to late equipment arrivals and installations
MTC1BSRA01-ROUTER | CE | OMA | OMM | CB - Metro Core | CBMC CE OMA OMM ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
MTC1BSRA01-ROUTER | CE | OMA | OMM | CB - Metro Core | CBMC CE OMA OMM ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-07-15 | 2020-10-15 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
MTC1BSRA01-ROUTER | CE | OMA | OMM | CB - Metro Core | CBMC CE OMA OMM ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
CLVDBSRA02.RI.CL.COX.NET-ROUTER | NE | CLE | CLV | CB - Metro Core | CBMC NE CLE CLV ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-07-15 |  | Active | EP
CLVDBSRA02.RI.CL.COX.NET-ROUTER | NE | CLE | CLV | CB - Metro Core | CBMC NE CLE CLV ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-07-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
ELCNBPRA01-ROUTER | CA | SAN | ELC | CB - Metro Core | CBMC CA SAN ELC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 1 | 2020-01-15 | 2020-07-31 |  | Active | EP
ELCNBPRA01-ROUTER | CA | SAN | ELC | CB - Metro Core | CBMC CA SAN ELC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-04-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
ELCNBPRA01-ROUTER | CA | SAN | ELC | CB - Metro Core | CBMC CA SAN ELC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 1 | 2020-01-15 | 2020-04-15 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
ELCNBPRA01-ROUTER | CA | SAN | ELC | CB - Metro Core | CBMC CA SAN ELC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 1 | 2020-01-15 | 2020-07-31 |  | Active | Log | Upd | SN-0618 | Schedule Change | Approved | 2020-06-05 14:52 | Removing deferred projects that still remain in the POR and moving out activation dates due to various equipment delays
ELCNEWAA02-ROUTER | CA | SAN | ELC | CB - Metro Core | CBMC CA SAN ELC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 1 | 2020-02-15 | 2020-07-31 |  | Active | EP
ELCNEWAA02-ROUTER | CA | SAN | ELC | CB - Metro Core | CBMC CA SAN ELC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-05-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
ELCNEWAA02-ROUTER | CA | SAN | ELC | CB - Metro Core | CBMC CA SAN ELC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 1 | 2020-02-15 | 2020-05-15 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
ELCNEWAA02-ROUTER | CA | SAN | ELC | CB - Metro Core | CBMC CA SAN ELC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 1 | 2020-02-15 | 2020-07-31 |  | Active | Log | Upd | SN-0618 | Schedule Change | Approved | 2020-06-05 14:52 | Removing deferred projects that still remain in the POR and moving out activation dates due to various equipment delays
FED1BPRA01-ROUTER | CA | SAN | FED | CB - Metro Core | CBMC CA SAN FED ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-07-31 |  | Active | EP
FED1BPRA01-ROUTER | CA | SAN | FED | CB - Metro Core | CBMC CA SAN FED ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-04-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
FED1BPRA01-ROUTER | CA | SAN | FED | CB - Metro Core | CBMC CA SAN FED ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-06-20 |  | Active | Log | Upd | SN-0586 | Schedule Change | Approved | 2020-05-14 14:37 | Adjusting dates for CBMC POR Most of the changes are pushing activation dates out due to equipment delays
FED1BPRA01-ROUTER | CA | SAN | FED | CB - Metro Core | CBMC CA SAN FED ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-07-31 |  | Active | Log | Upd | SN-0654 | Schedule Change | Approved | 2020-06-14 18:38 | Changes to projects in the SE and CA regions due to material delays
VISTEWAA01-ROUTER | CA | SAN | VST | CB - Metro Core | CBMC CA SAN VST ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
VISTEWAA01-ROUTER | CA | SAN | VST | CB - Metro Core | CBMC CA SAN VST ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-04-15 | 2020-07-15 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
VISTEWAA01-ROUTER | CA | SAN | VST | CB - Metro Core | CBMC CA SAN VST ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
KSCYBSRA99-ROUTER | COR | NAT | KCY | CB - Metro Core | CBMC CE KAN KCY ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-05 | 2020-08-30 |  | Active | EP
KSCYBSRA99-ROUTER | COR | NAT | KCY | CB - Metro Core | CBMC CE KAN KCY ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-05 | 2020-04-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
KSCYBSRA99-ROUTER | COR | NAT | KCY | CB - Metro Core | CBMC CE KAN KCY ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-05 | 2020-08-30 |  | Active | Log | Upd | SN-0796 | Schedule Change | Approved | 2020-07-31 10:03 | Moving activation dates out for projects in the CA and SW regions due to various delays
sr01.gar.tul.ok-ROUTER | CE | TUL | GAR | CB - Metro Core | CBMC CE TUL GAR ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-04-15 | 2020-08-30 |  | Active | EP
sr01.gar.tul.ok-ROUTER | CE | TUL | GAR | CB - Metro Core | CBMC CE TUL GAR ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-04-15 | 2020-07-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
sr01.gar.tul.ok-ROUTER | CE | TUL | GAR | CB - Metro Core | CBMC CE TUL GAR ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-04-15 | 2020-08-30 |  | Active | Log | Upd | SN-0796 | Schedule Change | Approved | 2020-07-31 10:03 | Moving activation dates out for projects in the CA and SW regions due to various delays
sr01.owh.tul.ok-ROUTER | CE | TUL | OWA | CB - Metro Core | CBMC CE TUL OWA ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-04-15 | 2020-09-30 |  | Active | EP
sr01.owh.tul.ok-ROUTER | CE | TUL | OWA | CB - Metro Core | CBMC CE TUL OWA ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-04-15 | 2020-07-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
sr01.owh.tul.ok-ROUTER | CE | TUL | OWA | CB - Metro Core | CBMC CE TUL OWA ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-04-15 | 2020-08-31 |  | Active | Log | Upd | SN-0819 | Schedule Change | Approved | 2020-08-14 15:09 | POR Changes for CBMC
sr01.owh.tul.ok-ROUTER | CE | TUL | OWA | CB - Metro Core | CBMC CE TUL OWA ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-04-15 | 2020-09-30 |  | Active | Log | Upd | SN-0934 | Schedule Change | Approved | 2020-09-18 09:35 | Moving out activation dates due to delays
sr02.sap.tul.ok-ROUTER | CE | TUL | SAP | CB - Metro Core | CBMC CE TUL SAP ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
sr02.sap.tul.ok-ROUTER | CE | TUL | SAP | CB - Metro Core | CBMC CE TUL SAP ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-04-15 | 2020-07-15 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
sr02.sap.tul.ok-ROUTER | CE | TUL | SAP | CB - Metro Core | CBMC CE TUL SAP ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0771 | Schedule Change | Approved | 2020-07-20 09:31 | Adjusting POR activation months in CE SE and SW due to impacts from equipment delays
sr01.sap.tul.ok-ROUTER | CE | TUL | SAP | CB - Metro Core | CBMC CE TUL SAP ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-04-15 | 2020-09-30 |  | Active | EP
sr01.sap.tul.ok-ROUTER | CE | TUL | SAP | CB - Metro Core | CBMC CE TUL SAP ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-04-15 | 2020-07-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
sr01.sap.tul.ok-ROUTER | CE | TUL | SAP | CB - Metro Core | CBMC CE TUL SAP ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-04-15 | 2020-08-31 |  | Active | Log | Upd | SN-0819 | Schedule Change | Approved | 2020-08-14 15:09 | POR Changes for CBMC
sr01.sap.tul.ok-ROUTER | CE | TUL | SAP | CB - Metro Core | CBMC CE TUL SAP ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-04-15 | 2020-09-30 |  | Active | Log | Upd | SN-0934 | Schedule Change | Approved | 2020-09-18 09:35 | Moving out activation dates due to delays
sr01.wlh.okc.ok-ROUTER | CE | OKC | WLH | CB - Metro Core | CBMC CE OKC WLH ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-08-30 |  | Active | EP
sr01.wlh.okc.ok-ROUTER | CE | OKC | WLH | CB - Metro Core | CBMC CE OKC WLH ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-05-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
sr01.wlh.okc.ok-ROUTER | CE | OKC | WLH | CB - Metro Core | CBMC CE OKC WLH ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-07-31 |  | Active | Log | Upd | SN-0686 | New | Approved | 2020-06-22 10:17 | POR clean up for the CE and SE regions Deleting duplicate entries and adusting activation months
sr01.wlh.okc.ok-ROUTER | CE | OKC | WLH | CB - Metro Core | CBMC CE OKC WLH ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-08-30 |  | Active | Log | Upd | SN-0796 | Schedule Change | Approved | 2020-07-31 10:03 | Moving activation dates out for projects in the CA and SW regions due to various delays
ENFDBSPA01.CT.RI-ROUTER | NE | CON | ENF | CB - Metro Core | CBMC NE CON ENF ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 1 | 2020-01-15 | 2020-08-31 |  | Active | EP
ENFDBSPA01.CT.RI-ROUTER | NE | CON | ENF | CB - Metro Core | CBMC NE CON ENF ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-04-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
ENFDBSPA01.CT.RI-ROUTER | NE | CON | ENF | CB - Metro Core | CBMC NE CON ENF ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-05-20 |  | Active | Log | Upd | SN-0478 | Schedule Change | Approved | 2020-04-24 14:37 | Adjusting schedule dates across multpile PPMs
ENFDBSPA01.CT.RI-ROUTER | NE | CON | ENF | CB - Metro Core | CBMC NE CON ENF ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-06-30 |  | Active | Log | Upd | SN-0618 | Schedule Change | Approved | 2020-06-05 14:52 | Removing deferred projects that still remain in the POR and moving out activation dates due to various equipment delays
ENFDBSPA01.CT.RI-ROUTER | NE | CON | ENF | CB - Metro Core | CBMC NE CON ENF ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-08-31 |  | Active | Log | Upd | SN-0782 | Schedule Change | Approved | 2020-07-27 09:31 | Adjusting activation dates due to equipment delays and removing POR records for deferred projects for CBMC
ENFDBSPA01.CT.RI-ROUTER | NE | CON | ENF | CB - Metro Core | CBMC NE CON ENF ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 1 | 2020-01-15 | 2020-08-31 |  | Active | Log | Upd | SN-0944 | Schedule Change | Approved | 2020-09-25 09:33 | Pushing out activation dates due to delays and deleting records as POR cleanup
MNCHBSPA01.CT.RI-ROUTER | NE | CON | MAN | CB - Metro Core | CBMC NE CON MAN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 1 | 2020-01-15 | 2020-08-31 |  | Active | EP
MNCHBSPA01.CT.RI-ROUTER | NE | CON | MAN | CB - Metro Core | CBMC NE CON MAN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-04-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
MNCHBSPA01.CT.RI-ROUTER | NE | CON | MAN | CB - Metro Core | CBMC NE CON MAN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 1 | 2020-01-15 | 2020-04-15 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
MNCHBSPA01.CT.RI-ROUTER | NE | CON | MAN | CB - Metro Core | CBMC NE CON MAN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 1 | 2020-01-15 | 2020-05-20 |  | Active | Log | Upd | SN-0478 | Schedule Change | Approved | 2020-04-24 14:37 | Adjusting schedule dates across multpile PPMs
MNCHBSPA01.CT.RI-ROUTER | NE | CON | MAN | CB - Metro Core | CBMC NE CON MAN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 1 | 2020-01-15 | 2020-06-30 |  | Active | Log | Upd | SN-0618 | Schedule Change | Approved | 2020-06-05 14:52 | Removing deferred projects that still remain in the POR and moving out activation dates due to various equipment delays
MNCHBSPA01.CT.RI-ROUTER | NE | CON | MAN | CB - Metro Core | CBMC NE CON MAN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 1 | 2020-01-15 | 2020-08-31 |  | Active | Log | Upd | SN-0782 | Schedule Change | Approved | 2020-07-27 09:31 | Adjusting activation dates due to equipment delays and removing POR records for deferred projects for CBMC
MNCHCBSA02.CT.RI-ROUTER | NE | CON | MAN | CB - Metro Core | CBMC NE CON MAN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
MNCHCBSA02.CT.RI-ROUTER | NE | CON | MAN | CB - Metro Core | CBMC NE CON MAN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-07-15 | 2020-10-15 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
MNCHCBSA02.CT.RI-ROUTER | NE | CON | MAN | CB - Metro Core | CBMC NE CON MAN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 1 | 2020-07-15 | 2020-10-15 |  | Deleted | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
MNCHCBSA02.CT.RI-ROUTER | NE | CON | MAN | CB - Metro Core | CBMC NE CON MAN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0618 | Schedule Change | Approved | 2020-06-05 14:52 | Removing deferred projects that still remain in the POR and moving out activation dates due to various equipment delays
MNCHCBSA01.CT.RI-ROUTER | NE | CON | MAN | CB - Metro Core | CBMC NE CON MAN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
MNCHCBSA01.CT.RI-ROUTER | NE | CON | MAN | CB - Metro Core | CBMC NE CON MAN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-07-15 | 2020-10-15 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
MNCHCBSA01.CT.RI-ROUTER | NE | CON | MAN | CB - Metro Core | CBMC NE CON MAN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 1 | 2020-07-15 | 2020-10-15 |  | Deleted | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
MNCHCBSA01.CT.RI-ROUTER | NE | CON | MAN | CB - Metro Core | CBMC NE CON MAN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
MNCHCBSA01.CT.RI-ROUTER | NE | CON | MAN | CB - Metro Core | CBMC NE CON MAN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0618 | Schedule Change | Approved | 2020-06-05 14:52 | Removing deferred projects that still remain in the POR and moving out activation dates due to various equipment delays
PROVCBSA01.RI.RI-ROUTER | NE | RHD | PRV | CB - Metro Core | CBMC NE RHD PRV ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
PROVCBSA01.RI.RI-ROUTER | NE | RHD | PRV | CB - Metro Core | CBMC NE RHD PRV ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-04-15 | 2020-07-15 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
PROVCBSA01.RI.RI-ROUTER | NE | RHD | PRV | CB - Metro Core | CBMC NE RHD PRV ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-06-15 | 2020-09-20 |  | Deleted | Log | Upd | SN-0478 | Schedule Change | Approved | 2020-04-24 14:37 | Adjusting schedule dates across multpile PPMs
PROVCBSA01.RI.RI-ROUTER | NE | RHD | PRV | CB - Metro Core | CBMC NE RHD PRV ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
RMNDCBSA01.RI.RI-ROUTER | NE | RHD | RMD | CB - Metro Core | CBMC NE RHD RMD ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-06-30 |  | Active | EP
RMNDCBSA01.RI.RI-ROUTER | NE | RHD | RMD | CB - Metro Core | CBMC NE RHD RMD ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-05-20 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
RMNDCBSA01.RI.RI-ROUTER | NE | RHD | RMD | CB - Metro Core | CBMC NE RHD RMD ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-06-30 |  | Active | Log | Upd | SN-0618 | Schedule Change | Approved | 2020-06-05 14:52 | Removing deferred projects that still remain in the POR and moving out activation dates due to various equipment delays
GAINBSRA02.GA.AT-ROUTER | SE | GAN | GNS | CB - Metro Core | CBMC SE GAN GNS ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-03-15 | 2020-07-31 |  | Active | EP
GAINBSRA02.GA.AT-ROUTER | SE | GAN | GNS | CB - Metro Core | CBMC SE GAN GNS ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-03-15 | 2020-06-01 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
GAINBSRA02.GA.AT-ROUTER | SE | GAN | GNS | CB - Metro Core | CBMC SE GAN GNS ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-03-15 | 2020-07-31 |  | Active | Log | Upd | SN-0737 | Schedule Change | Approved | 2020-07-10 10:12 | Pushing out activation dates in the SER due to equipment delays Deleting duplicate record in CE and pushing out activation month due to site readiness delays
BTRGLA741AW-24BTRMTC7750X01-ROUTER | SE | BTR | BTR | CB - Metro Core | CBMC SE BTR BTR ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-08-31 |  | Active | EP
BTRGLA741AW-24BTRMTC7750X01-ROUTER | SE | BTR | BTR | CB - Metro Core | CBMC SE BTR BTR ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-05-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
BTRGLA741AW-24BTRMTC7750X01-ROUTER | SE | BTR | BTR | CB - Metro Core | CBMC SE BTR BTR ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-08-31 |  | Active | Log | Upd | SN-0618 | Schedule Change | Approved | 2020-06-05 14:52 | Removing deferred projects that still remain in the POR and moving out activation dates due to various equipment delays
LFY-NEW-P02-ROUTER | SE | LFY | LFY | CB - Metro Core | CBMC SE LFY LFY ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-06-01 |  | Active | EP
LFY-NEW-P02-ROUTER | SE | LFY | LFY | CB - Metro Core | CBMC SE LFY LFY ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-04-01 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
LFY-NEW-P02-ROUTER | SE | LFY | LFY | CB - Metro Core | CBMC SE LFY LFY ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-06-01 |  | Active | Log | Upd | SN-0419 | Schedule Change | Approved | 2020-04-02 09:36 | Updates driven by field audit and material delays
LFYTLAUO1BW-42LAFMTC7750X02-ROUTER | SE | LFY | LFY | CB - Metro Core | CBMC SE LFY LFY ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-06-30 |  | Active | EP
LFYTLAUO1BW-42LAFMTC7750X02-ROUTER | SE | LFY | LFY | CB - Metro Core | CBMC SE LFY LFY ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-05-01 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
LFYTLAUO1BW-42LAFMTC7750X02-ROUTER | SE | LFY | LFY | CB - Metro Core | CBMC SE LFY LFY ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-06-30 |  | Active | Log | Upd | SN-0654 | Schedule Change | Approved | 2020-06-14 18:38 | Changes to projects in the SE and CA regions due to material delays
NWORLAUI1AW-ROUTER | SE | NOR | NOE | CB - Metro Core | CBMC SE NOR NOE ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-06-30 |  | Active | EP
NWORLAUI1AW-ROUTER | SE | NOR | NOE | CB - Metro Core | CBMC SE NOR NOE ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-04-01 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
NWORLAUI1AW-ROUTER | SE | NOR | NOE | CB - Metro Core | CBMC SE NOR NOE ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-05-01 |  | Active | Log | Upd | SN-0419 | Schedule Change | Approved | 2020-04-02 09:36 | Updates driven by field audit and material delays
NWORLAUI1AW-ROUTER | SE | NOR | NOE | CB - Metro Core | CBMC SE NOR NOE ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-06-30 |  | Active | Log | Upd | SN-0654 | Schedule Change | Approved | 2020-06-14 18:38 | Changes to projects in the SE and CA regions due to material delays
BTRILA572AW-24STHHUB7750X02-ROUTER | SE | BTR | SPC | CB - Metro Core | CBMC SE BTR SPC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-04-15 | 2020-09-30 |  | Active | EP
BTRILA572AW-24STHHUB7750X02-ROUTER | SE | BTR | SPC | CB - Metro Core | CBMC SE BTR SPC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-04-15 | 2020-07-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
BTRILA572AW-24STHHUB7750X02-ROUTER | SE | BTR | SPC | CB - Metro Core | CBMC SE BTR SPC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-04-15 | 2020-09-30 |  | Active | Log | Upd | SN-0618 | Schedule Change | Approved | 2020-06-05 14:52 | Removing deferred projects that still remain in the POR and moving out activation dates due to various equipment delays
PNS-NEW-P02-ROUTER | SE | GCT | PNS | CB - Metro Core | CBMC SE GCT PNS ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-06-01 |  | Active | EP
PNS-NEW-P02-ROUTER | SE | GCT | PNS | CB - Metro Core | CBMC SE GCT PNS ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-04-01 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
PNS-NEW-P02-ROUTER | SE | GCT | PNS | CB - Metro Core | CBMC SE GCT PNS ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-06-01 |  | Active | Log | Upd | SN-0419 | Schedule Change | Approved | 2020-04-02 09:36 | Updates driven by field audit and material delays
PNSCBSRA02.PN.AT-ROUTER | SE | GCT | PNS | CB - Metro Core | CBMC SE GCT PNS ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-06-15 | 2020-07-20 |  | Active | EP
PNSCBSRA02.PN.AT-ROUTER | SE | GCT | PNS | CB - Metro Core | CBMC SE GCT PNS ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-06-15 | 2020-05-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
PNSCBSRA02.PN.AT-ROUTER | SE | GCT | PNS | CB - Metro Core | CBMC SE GCT PNS ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-06-15 | 2020-07-20 |  | Active | Log | Upd | SN-0586 | Schedule Change | Approved | 2020-05-14 14:37 | Adjusting dates for CBMC POR Most of the changes are pushing activation dates out due to equipment delays
MACNBSRA01.mc.at.cox.net-ROUTER | SE | MGA | MCN | CB - Metro Core | CBMC SE MGA MCN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-03-15 | 2020-09-30 |  | Active | EP
MACNBSRA01.mc.at.cox.net-ROUTER | SE | MGA | MCN | CB - Metro Core | CBMC SE MGA MCN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-03-15 | 2020-06-01 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
MACNBSRA01.mc.at.cox.net-ROUTER | SE | MGA | MCN | CB - Metro Core | CBMC SE MGA MCN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-03-15 | 2020-09-30 |  | Active | Log | Upd | SN-0618 | Schedule Change | Approved | 2020-06-05 14:52 | Removing deferred projects that still remain in the POR and moving out activation dates due to various equipment delays
TUCSSYSA01-ROUTER | SW | ARZ | TUC | CB - Metro Core | CBMC SW ARZ TUC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-09-30 |  | Active | EP
TUCSSYSA01-ROUTER | SW | ARZ | TUC | CB - Metro Core | CBMC SW ARZ TUC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-04-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
TUCSSYSA01-ROUTER | SW | ARZ | TUC | CB - Metro Core | CBMC SW ARZ TUC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-04-15 |  | Active | Log | Upd | SN-0419 | Schedule Change | Approved | 2020-04-02 09:36 | Updates driven by field audit and material delays
TUCSSYSA01-ROUTER | SW | ARZ | TUC | CB - Metro Core | CBMC SW ARZ TUC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-06-30 |  | Active | Log | Upd | SN-0618 | Schedule Change | Approved | 2020-06-05 14:52 | Removing deferred projects that still remain in the POR and moving out activation dates due to various equipment delays
TUCSSYSA01-ROUTER | SW | ARZ | TUC | CB - Metro Core | CBMC SW ARZ TUC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-07-30 |  | Active | Log | Upd | SN-0701 | Schedule Change | Approved | 2020-07-02 11:45 | Pushing out activation dates in CE CA VA and SW due to equipment delays
TUCSSYSA01-ROUTER | SW | ARZ | TUC | CB - Metro Core | CBMC SW ARZ TUC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-09-30 |  | Active | Log | Upd | SN-0771 | Schedule Change | Approved | 2020-07-20 09:31 | Adjusting POR activation months in CE SE and SW due to impacts from equipment delays
SWSTA01.LV.LV.COX.NET-ROUTER | SW | LAS | BLU | CB - Metro Core | CBMC SW LAS BLU ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  | 2020-01-15 |  |  | Deleted | EP
SWSTA01.LV.LV.COX.NET-ROUTER | SW | LAS | BLU | CB - Metro Core | CBMC SW LAS BLU ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  | 2020-01-15 |  |  | Deleted | Log | Del | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
SESTCORA01.LV.LV.COX.NET-ROUTER | SW | LAS | HEN | CB - Metro Core | CBMC SW LAS HEN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 1 | 2020-01-15 | 2020-09-30 |  | Active | EP
SESTCORA01.LV.LV.COX.NET-ROUTER | SW | LAS | HEN | CB - Metro Core | CBMC SW LAS HEN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-04-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
SESTCORA01.LV.LV.COX.NET-ROUTER | SW | LAS | HEN | CB - Metro Core | CBMC SW LAS HEN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-05-15 |  | Active | Log | Upd | SN-0419 | Schedule Change | Approved | 2020-04-02 09:36 | Updates driven by field audit and material delays
SESTCORA01.LV.LV.COX.NET-ROUTER | SW | LAS | HEN | CB - Metro Core | CBMC SW LAS HEN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-07-20 |  | Active | Log | Upd | SN-0586 | Schedule Change | Approved | 2020-05-14 14:37 | Adjusting dates for CBMC POR Most of the changes are pushing activation dates out due to equipment delays
SESTCORA01.LV.LV.COX.NET-ROUTER | SW | LAS | HEN | CB - Metro Core | CBMC SW LAS HEN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 1 | 2020-01-15 | 2020-07-20 |  | Active | Log | Upd | SN-0599 | Schedule Change | Approved | 2020-05-20 16:50 | Adding a missing POR entry for SWR adjusting qty for projects as well as activation dates
SESTCORA01.LV.LV.COX.NET-ROUTER | SW | LAS | HEN | CB - Metro Core | CBMC SW LAS HEN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 1 | 2020-01-15 | 2020-09-30 |  | Active | Log | Upd | SN-0771 | Schedule Change | Approved | 2020-07-20 09:31 | Adjusting POR activation months in CE SE and SW due to impacts from equipment delays
NWSTSYSA03.LV.LV-ROUTER | SW | LAS | TEN | CB - Metro Core | CBMC SW LAS TEN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
NWSTSYSA03.LV.LV-ROUTER | SW | LAS | TEN | CB - Metro Core | CBMC SW LAS TEN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-08-15 | 2020-11-15 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
NWSTSYSA03.LV.LV-ROUTER | SW | LAS | TEN | CB - Metro Core | CBMC SW LAS TEN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0419 | Schedule Change | Approved | 2020-04-02 09:36 | Updates driven by field audit and material delays
NWSTSYSA03.LV.LV-ROUTER | SW | LAS | TEN | CB - Metro Core | CBMC SW LAS TEN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-05-20 |  | Deleted | Log | Undel | SN-0478 | Schedule Change | Approved | 2020-04-24 14:37 | Adjusting schedule dates across multpile PPMs
NWSTSYSA03.LV.LV-ROUTER | SW | LAS | TEN | CB - Metro Core | CBMC SW LAS TEN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-01-15 | 2020-07-20 |  | Deleted | Log | Upd | SN-0586 | Schedule Change | Approved | 2020-05-14 14:37 | Adjusting dates for CBMC POR Most of the changes are pushing activation dates out due to equipment delays
NWSTSYSA03.LV.LV-ROUTER | SW | LAS | TEN | CB - Metro Core | CBMC SW LAS TEN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 1 | 2020-01-15 | 2020-07-20 |  | Deleted | Log | Upd | SN-0599 | Schedule Change | Approved | 2020-05-20 16:50 | Adding a missing POR entry for SWR adjusting qty for projects as well as activation dates
NWSTSYSA03.LV.LV-ROUTER | SW | LAS | TEN | CB - Metro Core | CBMC SW LAS TEN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0611 | Schedule Change | Approved | 2020-05-29 15:06 | Adjusting POR for CBMC
CHSKVAKV43W-A701KV7750-ROUTER | VA | HRD | GBR | CB - Metro Core | CBMC VA HRD GBR ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-04-15 | 2020-07-01 |  | Deleted | EP
CHSKVAKV43W-A701KV7750-ROUTER | VA | HRD | GBR | CB - Metro Core | CBMC VA HRD GBR ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-04-15 | 2020-07-01 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
CHSKVAKV43W-A701KV7750-ROUTER | VA | HRD | GBR | CB - Metro Core | CBMC VA HRD GBR ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0213 | Scope Change | Approved | 2020-01-24 14:43 | Determined that SR 7 is no longer needed at the Greenbriar location Will be reallocating that router to Butler faciility in Q2 Project needs to be loaded in EPS Will not be availble to add to POR until next CCRB
NWNWCRBSRA7750-1-ROUTER | VA | HRD | NWP | CB - Metro Core | CBMC VA HRD NWP ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-03-15 | 2020-06-01 |  | Active | EP
NWNWCRBSRA7750-1-ROUTER | VA | HRD | NWP | CB - Metro Core | CBMC VA HRD NWP ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-03-15 | 2020-06-01 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
NRFLVAJTBSRA7750-1-ROUTER | VA | HRD | NRF | CB - Metro Core | CBMC VA HRD NRF ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-03-15 | 2020-07-30 |  | Active | EP
NRFLVAJTBSRA7750-1-ROUTER | VA | HRD | NRF | CB - Metro Core | CBMC VA HRD NRF ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-03-15 | 2020-06-01 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
NRFLVAJTBSRA7750-1-ROUTER | VA | HRD | NRF | CB - Metro Core | CBMC VA HRD NRF ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-03-15 | 2020-07-30 |  | Active | Log | Upd | SN-0701 | Schedule Change | Approved | 2020-07-02 11:45 | Pushing out activation dates in CE CA VA and SW due to equipment delays
FRFYVA0631W-ROUTER | VA | NVA | FLK | CB - Metro Core | CBMC VA NVA FLK ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-07-30 |  | Active | EP
FRFYVA0631W-ROUTER | VA | NVA | FLK | CB - Metro Core | CBMC VA NVA FLK ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-05-01 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
FRFYVA0631W-ROUTER | VA | NVA | FLK | CB - Metro Core | CBMC VA NVA FLK ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-06-12 |  | Active | Log | Upd | SN-0528 | Schedule Change | Canceled | 2020-05-06 16:46 | Updating POR for CE and VA
FRFYVA0631W-ROUTER | VA | NVA | FLK | CB - Metro Core | CBMC VA NVA FLK ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-06-15 |  | Active | Log | Upd | SN-0586 | Schedule Change | Approved | 2020-05-14 14:37 | Adjusting dates for CBMC POR Most of the changes are pushing activation dates out due to equipment delays
FRFYVA0631W-ROUTER | VA | NVA | FLK | CB - Metro Core | CBMC VA NVA FLK ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-07-30 |  | Active | Log | Upd | SN-0701 | Schedule Change | Approved | 2020-07-02 11:45 | Pushing out activation dates in CE CA VA and SW due to equipment delays
RONLVA3100W-A702317750-ROUTER | VA | ROA | RON | CB - Metro Core | CBMC VA ROA RON ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-08-31 |  | Active | EP
RONLVA3100W-A702317750-ROUTER | VA | ROA | RON | CB - Metro Core | CBMC VA ROA RON ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-05-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
RONLVA3100W-A702317750-ROUTER | VA | ROA | RON | CB - Metro Core | CBMC VA ROA RON ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-06-30 |  | Active | Log | Upd | SN-0618 | Schedule Change | Approved | 2020-06-05 14:52 | Removing deferred projects that still remain in the POR and moving out activation dates due to various equipment delays
RONLVA3100W-A702317750-ROUTER | VA | ROA | RON | CB - Metro Core | CBMC VA ROA RON ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-08-31 |  | Active | Log | Upd | SN-0782 | Schedule Change | Approved | 2020-07-27 09:31 | Adjusting activation dates due to equipment delays and removing POR records for deferred projects for CBMC
CB Transport - New Router Aliso Viejo - AVJ - Optics | CA | ORG | AVJ | CB - Metro Core | CBMC CA ORG AVJ Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 |  |  |  |  | Deleted | EP
CB Transport - New Router Aliso Viejo - AVJ - Optics | CA | ORG | AVJ | CB - Metro Core | CBMC CA ORG AVJ Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-04-15 | 2020-06-20 |  | Deleted | Log | Upd | SN-0586 | Schedule Change | Approved | 2020-05-14 14:37 | Adjusting dates for CBMC POR Most of the changes are pushing activation dates out due to equipment delays
CB Transport - New Router Aliso Viejo - AVJ - Optics | CA | ORG | AVJ | CB - Metro Core | CBMC CA ORG AVJ Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-04-15 | 2020-07-30 |  | Deleted | Log | Upd | SN-0701 | Schedule Change | Approved | 2020-07-02 11:45 | Pushing out activation dates in CE CA VA and SW due to equipment delays
CB Transport - New Router Aliso Viejo - AVJ - Optics | CA | ORG | AVJ | CB - Metro Core | CBMC CA ORG AVJ Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 |  |  |  |  | Deleted | Log | Del | SN-0782 | Schedule Change | Approved | 2020-07-27 09:31 | Adjusting activation dates due to equipment delays and removing POR records for deferred projects for CBMC
Lafayette-OCML-IXR | SE | LFY | LFY | CB - Metro Core | CBMC SE LFY LFY OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
Lafayette-OCML-IXR | SE | LFY | LFY | CB - Metro Core | CBMC SE LFY LFY OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
Peoria-OCML-IXR | SW | ARZ | PEO | CB - Metro Core | CBMC SW ARZ PEO OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
Peoria-OCML-IXR | SW | ARZ | PEO | CB - Metro Core | CBMC SW ARZ PEO OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0419 | Schedule Change | Approved | 2020-04-02 09:36 | Updates driven by field audit and material delays
Pinal County-OCML-IXR | SW | ARZ | PNL | CB - Metro Core | CBMC SW ARZ PNL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-09-30 |  | Active | EP
Pinal County-OCML-IXR | SW | ARZ | PNL | CB - Metro Core | CBMC SW ARZ PNL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-07-20 |  | Active | Log | Upd | SN-0586 | Schedule Change | Approved | 2020-05-14 14:37 | Adjusting dates for CBMC POR Most of the changes are pushing activation dates out due to equipment delays
Pinal County-OCML-IXR | SW | ARZ | PNL | CB - Metro Core | CBMC SW ARZ PNL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-09-30 |  | Active | Log | Upd | SN-0701 | Schedule Change | Approved | 2020-07-02 11:45 | Pushing out activation dates in CE CA VA and SW due to equipment delays
S Scottsdale-OCML-IXR | SW | ARZ | SSC | CB - Metro Core | CBMC SW ARZ SSC OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-08-31 |  | Active | EP
S Scottsdale-OCML-IXR | SW | ARZ | SSC | CB - Metro Core | CBMC SW ARZ SSC OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-07-20 |  | Active | Log | Upd | SN-0586 | Schedule Change | Approved | 2020-05-14 14:37 | Adjusting dates for CBMC POR Most of the changes are pushing activation dates out due to equipment delays
S Scottsdale-OCML-IXR | SW | ARZ | SSC | CB - Metro Core | CBMC SW ARZ SSC OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-08-31 |  | Active | Log | Upd | SN-0796 | Schedule Change | Approved | 2020-07-31 10:03 | Moving activation dates out for projects in the CA and SW regions due to various delays
Rancho Santa Margarita (RSM)-OCML-IXR | CA | ORG | RSM | CB - Metro Core | CBMC CA ORG RSM OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | EP
Rancho Santa Margarita (RSM)-OCML-IXR | CA | ORG | RSM | CB - Metro Core | CBMC CA ORG RSM OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0132 | Schedule Change | Approved | 2020-02-06 11:03 | All IXR projects for CBMC In January were moved to March in order lighten January budget Financials have already been updated to reflect the change This is an adminstrative CR
Rancho Santa Margarita (RSM)-OCML-IXR | CA | ORG | RSM | CB - Metro Core | CBMC CA ORG RSM OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
CB Transport - New Router Aliso Viejo - RSM - Optics | CA | ORG | RSM | CB - Metro Core | CBMC CA ORG RSM Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 |  |  |  |  | Deleted | EP
CB Transport - New Router Aliso Viejo - RSM - Optics | CA | ORG | RSM | CB - Metro Core | CBMC CA ORG RSM Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-04-15 | 2020-06-20 |  | Deleted | Log | Upd | SN-0586 | Schedule Change | Approved | 2020-05-14 14:37 | Adjusting dates for CBMC POR Most of the changes are pushing activation dates out due to equipment delays
CB Transport - New Router Aliso Viejo - RSM - Optics | CA | ORG | RSM | CB - Metro Core | CBMC CA ORG RSM Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-04-15 | 2020-07-30 |  | Deleted | Log | Upd | SN-0701 | Schedule Change | Approved | 2020-07-02 11:45 | Pushing out activation dates in CE CA VA and SW due to equipment delays
CB Transport - New Router Aliso Viejo - RSM - Optics | CA | ORG | RSM | CB - Metro Core | CBMC CA ORG RSM Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 |  |  |  |  | Deleted | Log | Del | SN-0782 | Schedule Change | Approved | 2020-07-27 09:31 | Adjusting activation dates due to equipment delays and removing POR records for deferred projects for CBMC
Chula Vista-OCML-IXR | CA | SAN | CHU | CB - Metro Core | CBMC CA SAN CHU OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
Chula Vista-OCML-IXR | CA | SAN | CHU | CB - Metro Core | CBMC CA SAN CHU OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
Downtown-OCML-IXR | CA | SAN | DWN | CB - Metro Core | CBMC CA SAN DWN OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
Downtown-OCML-IXR | CA | SAN | DWN | CB - Metro Core | CBMC CA SAN DWN OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Deleted | Log | Upd | SN-0132 | Schedule Change | Approved | 2020-02-06 11:03 | All IXR projects for CBMC In January were moved to March in order lighten January budget Financials have already been updated to reflect the change This is an adminstrative CR
Downtown-OCML-IXR | CA | SAN | DWN | CB - Metro Core | CBMC CA SAN DWN OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Deleted | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
Downtown-OCML-IXR | CA | SAN | DWN | CB - Metro Core | CBMC CA SAN DWN OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
CB Transport - New Router Chula Vista - ELC - Optics | CA | SAN | ELC | CB - Metro Core | CBMC CA SAN ELC Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-06-15 | 2020-08-31 |  | Active | EP
CB Transport - New Router Chula Vista - ELC - Optics | CA | SAN | ELC | CB - Metro Core | CBMC CA SAN ELC Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-06-15 | 2020-08-31 |  | Active | Log | Upd | SN-0796 | Schedule Change | Approved | 2020-07-31 10:03 | Moving activation dates out for projects in the CA and SW regions due to various delays
CB Transport - New Router Escondido, Vista - ELC - Card Add | CA | SAN | ELC | CB - Metro Core | CBMC CA SAN ELC Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-03-15 | 2020-04-15 |  | Active | EP
El Cajon-OCML-IXR | CA | SAN | ELC | CB - Metro Core | CBMC CA SAN ELC OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-07-31 |  | Active | EP
El Cajon-OCML-IXR | CA | SAN | ELC | CB - Metro Core | CBMC CA SAN ELC OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-07-31 |  | Active | Log | Upd | SN-0618 | Schedule Change | Approved | 2020-06-05 14:52 | Removing deferred projects that still remain in the POR and moving out activation dates due to various equipment delays
CB Transport - New Router Escondido - ESC - Optics | CA | SAN | ESC | CB - Metro Core | CBMC CA SAN ESC Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-03-15 | 2020-07-31 |  | Active | EP
CB Transport - New Router Escondido - ESC - Optics | CA | SAN | ESC | CB - Metro Core | CBMC CA SAN ESC Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-03-15 | 2020-06-20 |  | Active | Log | Upd | SN-0586 | Schedule Change | Approved | 2020-05-14 14:37 | Adjusting dates for CBMC POR Most of the changes are pushing activation dates out due to equipment delays
CB Transport - New Router Escondido - ESC - Optics | CA | SAN | ESC | CB - Metro Core | CBMC CA SAN ESC Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-03-15 | 2020-07-31 |  | Active | Log | Upd | SN-0701 | Schedule Change | Approved | 2020-07-02 11:45 | Pushing out activation dates in CE CA VA and SW due to equipment delays
Escondido-OCML-IXR | CA | SAN | ESC | CB - Metro Core | CBMC CA SAN ESC OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
Escondido-OCML-IXR | CA | SAN | ESC | CB - Metro Core | CBMC CA SAN ESC OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
CB Transport - New Router Chula Vista - FED - Optics | CA | SAN | FED | CB - Metro Core | CBMC CA SAN FED Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-06-15 | 2020-08-31 |  | Active | EP
CB Transport - New Router Chula Vista - FED - Optics | CA | SAN | FED | CB - Metro Core | CBMC CA SAN FED Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-06-15 | 2020-08-31 |  | Active | Log | Upd | SN-0796 | Schedule Change | Approved | 2020-07-31 10:03 | Moving activation dates out for projects in the CA and SW regions due to various delays
CB Transport - New Router Escondido, Vista - FED - Card Add | CA | SAN | FED | CB - Metro Core | CBMC CA SAN FED Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-03-15 | 2020-04-15 |  | Active | EP
CB Transport - New Router Escondido, Vista - FED - Chassis Add | CA | SAN | FED | CB - Metro Core | CBMC CA SAN FED Cisco M6_M15 Chassis Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 1 | 2020-01-01 | 2020-04-15 |  | Active | EP
Federal-OCML-IXR | CA | SAN | FED | CB - Metro Core | CBMC CA SAN FED OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-06-30 |  | Active | EP
Federal-OCML-IXR | CA | SAN | FED | CB - Metro Core | CBMC CA SAN FED OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-06-30 |  | Active | Log | Upd | SN-0618 | Schedule Change | Approved | 2020-06-05 14:52 | Removing deferred projects that still remain in the POR and moving out activation dates due to various equipment delays
Oceanside-OCML-IXR | CA | SAN | OCE | CB - Metro Core | CBMC CA SAN OCE OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | EP
Oceanside-OCML-IXR | CA | SAN | OCE | CB - Metro Core | CBMC CA SAN OCE OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0132 | Schedule Change | Approved | 2020-02-06 11:03 | All IXR projects for CBMC In January were moved to March in order lighten January budget Financials have already been updated to reflect the change This is an adminstrative CR
Oceanside-OCML-IXR | CA | SAN | OCE | CB - Metro Core | CBMC CA SAN OCE OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
Poway-OCML-IXR | CA | SAN | PWY | CB - Metro Core | CBMC CA SAN PWY OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | EP
Poway-OCML-IXR | CA | SAN | PWY | CB - Metro Core | CBMC CA SAN PWY OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0132 | Schedule Change | Approved | 2020-02-06 11:03 | All IXR projects for CBMC In January were moved to March in order lighten January budget Financials have already been updated to reflect the change This is an adminstrative CR
Poway-OCML-IXR | CA | SAN | PWY | CB - Metro Core | CBMC CA SAN PWY OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
CB Transport - New Router Vista - VST - Optics | CA | SAN | VST | CB - Metro Core | CBMC CA SAN VST Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-03-15 | 2020-04-15 |  | Active | EP
sr01.bra.tul.ok-ROUTER | CE | TUL | BRD | CB - Metro Core | CBMC CE TUL BRD ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-07-31 |  | Active | EP
sr01.bra.tul.ok-ROUTER | CE | TUL | BRD | CB - Metro Core | CBMC CE TUL BRD ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-05-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
sr01.bra.tul.ok-ROUTER | CE | TUL | BRD | CB - Metro Core | CBMC CE TUL BRD ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-07-31 |  | Active | Log | Upd | SN-0686 | New | Approved | 2020-06-22 10:17 | POR clean up for the CE and SE regions Deleting duplicate entries and adusting activation months
CB Transport - New Router North - NTH - Optics | SE | BTR | NTH | CB - Metro Core | CBMC SE BTR NTH Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-04-15 | 2020-05-15 |  | Active | EP
CB Transport - New Router St Charles - STC - Card Add | SE | BTR | STC | CB - Metro Core | CBMC SE BTR STC Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-15 | 2020-05-15 |  | Active | EP
Bell-OCML-IXR | SW | ARZ | BEL | CB - Metro Core | CBMC SW ARZ BEL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-07-20 |  | Active | EP
Bell-OCML-IXR | SW | ARZ | BEL | CB - Metro Core | CBMC SW ARZ BEL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-05-15 |  | Active | Log | Upd | SN-0419 | Schedule Change | Approved | 2020-04-02 09:36 | Updates driven by field audit and material delays
Bell-OCML-IXR | SW | ARZ | BEL | CB - Metro Core | CBMC SW ARZ BEL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-07-20 |  | Active | Log | Upd | SN-0586 | Schedule Change | Approved | 2020-05-14 14:37 | Adjusting dates for CBMC POR Most of the changes are pushing activation dates out due to equipment delays
Buckeye-OCML-IXR | SW | ARZ | BUK | CB - Metro Core | CBMC SW ARZ BUK OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-07-20 |  | Active | EP
Buckeye-OCML-IXR | SW | ARZ | BUK | CB - Metro Core | CBMC SW ARZ BUK OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0132 | Schedule Change | Approved | 2020-02-06 11:03 | All IXR projects for CBMC In January were moved to March in order lighten January budget Financials have already been updated to reflect the change This is an adminstrative CR
Buckeye-OCML-IXR | SW | ARZ | BUK | CB - Metro Core | CBMC SW ARZ BUK OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
Buckeye-OCML-IXR | SW | ARZ | BUK | CB - Metro Core | CBMC SW ARZ BUK OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-07-20 |  | Active | Log | Upd | SN-0586 | Schedule Change | Approved | 2020-05-14 14:37 | Adjusting dates for CBMC POR Most of the changes are pushing activation dates out due to equipment delays
CB Transport - New Router Chandler/McDowellCORA - CHD - Card Add | SW | ARZ | CHD | CB - Metro Core | CBMC SW ARZ CHD Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-08-15 | 2020-09-15 |  | Active | EP
CB Transport - New Router Tucson, Fowler - CHD - Card Add | SW | ARZ | CHD | CB - Metro Core | CBMC SW ARZ CHD Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-01 | 2020-01-15 |  | Deleted | EP
CB Transport - New Router Fowler - CHD - Optics | SW | ARZ | CHD | CB - Metro Core | CBMC SW ARZ CHD Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-05-15 | 2020-07-15 |  | Active | EP
CB Transport - New Router McDowell - CHD - Optics | SW | ARZ | CHD | CB - Metro Core | CBMC SW ARZ CHD Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-02-14 | 2020-04-15 |  | Active | EP
CB Transport - New Router South Scottsdale - CHD - Optics | SW | ARZ | CHD | CB - Metro Core | CBMC SW ARZ CHD Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-05-15 | 2020-06-15 |  | Deleted | EP
Chandler-OCML-IXR | SW | ARZ | CHD | CB - Metro Core | CBMC SW ARZ CHD OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-08-31 |  | Active | EP
Chandler-OCML-IXR | SW | ARZ | CHD | CB - Metro Core | CBMC SW ARZ CHD OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0132 | Schedule Change | Approved | 2020-02-06 11:03 | All IXR projects for CBMC In January were moved to March in order lighten January budget Financials have already been updated to reflect the change This is an adminstrative CR
Chandler-OCML-IXR | SW | ARZ | CHD | CB - Metro Core | CBMC SW ARZ CHD OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
Chandler-OCML-IXR | SW | ARZ | CHD | CB - Metro Core | CBMC SW ARZ CHD OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-08-31 |  | Active | Log | Upd | SN-0618 | Schedule Change | Approved | 2020-06-05 14:52 | Removing deferred projects that still remain in the POR and moving out activation dates due to various equipment delays
E Mesa-OCML-IXR | SW | ARZ | MSA | CB - Metro Core | CBMC SW ARZ MSA OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-09-30 |  | Active | EP
E Mesa-OCML-IXR | SW | ARZ | MSA | CB - Metro Core | CBMC SW ARZ MSA OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0132 | Schedule Change | Approved | 2020-02-06 11:03 | All IXR projects for CBMC In January were moved to March in order lighten January budget Financials have already been updated to reflect the change This is an adminstrative CR
E Mesa-OCML-IXR | SW | ARZ | MSA | CB - Metro Core | CBMC SW ARZ MSA OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
E Mesa-OCML-IXR | SW | ARZ | MSA | CB - Metro Core | CBMC SW ARZ MSA OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-07-20 |  | Active | Log | Upd | SN-0586 | Schedule Change | Approved | 2020-05-14 14:37 | Adjusting dates for CBMC POR Most of the changes are pushing activation dates out due to equipment delays
E Mesa-OCML-IXR | SW | ARZ | MSA | CB - Metro Core | CBMC SW ARZ MSA OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-09-30 |  | Active | Log | Upd | SN-0771 | Schedule Change | Approved | 2020-07-20 09:31 | Adjusting POR activation months in CE SE and SW due to impacts from equipment delays
Fowler-OCML-IXR | SW | ARZ | FWL | CB - Metro Core | CBMC SW ARZ FWL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-09-30 |  | Active | EP
Fowler-OCML-IXR | SW | ARZ | FWL | CB - Metro Core | CBMC SW ARZ FWL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0132 | Schedule Change | Approved | 2020-02-06 11:03 | All IXR projects for CBMC In January were moved to March in order lighten January budget Financials have already been updated to reflect the change This is an adminstrative CR
Fowler-OCML-IXR | SW | ARZ | FWL | CB - Metro Core | CBMC SW ARZ FWL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
Fowler-OCML-IXR | SW | ARZ | FWL | CB - Metro Core | CBMC SW ARZ FWL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-07-20 |  | Active | Log | Upd | SN-0586 | Schedule Change | Approved | 2020-05-14 14:37 | Adjusting dates for CBMC POR Most of the changes are pushing activation dates out due to equipment delays
Fowler-OCML-IXR | SW | ARZ | FWL | CB - Metro Core | CBMC SW ARZ FWL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-09-30 |  | Active | Log | Upd | SN-0796 | Schedule Change | Approved | 2020-07-31 10:03 | Moving activation dates out for projects in the CA and SW regions due to various delays
CB Transport - New Router Fowler - MCD - Optics | SW | ARZ | MCD | CB - Metro Core | CBMC SW ARZ MCD Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-05-15 | 2020-07-15 |  | Active | EP
CB Transport - New Router McDowell - MCD - Optics | SW | ARZ | MCD | CB - Metro Core | CBMC SW ARZ MCD Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-03-13 | 2020-04-15 |  | Active | EP
CB Transport - New Router South Scottsdale - MCD - Optics | SW | ARZ | MCD | CB - Metro Core | CBMC SW ARZ MCD Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-05-15 | 2020-06-15 |  | Deleted | EP
McDowell-OCML-IXR | SW | ARZ | MCD | CB - Metro Core | CBMC SW ARZ MCD OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
McDowell-OCML-IXR | SW | ARZ | MCD | CB - Metro Core | CBMC SW ARZ MCD OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
N Scottsdale-OCML-IXR | SW | ARZ | NSC | CB - Metro Core | CBMC SW ARZ NSC OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-10-31 |  | Active | EP
N Scottsdale-OCML-IXR | SW | ARZ | NSC | CB - Metro Core | CBMC SW ARZ NSC OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-07-20 |  | Active | Log | Upd | SN-0586 | Schedule Change | Approved | 2020-05-14 14:37 | Adjusting dates for CBMC POR Most of the changes are pushing activation dates out due to equipment delays
N Scottsdale-OCML-IXR | SW | ARZ | NSC | CB - Metro Core | CBMC SW ARZ NSC OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-09-30 |  | Active | Log | Upd | SN-0701 | Schedule Change | Approved | 2020-07-02 11:45 | Pushing out activation dates in CE CA VA and SW due to equipment delays
N Scottsdale-OCML-IXR | SW | ARZ | NSC | CB - Metro Core | CBMC SW ARZ NSC OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-10-31 |  | Active | Log | Upd | SN-0934 | Schedule Change | Approved | 2020-09-18 09:35 | Moving out activation dates due to delays
Newport-OCML-IXR | VA | HRD | NWP | CB - Metro Core | CBMC VA HRD NWP OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | EP
Newport-OCML-IXR | VA | HRD | NWP | CB - Metro Core | CBMC VA HRD NWP OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0132 | Schedule Change | Approved | 2020-02-06 11:03 | All IXR projects for CBMC In January were moved to March in order lighten January budget Financials have already been updated to reflect the change This is an adminstrative CR
Newport-OCML-IXR | VA | HRD | NWP | CB - Metro Core | CBMC VA HRD NWP OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
CB Transport - New Router Greenbrier - NRF - Optics | VA | HRD | NRF | CB - Metro Core | CBMC VA HRD NRF Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-03-15 | 2020-11-30 |  | Active | EP
CB Transport - New Router Greenbrier - NRF - Optics | VA | HRD | NRF | CB - Metro Core | CBMC VA HRD NRF Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-03-15 | 2020-11-30 |  | Active | Log | Upd | SN-0934 | Schedule Change | Approved | 2020-09-18 09:35 | Moving out activation dates due to delays
CB Transport - New Router Princess Anne - NRF - Optics | VA | HRD | NRF | CB - Metro Core | CBMC VA HRD NRF Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-09-15 | 2020-12-31 |  | Active | EP
CB Transport - New Router Princess Anne - NRF - Optics | VA | HRD | NRF | CB - Metro Core | CBMC VA HRD NRF Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-09-15 | 2020-12-31 |  | Active | Log | Upd | SN-1049 | New | Approved | 2020-11-13 09:56 | Moving out activation dates for CBMC projects
CB Transport - New Router Portsmouth - NRF - Optics | VA | HRD | NRF | CB - Metro Core | CBMC VA HRD NRF Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-06-15 | 2020-12-31 |  | Active | EP
CB Transport - New Router Portsmouth - NRF - Optics | VA | HRD | NRF | CB - Metro Core | CBMC VA HRD NRF Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-06-15 | 2020-10-31 |  | Active | Log | Upd | SN-0934 | Schedule Change | Approved | 2020-09-18 09:35 | Moving out activation dates due to delays
CB Transport - New Router Portsmouth - NRF - Optics | VA | HRD | NRF | CB - Metro Core | CBMC VA HRD NRF Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-06-15 | 2020-12-31 |  | Active | Log | Upd | SN-1049 | New | Approved | 2020-11-13 09:56 | Moving out activation dates for CBMC projects
Norfolk-OCML-IXR | VA | HRD | NRF | CB - Metro Core | CBMC VA HRD NRF OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-07-30 |  | Active | EP
Norfolk-OCML-IXR | VA | HRD | NRF | CB - Metro Core | CBMC VA HRD NRF OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0132 | Schedule Change | Approved | 2020-02-06 11:03 | All IXR projects for CBMC In January were moved to March in order lighten January budget Financials have already been updated to reflect the change This is an adminstrative CR
Norfolk-OCML-IXR | VA | HRD | NRF | CB - Metro Core | CBMC VA HRD NRF OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
Norfolk-OCML-IXR | VA | HRD | NRF | CB - Metro Core | CBMC VA HRD NRF OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-07-30 |  | Active | Log | Upd | SN-0701 | Schedule Change | Approved | 2020-07-02 11:45 | Pushing out activation dates in CE CA VA and SW due to equipment delays
Oceana-OCML-IXR | VA | HRD | OCN | CB - Metro Core | CBMC VA HRD OCN OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
Oceana-OCML-IXR | VA | HRD | OCN | CB - Metro Core | CBMC VA HRD OCN OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
CB Transport - New Router Tysons - TCR - Optics | VA | NVA | TCR | CB - Metro Core | CBMC VA NVA TCR Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 3 | 2020-04-15 | 2020-03-31 |  | Active | EP
CB Transport - New Router Tysons - TCR - Optics | VA | NVA | TCR | CB - Metro Core | CBMC VA NVA TCR Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 3 | 2020-04-15 | 2020-03-31 |  | Active | Log | Upd | SN-0934 | Schedule Change | Approved | 2020-09-18 09:35 | Moving out activation dates due to delays
Roanoke-OCML-IXR | VA | ROA | RON | CB - Metro Core | CBMC VA ROA RON OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | EP
Roanoke-OCML-IXR | VA | ROA | RON | CB - Metro Core | CBMC VA ROA RON OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0132 | Schedule Change | Approved | 2020-02-06 11:03 | All IXR projects for CBMC In January were moved to March in order lighten January budget Financials have already been updated to reflect the change This is an adminstrative CR
Roanoke-OCML-IXR | VA | ROA | RON | CB - Metro Core | CBMC VA ROA RON OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
Tucson-OCML-IXR | SW | ARZ | TUC | CB - Metro Core | CBMC SW ARZ TUC OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-09-30 | 2020-09-30 | Active | EP
Tucson-OCML-IXR | SW | ARZ | TUC | CB - Metro Core | CBMC SW ARZ TUC OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-06-30 |  | Active | Log | Upd | SN-0618 | Schedule Change | Approved | 2020-06-05 14:52 | Removing deferred projects that still remain in the POR and moving out activation dates due to various equipment delays
Tucson-OCML-IXR | SW | ARZ | TUC | CB - Metro Core | CBMC SW ARZ TUC OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-07-30 |  | Active | Log | Upd | SN-0701 | Schedule Change | Approved | 2020-07-02 11:45 | Pushing out activation dates in CE CA VA and SW due to equipment delays
Tucson-OCML-IXR | SW | ARZ | TUC | CB - Metro Core | CBMC SW ARZ TUC OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-07-30 | 2020-09-30 | Active | Log | Upd | SN-0819 | Schedule Change | Approved | 2020-08-14 15:09 | POR Changes for CBMC
Tucson-OCML-IXR | SW | ARZ | TUC | CB - Metro Core | CBMC SW ARZ TUC OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0944 | Schedule Change | Approved | 2020-09-25 09:33 | Pushing out activation dates due to delays and deleting records as POR cleanup
CB Transport - New Router Blue Diamond - BLU - Card Add | SW | LAS | BLU | CB - Metro Core | CBMC SW LAS BLU Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-01 | 2020-01-15 |  | Deleted | EP
South West-OCML-IXR | SW | LAS | BLU | CB - Metro Core | CBMC SW LAS BLU OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-09-30 | 2020-09-30 | Active | EP
South West-OCML-IXR | SW | LAS | BLU | CB - Metro Core | CBMC SW LAS BLU OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-07-20 |  | Active | Log | Upd | SN-0586 | Schedule Change | Approved | 2020-05-14 14:37 | Adjusting dates for CBMC POR Most of the changes are pushing activation dates out due to equipment delays
South West-OCML-IXR | SW | LAS | BLU | CB - Metro Core | CBMC SW LAS BLU OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-07-20 | 2020-09-30 | Active | Log | Upd | SN-0819 | Schedule Change | Approved | 2020-08-14 15:09 | POR Changes for CBMC
South West-OCML-IXR | SW | LAS | BLU | CB - Metro Core | CBMC SW LAS BLU OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0944 | Schedule Change | Approved | 2020-09-25 09:33 | Pushing out activation dates due to delays and deleting records as POR cleanup
Ernest May-OCML-IXR | SW | LAS | ERN | CB - Metro Core | CBMC SW LAS ERN OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-07-20 | 2020-09-30 | Active | EP
Ernest May-OCML-IXR | SW | LAS | ERN | CB - Metro Core | CBMC SW LAS ERN OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-07-20 |  | Active | Log | Upd | SN-0586 | Schedule Change | Approved | 2020-05-14 14:37 | Adjusting dates for CBMC POR Most of the changes are pushing activation dates out due to equipment delays
Ernest May-OCML-IXR | SW | LAS | ERN | CB - Metro Core | CBMC SW LAS ERN OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-07-20 | 2020-09-30 | Active | Log | Upd | SN-0819 | Schedule Change | Approved | 2020-08-14 15:09 | POR Changes for CBMC
CB Transport - New Router Blue Diamond - HEN - Optics | SW | LAS | HEN | CB - Metro Core | CBMC SW LAS HEN Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-01-01 | 2020-01-15 |  | Deleted | EP
CB Transport - New Router Tenaya - HEN - Optics | SW | LAS | HEN | CB - Metro Core | CBMC SW LAS HEN Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-06-01 | 2020-08-15 |  | Active | EP
CB Transport - New Router Aliante - HEN - Optics | SW | LAS | HEN | CB - Metro Core | CBMC SW LAS HEN Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-08-03 | 2020-10-15 |  | Active | EP
CB Transport - New Router Valley - HEN - Optics | SW | LAS | HEN | CB - Metro Core | CBMC SW LAS HEN Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-03-02 | 2020-05-15 |  | Active | EP
OSO BLANCA-OCML-IXR | SW | LAS | OSB | CB - Metro Core | CBMC SW LAS OSB OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-09-30 |  | Active | EP
OSO BLANCA-OCML-IXR | SW | LAS | OSB | CB - Metro Core | CBMC SW LAS OSB OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-06-15 |  | Active | Log | Upd | SN-0419 | Schedule Change | Approved | 2020-04-02 09:36 | Updates driven by field audit and material delays
OSO BLANCA-OCML-IXR | SW | LAS | OSB | CB - Metro Core | CBMC SW LAS OSB OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-07-20 |  | Active | Log | Upd | SN-0599 | Schedule Change | Approved | 2020-05-20 16:50 | Adding a missing POR entry for SWR adjusting qty for projects as well as activation dates
OSO BLANCA-OCML-IXR | SW | LAS | OSB | CB - Metro Core | CBMC SW LAS OSB OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-09-30 |  | Active | Log | Upd | SN-0701 | Schedule Change | Approved | 2020-07-02 11:45 | Pushing out activation dates in CE CA VA and SW due to equipment delays
CB Transport - New Router Blue Diamond, Aliante - TEN - Card Add | SW | LAS | TEN | CB - Metro Core | CBMC SW LAS TEN Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-01 | 2020-01-15 |  | Deleted | EP
CB Transport - New Router Tenaya - TEN - Optics | SW | LAS | TEN | CB - Metro Core | CBMC SW LAS TEN Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-06-01 | 2020-08-15 |  | Active | EP
CB Transport - New Router Aliante - TEN - Optics | SW | LAS | TEN | CB - Metro Core | CBMC SW LAS TEN Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-08-03 | 2020-10-15 |  | Active | EP
CB Transport - New Router Valley - TEN - Optics | SW | LAS | TEN | CB - Metro Core | CBMC SW LAS TEN Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-03-02 | 2020-05-15 |  | Active | EP
CB Transport - New Router Valley - VLY - Optics | SW | LAS | VLY | CB - Metro Core | CBMC SW LAS VLY Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-03-02 | 2020-05-15 |  | Active | EP
North East-OCML-IXR | SW | LAS | VLY | CB - Metro Core | CBMC SW LAS VLY OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-12 | 2020-09-30 |  | Active | EP
North East-OCML-IXR | SW | LAS | VLY | CB - Metro Core | CBMC SW LAS VLY OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-12 | 2020-07-20 |  | Active | Log | Upd | SN-0586 | Schedule Change | Approved | 2020-05-14 14:37 | Adjusting dates for CBMC POR Most of the changes are pushing activation dates out due to equipment delays
North East-OCML-IXR | SW | LAS | VLY | CB - Metro Core | CBMC SW LAS VLY OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-12 | 2020-09-30 |  | Active | Log | Upd | SN-0771 | Schedule Change | Approved | 2020-07-20 09:31 | Adjusting POR activation months in CE SE and SW due to impacts from equipment delays
Chesapeake-OCML-IXR | VA | HRD | CHS | CB - Metro Core | CBMC VA HRD CHS OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | EP
Chesapeake-OCML-IXR | VA | HRD | CHS | CB - Metro Core | CBMC VA HRD CHS OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0132 | Schedule Change | Approved | 2020-02-06 11:03 | All IXR projects for CBMC In January were moved to March in order lighten January budget Financials have already been updated to reflect the change This is an adminstrative CR
Chesapeake-OCML-IXR | VA | HRD | CHS | CB - Metro Core | CBMC VA HRD CHS OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
CB Transport - New Router Greenbrier - GBR - Card Add | VA | HRD | GBR | CB - Metro Core | CBMC VA HRD GBR Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics |  |  |  |  | Deleted | EP
CB Transport - New Router Greenbrier - GBR - Card Add | VA | HRD | GBR | CB - Metro Core | CBMC VA HRD GBR Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics |  |  |  |  | Deleted | Log | Del | SN-0819 | Schedule Change | Approved | 2020-08-14 15:09 | POR Changes for CBMC
Princess Anne-OCML-IXR | VA | HRD | PRA | CB - Metro Core | CBMC VA HRD PRA OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
Princess Anne-OCML-IXR | VA | HRD | PRA | CB - Metro Core | CBMC VA HRD PRA OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
CB Transport - New Router Greenbrier - VBC - Optics | VA | HRD | VBC | CB - Metro Core | CBMC VA HRD VBC Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-03-15 | 2020-04-15 |  | Active | EP
CB Transport - New Router Princess Anne - VBC - Optics | VA | HRD | VBC | CB - Metro Core | CBMC VA HRD VBC Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-09-15 | 2020-12-31 |  | Active | EP
CB Transport - New Router Princess Anne - VBC - Optics | VA | HRD | VBC | CB - Metro Core | CBMC VA HRD VBC Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-09-15 | 2020-12-31 |  | Active | Log | Upd | SN-1049 | New | Approved | 2020-11-13 09:56 | Moving out activation dates for CBMC projects
CB Transport - New Router Portsmouth - VBC - Optics | VA | HRD | VBC | CB - Metro Core | CBMC VA HRD VBC Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-06-15 | 2020-12-31 |  | Active | EP
CB Transport - New Router Portsmouth - VBC - Optics | VA | HRD | VBC | CB - Metro Core | CBMC VA HRD VBC Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-06-15 | 2020-10-31 |  | Active | Log | Upd | SN-0934 | Schedule Change | Approved | 2020-09-18 09:35 | Moving out activation dates due to delays
CB Transport - New Router Portsmouth - VBC - Optics | VA | HRD | VBC | CB - Metro Core | CBMC VA HRD VBC Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-06-15 | 2020-12-31 |  | Active | Log | Upd | SN-1049 | New | Approved | 2020-11-13 09:56 | Moving out activation dates for CBMC projects
Virginia Beach-OCML-IXR | VA | HRD | VBC | CB - Metro Core | CBMC VA HRD VBC OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
Virginia Beach-OCML-IXR | VA | HRD | VBC | CB - Metro Core | CBMC VA HRD VBC OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
CB Transport - New Router Fairlakes - FLK - Optics | VA | NVA | FLK | CB - Metro Core | CBMC VA NVA FLK Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-04-15 | 2020-03-31 |  | Active | EP
CB Transport - New Router Fairlakes - FLK - Optics | VA | NVA | FLK | CB - Metro Core | CBMC VA NVA FLK Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-04-15 | 2020-03-31 |  | Active | Log | Upd | SN-0934 | Schedule Change | Approved | 2020-09-18 09:35 | Moving out activation dates due to delays
CB Transport - New Router Fredericksburg - FLK - Optics | VA | NVA | FLK | CB - Metro Core | CBMC VA NVA FLK Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-07-15 | 2020-09-30 |  | Active | EP
CB Transport - New Router Fredericksburg - FLK - Optics | VA | NVA | FLK | CB - Metro Core | CBMC VA NVA FLK Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-07-15 | 2020-09-30 |  | Active | Log | Upd | SN-0934 | Schedule Change | Approved | 2020-09-18 09:35 | Moving out activation dates due to delays
CB Transport - New Router Tysons - FLK - Optics | VA | NVA | FLK | CB - Metro Core | CBMC VA NVA FLK Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-04-15 | 2020-03-03 |  | Active | EP
CB Transport - New Router Tysons - FLK - Optics | VA | NVA | FLK | CB - Metro Core |  | Card & Optics | Optics Only for Cisco T5 |  |  |  |  | Active | Log | Del | SN-0020 | New | Approved | 2020-02-06 09:59 | Cleaning up POR Deleting duplicate records from the POR No financials are attached to this CR
CB Transport - New Router Tysons - FLK - Optics | VA | NVA | FLK | CB - Metro Core | CBMC VA NVA FLK Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 |  | 2020-05-15 | 2020-04-15 | Active | Log | New | SN-0131 | New | Approved | 2020-02-06 11:02 | 18 line items inadverntly were deleted from the POR
CB Transport - New Router Tysons - FLK - Optics | VA | NVA | FLK | CB - Metro Core | CBMC VA NVA FLK Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0309 | Schedule Change | Approved | 2020-03-02 16:17 | Audit of POR and making changed based on results
CB Transport - New Router Tysons - FLK - Optics | VA | NVA | FLK | CB - Metro Core | CBMC VA NVA FLK Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-04-15 | 2020-03-03 |  | Active | Log | Upd | SN-0934 | Schedule Change | Approved | 2020-09-18 09:35 | Moving out activation dates due to delays
CB Transport - New Router Fairlakes - MFD - Optics | VA | NVA | MFD | CB - Metro Core | CBMC VA NVA MFD Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-04-15 | 2020-03-31 |  | Active | EP
CB Transport - New Router Fairlakes - MFD - Optics | VA | NVA | MFD | CB - Metro Core | CBMC VA NVA MFD Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-04-15 | 2020-03-31 |  | Active | Log | Upd | SN-0934 | Schedule Change | Approved | 2020-09-18 09:35 | Moving out activation dates due to delays
CB Transport - New Router Fredericksburg - MFD - Optics | VA | NVA | MFD | CB - Metro Core | CBMC VA NVA MFD Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 5 | 2020-07-15 | 2020-09-30 |  | Active | EP
CB Transport - New Router Fredericksburg - MFD - Optics | VA | NVA | MFD | CB - Metro Core | CBMC VA NVA MFD Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 5 | 2020-07-15 | 2020-09-30 |  | Active | Log | Upd | SN-0934 | Schedule Change | Approved | 2020-09-18 09:35 | Moving out activation dates due to delays
CB Transport - New Router Tysons - MFD - Optics | VA | NVA | MFD | CB - Metro Core | CBMC VA NVA MFD Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-04-15 | 2020-03-31 |  | Active | EP
CB Transport - New Router Tysons - MFD - Optics | VA | NVA | MFD | CB - Metro Core | CBMC VA NVA MFD Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-04-15 | 2020-03-31 |  | Active | Log | Upd | SN-0934 | Schedule Change | Approved | 2020-09-18 09:35 | Moving out activation dates due to delays
HRHNLA061BW-100G CARD | SE | NOR | ELM | CB - Metro Core | CBMC SE NOR ELM 100G CARD Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-01-15 | 2020-02-15 |  | Active | EP
HRHNLA061BW-100G CARD | SE | NOR | ELM | CB - Metro Core | CBMC SE NOR ELM 100G CARD Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 1 | 2020-01-15 | 2020-02-15 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
HRHNLA061BW-SFM | SE | NOR | ELM | CB - Metro Core | CBMC SE NOR ELM Nokia SFM - 7950 Augment POR20 | Card & Optics | Nokia SFM-7950 XRS-20/20e SFM2-SA | 8 | 2020-01-15 | 2020-02-15 |  | Active | EP
HRHNLA061BW-SFM | SE | NOR | ELM | CB - Metro Core | CBMC SE NOR ELM Nokia SFM - 7950 Augment POR20 | Card & Optics | Nokia SFM-7950 XRS-20/20e SFM2-SA | 8 | 2020-01-15 | 2020-02-15 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
NWORLAMO1GW-ROUTER | SE | NOR | MCY | CB - Metro Core | CBMC SE NOR MCY ROUTER-7750 SR-7s Deployment POR20 Poydras | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
NWORLAMO1GW-ROUTER | SE | NOR | NWORLAMO | CB - Metro Core | CBMC SE NOR MCY ROUTER-7750 SR-7s Deployment POR20 Poydras | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-04-15 | 2020-07-15 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
NWORLAMO1GW-ROUTER | SE | NOR | MCY | CB - Metro Core | CBMC SE NOR MCY ROUTER-7750 SR-7s Deployment POR20 Poydras | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-04-15 | 2020-07-15 |  | Deleted | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
NWORLAMO1GW-ROUTER | SE | NOR | MCY | CB - Metro Core | CBMC SE NOR MCY ROUTER-7750 SR-7s Deployment POR20 Poydras | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
BELLSYSA01-ROUTER | SW | ARZ | BEL | CB - Metro Core | CBMC SW ARZ BEL ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-05-15 |  | Active | EP
BELLSYSA01-ROUTER | SW | ARZ | BEL | CB - Metro Core | CBMC SW ARZ BEL ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-02-15 | 2020-05-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
MCDLSYSA01-ROUTER | SW | ARZ | MCD | CB - Metro Core | CBMC SW ARZ MCD ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-04-15 | 2020-07-15 |  | Active | EP
MCDLSYSA01-ROUTER | SW | ARZ | MCD | CB - Metro Core | CBMC SW ARZ MCD ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-04-15 | 2020-07-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
MCDLCORA01-ROUTER | SW | ARZ | MCD | CB - Metro Core | CBMC SW ARZ MCD ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
MCDLCORA01-ROUTER | SW | ARZ | MCD | CB - Metro Core | CBMC SW ARZ MCD ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-09-15 | 2020-12-15 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
MCDLCORA01-ROUTER | SW | ARZ | MCD | CB - Metro Core | CBMC SW ARZ MCD ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
PEORSYSA01-ROUTER | SW | ARZ | PEO | CB - Metro Core | CBMC SW ARZ PEO ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-03-15 | 2020-08-31 |  | Active | EP
PEORSYSA01-ROUTER | SW | ARZ | PEO | CB - Metro Core | CBMC SW ARZ PEO ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-03-15 | 2020-06-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
PEORSYSA01-ROUTER | SW | ARZ | PEO | CB - Metro Core | CBMC SW ARZ PEO ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-03-15 | 2020-08-31 |  | Active | Log | Upd | SN-0618 | Schedule Change | Approved | 2020-06-05 14:52 | Removing deferred projects that still remain in the POR and moving out activation dates due to various equipment delays
CB Transport - New Router Fayetteville - NWA - Optics | CE | NWA | NWA | CB - Metro Core | CBMC CE ARK NWA Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-05-15 | 2020-06-15 |  | Active | EP
CB Transport - New Router Johnson - NWA - Optics | CE | NWA | NWA | CB - Metro Core | CBMC CE ARK NWA Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-05-15 | 2020-06-15 |  | Active | EP
CB Transport - New Router Bentonville - NWA - Optics | CE | NWA | NWA | CB - Metro Core | CBMC CE ARK NWA Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-06-15 | 2020-07-15 |  | Active | EP
CB Transport - New Router Strotherfield - KCY - Card Add | COR | NAT | KCY | CB - Metro Core | CBMC CE KAN KCY Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-04-15 | 2020-05-15 |  | Active | EP
CB Transport - New Router Topeka - KCY - Card Add | COR | NAT | KCY | CB - Metro Core | CBMC CE KAN KCY Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-04-15 | 2020-05-15 |  | Active | EP
CB Transport - New Router Topeka - KCY - Card Add | COR | NAT | KCY | CB - Metro Core |  | Card & Optics | Cisco T5 Card and Optics |  |  |  |  | Active | Log | Del | SN-0020 | New | Approved | 2020-02-06 09:59 | Cleaning up POR Deleting duplicate records from the POR No financials are attached to this CR
CB Transport - New Router Topeka - KCY - Card Add | COR | NAT | KCY | CB - Metro Core | CBMC CE KAN KCY Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 |  | 2020-05-15 |  | Active | Log | New | SN-0131 | New | Approved | 2020-02-06 11:02 | 18 line items inadverntly were deleted from the POR
CB Transport - New Router Topeka - KCY - Card Add | COR | NAT | KCY | CB - Metro Core | CBMC CE KAN KCY Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0309 | Schedule Change | Approved | 2020-03-02 16:17 | Audit of POR and making changed based on results
CB Transport - New Router Topeka - NWT - Card Add | CE | KAN | NWT | CB - Metro Core | CBMC CE KAN NWT Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-04-15 | 2020-05-15 |  | Active | EP
Baton Rouge-OCML-IXR | SE | BTR | BTR | CB - Metro Core | CBMC SE BTR BTR OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
Baton Rouge-OCML-IXR | SE | BTR | BTR | CB - Metro Core | CBMC SE BTR BTR OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
Vista-OCML-IXR | CA | SAN | VST | CB - Metro Core | CBMC CA SAN VST OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
Vista-OCML-IXR | CA | SAN | VST | CB - Metro Core | CBMC CA SAN VST OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
SANTA BARBARA-OCML-IXR | CA | SAB | SAB | CB - Metro Core | CBMC CA SAB SAB OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
SANTA BARBARA-OCML-IXR | CA | SAB | SAB | CB - Metro Core | CBMC CA SAB SAB OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-04-30 | 2020-07-31 |  | Deleted | Log | Upd | SN-0377 | Schedule Change | Canceled | 2020-04-14 09:04 | Pulling 1 38M for Nokia SR-7s and IXRs from Q3 and Q4 activities into Q2 due to acceleration
SANTA BARBARA-OCML-IXR | CA | SAB | SAB | CB - Metro Core | CBMC CA SAB SAB OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
CB Transport - New Router Bentonville - BVL - Card Add | CE | NWA | BVL | CB - Metro Core | CBMC CE ARK BVL Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-15 | 2020-07-15 |  | Active | EP
CB Transport - New Router Fayetteville - FAY - Optics | CE | NWA | FAY | CB - Metro Core | CBMC CE ARK FAY Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-05-15 | 2020-06-15 |  | Active | EP
CB Transport - New Router Johnson - FAY - Optics | CE | NWA | FAY | CB - Metro Core | CBMC CE NWA FAY Optics Only for Cisco T5 Augment POR20_V2 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-05-15 | 2020-08-20 |  | Active | EP
CB Transport - New Router Johnson - FAY - Optics | CE | NWA | FAY | CB - Metro Core |  | Card & Optics | Optics Only for Cisco T5 |  |  |  |  | Active | Log | Del | SN-0020 | New | Approved | 2020-02-06 09:59 | Cleaning up POR Deleting duplicate records from the POR No financials are attached to this CR
CB Transport - New Router Johnson - FAY - Optics | CE | NWA | FAY | CB - Metro Core | CBMC CE NWA FAY Optics Only for Cisco T5 Augment POR20_V2 | Card & Optics | Optics Only for Cisco T5 | 1 |  | 2020-06-15 |  | Active | Log | New | SN-0131 | New | Approved | 2020-02-06 11:02 | 18 line items inadverntly were deleted from the POR
CB Transport - New Router Johnson - FAY - Optics | CE | NWA | FAY | CB - Metro Core | CBMC CE NWA FAY Optics Only for Cisco T5 Augment POR20_V2 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-05-15 | 2020-06-15 |  | Active | Log | Upd | SN-0309 | Schedule Change | Approved | 2020-03-02 16:17 | Audit of POR and making changed based on results
CB Transport - New Router Johnson - FAY - Optics | CE | NWA | FAY | CB - Metro Core | CBMC CE NWA FAY Optics Only for Cisco T5 Augment POR20_V2 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-05-15 | 2020-08-20 |  | Active | Log | Upd | SN-0586 | Schedule Change | Approved | 2020-05-14 14:37 | Adjusting dates for CBMC POR Most of the changes are pushing activation dates out due to equipment delays
CB Transport - New Router Bentonville - FAY - Optics | CE | NWA | FAY | CB - Metro Core | CBMC CE ARK FAY Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-06-15 | 2020-07-15 |  | Active | EP
CB Transport - New Router Strotherfield - STR - Card Add | CE | KAN | STR | CB - Metro Core | CBMC CE KAN STR Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-15 | 2020-05-15 |  | Active | EP
CB Transport - New Router Topeka - TOP - Card Add | CE | KAN | TOP | CB - Metro Core | CBMC CE KAN TOP Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-15 | 2020-05-15 |  | Active | EP
WICHITA-OCML-IXR | CE | KAN | WIC | CB - Metro Core | CBMC CE KAN WIC OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
WICHITA-OCML-IXR | CE | KAN | WIC | CB - Metro Core | CBMC CE KAN WIC OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-06-30 | 2020-09-30 |  | Deleted | Log | Upd | SN-0377 | Schedule Change | Canceled | 2020-04-14 09:04 | Pulling 1 38M for Nokia SR-7s and IXRs from Q3 and Q4 activities into Q2 due to acceleration
WICHITA-OCML-IXR | CE | KAN | WIC | CB - Metro Core | CBMC CE KAN WIC OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-06-20 | 2020-08-20 |  | Deleted | Log | Upd | SN-0528 | Schedule Change | Canceled | 2020-05-06 16:46 | Updating POR for CE and VA
WICHITA-OCML-IXR | CE | KAN | WIC | CB - Metro Core | CBMC CE KAN WIC OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
CB Transport - New Router Garnett, Owasso - BAR - Card Add | CE | TUL | BAR | CB - Metro Core | CBMC CE TUL BAR Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-03-15 | 2020-04-15 |  | Active | EP
CB Transport - New Router Sapulpa, Quincy - BAR - Card Add | CE | TUL | BAR | CB - Metro Core | CBMC CE TUL BAR Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-03-15 | 2020-04-15 |  | Active | EP
CB Transport - New Router Downtown (TUL) - BAR - Optics | CE | TUL | BAR | CB - Metro Core | CBMC CE TUL BAR Optics Only for Cisco T5 Augment POR20 v1 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-05-15 | 2020-06-15 |  | Active | EP
CB Transport - New Router Quincy - BAR - Optics | CE | TUL | BAR | CB - Metro Core | CBMC CE TUL BAR Optics Only for Cisco T5 Augment POR20 v1 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-08-15 | 2020-09-15 |  | Active | EP
Broken Arrow-OCML-IXR | CE | TUL | BAR | CB - Metro Core | CBMC CE TUL BAR OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-08-30 |  | Active | EP
Broken Arrow-OCML-IXR | CE | TUL | BAR | CB - Metro Core | CBMC CE TUL BAR OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-05-20 |  | Active | Log | Upd | SN-0586 | Schedule Change | Approved | 2020-05-14 14:37 | Adjusting dates for CBMC POR Most of the changes are pushing activation dates out due to equipment delays
Broken Arrow-OCML-IXR | CE | TUL | BAR | CB - Metro Core | CBMC CE TUL BAR OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-07-31 |  | Active | Log | Upd | SN-0686 | New | Approved | 2020-06-22 10:17 | POR clean up for the CE and SE regions Deleting duplicate entries and adusting activation months
Broken Arrow-OCML-IXR | CE | TUL | BAR | CB - Metro Core | CBMC CE TUL BAR OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-08-30 |  | Active | Log | Upd | SN-0796 | Schedule Change | Approved | 2020-07-31 10:03 | Moving activation dates out for projects in the CA and SW regions due to various delays
OKCKOKCE9AW-xr01.clh.okc.ok-100G CARD | CE | OKC | CLH | CB - Metro Core | CBMC CE OKC CLH 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 2 | 2020-03-15 | 2020-04-15 |  | Active | EP
OKCKOKCE9AW-xr01.clh.okc.ok-100G CARD | CE | OKC | CLH | CB - Metro Core | CBMC CE OKC CLH 100GCard-7950-XRS20 Augment POR20 | Card & Optics | Nokia 7950-XRS20-100GCard-XCM-XMA | 2 | 2020-03-15 | 2020-04-15 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
OKCKOKCE9AW-xr01.clh.okc.ok-SFM | CE | OKC | CLH | CB - Metro Core | CBMC CE OKC CLH SFM-7950 XRS-20 Augment POR20 | Card & Optics | Nokia SFM-7950 XRS-20/20e SFM2-SA | 8 | 2020-03-15 | 2020-04-15 |  | Active | EP
OKCKOKCE9BW-xr02.clh.okc.ok-SFM | CE | OKC | CLH | CB - Metro Core | CBMC CE OKC CLH SFM-7950 XRS-20 Augment POR20 | Card & Optics | Nokia SFM-7950 XRS-20/20e SFM2-SA | 8 | 2020-03-15 | 2020-04-15 |  | Active | EP
CB Transport - New Router Downtown (TUL) - DTN - Optics | CE | TUL | DTN | CB - Metro Core | CBMC CE OKC DTN Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-05-15 | 2020-06-15 |  | Active | EP
CB Transport - New Router Garnett - GAR - Optics | CE | TUL | GAR | CB - Metro Core | CBMC CE TUL GAR Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-03-15 | 2020-06-20 |  | Active | EP
CB Transport - New Router Garnett - GAR - Optics | CE | TUL | GAR | CB - Metro Core | CBMC CE TUL GAR Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-03-15 | 2020-06-20 |  | Active | Log | Upd | SN-0586 | Schedule Change | Approved | 2020-05-14 14:37 | Adjusting dates for CBMC POR Most of the changes are pushing activation dates out due to equipment delays
GARNET-OCML-IXR | CE | TUL | GAR | CB - Metro Core | CBMC CE OKC GAR OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
GARNET-OCML-IXR | CE | TUL | GAR | CB - Metro Core | CBMC CE OKC GAR OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
CB Transport - New Router Irish Lane - ILH - Optics | CE | OKC | ILH | CB - Metro Core | CBMC CE OKC ILH Optics Only for Cisco T5 Augment POR20_V2 | Card & Optics | Optics Only for Cisco T5 | 3 | 2020-06-15 | 2020-07-15 |  | Active | EP
Elkhorn-OCML-IXR | CE | OMA | ELK | CB - Metro Core | CBMC CE OMA ELK OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-04-15 |  | Active | EP
CB Transport - New Router North - ONA - Optics | CE | OMA | ONA | CB - Metro Core | CBMC CE OMA ONA Optics Only for Cisco T5 Augment POR20_V2 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-06-15 | 2020-07-15 |  | Active | EP
NORTH-OCML-IXR | CE | OMA | ONA | CB - Metro Core | CBMC CE OMA ONA OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
NORTH-OCML-IXR | CE | OMA | ONA | CB - Metro Core | CBMC CE OMA ONA OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
CB Transport - New Router North - OMM - Optics | CE | OMA | OMM | CB - Metro Core | CBMC CE OMA OMM Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-06-15 | 2020-07-15 |  | Active | EP
CB Transport - New Router South (OM) - OMM - Optics | CE | OMA | OMM | CB - Metro Core | CBMC CE OMA OMM Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-09-15 | 2020-10-15 |  | Active | EP
CB Transport - New Router South (OM) - SOU - Optics | CE | OMA | SOU | CB - Metro Core | CBMC CE OMA SOU Optics Only for Cisco T5 Augment POR20_V2 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-09-15 | 2020-10-15 |  | Active | EP
CLEVELAND-OCML-IXR | NE | CLE | CLV | CB - Metro Core | CBMC NE CLE CLV OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
CLEVELAND-OCML-IXR | NE | CLE | CLV | CB - Metro Core | CBMC NE CLE CLV OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-04-30 | 2020-07-31 |  | Deleted | Log | Upd | SN-0377 | Schedule Change | Canceled | 2020-04-14 09:04 | Pulling 1 38M for Nokia SR-7s and IXRs from Q3 and Q4 activities into Q2 due to acceleration
CLEVELAND-OCML-IXR | NE | CLE | CLV | CB - Metro Core | CBMC NE CLE CLV OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
CB Transport - New Router Manchester PE - ENF - Optics | NE | CON | ENF | CB - Metro Core | CBMC NE CON ENF Optics Only for Cisco T5 Augment POR20_V2 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-06-15 | 2020-07-15 |  | Active | EP
CB Transport - New Router Manchester PE - MAN - Optics | NE | CON | MAN | CB - Metro Core | CBMC NE CON MAN Optics Only for Cisco T5 Augment POR20_V2 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-06-15 | 2020-07-15 |  | Active | EP
CB Transport - New Router Midwest City - MWC - Optics | CE | OKC | MWC | CB - Metro Core | CBMC CE OKC MWC Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 3 | 2020-08-15 | 2020-09-15 |  | Active | EP
MIDWEST CITY-OCML-IXR | CE | OKC | MWC | CB - Metro Core | CBMC CE OKC MWC OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
MIDWEST CITY-OCML-IXR | CE | OKC | MWC | CB - Metro Core | CBMC CE OKC MWC OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-06-30 | 2020-09-30 |  | Deleted | Log | Upd | SN-0377 | Schedule Change | Canceled | 2020-04-14 09:04 | Pulling 1 38M for Nokia SR-7s and IXRs from Q3 and Q4 activities into Q2 due to acceleration
MIDWEST CITY-OCML-IXR | CE | OKC | MWC | CB - Metro Core | CBMC CE OKC MWC OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
CB Transport - New Router Norman - NOR - Card Add | CE | OKC | NOR | CB - Metro Core | CBMC CE OKC NOR Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-07-15 | 2020-08-15 |  | Active | EP
CB Transport - New Router Norman - NOR - Card Add | CE | OKC | NOR | CB - Metro Core |  | Card & Optics | Cisco T5 Card and Optics |  |  |  |  | Active | Log | Del | SN-0020 | New | Approved | 2020-02-06 09:59 | Cleaning up POR Deleting duplicate records from the POR No financials are attached to this CR
CB Transport - New Router Norman - NOR - Card Add | CE | OKC | NOR | CB - Metro Core | CBMC CE OKC NOR Optics Only for Cisco T5 Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 |  | 2020-08-15 |  | Active | Log | New | SN-0131 | New | Approved | 2020-02-06 11:02 | 18 line items inadverntly were deleted from the POR
CB Transport - New Router Norman - NOR - Card Add | CE | OKC | NOR | CB - Metro Core | CBMC CE OKC NOR Optics Only for Cisco T5 Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-07-15 | 2020-08-15 |  | Active | Log | Upd | SN-0309 | Schedule Change | Approved | 2020-03-02 16:17 | Audit of POR and making changed based on results
CB Transport - New Router Norman - NOR - Card Add | CE | OKC | NOR | CB - Metro Core | CBMC CE OKC NOR Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-07-15 | 2020-08-15 |  | Active | Log | Upd | SN-0701 | Schedule Change | Approved | 2020-07-02 11:45 | Pushing out activation dates in CE CA VA and SW due to equipment delays
CB Transport - New Router Moore - NOR - Card Add | CE | OKC | NOR | CB - Metro Core | CBMC CE OKC NOR Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-07-15 | 2020-08-15 |  | Active | EP
CB Transport - New Router Northeast - NOR - Card Add | CE | OKC | NOR | CB - Metro Core | CBMC CE OKC NOR Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-07-15 | 2020-08-15 |  | Active | EP
CB Transport - New Router Northeast - NOR - Card Add | CE | OKC | NOR | CB - Metro Core |  | Card & Optics | Cisco T5 Card and Optics |  |  |  |  | Active | Log | Del | SN-0020 | New | Approved | 2020-02-06 09:59 | Cleaning up POR Deleting duplicate records from the POR No financials are attached to this CR
CB Transport - New Router Northeast - NOR - Card Add | CE | OKC | NOR | CB - Metro Core | CBMC CE OKC NOR Optics Only for Cisco T5 Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 |  | 2020-08-01 |  | Active | Log | New | SN-0131 | New | Approved | 2020-02-06 11:02 | 18 line items inadverntly were deleted from the POR
CB Transport - New Router Northeast - NOR - Card Add | CE | OKC | NOR | CB - Metro Core | CBMC CE OKC NOR Optics Only for Cisco T5 Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-07-15 | 2020-08-15 |  | Active | Log | Upd | SN-0309 | Schedule Change | Approved | 2020-03-02 16:17 | Audit of POR and making changed based on results
CB Transport - New Router Northeast - NOR - Card Add | CE | OKC | NOR | CB - Metro Core | CBMC CE OKC NOR Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-07-15 | 2020-08-15 |  | Active | Log | Upd | SN-0701 | Schedule Change | Approved | 2020-07-02 11:45 | Pushing out activation dates in CE CA VA and SW due to equipment delays
CB Transport - New Router Northeast - NEH - Optics | CE | OKC | NEH | CB - Metro Core | CBMC CE OKC NEH Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 3 | 2020-07-15 | 2020-08-15 |  | Active | EP
CB Transport - New Router Irish Lane - OKC - Optics | CE | OKC | OKC | CB - Metro Core | CBMC CE OKC OKC Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-06-15 | 2020-07-15 |  | Active | EP
CB Transport - New Router Moore - OKC - Optics | CE | OKC | OKC | CB - Metro Core | CBMC CE OKC OKC Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-07-15 | 2020-08-15 |  | Deleted | EP
CB Transport - New Router Midwest City - OKC - Optics | CE | OKC | OKC | CB - Metro Core | CBMC CE OKC OKC Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-08-15 | 2020-09-15 |  | Active | EP
CB Transport - New Router Owasso - OWA - Optics | CE | TUL | OWA | CB - Metro Core | CBMC CE TUL OWA Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-03-15 | 2020-04-15 |  | Active | EP
Owasso-OCML-IXR | CE | TUL | OWA | CB - Metro Core | CBMC CE TUL OWA OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
Owasso-OCML-IXR | CE | TUL | OWA | CB - Metro Core | CBMC CE TUL OWA OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-04-15 | 2020-07-20 |  | Deleted | Log | Upd | SN-0478 | Schedule Change | Approved | 2020-04-24 14:37 | Adjusting schedule dates across multpile PPMs
Owasso-OCML-IXR | CE | TUL | OWA | CB - Metro Core | CBMC CE TUL OWA OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
CB Transport - New Router Quincy - QNC - Optics | CE | TUL | QNC | CB - Metro Core | CBMC CE TUL QNC Optics Only for Cisco T5 Augment POR20_V2 | Card & Optics | Optics Only for Cisco T5 | 3 | 2020-08-15 | 2020-10-31 |  | Active | EP
CB Transport - New Router Quincy - QNC - Optics | CE | TUL | QNC | CB - Metro Core | CBMC CE TUL QNC Optics Only for Cisco T5 Augment POR20_V2 | Card & Optics | Optics Only for Cisco T5 | 3 | 2020-08-15 | 2020-10-31 |  | Active | Log | Upd | SN-0986 | Schedule Change | Approved | 2020-10-14 16:16 | Adjusting acticvation dates in the CE and SE regions
Sara Rd-OCML-IXR | CE | OKC | SRH | CB - Metro Core | CBMC CE OKC SRH OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
Sara Rd-OCML-IXR | CE | OKC | SRH | CB - Metro Core | CBMC CE OKC SRH OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
CB Transport - New Router Garnett, Downtown (TUL) - TUL - Card Add | CE | TUL | TUL | CB - Metro Core | CBMC CE TUL TUL Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-03-15 | 2020-07-30 |  | Active | EP
CB Transport - New Router Garnett, Downtown (TUL) - TUL - Card Add | CE | TUL | TUL | CB - Metro Core | CBMC CE TUL TUL Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-03-15 | 2020-05-20 |  | Active | Log | Upd | SN-0586 | Schedule Change | Approved | 2020-05-14 14:37 | Adjusting dates for CBMC POR Most of the changes are pushing activation dates out due to equipment delays
CB Transport - New Router Garnett, Downtown (TUL) - TUL - Card Add | CE | TUL | TUL | CB - Metro Core | CBMC CE TUL TUL Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-03-15 | 2020-07-30 |  | Active | Log | Upd | SN-0701 | Schedule Change | Approved | 2020-07-02 11:45 | Pushing out activation dates in CE CA VA and SW due to equipment delays
CB Transport - New Router Downtown (TUL) - TUL - Optics | CE | TUL | TUL | CB - Metro Core | CBMC CE TUL TUL Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-05-15 | 2020-06-15 |  | Active | EP
CB Transport - New Router Owasso - TUL - Optics | CE | TUL | TUL | CB - Metro Core | CBMC CE TUL TUL Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-03-15 | 2020-04-15 |  | Active | EP
CB Transport - New Router Sapulpa - TUL - Optics | CE | TUL | TUL | CB - Metro Core | CBMC CE TUL TUL Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-03-15 | 2020-05-20 |  | Active | EP
CB Transport - New Router Sapulpa - TUL - Optics | CE | TUL | TUL | CB - Metro Core | CBMC CE TUL TUL Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-03-15 | 2020-05-20 |  | Active | Log | Upd | SN-0586 | Schedule Change | Approved | 2020-05-14 14:37 | Adjusting dates for CBMC POR Most of the changes are pushing activation dates out due to equipment delays
CB Transport - New Router Quincy - TUL - Optics | CE | TUL | TUL | CB - Metro Core | CBMC CE TUL TUL Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-08-15 | 2020-09-15 |  | Active | EP
Local - MTC-OCML-IXR | CE | TUL | TUL | CB - Metro Core | CBMC CE TUL TUL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-08-30 |  | Active | EP
Local - MTC-OCML-IXR | CE | TUL | TUL | CB - Metro Core | CBMC CE TUL TUL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 1 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0132 | Schedule Change | Approved | 2020-02-06 11:03 | All IXR projects for CBMC In January were moved to March in order lighten January budget Financials have already been updated to reflect the change This is an adminstrative CR
Local - MTC-OCML-IXR | CE | TUL | TUL | CB - Metro Core | CBMC CE TUL TUL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-06-01 |  | Active | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
Local - MTC-OCML-IXR | CE | TUL | TUL | CB - Metro Core | CBMC CE TUL TUL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-07-30 |  | Active | Log | Upd | SN-0701 | Schedule Change | Approved | 2020-07-02 11:45 | Pushing out activation dates in CE CA VA and SW due to equipment delays
Local - MTC-OCML-IXR | CE | TUL | TUL | CB - Metro Core | CBMC CE TUL TUL OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-03-01 | 2020-08-30 |  | Active | Log | Upd | SN-0796 | Schedule Change | Approved | 2020-07-31 10:03 | Moving activation dates out for projects in the CA and SW regions due to various delays
Walker-OCML-IXR | CE | OKC | WLK | CB - Metro Core | CBMC CE OKC WLK OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-05-20 |  | Active | EP
Walker-OCML-IXR | CE | OKC | WLK | CB - Metro Core | CBMC CE OKC WLK OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-02-15 | 2020-05-20 |  | Active | Log | Upd | SN-0586 | Schedule Change | Approved | 2020-05-14 14:37 | Adjusting dates for CBMC POR Most of the changes are pushing activation dates out due to equipment delays
WEST-OCML-IXR | CE | OKC | WEH | CB - Metro Core | CBMC CE OKC WEH OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  | 2020-10-01 |  |  | Deleted | EP
WEST-OCML-IXR | CE | OKC | WEH | CB - Metro Core | CBMC CE OKC WEH OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  | 2020-10-01 |  |  | Deleted | Log | Del | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
CB Transport - New Router North - BLV - Optics | CE | OMA | BLV | CB - Metro Core | CBMC CE OMA BLV Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-06-15 | 2020-07-15 |  | Active | EP
CB Transport - New Router South (OM) - BLV - Optics | CE | OMA | BLV | CB - Metro Core | CBMC CE OMA BLV Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-09-15 | 2020-10-15 |  | Active | EP
Bellevue-OCML-IXR | CE | OMA | BLV | CB - Metro Core | CBMC CE OMA BLV OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
Bellevue-OCML-IXR | CE | OMA | BLV | CB - Metro Core | CBMC CE OMA BLV OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-06-30 | 2020-09-30 |  | Deleted | Log | Upd | SN-0377 | Schedule Change | Canceled | 2020-04-14 09:04 | Pulling 1 38M for Nokia SR-7s and IXRs from Q3 and Q4 activities into Q2 due to acceleration
Bellevue-OCML-IXR | CE | OMA | BLV | CB - Metro Core | CBMC CE OMA BLV OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-10-01 | 2020-07-31 |  | Deleted | Log | Upd | SN-0686 | New | Approved | 2020-06-22 10:17 | POR clean up for the CE and SE regions Deleting duplicate entries and adusting activation months
Bellevue-OCML-IXR | CE | OMA | BLV | CB - Metro Core | CBMC CE OMA BLV OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-10-01 | 2020-12-30 |  | Deleted | Log | Upd | SN-0771 | Schedule Change | Approved | 2020-07-20 09:31 | Adjusting POR activation months in CE SE and SW due to impacts from equipment delays
Bellevue-OCML-IXR | CE | OMA | BLV | CB - Metro Core | CBMC CE OMA BLV OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0944 | Schedule Change | Approved | 2020-09-25 09:33 | Pushing out activation dates due to delays and deleting records as POR cleanup
CB Transport - New Router Providence - PRV - Optics | NE | RHD | PRV | CB - Metro Core | CBMC NE RHD PRV Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-03-15 | 2020-06-30 |  | Active | EP
CB Transport - New Router Providence - PRV - Optics | NE | RHD | PRV | CB - Metro Core |  | Card & Optics | Optics Only for Cisco T5 |  |  |  |  | Active | Log | Del | SN-0020 | New | Approved | 2020-02-06 09:59 | Cleaning up POR Deleting duplicate records from the POR No financials are attached to this CR
CB Transport - New Router Providence - PRV - Optics | NE | RHD | PRV | CB - Metro Core | CBMC NE RHD PRV Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 |  | 2020-01-15 |  | Active | Log | New | SN-0131 | New | Approved | 2020-02-06 11:02 | 18 line items inadverntly were deleted from the POR
CB Transport - New Router Providence - PRV - Optics | NE | RHD | PRV | CB - Metro Core | CBMC NE RHD PRV Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-03-15 | 2020-04-15 |  | Active | Log | Upd | SN-0309 | Schedule Change | Approved | 2020-03-02 16:17 | Audit of POR and making changed based on results
CB Transport - New Router Providence - PRV - Optics | NE | RHD | PRV | CB - Metro Core | CBMC NE RHD PRV Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-03-15 | 2020-05-20 |  | Active | Log | Upd | SN-0478 | Schedule Change | Approved | 2020-04-24 14:37 | Adjusting schedule dates across multpile PPMs
CB Transport - New Router Providence - PRV - Optics | NE | RHD | PRV | CB - Metro Core | CBMC NE RHD PRV Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-03-15 | 2020-06-30 |  | Active | Log | Upd | SN-0618 | Schedule Change | Approved | 2020-06-05 14:52 | Removing deferred projects that still remain in the POR and moving out activation dates due to various equipment delays
CB Transport - New Router Providence - WWK - Optics | NE | RHD | WWK | CB - Metro Core | CBMC NE RHD WWK Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-03-15 | 2020-06-30 |  | Active | EP
CB Transport - New Router Providence - WWK - Optics | NE | RHD | WWK | CB - Metro Core | CBMC NE RHD WWK Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-03-15 | 2020-05-20 |  | Active | Log | Upd | SN-0478 | Schedule Change | Approved | 2020-04-24 14:37 | Adjusting schedule dates across multpile PPMs
CB Transport - New Router Providence - WWK - Optics | NE | RHD | WWK | CB - Metro Core | CBMC NE RHD WWK Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-03-15 | 2020-06-30 |  | Active | Log | Upd | SN-0618 | Schedule Change | Approved | 2020-06-05 14:52 | Removing deferred projects that still remain in the POR and moving out activation dates due to various equipment delays
Metairie-OCML-IXR | SE | NOR | CLR | CB - Metro Core | CBMC SE GLA CLR OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-10-01 | 2020-09-30 |  | Active | EP
Metairie-OCML-IXR | SE | NOR | CLR | CB - Metro Core | CBMC SE GLA CLR OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-10-01 | 2020-07-31 |  | Active | Log | Upd | SN-0654 | Schedule Change | Approved | 2020-06-14 18:38 | Changes to projects in the SE and CA regions due to material delays
Metairie-OCML-IXR | SE | NOR | CLR | CB - Metro Core | CBMC SE GLA CLR OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-10-01 | 2020-08-31 |  | Active | Log | Upd | SN-0737 | Schedule Change | Approved | 2020-07-10 10:12 | Pushing out activation dates in the SER due to equipment delays Deleting duplicate record in CE and pushing out activation month due to site readiness delays
Metairie-OCML-IXR | SE | NOR | CLR | CB - Metro Core | CBMC SE GLA CLR OCML-IXR-R6 7250 Augment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-10-01 | 2020-09-30 |  | Active | Log | Upd | SN-0819 | Schedule Change | Approved | 2020-08-14 15:09 | POR Changes for CBMC
FRBGVAPM17W-ROUTER | VA | NVA | FBG | CB - Metro Core | CBMC VA NVA FBG ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
FRBGVAPM17W-ROUTER | VA | NVA | FBG | CB - Metro Core | CBMC VA NVA FBG ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-08-15 | 2020-11-01 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
FRBGVAPM17W-ROUTER | VA | NVA | FBG | CB - Metro Core | CBMC VA NVA FBG ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-04-30 | 2020-07-31 |  | Deleted | Log | Upd | SN-0377 | Schedule Change | Canceled | 2020-04-14 09:04 | Pulling 1 38M for Nokia SR-7s and IXRs from Q3 and Q4 activities into Q2 due to acceleration
FRBGVAPM17W-ROUTER | VA | NVA | FBG | CB - Metro Core | CBMC VA NVA FBG ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
CB Transport - New Router Fredericksburg - FBG - Optics | VA | NVA | FBG | CB - Metro Core | CBMC VA NVA FBG Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-07-15 | 2020-12-31 |  | Active | EP
CB Transport - New Router Fredericksburg - FBG - Optics | VA | NVA | FBG | CB - Metro Core | CBMC VA NVA FBG Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-07-15 | 2020-10-30 |  | Active | Log | Upd | SN-0934 | Schedule Change | Approved | 2020-09-18 09:35 | Moving out activation dates due to delays
CB Transport - New Router Fredericksburg - FBG - Optics | VA | NVA | FBG | CB - Metro Core | CBMC VA NVA FBG Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-07-15 | 2020-12-31 |  | Active | Log | Upd | SN-1049 | New | Approved | 2020-11-13 09:56 | Moving out activation dates for CBMC projects
FRED-OCML-IXR | VA | NVA | FBG | CB - Metro Core | CBMC VA NVA FBG OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-06-15 | 2020-09-15 |  | Active | EP
ALSVBSRA02-ROUTER | CA | ORG | AVJ | CB - Metro Core | CBMC CA ORG AVJ ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
ALSVBSRA02-ROUTER | CA | ORG | AVJ | CB - Metro Core | CBMC CA ORG AVJ ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-05-15 | 2020-08-15 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
ALSVBSRA02-ROUTER | CA | ORG | AVJ | CB - Metro Core | CBMC CA ORG AVJ ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
CV1XEWAA01-ROUTER | CA | SAN | CHU | CB - Metro Core | CBMC CA SAN CHU ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-07-15 | 2020-10-15 |  | Active | EP
CV1XEWAA01-ROUTER | CA | SAN | CHU | CB - Metro Core | CBMC CA SAN CHU ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-07-15 | 2020-10-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
CB Transport - New Router Chula Vista - CHU - Optics | CA | SAN | CHU | CB - Metro Core | CBMC CA SAN CHU Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-06-15 | 2020-08-31 |  | Active | EP
CB Transport - New Router Chula Vista - CHU - Optics | CA | SAN | CHU | CB - Metro Core | CBMC CA SAN CHU Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-06-15 | 2020-08-31 |  | Active | Log | Upd | SN-0796 | Schedule Change | Approved | 2020-07-31 10:03 | Moving activation dates out for projects in the CA and SW regions due to various delays
DT1XEWAA01-ROUTER | CA | SAN | DWN | CB - Metro Core | CBMC CA SAN DWN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
DT1XEWAA01-ROUTER | CA | SAN | DWN | CB - Metro Core | CBMC CA SAN DWN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-07-15 | 2020-10-15 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
DT1XEWAA01-ROUTER | CA | SAN | DWN | CB - Metro Core | CBMC CA SAN DWN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
CB Transport - New Router Downtown (SD) - DWN - Optics | CA | SAN | DWN | CB - Metro Core | CBMC CA SAN DWN Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-06-15 | 2020-08-31 |  | Active | EP
CB Transport - New Router Downtown (SD) - DWN - Optics | CA | SAN | DWN | CB - Metro Core | CBMC CA SAN DWN Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-06-15 | 2020-07-15 |  | Active | Log | Upd | SN-0796 | Schedule Change | Approved | 2020-07-31 10:03 | Moving activation dates out for projects in the CA and SW regions due to various delays
CB Transport - New Router Downtown (SD) - DWN - Optics | CA | SAN | DWN | CB - Metro Core | CBMC CA SAN DWN Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-06-15 | 2020-08-31 |  | Active | Log | Upd | SN-0819 | Schedule Change | Approved | 2020-08-14 15:09 | POR Changes for CBMC
SNTBBSRA01-ROUTER | CA | SAB | SAB | CB - Metro Core | CBMC CA SAB SAB ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-07-20 | 2021-02-21 |  | Active | EP
SNTBBSRA01-ROUTER | CA | SAB | SAB | CB - Metro Core | CBMC CA SAB SAB ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-10-15 | 2020-10-01 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
SNTBBSRA01-ROUTER | CA | SAB | SAB | CB - Metro Core | CBMC CA SAB SAB ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-07-20 | 2020-10-01 |  | Active | Log | Upd | SN-0586 | Schedule Change | Approved | 2020-05-14 14:37 | Adjusting dates for CBMC POR Most of the changes are pushing activation dates out due to equipment delays
SNTBBSRA01-ROUTER | CA | SAB | SAB | CB - Metro Core | CBMC CA SAB SAB ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-07-20 | 2021-02-21 |  | Active | Log | Upd | SN-1049 | New | Approved | 2020-11-13 09:56 | Moving out activation dates for CBMC projects
BNVLBSRA01-ROUTER | CE | NWA | BVL | CB - Metro Core | CBMC CE NWA BVL ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-07-15 | 2020-12-31 |  | Active | EP
BNVLBSRA01-ROUTER | CE | NWA | BVL | CB - Metro Core | CBMC CE NWA BVL ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-07-15 | 2020-10-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
BNVLBSRA01-ROUTER | CE | NWA | BVL | CB - Metro Core | CBMC CE NWA BVL ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-07-15 | 2020-12-31 |  | Active | Log | Upd | SN-1049 | New | Approved | 2020-11-13 09:56 | Moving out activation dates for CBMC projects
FT SMITH-OCML-IXR | CE | NWA | FTS | CB - Metro Core | CBMC CE NWA FTS OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
FT SMITH-OCML-IXR | CE | NWA | FTS | CB - Metro Core | CBMC CE NWA FTS OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
HRSNBSRA11-ROUTER | CE | NWA | HRN | CB - Metro Core | CBMC CE NWA HRN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
HRSNBSRA11-ROUTER | CE | NWA | HRN | CB - Metro Core | CBMC CE NWA HRN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-05-15 | 2020-08-15 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
HRSNBSRA11-ROUTER | CE | NWA | HRN | CB - Metro Core | CBMC CE NWA HRN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
JHSNBSRA02-ROUTER | CE | NWA | NWA | CB - Metro Core | CBMC CE NWA NWA ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
JHSNBSRA02-ROUTER | CE | NWA | NWA | CB - Metro Core | CBMC CE NWA NWA ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-06-15 | 2020-09-15 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
JHSNBSRA02-ROUTER | CE | NWA | NWA | CB - Metro Core | CBMC CE NWA NWA ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 1 | 2020-06-15 | 2020-09-15 |  | Deleted | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
JHSNBSRA02-ROUTER | CE | NWA | NWA | CB - Metro Core | CBMC CE NWA NWA ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
WINFBSRA11-ROUTER | CE | KAN | STR | CB - Metro Core | CBMC CE KAN STR ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
WINFBSRA11-ROUTER | CE | KAN | STR | CB - Metro Core | CBMC CE KAN STR ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-05-15 | 2020-08-15 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
WINFBSRA11-ROUTER | CE | KAN | STR | CB - Metro Core | CBMC CE KAN STR ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
sr01.dth.tul.ok-ROUTER | CE | TUL | DTN | CB - Metro Core | CBMC CE TUL DTN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
sr01.dth.tul.ok-ROUTER | CE | TUL | DTN | CB - Metro Core | CBMC CE TUL DTN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-06-15 | 2020-09-15 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
sr01.dth.tul.ok-ROUTER | CE | TUL | DTN | CB - Metro Core | CBMC CE TUL DTN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
sr01.edm.okc.ok-ROUTER | CE | OKC | ILH | CB - Metro Core | CBMC CE OKC ILH ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
sr01.edm.okc.ok-ROUTER | CE | OKC | ILH | CB - Metro Core | CBMC CE OKC ILH ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-07-15 | 2020-10-15 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
sr01.edm.okc.ok-ROUTER | CE | OKC | ILH | CB - Metro Core | CBMC CE OKC ILH ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
CB Transport - New Router Moore - MOO - Optics | CE | OKC | MOO | CB - Metro Core | CBMC CE OKC MOO Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-07-15 | 2020-08-15 |  | Active | EP
sr01.nor.okc.ok-ROUTER | CE | OKC | NOR | CB - Metro Core | CBMC CE OKC NOR ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-08-15 | 2020-11-15 |  | Active | EP
sr01.nor.okc.ok-ROUTER | CE | OKC | NOR | CB - Metro Core | CBMC CE OKC NOR ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-08-15 | 2020-11-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
CB Transport - New Router Irish Lane - NOR - Optics | CE | OKC | NOR | CB - Metro Core | CBMC CE OKC NOR Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-06-15 | 2020-07-15 |  | Active | EP
NORTHEAST-OCML-IXR | CE | OKC | NEH | CB - Metro Core | CBMC CE OKC NEH OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
NORTHEAST-OCML-IXR | CE | OKC | NEH | CB - Metro Core | CBMC CE OKC NEH OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
OMHSBSRA01-ROUTER | CE | OMA | SOU | CB - Metro Core | CBMC CE OMA SOU ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-10-15 | 2020-12-15 |  | Active | EP
OMHSBSRA01-ROUTER | CE | OMA | SOU | CB - Metro Core | CBMC CE OMA SOU ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-10-15 | 2020-12-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
CB Transport - New Router St Martinville - STM - Card Add | SE | LFY | STM | CB - Metro Core | CBMC SE LFY STM Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-15 | 2020-07-15 |  | Active | EP
PENSACOLA-OCML-IXR | SE | GCT | PNS | CB - Metro Core | CBMC SE GCT PNS OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
PENSACOLA-OCML-IXR | SE | GCT | PNS | CB - Metro Core | CBMC SE GCT PNS OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
CB Transport - New Router Holt - HLT - Chassis Add | SE | MGA | HLT | CB - Metro Core | CBMC SE MGA HLT Cisco M6_M15 Chassis Augment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-04-15 | 2020-06-01 |  | Active | EP
CB Transport - New Router Holt - HLT - Optics | SE | MGA | HLT | CB - Metro Core | CBMC SE MGA HLT Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-04-15 | 2020-06-01 |  | Active | EP
WARNER ROBINS-OCML-IXR | SE | MGA | WRB | CB - Metro Core | CBMC SE MGA WRB OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-10-01 | 2020-09-30 |  | Active | EP
WARNER ROBINS-OCML-IXR | SE | MGA | WRB | CB - Metro Core | CBMC SE MGA WRB OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-10-01 | 2020-07-31 |  | Active | Log | Upd | SN-0654 | Schedule Change | Approved | 2020-06-14 18:38 | Changes to projects in the SE and CA regions due to material delays
WARNER ROBINS-OCML-IXR | SE | MGA | WRB | CB - Metro Core | CBMC SE MGA WRB OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-10-01 | 2020-08-31 |  | Active | Log | Upd | SN-0737 | Schedule Change | Approved | 2020-07-10 10:12 | Pushing out activation dates in the SER due to equipment delays Deleting duplicate record in CE and pushing out activation month due to site readiness delays
WARNER ROBINS-OCML-IXR | SE | MGA | WRB | CB - Metro Core | CBMC SE MGA WRB OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-10-01 | 2020-09-30 |  | Active | Log | Upd | SN-0819 | Schedule Change | Approved | 2020-08-14 15:09 | POR Changes for CBMC
CHNDCORA01-ROUTER | SW | ARZ | CHD | CB - Metro Core | CBMC SW ARZ CHD ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
CHNDCORA01-ROUTER | SW | ARZ | CHD | CB - Metro Core | CBMC SW ARZ CHD ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-09-15 | 2020-12-15 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
CHNDCORA01-ROUTER | SW | ARZ | CHD | CB - Metro Core | CBMC SW ARZ CHD ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
FWLRSYSA01-ROUTER | SW | ARZ | FWL | CB - Metro Core | CBMC SW ARZ FWL ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
FWLRSYSA01-ROUTER | SW | ARZ | FWL | CB - Metro Core | CBMC SW ARZ FWL ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-07-15 | 2020-10-15 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
FWLRSYSA01-ROUTER | SW | ARZ | FWL | CB - Metro Core | CBMC SW ARZ FWL ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-07-15 | 2020-06-20 |  | Deleted | Log | Upd | SN-0478 | Schedule Change | Approved | 2020-04-24 14:37 | Adjusting schedule dates across multpile PPMs
FWLRSYSA01-ROUTER | SW | ARZ | FWL | CB - Metro Core | CBMC SW ARZ FWL ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
CB Transport - New Router Fowler - FWL - Optics | SW | ARZ | FWL | CB - Metro Core | CBMC SW ARZ FWL Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-05-22 | 2020-07-15 |  | Active | EP
CB Transport - New Router Chandler/McDowellCORA - MCD - Card Add | SW | ARZ | MCD | CB - Metro Core | CBMC SW ARZ MCD Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-07-24 | 2020-09-15 |  | Active | EP
SSCTSYSA01-ROUTER | SW | ARZ | SSC | CB - Metro Core | CBMC SW ARZ SSC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-06-15 | 2020-07-31 |  | Active | EP
SSCTSYSA01-ROUTER | SW | ARZ | SSC | CB - Metro Core | CBMC SW ARZ SSC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-06-15 | 2020-09-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
SSCTSYSA01-ROUTER | SW | ARZ | SSC | CB - Metro Core | CBMC SW ARZ SSC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-06-15 | 2020-06-20 |  | Active | Log | Upd | SN-0478 | Schedule Change | Approved | 2020-04-24 14:37 | Adjusting schedule dates across multpile PPMs
SSCTSYSA01-ROUTER | SW | ARZ | SSC | CB - Metro Core | CBMC SW ARZ SSC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-06-15 | 2020-07-31 |  | Active | Log | Upd | SN-0618 | Schedule Change | Approved | 2020-06-05 14:52 | Removing deferred projects that still remain in the POR and moving out activation dates due to various equipment delays
ALIAA01.LV.LV.COX.NET-ROUTER | SW | LAS | ALI | CB - Metro Core | CBMC SW LAS ALI ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
ALIAA01.LV.LV.COX.NET-ROUTER | SW | LAS | ALI | CB - Metro Core | CBMC SW LAS ALI ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-10-15 | 2020-12-15 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
ALIAA01.LV.LV.COX.NET-ROUTER | SW | LAS | ALI | CB - Metro Core | CBMC SW LAS ALI ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
CB Transport - New Router Aliante - ALI - Optics | SW | LAS | ALI | CB - Metro Core | CBMC SW LAS ALI Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-08-03 | 2020-10-15 |  | Active | EP
VINNVA3624W-ROUTER | VA | NVA | TCR | CB - Metro Core | CBMC VA NVA TCR ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
VINNVA3624W-ROUTER | VA | NVA | TCR | CB - Metro Core | CBMC VA NVA TCR ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-05-15 | 2020-08-01 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
VINNVA3624W-ROUTER | VA | NVA | TCR | CB - Metro Core | CBMC VA NVA TCR ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
DNVLLABP2AW-24DNVHUB7750X02-ROUTER | SE | BTR | DVL | CB - Metro Core | CBMC SE BTR DVL ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
DNVLLABP2AW-24DNVHUB7750X02-ROUTER | SE | BTR | DVL | CB - Metro Core | CBMC SE BTR DVL ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-06-15 | 2020-09-15 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
DNVLLABP2AW-24DNVHUB7750X02-ROUTER | SE | BTR | DVL | CB - Metro Core | CBMC SE BTR DVL ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
CB Transport - New Router Donaldsonville - DVL - Optics | SE | BTR | DVL | CB - Metro Core | CBMC SE BTR DVL Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 2 | 2020-05-15 | 2020-06-15 |  | Active | EP
ELMWOOD-OCML-IXR | SE | NOR | ELM | CB - Metro Core | CBMC SE NOR ELM OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
ELMWOOD-OCML-IXR | SE | NOR | ELM | CB - Metro Core | CBMC SE NOR ELM OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0686 | New | Approved | 2020-06-22 10:17 | POR clean up for the CE and SE regions Deleting duplicate entries and adusting activation months
KENNER-OCML-IXR | SE | NOR | KNN | CB - Metro Core | CBMC SE NOR KNN OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
KENNER-OCML-IXR | SE | NOR | KNN | CB - Metro Core | CBMC SE NOR KNN OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0686 | New | Approved | 2020-06-22 10:17 | POR clean up for the CE and SE regions Deleting duplicate entries and adusting activation months
LAPALCO-OCML-IXR | SE | NOR | LPL | CB - Metro Core | CBMC SE NOR LPL OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
LAPALCO-OCML-IXR | SE | NOR | LPL | CB - Metro Core | CBMC SE NOR LPL OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0686 | New | Approved | 2020-06-22 10:17 | POR clean up for the CE and SE regions Deleting duplicate entries and adusting activation months
SOUTH BATON ROUGE-OCML-IXR | SE | BTR | SPC | CB - Metro Core | CBMC SE BTR SPC OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-10-01 | 2020-09-30 |  | Active | EP
SOUTH BATON ROUGE-OCML-IXR | SE | BTR | SPC | CB - Metro Core | CBMC SE BTR SPC OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-10-01 | 2020-09-30 |  | Active | Log | Upd | SN-0986 | Schedule Change | Approved | 2020-10-14 16:16 | Adjusting acticvation dates in the CE and SE regions
NESTA01.LV.LV.COX.NET-ROUTER | SW | LAS | VLY | CB - Metro Core | CBMC SW LAS VLY ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
NESTA01.LV.LV.COX.NET-ROUTER | SW | LAS | VLY | CB - Metro Core | CBMC SW LAS VLY ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-05-15 | 2020-08-15 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
NESTA01.LV.LV.COX.NET-ROUTER | SW | LAS | VLY | CB - Metro Core | CBMC SW LAS VLY ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
LIGHTFOOT-OCML-IXR | VA | HRD | LTF | CB - Metro Core | CBMC VA HRD LTF OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | EP
LIGHTFOOT-OCML-IXR | VA | HRD | LTF | CB - Metro Core | CBMC VA HRD LTF OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis | 2 | 2020-04-30 | 2020-07-31 |  | Deleted | Log | Upd | SN-0377 | Schedule Change | Canceled | 2020-04-14 09:04 | Pulling 1 38M for Nokia SR-7s and IXRs from Q3 and Q4 activities into Q2 due to acceleration
LIGHTFOOT-OCML-IXR | VA | HRD | LTF | CB - Metro Core | CBMC VA HRD LTF OCML-IXR-R6 7250 Deployment POR20 | Chassis | 2x Nokia 7250 IXR-R6 Chassis |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
CB Transport - New Router Portsmouth - PTM - Optics | VA | HRD | PTM | CB - Metro Core | CBMC VA HRD PTM Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-06-15 | 2020-12-31 |  | Active | EP
CB Transport - New Router Portsmouth - PTM - Optics | VA | HRD | PTM | CB - Metro Core | CBMC VA HRD PTM Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-06-15 | 2020-10-31 |  | Active | Log | Upd | SN-0934 | Schedule Change | Approved | 2020-09-18 09:35 | Moving out activation dates due to delays
CB Transport - New Router Portsmouth - PTM - Optics | VA | HRD | PTM | CB - Metro Core | CBMC VA HRD PTM Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 1 | 2020-06-15 | 2020-12-31 |  | Active | Log | Upd | SN-1049 | New | Approved | 2020-11-13 09:56 | Moving out activation dates for CBMC projects
VRBIVAFJ54W-A701FJ7750-ROUTER | VA | HRD | PRA | CB - Metro Core | CBMC VA HRD PRA ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
VRBIVAFJ54W-A701FJ7750-ROUTER | VA | HRD | PRA | CB - Metro Core | CBMC VA HRD PRA ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-10-15 | 2020-12-01 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
VRBIVAFJ54W-A701FJ7750-ROUTER | VA | HRD | PRA | CB - Metro Core | CBMC VA HRD PRA ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-04-30 | 2020-07-31 |  | Deleted | Log | Upd | SN-0377 | Schedule Change | Canceled | 2020-04-14 09:04 | Pulling 1 38M for Nokia SR-7s and IXRs from Q3 and Q4 activities into Q2 due to acceleration
VRBIVAFJ54W-A701FJ7750-ROUTER | VA | HRD | PRA | CB - Metro Core | CBMC VA HRD PRA ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
CB Transport - New Router Princess Anne - PRA - Optics | VA | HRD | PRA | CB - Metro Core | CBMC VA HRD PRA Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-09-15 | 2020-12-31 |  | Active | EP
CB Transport - New Router Princess Anne - PRA - Optics | VA | HRD | PRA | CB - Metro Core | CBMC VA HRD PRA Optics Only for Cisco T5 Augment POR20 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-09-15 | 2020-12-31 |  | Active | Log | Upd | SN-1049 | New | Approved | 2020-11-13 09:56 | Moving out activation dates for CBMC projects
ESCNEWAA01-ROUTER | CA | SAN | ESC | CB - Metro Core | CBMC CA SAN ESC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
ESCNEWAA01-ROUTER | CA | SAN | ESC | CB - Metro Core | CBMC CA SAN ESC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-04-15 | 2020-07-15 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
ESCNEWAA01-ROUTER | CA | SAN | ESC | CB - Metro Core | CBMC CA SAN ESC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
RSMTBSRA01-ROUTER | CA | ORG | RSM | CB - Metro Core | CBMC CA ORG RSM ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
RSMTBSRA01-ROUTER | CA | ORG | RSM | CB - Metro Core | CBMC CA ORG RSM ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-08-15 | 2020-11-15 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
RSMTBSRA01-ROUTER | CA | ORG | RSM | CB - Metro Core | CBMC CA ORG RSM ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
FAYTBSRA01-ROUTER | CE | NWA | FAY | CB - Metro Core | CBMC CE NWA FAY ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-06-15 | 2020-09-15 |  | Active | EP
FAYTBSRA01-ROUTER | CE | NWA | FAY | CB - Metro Core | CBMC CE NWA FAY ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-06-15 | 2020-09-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
CB Transport - New Router Harrison - FAY - Card Add | CE | NWA | FAY | CB - Metro Core | CBMC CE NWA FAY Optics Only for Cisco T5 Augment POR20_V2 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-04-15 | 2020-05-15 |  | Active | EP
CB Transport - New Router Harrison - FAY - Chassis Add | CE | NWA | FAY | CB - Metro Core | CBMC CE NWA FAY Cisco M6_M15 Chassis Augment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 1 | 2020-04-15 | 2020-05-15 |  | Active | EP
CB Transport - New Router Harrison - FAY - Chassis Add | CE | NWA | FAY | CB - Metro Core | CBMC CE NWA FAY Optics Only for Cisco T5 Augment POR20_V2 | Chassis | 1x Cisco M6 Transport Chassis | 1 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
CB Transport - New Router Harrison - FAY - Chassis Add | CE | NWA | FAY | CB - Metro Core | CBMC CE NWA FAY Cisco M6_M15 Chassis Augment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 1 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0419 | Schedule Change | Approved | 2020-04-02 09:36 | Updates driven by field audit and material delays
CB Transport - New Router Harrison - HRN - Optics | CE | NWA | HRN | CB - Metro Core | CBMC CE NWA FAY Optics Only for Cisco T5 Augment POR20_V2 | Card & Optics | Optics Only for Cisco T5 | 4 | 2020-04-15 | 2020-05-15 |  | Active | EP
JHSNBSRA01-ROUTER | CE | NWA | NWA | CB - Metro Core | CBMC CE NWA NWA ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
JHSNBSRA01-ROUTER | CE | NWA | NWA | CB - Metro Core | CBMC CE NWA NWA ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-06-15 | 2020-09-15 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
JHSNBSRA01-ROUTER | CE | NWA | NWA | CB - Metro Core | CBMC CE NWA NWA ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 1 | 2020-06-15 | 2020-09-15 |  | Deleted | Log | Upd | SN-0246 | Scope Change | Approved | 2020-02-24 12:37 | Audit of POR after outage Correcting errors in quantity counts There are no date changes or financial impacts
JHSNBSRA01-ROUTER | CE | NWA | NWA | CB - Metro Core | CBMC CE NWA NWA ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
CB Transport - New Router Harrison - NWA - Card Add | CE | NWA | NWA | CB - Metro Core | CBMC CE NWA NWA Optics Only for Cisco T5 Augment POR20_V2 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-04-15 | 2020-05-15 |  | Active | EP
TOPEBSRA01-ROUTER | CE | KAN | TOP | CB - Metro Core | CBMC CE KAN TOP ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-05-15 | 2020-11-30 |  | Active | EP
TOPEBSRA01-ROUTER | CE | KAN | TOP | CB - Metro Core | CBMC CE KAN TOP ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-05-15 | 2020-08-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
TOPEBSRA01-ROUTER | CE | KAN | TOP | CB - Metro Core | CBMC CE KAN TOP ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-05-15 | 2020-09-30 |  | Active | Log | Upd | SN-0934 | Schedule Change | Approved | 2020-09-18 09:35 | Moving out activation dates due to delays
TOPEBSRA01-ROUTER | CE | KAN | TOP | CB - Metro Core | CBMC CE KAN TOP ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-05-15 | 2020-10-31 |  | Active | Log | Upd | SN-0986 | Schedule Change | Approved | 2020-10-14 16:16 | Adjusting acticvation dates in the CE and SE regions
TOPEBSRA01-ROUTER | CE | KAN | TOP | CB - Metro Core | CBMC CE KAN TOP ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-05-15 | 2020-11-30 |  | Active | Log | Upd | SN-1049 | New | Approved | 2020-11-13 09:56 | Moving out activation dates for CBMC projects
sr01.mwc.okc.ok-ROUTER | CE | OKC | MWC | CB - Metro Core | CBMC CE OKC MWC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
sr01.mwc.okc.ok-ROUTER | CE | OKC | MWC | CB - Metro Core | CBMC CE OKC MWC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-09-15 | 2020-12-15 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
sr01.mwc.okc.ok-ROUTER | CE | OKC | MWC | CB - Metro Core | CBMC CE OKC MWC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
sr01.moo.okc.ok-ROUTER | CE | OKC | MOO | CB - Metro Core | CBMC CE OKC MOO ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
sr01.moo.okc.ok-ROUTER | CE | OKC | MOO | CB - Metro Core | CBMC CE OKC MOO ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-08-15 | 2020-11-15 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
sr01.moo.okc.ok-ROUTER | CE | OKC | MOO | CB - Metro Core | CBMC CE OKC MOO ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
sr01.neh.okc.ok-ROUTER | CE | OKC | NEH | CB - Metro Core | CBMC CE OKC NEH ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-08-15 | 2020-11-15 |  | Active | EP
sr01.neh.okc.ok-ROUTER | CE | OKC | NEH | CB - Metro Core | CBMC CE OKC NEH ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-08-15 | 2020-11-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
CB Transport - New Router Moore - OKC - Chassis Add | CE | OKC | OKC | CB - Metro Core | CBMC CE OKC OKC Optics Only for Cisco T5 Augment POR20_V2 | Chassis | 1x Cisco M6 Transport Chassis | 1 | 2020-07-15 | 2020-08-15 |  | Active | EP
CB Transport - New Router Moore - OKC - Chassis Add | CE | OKC | OKC | CB - Metro Core | CBMC CE OKC OKC Optics Only for Cisco T5 Augment POR20_V2 | Chassis | 1x Cisco M6 Transport Chassis | 1 | 2020-07-15 | 2020-08-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
sr01.qch.tul.ok-ROUTER | CE | TUL | QNC | CB - Metro Core | CBMC CE TUL QNC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
sr01.qch.tul.ok-ROUTER | CE | TUL | QNC | CB - Metro Core | CBMC CE TUL QNC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-09-15 | 2020-12-01 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
sr01.qch.tul.ok-ROUTER | CE | TUL | QNC | CB - Metro Core | CBMC CE TUL QNC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
OMHNBSRA01-ROUTER | CE | OMA | ONA | CB - Metro Core | CBMC CE OMA ONA ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-07-15 | 2020-10-15 |  | Active | EP
OMHNBSRA01-ROUTER | CE | OMA | ONA | CB - Metro Core | CBMC CE OMA ONA ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-07-15 | 2020-10-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
PRKSLAAA1GW-42STVHUB7750X02-ROUTER | SE | LFY | STM | CB - Metro Core | CBMC SE LFY STM ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
PRKSLAAA1GW-42STVHUB7750X02-ROUTER | SE | LFY | STM | CB - Metro Core | CBMC SE LFY STM ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-07-15 | 2020-10-01 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
PRKSLAAA1GW-42STVHUB7750X02-ROUTER | SE | LFY | STM | CB - Metro Core | CBMC SE LFY STM ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
MACNGAWH1AW-HOLTBSRA01-ROUTER | SE | MGA | HLT | CB - Metro Core | CBMC SE MGA HLT ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-07-15 | 2020-10-01 |  | Active | EP
MACNGAWH1AW-HOLTBSRA01-ROUTER | SE | MGA | HLT | CB - Metro Core | CBMC SE MGA HLT ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-07-15 | 2020-10-01 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
CB Transport - New Router South Scottsdale - CHD - Card Add | SW | ARZ | CHD | CB - Metro Core | CBMC SW ARZ CHD Cisco T5 card and optics Augment POR20_V2 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-04-17 | 2020-06-15 |  | Active | EP
CB Transport - New Router South Scottsdale - CHD - Card Add | SW | ARZ | CHD | CB - Metro Core | CBMC SW ARZ CHD Cisco T5 card and optics Augment POR20_V2 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-04-17 | 2020-06-15 |  | Active | Log | Upd | SN-0419 | Schedule Change | Approved | 2020-04-02 09:36 | Updates driven by field audit and material delays
CB Transport - New Router South Scottsdale - MCD - Card Add | SW | ARZ | MCD | CB - Metro Core | CBMC SW ARZ MCD Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-04-17 | 2020-06-15 |  | Active | EP
CB Transport - New Router South Scottsdale - MCD - Card Add | SW | ARZ | MCD | CB - Metro Core | CBMC SW ARZ MCD Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-04-17 | 2020-06-15 |  | Active | Log | Upd | SN-0419 | Schedule Change | Approved | 2020-04-02 09:36 | Updates driven by field audit and material delays
CB Transport - New Router South Scottsdale - SSC - Card Add | SW | ARZ | SSC | CB - Metro Core | CBMC SW ARZ SSC Optics Only for Cisco T5 Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-17 | 2020-06-15 |  | Active | EP
BTRILA771FW-24NTHHUB7750X02-ROUTER | SE | BTR | NTH | CB - Metro Core | CBMC SE BTR NTH ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
BTRILA771FW-24NTHHUB7750X02-ROUTER | SE | BTR | NTH | CB - Metro Core | CBMC SE BTR NTH ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-05-15 | 2020-08-15 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
BTRILA771FW-24NTHHUB7750X02-ROUTER | SE | BTR | NTH | CB - Metro Core | CBMC SE BTR NTH ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
BTRHLAUE1BW-24STCHUB7750X02-ROUTER | SE | BTR | STC | CB - Metro Core | CBMC SE BTR STC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
BTRHLAUE1BW-24STCHUB7750X02-ROUTER | SE | BTR | STC | CB - Metro Core | CBMC SE BTR STC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-05-15 | 2020-08-01 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
BTRHLAUE1BW-24STCHUB7750X02-ROUTER | SE | BTR | STC | CB - Metro Core | CBMC SE BTR STC ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
PTMOVADIBSRA7750-1-ROUTER | VA | HRD | PTM | CB - Metro Core | CBMC VA HRD PTM ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
PTMOVADIBSRA7750-1-ROUTER | VA | HRD | PTM | CB - Metro Core | CBMC VA HRD PTM ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-07-15 | 2020-10-01 |  | Deleted | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
PTMOVADIBSRA7750-1-ROUTER | VA | HRD | PTM | CB - Metro Core | CBMC VA HRD PTM ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-04-30 | 2020-07-31 |  | Deleted | Log | Upd | SN-0377 | Schedule Change | Canceled | 2020-04-14 09:04 | Pulling 1 38M for Nokia SR-7s and IXRs from Q3 and Q4 activities into Q2 due to acceleration
PTMOVADIBSRA7750-1-ROUTER | VA | HRD | PTM | CB - Metro Core | CBMC VA HRD PTM ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
CB Transport - New Router Strotherfield - WIC - Card Add | CE | KAN | WIC | CB - Metro Core | CBMC CE KAN WIC Cisco T5 Card and Optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-04-15 | 2020-05-15 |  | Active | EP
CB Transport - New Router Strotherfield - WIC - Card Add | CE | KAN | WIC | CB - Metro Core | CBMC CE KAN WIC OCML-IXR-R6 7250 Deployment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
CB Transport - New Router Strotherfield - WIC - Card Add | CE | KAN | WIC | CB - Metro Core | CBMC CE KAN WIC Cisco T5 Card and Optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-04-15 | 2020-05-15 |  | Active | Log | Upd | SN-0419 | Schedule Change | Approved | 2020-04-02 09:36 | Updates driven by field audit and material delays
CB Transport - New Router Sapulpa - SAP - Optics | CE | TUL | SAP | CB - Metro Core | CB Metro Core OKC SAP CB Card 2018 | Card & Optics | Optics Only for Cisco T5 | 3 | 2020-03-15 | 2020-04-15 |  | Active | EP
CB Transport - New Router Moore - OKC - Card Add | CE | OKC | OKC | CB - Metro Core | CBMC CE OKC OKC Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-07-15 | 2020-08-15 |  | Active | EP
CB Transport - New Router Moore - OKC - Card Add | CE | OKC | OKC | CB - Metro Core | CBMC CE OKC OKC Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-07-15 | 2020-08-15 |  | Active | Log | Upd | SN-0419 | Schedule Change | Approved | 2020-04-02 09:36 | Updates driven by field audit and material delays
CB Transport - New Router Midwest City - NOR - Card Add | CE | OKC | NOR | CB - Metro Core | CBMC CE OKC NOR Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-08-15 | 2020-09-15 |  | Active | EP
CB Transport - New Router Midwest City - NOR - Card Add | CE | OKC | NOR | CB - Metro Core | CBMC CE OKC NOR Cisco T5 card and optics Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-08-15 | 2020-09-15 |  | Active | Log | Upd | SN-0419 | Schedule Change | Approved | 2020-04-02 09:36 | Updates driven by field audit and material delays
LANGBSRA01 | COR | NAT | LA1 | CB - Metro Core | CBMC CA NAT LA1 COI 3_0 Deployment POR20 | Chassis | 2x Nokia 7750 SR-1 Chassis |  |  |  |  | Deleted | EP
LANGBSRA01 | COR | NAT | LA1 | CB - Metro Core | CBMC CA NAT LA1 COI 3_0 Deployment POR20 | Chassis | 2x Nokia 7750 SR-1 Chassis | 2 | 2020-03-15 | 2020-06-01 |  | Deleted | Log | New | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
LANGBSRA01 | COR | NAT | LA1 | CB - Metro Core | CBMC CA NAT LA1 COI 3_0 Deployment POR20 | Chassis | 2x Nokia 7750 SR-1 Chassis |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
SANJBSRA01 | COR | NAT | SV5 | CB - Metro Core | CBMC CA NAT SV5 COI 3_0 Deployment POR20 | Chassis | 2x Nokia 7750 SR-1 Chassis |  |  |  |  | Deleted | EP
SANJBSRA01 | COR | NAT | SV5 | CB - Metro Core | CBMC CA NAT SV5 COI 3_0 Deployment POR20 | Chassis | 2x Nokia 7750 SR-1 Chassis | 2 | 2020-03-15 | 2020-06-01 |  | Deleted | Log | New | SN-0144 | Schedule Change | Approved | 2020-02-06 11:07 | Final audit update of POR
SANJBSRA01 | COR | NAT | SV5 | CB - Metro Core | CBMC CA NAT SV5 COI 3_0 Deployment POR20 | Chassis | 2x Nokia 7750 SR-1 Chassis |  |  |  |  | Deleted | Log | Del | SN-0530 | COVID-19 Related | Approved | 2020-05-08 14:26 | Deleting projects from POR to align with 2020 deferrals
CHPKVAEHBSRA7750-1ROUTER | VA | HRD | CHS | CB - Metro Core | CBMC VA HRD CHS Nokia 7750 Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | EP
CHPKVAEHBSRA7750-1ROUTER | VA | HRD | CHS | CB - Metro Core | CBMC VA HRD CHS Nokia 7750 Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-05-01 | 2020-08-01 |  | Deleted | Log | New | SN-0226 | Schedule Change | Approved | 2020-02-03 16:48 | Adding Butler (Chesapeake) to the POR to replace Greenbrier in the plan
CHPKVAEHBSRA7750-1ROUTER | VA | HRD | CHS | CB - Metro Core | CBMC VA HRD CHS Nokia 7750 Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha |  |  |  |  | Deleted | Log | Del | SN-0618 | Schedule Change | Approved | 2020-06-05 14:52 | Removing deferred projects that still remain in the POR and moving out activation dates due to various equipment delays
SESTA01.LV.LV.COX.NET-ROUTER | SW | LAS | HEN | CB - Metro Core | CBMC SW LAS HEN ROUTER-7750 SR-7s Deployment POR20 v2 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-08-01 | 2020-11-30 |  | Active | EP
SESTA01.LV.LV.COX.NET-ROUTER | SW | LAS | HEN | CB - Metro Core | CBMC SW LAS HEN ROUTER-7750 SR-7s Deployment POR20 v2 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 2 | 2020-08-01 | 2020-11-30 |  | Active | Log | New | SN-0611 | Schedule Change | Approved | 2020-05-29 15:06 | Adjusting POR for CBMC
NWSTCORA01.LV.LV.COX.NET | SW | LAS | TEN | CB - Metro Core | CBMC SW LAS TEN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 1 | 2020-01-15 | 2020-09-30 |  | Active | EP
NWSTCORA01.LV.LV.COX.NET | SW | LAS | TEN | CB - Metro Core | CBMC SW LAS TEN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 1 | 2020-01-15 | 2020-07-20 |  | Active | Log | New | SN-0611 | Schedule Change | Approved | 2020-05-29 15:06 | Adjusting POR for CBMC
NWSTCORA01.LV.LV.COX.NET | SW | LAS | TEN | CB - Metro Core | CBMC SW LAS TEN ROUTER-7750 SR-7s Deployment POR20 | Chassis | 1x Nokia 7750 SR-7s Chassis and 1x 7210 SAS-Sx Cha | 1 | 2020-01-15 | 2020-09-30 |  | Active | Log | Upd | SN-0771 | Schedule Change | Approved | 2020-07-20 09:31 | Adjusting POR activation months in CE SE and SW due to impacts from equipment delays
CDN Deploy 11 | CA | SAN | ELC | CDN | CDN CA SAN ELC Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 1 | 2020-04-01 | 2020-06-30 | 2020-07-14 | Active | EP
CDN Deploy 11 | CA | SAN | ELC | CDN | CDN CA SAN ELC Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 1 | 2020-04-01 | 2020-06-30 | 2020-07-14 | Active | Log | Upd | SN-0285 | Schedule Change | Approved | 2020-02-24 12:38 | POR changes to reflect updated schedule No changes in financials
CDN Deploy 10 | CA | SAN | FED | CDN | CDN CA SAN FED Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 1 | 2020-04-01 | 2020-06-30 | 2020-07-14 | Active | EP
CDN Deploy 10 | CA | SAN | FED | CDN | CDN CA SAN FED Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 1 | 2020-04-01 | 2020-06-30 | 2020-07-14 | Active | Log | Upd | SN-0285 | Schedule Change | Approved | 2020-02-24 12:38 | POR changes to reflect updated schedule No changes in financials
CDN Deploy 12 | CE | KAN | WIC | CDN | CDN CE KAN WIC Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-06-01 | 2020-07-31 | 2020-08-14 | Active | EP
CDN Deploy 12 | CE | KAN | WIC | CDN | CDN CE KAN WIC Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-06-01 | 2020-07-31 | 2020-08-14 | Active | Log | Upd | SN-0285 | Schedule Change | Approved | 2020-02-24 12:38 | POR changes to reflect updated schedule No changes in financials
CDN Deploy 13 | CE | OKC | OKC | CDN | CDN CE OKC OKC Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-03-01 | 2020-04-30 | 2020-05-14 | Active | EP
CDN Deploy 13 | CE | OKC | OKC | CDN | CDN CE OKC OKC Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-06-01 | 2020-07-31 | 2020-08-14 | Active | Log | Upd | SN-0285 | Schedule Change | Approved | 2020-02-24 12:38 | POR changes to reflect updated schedule No changes in financials
CDN Deploy 13 | CE | OKC | OKC | CDN | CDN CE OKC OKC Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-03-01 | 2020-04-30 | 2020-05-14 | Active | Log | Upd | SN-0421 | Schedule Change | Approved | 2020-04-02 09:36 | This CR updates the POR as per latest plan, no change to financials
CDN Deploy 17 | NE | RHD | PRV | CDN | CDN NE RHD PRV Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-05-01 | 2020-06-30 | 2020-07-14 | Active | EP
CDN Deploy 17 | NE | RHD | PRV | CDN | CDN NE RHD PRV Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-05-01 | 2020-06-30 | 2020-07-14 | Active | Log | Upd | SN-0285 | Schedule Change | Approved | 2020-02-24 12:38 | POR changes to reflect updated schedule No changes in financials
CDN Deploy 14 | SE | GAN | GNS | CDN | CDN SE GAN GNS Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-08-01 | 2020-10-14 | 2020-11-01 | Active | EP
CDN Deploy 14 | SE | GAN | GNS | CDN | CDN SE GAN GNS Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-08-01 | 2020-09-20 | 2020-10-14 | Active | Log | Upd | SN-0285 | Schedule Change | Approved | 2020-02-24 12:38 | POR changes to reflect updated schedule No changes in financials
CDN Deploy 14 | SE | GAN | GNS | CDN | CDN SE GAN GNS Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-08-01 | 2020-10-14 | 2020-11-01 | Active | Log | Upd | SN-0803 | Schedule Change | Approved | 2020-08-07 09:43 | POR update for Dell server migration date change in Mesa Fowler Tucson Duke Drive Macon Federal Chandler Peoria Bell Gainesville Merrifield Blue Diamond and Chula Vista
CDN Deploy 7 | SE | BTR | BTR | CDN | CDN SE BTR BTR Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-05-01 | 2020-06-30 | 2020-07-14 | Active | EP
CDN Deploy 7 | SE | BTR | BTR | CDN | CDN SE BTR BTR Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-05-01 | 2020-06-30 | 2020-07-14 | Active | Log | Upd | SN-0285 | Schedule Change | Approved | 2020-02-24 12:38 | POR changes to reflect updated schedule No changes in financials
CDN Deploy 1 | SW | ARZ | CHD | CDN | CDN SW ARZ CHD Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 2 | 2020-02-20 | 2020-04-20 | 2020-05-04 | Active | EP
CDN Deploy 1 | SW | ARZ | CHD | CDN | CDN SW ARZ CHD Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 2 | 2020-02-20 | 2020-04-20 | 2020-05-04 | Active | Log | Upd | SN-0285 | Schedule Change | Approved | 2020-02-24 12:38 | POR changes to reflect updated schedule No changes in financials
CDN Deploy 2 | SW | ARZ | CHD | CDN | CDN SW ARZ CHD Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-03-01 | 2020-04-30 | 2020-05-14 | Active | EP
CDN Deploy 2 | SW | ARZ | CHD | CDN | CDN SW ARZ CHD Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-03-01 | 2020-04-30 | 2020-05-14 | Active | Log | Upd | SN-0285 | Schedule Change | Approved | 2020-02-24 12:38 | POR changes to reflect updated schedule No changes in financials
CDN Deploy 3 | SW | ARZ | MCD | CDN | CDN SW ARZ MCD Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 2 | 2020-02-20 | 2020-04-30 | 2020-05-04 | Active | EP
CDN Deploy 3 | SW | ARZ | MCD | CDN | CDN SW ARZ MCD Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 2 | 2020-02-20 | 2020-04-30 | 2020-05-04 | Active | Log | Upd | SN-0285 | Schedule Change | Approved | 2020-02-24 12:38 | POR changes to reflect updated schedule No changes in financials
CDN Deploy 4 | SW | ARZ | MCD | CDN | CDN SW ARZ MCD Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-03-01 | 2020-04-30 | 2020-05-14 | Active | EP
CDN Deploy 4 | SW | ARZ | MCD | CDN | CDN SW ARZ MCD Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-03-01 | 2020-04-30 | 2020-05-14 | Active | Log | Upd | SN-0285 | Schedule Change | Approved | 2020-02-24 12:38 | POR changes to reflect updated schedule No changes in financials
CDN Deploy 9 | SW | LAS | HEN | CDN | CDN SW LAS HEN Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 1 | 2020-04-01 | 2020-05-31 | 2020-06-14 | Active | EP
CDN Deploy 9 | SW | LAS | HEN | CDN | CDN SW LAS HEN Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 1 | 2020-04-01 | 2020-05-31 | 2020-06-14 | Active | Log | Upd | SN-0285 | Schedule Change | Approved | 2020-02-24 12:38 | POR changes to reflect updated schedule No changes in financials
CDN Deploy 8 | SW | LAS | TEN | CDN | CDN SW LAS TEN Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 1 | 2020-04-01 | 2020-05-31 | 2020-06-14 | Active | EP
CDN Deploy 8 | SW | LAS | TEN | CDN | CDN SW LAS TEN Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 1 | 2020-04-01 | 2020-05-31 | 2020-06-14 | Active | Log | Upd | SN-0285 | Schedule Change | Approved | 2020-02-24 12:38 | POR changes to reflect updated schedule No changes in financials
CDN Deploy 15 | VA | HRD | NRF | CDN | CDN VA HRD NRF Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 1 | 2020-07-01 | 2020-09-29 | 2020-10-13 | Active | EP
CDN Deploy 15 | VA | HRD | NRF | CDN | CDN VA HRD NRF Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 1 | 2020-07-01 | 2020-09-29 | 2020-10-13 | Active | Log | Upd | SN-0285 | Schedule Change | Approved | 2020-02-24 12:38 | POR changes to reflect updated schedule No changes in financials
CDN Deploy 16 | VA | HRD | VBC | CDN | CDN VA HRD VBC Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 1 | 2020-07-01 | 2020-09-29 | 2020-10-13 | Active | EP
CDN Deploy 16 | VA | HRD | VBC | CDN | CDN VA HRD VBC Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 1 | 2020-07-01 | 2020-09-29 | 2020-10-13 | Active | Log | Upd | SN-0285 | Schedule Change | Approved | 2020-02-24 12:38 | POR changes to reflect updated schedule No changes in financials
CDN Deploy 5 | VA | NVA | MFD | CDN | CDN VA NVA MFD Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 4 | 2020-08-01 | 2020-10-31 | 2020-11-13 | Active | EP
CDN Deploy 5 | VA | NVA | MFD | CDN | CDN VA NVA MFD Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 4 | 2020-08-01 | 2020-10-31 | 2020-11-13 | Active | Log | Upd | SN-0285 | Schedule Change | Approved | 2020-02-24 12:38 | POR changes to reflect updated schedule No changes in financials
CDN Deploy 6 | VA | NVA | MFD | CDN | CDN VA NVA MFD Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-08-01 | 2020-11-13 | 2020-11-30 | Active | EP
CDN Deploy 6 | VA | NVA | MFD | CDN | CDN VA NVA MFD Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-08-01 | 2020-10-31 | 2020-11-13 | Active | Log | Upd | SN-0285 | Schedule Change | Approved | 2020-02-24 12:38 | POR changes to reflect updated schedule No changes in financials
CDN Deploy 6 | VA | NVA | MFD | CDN | CDN VA NVA MFD Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-08-01 | 2020-11-13 | 2020-11-30 | Active | Log | Upd | SN-0803 | Schedule Change | Approved | 2020-08-07 09:43 | POR update for Dell server migration date change in Mesa Fowler Tucson Duke Drive Macon Federal Chandler Peoria Bell Gainesville Merrifield Blue Diamond and Chula Vista
CDN Deploy 18 | SW | ARZ | BEL | CDN | CDN SW ARZ BEL Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-05-01 | 2020-09-30 | 2020-10-15 | Active | EP
CDN Deploy 18 | SW | ARZ | BEL | CDN | CDN SW ARZ BEL Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-05-01 | 2020-07-30 | 2020-08-13 | Active | Log | New | SN-0285 | Schedule Change | Approved | 2020-02-24 12:38 | POR changes to reflect updated schedule No changes in financials
CDN Deploy 18 | SW | ARZ | BEL | CDN | CDN SW ARZ BEL Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-05-01 | 2020-09-30 | 2020-10-15 | Active | Log | Upd | SN-0803 | Schedule Change | Approved | 2020-08-07 09:43 | POR update for Dell server migration date change in Mesa Fowler Tucson Duke Drive Macon Federal Chandler Peoria Bell Gainesville Merrifield Blue Diamond and Chula Vista
CDN Deploy 19 | SW | ARZ | PEO | CDN | CDN SW ARZ PEO Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-07-01 | 2020-12-14 | 2020-12-30 | Active | EP
CDN Deploy 19 | SW | ARZ | PEO | CDN | CDN SW ARZ PEO Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-05-01 | 2020-07-30 | 2020-08-13 | Active | Log | New | SN-0285 | Schedule Change | Approved | 2020-02-24 12:38 | POR changes to reflect updated schedule No changes in financials
CDN Deploy 19 | SW | ARZ | PEO | CDN | CDN SW ARZ PEO Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-07-01 | 2020-12-14 | 2020-12-30 | Active | Log | Upd | SN-0803 | Schedule Change | Approved | 2020-08-07 09:43 | POR update for Dell server migration date change in Mesa Fowler Tucson Duke Drive Macon Federal Chandler Peoria Bell Gainesville Merrifield Blue Diamond and Chula Vista
CDN Deploy 20 | SW | ARZ | TUC | CDN | CDN SW ARZ TUC Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-06-01 | 2020-09-30 | 2020-10-15 | Active | EP
CDN Deploy 20 | SW | ARZ | TUC | CDN | CDN SW ARZ TUC Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-06-01 | 2020-08-30 | 2020-09-13 | Active | Log | New | SN-0285 | Schedule Change | Approved | 2020-02-24 12:38 | POR changes to reflect updated schedule No changes in financials
CDN Deploy 20 | SW | ARZ | TUC | CDN | CDN SW ARZ TUC Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-06-01 | 2020-09-30 | 2020-10-15 | Active | Log | Upd | SN-0803 | Schedule Change | Approved | 2020-08-07 09:43 | POR update for Dell server migration date change in Mesa Fowler Tucson Duke Drive Macon Federal Chandler Peoria Bell Gainesville Merrifield Blue Diamond and Chula Vista
CDN Deploy 21 | SW | ARZ | FWL | CDN | CDN SW ARZ FWL Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-06-01 | 2020-09-13 | 2020-09-30 | Active | EP
CDN Deploy 21 | SW | ARZ | FWL | CDN | CDN SW ARZ FWL Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-06-01 | 2020-08-30 | 2020-09-13 | Active | Log | New | SN-0285 | Schedule Change | Approved | 2020-02-24 12:38 | POR changes to reflect updated schedule No changes in financials
CDN Deploy 21 | SW | ARZ | FWL | CDN | CDN SW ARZ FWL Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-06-01 | 2020-09-13 | 2020-09-30 | Active | Log | Upd | SN-0803 | Schedule Change | Approved | 2020-08-07 09:43 | POR update for Dell server migration date change in Mesa Fowler Tucson Duke Drive Macon Federal Chandler Peoria Bell Gainesville Merrifield Blue Diamond and Chula Vista
CDN Deploy 22 | SE | MGA | MCN | CDN | CDN SE MGA MCN Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-07-01 | 2020-08-31 | 2020-09-14 | Active | EP
CDN Deploy 22 | SE | MGA | MCN | CDN | CDN SE MGA MCN Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-07-01 | 2020-09-29 | 2020-10-13 | Active | Log | New | SN-0285 | Schedule Change | Approved | 2020-02-24 12:38 | POR changes to reflect updated schedule No changes in financials
CDN Deploy 22 | SE | MGA | MCN | CDN | CDN SE MGA MCN Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-07-01 | 2020-08-31 | 2020-09-14 | Active | Log | Upd | SN-0803 | Schedule Change | Approved | 2020-08-07 09:43 | POR update for Dell server migration date change in Mesa Fowler Tucson Duke Drive Macon Federal Chandler Peoria Bell Gainesville Merrifield Blue Diamond and Chula Vista
CDN Deploy 23 | SW | LAS | BLU | CDN | CDN SW LAS BLU Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-07-01 | 2020-10-13 | 2020-10-30 | Active | EP
CDN Deploy 23 | SW | LAS | BLU | CDN | CDN SW LAS BLU Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-07-01 | 2020-09-29 | 2020-10-13 | Active | Log | New | SN-0285 | Schedule Change | Approved | 2020-02-24 12:38 | POR changes to reflect updated schedule No changes in financials
CDN Deploy 23 | SW | LAS | BLU | CDN | CDN SW LAS BLU Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-07-01 | 2020-10-13 | 2020-10-30 | Active | Log | Upd | SN-0803 | Schedule Change | Approved | 2020-08-07 09:43 | POR update for Dell server migration date change in Mesa Fowler Tucson Duke Drive Macon Federal Chandler Peoria Bell Gainesville Merrifield Blue Diamond and Chula Vista
CDN Deploy 27 | SW | ARZ | MSA | CDN | CDN SW ARZ MSA Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-10-15 | Active | EP
CDN Deploy 27 | SW | ARZ | MSA | CDN | CDN SW ARZ MSA Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-07-01 | 2020-09-29 | 2020-10-13 | Active | Log | New | SN-0285 | Schedule Change | Approved | 2020-02-24 12:38 | POR changes to reflect updated schedule No changes in financials
CDN Deploy 27 | SW | ARZ | MSA | CDN | CDN SW ARZ MSA Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-10-15 | Active | Log | Upd | SN-0803 | Schedule Change | Approved | 2020-08-07 09:43 | POR update for Dell server migration date change in Mesa Fowler Tucson Duke Drive Macon Federal Chandler Peoria Bell Gainesville Merrifield Blue Diamond and Chula Vista
CDN Deploy 24 | CA | SAN | CHU | CDN | CDN CA SAN CHU Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-10-01 | 2020-12-30 | 2021-01-13 | Active | EP
CDN Deploy 24 | CA | SAN | CHU | CDN | CDN CA SAN CHU Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-10-01 | 2020-12-30 | 2021-01-13 | Active | Log | New | SN-0285 | Schedule Change | Approved | 2020-02-24 12:38 | POR changes to reflect updated schedule No changes in financials
CDN Deploy 25 | COR | COR | DDR | CDN | CDN CO -CO DDR Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 4 | 2020-02-01 | 2020-08-31 | 2020-09-15 | Active | EP
CDN Deploy 25 | COR | COR | DDR | CDN | CDN CO -CO DDR Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 4 | 2020-02-01 | 2020-04-01 | 2020-04-15 | Active | Log | New | SN-0285 | Schedule Change | Approved | 2020-02-24 12:38 | POR changes to reflect updated schedule No changes in financials
CDN Deploy 25 | COR | COR | DDR | CDN | CDN CO -CO DDR Dell Server Deployment POR20 | Chassis | 1x Dell R740 Chassis | 4 | 2020-02-01 | 2020-08-31 | 2020-09-15 | Active | Log | Upd | SN-0803 | Schedule Change | Approved | 2020-08-07 09:43 | POR update for Dell server migration date change in Mesa Fowler Tucson Duke Drive Macon Federal Chandler Peoria Bell Gainesville Merrifield Blue Diamond and Chula Vista
CDN Deploy 26 | NE | CLE | CLV | CDN | CDN NE CLE CLV Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-10-01 | 2020-12-15 | 2020-12-31 | Active | EP
CDN Deploy 26 | NE | CLE | CLV | CDN | CDN NE CLE CLV Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-10-01 | 2020-11-30 | 2020-12-14 | Active | Log | New | SN-0285 | Schedule Change | Approved | 2020-02-24 12:38 | POR changes to reflect updated schedule No changes in financials
CDN Deploy 26 | NE | CLE | CLV | CDN | CDN NE CLE CLV Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 2 | 2020-10-01 | 2020-12-15 | 2020-12-31 | Active | Log | Upd | SN-0966 | Schedule Change | Approved | 2020-10-02 09:35 | CDN Dell Server migration date updates for Cleveland
CDN Deploy 28 | SW | ARZ | CHD | CDN | CDN SW ARZ CHD VHST Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 3 | 2020-05-01 | 2020-10-31 | 2020-11-15 | Active | EP
CDN Deploy 28 | SW | ARZ | CHD | CDN | CDN SW ARZ CHD VHST Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 3 | 2020-05-01 | 2020-06-30 | 2020-07-14 | Active | Log | Undel | SN-0421 | Schedule Change | Approved | 2020-04-02 09:36 | This CR updates the POR as per latest plan, no change to financials
CDN Deploy 28 | SW | ARZ | CHD | CDN | CDN SW ARZ CHD VHST Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 3 | 2020-05-01 | 2020-10-31 | 2020-11-15 | Active | Log | Upd | SN-0803 | Schedule Change | Approved | 2020-08-07 09:43 | POR update for Dell server migration date change in Mesa Fowler Tucson Duke Drive Macon Federal Chandler Peoria Bell Gainesville Merrifield Blue Diamond and Chula Vista
CDN Deploy 29 | CA | SAN | FED | CDN | CDN CA SAN FED VHST Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 3 | 2020-05-01 | 2020-10-31 | 2020-11-30 | Active | EP
CDN Deploy 29 | CA | SAN | FED | CDN | CDN CA SAN FED VHST Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 3 | 2020-05-01 | 2020-06-30 | 2020-07-14 | Active | Log | Undel | SN-0421 | Schedule Change | Approved | 2020-04-02 09:36 | This CR updates the POR as per latest plan, no change to financials
CDN Deploy 29 | CA | SAN | FED | CDN | CDN CA SAN FED VHST Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 3 | 2020-05-01 | 2020-10-31 | 2020-11-30 | Active | Log | Upd | SN-0803 | Schedule Change | Approved | 2020-08-07 09:43 | POR update for Dell server migration date change in Mesa Fowler Tucson Duke Drive Macon Federal Chandler Peoria Bell Gainesville Merrifield Blue Diamond and Chula Vista
CDN Deploy 30 | COR | COR | DDR | CDN | CDN CO -CO DDR VHST Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 6 | 2020-05-10 | 2020-10-31 | 2020-11-14 | Active | EP
CDN Deploy 30 | COR | COR | DDR | CDN | CDN CO -CO DDR VHST Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 6 | 2020-05-10 | 2020-06-30 | 2020-07-14 | Active | Log | Undel | SN-0421 | Schedule Change | Approved | 2020-04-02 09:36 | This CR updates the POR as per latest plan, no change to financials
CDN Deploy 30 | COR | COR | DDR | CDN | CDN CO -CO DDR VHST Dell Server Deployment POR20 | Chassis | 1x Dell R640 Chassis | 6 | 2020-05-10 | 2020-10-31 | 2020-11-14 | Active | Log | Upd | SN-0803 | Schedule Change | Approved | 2020-08-07 09:43 | POR update for Dell server migration date change in Mesa Fowler Tucson Duke Drive Macon Federal Chandler Peoria Bell Gainesville Merrifield Blue Diamond and Chula Vista
CFG MOO AC-CFG GEN GROW PROJECT - MEDIUM | CE | OKC | MOO | Critical Facilities (Grow) | CFG CE OKC MOO AC-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG NEH AC-CFG GEN GROW PROJECT - MEDIUM | CE | OKC | NEH | Critical Facilities (Grow) | CFG CE OKC NEH AC-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG SEH AC-CFG GEN GROW PROJECT - MEDIUM | CE | OKC | SEH | Critical Facilities (Grow) | CFG CE OKC SEH BS-CFG Deployment POR20_0 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG SEH AC-CFG GEN GROW PROJECT - MEDIUM | CE | OKC | SEH | Critical Facilities (Grow) | CFG CE OKC SEH BS-CFG Deployment POR20_0 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG SOU BD-CFG GEN GROW PROJECT - MEDIUM | CE | OMA | SOU | Critical Facilities (Grow) | CFG CE OMA SOU BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-04-01 | 2020-04-15 |  | Active | EP
CFG GAR BD-CFG GEN GROW PROJECT - MEDIUM | CE | TUL | GAR | Critical Facilities (Grow) | CFG CE TUL GAR BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG WES BD-CFG GEN GROW PROJECT - LARGE | CE | OMA | WES | Critical Facilities (Grow) | CFG CE OMA WES BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-04-01 | 2020-04-15 |  | Active | EP
CFG WIC BD-CFG GEN GROW PROJECT - MEDIUM | CE | KAN | WIC | Critical Facilities (Grow) | CFG CE KAN WIC BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG OWA BD-CFG GEN GROW PROJECT - MEDIUM | CE | TUL | OWA | Critical Facilities (Grow) | CFG CE TUL OWA BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG QNC BD-CFG GEN GROW PROJECT - MEDIUM | CE | TUL | QNC | Critical Facilities (Grow) | CFG CE TUL QNC BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG SAP BD-CFG GEN GROW PROJECT - MEDIUM | CE | TUL | SAP | Critical Facilities (Grow) | CFG CE TUL SAP BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG BRD BD-CFG GEN GROW PROJECT - MEDIUM | CE | TUL | BRD | Critical Facilities (Grow) | CFG CE TUL BRD BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG DTN BD-CFG GEN GROW PROJECT - MEDIUM | CE | TUL | DTN | Critical Facilities (Grow) | CFG CE TUL DTN BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG WLH BD-CFG GEN GROW PROJECT - MEDIUM | CE | OKC | WLH | Critical Facilities (Grow) | CFG CE OKC WLH BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG ONA BD-CFG GEN GROW PROJECT - MEDIUM | CE | OMA | ONA | Critical Facilities (Grow) | CFG CE OMA ONA BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-04-01 | 2020-04-15 |  | Active | EP
CFG GBD BD-CFG GEN GROW PROJECT - LARGE | CE | KAN | GBD | Critical Facilities (Grow) | CFG CE KAN GBD BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG GDY GN-CFG GEN GROW PROJECT - LARGE | CE | KAN | GDY | Critical Facilities (Grow) | CFG CE KAN GDY GN-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG BLV GN-CFG GEN GROW PROJECT - LARGE | CE | OMA | BLV | Critical Facilities (Grow) | CFG CE OMA BLV GN-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG DBY GN-CFG GEN GROW PROJECT - LARGE | CE | KAN | DBY | Critical Facilities (Grow) | CFG CE KAN DBY HV-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG OMM GN-CFG GEN GROW PROJECT - LARGE | CE | OMA | OMM | Critical Facilities (Grow) | CFG CE OMA OMM GN-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-04-01 | 2020-04-15 |  | Active | EP
CFG CNY GN-CFG GEN GROW PROJECT - MEDIUM | CE | KAN | CNY | Critical Facilities (Grow) | CFG CE KAN CNY GN-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG SSP GN-CFG GEN GROW PROJECT - LARGE | CE | NWA | SSP | Critical Facilities (Grow) | CFG CE NWA SSP GN-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-04-01 | 2020-04-15 |  | Active | EP
CFG SDN GN-CFG GEN GROW PROJECT - MEDIUM | CE | KAN | SDN | Critical Facilities (Grow) | CFG CE KAN SDN GN-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-04-01 | 2020-04-15 |  | Active | EP
CFG OLA GN-CFG GEN GROW PROJECT - MEDIUM | CE | KAN | OLA | Critical Facilities (Grow) | CFG CE KAN OLA GN-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG PIT GN-CFG GEN GROW PROJECT - LARGE | CE | KAN | PIT | Critical Facilities (Grow) | CFG CE KAN PIT GN-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-04-01 | 2020-04-15 |  | Active | EP
CFG DBY HV-CFG GEN GROW PROJECT - LARGE | CE | KAN | DBY | Critical Facilities (Grow) | CFG CE KAN DBY HV-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-04-01 | 2020-04-15 |  | Active | EP
CFG NCH HV-CFG GEN GROW PROJECT - MEDIUM | CE | OKC | NCH | Critical Facilities (Grow) | CFG CE OKC NCH HV-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-04-01 | 2020-04-15 |  | Active | EP
CFG NWT HV-CFG GEN GROW PROJECT - MEDIUM | CE | KAN | NWT | Critical Facilities (Grow) | CFG CE KAN NWT HV-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-07-01 | 2020-07-15 |  | Active | EP
CFG CLH HV-CFG GEN GROW PROJECT - MEDIUM | CE | OKC | CLH | Critical Facilities (Grow) | CFG CE OKC CLH BS-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG NEH HV-CFG GEN GROW PROJECT - MEDIUM | CE | OKC | NEH | Critical Facilities (Grow) | CFG CE OKC NEH AC-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG SEH HV-CFG GEN GROW PROJECT - MEDIUM | CE | OKC | SEH | Critical Facilities (Grow) | CFG CE OKC SEH BS-CFG Deployment POR20_0 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG SEH HV-CFG GEN GROW PROJECT - MEDIUM | CE | OKC | SEH | Critical Facilities (Grow) | CFG CE OKC SEH BS-CFG Deployment POR20_0 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG WLH HV-CFG GEN GROW PROJECT - MEDIUM | CE | OKC | WLH | Critical Facilities (Grow) | CFG CE OKC WLH BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG GBD HV-CFG GEN GROW PROJECT - MEDIUM | CE | KAN | GBD | Critical Facilities (Grow) | CFG CE KAN GBD BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-04-01 | 2020-04-15 |  | Active | EP
CFG CBL HV-CFG GEN GROW PROJECT - SMALL | CE | OMA | CBL | Critical Facilities (Grow) | CFG CE OMA CBL RK-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-04-01 | 2020-04-15 |  | Active | EP
CFG WES HV-CFG GEN GROW PROJECT - SMALL | CE | OMA | WES | Critical Facilities (Grow) | CFG CE OMA WES BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-04-01 | 2020-04-15 |  | Active | EP
CFG MPN HV-CFG GEN GROW PROJECT - LARGE | CE | KAN | MPN | Critical Facilities (Grow) | CFG CE KAN MPN HV-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG BAR RK-CBMC GEN GROW PROJECT - SMALL | CE | TUL | BAR | Critical Facilities (Grow) | CFG CE TUL BAR RK-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG BER RK-CBMC GEN GROW PROJECT - SMALL | CE | NWA | BER | Critical Facilities (Grow) | CFG CE ARK BER RK-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG BVL RK-CBMC GEN GROW PROJECT - SMALL | CE | NWA | BVL | Critical Facilities (Grow) | CFG CE ARK BVL IV MEDIUM Deployment POR19 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG BVL RK-CBMC GEN GROW PROJECT - SMALL | CE | NWA | BVL | Critical Facilities (Grow) | CFG CE ARK BVL IV MEDIUM Deployment POR19 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG ELR RK-CBMC GEN GROW PROJECT - SMALL | CE | OKC | ELR | Critical Facilities (Grow) | CFG CE OKC ELR RK-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG OWA RK-CBMC GEN GROW PROJECT - SMALL | CE | TUL | OWA | Critical Facilities (Grow) | CFG CE TUL OWA BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG QNC RK-CBMC GEN GROW PROJECT - SMALL | CE | TUL | QNC | Critical Facilities (Grow) | CFG CE TUL QNC BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG SAP RK-CBMC GEN GROW PROJECT - SMALL | CE | TUL | SAP | Critical Facilities (Grow) | CFG CE TUL SAP BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG VBN RK-CBMC GEN GROW PROJECT - SMALL | CE | NWA | VBN | Critical Facilities (Grow) | CFG CE ARK VBN RK-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG CBL RK-R PHY GEN GROW PROJECT - MEDIUM | CE | OMA | CBL | Critical Facilities (Grow) | CFG CE OMA CBL RK-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG MOO RK-CFG GEN GROW PROJECT - SMALL | CE | OKC | MOO | Critical Facilities (Grow) | CFG CE OKC MOO AC-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG SEH RK-CFG GEN GROW PROJECT - MEDIUM | CE | OKC | SEH | Critical Facilities (Grow) | CFG CE OKC SEH BS-CFG Deployment POR20_0 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG SEH RK-CFG GEN GROW PROJECT - MEDIUM | CE | OKC | SEH | Critical Facilities (Grow) | CFG CE OKC SEH BS-CFG Deployment POR20_0 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG WLH RK-CFG GEN GROW PROJECT - SMALL | CE | OKC | WLH | Critical Facilities (Grow) | CFG CE OKC WLH BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG GAR RK-CFG GEN GROW PROJECT - MEDIUM | CE | TUL | GAR | Critical Facilities (Grow) | CFG CE TUL GAR BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG SOU RK-CFG GEN GROW PROJECT - MEDIUM | CE | OMA | SOU | Critical Facilities (Grow) | CFG CE OMA SOU BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-07-01 | 2020-07-15 |  | Active | EP
CFG TOP RK-CFG GEN GROW PROJECT - SMALL | CE | KAN | TOP | Critical Facilities (Grow) | CFG CE KAN TOP RK-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-04-01 | 2020-04-15 |  | Active | EP
CFG ONA RK-R PHY GEN GROW PROJECT - MEDIUM | CE | OMA | ONA | Critical Facilities (Grow) | CFG CE OMA ONA BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-04-01 | 2020-04-15 |  | Active | EP
CFG HRN RK-CFG GEN GROW PROJECT - SMALL | CE | NWA | HRN | Critical Facilities (Grow) | CFG CE ARK HRN RK-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG WES RK-CFG GEN GROW PROJECT - MEDIUM | CE | OMA | WES | Critical Facilities (Grow) | CFG CE OMA WES BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-07-01 | 2020-07-15 |  | Active | EP
CFG OKC RC-CFG GEN GROW PROJECT - MEDIUM | CE | OKC | OKC | Critical Facilities (Grow) | CFG CE OKC OKC BS-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG STR RC-CFG GEN GROW PROJECT - MEDIUM | CE | KAN | STR | Critical Facilities (Grow) | CFG CE KAN STR RC-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG WIC IV-CFG GEN GROW PROJECT - MEDIUM | CE | KAN | WIC | Critical Facilities (Grow) | CFG CE KAN WIC BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG ONA BS-CFG GEN GROW PROJECT - MEDIUM | CE | OMA | ONA | Critical Facilities (Grow) | CFG CE OMA ONA BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-04-01 | 2020-04-15 |  | Active | EP
CFG OKC BS-CFG GEN GROW PROJECT - MEDIUM | CE | OKC | OKC | Critical Facilities (Grow) | CFG CE OKC OKC BS-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG WLH BS-CFG GEN GROW PROJECT - MEDIUM | CE | OKC | WLH | Critical Facilities (Grow) | CFG CE OKC WLH BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG CLH BS-CFG GEN GROW PROJECT - LARGE | CE | OKC | CLH | Critical Facilities (Grow) | CFG CE OKC CLH BS-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG CHO BS-CFG GEN GROW PROJECT - MEDIUM | CE | OKC | CHO | Critical Facilities (Grow) | CFG CE OKC CHO BS-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG NOR BS-CFG GEN GROW PROJECT - LARGE | CE | OKC | NOR | Critical Facilities (Grow) | CFG CE OKC NOR BS-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG SEH BS-CFG GEN GROW PROJECT - LARGE | CE | OKC | SEH | Critical Facilities (Grow) | CFG CE OKC SEH BS-CFG Deployment POR20_0 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG SEH BS-CFG GEN GROW PROJECT - LARGE | CE | OKC | SEH | Critical Facilities (Grow) | CFG CE OKC SEH BS-CFG Deployment POR20_0 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG BLV RK-CFG GEN GROW PROJECT - MEDIUM | CE | OMA | BLV | Critical Facilities (Grow) | CFG CE OMA BLV GN-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-06 | 2020-02-15 |  | Active | EP
CFG NWA RK-CFG GEN GROW PROJECT - MEDIUM | CE | NWA | NWA | Critical Facilities (Grow) | CFG CE ARK NWA BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-06 | 2020-02-15 |  | Active | EP
CFG NOR BD-CFG GEN GROW PROJECT - MEDIUM | CE | OKC | NOR | Critical Facilities (Grow) | CFG CE OKC NOR BS-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-06 | 2020-02-15 |  | Active | EP
CFG NWA BD-CFG GEN GROW PROJECT - MEDIUM | CE | NWA | NWA | Critical Facilities (Grow) | CFG CE ARK NWA BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-06 | 2020-02-15 |  | Active | EP
CFG SEH DC-CFG GEN GROW PROJECT - MEDIUM | CE | OKC | SEH | Critical Facilities (Grow) | CFG CE OKC SEH BS-CFG Deployment POR20_0 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG SEH DC-CFG GEN GROW PROJECT - MEDIUM | CE | OKC | SEH | Critical Facilities (Grow) | CFG CE OKC SEH BS-CFG Deployment POR20_0 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG PNS BD-CFG NEWBDCBB_8_PANEL | SE | GCT | PNS | Critical Facilities (Grow) | CFG SE GCT PNS BS-MEDIUM Deployment POR19 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG PNS BD-CFG NEWBDCBB_8_PANEL | SE | GCT | PNS | Critical Facilities (Grow) | CFG SE GCT PNS BS-MEDIUM Deployment POR19 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG PNS BS-CFG LARGE_2V_BATTSTRING | SE | GCT | PNS | Critical Facilities (Grow) | CFG SE GCT PNS BS-MEDIUM Deployment POR19 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG PNS BS-CFG LARGE_2V_BATTSTRING | SE | GCT | PNS | Critical Facilities (Grow) | CFG SE GCT PNS BS-MEDIUM Deployment POR19 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG LFY BS-CFG LARGE_2V_BATTSTRING | SE | LFY | LFY | Critical Facilities (Grow) | CFG SE LFY LFY AC SMALL Deployment POR19 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG LFY BS-CFG LARGE_2V_BATTSTRING | SE | LFY | LFY | Critical Facilities (Grow) | CFG SE LFY LFY AC SMALL Deployment POR19 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG BTR BS-CFG LARGE_2V_BATTSTRING | SE | BTR | BTR | Critical Facilities (Grow) | CFG SE BTR BTR AC SMALL Deployment POR19 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG BTR BS-CFG LARGE_2V_BATTSTRING | SE | BTR | BTR | Critical Facilities (Grow) | CFG SE BTR BTR AC SMALL Deployment POR19 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG LUL BS-CFG LARGE_2V_BATTSTRING | SE | NOR | LUL | Critical Facilities (Grow) | CFG SE NOR LUL AC SMALL Deployment POR19 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG LUL BS-CFG LARGE_2V_BATTSTRING | SE | NOR | LUL | Critical Facilities (Grow) | CFG SE NOR LUL AC SMALL Deployment POR19 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG LFY HV-CFG HVAC_31-40TON | SE | LFY | LFY | Critical Facilities (Grow) | CFG SE LFY LFY AC SMALL Deployment POR19 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG LFY HV-CFG HVAC_31-40TON | SE | LFY | LFY | Critical Facilities (Grow) | CFG SE LFY LFY AC SMALL Deployment POR19 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG LUL RC-CFG GEN GROW PROJECT - SMALL | SE | NOR | LUL | Critical Facilities (Grow) | CFG SE NOR LUL AC SMALL Deployment POR19 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG LUL RC-CFG GEN GROW PROJECT - SMALL | SE | NOR | LUL | Critical Facilities (Grow) | CFG SE NOR LUL AC SMALL Deployment POR19 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG OCN BD-CFG NEWBDCBB_6_PANEL | VA | HRD | OCN | Critical Facilities (Grow) | CFG VA HRD OCN BD-CFG Deployment POR20 | Critical Facilities | NEWBDCBB_6_PANEL | 1 | 2020-01-01 | 2020-02-15 |  | Active | EP
CFG PTM BD-CFG GEN GROW PROJECT - MEDIUM | VA | HRD | PTM | Critical Facilities (Grow) | CFG VA HRD PTM BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG DRA BS-CFG LARGE_2V_BATTSTRING | VA | NVA | DRA | Critical Facilities (Grow) | CFG VA NVA DRA BS-CFG Deployment POR20 | Critical Facilities | LARGE_2V_BATTSTRING | 1 | 2020-01-01 | 2020-03-15 |  | Active | EP
CFG FBG BS-CFG LARGE_2V_BATTSTRING | VA | NVA | FBG | Critical Facilities (Grow) | CFG VA NVA FBG BS-CFG Deployment POR20 | Critical Facilities | LARGE_2V_BATTSTRING | 1 | 2020-01-01 | 2020-03-15 |  | Active | EP
CFG JCC BS-CFG LARGE_2V_BATTSTRING | VA | HRD | JCC | Critical Facilities (Grow) | CFG VA HRD JCC BS-CFG Deployment POR20 | Critical Facilities | LARGE_2V_BATTSTRING | 1 | 2020-01-01 | 2020-03-15 |  | Active | EP
CFG LTF BS-CFG LARGE_2V_BATTSTRING | VA | HRD | LTF | Critical Facilities (Grow) | CFG VA HRD LTF BS-CFG Deployment POR20 | Critical Facilities | LARGE_2V_BATTSTRING | 1 | 2020-01-01 | 2020-05-15 |  | Active | EP
CFG MFD BS-CFG LARGE_2V_BATTSTRING | VA | NVA | MFD | Critical Facilities (Grow) | CFG VA NVA MFD BS-CFG Deployment POR20 | Critical Facilities | LARGE_2V_BATTSTRING | 1 | 2020-01-01 | 2020-06-15 |  | Active | EP
CFG RON BS-CFG LARGE_2V_BATTSTRING | VA | ROA | RON | Critical Facilities (Grow) | CFG VA ROA RON BS-CFG Deployment POR20 | Critical Facilities | LARGE_2V_BATTSTRING | 1 | 2020-01-01 | 2020-02-15 |  | Active | EP
CFG NRF AT-CFG GEN GROW PROJECT - MEDIUM | VA | HRD | NRF | Critical Facilities (Grow) | CFG VA HRD NRF AT-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-04-15 |  | Active | EP
CFG NWP AT-CFG GEN GROW PROJECT - MEDIUM | VA | HRD | NWP | Critical Facilities (Grow) | CFG VA HRD NWP AT-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG CHS RC-CFG GEN GROW PROJECT - MEDIUM | VA | HRD | CHS | Critical Facilities (Grow) | CFG VA HRD CHS RC-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-01 | 2020-05-15 |  | Active | EP
CFG PTH BD-MRTR BDFBSPLIT_0-150 | NE | RHD | PTH | Critical Facilities (Grow) | CFG NE RHD PTH BD-CFG Deployment POR20 | Critical Facilities | BDFBSPLIT_0-150 | 1 | 2020-01-20 | 2020-03-15 |  | Active | EP
CFG ENF BD-MTRN BDFBSPLIT_0-150 | NE | CON | ENF | Critical Facilities (Grow) | CFG NE CON ENF BD-CFG Deployment POR20 | Critical Facilities | BDFBSPLIT_0-150 | 1 | 2020-01-20 | 2020-03-15 |  | Active | EP
CFG MAN BD-MTRN NEWBDCBB_6_PANEL | NE | CON | MAN | Critical Facilities (Grow) | CFG NE CON MAN GN-CFG Deployment POR20 | Critical Facilities | NEWBDCBB_6_PANEL | 1 | 2020-01-20 | 2020-03-15 |  | Active | EP
CFG CLV RK-CFG GEN GROW PROJECT - LARGE | NE | CLE | CLV | Critical Facilities (Grow) | CFG NE CLE CLV RK LARGE Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-03-18 | 2020-03-15 |  | Active | EP
CFG CLV RK-CFG GEN GROW PROJECT - LARGE | NE | CLE | CLV | Critical Facilities (Grow) | CFG NE CLE CLV RK LARGE Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-03-01 | 2020-03-15 |  | Active | Log | Upd | SN-0593 | Schedule Change | Canceled | 2020-06-22 11:08 | updating need by date for grown projects
CFG MAN GN-CFG GENSET_500-750KW | NE | CON | MAN | Critical Facilities (Grow) | CFG NE CON MAN GN-CFG Deployment POR20 | Critical Facilities | GENSET_500-750KW | 1 | 2020-03-20 | 2020-03-15 |  | Active | EP
CFG MAN GN-CFG GENSET_500-750KW | NE | CON | MAN | Critical Facilities (Grow) | CFG NE CON MAN GN-CFG Deployment POR20 | Critical Facilities | GENSET_500-750KW | 1 | 2020-03-01 | 2020-03-15 |  | Active | Log | Upd | SN-0593 | Schedule Change | Canceled | 2020-06-22 11:08 | updating need by date for grown projects
CFG MAN BS-MTRN LARGE_2V_BATTSTRING | NE | CON | MAN | Critical Facilities (Grow) | CFG NE CON MAN GN-CFG Deployment POR20 | Critical Facilities | LARGE_2V_BATTSTRING | 1 | 2020-03-20 | 2020-03-15 |  | Active | EP
CFG RMD BS-CBMC LARGE_2V_BATTSTRING | NE | RHD | RMD | Critical Facilities (Grow) | CFG NE RHD RMD BS-CFG Deployment POR20 | Critical Facilities | LARGE_2V_BATTSTRING | 1 | 2020-02-15 | 2020-05-15 |  | Active | EP
CFG HEN BU-CFG GEN GROW PROJECT - LARGE | SW | LAS | HEN | Critical Facilities (Grow) | CFG SW LAS HEN AC MEDIUM Augment POR19 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG HEN BU-CFG GEN GROW PROJECT - LARGE | SW | LAS | HEN | Critical Facilities (Grow) | CFG SW LAS HEN AC MEDIUM Augment POR19 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG SSC BD-CFG GEN GROW PROJECT - LARGE | SW | ARZ | SSC | Critical Facilities (Grow) | CFG SW ARZ SSC GN-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-04-01 | 2020-06-15 |  | Active | EP
CFG PEO BD-CFG GEN GROW PROJECT - LARGE | SW | ARZ | PEO | Critical Facilities (Grow) | CFG SW ARZ PEO RC LARGE Augment POR19 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG PEO BD-CFG GEN GROW PROJECT - LARGE | SW | ARZ | PEO | Critical Facilities (Grow) | CFG SW ARZ PEO RC LARGE Augment POR19 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG FWL BD-CFG GEN GROW PROJECT - LARGE | SW | ARZ | FWL | Critical Facilities (Grow) | CFG SW ARZ FWL RC LARGE Augment POR19 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG FWL BD-CFG GEN GROW PROJECT - LARGE | SW | ARZ | FWL | Critical Facilities (Grow) | CFG SW ARZ FWL RC LARGE Augment POR19 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG CHD BD-CFG GEN GROW PROJECT - LARGE | SW | ARZ | CHD | Critical Facilities (Grow) | CFG SW ARZ CHD BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-03-01 | 2020-07-15 |  | Active | EP
CFG TUC BD-CFG GEN GROW PROJECT - LARGE | SW | ARZ | TUC | Critical Facilities (Grow) | CFG SW ARZ TUC BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-03-01 | 2020-08-15 |  | Active | EP
CFG TEN BD-CFG GEN GROW PROJECT - LARGE | SW | LAS | TEN | Critical Facilities (Grow) | CFG SW LAS TEN HV-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-07-01 | 2020-06-15 |  | Active | EP
CFG CHD DC-CFG GEN GROW PROJECT - MEDIUM | SW | ARZ | CHD | Critical Facilities (Grow) | CFG SW ARZ CHD BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-07-01 | 2020-09-15 |  | Active | EP
CFG CHD DC-CFG GEN GROW PROJECT - SMALL | SW | ARZ | CHD | Critical Facilities (Grow) | CFG SW ARZ CHD BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-03-01 | 2020-05-15 |  | Active | EP
CFG FWL DC-CFG GEN GROW PROJECT - LARGE | SW | ARZ | FWL | Critical Facilities (Grow) | CFG SW ARZ FWL RC LARGE Augment POR19 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG FWL DC-CFG GEN GROW PROJECT - LARGE | SW | ARZ | FWL | Critical Facilities (Grow) | CFG SW ARZ FWL RC LARGE Augment POR19 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG TEN HV-CFG GEN GROW PROJECT - MEDIUM | SW | LAS | TEN | Critical Facilities (Grow) | CFG SW LAS TEN HV-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-06-01 | 2020-07-15 |  | Active | EP
CFG PNL HV-CFG GEN GROW PROJECT - MEDIUM | SW | ARZ | PNL | Critical Facilities (Grow) | CFG SW ARZ PNL GN-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-06-01 | 2020-07-15 |  | Active | EP
CFG TEN HV-CFG GEN GROW PROJECT - LARGE | SW | LAS | TEN | Critical Facilities (Grow) | CFG SW LAS TEN HV-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-02-01 | 2020-05-15 |  | Active | EP
CFG HEN HV-CFG GEN GROW PROJECT - LARGE | SW | LAS | HEN | Critical Facilities (Grow) | CFG SW LAS HEN AC MEDIUM Augment POR19 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG HEN HV-CFG GEN GROW PROJECT - LARGE | SW | LAS | HEN | Critical Facilities (Grow) | CFG SW LAS HEN AC MEDIUM Augment POR19 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG CEN HV-CFG GEN GROW PROJECT - LARGE | SW | LAS | CEN | Critical Facilities (Grow) | CFG SW LAS CEN RC LARGE Augment POR19 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG CEN HV-CFG GEN GROW PROJECT - LARGE | SW | LAS | CEN | Critical Facilities (Grow) | CFG SW LAS CEN RC LARGE Augment POR19 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG BEL HV-CFG GEN GROW PROJECT - LARGE | SW | ARZ | BEL | Critical Facilities (Grow) | CFG SW ARZ BEL BD MEDIUM Deployment POR19 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG BEL HV-CFG GEN GROW PROJECT - LARGE | SW | ARZ | BEL | Critical Facilities (Grow) | CFG SW ARZ BEL BD MEDIUM Deployment POR19 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG CHD HV-CFG GEN GROW PROJECT - LARGE | SW | ARZ | CHD | Critical Facilities (Grow) | CFG SW ARZ CHD BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-09-01 | 2020-10-15 |  | Active | EP
CFG MSA HV-CFG GEN GROW PROJECT - MEDIUM | SW | ARZ | MSA | Critical Facilities (Grow) | CFG SW ARZ MSA HV-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-08-01 | 2020-09-15 |  | Active | EP
CFG CHD HV-CFG GEN GROW PROJECT - MEDIUM | SW | ARZ | CHD | Critical Facilities (Grow) | CFG SW ARZ CHD BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-10-01 | 2020-11-15 |  | Active | EP
CFG SSC HV-CFG GEN GROW PROJECT - LARGE | SW | ARZ | SSC | Critical Facilities (Grow) | CFG SW ARZ SSC GN-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-03-01 | 2020-03-15 |  | Active | EP
CFG CHD IV-CFG GEN GROW PROJECT - MEDIUM | SW | ARZ | CHD | Critical Facilities (Grow) | CFG SW ARZ CHD BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-07-01 | 2020-07-15 |  | Active | EP
CFG HEN IV-CFG GEN GROW PROJECT - MEDIUM | SW | LAS | HEN | Critical Facilities (Grow) | CFG SW LAS HEN AC MEDIUM Augment POR19 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG HEN IV-CFG GEN GROW PROJECT - MEDIUM | SW | LAS | HEN | Critical Facilities (Grow) | CFG SW LAS HEN AC MEDIUM Augment POR19 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG PNL AC-CFG GEN GROW PROJECT - LARGE | SW | ARZ | PNL | Critical Facilities (Grow) | CFG SW ARZ PNL GN-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-01-01 | 2020-04-15 |  | Active | EP
CFG SSC AC-CFG GEN GROW PROJECT - LARGE | SW | ARZ | SSC | Critical Facilities (Grow) | CFG SW ARZ SSC GN-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-01-01 | 2020-07-15 |  | Active | EP
CFG MSA RC-CFG GEN GROW PROJECT - SMALL | SW | ARZ | MSA | Critical Facilities (Grow) | CFG SW ARZ MSA HV-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-03-01 | 2020-04-15 |  | Active | EP
CFG FWL RC-CFG GEN GROW PROJECT - SMALL | SW | ARZ | FWL | Critical Facilities (Grow) | CFG SW ARZ FWL RC LARGE Augment POR19 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG FWL RC-CFG GEN GROW PROJECT - SMALL | SW | ARZ | FWL | Critical Facilities (Grow) | CFG SW ARZ FWL RC LARGE Augment POR19 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG MCD RC-CFG GEN GROW PROJECT - SMALL | SW | ARZ | MCD | Critical Facilities (Grow) | CFG SW ARZ MCD BS-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-03-01 | 2020-04-15 |  | Active | EP
CFG PEO RC-CFG GEN GROW PROJECT - SMALL | SW | ARZ | PEO | Critical Facilities (Grow) | CFG SW ARZ PEO RC LARGE Augment POR19 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG PEO RC-CFG GEN GROW PROJECT - SMALL | SW | ARZ | PEO | Critical Facilities (Grow) | CFG SW ARZ PEO RC LARGE Augment POR19 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG WCG RC-CFG GEN GROW PROJECT - SMALL | SW | ARZ | WCG | Critical Facilities (Grow) | CFG SW ARZ WCG BS-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-03-01 | 2020-04-15 |  | Active | EP
CFG BEN RC-CFG GEN GROW PROJECT - SMALL | SW | ARZ | BEN | Critical Facilities (Grow) | CFG SW ARZ BEN RC-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-03-01 | 2020-07-15 |  | Active | EP
CFG DGL RC-CFG GEN GROW PROJECT - SMALL | SW | ARZ | DGL | Critical Facilities (Grow) | CFG SW ARZ DGL RC-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-03-01 | 2020-07-15 |  | Active | EP
CFG TUC RC-CFG GEN GROW PROJECT - SMALL | SW | ARZ | TUC | Critical Facilities (Grow) | CFG SW ARZ TUC BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-03-01 | 2020-07-15 |  | Active | EP
CFG HEN RC-CFG GEN GROW PROJECT - SMALL | SW | LAS | HEN | Critical Facilities (Grow) | CFG SW LAS HEN AC MEDIUM Augment POR19 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG HEN RC-CFG GEN GROW PROJECT - SMALL | SW | LAS | HEN | Critical Facilities (Grow) | CFG SW LAS HEN AC MEDIUM Augment POR19 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG ERN RC-CFG GEN GROW PROJECT - SMALL | SW | LAS | ERN | Critical Facilities (Grow) | CFG SW LAS ERN RC-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-03-01 | 2020-07-15 |  | Active | EP
CFG TEN RC-CFG GEN GROW PROJECT - SMALL | SW | LAS | TEN | Critical Facilities (Grow) | CFG SW LAS TEN HV-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - SMALL | 1 | 2020-03-01 | 2020-07-15 |  | Active | EP
CFG HEN BS-CFG GEN GROW PROJECT - MEDIUM | SW | LAS | HEN | Critical Facilities (Grow) | CFG SW LAS HEN AC MEDIUM Augment POR19 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG HEN BS-CFG GEN GROW PROJECT - MEDIUM | SW | LAS | HEN | Critical Facilities (Grow) | CFG SW LAS HEN AC MEDIUM Augment POR19 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG CHD BS-CFG GEN GROW PROJECT - MEDIUM | SW | ARZ | CHD | Critical Facilities (Grow) | CFG SW ARZ CHD BD-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-08-01 | 2020-09-15 |  | Active | EP
CFG MCD BS-CFG GEN GROW PROJECT - MEDIUM | SW | ARZ | MCD | Critical Facilities (Grow) | CFG SW ARZ MCD BS-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-09-01 | 2020-10-15 |  | Active | EP
CFG MSA BS-CFG GEN GROW PROJECT - MEDIUM | SW | ARZ | MSA | Critical Facilities (Grow) | CFG SW ARZ MSA HV-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-08-01 | 2020-09-15 |  | Active | EP
CFG WCG BS-CFG GEN GROW PROJECT - MEDIUM | SW | ARZ | WCG | Critical Facilities (Grow) | CFG SW ARZ WCG BS-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-06-01 | 2020-07-15 |  | Active | EP
CFG PNL GN-CFG GEN GROW PROJECT - LARGE | SW | ARZ | PNL | Critical Facilities (Grow) | CFG SW ARZ PNL GN-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-02-01 | 2020-07-15 |  | Active | EP
CFG SSC GN-CFG GEN GROW PROJECT - LARGE | SW | ARZ | SSC | Critical Facilities (Grow) | CFG SW ARZ SSC GN-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - LARGE | 1 | 2020-02-01 | 2020-07-15 |  | Active | EP
CFG OSB IV-CFG GEN GROW PROJECT - SMALL | SW | LAS | OSB | Critical Facilities (Grow) | CFG SW LAS OSB SC MEDIUM Deployment POR19 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG OSB IV-CFG GEN GROW PROJECT - SMALL | SW | LAS | OSB | Critical Facilities (Grow) | CFG SW LAS OSB SC MEDIUM Deployment POR19 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG OSB BD-CFG GEN GROW PROJECT - MEDIUM | SW | LAS | OSB | Critical Facilities (Grow) | CFG SW LAS OSB SC MEDIUM Deployment POR19 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG OSB BD-CFG GEN GROW PROJECT - MEDIUM | SW | LAS | OSB | Critical Facilities (Grow) | CFG SW LAS OSB SC MEDIUM Deployment POR19 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG OSB DC-CFG GEN GROW PROJECT - MEDIUM | SW | LAS | OSB | Critical Facilities (Grow) | CFG SW LAS OSB SC MEDIUM Deployment POR19 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG OSB DC-CFG GEN GROW PROJECT - MEDIUM | SW | LAS | OSB | Critical Facilities (Grow) | CFG SW LAS OSB SC MEDIUM Deployment POR19 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG OSB BS-CFG GEN GROW PROJECT - SMALL | SW | LAS | OSB | Critical Facilities (Grow) | CFG SW LAS OSB SC MEDIUM Deployment POR19 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG OSB BS-CFG GEN GROW PROJECT - SMALL | SW | LAS | OSB | Critical Facilities (Grow) | CFG SW LAS OSB SC MEDIUM Deployment POR19 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG ELC BS-CFG GEN GROW PROJECT - MEDIUM | CA | SAN | ELC | Critical Facilities (Grow) | CFG CA SAN ELC BS-CFG Augment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-02-02 | 2020-03-15 |  | Active | EP
CFG FED BS-CFG GEN GROW PROJECT - MEDIUM | CA | SAN | FED | Critical Facilities (Grow) | CFG CA SAN FED BS-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-01-02 | 2020-01-15 |  | Active | EP
CFG ESC BS-CFG GEN GROW PROJECT - MEDIUM | CA | SAN | ESC | Critical Facilities (Grow) | CFG CA SAN ESC BS-CFG Deployment POR20 | Critical Facilities | GEN GROW PROJECT - MEDIUM | 1 | 2020-02-02 | 2020-03-15 |  | Active | EP
CFG ORG BS-CFG GEN GROW PROJECT - MEDIUM | CA | ORG | ORG | Critical Facilities (Grow) | CFG CA ORG ORG BS-CFG Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG ORG BS-CFG GEN GROW PROJECT - MEDIUM | CA | ORG | ORG | Critical Facilities (Grow) | CFG CA ORG ORG BS-CFG Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG AVJ BS-CFG GEN GROW PROJECT - MEDIUM | CA | ORG | AVJ | Critical Facilities (Grow) | CFG CA ORG AVJ BS SMALL Deployment POR19 v2 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG AVJ BS-CFG GEN GROW PROJECT - MEDIUM | CA | ORG | AVJ | Critical Facilities (Grow) | CFG CA ORG AVJ BS SMALL Deployment POR19 v2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG DNP BS-CFG GEN GROW PROJECT - MEDIUM | CA | ORG | DNP | Critical Facilities (Grow) | CFG CA ORG DNP BS-CFG Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG DNP BS-CFG GEN GROW PROJECT - MEDIUM | CA | ORG | DNP | Critical Facilities (Grow) | CFG CA ORG DNP BS-CFG Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG PAV BS-CFG GEN GROW PROJECT - MEDIUM | CA | ORG | PAV | Critical Facilities (Grow) | CFG CA ORG PAV RK MEDIUM Deployment POR19 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG PAV BS-CFG GEN GROW PROJECT - MEDIUM | CA | ORG | PAV | Critical Facilities (Grow) | CFG CA ORG PAV RK MEDIUM Deployment POR19 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG IRV BS-CFG GEN GROW PROJECT - MEDIUM | CA | ORG | IRV | Critical Facilities (Grow) | CFG CA ORG IRV BS SMALL Deployment POR19 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG IRV BS-CFG GEN GROW PROJECT - MEDIUM | CA | ORG | IRV | Critical Facilities (Grow) | CFG CA ORG IRV BS SMALL Deployment POR19 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFD ELC BUP DMS/HDT PROJECT - LARGE | CA | SAN | ELC | Critical Facilities (Grow) | CFG CA SAN ELC BS-CFG Augment POR20 | Critical Facilities | DMS/HDT PROJECT - LARGE | 1 | 2020-04-06 | 2020-06-15 |  | Active | EP
CFD RSM BUP DMS/HDT PROJECT - LARGE | CA | ORG | RSM | Critical Facilities (Grow) | CFG CA ORG RSM BS MEDIUM Deployment POR19 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFD RSM BUP DMS/HDT PROJECT - LARGE | CA | ORG | RSM | Critical Facilities (Grow) | CFG CA ORG RSM BS MEDIUM Deployment POR19 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFD RSM BUP DMS/HDT PROJECT - LARGE2 | CA | ORG | RSM | Critical Facilities (Grow) | CFG CA ORG RSM BS MEDIUM Deployment POR19 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFD RSM BUP DMS/HDT PROJECT - LARGE2 | CA | ORG | RSM | Critical Facilities (Grow) | CFG CA ORG RSM BS MEDIUM Deployment POR19 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFD CHS BUP DMS/HDT PROJECT - LARGE | VA | HRD | CHS | Critical Facilities (Grow) | CFG VA HRD CHS RC-CFG Deployment POR20 | Critical Facilities | DMS/HDT PROJECT - LARGE | 1 | 2020-04-06 | 2020-06-15 |  | Active | EP
CFG CE OKC NOR BS-CFG Deployment POR20 | CE | NWA | BVL | Critical Facilities (Grow) | CFG CE OKC NOR BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFG CE OKC NOR BS-CFG Deployment POR20 | CE | NWA | BVL | Critical Facilities (Grow) | CFG CE OKC NOR BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFG CE TUL GAR RK-CFG Deployment POR20 | CE | TUL | GAR | Critical Facilities (Grow) | CFG CE TUL GAR RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFG CE TUL GAR RK-CFG Deployment POR20 | CE | TUL | GAR | Critical Facilities (Grow) | CFG CE TUL GAR RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFG CE OMA ONA RK-CFG Deployment POR20 | CE | TUL | OWA | Critical Facilities (Grow) | CFG CE OMA ONA RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFG CE OMA ONA RK-CFG Deployment POR20 | CE | TUL | OWA | Critical Facilities (Grow) | CFG CE OMA ONA RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFG CE OMA BLV RK-CFG Deployment POR20 | CE | TUL | SAP | Critical Facilities (Grow) | CFG CE OMA BLV RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFG CE OMA BLV RK-CFG Deployment POR20 | CE | TUL | SAP | Critical Facilities (Grow) | CFG CE OMA BLV RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFG SW LAS OSB BS-CFG Deployment POR20 | SW | LAS | OSB | Critical Facilities (Grow) | CFG SW LAS OSB BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-02-01 |  | Active | EP
CFG SW LAS OSB BS-CFG Deployment POR20 | SW | LAS | OSB | Critical Facilities (Grow) | CFG SW LAS OSB BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-02-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFG SW ARZ MCD BS-CFG Deployment POR20 | SW | ARZ | MCD | Critical Facilities (Grow) | CFG SW ARZ MCD BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFG SW ARZ MCD BS-CFG Deployment POR20 | SW | ARZ | MCD | Critical Facilities (Grow) | CFG SW ARZ MCD BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFG SW ARZ MSA BS-CFG Deployment POR20 | SW | ARZ | MSA | Critical Facilities (Grow) | CFG SW ARZ MSA BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-10-01 |  | Active | EP
CFG SW ARZ MSA BS-CFG Deployment POR20 | SW | ARZ | MSA | Critical Facilities (Grow) | CFG SW ARZ MSA BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-10-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFG SW ARZ CHD HV-CFG Deployment POR20 | SW | ARZ | CHD | Critical Facilities (Grow) | CFG SW ARZ CHD HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-02-01 |  | Active | EP
CFG SW ARZ CHD HV-CFG Deployment POR20 | SW | ARZ | CHD | Critical Facilities (Grow) | CFG SW ARZ CHD HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-02-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFG SW ARZ SSC HV-CFG Deployment POR20 | SW | ARZ | SSC | Critical Facilities (Grow) | CFG SW ARZ SSC HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-02-01 |  | Active | EP
CFG SW ARZ SSC HV-CFG Deployment POR20 | SW | ARZ | SSC | Critical Facilities (Grow) | CFG SW ARZ SSC HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-02-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFG CA ORG RSM RK MEDIUM Deployment POR19 | CA | ORG | RSM | Critical Facilities (Grow) | CFG CA ORG RSM RK MEDIUM Deployment POR19 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFG CA ORG RSM RK MEDIUM Deployment POR19 | SE | BTR | SPC | Critical Facilities (Grow) | CFG CA ORG RSM RK MEDIUM Deployment POR19 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Deleted | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFG CA ORG RSM RK MEDIUM Deployment POR19 | CA | ORG | RSM | Critical Facilities (Grow) | CFG CA ORG RSM RK MEDIUM Deployment POR19 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG SE GCT PNS BS-CFG Deployment POR20 | SE | GCT | PNS | Critical Facilities (Grow) | CFG SE GCT PNS BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-02 |  | Active | EP
CFG SE GCT PNS BS-CFG Deployment POR20 | SE | GCT | PNS | Critical Facilities (Grow) | CFG SE GCT PNS BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-02 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFG CA ORG AVJ BS-CFG Augment POR20 | CA | ORG | AVJ | Critical Facilities (Grow) | CFG CA ORG AVJ BS-CFG Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-20 |  | Active | EP
CFG CA ORG AVJ BS-CFG Augment POR20 | CA | ORG | AVJ | Critical Facilities (Grow) | CFG CA ORG AVJ BS-CFG Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-20 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CA ORG DNP BS-CFG Augment POR20 | CA | ORG | DNP | Critical Facilities (Grow) | CFG CA ORG DNP BS-CFG Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-20 |  | Active | EP
CFG CA ORG DNP BS-CFG Augment POR20 | CA | ORG | DNP | Critical Facilities (Grow) | CFG CA ORG DNP BS-CFG Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-20 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CA ORG IRV BS-CFG Augment POR20 | CA | ORG | IRV | Critical Facilities (Grow) | CFG CA ORG IRV BS-CFG Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-20 |  | Active | EP
CFG CA ORG IRV BS-CFG Augment POR20 | CA | ORG | IRV | Critical Facilities (Grow) | CFG CA ORG IRV BS-CFG Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-20 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CA ORG ORG BS-CFG Augment POR20 | CA | ORG | ORG | Critical Facilities (Grow) | CFG CA ORG ORG BS-CFG Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-20 |  | Active | EP
CFG CA ORG ORG BS-CFG Augment POR20 | CA | ORG | ORG | Critical Facilities (Grow) | CFG CA ORG ORG BS-CFG Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-20 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CA ORG PAV BS-CFG Augment POR20 | CA | ORG | PAV | Critical Facilities (Grow) | CFG CA ORG PAV BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-03-20 |  | Active | EP
CFG CA ORG PAV BS-CFG Augment POR20 | CA | ORG | PAV | Critical Facilities (Grow) | CFG CA ORG PAV BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-03-20 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CA SAN ELC BS-CFG Augment POR20 | CA | SAN | ELC | Critical Facilities (Grow) | CFG CA SAN ELC BS-CFG Augment POR20 | Labor | No Equipment | 1 | 2020-02-03 | 2020-02-20 |  | Active | EP
CFG CA SAN ELC BS-CFG Augment POR20 | CA | SAN | ELC | Critical Facilities (Grow) | CFG CA SAN ELC BS-CFG Augment POR20 | Labor | No Equipment | 1 |  | 2020-02-20 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CA SAN ELC BS-CFG Augment POR20 | CA | SAN | ELC | Critical Facilities (Grow) | CFG CA SAN ELC BS-CFG Augment POR20 | Labor | No Equipment | 1 | 2020-02-03 | 2020-02-20 |  | Active | Log | Upd | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG CA SAN ESC BS-CFG Augment POR20 | CA | SAN | ESC | Critical Facilities (Grow) | CFG CA SAN ESC BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-02-20 |  | Active | EP
CFG CA SAN ESC BS-CFG Augment POR20 | CA | SAN | ESC | Critical Facilities (Grow) | CFG CA SAN ESC BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-02-20 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CA SAN FED BS-CFG Augment POR20 | CA | SAN | FED | Critical Facilities (Grow) | CFG CA SAN FED BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | Active | EP
CFG CA SAN FED BS-CFG Augment POR20 | CA | SAN | FED | Critical Facilities (Grow) | CFG CA SAN FED BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE ARK BER RK-CFG Deployment POR20 | CE | NWA | BER | Critical Facilities (Grow) | CFG CE ARK BER RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE ARK BER RK-CFG Deployment POR20 | CE | NWA | BER | Critical Facilities (Grow) | CFG CE ARK BER RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE ARK BVL RK-CFG Deployment POR20 | CE | NWA | BVL | Critical Facilities (Grow) | CFG CE ARK BVL RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE ARK BVL RK-CFG Deployment POR20 | CE | NWA | BVL | Critical Facilities (Grow) | CFG CE ARK BVL RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE ARK HRN RK-CFG Deployment POR20 | CE | NWA | HRN | Critical Facilities (Grow) | CFG CE ARK HRN RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE ARK HRN RK-CFG Deployment POR20 | CE | NWA | HRN | Critical Facilities (Grow) | CFG CE ARK HRN RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE ARK NWA BD-CFG Deployment POR20 | CE | NWA | NWA | Critical Facilities (Grow) | CFG CE ARK NWA BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE ARK NWA BD-CFG Deployment POR20 | CE | NWA | NWA | Critical Facilities (Grow) | CFG CE ARK NWA BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE ARK NWA RK-CFG Deployment POR20 | CE | NWA | NWA | Critical Facilities (Grow) | CFG CE ARK NWA RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE ARK NWA RK-CFG Deployment POR20 | CE | NWA | NWA | Critical Facilities (Grow) | CFG CE ARK NWA RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE ARK VBN RK-CFG Deployment POR20 | CE | NWA | VBN | Critical Facilities (Grow) | CFG CE ARK VBN RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE ARK VBN RK-CFG Deployment POR20 | CE | NWA | VBN | Critical Facilities (Grow) | CFG CE ARK VBN RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE KAN CNY GN-CFG Deployment POR20 | CE | KAN | CNY | Critical Facilities (Grow) | CFG CE KAN CNY GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE KAN CNY GN-CFG Deployment POR20 | CE | KAN | CNY | Critical Facilities (Grow) | CFG CE KAN CNY GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE KAN DBY GN-CFG Deployment POR20 | CE | KAN | DBY | Critical Facilities (Grow) | CFG CE KAN DBY GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE KAN DBY GN-CFG Deployment POR20 | CE | KAN | DBY | Critical Facilities (Grow) | CFG CE KAN DBY GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE KAN DBY HV-CFG Deployment POR20 | CE | KAN | DBY | Critical Facilities (Grow) | CFG CE KAN DBY HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE KAN DBY HV-CFG Deployment POR20 | CE | KAN | DBY | Critical Facilities (Grow) | CFG CE KAN DBY HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE KAN GBD BD-CFG Deployment POR20 | CE | KAN | GBD | Critical Facilities (Grow) | CFG CE KAN GBD BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE KAN GBD BD-CFG Deployment POR20 | CE | KAN | GBD | Critical Facilities (Grow) | CFG CE KAN GBD BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE KAN GBD HV-CFG Deployment POR20 | CE | KAN | GBD | Critical Facilities (Grow) | CFG CE KAN GBD HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE KAN GBD HV-CFG Deployment POR20 | CE | KAN | GBD | Critical Facilities (Grow) | CFG CE KAN GBD HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE KAN GDY GN-CFG Deployment POR20 | CE | KAN | GDY | Critical Facilities (Grow) | CFG CE KAN GDY GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE KAN GDY GN-CFG Deployment POR20 | CE | KAN | GDY | Critical Facilities (Grow) | CFG CE KAN GDY GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE KAN MPN HV-CFG Deployment POR20 | CE | KAN | MPN | Critical Facilities (Grow) | CFG CE KAN MPN HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE KAN MPN HV-CFG Deployment POR20 | CE | KAN | MPN | Critical Facilities (Grow) | CFG CE KAN MPN HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE KAN NWT HV-CFG Deployment POR20 | CE | KAN | NWT | Critical Facilities (Grow) | CFG CE KAN NWT HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE KAN NWT HV-CFG Deployment POR20 | CE | KAN | NWT | Critical Facilities (Grow) | CFG CE KAN NWT HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE KAN OLA GN-CFG Deployment POR20 | CE | KAN | OLA | Critical Facilities (Grow) | CFG CE KAN OLA GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE KAN OLA GN-CFG Deployment POR20 | CE | KAN | OLA | Critical Facilities (Grow) | CFG CE KAN OLA GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE KAN PIT GN-CFG Deployment POR20 | CE | KAN | PIT | Critical Facilities (Grow) | CFG CE KAN PIT GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE KAN PIT GN-CFG Deployment POR20 | CE | KAN | PIT | Critical Facilities (Grow) | CFG CE KAN PIT GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE KAN SDN GN-CFG Deployment POR20 | CE | KAN | SDN | Critical Facilities (Grow) | CFG CE KAN SDN GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE KAN SDN GN-CFG Deployment POR20 | CE | KAN | SDN | Critical Facilities (Grow) | CFG CE KAN SDN GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE KAN STR RC-CFG Deployment POR20 | CE | KAN | STR | Critical Facilities (Grow) | CFG CE KAN STR RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE KAN STR RC-CFG Deployment POR20 | CE | KAN | STR | Critical Facilities (Grow) | CFG CE KAN STR RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE KAN TOP RK-CFG Deployment POR20 | CE | KAN | TOP | Critical Facilities (Grow) | CFG CE KAN TOP RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE KAN TOP RK-CFG Deployment POR20 | CE | KAN | TOP | Critical Facilities (Grow) | CFG CE KAN TOP RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE KAN WIC BD-CFG Deployment POR20 | CE | KAN | WIC | Critical Facilities (Grow) | CFG CE KAN WIC BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE KAN WIC BD-CFG Deployment POR20 | CE | KAN | WIC | Critical Facilities (Grow) | CFG CE KAN WIC BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE KAN WIC IV-CFG Deployment POR20 | CE | KAN | WIC | Critical Facilities (Grow) | CFG CE KAN WIC IV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE KAN WIC IV-CFG Deployment POR20 | CE | KAN | WIC | Critical Facilities (Grow) | CFG CE KAN WIC IV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE NWA SSP GN-CFG Deployment POR20 | CE | NWA | SSP | Critical Facilities (Grow) | CFG CE NWA SSP GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE NWA SSP GN-CFG Deployment POR20 | CE | NWA | SSP | Critical Facilities (Grow) | CFG CE NWA SSP GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE OKC CHO BS-CFG Deployment POR20 | CE | OKC | CHO | Critical Facilities (Grow) | CFG CE OKC CHO BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE OKC CHO BS-CFG Deployment POR20 | CE | OKC | CHO | Critical Facilities (Grow) | CFG CE OKC CHO BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE OKC CLH BS-CFG Deployment POR20 | CE | OKC | CLH | Critical Facilities (Grow) | CFG CE OKC CLH BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE OKC CLH BS-CFG Deployment POR20 | CE | OKC | CLH | Critical Facilities (Grow) | CFG CE OKC CLH BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE OKC CLH HV-CFG Deployment POR20 | CE | OKC | CLH | Critical Facilities (Grow) | CFG CE OKC CLH HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE OKC CLH HV-CFG Deployment POR20 | CE | OKC | CLH | Critical Facilities (Grow) | CFG CE OKC CLH HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE OKC ELR RK-CFG Deployment POR20 | CE | OKC | ELR | Critical Facilities (Grow) | CFG CE OKC ELR RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE OKC ELR RK-CFG Deployment POR20 | CE | OKC | ELR | Critical Facilities (Grow) | CFG CE OKC ELR RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE OKC MOO AC-CFG Deployment POR20 | CE | OKC | MOO | Critical Facilities (Grow) | CFG CE OKC MOO AC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE OKC MOO AC-CFG Deployment POR20 | CE | OKC | MOO | Critical Facilities (Grow) | CFG CE OKC MOO AC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE OKC MOO RK-CFG Deployment POR20 | CE | OKC | MOO | Critical Facilities (Grow) | CFG CE OKC MOO RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE OKC MOO RK-CFG Deployment POR20 | CE | OKC | MOO | Critical Facilities (Grow) | CFG CE OKC MOO RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE OKC NCH HV-CFG Deployment POR20 | CE | OKC | NCH | Critical Facilities (Grow) | CFG CE OKC NCH HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE OKC NCH HV-CFG Deployment POR20 | CE | OKC | NCH | Critical Facilities (Grow) | CFG CE OKC NCH HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE OKC NEH AC-CFG Deployment POR20 | CE | OKC | NEH | Critical Facilities (Grow) | CFG CE OKC NEH AC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE OKC NEH AC-CFG Deployment POR20 | CE | OKC | NEH | Critical Facilities (Grow) | CFG CE OKC NEH AC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE OKC NEH HV-CFG Deployment POR20 | CE | OKC | NEH | Critical Facilities (Grow) | CFG CE OKC NEH HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE OKC NEH HV-CFG Deployment POR20 | CE | OKC | NEH | Critical Facilities (Grow) | CFG CE OKC NEH HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE OKC NOR BD-CFG Deployment POR20 | CE | OKC | NOR | Critical Facilities (Grow) | CFG CE OKC NOR BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE OKC NOR BD-CFG Deployment POR20 | CE | OKC | NOR | Critical Facilities (Grow) | CFG CE OKC NOR BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE OKC OKC BS-CFG Deployment POR20 | CE | OKC | OKC | Critical Facilities (Grow) | CFG CE OKC OKC BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE OKC OKC BS-CFG Deployment POR20 | CE | OKC | OKC | Critical Facilities (Grow) | CFG CE OKC OKC BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE OKC OKC RC-CFG Deployment POR20 | CE | OKC | OKC | Critical Facilities (Grow) | CFG CE OKC OKC RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE OKC OKC RC-CFG Deployment POR20 | CE | OKC | OKC | Critical Facilities (Grow) | CFG CE OKC OKC RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE OKC SEH AC-CFG Deployment POR20 | CE | OKC | SEH | Critical Facilities (Grow) | CFG CE OKC SEH AC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE OKC SEH AC-CFG Deployment POR20 | CE | OKC | SEH | Critical Facilities (Grow) | CFG CE OKC SEH AC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE OKC SEH BS-CFG Deployment POR20 | CE | OKC | SEH | Critical Facilities (Grow) | CFG CE OKC SEH BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE OKC SEH BS-CFG Deployment POR20 | CE | OKC | SEH | Critical Facilities (Grow) | CFG CE OKC SEH BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE OKC SEH DC-CFG Deployment POR20 | CE | OKC | SEH | Critical Facilities (Grow) | CFG CE OKC SEH DC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE OKC SEH DC-CFG Deployment POR20 | CE | OKC | SEH | Critical Facilities (Grow) | CFG CE OKC SEH DC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE OKC SEH HV-CFG Deployment POR20 | CE | OKC | SEH | Critical Facilities (Grow) | CFG CE OKC SEH HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE OKC SEH HV-CFG Deployment POR20 | CE | OKC | SEH | Critical Facilities (Grow) | CFG CE OKC SEH HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE OKC SEH RK-CFG Deployment POR20 | CE | OKC | SEH | Critical Facilities (Grow) | CFG CE OKC SEH RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE OKC SEH RK-CFG Deployment POR20 | CE | OKC | SEH | Critical Facilities (Grow) | CFG CE OKC SEH RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE OKC WLH BD-CFG Deployment POR20 | CE | OKC | WLH | Critical Facilities (Grow) | CFG CE OKC WLH BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE OKC WLH BD-CFG Deployment POR20 | CE | OKC | WLH | Critical Facilities (Grow) | CFG CE OKC WLH BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE OKC WLH BS-CFG Deployment POR20 | CE | OKC | WLH | Critical Facilities (Grow) | CFG CE OKC WLH BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE OKC WLH BS-CFG Deployment POR20 | CE | OKC | WLH | Critical Facilities (Grow) | CFG CE OKC WLH BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE OKC WLH HV-CFG Deployment POR20 | CE | OKC | WLH | Critical Facilities (Grow) | CFG CE OKC WLH HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE OKC WLH HV-CFG Deployment POR20 | CE | OKC | WLH | Critical Facilities (Grow) | CFG CE OKC WLH HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE OKC WLH RK-CFG Deployment POR20 | CE | OKC | WLH | Critical Facilities (Grow) | CFG CE OKC WLH RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE OKC WLH RK-CFG Deployment POR20 | CE | OKC | WLH | Critical Facilities (Grow) | CFG CE OKC WLH RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE OMA BLV GN-CFG Deployment POR20 | CE | OMA | BLV | Critical Facilities (Grow) | CFG CE OMA BLV GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE OMA BLV GN-CFG Deployment POR20 | CE | OMA | BLV | Critical Facilities (Grow) | CFG CE OMA BLV GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE OMA CBL HV-CFG Deployment POR20 | CE | OMA | CBL | Critical Facilities (Grow) | CFG CE OMA CBL HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE OMA CBL HV-CFG Deployment POR20 | CE | OMA | CBL | Critical Facilities (Grow) | CFG CE OMA CBL HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE OMA CBL RK-CFG Deployment POR20 | CE | OMA | CBL | Critical Facilities (Grow) | CFG CE OMA CBL RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE OMA CBL RK-CFG Deployment POR20 | CE | OMA | CBL | Critical Facilities (Grow) | CFG CE OMA CBL RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE OMA OMM GN-CFG Deployment POR20 | CE | OMA | OMM | Critical Facilities (Grow) | CFG CE OMA OMM GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE OMA OMM GN-CFG Deployment POR20 | CE | OMA | OMM | Critical Facilities (Grow) | CFG CE OMA OMM GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE OMA ONA BD-CFG Deployment POR20 | CE | OMA | ONA | Critical Facilities (Grow) | CFG CE OMA ONA BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE OMA ONA BD-CFG Deployment POR20 | CE | OMA | ONA | Critical Facilities (Grow) | CFG CE OMA ONA BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE OMA ONA BS-CFG Deployment POR20 | CE | OMA | ONA | Critical Facilities (Grow) | CFG CE OMA ONA BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE OMA ONA BS-CFG Deployment POR20 | CE | OMA | ONA | Critical Facilities (Grow) | CFG CE OMA ONA BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE OMA SOU BD-CFG Deployment POR20 | CE | OMA | SOU | Critical Facilities (Grow) | CFG CE OMA SOU BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE OMA SOU BD-CFG Deployment POR20 | CE | OMA | SOU | Critical Facilities (Grow) | CFG CE OMA SOU BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE OMA SOU RK-CFG Deployment POR20 | CE | OMA | SOU | Critical Facilities (Grow) | CFG CE OMA SOU RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE OMA SOU RK-CFG Deployment POR20 | CE | OMA | SOU | Critical Facilities (Grow) | CFG CE OMA SOU RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE OMA WES BD-CFG Deployment POR20 | CE | OMA | WES | Critical Facilities (Grow) | CFG CE OMA WES BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE OMA WES BD-CFG Deployment POR20 | CE | OMA | WES | Critical Facilities (Grow) | CFG CE OMA WES BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE OMA WES HV-CFG Deployment POR20 | CE | OMA | WES | Critical Facilities (Grow) | CFG CE OMA WES HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE OMA WES HV-CFG Deployment POR20 | CE | OMA | WES | Critical Facilities (Grow) | CFG CE OMA WES HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE OMA WES RK-CFG Deployment POR20 | CE | OMA | WES | Critical Facilities (Grow) | CFG CE OMA WES RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE OMA WES RK-CFG Deployment POR20 | CE | OMA | WES | Critical Facilities (Grow) | CFG CE OMA WES RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE TUL BAR RK-CFG Deployment POR20 | CE | TUL | BAR | Critical Facilities (Grow) | CFG CE TUL BAR RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE TUL BAR RK-CFG Deployment POR20 | CE | TUL | BAR | Critical Facilities (Grow) | CFG CE TUL BAR RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE TUL BRD BD-CFG Deployment POR20 | CE | TUL | BRD | Critical Facilities (Grow) | CFG CE TUL BRD BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE TUL BRD BD-CFG Deployment POR20 | CE | TUL | BRD | Critical Facilities (Grow) | CFG CE TUL BRD BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE TUL DTN BD-CFG Deployment POR20 | CE | TUL | DTN | Critical Facilities (Grow) | CFG CE TUL DTN BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE TUL DTN BD-CFG Deployment POR20 | CE | TUL | DTN | Critical Facilities (Grow) | CFG CE TUL DTN BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE TUL GAR BD-CFG Deployment POR20 | CE | TUL | GAR | Critical Facilities (Grow) | CFG CE TUL GAR BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE TUL GAR BD-CFG Deployment POR20 | CE | TUL | GAR | Critical Facilities (Grow) | CFG CE TUL GAR BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE TUL OWA BD-CFG Deployment POR20 | CE | TUL | OWA | Critical Facilities (Grow) | CFG CE TUL OWA BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE TUL OWA BD-CFG Deployment POR20 | CE | TUL | OWA | Critical Facilities (Grow) | CFG CE TUL OWA BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE TUL OWA RK-CFG Deployment POR20 | CE | TUL | OWA | Critical Facilities (Grow) | CFG CE TUL OWA RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE TUL OWA RK-CFG Deployment POR20 | CE | TUL | OWA | Critical Facilities (Grow) | CFG CE TUL OWA RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE TUL QNC BD-CFG Deployment POR20 | CE | TUL | QNC | Critical Facilities (Grow) | CFG CE TUL QNC BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE TUL QNC BD-CFG Deployment POR20 | CE | TUL | QNC | Critical Facilities (Grow) | CFG CE TUL QNC BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE TUL QNC RK-CFG Deployment POR20 | CE | TUL | QNC | Critical Facilities (Grow) | CFG CE TUL QNC RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE TUL QNC RK-CFG Deployment POR20 | CE | TUL | QNC | Critical Facilities (Grow) | CFG CE TUL QNC RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE TUL SAP BD-CFG Deployment POR20 | CE | TUL | SAP | Critical Facilities (Grow) | CFG CE TUL SAP BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE TUL SAP BD-CFG Deployment POR20 | CE | TUL | SAP | Critical Facilities (Grow) | CFG CE TUL SAP BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CE TUL SAP RK-CFG Deployment POR20 | CE | TUL | SAP | Critical Facilities (Grow) | CFG CE TUL SAP RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | EP
CFG CE TUL SAP RK-CFG Deployment POR20 | CE | TUL | SAP | Critical Facilities (Grow) | CFG CE TUL SAP RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-10-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG NE CLE CLV RK LARGE Deployment POR20 | NE | CLE | CLV | Critical Facilities (Grow) | CFG NE CLE CLV RK LARGE Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-19 |  | Active | EP
CFG NE CLE CLV RK LARGE Deployment POR20 | NE | CLE | CLV | Critical Facilities (Grow) | CFG NE CLE CLV RK LARGE Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG NE CLE CLV RK-CFG Deployment POR20 | NE | CLE | CLV | Critical Facilities (Grow) | CFG NE CLE CLV RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-03-20 |  | Active | EP
CFG NE CLE CLV RK-CFG Deployment POR20 | NE | CLE | CLV | Critical Facilities (Grow) | CFG NE CLE CLV RK-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-03-20 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG NE CON ENF BD-CFG Deployment POR20 | NE | CON | ENF | Critical Facilities (Grow) | CFG NE CON ENF BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | Active | EP
CFG NE CON ENF BD-CFG Deployment POR20 | NE | CON | ENF | Critical Facilities (Grow) | CFG NE CON ENF BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG NE CON MAN BD-CFG Deployment POR20 | NE | CON | MAN | Critical Facilities (Grow) | CFG NE CON MAN BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | Active | EP
CFG NE CON MAN BD-CFG Deployment POR20 | NE | CON | MAN | Critical Facilities (Grow) | CFG NE CON MAN BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG NE CON MAN BS-CFG Deployment POR20 | NE | CON | MAN | Critical Facilities (Grow) | CFG NE CON MAN BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-03-20 |  | Active | EP
CFG NE CON MAN BS-CFG Deployment POR20 | NE | CON | MAN | Critical Facilities (Grow) | CFG NE CON MAN BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-03-20 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG NE CON MAN GN-CFG Deployment POR20 | NE | CON | MAN | Critical Facilities (Grow) | CFG NE CON MAN GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-03-20 |  | Active | EP
CFG NE CON MAN GN-CFG Deployment POR20 | NE | CON | MAN | Critical Facilities (Grow) | CFG NE CON MAN GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-03-20 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG NE CON MAN GN-CFG Deployment POR20 | NE | CON | MAN | Critical Facilities (Grow) | CFG NE CON MAN GN-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-20 |  | Active | Log | Upd | SN-0593 | Schedule Change | Canceled | 2020-06-22 11:08 | updating need by date for grown projects
CFG NE RHD PTH BD-CFG Deployment POR20 | NE | RHD | PTH | Critical Facilities (Grow) | CFG NE RHD PTH BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | Active | EP
CFG NE RHD PTH BD-CFG Deployment POR20 | NE | RHD | PTH | Critical Facilities (Grow) | CFG NE RHD PTH BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG NE RHD RMD BS-CFG Deployment POR20 | NE | RHD | RMD | Critical Facilities (Grow) | CFG NE RHD RMD BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-02-20 |  | Active | EP
CFG NE RHD RMD BS-CFG Deployment POR20 | NE | RHD | RMD | Critical Facilities (Grow) | CFG NE RHD RMD BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-02-20 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SE BTR BTR BS-CFG Deployment POR20 | SE | BTR | BTR | Critical Facilities (Grow) | CFG SE BTR BTR BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFG SE BTR BTR BS-CFG Deployment POR20 | SE | BTR | BTR | Critical Facilities (Grow) | CFG SE BTR BTR BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SE GCT PNS BD-CFG Deployment POR20 | SE | GCT | PNS | Critical Facilities (Grow) | CFG SE GCT PNS BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFG SE GCT PNS BD-CFG Deployment POR20 | SE | GCT | PNS | Critical Facilities (Grow) | CFG SE GCT PNS BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SE LFY LFY BS-CFG Deployment POR20 | SE | LFY | LFY | Critical Facilities (Grow) | CFG SE LFY LFY BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFG SE LFY LFY BS-CFG Deployment POR20 | SE | LFY | LFY | Critical Facilities (Grow) | CFG SE LFY LFY BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SE LFY LFY HV-CFG Deployment POR20 | SE | LFY | LFY | Critical Facilities (Grow) | CFG SE LFY LFY HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFG SE LFY LFY HV-CFG Deployment POR20 | SE | LFY | LFY | Critical Facilities (Grow) | CFG SE LFY LFY HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SE NOR LUL BS-CFG Deployment POR20 | SE | NOR | LUL | Critical Facilities (Grow) | CFG SE NOR LUL BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFG SE NOR LUL BS-CFG Deployment POR20 | SE | NOR | LUL | Critical Facilities (Grow) | CFG SE NOR LUL BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SE NOR LUL RC-CFG Deployment POR20 | SE | NOR | LUL | Critical Facilities (Grow) | CFG SE NOR LUL RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFG SE NOR LUL RC-CFG Deployment POR20 | SE | NOR | LUL | Critical Facilities (Grow) | CFG SE NOR LUL RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW ARZ BEL HV-CFG Deployment POR20 | SW | ARZ | BEL | Critical Facilities (Grow) | CFG SW ARZ BEL HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | EP
CFG SW ARZ BEL HV-CFG Deployment POR20 | SW | ARZ | BEL | Critical Facilities (Grow) | CFG SW ARZ BEL HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW ARZ BEN RC-CFG Deployment POR20 | SW | ARZ | CHD | Critical Facilities (Grow) | CFG SW ARZ BEN RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | EP
CFG SW ARZ BEN RC-CFG Deployment POR20 | SW | ARZ | CHD | Critical Facilities (Grow) | CFG SW ARZ BEN RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW ARZ CHD BD-CFG Deployment POR20 | SW | ARZ | CHD | Critical Facilities (Grow) | CFG SW ARZ CHD BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | EP
CFG SW ARZ CHD BD-CFG Deployment POR20 | SW | ARZ | CHD | Critical Facilities (Grow) | CFG SW ARZ CHD BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW ARZ CHD BS-CFG Deployment POR20 | SW | ARZ | CHD | Critical Facilities (Grow) | CFG SW ARZ CHD BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | EP
CFG SW ARZ CHD BS-CFG Deployment POR20 | SW | ARZ | CHD | Critical Facilities (Grow) | CFG SW ARZ CHD BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW ARZ CHD DC-CFG Deployment POR20 | SW | ARZ | CHD | Critical Facilities (Grow) | CFG SW ARZ CHD DC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | EP
CFG SW ARZ CHD DC-CFG Deployment POR20 | SW | ARZ | CHD | Critical Facilities (Grow) | CFG SW ARZ CHD DC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW ARZ CHD DC-CFG Deployment POR20 - 2 | SW | ARZ | CHD | Critical Facilities (Grow) | CFG SW ARZ CHD DC-CFG Deployment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFG SW ARZ CHD DC-CFG Deployment POR20 - 2 | SW | ARZ | CHD | Critical Facilities (Grow) | CFG SW ARZ CHD DC-CFG Deployment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW ARZ CHD HV-CFG Deployment POR20 - 2 | SW | ARZ | CHD | Critical Facilities (Grow) | CFG SW ARZ CHD HV-CFG Deployment POR20 - 2 | Labor | No Equipment | 1 |  | 2019-01-20 |  | Active | EP
CFG SW ARZ CHD HV-CFG Deployment POR20 - 2 | SW | ARZ | CHD | Critical Facilities (Grow) | CFG SW ARZ CHD HV-CFG Deployment POR20 - 2 | Labor | No Equipment | 1 |  | 2019-01-20 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW ARZ CHD IV-CFG Deployment POR20 | SW | ARZ | CHD | Critical Facilities (Grow) | CFG SW ARZ CHD IV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-19 |  | Active | EP
CFG SW ARZ CHD IV-CFG Deployment POR20 | SW | ARZ | CHD | Critical Facilities (Grow) | CFG SW ARZ CHD IV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW ARZ DGL RC-CFG Deployment POR20 | SW | ARZ | DGL | Critical Facilities (Grow) | CFG SW ARZ DGL RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-19 |  | Active | EP
CFG SW ARZ DGL RC-CFG Deployment POR20 | SW | ARZ | DGL | Critical Facilities (Grow) | CFG SW ARZ DGL RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW ARZ FWL BD-CFG Deployment POR20 | SW | ARZ | FWL | Critical Facilities (Grow) | CFG SW ARZ FWL BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-19 |  | Active | EP
CFG SW ARZ FWL BD-CFG Deployment POR20 | SW | ARZ | FWL | Critical Facilities (Grow) | CFG SW ARZ FWL BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW ARZ FWL DC-CFG Deployment POR20 | SW | ARZ | FWL | Critical Facilities (Grow) | CFG SW ARZ FWL DC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-19 |  | Active | EP
CFG SW ARZ FWL DC-CFG Deployment POR20 | SW | ARZ | FWL | Critical Facilities (Grow) | CFG SW ARZ FWL DC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW ARZ FWL RC-CFG Deployment POR20 | SW | ARZ | FWL | Critical Facilities (Grow) | CFG SW ARZ FWL RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-19 |  | Active | EP
CFG SW ARZ FWL RC-CFG Deployment POR20 | SW | ARZ | FWL | Critical Facilities (Grow) | CFG SW ARZ FWL RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW ARZ MCD RC-CFG Deployment POR20 | SW | ARZ | MCD | Critical Facilities (Grow) | CFG SW ARZ MCD RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-19 |  | Active | EP
CFG SW ARZ MCD RC-CFG Deployment POR20 | SW | ARZ | MCD | Critical Facilities (Grow) | CFG SW ARZ MCD RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-19 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW ARZ MSA HV-CFG Deployment POR20 | SW | ARZ | MSA | Critical Facilities (Grow) | CFG SW ARZ MSA HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | EP
CFG SW ARZ MSA HV-CFG Deployment POR20 | SW | ARZ | MSA | Critical Facilities (Grow) | CFG SW ARZ MSA HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW ARZ MSA RC-CFG Deployment POR20 | SW | ARZ | MSA | Critical Facilities (Grow) | CFG SW ARZ MSA RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | EP
CFG SW ARZ MSA RC-CFG Deployment POR20 | SW | ARZ | MSA | Critical Facilities (Grow) | CFG SW ARZ MSA RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW ARZ PEO BD-CFG Deployment POR20 | SW | ARZ | PEO | Critical Facilities (Grow) | CFG SW ARZ PEO BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | EP
CFG SW ARZ PEO BD-CFG Deployment POR20 | SW | ARZ | PEO | Critical Facilities (Grow) | CFG SW ARZ PEO BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW ARZ PEO RC-CFG Deployment POR20 | SW | ARZ | PEO | Critical Facilities (Grow) | CFG SW ARZ PEO RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | EP
CFG SW ARZ PEO RC-CFG Deployment POR20 | SW | ARZ | PEO | Critical Facilities (Grow) | CFG SW ARZ PEO RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW ARZ PNL AC-CFG Deployment POR20 | SW | ARZ | PNL | Critical Facilities (Grow) | CFG SW ARZ PNL AC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | EP
CFG SW ARZ PNL AC-CFG Deployment POR20 | SW | ARZ | PNL | Critical Facilities (Grow) | CFG SW ARZ PNL AC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW ARZ PNL GN-CFG Deployment POR20 | SW | ARZ | PNL | Critical Facilities (Grow) | CFG SW ARZ PNL GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | EP
CFG SW ARZ PNL GN-CFG Deployment POR20 | SW | ARZ | PNL | Critical Facilities (Grow) | CFG SW ARZ PNL GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW ARZ PNL HV-CFG Deployment POR20 | SW | ARZ | PNL | Critical Facilities (Grow) | CFG SW ARZ PNL HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | EP
CFG SW ARZ PNL HV-CFG Deployment POR20 | SW | ARZ | PNL | Critical Facilities (Grow) | CFG SW ARZ PNL HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW ARZ SSC AC-CFG Deployment POR20 | SW | ARZ | SSC | Critical Facilities (Grow) | CFG SW ARZ SSC AC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | EP
CFG SW ARZ SSC AC-CFG Deployment POR20 | SW | ARZ | SSC | Critical Facilities (Grow) | CFG SW ARZ SSC AC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW ARZ SSC BD-CFG Deployment POR20 | SW | ARZ | SSC | Critical Facilities (Grow) | CFG SW ARZ SSC BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | EP
CFG SW ARZ SSC BD-CFG Deployment POR20 | SW | ARZ | SSC | Critical Facilities (Grow) | CFG SW ARZ SSC BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW ARZ SSC GN-CFG Deployment POR20 | SW | ARZ | SSC | Critical Facilities (Grow) | CFG SW ARZ SSC GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | EP
CFG SW ARZ SSC GN-CFG Deployment POR20 | SW | ARZ | SSC | Critical Facilities (Grow) | CFG SW ARZ SSC GN-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW ARZ TUC BD-CFG Deployment POR20 | SW | ARZ | TUC | Critical Facilities (Grow) | CFG SW ARZ TUC BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | EP
CFG SW ARZ TUC BD-CFG Deployment POR20 | SW | ARZ | TUC | Critical Facilities (Grow) | CFG SW ARZ TUC BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW ARZ TUC RC-CFG Deployment POR20 | SW | ARZ | TUC | Critical Facilities (Grow) | CFG SW ARZ TUC RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | EP
CFG SW ARZ TUC RC-CFG Deployment POR20 | SW | ARZ | TUC | Critical Facilities (Grow) | CFG SW ARZ TUC RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW ARZ WCG BS-CFG Deployment POR20 | SW | ARZ | WCG | Critical Facilities (Grow) | CFG SW ARZ WCG BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | EP
CFG SW ARZ WCG BS-CFG Deployment POR20 | SW | ARZ | WCG | Critical Facilities (Grow) | CFG SW ARZ WCG BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW ARZ WCG RC-CFG Deployment POR20 | SW | ARZ | WCG | Critical Facilities (Grow) | CFG SW ARZ WCG RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | EP
CFG SW ARZ WCG RC-CFG Deployment POR20 | SW | ARZ | WCG | Critical Facilities (Grow) | CFG SW ARZ WCG RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW LAS ERN RC-CFG Deployment POR20 | SW | LAS | ERN | Critical Facilities (Grow) | CFG SW LAS ERN RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | EP
CFG SW LAS ERN RC-CFG Deployment POR20 | SW | LAS | ERN | Critical Facilities (Grow) | CFG SW LAS ERN RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW LAS HEN BS-CFG Deployment POR20 | SW | LAS | HEN | Critical Facilities (Grow) | CFG SW LAS HEN BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | EP
CFG SW LAS HEN BS-CFG Deployment POR20 | SW | LAS | HEN | Critical Facilities (Grow) | CFG SW LAS HEN BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW LAS HEN BU-CFG Deployment POR20 | SW | LAS | HEN | Critical Facilities (Grow) | CFG SW LAS HEN BU-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | EP
CFG SW LAS HEN BU-CFG Deployment POR20 | SW | LAS | HEN | Critical Facilities (Grow) | CFG SW LAS HEN BU-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW LAS HEN HV-CFG Deployment POR20 | SW | LAS | HEN | Critical Facilities (Grow) | CFG SW LAS HEN HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | EP
CFG SW LAS HEN HV-CFG Deployment POR20 | SW | LAS | HEN | Critical Facilities (Grow) | CFG SW LAS HEN HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW LAS HEN IV-CFG Deployment POR20 | SW | LAS | HEN | Critical Facilities (Grow) | CFG SW LAS HEN IV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | EP
CFG SW LAS HEN IV-CFG Deployment POR20 | SW | LAS | HEN | Critical Facilities (Grow) | CFG SW LAS HEN IV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW LAS HEN RC-CFG Deployment POR20 | SW | LAS | HEN | Critical Facilities (Grow) | CFG SW LAS HEN RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | EP
CFG SW LAS HEN RC-CFG Deployment POR20 | SW | LAS | HEN | Critical Facilities (Grow) | CFG SW LAS HEN RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW LAS OSB BD-CFG Deployment POR20 | SW | LAS | OSB | Critical Facilities (Grow) | CFG SW LAS OSB BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | EP
CFG SW LAS OSB BD-CFG Deployment POR20 | SW | LAS | OSB | Critical Facilities (Grow) | CFG SW LAS OSB BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW LAS OSB DC-CFG Deployment POR20 | SW | LAS | OSB | Critical Facilities (Grow) | CFG SW LAS OSB DC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | EP
CFG SW LAS OSB DC-CFG Deployment POR20 | SW | LAS | OSB | Critical Facilities (Grow) | CFG SW LAS OSB DC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW LAS OSB IV-CFG Deployment POR20 | SW | LAS | OSB | Critical Facilities (Grow) | CFG SW LAS OSB IV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | EP
CFG SW LAS OSB IV-CFG Deployment POR20 | SW | LAS | OSB | Critical Facilities (Grow) | CFG SW LAS OSB IV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW LAS TEN BD-CFG Deployment POR20 | SW | LAS | TEN | Critical Facilities (Grow) | CFG SW LAS TEN BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | EP
CFG SW LAS TEN BD-CFG Deployment POR20 | SW | LAS | TEN | Critical Facilities (Grow) | CFG SW LAS TEN BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW LAS TEN HV-CFG Deployment POR20 | SW | LAS | TEN | Critical Facilities (Grow) | CFG SW LAS TEN HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | EP
CFG SW LAS TEN HV-CFG Deployment POR20 | SW | LAS | TEN | Critical Facilities (Grow) | CFG SW LAS TEN HV-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW LAS TEN HV-CFG Deployment POR20 - 2 | SW | LAS | TEN | Critical Facilities (Grow) | CFG SW LAS TEN HV-CFG Deployment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFG SW LAS TEN HV-CFG Deployment POR20 - 2 | SW | LAS | TEN | Critical Facilities (Grow) | CFG SW LAS TEN HV-CFG Deployment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG SW LAS TEN RC-CFG Deployment POR20 | SW | LAS | TEN | Critical Facilities (Grow) | CFG SW LAS TEN RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | EP
CFG SW LAS TEN RC-CFG Deployment POR20 | SW | LAS | TEN | Critical Facilities (Grow) | CFG SW LAS TEN RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2019-11-01 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG VA HRD CHS RC-CFG Deployment POR20 | VA | HRD | CHS | Critical Facilities (Grow) | CFG VA HRD CHS RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | Active | EP
CFG VA HRD CHS RC-CFG Deployment POR20 | VA | HRD | CHS | Critical Facilities (Grow) | CFG VA HRD CHS RC-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG VA HRD JCC BS-CFG Deployment POR20 | VA | HRD | JCC | Critical Facilities (Grow) | CFG VA HRD JCC BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | Active | EP
CFG VA HRD JCC BS-CFG Deployment POR20 | VA | HRD | JCC | Critical Facilities (Grow) | CFG VA HRD JCC BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG VA HRD LTF BS-CFG Deployment POR20 | VA | HRD | LTF | Critical Facilities (Grow) | CFG VA HRD LTF BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | Active | EP
CFG VA HRD LTF BS-CFG Deployment POR20 | VA | HRD | LTF | Critical Facilities (Grow) | CFG VA HRD LTF BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG VA HRD NRF AT-CFG Deployment POR20 | VA | HRD | NRF | Critical Facilities (Grow) | CFG VA HRD NRF AT-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | Active | EP
CFG VA HRD NRF AT-CFG Deployment POR20 | VA | HRD | NRF | Critical Facilities (Grow) | CFG VA HRD NRF AT-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG VA HRD NWP AT-CFG Deployment POR20 | VA | HRD | NWP | Critical Facilities (Grow) | CFG VA HRD NWP AT-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | Active | EP
CFG VA HRD NWP AT-CFG Deployment POR20 | VA | HRD | NWP | Critical Facilities (Grow) | CFG VA HRD NWP AT-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG VA HRD OCN BD-CFG Deployment POR20 | VA | HRD | OCN | Critical Facilities (Grow) | CFG VA HRD OCN BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | Active | EP
CFG VA HRD OCN BD-CFG Deployment POR20 | VA | HRD | OCN | Critical Facilities (Grow) | CFG VA HRD OCN BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG VA HRD PTM BD-CFG Deployment POR20 | VA | HRD | PTM | Critical Facilities (Grow) | CFG VA HRD PTM BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | Active | EP
CFG VA HRD PTM BD-CFG Deployment POR20 | VA | HRD | PTM | Critical Facilities (Grow) | CFG VA HRD PTM BD-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG VA NVA DRA BS-CFG Deployment POR20 | VA | NVA | DRA | Critical Facilities (Grow) | CFG VA NVA DRA BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | Active | EP
CFG VA NVA DRA BS-CFG Deployment POR20 | VA | NVA | DRA | Critical Facilities (Grow) | CFG VA NVA DRA BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG VA NVA FBG BS-CFG Deployment POR20 | VA | NVA | FBG | Critical Facilities (Grow) | CFG VA NVA FBG BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | Active | EP
CFG VA NVA FBG BS-CFG Deployment POR20 | VA | NVA | FBG | Critical Facilities (Grow) | CFG VA NVA FBG BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG VA NVA MFD BS-CFG Deployment POR20 | VA | NVA | MFD | Critical Facilities (Grow) | CFG VA NVA MFD BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | Active | EP
CFG VA NVA MFD BS-CFG Deployment POR20 | VA | NVA | MFD | Critical Facilities (Grow) | CFG VA NVA MFD BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG VA ROA RON BS-CFG Deployment POR20 | VA | ROA | RON | Critical Facilities (Grow) | CFG VA ROA RON BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | Active | EP
CFG VA ROA RON BS-CFG Deployment POR20 | VA | ROA | RON | Critical Facilities (Grow) | CFG VA ROA RON BS-CFG Deployment POR20 | Labor | No Equipment | 1 |  | 2020-01-20 |  | Active | Log | Upd | SN-0130 | New | Approved | 2020-02-06 11:01
CFG CA ORG AVJ BD-CFG Deployment POR20 | CA | ORG | AVJ | Critical Facilities (Grow) | CFG CA ORG AVJ BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | EP
CFG CA ORG AVJ BD-CFG Deployment POR20 | CA | ORG | AVJ | Critical Facilities (Grow) | CFG CA ORG AVJ BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | New | SN-0228 | New | Approved | 2020-02-07 14:33 | Missing 2020 Projects are needed to get added to POR
CFG CA ORG AVJ RC-CFG Deployment POR20 | CA | ORG | AVJ | Critical Facilities (Grow) | CFG CA ORG AVJ RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | EP
CFG CA ORG AVJ RC-CFG Deployment POR20 | CA | ORG | AVJ | Critical Facilities (Grow) | CFG CA ORG AVJ RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | New | SN-0228 | New | Approved | 2020-02-07 14:33 | Missing 2020 Projects are needed to get added to POR
CFG CA ORG ORG RK-CFG Deployment POR20 | CA | ORG | ORG | Critical Facilities (Grow) | CFG CA ORG ORG RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG CA ORG ORG RK-CFG Deployment POR20 | CA | ORG | ORG | Critical Facilities (Grow) | CFG CA ORG ORG RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | Active | Log | New | SN-0228 | New | Approved | 2020-02-07 14:33 | Missing 2020 Projects are needed to get added to POR
CFG CA SAN ESC RC-CFG Deployment POR20 | CA | SAN | ESC | Critical Facilities (Grow) | CFG CA SAN ESC RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-15 |  | Active | EP
CFG CA SAN ESC RC-CFG Deployment POR20 | CA | SAN | ESC | Critical Facilities (Grow) | CFG CA SAN ESC RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-15 |  | Active | Log | New | SN-0228 | New | Approved | 2020-02-07 14:33 | Missing 2020 Projects are needed to get added to POR
CFG CA SAN OCE RC-CFG Deployment POR20 | CA | SAN | OCE | Critical Facilities (Grow) | CFG CA SAN OCE RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-15 |  | Active | EP
CFG CA SAN OCE RC-CFG Deployment POR20 | CA | SAN | OCE | Critical Facilities (Grow) | CFG CA SAN OCE RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-15 |  | Active | Log | New | SN-0228 | New | Approved | 2020-02-07 14:33 | Missing 2020 Projects are needed to get added to POR
CFG CA SAN PWY RC-CFG Deployment POR20 | CA | SAN | PWY | Critical Facilities (Grow) | CFG CA SAN PWY RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-15 |  | Active | EP
CFG CA SAN PWY RC-CFG Deployment POR20 | CA | SAN | PWY | Critical Facilities (Grow) | CFG CA SAN PWY RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-15 |  | Active | Log | New | SN-0228 | New | Approved | 2020-02-07 14:33 | Missing 2020 Projects are needed to get added to POR
CFG CA SAN VST BS-CFG Deployment POR20 | CA | SAN | VST | Critical Facilities (Grow) | CFG CA SAN VST BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-15 |  | Active | EP
CFG CA SAN VST BS-CFG Deployment POR20 | CA | SAN | VST | Critical Facilities (Grow) | CFG CA SAN VST BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-15 |  | Active | Log | New | SN-0228 | New | Approved | 2020-02-07 14:33 | Missing 2020 Projects are needed to get added to POR
CFG CA SAN VST RC-CFG Deployment POR20 | CA | SAN | VST | Critical Facilities (Grow) | CFG CA SAN VST RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-15 |  | Active | EP
CFG CA SAN VST RC-CFG Deployment POR20 | CA | SAN | VST | Critical Facilities (Grow) | CFG CA SAN VST RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-15 |  | Active | Log | New | SN-0228 | New | Approved | 2020-02-07 14:33 | Missing 2020 Projects are needed to get added to POR
CFG CE OMA OMM RK-CFG Deployment POR20 | CE | OMA | OMM | Critical Facilities (Grow) | CFG CE OMA OMM RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-15 |  | Active | EP
CFG CE OMA OMM RK-CFG Deployment POR20 | CE | OMA | OMM | Critical Facilities (Grow) | CFG CE OMA OMM RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-15 |  | Active | Log | New | SN-0228 | New | Approved | 2020-02-07 14:33 | Missing 2020 Projects are needed to get added to POR
CFG NE CLE CLV RC-CFG Deployment POR20 | NE | CLE | CLV | Critical Facilities (Grow) | CFG NE CLE CLV RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | EP
CFG NE CLE CLV RC-CFG Deployment POR20 | NE | CLE | CLV | Critical Facilities (Grow) | CFG NE CLE CLV RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | New | SN-0228 | New | Approved | 2020-02-07 14:33 | Missing 2020 Projects are needed to get added to POR
CFG NE CON SFD BD-CFG Deployment POR20 | NE | CON | SFD | Critical Facilities (Grow) | CFG NE CON SFD BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | EP
CFG NE CON SFD BD-CFG Deployment POR20 | NE | CON | SFD | Critical Facilities (Grow) | CFG NE CON SFD BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | New | SN-0228 | New | Approved | 2020-02-07 14:33 | Missing 2020 Projects are needed to get added to POR
CFG NE RHD LNC BD-CFG Deployment POR20 | NE | RHD | LNC | Critical Facilities (Grow) | CFG NE RHD LNC BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | EP
CFG NE RHD LNC BD-CFG Deployment POR20 | NE | RHD | LNC | Critical Facilities (Grow) | CFG NE RHD LNC BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | New | SN-0228 | New | Approved | 2020-02-07 14:33 | Missing 2020 Projects are needed to get added to POR
CFG SE GCT PNS RK-CFG Deployment POR20 | SE | GCT | PNS | Critical Facilities (Grow) | CFG SE GCT PNS RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG SE GCT PNS RK-CFG Deployment POR20 | SE | GCT | PNS | Critical Facilities (Grow) | CFG SE GCT PNS RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | Active | Log | New | SN-0228 | New | Approved | 2020-02-07 14:33 | Missing 2020 Projects are needed to get added to POR
CFG SE NOR CLR BM-CFG Deployment POR20 | SE | NOR | CLR | Critical Facilities (Grow) | CFG SE NOR CLR BM-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG SE NOR CLR BM-CFG Deployment POR20 | SE | NOR | CLR | Critical Facilities (Grow) | CFG SE NOR CLR BM-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | Active | Log | New | SN-0228 | New | Approved | 2020-02-07 14:33 | Missing 2020 Projects are needed to get added to POR
CFG SE NOR CLR BS-CFG Deployment POR20 | SE | NOR | CLR | Critical Facilities (Grow) | CFG SE NOR CLR BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG SE NOR CLR BS-CFG Deployment POR20 | SE | NOR | CLR | Critical Facilities (Grow) | CFG SE NOR CLR BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | Active | Log | New | SN-0228 | New | Approved | 2020-02-07 14:33 | Missing 2020 Projects are needed to get added to POR
CFG SE NOR CLR BS-CFG Deployment POR20 - 2 | SE | NOR | CLR | Critical Facilities (Grow) | CFG SE NOR CLR BS-CFG Deployment POR20 - 2 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG SE NOR CLR BS-CFG Deployment POR20 - 2 | SE | NOR | CLR | Critical Facilities (Grow) | CFG SE NOR CLR BS-CFG Deployment POR20 - 2 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | Active | Log | New | SN-0228 | New | Approved | 2020-02-07 14:33 | Missing 2020 Projects are needed to get added to POR
CFG SE NOR CLR RC-CFG Deployment POR20 | SE | NOR | CLR | Critical Facilities (Grow) | CFG SE NOR CLR RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG SE NOR CLR RC-CFG Deployment POR20 | SE | NOR | CLR | Critical Facilities (Grow) | CFG SE NOR CLR RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | Active | Log | New | SN-0228 | New | Approved | 2020-02-07 14:33 | Missing 2020 Projects are needed to get added to POR
CFG SE NOR KNN BD-CFG Deployment POR20 | SE | NOR | KNN | Critical Facilities (Grow) | CFG SE NOR KNN BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | EP
CFG SE NOR KNN BD-CFG Deployment POR20 | SE | NOR | KNN | Critical Facilities (Grow) | CFG SE NOR KNN BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | New | SN-0228 | New | Approved | 2020-02-07 14:33 | Missing 2020 Projects are needed to get added to POR
CFG SE NOR MCY HV-CFG Deployment POR20 | SE | NOR | MCY | Critical Facilities (Grow) | CFG SE NOR MCY HV-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG SE NOR MCY HV-CFG Deployment POR20 | SE | NOR | MCY | Critical Facilities (Grow) | CFG SE NOR MCY HV-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | Active | Log | New | SN-0228 | New | Approved | 2020-02-07 14:33 | Missing 2020 Projects are needed to get added to POR
CFG SE NOR NOE BM-CFG Deployment POR20 | SE | NOR | NOE | Critical Facilities (Grow) | CFG SE NOR NOE BM-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG SE NOR NOE BM-CFG Deployment POR20 | SE | NOR | NOE | Critical Facilities (Grow) | CFG SE NOR NOE BM-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | Active | Log | New | SN-0228 | New | Approved | 2020-02-07 14:33 | Missing 2020 Projects are needed to get added to POR
CFG SE NOR NOE BS-CFG Deployment POR20 | SE | NOR | NOE | Critical Facilities (Grow) | CFG SE NOR NOE BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG SE NOR NOE BS-CFG Deployment POR20 | SE | NOR | NOE | Critical Facilities (Grow) | CFG SE NOR NOE BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | Active | Log | New | SN-0228 | New | Approved | 2020-02-07 14:33 | Missing 2020 Projects are needed to get added to POR
CFG SE NOR NOE BS-CFG Deployment POR20 - 2 | SE | NOR | NOE | Critical Facilities (Grow) | CFG SE NOR NOE BS-CFG Deployment POR20 - 2 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG SE NOR NOE BS-CFG Deployment POR20 - 2 | SE | NOR | NOE | Critical Facilities (Grow) | CFG SE NOR NOE BS-CFG Deployment POR20 - 2 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | Active | Log | New | SN-0228 | New | Approved | 2020-02-07 14:33 | Missing 2020 Projects are needed to get added to POR
CFG SE NOR NOE RC-CFG Deployment POR20 | SE | NOR | NOE | Critical Facilities (Grow) | CFG SE NOR NOE RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG SE NOR NOE RC-CFG Deployment POR20 | SE | NOR | NOE | Critical Facilities (Grow) | CFG SE NOR NOE RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | Active | Log | New | SN-0228 | New | Approved | 2020-02-07 14:33 | Missing 2020 Projects are needed to get added to POR
CFG SW ARZ CHD RK-CFG Deployment POR20 | SW | ARZ | CHD | Critical Facilities (Grow) | CFG SW ARZ CHD RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | EP
CFG SW ARZ CHD RK-CFG Deployment POR20 | SW | ARZ | CHD | Critical Facilities (Grow) | CFG SW ARZ CHD RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | New | SN-0228 | New | Approved | 2020-02-07 14:33 | Missing 2020 Projects are needed to get added to POR
CFG SW ARZ DGL RK-CFG Deployment POR20 | SW | ARZ | DGL | Critical Facilities (Grow) | CFG SW ARZ DGL RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | EP
CFG SW ARZ DGL RK-CFG Deployment POR20 | SW | ARZ | DGL | Critical Facilities (Grow) | CFG SW ARZ DGL RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | New | SN-0228 | New | Approved | 2020-02-07 14:33 | Missing 2020 Projects are needed to get added to POR
CFG VA HRD GBR RC-CFG Deployment POR20 | VA | HRD | GBR | Critical Facilities (Grow) | CFG VA HRD GBR RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-15 |  | Active | EP
CFG VA HRD GBR RC-CFG Deployment POR20 | VA | HRD | GBR | Critical Facilities (Grow) | CFG VA HRD GBR RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-15 |  | Active | Log | New | SN-0228 | New | Approved | 2020-02-07 14:33 | Missing 2020 Projects are needed to get added to POR
CFG VA HRD OCN BS-CFG Deployment POR20 | VA | HRD | OCN | Critical Facilities (Grow) | CFG VA HRD OCN BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | EP
CFG VA HRD OCN BS-CFG Deployment POR20 | VA | HRD | OCN | Critical Facilities (Grow) | CFG VA HRD OCN BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | New | SN-0228 | New | Approved | 2020-02-07 14:33 | Missing 2020 Projects are needed to get added to POR
CFG VA HRD PTM BS-CFG Deployment POR20 | VA | HRD | PTM | Critical Facilities (Grow) | CFG VA HRD PTM BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-15 |  | Active | EP
CFG VA HRD PTM BS-CFG Deployment POR20 | VA | HRD | PTM | Critical Facilities (Grow) | CFG VA HRD PTM BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-15 |  | Active | Log | New | SN-0228 | New | Approved | 2020-02-07 14:33 | Missing 2020 Projects are needed to get added to POR
CFG VA HRD VBC BS-CFG Deployment POR20 | VA | HRD | VBC | Critical Facilities (Grow) | CFG VA HRD VBC BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-15 |  | Active | EP
CFG VA HRD VBC BS-CFG Deployment POR20 | VA | HRD | VBC | Critical Facilities (Grow) | CFG VA HRD VBC BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-15 |  | Active | Log | New | SN-0228 | New | Approved | 2020-02-07 14:33 | Missing 2020 Projects are needed to get added to POR
CFG CA ORG AVJ RK-CFG Deployment POR20 | CA | ORG | AVJ | Critical Facilities (Grow) | CFG CA ORG AVJ RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | Active | EP
CFG CA ORG AVJ RK-CFG Deployment POR20 | CA | ORG | AVJ | Critical Facilities (Grow) | CFG CA ORG AVJ RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | Active | Log | New | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG CA ORG IRV RK-CFG Deployment POR20 | CA | ORG | IRV | Critical Facilities (Grow) | CFG CA ORG IRV RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | Active | EP
CFG CA ORG IRV RK-CFG Deployment POR20 | CA | ORG | IRV | Critical Facilities (Grow) | CFG CA ORG IRV RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | Active | Log | New | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG CA ORG RSM AC-CFG Deployment POR20 | CA | ORG | RSM | Critical Facilities (Grow) | CFG CA ORG RSM AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-20 |  | Active | EP
CFG CA ORG RSM AC-CFG Deployment POR20 | CA | ORG | RSM | Critical Facilities (Grow) | CFG CA ORG RSM AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-20 |  | Active | Log | New | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG CA ORG RSM BD-CFG Deployment POR20 | CA | ORG | RSM | Critical Facilities (Grow) | CFG CA ORG RSM BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-06-01 | 2020-06-20 |  | Active | EP
CFG CA ORG RSM BD-CFG Deployment POR20 | CA | ORG | RSM | Critical Facilities (Grow) | CFG CA ORG RSM BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-06-01 | 2020-06-20 |  | Active | Log | New | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG CA ORG RSM BS-CFG Deployment POR20 | CA | ORG | RSM | Critical Facilities (Grow) | CFG CA ORG RSM BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | EP
CFG CA ORG RSM BS-CFG Deployment POR20 | CA | ORG | RSM | Critical Facilities (Grow) | CFG CA ORG RSM BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | Log | New | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG CA ORG RSM RK-CFG Deployment POR20 | CA | ORG | RSM | Critical Facilities (Grow) | CFG CA ORG RSM RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | EP
CFG CA ORG RSM RK-CFG Deployment POR20 | CA | ORG | RSM | Critical Facilities (Grow) | CFG CA ORG RSM RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | Log | New | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG CA SAN CHU RC-CFG Deployment POR20 | CA | SAN | CHU | Critical Facilities (Grow) | CFG CA SAN CHU RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | EP
CFG CA SAN CHU RC-CFG Deployment POR20 | CA | SAN | CHU | Critical Facilities (Grow) | CFG CA SAN CHU RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | Log | New | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG CA SAN DWN RC-CFG Deployment POR20 | CA | SAN | DWN | Critical Facilities (Grow) | CFG CA SAN DWN RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | EP
CFG CA SAN DWN RC-CFG Deployment POR20 | CA | SAN | DWN | Critical Facilities (Grow) | CFG CA SAN DWN RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | Log | New | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG CA SAN ELC RK-CFG Deployment POR20 | CA | SAN | ELC | Critical Facilities (Grow) | CFG CA SAN ELC RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | EP
CFG CA SAN ELC RK-CFG Deployment POR20 | CA | SAN | ELC | Critical Facilities (Grow) | CFG CA SAN ELC RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG CA SAN FED RC-CFG Deployment POR20 | CA | SAN | FED | Critical Facilities (Grow) | CFG CA SAN FED RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | EP
CFG CA SAN FED RC-CFG Deployment POR20 | CA | SAN | FED | Critical Facilities (Grow) | CFG CA SAN FED RC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG CA SAN OCE RK-CFG Deployment POR20 | CA | SAN | OCE | Critical Facilities (Grow) | CFG CA SAN OCE RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | EP
CFG CA SAN OCE RK-CFG Deployment POR20 | CA | SAN | OCE | Critical Facilities (Grow) | CFG CA SAN OCE RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG CA SAN PWY BS-CFG Deployment POR20 | CA | SAN | PWY | Critical Facilities (Grow) | CFG CA SAN PWY BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | EP
CFG CA SAN PWY BS-CFG Deployment POR20 | CA | SAN | PWY | Critical Facilities (Grow) | CFG CA SAN PWY BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG CE OKC MWC RK-CFG Deployment POR20 | CE | OKC | MWC | Critical Facilities (Grow) | CFG CE OKC MWC RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | Active | EP
CFG CE OKC MWC RK-CFG Deployment POR20 | CE | OKC | MWC | Critical Facilities (Grow) | CFG CE OKC MWC RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG NE CLE CLV RC-CFS Deployment POR20 | NE | CLE | CLV | Critical Facilities (Grow) | CFG NE CLE CLV RC-CFS Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | EP
CFG NE CLE CLV RC-CFS Deployment POR20 | NE | CLE | CLV | Critical Facilities (Grow) | CFG NE CLE CLV RC-CFS Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG NE CON ENF AC-CFG Deployment POR20 | NE | CON | ENF | Critical Facilities (Grow) | CFG NE CON ENF AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | Active | EP
CFG NE CON ENF AC-CFG Deployment POR20 | NE | CON | ENF | Critical Facilities (Grow) | CFG NE CON ENF AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG NE CON ENF AC-CFG Deployment POR20 | NE | CON | ENF | Critical Facilities (Grow) | CFG NE CON ENF AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | Upd | SN-0593 | Schedule Change | Canceled | 2020-06-22 11:08 | updating need by date for grown projects
CFG NE CON ENF HV-CFG Deployment POR20 | NE | CON | ENF | Critical Facilities (Grow) | CFG NE CON ENF HV-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-20 |  | Active | EP
CFG NE CON ENF HV-CFG Deployment POR20 | NE | CON | ENF | Critical Facilities (Grow) | CFG NE CON ENF HV-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG NE CON RKH HV-CFG Deployment POR20 | NE | CON | RKH | Critical Facilities (Grow) | CFG NE CON RKH HV-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-20 |  | Active | EP
CFG NE CON RKH HV-CFG Deployment POR20 | NE | CON | RKH | Critical Facilities (Grow) | CFG NE CON RKH HV-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG NE RHD PAW AC-CFG Deployment POR20 | NE | RHD | PAW | Critical Facilities (Grow) | CFG NE RHD PAW AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | Active | EP
CFG NE RHD PAW AC-CFG Deployment POR20 | NE | RHD | PAW | Critical Facilities (Grow) | CFG NE RHD PAW AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG NE RHD PAW AC-CFG Deployment POR20 | NE | RHD | PAW | Critical Facilities (Grow) | CFG NE RHD PAW AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | Upd | SN-0593 | Schedule Change | Canceled | 2020-06-22 11:08 | updating need by date for grown projects
CFG NE RHD PRV AC-CFG Deployment POR20 | NE | RHD | PRV | Critical Facilities (Grow) | CFG NE RHD PRV AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | Active | EP
CFG NE RHD PRV AC-CFG Deployment POR20 | NE | RHD | PRV | Critical Facilities (Grow) | CFG NE RHD PRV AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG NE RHD PRV AC-CFG Deployment POR20 | NE | RHD | PRV | Critical Facilities (Grow) | CFG NE RHD PRV AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | Upd | SN-0593 | Schedule Change | Canceled | 2020-06-22 11:08 | updating need by date for grown projects
CFG SE BTR BTR RK-CFG Deployment POR20 | SE | BTR | BTR | Critical Facilities (Grow) | CFG SE BTR BTR RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | EP
CFG SE BTR BTR RK-CFG Deployment POR20 | SE | BTR | BTR | Critical Facilities (Grow) | CFG SE BTR BTR RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG SE BTR SPC AC-CFG Deployment POR20 | SE | BTR | SPC | Critical Facilities (Grow) | CFG SE BTR SPC AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | EP
CFG SE BTR SPC AC-CFG Deployment POR20 | SE | BTR | SPC | Critical Facilities (Grow) | CFG SE BTR SPC AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG SE GAN GNS RK-CFG Deployment POR20 | SE | GAN | GNS | Critical Facilities (Grow) | CFG SE GAN GNS RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | EP
CFG SE GAN GNS RK-CFG Deployment POR20 | SE | GAN | GNS | Critical Facilities (Grow) | CFG SE GAN GNS RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG SE LFY LFY RK-CFG Deployment POR20 | SE | LFY | LFY | Critical Facilities (Grow) | CFG SE LFY LFY RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | EP
CFG SE LFY LFY RK-CFG Deployment POR20 | SE | LFY | LFY | Critical Facilities (Grow) | CFG SE LFY LFY RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG SE MGA MCN RK-CFG Deployment POR20 | SE | MGA | MCN | Critical Facilities (Grow) | CFG SE MGA MCN RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | EP
CFG SE MGA MCN RK-CFG Deployment POR20 | SE | MGA | MCN | Critical Facilities (Grow) | CFG SE MGA MCN RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG SE NOR CLR AC-CFG Deployment POR20 | SE | NOR | CLR | Critical Facilities (Grow) | CFG SE NOR CLR AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | Active | EP
CFG SE NOR CLR AC-CFG Deployment POR20 | SE | NOR | CLR | Critical Facilities (Grow) | CFG SE NOR CLR AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG SE NOR CLR RK-CFG Deployment POR20 | SE | NOR | CLR | Critical Facilities (Grow) | CFG SE NOR CLR RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | EP
CFG SE NOR CLR RK-CFG Deployment POR20 | SE | NOR | CLR | Critical Facilities (Grow) | CFG SE NOR CLR RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG SE NOR NOE AC-CFG Deployment POR20 | SE | NOR | NOE | Critical Facilities (Grow) | CFG SE NOR NOE AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | EP
CFG SE NOR NOE AC-CFG Deployment POR20 | SE | NOR | NOE | Critical Facilities (Grow) | CFG SE NOR NOE AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG SE NOR NOE BD-CFG Deployment POR20 | SE | NOR | NOE | Critical Facilities (Grow) | CFG SE NOR NOE BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | Active | EP
CFG SE NOR NOE BD-CFG Deployment POR20 | SE | NOR | NOE | Critical Facilities (Grow) | CFG SE NOR NOE BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG SW ARZ PEO RK-CFG Deployment POR20 | SW | ARZ | PEO | Critical Facilities (Grow) | CFG SW ARZ PEO RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-03 | 2020-02-20 |  | Active | EP
CFG SW ARZ PEO RK-CFG Deployment POR20 | SW | ARZ | PEO | Critical Facilities (Grow) | CFG SW ARZ PEO RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-03 | 2020-02-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG SW LAS OSB HV-CFG Deployment POR20 | SW | LAS | OSB | Critical Facilities (Grow) | CFG SW LAS OSB HV-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | EP
CFG SW LAS OSB HV-CFG Deployment POR20 | SW | LAS | OSB | Critical Facilities (Grow) | CFG SW LAS OSB HV-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG VA HRD CHS AC-CFG Deployment POR20 | VA | HRD | CHS | Critical Facilities (Grow) | CFG VA HRD CHS AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | Active | EP
CFG VA HRD CHS AC-CFG Deployment POR20 | VA | HRD | CHS | Critical Facilities (Grow) | CFG VA HRD CHS AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG VA HRD CHS AC-CFG Deployment POR20 | VA | HRD | CHS | Critical Facilities (Grow) | CFG VA HRD CHS AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | Upd | SN-0593 | Schedule Change | Canceled | 2020-06-22 11:08 | updating need by date for grown projects
CFG VA HRD HCK AC-CFG Deployment POR20 | VA | HRD | HCK | Critical Facilities (Grow) | CFG VA HRD HCK AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | Active | EP
CFG VA HRD HCK AC-CFG Deployment POR20 | VA | HRD | HCK | Critical Facilities (Grow) | CFG VA HRD HCK AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG VA HRD HCK AC-CFG Deployment POR20 | VA | HRD | HCK | Critical Facilities (Grow) | CFG VA HRD HCK AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | Upd | SN-0593 | Schedule Change | Canceled | 2020-06-22 11:08 | updating need by date for grown projects
CFG VA HRD LTF AC-CFG Deployment POR20 | VA | HRD | LTF | Critical Facilities (Grow) | CFG VA HRD LTF AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | Active | EP
CFG VA HRD LTF AC-CFG Deployment POR20 | VA | HRD | LTF | Critical Facilities (Grow) | CFG VA HRD LTF AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG VA HRD LTF AC-CFG Deployment POR20 | VA | HRD | LTF | Critical Facilities (Grow) | CFG VA HRD LTF AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | Upd | SN-0593 | Schedule Change | Canceled | 2020-06-22 11:08 | updating need by date for grown projects
CFG VA HRD NRF AC-CFG Deployment POR20 | VA | HRD | NRF | Critical Facilities (Grow) | CFG VA HRD NRF AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | Active | EP
CFG VA HRD NRF AC-CFG Deployment POR20 | VA | HRD | NRF | Critical Facilities (Grow) | CFG VA HRD NRF AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG VA HRD NRF AC-CFG Deployment POR20 | VA | HRD | NRF | Critical Facilities (Grow) | CFG VA HRD NRF AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | Upd | SN-0593 | Schedule Change | Canceled | 2020-06-22 11:08 | updating need by date for grown projects
CFG VA HRD OCN AC-CFG Deployment POR20 | VA | HRD | OCN | Critical Facilities (Grow) | CFG VA HRD OCN AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | Active | EP
CFG VA HRD OCN AC-CFG Deployment POR20 | VA | HRD | OCN | Critical Facilities (Grow) | CFG VA HRD OCN AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG VA HRD OCN AC-CFG Deployment POR20 | VA | HRD | OCN | Critical Facilities (Grow) | CFG VA HRD OCN AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | Upd | SN-0593 | Schedule Change | Canceled | 2020-06-22 11:08 | updating need by date for grown projects
CFG VA HRD PRA AC-CFG Deployment POR20 | VA | HRD | PRA | Critical Facilities (Grow) | CFG VA HRD PRA AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | Active | EP
CFG VA HRD PRA AC-CFG Deployment POR20 | VA | HRD | PRA | Critical Facilities (Grow) | CFG VA HRD PRA AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG VA HRD PRA AC-CFG Deployment POR20 | VA | HRD | PRA | Critical Facilities (Grow) | CFG VA HRD PRA AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | Upd | SN-0593 | Schedule Change | Canceled | 2020-06-22 11:08 | updating need by date for grown projects
CFG VA HRD PRA BD-CFG Deployment POR20 | VA | HRD | PRA | Critical Facilities (Grow) | CFG VA HRD PRA BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | EP
CFG VA HRD PRA BD-CFG Deployment POR20 | VA | HRD | PRA | Critical Facilities (Grow) | CFG VA HRD PRA BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG VA HRD PTM AC-CFG Deployment POR20 | VA | HRD | PTM | Critical Facilities (Grow) | CFG VA HRD PTM AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | Active | EP
CFG VA HRD PTM AC-CFG Deployment POR20 | VA | HRD | PTM | Critical Facilities (Grow) | CFG VA HRD PTM AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG VA HRD PTM AC-CFG Deployment POR20 | VA | HRD | PTM | Critical Facilities (Grow) | CFG VA HRD PTM AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | Upd | SN-0593 | Schedule Change | Canceled | 2020-06-22 11:08 | updating need by date for grown projects
CFG VA NVA FBG BD-CFG Deployment POR20 | VA | NVA | FBG | Critical Facilities (Grow) | CFG VA NVA FBG BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | EP
CFG VA NVA FBG BD-CFG Deployment POR20 | VA | NVA | FBG | Critical Facilities (Grow) | CFG VA NVA FBG BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG VA NVA FLK BD-CFG Deployment POR20 | VA | NVA | FLK | Critical Facilities (Grow) | CFG VA NVA FLK BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | Active | EP
CFG VA NVA FLK BD-CFG Deployment POR20 | VA | NVA | FLK | Critical Facilities (Grow) | CFG VA NVA FLK BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG VA NVA FLK BD-CFG Deployment POR20 | VA | NVA | FLK | Critical Facilities (Grow) | CFG VA NVA FLK BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | Upd | SN-0593 | Schedule Change | Canceled | 2020-06-22 11:08 | updating need by date for grown projects
CFG VA NVA MFD BD-CFG Deployment POR20 | VA | NVA | MFD | Critical Facilities (Grow) | CFG VA NVA MFD BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | EP
CFG VA NVA MFD BD-CFG Deployment POR20 | VA | NVA | MFD | Critical Facilities (Grow) | CFG VA NVA MFD BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG VA ROA RON AC-CFG Deployment POR20 | VA | ROA | RON | Critical Facilities (Grow) | CFG VA ROA RON AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | Active | EP
CFG VA ROA RON AC-CFG Deployment POR20 | VA | ROA | RON | Critical Facilities (Grow) | CFG VA ROA RON AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG VA ROA RON AC-CFG Deployment POR20 | VA | ROA | RON | Critical Facilities (Grow) | CFG VA ROA RON AC-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | Upd | SN-0593 | Schedule Change | Canceled | 2020-06-22 11:08 | updating need by date for grown projects
CFG CA ORG AVJ BS-CFG Deployment POR20 | CA | ORG | AVJ | Critical Facilities (Grow) | CFG CA ORG AVJ BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | EP
CFG CA ORG AVJ BS-CFG Deployment POR20 | CA | ORG | AVJ | Critical Facilities (Grow) | CFG CA ORG AVJ BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | Log | Undel | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG CA ORG DNP BS-CFG Deployment POR20 | CA | ORG | DNP | Critical Facilities (Grow) | CFG CA ORG DNP BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | EP
CFG CA ORG DNP BS-CFG Deployment POR20 | CA | ORG | DNP | Critical Facilities (Grow) | CFG CA ORG DNP BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | Log | Undel | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG CA ORG IRV BS-CFG Deployment POR20 | CA | ORG | IRV | Critical Facilities (Grow) | CFG CA ORG IRV BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-03 | 2020-02-20 |  | Active | EP
CFG CA ORG IRV BS-CFG Deployment POR20 | CA | ORG | IRV | Critical Facilities (Grow) | CFG CA ORG IRV BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-02-03 | 2020-02-20 |  | Active | Log | Undel | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG CA ORG ORG BS-CFG Deployment POR20 | CA | ORG | ORG | Critical Facilities (Grow) | CFG CA ORG ORG BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | EP
CFG CA ORG ORG BS-CFG Deployment POR20 | CA | ORG | ORG | Critical Facilities (Grow) | CFG CA ORG ORG BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | Log | Undel | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG CA SAN DWN BS-CFG Deployment POR20 | CA | SAN | DWN | Critical Facilities (Grow) | CFG CA SAN DWN BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-20 |  | Active | EP
CFG CA SAN DWN BS-CFG Deployment POR20 | CA | SAN | DWN | Critical Facilities (Grow) | CFG CA SAN DWN BS-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-20 |  | Active | Log | Undel | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG CA SAN DWN RK-CFG Deployment POR20 | CA | SAN | DWN | Critical Facilities (Grow) | CFG CA SAN DWN RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | EP
CFG CA SAN DWN RK-CFG Deployment POR20 | CA | SAN | DWN | Critical Facilities (Grow) | CFG CA SAN DWN RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | Log | Undel | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG NE CLE CLV IV-CFG Deployment POR20 | NE | CLE | CLV | Critical Facilities (Grow) | CFG NE CLE CLV IV-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-20 |  | Active | EP
CFG NE CLE CLV IV-CFG Deployment POR20 | NE | CLE | CLV | Critical Facilities (Grow) | CFG NE CLE CLV IV-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-20 |  | Active | Log | Undel | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG NE CON ENF RK-CFG Deployment POR20 | NE | CON | ENF | Critical Facilities (Grow) | CFG NE CON ENF RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | EP
CFG NE CON ENF RK-CFG Deployment POR20 | NE | CON | ENF | Critical Facilities (Grow) | CFG NE CON ENF RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | Log | Undel | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG NE CON SFD GN-CFG Deployment POR20 | NE | CON | SFD | Critical Facilities (Grow) | CFG NE CON SFD GN-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-06-01 | 2020-06-20 |  | Active | EP
CFG NE CON SFD GN-CFG Deployment POR20 | NE | CON | SFD | Critical Facilities (Grow) | CFG NE CON SFD GN-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-06-01 | 2020-06-20 |  | Active | Log | Undel | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG NE RHD BUR BD-CFG Deployment POR20 | NE | RHD | BUR | Critical Facilities (Grow) | CFG NE RHD BUR BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | Active | EP
CFG NE RHD BUR BD-CFG Deployment POR20 | NE | RHD | BUR | Critical Facilities (Grow) | CFG NE RHD BUR BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | Active | Log | Undel | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG NE RHD BUR GN-CFG Deployment POR20 | NE | RHD | BUR | Critical Facilities (Grow) | CFG NE RHD BUR GN-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | Active | EP
CFG NE RHD BUR GN-CFG Deployment POR20 | NE | RHD | BUR | Critical Facilities (Grow) | CFG NE RHD BUR GN-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | Active | Log | Undel | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG NE RHD CRN RK-CFG Deployment POR20 | NE | RHD | CRN | Critical Facilities (Grow) | CFG NE RHD CRN RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-08-03 | 2020-08-20 |  | Active | EP
CFG NE RHD CRN RK-CFG Deployment POR20 | NE | RHD | CRN | Critical Facilities (Grow) | CFG NE RHD CRN RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-08-03 | 2020-08-20 |  | Active | Log | Undel | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG NE RHD EXT RK-CFG Deployment POR20 | NE | RHD | EXT | Critical Facilities (Grow) | CFG NE RHD EXT RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-06-01 | 2020-06-20 |  | Active | EP
CFG NE RHD EXT RK-CFG Deployment POR20 | NE | RHD | EXT | Critical Facilities (Grow) | CFG NE RHD EXT RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-06-01 | 2020-06-20 |  | Active | Log | Undel | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG NE RHD LNC RK-CFG Deployment POR20 | NE | RHD | LNC | Critical Facilities (Grow) | CFG NE RHD LNC RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-07-14 | 2020-07-20 |  | Active | EP
CFG NE RHD LNC RK-CFG Deployment POR20 | NE | RHD | LNC | Critical Facilities (Grow) | CFG NE RHD LNC RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-07-14 | 2020-07-20 |  | Active | Log | Undel | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG NE RHD PAW RK-CFG Deployment POR20 | NE | RHD | PAW | Critical Facilities (Grow) | CFG NE RHD PAW RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | Active | EP
CFG NE RHD PAW RK-CFG Deployment POR20 | NE | RHD | PAW | Critical Facilities (Grow) | CFG NE RHD PAW RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | Active | Log | Undel | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG NE RHD PRV BD-CFG Deployment POR20 | NE | RHD | PRV | Critical Facilities (Grow) | CFG NE RHD PRV BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | EP
CFG NE RHD PRV BD-CFG Deployment POR20 | NE | RHD | PRV | Critical Facilities (Grow) | CFG NE RHD PRV BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | Log | Undel | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG NE RHD PRV RK-CFG Deployment POR20 | NE | RHD | PRV | Critical Facilities (Grow) | CFG NE RHD PRV RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | EP
CFG NE RHD PRV RK-CFG Deployment POR20 | NE | RHD | PRV | Critical Facilities (Grow) | CFG NE RHD PRV RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | Log | Undel | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG SE BTR SPC RK-CFG Deployment POR20 | SE | BTR | SPC | Critical Facilities (Grow) | CFG SE BTR SPC RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | EP
CFG SE BTR SPC RK-CFG Deployment POR20 | SE | BTR | SPC | Critical Facilities (Grow) | CFG SE BTR SPC RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | Log | Undel | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG SE GAN OCL RK-CFG Deployment POR20 | SE | GAN | OCL | Critical Facilities (Grow) | CFG SE GAN OCL RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | Active | EP
CFG SE GAN OCL RK-CFG Deployment POR20 | SE | GAN | OCL | Critical Facilities (Grow) | CFG SE GAN OCL RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | Active | Log | Undel | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG SE MGA WRB RK-CFG Deployment POR20 | SE | MGA | WRB | Critical Facilities (Grow) | CFG SE MGA WRB RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | EP
CFG SE MGA WRB RK-CFG Deployment POR20 | SE | MGA | WRB | Critical Facilities (Grow) | CFG SE MGA WRB RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | Log | Undel | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG CA SAN CHU BD-CFG Deployment POR20 | CA | SAN | CHU | Critical Facilities (Grow) | CFG CA SAN CHU BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | Active | EP
CFG CA SAN CHU BD-CFG Deployment POR20 | CA | SAN | CHU | Critical Facilities (Grow) | CFG CA SAN CHU BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | Active | Log | Undel | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG CA SAN CHU RK-CFG Deployment POR20 | CA | SAN | CHU | Critical Facilities (Grow) | CFG CA SAN CHU RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | Active | EP
CFG CA SAN CHU RK-CFG Deployment POR20 | CA | SAN | CHU | Critical Facilities (Grow) | CFG CA SAN CHU RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | Active | Log | Undel | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG CA SAN DWN RK-CFG Deployment POR20 - 2 | CA | SAN | DWN | Critical Facilities (Grow) | CFG CA SAN DWN RK-CFG Deployment POR20 - 2 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | Active | EP
CFG CA SAN DWN RK-CFG Deployment POR20 - 2 | CA | SAN | DWN | Critical Facilities (Grow) | CFG CA SAN DWN RK-CFG Deployment POR20 - 2 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | Active | Log | Undel | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG CE TUL BRD RK-CFG Deployment POR20 | CE | TUL | BRD | Critical Facilities (Grow) | CFG CE TUL BRD RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-20 |  | Active | EP
CFG CE TUL BRD RK-CFG Deployment POR20 | CE | TUL | BRD | Critical Facilities (Grow) | CFG CE TUL BRD RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-20 |  | Active | Log | Undel | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG NE CLE CLV FF-CFG Deployment POR20 | NE | CLE | CLV | Critical Facilities (Grow) | CFG NE CLE CLV FF-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-16 | 2020-03-20 |  | Active | EP
CFG NE CLE CLV FF-CFG Deployment POR20 | NE | CLE | CLV | Critical Facilities (Grow) | CFG NE CLE CLV FF-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-16 | 2020-03-20 |  | Active | Log | Undel | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG NE CLE CLV FF-CFG Deployment POR20 | NE | CLE | CLV | Critical Facilities (Grow) | CFG NE CLE CLV FF-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-20 |  | Active | Log | Upd | SN-0593 | Schedule Change | Canceled | 2020-06-22 11:08 | updating need by date for grown projects
CFG NE RHD RMD RK-CFG Deployment POR20 | NE | RHD | RMD | Critical Facilities (Grow) | CFG NE RHD RMD RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-16 | 2020-03-20 |  | Active | EP
CFG NE RHD RMD RK-CFG Deployment POR20 | NE | RHD | RMD | Critical Facilities (Grow) | CFG NE RHD RMD RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-16 | 2020-03-20 |  | Active | Log | Undel | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFG NE RHD RMD RK-CFG Deployment POR20 | NE | RHD | RMD | Critical Facilities (Grow) | CFG NE RHD RMD RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-20 |  | Active | Log | Upd | SN-0593 | Schedule Change | Canceled | 2020-06-22 11:08 | updating need by date for grown projects
CORP CFS VA HRD CHS FS-CFS Augment POR20 | VA | HRD | CHS | Critical Facilities Sustaining (Corp) | CORP CFS VA HRD CHS FS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CORP CFS VA HRD CHS FS-CFS Augment POR20 | VA | HRD | CHS | Critical Facilities Sustaining (Corp) |  | Labor | No Equipment | 1 |  | 2019-10-01 |  | Deleted | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CORP CFS VA HRD CHS FS-CFS Augment POR20 | VA | HRD | CHS | Critical Facilities Sustaining (Corp) | CORP CFS VA HRD CHS FS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0136 | Schedule Change | Approved | 2020-05-20 16:54 | Projects are no longer needed Removing them
CORP CFS VA HRD NRF FS-CFS Augment POR20 | VA | HRD | NRF | Critical Facilities Sustaining (Corp) | CORP CFS VA HRD NRF FS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CORP CFS VA HRD NRF FS-CFS Augment POR20 | VA | HRD | NRF | Critical Facilities Sustaining (Corp) |  | Labor | No Equipment | 1 |  | 2019-10-01 |  | Deleted | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CORP CFS VA HRD NRF FS-CFS Augment POR20 | VA | HRD | NRF | Critical Facilities Sustaining (Corp) | CORP CFS VA HRD NRF FS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0136 | Schedule Change | Approved | 2020-05-20 16:54 | Projects are no longer needed Removing them
CORP CFS VA HRD NWP FS-CFS Augment POR20 | VA | HRD | NWP | Critical Facilities Sustaining (Corp) | CORP CFS VA HRD NWP FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | Active | EP
CORP CFS VA HRD NWP FS-CFS Augment POR20 | VA | HRD | NWP | Critical Facilities Sustaining (Corp) |  | Labor | No Equipment | 1 |  | 2019-10-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CORP CFS VA HRD VBC FS-CFS Augment POR20 | VA | HRD | VBC | Critical Facilities Sustaining (Corp) | CORP CFS VA HRD VBC FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | Active | EP
CORP CFS VA HRD VBC FS-CFS Augment POR20 | VA | HRD | VBC | Critical Facilities Sustaining (Corp) |  | Labor | No Equipment | 1 |  | 2019-10-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CORP CFS VA NVA DRA FS-CFS Augment POR20 | VA | NVA | DRA | Critical Facilities Sustaining (Corp) | CORP CFS VA NVA DRA FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | Active | EP
CORP CFS VA NVA DRA FS-CFS Augment POR20 | VA | NVA | DRA | Critical Facilities Sustaining (Corp) |  | Labor | No Equipment | 1 |  | 2019-10-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CORP CFS VA NVA FLK FS-CFS Augment POR20 | VA | NVA | FLK | Critical Facilities Sustaining (Corp) | CORP CFS VA NVA FLK FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | Active | EP
CORP CFS VA NVA FLK FS-CFS Augment POR20 | VA | NVA | FLK | Critical Facilities Sustaining (Corp) |  | Labor | No Equipment | 1 |  | 2019-10-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CORP CFS VA NVA FST FS-CFS Augment POR20 | VA | NVA | FST | Critical Facilities Sustaining (Corp) | CORP CFS VA NVA FST FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | Active | EP
CORP CFS VA NVA FST FS-CFS Augment POR20 | VA | NVA | FST | Critical Facilities Sustaining (Corp) |  | Labor | No Equipment | 1 |  | 2019-10-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CORP CFS VA NVA GCR FS-CFS Augment POR20 | VA | NVA | GCR | Critical Facilities Sustaining (Corp) | CORP CFS VA NVA GCR FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | Active | EP
CORP CFS VA NVA GCR FS-CFS Augment POR20 | VA | NVA | GCR | Critical Facilities Sustaining (Corp) |  | Labor | No Equipment | 1 |  | 2019-10-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CORP CFS VA NVA MFD FS-CFS Augment POR20 | VA | NVA | MFD | Critical Facilities Sustaining (Corp) | CORP CFS VA NVA MFD FS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CORP CFS VA NVA MFD FS-CFS Augment POR20 | VA | NVA | MFD | Critical Facilities Sustaining (Corp) |  | Labor | No Equipment | 1 |  | 2019-10-01 |  | Deleted | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CORP CFS VA NVA MFD FS-CFS Augment POR20 | VA | NVA | MFD | Critical Facilities Sustaining (Corp) | CORP CFS VA NVA MFD FS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0136 | Schedule Change | Approved | 2020-05-20 16:54 | Projects are no longer needed Removing them
CORP CFS VA NVA RHL FS-CFS Augment POR20 | VA | NVA | RHL | Critical Facilities Sustaining (Corp) | CORP CFS VA NVA RHL FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | Active | EP
CORP CFS VA NVA RHL FS-CFS Augment POR20 | VA | NVA | RHL | Critical Facilities Sustaining (Corp) |  | Labor | No Equipment | 1 |  | 2019-10-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CORP CFS VA NVA TCR FS-CFS Augment POR20 | VA | NVA | TCR | Critical Facilities Sustaining (Corp) | CORP CFS VA NVA TCR FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | Active | EP
CORP CFS VA NVA TCR FS-CFS Augment POR20 | VA | NVA | TCR | Critical Facilities Sustaining (Corp) |  | Labor | No Equipment | 1 |  | 2019-10-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CORP CFS VA ROA RON FS-CFS Augment POR20 | VA | ROA | RON | Critical Facilities Sustaining (Corp) | CORP CFS VA ROA RON FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | Active | EP
CORP CFS VA ROA RON FS-CFS Augment POR20 | VA | ROA | RON | Critical Facilities Sustaining (Corp) |  | Labor | No Equipment | 1 |  | 2019-10-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CTA BM-CFS CF CONSTRUCTION PROJECT - MEDIUM | CA | ORG | CTA | Critical Facilities Sustaining (Field) | CFS CA ORG CTA BM-CFS Augment POR20 | Critical Facilities | CF CONSTRUCTION PROJECT - MEDIUM | 1 | 2020-01-15 | 2020-02-15 |  | Active | EP
CFS CTA BM-CFS CF CONSTRUCTION PROJECT - MEDIUM | CA | ORG | CTA | Critical Facilities Sustaining (Field) | CFS CA ORG CTA BM-CFS Augment POR20 | Critical Facilities | CF CONSTRUCTION PROJECT - MEDIUM | 1 | 2020-01-15 | 2020-02-15 |  | Active | Log | Upd | SB-0010 | Schedule Change | Approved | 2020-01-30 10:23 | Critical Facilities is Updating activity plan Christophe pointed out my dates were not coherent
CFS DNP HV-CFS BAU SUSTAIN PROJECT - LARGE | CA | ORG | DNP | Critical Facilities Sustaining (Field) | CFS CA ORG DNP HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS DNP HV-CFS BAU SUSTAIN PROJECT - LARGE | CA | ORG | DNP | Critical Facilities Sustaining (Field) | CFS CA ORG DNP HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS IRV HV-CFS BAU SUSTAIN PROJECT - MEDIUM | CA | ORG | IRV | Critical Facilities Sustaining (Field) | CFS CA ORG IRV HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS IRV HV-CFS BAU SUSTAIN PROJECT - MEDIUM | CA | ORG | IRV | Critical Facilities Sustaining (Field) | CFS CA ORG IRV HV-CFS Augment POR20 | Critical Facilities | BAU SUSTAIN PROJECT - MEDIUM | 1 | 2020-02-10 | 2020-04-15 |  | Deleted | Log | Upd | SB-0010 | Schedule Change | Approved | 2020-01-30 10:23 | Critical Facilities is Updating activity plan Christophe pointed out my dates were not coherent
CFS IRV HV-CFS BAU SUSTAIN PROJECT - MEDIUM | CA | ORG | IRV | Critical Facilities Sustaining (Field) | CFS CA ORG IRV HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS SAB BM BAU SUSTAIN PROJECT - MEDIUM | CA | SAB | SAB | Critical Facilities Sustaining (Field) | CFS CA SAB SAB BM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS SAB BM BAU SUSTAIN PROJECT - MEDIUM | CA | SAB | SAB | Critical Facilities Sustaining (Field) | CFS CA SAB SAB BM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS SAN BM-CFS BAU SUSTAIN PROJECT - SMALL | CA | SAN | DWN | Critical Facilities Sustaining (Field) | CFS CA SAN DWN BM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS SAN BM-CFS BAU SUSTAIN PROJECT - SMALL | CA | SAN | DWN | Critical Facilities Sustaining (Field) | CFS CA SAN DWN BM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS ELC AC-CFS BAU SUSTAIN PROJECT - LARGE | CA | SAN | ELC | Critical Facilities Sustaining (Field) | CFS CA SAN ELC AC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS ELC AC-CFS BAU SUSTAIN PROJECT - LARGE | CA | SAN | ELC | Critical Facilities Sustaining (Field) | CFS CA SAN ELC AC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS ESC BM-CFS BAU SUSTAIN PROJECT - SMALL | CA | SAN | ESC | Critical Facilities Sustaining (Field) | CFS CA SAN ESC BM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS ESC BM-CFS BAU SUSTAIN PROJECT - SMALL | CA | SAN | ESC | Critical Facilities Sustaining (Field) | CFS CA SAN ESC BM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS FED BM-CFS GEN SUSTAIN PROJECT - MEDIUM | CA | SAN | FED | Critical Facilities Sustaining (Field) | CFS CA SAN FED BM-CFS Augment POR20 - 2 | Critical Facilities | GEN SUSTAIN PROJECT - MEDIUM | 1 | 2020-04-01 | 2020-05-15 |  | Active | EP
CFS FED BM-CFS GEN SUSTAIN PROJECT - MEDIUM | CA | SAN | FED | Critical Facilities Sustaining (Field) |  | Critical Facilities | GEN SUSTAIN PROJECT - MEDIUM | 1 | 2020-04-01 | 2020-05-15 |  | Active | Log | Upd | SB-0010 | Schedule Change | Approved | 2020-01-30 10:23 | Critical Facilities is Updating activity plan Christophe pointed out my dates were not coherent
CFS OCN BM BAU SUSTAIN PROJECT - SMALL | CA | SAN | OCE | Critical Facilities Sustaining (Field) | CFS CA SAN OCE BM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS OCN BM BAU SUSTAIN PROJECT - SMALL | CA | SAN | OCE | Critical Facilities Sustaining (Field) | CFS CA SAN OCE BM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VST BM BAU SUSTAIN PROJECT - SMALL | CA | SAN | VST | Critical Facilities Sustaining (Field) | CFS CA SAN VST BM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS VST BM BAU SUSTAIN PROJECT - SMALL | CA | SAN | VST | Critical Facilities Sustaining (Field) | CFS CA SAN VST BM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VST BM-CFS BAU SUSTAIN PROJECT - SMALL | CA | SAN | VST | Critical Facilities Sustaining (Field) | CFS CA SAN VST BM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS VST BM-CFS BAU SUSTAIN PROJECT - SMALL | CA | SAN | VST | Critical Facilities Sustaining (Field) | CFS CA SAN VST BM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS BVL HVC BAU SUSTAIN PROJECT - MEDIUM | CE | NWA | BVL | Critical Facilities Sustaining (Field) | CFS CE NWA BVL HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS BVL HVC BAU SUSTAIN PROJECT - MEDIUM | CE | NWA | BVL | Critical Facilities Sustaining (Field) | CFS CE NWA BVL HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS BVL BDB BAU SUSTAIN PROJECT - MEDIUM | CE | NWA | BVL | Critical Facilities Sustaining (Field) | CFS CE NWA NWA BD-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS BVL BDB BAU SUSTAIN PROJECT - MEDIUM | CE | NWA | BVL | Critical Facilities Sustaining (Field) | CFS CE NWA NWA BD-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS FAY BDB BAU SUSTAIN PROJECT - SMALL | CE | NWA | FAY | Critical Facilities Sustaining (Field) | CFS CE NWA FAY BD-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS FAY BDB BAU SUSTAIN PROJECT - SMALL | CE | NWA | FAY | Critical Facilities Sustaining (Field) | CFS CE NWA FAY BD-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS NWA HVC BAU SUSTAIN PROJECT - MEDIUM | CE | NWA | NWA | Critical Facilities Sustaining (Field) | CFS CE NWA NWA HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS NWA HVC BAU SUSTAIN PROJECT - MEDIUM | CE | NWA | NWA | Critical Facilities Sustaining (Field) | CFS CE NWA NWA HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS TOP LGT BAU SUSTAIN PROJECT - MEDIUM | CE | KAN | TOP | Critical Facilities Sustaining (Field) | CFS CE KAN TOP FF-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS TOP LGT BAU SUSTAIN PROJECT - MEDIUM | CE | KAN | TOP | Critical Facilities Sustaining (Field) | CFS CE KAN TOP FF-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS BRD BAT BAU SUSTAIN PROJECT - MEDIUM | CE | TUL | BRD | Critical Facilities Sustaining (Field) | CFS CE TUL BRD BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS BRD BAT BAU SUSTAIN PROJECT - MEDIUM | CE | TUL | BRD | Critical Facilities Sustaining (Field) | CFS CE TUL BRD BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CHO BUP BAU SUSTAIN PROJECT - SMALL | CE | OKC | CHO | Critical Facilities Sustaining (Field) | CFS CE OKC CHO BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS CHO BUP BAU SUSTAIN PROJECT - SMALL | CE | OKC | CHO | Critical Facilities Sustaining (Field) | CFS CE OKC CHO BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CHO RAI BAU SUSTAIN PROJECT - MEDIUM | CE | OKC | CHO | Critical Facilities Sustaining (Field) | CFS CE OKC CHO RK-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS CHO RAI BAU SUSTAIN PROJECT - MEDIUM | CE | OKC | CHO | Critical Facilities Sustaining (Field) | CFS CE OKC CHO RK-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS DTN BAT BAU SUSTAIN PROJECT - MEDIUM | CE | TUL | DTN | Critical Facilities Sustaining (Field) | CFS CE TUL DTN BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS DTN BAT BAU SUSTAIN PROJECT - MEDIUM | CE | TUL | DTN | Critical Facilities Sustaining (Field) | CFS CE TUL DTN BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS OKC BDB BAU SUSTAIN PROJECT - MEDIUM | CE | OKC | OKC | Critical Facilities Sustaining (Field) | CFS CE OKC OKC BD-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS OKC BDB BAU SUSTAIN PROJECT - MEDIUM | CE | OKC | OKC | Critical Facilities Sustaining (Field) | CFS CE OKC OKC BD-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS OWA BDB BAU SUSTAIN PROJECT - MEDIUM | CE | TUL | OWA | Critical Facilities Sustaining (Field) | CFS CE TUL TUL BD-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS OWA BDB BAU SUSTAIN PROJECT - MEDIUM | CE | TUL | OWA | Critical Facilities Sustaining (Field) | CFS CE TUL TUL BD-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS SAP GEN BAU SUSTAIN PROJECT - MEDIUM | CE | TUL | SAP | Critical Facilities Sustaining (Field) | CFS CE TUL TUL GN-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS SAP GEN BAU SUSTAIN PROJECT - MEDIUM | CE | TUL | SAP | Critical Facilities Sustaining (Field) | CFS CE TUL TUL GN-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS TUL BAT BAU SUSTAIN PROJECT - MEDIUM | CE | TUL | TUL | Critical Facilities Sustaining (Field) | CFS CE TUL TUL BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS TUL BAT BAU SUSTAIN PROJECT - MEDIUM | CE | TUL | TUL | Critical Facilities Sustaining (Field) | CFS CE TUL TUL BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS BLV LGT BAU SUSTAIN PROJECT - MEDIUM | CE | OMA | BLV | Critical Facilities Sustaining (Field) | CFS CE OMA BLV FF-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS BLV LGT BAU SUSTAIN PROJECT - MEDIUM | CE | OMA | BLV | Critical Facilities Sustaining (Field) | CFS CE OMA BLV FF-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS ELK LGT BAU SUSTAIN PROJECT - MEDIUM | CE | OMA | ELK | Critical Facilities Sustaining (Field) | CFS CE OMA ELK FF-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS ELK LGT BAU SUSTAIN PROJECT - MEDIUM | CE | OMA | ELK | Critical Facilities Sustaining (Field) | CFS CE OMA ELK FF-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS OMM BDB BAU SUSTAIN PROJECT - MEDIUM | CE | OMA | OMM | Critical Facilities Sustaining (Field) | CFS CE OMA OMM BD-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS OMM BDB BAU SUSTAIN PROJECT - MEDIUM | CE | OMA | OMM | Critical Facilities Sustaining (Field) | CFS CE OMA OMM BD-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS OMM FIR BAU SUSTAIN PROJECT - MEDIUM | CE | OMA | OMM | Critical Facilities Sustaining (Field) | CFS CE OMA OMM FS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS OMM FIR BAU SUSTAIN PROJECT - MEDIUM | CE | OMA | OMM | Critical Facilities Sustaining (Field) | CFS CE OMA OMM FS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS ONA BUP BAU SUSTAIN PROJECT - SMALL | CE | OMA | ONA | Critical Facilities Sustaining (Field) | CFS CE OMA ONA BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS ONA BUP BAU SUSTAIN PROJECT - SMALL | CE | OMA | ONA | Critical Facilities Sustaining (Field) | CFS CE OMA ONA BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS SOU BUP BAU SUSTAIN PROJECT - SMALL | CE | OMA | SOU | Critical Facilities Sustaining (Field) | CFS CE OMA SOU BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS SOU BUP BAU SUSTAIN PROJECT - SMALL | CE | OMA | SOU | Critical Facilities Sustaining (Field) | CFS CE OMA SOU BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS SOU LGT BAU SUSTAIN PROJECT - MEDIUM | CE | OMA | SOU | Critical Facilities Sustaining (Field) | CFS CE OMA SOU FF-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS SOU LGT BAU SUSTAIN PROJECT - MEDIUM | CE | OMA | SOU | Critical Facilities Sustaining (Field) | CFS CE OMA SOU FF-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS WES BUP BAU SUSTAIN PROJECT - SMALL | CE | OMA | WES | Critical Facilities Sustaining (Field) | CFS CE OMA WES BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS WES BUP BAU SUSTAIN PROJECT - SMALL | CE | OMA | WES | Critical Facilities Sustaining (Field) | CFS CE OMA WES BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS ENF FIR BAU SUSTAIN PROJECT - SMALL | NE | CON | ENF | Critical Facilities Sustaining (Field) | CFS NE CON ENF FS-CFS Augment POR20 - 1 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS ENF FIR BAU SUSTAIN PROJECT - SMALL | NE | CON | ENF | Critical Facilities Sustaining (Field) | CFS NE CON ENF FS-CFS Augment POR20 - 1 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS GRB RC- BAU SUSTAIN PROJECT - MEDIUM | NE | CON | GRB | Critical Facilities Sustaining (Field) | CFS NE CON GRB RC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS GRB RC- BAU SUSTAIN PROJECT - MEDIUM | NE | CON | GRB | Critical Facilities Sustaining (Field) | CFS NE CON GRB RC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS MAN FIR BAU SUSTAIN PROJECT - SMALL | NE | CON | MAN | Critical Facilities Sustaining (Field) | CFS NE CON MAN FS-CFS Augment POR20 - 1 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS MAN FIR BAU SUSTAIN PROJECT - SMALL | NE | CON | MAN | Critical Facilities Sustaining (Field) | CFS NE CON MAN FS-CFS Augment POR20 - 1 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS MAN ACP BAU SUSTAIN PROJECT - MEDIUM | NE | CON | MAN | Critical Facilities Sustaining (Field) | CFS NE CON MAN AC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS MAN ACP BAU SUSTAIN PROJECT - MEDIUM | NE | CON | MAN | Critical Facilities Sustaining (Field) | CFS NE CON MAN AC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS MER FIR BAU SUSTAIN PROJECT - SMALL | NE | CON | MER | Critical Facilities Sustaining (Field) | CFS NE CON MER FS-CFS Augment POR20 - 1 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS MER FIR BAU SUSTAIN PROJECT - SMALL | NE | CON | MER | Critical Facilities Sustaining (Field) | CFS NE CON MER FS-CFS Augment POR20 - 1 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS RKH FIR BAU SUSTAIN PROJECT - SMALL | NE | CON | RKH | Critical Facilities Sustaining (Field) | CFS NE CON RKH FS-CFS Augment POR20 - 1 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS RKH FIR BAU SUSTAIN PROJECT - SMALL | NE | CON | RKH | Critical Facilities Sustaining (Field) | CFS NE CON RKH FS-CFS Augment POR20 - 1 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CRN FIR BAU SUSTAIN PROJECT - SMALL | NE | RHD | CRN | Critical Facilities Sustaining (Field) | CFS NE RHD CRN FS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS CRN FIR BAU SUSTAIN PROJECT - SMALL | NE | RHD | CRN | Critical Facilities Sustaining (Field) | CFS NE RHD CRN FS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CRN BAT BAU SUSTAIN PROJECT - MEDIUM | NE | RHD | CRN | Critical Facilities Sustaining (Field) | CFS NE RHD CRN BS-CFS Augment POR20 - 1 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS CRN BAT BAU SUSTAIN PROJECT - MEDIUM | NE | RHD | CRN | Critical Facilities Sustaining (Field) | CFS NE RHD CRN BS-CFS Augment POR20 - 1 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CRN BAT BAU SUSTAIN PROJECT - MEDIUM2 | NE | RHD | CRN | Critical Facilities Sustaining (Field) | CFS NE RHD CRN BS-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS CRN BAT BAU SUSTAIN PROJECT - MEDIUM2 | NE | RHD | CRN | Critical Facilities Sustaining (Field) | CFS NE RHD CRN BS-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS EXT RAI BAU SUSTAIN PROJECT - SMALL | NE | RHD | EXT | Critical Facilities Sustaining (Field) | CFS NE RHD EXT RK-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS EXT RAI BAU SUSTAIN PROJECT - SMALL | NE | RHD | EXT | Critical Facilities Sustaining (Field) | CFS NE RHD EXT RK-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS EXT FIR BAU SUSTAIN PROJECT - SMALL | NE | RHD | EXT | Critical Facilities Sustaining (Field) | CFS NE RHD EXT FS-CFS Augment POR20 - 1 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS EXT FIR BAU SUSTAIN PROJECT - SMALL | NE | RHD | EXT | Critical Facilities Sustaining (Field) | CFS NE RHD EXT FS-CFS Augment POR20 - 1 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS LNC FIR BAU SUSTAIN PROJECT - SMALL | NE | RHD | LNC | Critical Facilities Sustaining (Field) | CFS NE RHD LNC FS-CFS Augment POR20 - 1 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS LNC FIR BAU SUSTAIN PROJECT - SMALL | NE | RHD | LNC | Critical Facilities Sustaining (Field) | CFS NE RHD LNC FS-CFS Augment POR20 - 1 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PAW FIR BAU SUSTAIN PROJECT - SMALL | NE | RHD | PAW | Critical Facilities Sustaining (Field) | CFS NE RHD PAW FS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PAW FIR BAU SUSTAIN PROJECT - SMALL | NE | RHD | PAW | Critical Facilities Sustaining (Field) | CFS NE RHD PAW FS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PRV FIR BAU SUSTAIN PROJECT - SMALL | NE | RHD | PRV | Critical Facilities Sustaining (Field) | CFS NE RHD PRV FS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PRV FIR BAU SUSTAIN PROJECT - SMALL | NE | RHD | PRV | Critical Facilities Sustaining (Field) | CFS NE RHD PRV FS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PTH FIR BAU SUSTAIN PROJECT - SMALL | NE | RHD | PTH | Critical Facilities Sustaining (Field) | CFS NE RHD PTH FS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PTH FIR BAU SUSTAIN PROJECT - SMALL | NE | RHD | PTH | Critical Facilities Sustaining (Field) | CFS NE RHD PTH FS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS RMD FIR BAU SUSTAIN PROJECT - SMALL | NE | RHD | RMD | Critical Facilities Sustaining (Field) | CFS NE RHD RMD FS-CFS Augment POR20 - 1 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS RMD FIR BAU SUSTAIN PROJECT - SMALL | NE | RHD | RMD | Critical Facilities Sustaining (Field) | CFS NE RHD RMD FS-CFS Augment POR20 - 1 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS WWK FIR BAU SUSTAIN PROJECT - SMALL | NE | RHD | WWK | Critical Facilities Sustaining (Field) | CFS NE RHD WWK FS-CFS Augment POR20 - 1 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS WWK FIR BAU SUSTAIN PROJECT - SMALL | NE | RHD | WWK | Critical Facilities Sustaining (Field) | CFS NE RHD WWK FS-CFS Augment POR20 - 1 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS NCV BAT BAU SUSTAIN PROJECT - SMALL | SE | GCT | NCV | Critical Facilities Sustaining (Field) | CFS SE GCT NCV BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS NCV BAT BAU SUSTAIN PROJECT - SMALL | SE | GCT | NCV | Critical Facilities Sustaining (Field) | CFS SE GCT NCV BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS ALG HVC BAU SUSTAIN PROJECT - MEDIUM | SE | NOR | ALG | Critical Facilities Sustaining (Field) | CFS SE NOR ALG HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS ALG HVC BAU SUSTAIN PROJECT - MEDIUM | SE | NOR | ALG | Critical Facilities Sustaining (Field) | CFS SE NOR ALG HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS DVL BU BAU SUSTAIN PROJECT - SMALL | SE | BTR | DVL | Critical Facilities Sustaining (Field) | CFS SE BTR BTR BU-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS DVL BU BAU SUSTAIN PROJECT - SMALL | SE | BTR | DVL | Critical Facilities Sustaining (Field) | CFS SE BTR BTR BU-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS DVL HVC BAU SUSTAIN PROJECT - MEDIUM | SE | BTR | DVL | Critical Facilities Sustaining (Field) | CFS SE BTR BTR HV-CFS Augment POR20 | Critical Facilities | BAU SUSTAIN PROJECT - MEDIUM |  |  |  |  | Deleted | EP
CFS DVL HVC BAU SUSTAIN PROJECT - MEDIUM | SE | BTR | DVL | Critical Facilities Sustaining (Field) | CFS SE BTR BTR HV-CFS Augment POR20 | Critical Facilities | BAU SUSTAIN PROJECT - MEDIUM |  |  |  |  | Deleted | Log | Del | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS ERW BU BAU SUSTAIN PROJECT - SMALL | SE | BTR | ERW | Critical Facilities Sustaining (Field) | CFS SE BTR ERW BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS ERW BU BAU SUSTAIN PROJECT - SMALL | SE | BTR | ERW | Critical Facilities Sustaining (Field) | CFS SE BTR ERW BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS ERW HVC BAU SUSTAIN PROJECT - MEDIUM | SE | BTR | ERW | Critical Facilities Sustaining (Field) | CFS SE BTR ERW HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS ERW HVC BAU SUSTAIN PROJECT - MEDIUM | SE | BTR | ERW | Critical Facilities Sustaining (Field) | CFS SE BTR ERW HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS LFY RF BAU SUSTAIN PROJECT - LARGE | SE | LFY | LFY | Critical Facilities Sustaining (Field) | CFS SE LFY LFY RF-CFS Augment POR20 - 1 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS LFY RF BAU SUSTAIN PROJECT - LARGE | SE | LFY | LFY | Critical Facilities Sustaining (Field) | CFS SE LFY LFY RF-CFS Augment POR20 - 1 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS LFY RF BAU SUSTAIN PROJECT - MEDIUM | SE | LFY | LFY | Critical Facilities Sustaining (Field) | CFS SE LFY LFY RF-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS LFY RF BAU SUSTAIN PROJECT - MEDIUM | SE | LFY | LFY | Critical Facilities Sustaining (Field) | CFS SE LFY LFY RF-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS NTH BU BAU SUSTAIN PROJECT - SMALL | SE | BTR | NTH | Critical Facilities Sustaining (Field) | CFS SE BTR NTH BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS NTH BU BAU SUSTAIN PROJECT - SMALL | SE | BTR | NTH | Critical Facilities Sustaining (Field) | CFS SE BTR NTH BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS NTH HVC BAU SUSTAIN PROJECT - MEDIUM | SE | BTR | NTH | Critical Facilities Sustaining (Field) | CFS SE BTR BTR HV-CFS Augment POR20 - 1 | Critical Facilities | BAU SUSTAIN PROJECT - MEDIUM |  |  |  |  | Deleted | EP
CFS NTH HVC BAU SUSTAIN PROJECT - MEDIUM | SE | BTR | NTH | Critical Facilities Sustaining (Field) | CFS SE BTR BTR HV-CFS Augment POR20 - 1 | Critical Facilities | BAU SUSTAIN PROJECT - MEDIUM |  |  |  |  | Deleted | Log | Del | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS NTH HVC BAU SUSTAIN PROJECT - MEDIUM2 | SE | BTR | NTH | Critical Facilities Sustaining (Field) | CFS SE BTR BTR HV-CFS Augment POR20 - 2 | Critical Facilities | BAU SUSTAIN PROJECT - MEDIUM |  |  |  |  | Deleted | EP
CFS NTH HVC BAU SUSTAIN PROJECT - MEDIUM2 | SE | BTR | NTH | Critical Facilities Sustaining (Field) | CFS SE BTR BTR HV-CFS Augment POR20 - 2 | Critical Facilities | BAU SUSTAIN PROJECT - MEDIUM |  |  |  |  | Deleted | Log | Del | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS STC BU BAU SUSTAIN PROJECT - SMALL | SE | BTR | STC | Critical Facilities Sustaining (Field) | CFS SE BTR STC BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS STC BU BAU SUSTAIN PROJECT - SMALL | SE | BTR | STC | Critical Facilities Sustaining (Field) | CFS SE BTR STC BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS BEL SEC BAU SUSTAIN PROJECT - SMALL | SW | ARZ | BEL | Critical Facilities Sustaining (Field) | CFS SW ARZ BEL SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS BEL SEC BAU SUSTAIN PROJECT - SMALL | SW | ARZ | BEL | Critical Facilities Sustaining (Field) | CFS SW ARZ BEL SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS BEL HVC BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | BEL | Critical Facilities Sustaining (Field) | CFS SW ARZ BEL HV-CFS Augment POR20 - 1 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS BEL HVC BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | BEL | Critical Facilities Sustaining (Field) | CFS SW ARZ BEL HV-CFS Augment POR20 - 1 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS BUK SEC BAU SUSTAIN PROJECT - SMALL | SW | ARZ | BUK | Critical Facilities Sustaining (Field) | CFS SW ARZ BUK SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS BUK SEC BAU SUSTAIN PROJECT - SMALL | SW | ARZ | BUK | Critical Facilities Sustaining (Field) | CFS SW ARZ BUK SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS BUK HVC BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | BUK | Critical Facilities Sustaining (Field) | CFS SW ARZ BUK HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS BUK HVC BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | BUK | Critical Facilities Sustaining (Field) | CFS SW ARZ BUK HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CHD SEC BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | CHD | Critical Facilities Sustaining (Field) | CFS SW ARZ CHD SC-CFS Augment POR20 - 1 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS CHD SEC BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | CHD | Critical Facilities Sustaining (Field) | CFS SW ARZ CHD SC-CFS Augment POR20 - 1 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CHD HVC BAU SUSTAIN PROJECT - LARGE | SW | ARZ | CHD | Critical Facilities Sustaining (Field) | CFS SW ARZ CHD HV-CFS Augment POR20 - 1 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS CHD HVC BAU SUSTAIN PROJECT - LARGE | SW | ARZ | CHD | Critical Facilities Sustaining (Field) | CFS SW ARZ CHD HV-CFS Augment POR20 - 1 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CHD HVC BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | CHD | Critical Facilities Sustaining (Field) | CFS SW ARZ CHD HV-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS CHD HVC BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | CHD | Critical Facilities Sustaining (Field) | CFS SW ARZ CHD HV-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CHD SEC BAU SUSTAIN PROJECT - MEDIUM2 | SW | ARZ | CHD | Critical Facilities Sustaining (Field) | CFS SW ARZ CHD DC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS CHD SEC BAU SUSTAIN PROJECT - MEDIUM2 | SW | ARZ | CHD | Critical Facilities Sustaining (Field) | CFS SW ARZ CHD DC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CSG SEC BAU SUSTAIN PROJECT - SMALL | SW | ARZ | CSG | Critical Facilities Sustaining (Field) | CFS SW ARZ CSG SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS CSG SEC BAU SUSTAIN PROJECT - SMALL | SW | ARZ | CSG | Critical Facilities Sustaining (Field) | CFS SW ARZ CSG SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS DGL SEC BAU SUSTAIN PROJECT - SMALL | SW | ARZ | DGL | Critical Facilities Sustaining (Field) | CFS SW ARZ DGL SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS DGL SEC BAU SUSTAIN PROJECT - SMALL | SW | ARZ | DGL | Critical Facilities Sustaining (Field) | CFS SW ARZ DGL SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS MSA HVC BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | MSA | Critical Facilities Sustaining (Field) | CFS SW ARZ MSA HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS MSA HVC BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | MSA | Critical Facilities Sustaining (Field) | CFS SW ARZ MSA HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS MSA SEC BAU SUSTAIN PROJECT - SMALL | SW | ARZ | MSA | Critical Facilities Sustaining (Field) | CFS SW ARZ MSA SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS MSA SEC BAU SUSTAIN PROJECT - SMALL | SW | ARZ | MSA | Critical Facilities Sustaining (Field) | CFS SW ARZ MSA SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS NSC HVC BAU SUSTAIN PROJECT - LARGE | SW | ARZ | NSC | Critical Facilities Sustaining (Field) | CFS SW ARZ NSC HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS NSC HVC BAU SUSTAIN PROJECT - LARGE | SW | ARZ | NSC | Critical Facilities Sustaining (Field) | CFS SW ARZ NSC HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PNL HVC BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | PNL | Critical Facilities Sustaining (Field) | CFS SW ARZ PNL HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PNL HVC BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | PNL | Critical Facilities Sustaining (Field) | CFS SW ARZ PNL HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS SSC HVC BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | SSC | Critical Facilities Sustaining (Field) | CFS SW ARZ SSC HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS SSC HVC BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | SSC | Critical Facilities Sustaining (Field) | CFS SW ARZ SSC HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VSA SEC BAU SUSTAIN PROJECT - SMALL | SW | ARZ | VSA | Critical Facilities Sustaining (Field) | CFS SW ARZ VSA SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS VSA SEC BAU SUSTAIN PROJECT - SMALL | SW | ARZ | VSA | Critical Facilities Sustaining (Field) | CFS SW ARZ VSA SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS WKB SEC BAU SUSTAIN PROJECT - SMALL | SW | ARZ | WCG | Critical Facilities Sustaining (Field) | CFS SW ARZ WCG SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS WKB SEC BAU SUSTAIN PROJECT - SMALL | SW | ARZ | WCG | Critical Facilities Sustaining (Field) | CFS SW ARZ WCG SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS HEN SEC BAU SUSTAIN PROJECT - MEDIUM | SW | LAS | HEN | Critical Facilities Sustaining (Field) | CFS SW LAS HEN SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS HEN SEC BAU SUSTAIN PROJECT - MEDIUM | SW | LAS | HEN | Critical Facilities Sustaining (Field) | CFS SW LAS HEN SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CYP BL- BAU SUSTAIN PROJECT - SMALL | VA | HRD | CYP | Critical Facilities Sustaining (Field) | CFS VA HRD CYP BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS CYP BL- BAU SUSTAIN PROJECT - SMALL | VA | HRD | CYP | Critical Facilities Sustaining (Field) | CFS VA HRD CYP BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS JEF BS- BAU SUSTAIN PROJECT - MEDIUM | VA | HRD | JEF | Critical Facilities Sustaining (Field) | CFS VA HRD JEF BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS JEF BS- BAU SUSTAIN PROJECT - MEDIUM | VA | HRD | JEF | Critical Facilities Sustaining (Field) | CFS VA HRD JEF BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS JEF RC- BAU SUSTAIN PROJECT - SMALL | VA | HRD | JEF | Critical Facilities Sustaining (Field) | CFS VA HRD JEF RC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS JEF RC- BAU SUSTAIN PROJECT - SMALL | VA | HRD | JEF | Critical Facilities Sustaining (Field) | CFS VA HRD JEF RC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS NFR BL- BAU SUSTAIN PROJECT - MEDIUM | VA | HRD | NRF | Critical Facilities Sustaining (Field) | CFS VA HRD NRF BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS NFR BL- BAU SUSTAIN PROJECT - MEDIUM | VA | HRD | NRF | Critical Facilities Sustaining (Field) | CFS VA HRD NRF BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS NFR DC- BAU SUSTAIN PROJECT - LARGE | VA | HRD | NRF | Critical Facilities Sustaining (Field) | CFS VA HRD NRF DC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS NFR DC- BAU SUSTAIN PROJECT - LARGE | VA | HRD | NRF | Critical Facilities Sustaining (Field) | CFS VA HRD NRF DC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PRA GEN BAU SUSTAIN PROJECT - LARGE | VA | HRD | PRA | Critical Facilities Sustaining (Field) | CFS VA HRD PRA GN-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PRA GEN BAU SUSTAIN PROJECT - LARGE | VA | HRD | PRA | Critical Facilities Sustaining (Field) | CFS VA HRD PRA GN-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS DRA BL- BAU SUSTAIN PROJECT - SMALL | VA | NVA | DRA | Critical Facilities Sustaining (Field) | CFS VA NVA DRA BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS DRA BL- BAU SUSTAIN PROJECT - SMALL | VA | NVA | DRA | Critical Facilities Sustaining (Field) | CFS VA NVA DRA BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS FLK BL- BAU SUSTAIN PROJECT - SMALL | VA | NVA | FLK | Critical Facilities Sustaining (Field) | CFS VA NVA FLK BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS FLK BL- BAU SUSTAIN PROJECT - SMALL | VA | NVA | FLK | Critical Facilities Sustaining (Field) | CFS VA NVA FLK BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS MFD BL- BAU SUSTAIN PROJECT - MEDIUM | VA | NVA | MFD | Critical Facilities Sustaining (Field) | CFS VA NVA MFD BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS MFD BL- BAU SUSTAIN PROJECT - MEDIUM | VA | NVA | MFD | Critical Facilities Sustaining (Field) | CFS VA NVA MFD BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS TCR BL- BAU SUSTAIN PROJECT - SMALL | VA | NVA | TCR | Critical Facilities Sustaining (Field) | CFS VA NVA TCR BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS TCR BL- BAU SUSTAIN PROJECT - SMALL | VA | NVA | TCR | Critical Facilities Sustaining (Field) | CFS VA NVA TCR BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CRW BAT BAU SUSTAIN PROJECT - MEDIUM | SE | LFY | CRW | Critical Facilities Sustaining (Field) | CFS SE LFY LFY BS-CFS Augment POR20 | Critical Facilities | BAU SUSTAIN PROJECT - MEDIUM |  |  |  |  | Deleted | EP
CFS CRW BAT BAU SUSTAIN PROJECT - MEDIUM | SE | LFY | CRW | Critical Facilities Sustaining (Field) | CFS SE LFY LFY BS-CFS Augment POR20 | Critical Facilities | BAU SUSTAIN PROJECT - MEDIUM |  |  |  |  | Deleted | Log | Del | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS DNS BU BAU SUSTAIN PROJECT - SMALL | SE | BTR | DNS | Critical Facilities Sustaining (Field) | CFS SE BTR BTR BU-CFS Augment POR20 - 1 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS DNS BU BAU SUSTAIN PROJECT - SMALL | SE | BTR | DNS | Critical Facilities Sustaining (Field) | CFS SE BTR BTR BU-CFS Augment POR20 - 1 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CHD DCB BAU SUSTAIN PROJECT - LARGE | SW | ARZ | CHD | Critical Facilities Sustaining (Field) | CFS SW ARZ CHD DC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS CHD DCB BAU SUSTAIN PROJECT - LARGE | SW | ARZ | CHD | Critical Facilities Sustaining (Field) | CFS SW ARZ CHD DC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS FWL SEC BAU SUSTAIN PROJECT - SMALL | SW | ARZ | FWL | Critical Facilities Sustaining (Field) | CFS SW ARZ FWL SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS FWL SEC BAU SUSTAIN PROJECT - SMALL | SW | ARZ | FWL | Critical Facilities Sustaining (Field) | CFS SW ARZ FWL SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS GVA SEC BAU SUSTAIN PROJECT - SMALL | SW | ARZ | GVA | Critical Facilities Sustaining (Field) | CFS SW ARZ GVA SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS GVA SEC BAU SUSTAIN PROJECT - SMALL | SW | ARZ | GVA | Critical Facilities Sustaining (Field) | CFS SW ARZ GVA SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS MCD SEC BAU SUSTAIN PROJECT - SMALL | SW | ARZ | MCD | Critical Facilities Sustaining (Field) | CFS SW ARZ MCD SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS MCD SEC BAU SUSTAIN PROJECT - SMALL | SW | ARZ | MCD | Critical Facilities Sustaining (Field) | CFS SW ARZ MCD SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS MCD HVC BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | MCD | Critical Facilities Sustaining (Field) | CFS SW ARZ MCD HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS MCD HVC BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | MCD | Critical Facilities Sustaining (Field) | CFS SW ARZ MCD HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PEO HVC BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | PEO | Critical Facilities Sustaining (Field) | CFS SW ARZ PEO HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PEO HVC BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | PEO | Critical Facilities Sustaining (Field) | CFS SW ARZ PEO HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS JEF HV- BAU SUSTAIN PROJECT - MEDIUM | VA | HRD | JEF | Critical Facilities Sustaining (Field) | CFS VA HRD JEF HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS JEF HV- BAU SUSTAIN PROJECT - MEDIUM | VA | HRD | JEF | Critical Facilities Sustaining (Field) | CFS VA HRD JEF HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS OCN HV- BAU SUSTAIN PROJECT - MEDIUM | VA | HRD | OCN | Critical Facilities Sustaining (Field) | CFS VA HRD OCN HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS OCN HV- BAU SUSTAIN PROJECT - MEDIUM | VA | HRD | OCN | Critical Facilities Sustaining (Field) | CFS VA HRD OCN HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS RNK BS- BAU SUSTAIN PROJECT - LARGE | VA | ROA | RON | Critical Facilities Sustaining (Field) | CFS VA ROA RON BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS RNK BS- BAU SUSTAIN PROJECT - LARGE | VA | ROA | RON | Critical Facilities Sustaining (Field) | CFS VA ROA RON BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS LFY BDB BAU SUSTAIN PROJECT - LARGE | SE | LFY | LFY | Critical Facilities Sustaining (Field) | CFS SE LFY LFY BD-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS LFY BDB BAU SUSTAIN PROJECT - LARGE | SE | LFY | LFY | Critical Facilities Sustaining (Field) | CFS SE LFY LFY BD-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS LUL INV BAU SUSTAIN PROJECT - MEDIUM | SE | NOR | LUL | Critical Facilities Sustaining (Field) | CFS SE NOR LUL IV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS LUL INV BAU SUSTAIN PROJECT - MEDIUM | SE | NOR | LUL | Critical Facilities Sustaining (Field) | CFS SE NOR LUL IV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS SPC BAT BAU SUSTAIN PROJECT - MEDIUM | SE | BTR | SPC | Critical Facilities Sustaining (Field) | CFS SE BTR BTR BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS SPC BAT BAU SUSTAIN PROJECT - MEDIUM | SE | BTR | SPC | Critical Facilities Sustaining (Field) | CFS SE BTR BTR BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CRV BAT BAU SUSTAIN PROJECT - SMALL | SE | GCT | CRV | Critical Facilities Sustaining (Field) | CFS SE GCT CRV BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS CRV BAT BAU SUSTAIN PROJECT - SMALL | SE | GCT | CRV | Critical Facilities Sustaining (Field) | CFS SE GCT CRV BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PNS BAT BAU SUSTAIN PROJECT - MEDIUM | SE | GCT | PNS | Critical Facilities Sustaining (Field) | CFS SE GCT PNS BS-CFS Augment POR20 | Critical Facilities | BAU SUSTAIN PROJECT - MEDIUM |  |  |  |  | Deleted | EP
CFS PNS BAT BAU SUSTAIN PROJECT - MEDIUM | SE | GCT | PNS | Critical Facilities Sustaining (Field) | CFS SE GCT PNS BS-CFS Augment POR20 | Critical Facilities | BAU SUSTAIN PROJECT - MEDIUM |  |  |  |  | Deleted | Log | Del | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS BUK LMI BAU SUSTAIN PROJECT - LARGE | SW | ARZ | BUK | Critical Facilities Sustaining (Field) | CFS SW ARZ BUK LM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS BUK LMI BAU SUSTAIN PROJECT - LARGE | SW | ARZ | BUK | Critical Facilities Sustaining (Field) | CFS SW ARZ BUK LM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS WCG HVC BAU SUSTAIN PROJECT - SMALL | SW | ARZ | WCG | Critical Facilities Sustaining (Field) | CFS SW ARZ WCG HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS WCG HVC BAU SUSTAIN PROJECT - SMALL | SW | ARZ | WCG | Critical Facilities Sustaining (Field) | CFS SW ARZ WCG HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS BOC HVC BAU SUSTAIN PROJECT - SMALL | SW | LAS | BOC | Critical Facilities Sustaining (Field) | CFS SW LAS BOC HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS BOC HVC BAU SUSTAIN PROJECT - SMALL | SW | LAS | BOC | Critical Facilities Sustaining (Field) | CFS SW LAS BOC HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS DCY BUP BAU SUSTAIN PROJECT - SMALL | CE | KAN | DCY | Critical Facilities Sustaining (Field) | CFS CE KAN DCY BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS DCY BUP BAU SUSTAIN PROJECT - SMALL | CE | KAN | DCY | Critical Facilities Sustaining (Field) | CFS CE KAN DCY BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS GDY HVC BAU SUSTAIN PROJECT - MEDIUM | CE | KAN | GDY | Critical Facilities Sustaining (Field) | CFS CE KAN GDY HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS GDY HVC BAU SUSTAIN PROJECT - MEDIUM | CE | KAN | GDY | Critical Facilities Sustaining (Field) | CFS CE KAN GDY HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CHU HV BAU SUSTAIN PROJECT - MEDIUM | CA | SAN | CHU | Critical Facilities Sustaining (Field) | CFS CA SAN CHU HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS CHU HV BAU SUSTAIN PROJECT - MEDIUM | CA | SAN | CHU | Critical Facilities Sustaining (Field) | CFS CA SAN CHU HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CHU HV-CFS GEN SUSTAIN PROJECT - MEDIUM | CA | SAN | CHU | Critical Facilities Sustaining (Field) | CFS CA SAN CHU HV-CFS Augment POR20 | Critical Facilities | GEN SUSTAIN PROJECT - MEDIUM | 1 | 2020-02-01 | 2020-08-15 |  | Active | EP
CFS GAR SEC BAU SUSTAIN PROJECT - SMALL | CE | TUL | GAR | Critical Facilities Sustaining (Field) | CFS CE TUL TUL SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS GAR SEC BAU SUSTAIN PROJECT - SMALL | CE | TUL | GAR | Critical Facilities Sustaining (Field) | CFS CE TUL TUL SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS MOO BUP BAU SUSTAIN PROJECT - SMALL | CE | OKC | MOO | Critical Facilities Sustaining (Field) | CFS CE OKC MOO BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS MOO BUP BAU SUSTAIN PROJECT - SMALL | CE | OKC | MOO | Critical Facilities Sustaining (Field) | CFS CE OKC MOO BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS MOO HVC BAU SUSTAIN PROJECT - MEDIUM | CE | OKC | MOO | Critical Facilities Sustaining (Field) | CFS CE OKC MOO HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS MOO HVC BAU SUSTAIN PROJECT - MEDIUM | CE | OKC | MOO | Critical Facilities Sustaining (Field) | CFS CE OKC MOO HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS NEH GEN BAU SUSTAIN PROJECT - MEDIUM | CE | OKC | NEH | Critical Facilities Sustaining (Field) | CFS CE OKC NEH GN-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS NEH GEN BAU SUSTAIN PROJECT - MEDIUM | CE | OKC | NEH | Critical Facilities Sustaining (Field) | CFS CE OKC NEH GN-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS OKC HVC BAU SUSTAIN PROJECT - MEDIUM | CE | OKC | OKC | Critical Facilities Sustaining (Field) | CFS CE OKC OKC HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS OKC HVC BAU SUSTAIN PROJECT - MEDIUM | CE | OKC | OKC | Critical Facilities Sustaining (Field) | CFS CE OKC OKC HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS QNC BDB BAU SUSTAIN PROJECT - MEDIUM | CE | TUL | QNC | Critical Facilities Sustaining (Field) | CFS CE TUL QNC BD-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS QNC BDB BAU SUSTAIN PROJECT - MEDIUM | CE | TUL | QNC | Critical Facilities Sustaining (Field) | CFS CE TUL QNC BD-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS MAN FIR BAU SUSTAIN PROJECT - SMALL2 | NE | CON | MAN | Critical Facilities Sustaining (Field) | CFS NE CON MAN FS-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS MAN FIR BAU SUSTAIN PROJECT - SMALL2 | NE | CON | MAN | Critical Facilities Sustaining (Field) | CFS NE CON MAN FS-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS MER BU- BAU SUSTAIN PROJECT - MEDIUM | NE | CON | MER | Critical Facilities Sustaining (Field) | CFS NE CON MER BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS MER BU- BAU SUSTAIN PROJECT - MEDIUM | NE | CON | MER | Critical Facilities Sustaining (Field) | CFS NE CON MER BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS MER FIR BAU SUSTAIN PROJECT - SMALL2 | NE | CON | MER | Critical Facilities Sustaining (Field) | CFS NE CON MER FS-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS MER FIR BAU SUSTAIN PROJECT - SMALL2 | NE | CON | MER | Critical Facilities Sustaining (Field) | CFS NE CON MER FS-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS RKH FIR BAU SUSTAIN PROJECT - SMALL2 | NE | CON | RKH | Critical Facilities Sustaining (Field) | CFS NE CON RKH FS-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS RKH FIR BAU SUSTAIN PROJECT - SMALL2 | NE | CON | RKH | Critical Facilities Sustaining (Field) | CFS NE CON RKH FS-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS STN FIR BAU SUSTAIN PROJECT - SMALL | NE | CON | STN | Critical Facilities Sustaining (Field) | CFS NE CON STN FS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS STN FIR BAU SUSTAIN PROJECT - SMALL | NE | CON | STN | Critical Facilities Sustaining (Field) | CFS NE CON STN FS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS SFD FIR BAU SUSTAIN PROJECT - SMALL | NE | CON | SFD | Critical Facilities Sustaining (Field) | CFS NE CON SFD FS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS SFD FIR BAU SUSTAIN PROJECT - SMALL | NE | CON | SFD | Critical Facilities Sustaining (Field) | CFS NE CON SFD FS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS BUR FIR BAU SUSTAIN PROJECT - SMALL | NE | RHD | BUR | Critical Facilities Sustaining (Field) | CFS NE RHD BUR FS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS BUR FIR BAU SUSTAIN PROJECT - SMALL | NE | RHD | BUR | Critical Facilities Sustaining (Field) | CFS NE RHD BUR FS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS EXT FIR BAU SUSTAIN PROJECT - SMALL2 | NE | RHD | EXT | Critical Facilities Sustaining (Field) | CFS NE RHD EXT FS-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS EXT FIR BAU SUSTAIN PROJECT - SMALL2 | NE | RHD | EXT | Critical Facilities Sustaining (Field) | CFS NE RHD EXT FS-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS LNC FIR BAU SUSTAIN PROJECT - SMALL2 | NE | RHD | LNC | Critical Facilities Sustaining (Field) | CFS NE RHD LNC FS-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS LNC FIR BAU SUSTAIN PROJECT - SMALL2 | NE | RHD | LNC | Critical Facilities Sustaining (Field) | CFS NE RHD LNC FS-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PAW LMI BAU SUSTAIN PROJECT - SMALL | NE | RHD | PAW | Critical Facilities Sustaining (Field) | CFS NE RHD PAW LM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PAW LMI BAU SUSTAIN PROJECT - SMALL | NE | RHD | PAW | Critical Facilities Sustaining (Field) | CFS NE RHD PAW LM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PRV LMI BAU SUSTAIN PROJECT - SMALL | NE | RHD | PRV | Critical Facilities Sustaining (Field) | CFS NE RHD PRV LM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PRV LMI BAU SUSTAIN PROJECT - SMALL | NE | RHD | PRV | Critical Facilities Sustaining (Field) | CFS NE RHD PRV LM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS RMD FIR BAU SUSTAIN PROJECT - SMALL2 | NE | RHD | RMD | Critical Facilities Sustaining (Field) | CFS NE RHD RMD FS-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS RMD FIR BAU SUSTAIN PROJECT - SMALL2 | NE | RHD | RMD | Critical Facilities Sustaining (Field) | CFS NE RHD RMD FS-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS WWK LMI BAU SUSTAIN PROJECT - SMALL | NE | RHD | WWK | Critical Facilities Sustaining (Field) | CFS NE RHD WWK LM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS WWK LMI BAU SUSTAIN PROJECT - SMALL | NE | RHD | WWK | Critical Facilities Sustaining (Field) | CFS NE RHD WWK LM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS WWK FIR BAU SUSTAIN PROJECT - SMALL2 | NE | RHD | WWK | Critical Facilities Sustaining (Field) | CFS NE RHD WWK FS-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS WWK FIR BAU SUSTAIN PROJECT - SMALL2 | NE | RHD | WWK | Critical Facilities Sustaining (Field) | CFS NE RHD WWK FS-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS BTR BDB BAU SUSTAIN PROJECT - LARGE | SE | BTR | BTR | Critical Facilities Sustaining (Field) | CFS SE BTR BTR BD-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS BTR BDB BAU SUSTAIN PROJECT - LARGE | SE | BTR | BTR | Critical Facilities Sustaining (Field) | CFS SE BTR BTR BD-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CBL LGT BAU SUSTAIN PROJECT - MEDIUM | CE | OMA | CBL | Critical Facilities Sustaining (Field) | CFS CE OMA CBL FF-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS CBL LGT BAU SUSTAIN PROJECT - MEDIUM | CE | OMA | CBL | Critical Facilities Sustaining (Field) | CFS CE OMA CBL FF-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS ONA BDB BAU SUSTAIN PROJECT - MEDIUM | CE | OMA | ONA | Critical Facilities Sustaining (Field) | CFS CE OMA ONA BD-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS ONA BDB BAU SUSTAIN PROJECT - MEDIUM | CE | OMA | ONA | Critical Facilities Sustaining (Field) | CFS CE OMA ONA BD-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS SOU HVC BAU SUSTAIN PROJECT - MEDIUM | CE | OMA | SOU | Critical Facilities Sustaining (Field) | CFS CE OMA SOU HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS SOU HVC BAU SUSTAIN PROJECT - MEDIUM | CE | OMA | SOU | Critical Facilities Sustaining (Field) | CFS CE OMA SOU HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS ENF FIR BAU SUSTAIN PROJECT - SMALL2 | NE | CON | ENF | Critical Facilities Sustaining (Field) | CFS NE CON ENF FS-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS ENF FIR BAU SUSTAIN PROJECT - SMALL2 | NE | CON | ENF | Critical Facilities Sustaining (Field) | CFS NE CON ENF FS-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS GRB FIR BAU SUSTAIN PROJECT - SMALL | NE | CON | GRB | Critical Facilities Sustaining (Field) | CFS NE CON GRB FS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS GRB FIR BAU SUSTAIN PROJECT - SMALL | NE | CON | GRB | Critical Facilities Sustaining (Field) | CFS NE CON GRB FS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS HLT HVC BAU SUSTAIN PROJECT - MEDIUM | SE | MGA | HLT | Critical Facilities Sustaining (Field) | CFS SE MGA HLT HV-CFS Augment POR20 - 1 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS HLT HVC BAU SUSTAIN PROJECT - MEDIUM | SE | MGA | HLT | Critical Facilities Sustaining (Field) | CFS SE MGA HLT HV-CFS Augment POR20 - 1 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS FWL HVC BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | FWL | Critical Facilities Sustaining (Field) | CFS SW ARZ FWL HV-CFS Augment POR20 - 1 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS FWL HVC BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | FWL | Critical Facilities Sustaining (Field) | CFS SW ARZ FWL HV-CFS Augment POR20 - 1 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS HLT HVC BAU SUSTAIN PROJECT - MEDIUM2 | SE | MGA | HLT | Critical Facilities Sustaining (Field) | CFS SE MGA HLT HV-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS HLT HVC BAU SUSTAIN PROJECT - MEDIUM2 | SE | MGA | HLT | Critical Facilities Sustaining (Field) | CFS SE MGA HLT HV-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS BEL HVC BAU SUSTAIN PROJECT - LARGE | SW | ARZ | BEL | Critical Facilities Sustaining (Field) | CFS SW ARZ BEL HV-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS BEL HVC BAU SUSTAIN PROJECT - LARGE | SW | ARZ | BEL | Critical Facilities Sustaining (Field) | CFS SW ARZ BEL HV-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS OCN BM-CFS BAU SUSTAIN PROJECT - MEDIUM | VA | HRD | OCN | Critical Facilities Sustaining (Field) | CFS VA HRD OCN BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS OCN BM-CFS BAU SUSTAIN PROJECT - MEDIUM | VA | HRD | OCN | Critical Facilities Sustaining (Field) | CFS VA HRD OCN BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS FWL HVC BAU SUSTAIN PROJECT - MEDIUM2 | SW | ARZ | FWL | Critical Facilities Sustaining (Field) | CFS SW ARZ FWL HV-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS FWL HVC BAU SUSTAIN PROJECT - MEDIUM2 | SW | ARZ | FWL | Critical Facilities Sustaining (Field) | CFS SW ARZ FWL HV-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS IRV HV BAU SUSTAIN PROJECT - MEDIUM | CA | ORG | IRV | Critical Facilities Sustaining (Field) | CFS CA ORG IRV HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS IRV HV BAU SUSTAIN PROJECT - MEDIUM | CA | ORG | IRV | Critical Facilities Sustaining (Field) | CFS CA ORG IRV HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS SAN BM BAU SUSTAIN PROJECT - SMALL | CA | SAN | DWN | Critical Facilities Sustaining (Field) | CFS CA SAN DWN BM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS SAN BM BAU SUSTAIN PROJECT - SMALL | CA | SAN | DWN | Critical Facilities Sustaining (Field) | CFS CA SAN DWN BM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS ESC BM BAU SUSTAIN PROJECT - SMALL | CA | SAN | ESC | Critical Facilities Sustaining (Field) | CFS CA SAN ESC BM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS ESC BM BAU SUSTAIN PROJECT - SMALL | CA | SAN | ESC | Critical Facilities Sustaining (Field) | CFS CA SAN ESC BM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS FED BM BAU SUSTAIN PROJECT - MEDIUM | CA | SAN | FED | Critical Facilities Sustaining (Field) | CFS CA SAN FED BM-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS FED BM BAU SUSTAIN PROJECT - MEDIUM | CA | SAN | FED | Critical Facilities Sustaining (Field) | CFS CA SAN FED BM-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS DNP HV BAU SUSTAIN PROJECT - LARGE | CA | ORG | DNP | Critical Facilities Sustaining (Field) | CFS CA ORG DNP HV-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS DNP HV BAU SUSTAIN PROJECT - LARGE | CA | ORG | DNP | Critical Facilities Sustaining (Field) | CFS CA ORG DNP HV-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS GRB RUF BAU SUSTAIN PROJECT - SMALL | NE | CON | GRB | Critical Facilities Sustaining (Field) | CFS NE CON GRB RF-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS GRB RUF BAU SUSTAIN PROJECT - SMALL | NE | CON | GRB | Critical Facilities Sustaining (Field) | CFS NE CON GRB RF-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS ELC AC BAU SUSTAIN PROJECT - LARGE | CA | SAN | ELC | Critical Facilities Sustaining (Field) | CFS CA SAN ELC AC-CFS Augment POR20 | Critical Facilities | BAU SUSTAIN PROJECT - LARGE | 1 | 2020-03-06 | 2020-04-15 |  | Deleted | EP
CFS PAW FIR BAU SUSTAIN PROJECT - SMALL2 | NE | RHD | PAW | Critical Facilities Sustaining (Field) | CFS NE RHD PAW FS-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PAW FIR BAU SUSTAIN PROJECT - SMALL2 | NE | RHD | PAW | Critical Facilities Sustaining (Field) | CFS NE RHD PAW FS-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PTH LMI BAU SUSTAIN PROJECT - SMALL | NE | RHD | PTH | Critical Facilities Sustaining (Field) | CFS NE RHD PTH LM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PTH LMI BAU SUSTAIN PROJECT - SMALL | NE | RHD | PTH | Critical Facilities Sustaining (Field) | CFS NE RHD PTH LM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PTH SEC BAU SUSTAIN PROJECT - SMALL | NE | RHD | PTH | Critical Facilities Sustaining (Field) | CFS NE RHD PTH SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PTH SEC BAU SUSTAIN PROJECT - SMALL | NE | RHD | PTH | Critical Facilities Sustaining (Field) | CFS NE RHD PTH SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PTH FIR BAU SUSTAIN PROJECT - SMALL2 | NE | RHD | PTH | Critical Facilities Sustaining (Field) | CFS NE RHD PTH FS-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PTH FIR BAU SUSTAIN PROJECT - SMALL2 | NE | RHD | PTH | Critical Facilities Sustaining (Field) | CFS NE RHD PTH FS-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PRV ACP BAU SUSTAIN PROJECT - MEDIUM | NE | RHD | PRV | Critical Facilities Sustaining (Field) | CFS NE RHD PRV AC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PRV ACP BAU SUSTAIN PROJECT - MEDIUM | NE | RHD | PRV | Critical Facilities Sustaining (Field) | CFS NE RHD PRV AC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PRV BU- BAU SUSTAIN PROJECT - SMALL | NE | RHD | PRV | Critical Facilities Sustaining (Field) | CFS NE RHD PRV BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PRV BU- BAU SUSTAIN PROJECT - SMALL | NE | RHD | PRV | Critical Facilities Sustaining (Field) | CFS NE RHD PRV BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PRV FIR BAU SUSTAIN PROJECT - SMALL2 | NE | RHD | PRV | Critical Facilities Sustaining (Field) | CFS NE RHD PRV FS-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PRV FIR BAU SUSTAIN PROJECT - SMALL2 | NE | RHD | PRV | Critical Facilities Sustaining (Field) | CFS NE RHD PRV FS-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS RMD GEN BAU SUSTAIN PROJECT - MEDIUM | NE | RHD | RMD | Critical Facilities Sustaining (Field) | CFS NE RHD RMD GN-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS RMD GEN BAU SUSTAIN PROJECT - MEDIUM | NE | RHD | RMD | Critical Facilities Sustaining (Field) | CFS NE RHD RMD GN-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS RMD SEC BAU SUSTAIN PROJECT - SMALL | NE | RHD | RMD | Critical Facilities Sustaining (Field) | CFS NE RHD RMD SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS RMD SEC BAU SUSTAIN PROJECT - SMALL | NE | RHD | RMD | Critical Facilities Sustaining (Field) | CFS NE RHD RMD SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS RMD FIR BAU SUSTAIN PROJECT - SMALL3 | NE | RHD | RMD | Critical Facilities Sustaining (Field) | CFS NE RHD RMD FS-CFS Augment POR20 - 3 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS RMD FIR BAU SUSTAIN PROJECT - SMALL3 | NE | RHD | RMD | Critical Facilities Sustaining (Field) | CFS NE RHD RMD FS-CFS Augment POR20 - 3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS SCT RUF BAU SUSTAIN PROJECT - SMALL | NE | RHD | SCT | Critical Facilities Sustaining (Field) | CFS NE RHD SCT RF-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS SCT RUF BAU SUSTAIN PROJECT - SMALL | NE | RHD | SCT | Critical Facilities Sustaining (Field) | CFS NE RHD SCT RF-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS SCT GEN BAU SUSTAIN PROJECT - MEDIUM | NE | RHD | SCT | Critical Facilities Sustaining (Field) | CFS NE RHD SCT GN-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS SCT GEN BAU SUSTAIN PROJECT - MEDIUM | NE | RHD | SCT | Critical Facilities Sustaining (Field) | CFS NE RHD SCT GN-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS SCT ATS BAU SUSTAIN PROJECT - MEDIUM | NE | RHD | SCT | Critical Facilities Sustaining (Field) | CFS NE RHD SCT AT-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS SCT ATS BAU SUSTAIN PROJECT - MEDIUM | NE | RHD | SCT | Critical Facilities Sustaining (Field) | CFS NE RHD SCT AT-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS SCT SEC BAU SUSTAIN PROJECT - SMALL | NE | RHD | SCT | Critical Facilities Sustaining (Field) | CFS NE RHD SCT SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS SCT SEC BAU SUSTAIN PROJECT - SMALL | NE | RHD | SCT | Critical Facilities Sustaining (Field) | CFS NE RHD SCT SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS ERW SEC BAU SUSTAIN PROJECT - MEDIUM | SE | BTR | ERW | Critical Facilities Sustaining (Field) | CFS SE BTR ERW SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS ERW SEC BAU SUSTAIN PROJECT - MEDIUM | SE | BTR | ERW | Critical Facilities Sustaining (Field) | CFS SE BTR ERW SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS FRK SEC BAU SUSTAIN PROJECT - SMALL | SE | LFY | FRK | Critical Facilities Sustaining (Field) | CFS SE LFY FRK SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS FRK SEC BAU SUSTAIN PROJECT - SMALL | SE | LFY | FRK | Critical Facilities Sustaining (Field) | CFS SE LFY FRK SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS GNZ SEC BAU SUSTAIN PROJECT - MEDIUM | SE | BTR | GNZ | Critical Facilities Sustaining (Field) | CFS SE BTR GNZ SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS GNZ SEC BAU SUSTAIN PROJECT - MEDIUM | SE | BTR | GNZ | Critical Facilities Sustaining (Field) | CFS SE BTR GNZ SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS KNN HVC BAU SUSTAIN PROJECT - SMALL | SE | NOR | KNN | Critical Facilities Sustaining (Field) | CFS SE NOR KNN HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS KNN HVC BAU SUSTAIN PROJECT - SMALL | SE | NOR | KNN | Critical Facilities Sustaining (Field) | CFS SE NOR KNN HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS KNN SEC BAU SUSTAIN PROJECT - MEDIUM | SE | NOR | KNN | Critical Facilities Sustaining (Field) | CFS SE NOR KNN SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS KNN SEC BAU SUSTAIN PROJECT - MEDIUM | SE | NOR | KNN | Critical Facilities Sustaining (Field) | CFS SE NOR KNN SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS KNN SEC BAU SUSTAIN PROJECT - SMALL | SE | NOR | KNN | Critical Facilities Sustaining (Field) | CFS SE NOR KNN SC-CFS Augment POR20 - 2 | Critical Facilities | BAU SUSTAIN PROJECT - SMALL |  |  |  |  | Deleted | EP
CFS KNN SEC BAU SUSTAIN PROJECT - SMALL | SE | NOR | KNN | Critical Facilities Sustaining (Field) | CFS SE NOR KNN SC-CFS Augment POR20 - 2 | Critical Facilities | BAU SUSTAIN PROJECT - SMALL |  |  |  |  | Deleted | Log | Del | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS LAF SEC BAU SUSTAIN PROJECT - MEDIUM | SE | LFY | LFY | Critical Facilities Sustaining (Field) | CFS SE LFY LFY SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS LAF SEC BAU SUSTAIN PROJECT - MEDIUM | SE | LFY | LFY | Critical Facilities Sustaining (Field) | CFS SE LFY LFY SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS LUL SEC BAU SUSTAIN PROJECT - SMALL | SE | NOR | LUL | Critical Facilities Sustaining (Field) | CFS SE NOR LUL SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS LUL SEC BAU SUSTAIN PROJECT - SMALL | SE | NOR | LUL | Critical Facilities Sustaining (Field) | CFS SE NOR LUL SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS LGR SEC BAU SUSTAIN PROJECT - MEDIUM | SE | BTR | LGR | Critical Facilities Sustaining (Field) | CFS SE BTR LGR SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS LGR SEC BAU SUSTAIN PROJECT - MEDIUM | SE | BTR | LGR | Critical Facilities Sustaining (Field) | CFS SE BTR LGR SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS MCY BDB BAU SUSTAIN PROJECT - LARGE | SE | NOR | MCY | Critical Facilities Sustaining (Field) | CFS SE NOR MCY BD-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS MCY BDB BAU SUSTAIN PROJECT - LARGE | SE | NOR | MCY | Critical Facilities Sustaining (Field) | CFS SE NOR MCY BD-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS MCY SEC BAU SUSTAIN PROJECT - SMALL | SE | NOR | MCY | Critical Facilities Sustaining (Field) | CFS SE NOR MCY SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS MCY SEC BAU SUSTAIN PROJECT - SMALL | SE | NOR | MCY | Critical Facilities Sustaining (Field) | CFS SE NOR MCY SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS NIB SEC BAU SUSTAIN PROJECT - MEDIUM | SE | LFY | NIB | Critical Facilities Sustaining (Field) | CFS SE LFY NIB SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS NIB SEC BAU SUSTAIN PROJECT - MEDIUM | SE | LFY | NIB | Critical Facilities Sustaining (Field) | CFS SE LFY NIB SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS NTH SEC BAU SUSTAIN PROJECT - MEDIUM | SE | BTR | NTH | Critical Facilities Sustaining (Field) | CFS SE BTR NTH SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS NTH SEC BAU SUSTAIN PROJECT - MEDIUM | SE | BTR | NTH | Critical Facilities Sustaining (Field) | CFS SE BTR NTH SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PLQ SEC BAU SUSTAIN PROJECT - MEDIUM | SE | BTR | PLQ | Critical Facilities Sustaining (Field) | CFS SE BTR PLQ SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PLQ SEC BAU SUSTAIN PROJECT - MEDIUM | SE | BTR | PLQ | Critical Facilities Sustaining (Field) | CFS SE BTR PLQ SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS NCV SEC BAU SUSTAIN PROJECT - SMALL | SE | GCT | NCV | Critical Facilities Sustaining (Field) | CFS SE GCT NCV SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS NCV SEC BAU SUSTAIN PROJECT - SMALL | SE | GCT | NCV | Critical Facilities Sustaining (Field) | CFS SE GCT NCV SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS NCV SEC BAU SUSTAIN PROJECT - SMALL2 | SE | GCT | NCV | Critical Facilities Sustaining (Field) | CFS SE GCT NCV SC-CFS Augment POR20 - 2 | Critical Facilities | BAU SUSTAIN PROJECT - SMALL |  |  |  |  | Deleted | EP
CFS NCV SEC BAU SUSTAIN PROJECT - SMALL2 | SE | GCT | NCV | Critical Facilities Sustaining (Field) | CFS SE GCT NCV SC-CFS Augment POR20 - 2 | Critical Facilities | BAU SUSTAIN PROJECT - SMALL |  |  |  |  | Deleted | Log | Del | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS PNS HVC BAU SUSTAIN PROJECT - MEDIUM | SE | GCT | PNS | Critical Facilities Sustaining (Field) | CFS SE GCT PNS HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PNS HVC BAU SUSTAIN PROJECT - MEDIUM | SE | GCT | PNS | Critical Facilities Sustaining (Field) | CFS SE GCT PNS HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PNS SEC BAU SUSTAIN PROJECT - MEDIUM | SE | GCT | PNS | Critical Facilities Sustaining (Field) | CFS SE GCT PNS SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PNS SEC BAU SUSTAIN PROJECT - MEDIUM | SE | GCT | PNS | Critical Facilities Sustaining (Field) | CFS SE GCT PNS SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS GRY SEC BAU SUSTAIN PROJECT - MEDIUM | SE | MGA | GRY | Critical Facilities Sustaining (Field) | CFS SE MGA GRY SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS GRY SEC BAU SUSTAIN PROJECT - MEDIUM | SE | MGA | GRY | Critical Facilities Sustaining (Field) | CFS SE MGA GRY SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS BEN HVC BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | BEN | Critical Facilities Sustaining (Field) | CFS SW ARZ BEN HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS BEN HVC BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | BEN | Critical Facilities Sustaining (Field) | CFS SW ARZ BEN HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CSG LMI BAU SUSTAIN PROJECT - LARGE | SW | ARZ | CSG | Critical Facilities Sustaining (Field) | CFS SW ARZ CSG LM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS CSG LMI BAU SUSTAIN PROJECT - LARGE | SW | ARZ | CSG | Critical Facilities Sustaining (Field) | CFS SW ARZ CSG LM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CSG HVC BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | CSG | Critical Facilities Sustaining (Field) | CFS SW ARZ CSG HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS CSG HVC BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | CSG | Critical Facilities Sustaining (Field) | CFS SW ARZ CSG HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CHD BAT BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | CHD | Critical Facilities Sustaining (Field) | CFS SW ARZ CHD BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS CHD BAT BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | CHD | Critical Facilities Sustaining (Field) | CFS SW ARZ CHD BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS WWK BU- BAU SUSTAIN PROJECT - MEDIUM | NE | RHD | WWK | Critical Facilities Sustaining (Field) | CFS NE RHD WWK BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS WWK BU- BAU SUSTAIN PROJECT - MEDIUM | NE | RHD | WWK | Critical Facilities Sustaining (Field) | CFS NE RHD WWK BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS WWK SEC BAU SUSTAIN PROJECT - SMALL | NE | RHD | WWK | Critical Facilities Sustaining (Field) | CFS NE RHD WWK SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS WWK SEC BAU SUSTAIN PROJECT - SMALL | NE | RHD | WWK | Critical Facilities Sustaining (Field) | CFS NE RHD WWK SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS WWK FIR BAU SUSTAIN PROJECT - SMALL3 | NE | RHD | WWK | Critical Facilities Sustaining (Field) | CFS NE RHD WWK FS-CFS Augment POR20 - 3 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS WWK FIR BAU SUSTAIN PROJECT - SMALL3 | NE | RHD | WWK | Critical Facilities Sustaining (Field) | CFS NE RHD WWK FS-CFS Augment POR20 - 3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS GNS SEC BAU SUSTAIN PROJECT - MEDIUM | SE | GAN | GNS | Critical Facilities Sustaining (Field) | CFS SE GAN GNS SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS GNS SEC BAU SUSTAIN PROJECT - MEDIUM | SE | GAN | GNS | Critical Facilities Sustaining (Field) | CFS SE GAN GNS SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS ABV SEC BAU SUSTAIN PROJECT - MEDIUM | SE | LFY | ABV | Critical Facilities Sustaining (Field) | CFS SE LFY ABV SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS ABV SEC BAU SUSTAIN PROJECT - MEDIUM | SE | LFY | ABV | Critical Facilities Sustaining (Field) | CFS SE LFY ABV SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS ALG SEC BAU SUSTAIN PROJECT - SMALL | SE | NOR | ALG | Critical Facilities Sustaining (Field) | CFS SE NOR ALG SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS ALG SEC BAU SUSTAIN PROJECT - SMALL | SE | NOR | ALG | Critical Facilities Sustaining (Field) | CFS SE NOR ALG SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS BTR SEC BAU SUSTAIN PROJECT - MEDIUM | SE | BTR | BTR | Critical Facilities Sustaining (Field) | CFS SE BTR BTR SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS BTR SEC BAU SUSTAIN PROJECT - MEDIUM | SE | BTR | BTR | Critical Facilities Sustaining (Field) | CFS SE BTR BTR SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CLR BAT BAU SUSTAIN PROJECT - MEDIUM | SE | NOR | CLR | Critical Facilities Sustaining (Field) | CFS SE NOR CLR BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS CLR BAT BAU SUSTAIN PROJECT - MEDIUM | SE | NOR | CLR | Critical Facilities Sustaining (Field) | CFS SE NOR CLR BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CRW SEC BAU SUSTAIN PROJECT - MEDIUM | SE | LFY | CRW | Critical Facilities Sustaining (Field) | CFS SE LFY CRW SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS CRW SEC BAU SUSTAIN PROJECT - MEDIUM | SE | LFY | CRW | Critical Facilities Sustaining (Field) | CFS SE LFY CRW SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CRW SEC BAU SUSTAIN PROJECT - SMALL | SE | LFY | CRW | Critical Facilities Sustaining (Field) | CFS SE LFY CRW SC-CFS Augment POR20 - 2 | Critical Facilities | BAU SUSTAIN PROJECT - SMALL |  |  |  |  | Deleted | EP
CFS CRW SEC BAU SUSTAIN PROJECT - SMALL | SE | LFY | CRW | Critical Facilities Sustaining (Field) | CFS SE LFY CRW SC-CFS Augment POR20 - 2 | Critical Facilities | BAU SUSTAIN PROJECT - SMALL |  |  |  |  | Deleted | Log | Del | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS DNS SEC BAU SUSTAIN PROJECT - SMALL | SE | BTR | DNS | Critical Facilities Sustaining (Field) | CFS SE BTR DNS SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS DNS SEC BAU SUSTAIN PROJECT - SMALL | SE | BTR | DNS | Critical Facilities Sustaining (Field) | CFS SE BTR DNS SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS DST SEC BAU SUSTAIN PROJECT - MEDIUM | SE | NOR | DST | Critical Facilities Sustaining (Field) | CFS SE NOR DST SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS DST SEC BAU SUSTAIN PROJECT - MEDIUM | SE | NOR | DST | Critical Facilities Sustaining (Field) | CFS SE NOR DST SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS DVL SEC BAU SUSTAIN PROJECT - MEDIUM | SE | BTR | DVL | Critical Facilities Sustaining (Field) | CFS SE BTR DVL SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS DVL SEC BAU SUSTAIN PROJECT - MEDIUM | SE | BTR | DVL | Critical Facilities Sustaining (Field) | CFS SE BTR DVL SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS ELM SEC BAU SUSTAIN PROJECT - MEDIUM | SE | NOR | ELM | Critical Facilities Sustaining (Field) | CFS SE NOR ELM SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS ELM SEC BAU SUSTAIN PROJECT - MEDIUM | SE | NOR | ELM | Critical Facilities Sustaining (Field) | CFS SE NOR ELM SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS SPC SEC BAU SUSTAIN PROJECT - MEDIUM | SE | BTR | SPC | Critical Facilities Sustaining (Field) | CFS SE BTR SPC SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS SPC SEC BAU SUSTAIN PROJECT - MEDIUM | SE | BTR | SPC | Critical Facilities Sustaining (Field) | CFS SE BTR SPC SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS STB SEC BAU SUSTAIN PROJECT - SMALL | SE | NOR | STB | Critical Facilities Sustaining (Field) | CFS SE NOR STB SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS STB SEC BAU SUSTAIN PROJECT - SMALL | SE | NOR | STB | Critical Facilities Sustaining (Field) | CFS SE NOR STB SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS STB SEC BAU SUSTAIN PROJECT - SMALL2 | SE | NOR | STB | Critical Facilities Sustaining (Field) | CFS SE NOR STB SC-CFS Augment POR20 - 2 | Critical Facilities | BAU SUSTAIN PROJECT - SMALL |  |  |  |  | Deleted | EP
CFS STB SEC BAU SUSTAIN PROJECT - SMALL2 | SE | NOR | STB | Critical Facilities Sustaining (Field) | CFS SE NOR STB SC-CFS Augment POR20 - 2 | Critical Facilities | BAU SUSTAIN PROJECT - SMALL |  |  |  |  | Deleted | Log | Del | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS STC SEC BAU SUSTAIN PROJECT - MEDIUM | SE | BTR | STC | Critical Facilities Sustaining (Field) | CFS SE BTR STC SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS STC SEC BAU SUSTAIN PROJECT - MEDIUM | SE | BTR | STC | Critical Facilities Sustaining (Field) | CFS SE BTR STC SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS STM INV BAU SUSTAIN PROJECT - MEDIUM | SE | LFY | STM | Critical Facilities Sustaining (Field) | CFS SE LFY STM IV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS STM INV BAU SUSTAIN PROJECT - MEDIUM | SE | LFY | STM | Critical Facilities Sustaining (Field) | CFS SE LFY STM IV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS STM BAT BAU SUSTAIN PROJECT - MEDIUM | SE | LFY | STM | Critical Facilities Sustaining (Field) | CFS SE LFY STM BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS STM BAT BAU SUSTAIN PROJECT - MEDIUM | SE | LFY | STM | Critical Facilities Sustaining (Field) | CFS SE LFY STM BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS STM SEC BAU SUSTAIN PROJECT - MEDIUM | SE | LFY | STM | Critical Facilities Sustaining (Field) | CFS SE LFY STM SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS STM SEC BAU SUSTAIN PROJECT - MEDIUM | SE | LFY | STM | Critical Facilities Sustaining (Field) | CFS SE LFY STM SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CRV SEC BAU SUSTAIN PROJECT - SMALL | SE | GCT | CRV | Critical Facilities Sustaining (Field) | CFS SE GCT CRV SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS CRV SEC BAU SUSTAIN PROJECT - SMALL | SE | GCT | CRV | Critical Facilities Sustaining (Field) | CFS SE GCT CRV SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CRV SEC BAU SUSTAIN PROJECT - MEDIUM | SE | GCT | CRV | Critical Facilities Sustaining (Field) | CFS SE GCT CRV SC-CFS Augment POR20 - 2 | Critical Facilities | BAU SUSTAIN PROJECT - MEDIUM |  |  |  |  | Deleted | EP
CFS CRV SEC BAU SUSTAIN PROJECT - MEDIUM | SE | GCT | CRV | Critical Facilities Sustaining (Field) | CFS SE GCT CRV SC-CFS Augment POR20 - 2 | Critical Facilities | BAU SUSTAIN PROJECT - MEDIUM |  |  |  |  | Deleted | Log | Del | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS DES SEC BAU SUSTAIN PROJECT - SMALL | SE | GCT | DES | Critical Facilities Sustaining (Field) | CFS SE GCT DES SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS DES SEC BAU SUSTAIN PROJECT - SMALL | SE | GCT | DES | Critical Facilities Sustaining (Field) | CFS SE GCT DES SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS FWB SEC BAU SUSTAIN PROJECT - SMALL | SE | GCT | FWB | Critical Facilities Sustaining (Field) | CFS SE GCT FWB SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS FWB SEC BAU SUSTAIN PROJECT - SMALL | SE | GCT | FWB | Critical Facilities Sustaining (Field) | CFS SE GCT FWB SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS DGL BAT BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | DGL | Critical Facilities Sustaining (Field) | CFS SW ARZ DGL BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS DGL BAT BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | DGL | Critical Facilities Sustaining (Field) | CFS SW ARZ DGL BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS WWK BAT BAU SUSTAIN PROJECT - MEDIUM | NE | RHD | WWK | Critical Facilities Sustaining (Field) | CFS NE RHD WWK BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS WWK BAT BAU SUSTAIN PROJECT - MEDIUM | NE | RHD | WWK | Critical Facilities Sustaining (Field) | CFS NE RHD WWK BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS TEN BAT BAU SUSTAIN PROJECT - MEDIUM | SW | LAS | TEN | Critical Facilities Sustaining (Field) | CFS SW LAS TEN BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS TEN BAT BAU SUSTAIN PROJECT - MEDIUM | SW | LAS | TEN | Critical Facilities Sustaining (Field) | CFS SW LAS TEN BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VLY HVC BAU SUSTAIN PROJECT - MEDIUM | SW | LAS | VLY | Critical Facilities Sustaining (Field) | CFS SW LAS VLY HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS VLY HVC BAU SUSTAIN PROJECT - MEDIUM | SW | LAS | VLY | Critical Facilities Sustaining (Field) | CFS SW LAS VLY HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VLY BAT BAU SUSTAIN PROJECT - MEDIUM | SW | LAS | VLY | Critical Facilities Sustaining (Field) | CFS SW LAS VLY BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS VLY BAT BAU SUSTAIN PROJECT - MEDIUM | SW | LAS | VLY | Critical Facilities Sustaining (Field) | CFS SW LAS VLY BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS LTF GEN BAU SUSTAIN PROJECT - MEDIUM | VA | HRD | LTF | Critical Facilities Sustaining (Field) | CFS VA HRD LTF GN-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS LTF GEN BAU SUSTAIN PROJECT - MEDIUM | VA | HRD | LTF | Critical Facilities Sustaining (Field) | CFS VA HRD LTF GN-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS NRF GEN BAU SUSTAIN PROJECT - LARGE | VA | HRD | NRF | Critical Facilities Sustaining (Field) | CFS VA HRD NRF GN-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS NRF GEN BAU SUSTAIN PROJECT - LARGE | VA | HRD | NRF | Critical Facilities Sustaining (Field) | CFS VA HRD NRF GN-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS OCN BS- BAU SUSTAIN PROJECT - MEDIUM | VA | HRD | OCN | Critical Facilities Sustaining (Field) | CFS VA HRD OCN BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS OCN BS- BAU SUSTAIN PROJECT - MEDIUM | VA | HRD | OCN | Critical Facilities Sustaining (Field) | CFS VA HRD OCN BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS OCN DC- BAU SUSTAIN PROJECT - MEDIUM | VA | HRD | OCN | Critical Facilities Sustaining (Field) | CFS VA HRD OCN DC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS OCN DC- BAU SUSTAIN PROJECT - MEDIUM | VA | HRD | OCN | Critical Facilities Sustaining (Field) | CFS VA HRD OCN DC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PTM DC- BAU SUSTAIN PROJECT - MEDIUM | VA | HRD | PTM | Critical Facilities Sustaining (Field) | CFS VA HRD PTM DC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PTM DC- BAU SUSTAIN PROJECT - MEDIUM | VA | HRD | PTM | Critical Facilities Sustaining (Field) | CFS VA HRD PTM DC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PTM DC- BAU SUSTAIN PROJECT - LARGE | VA | HRD | PTM | Critical Facilities Sustaining (Field) | CFS VA HRD PTM DC-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PTM DC- BAU SUSTAIN PROJECT - LARGE | VA | HRD | PTM | Critical Facilities Sustaining (Field) | CFS VA HRD PTM DC-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PRA DC- BAU SUSTAIN PROJECT - MEDIUM | VA | HRD | PRA | Critical Facilities Sustaining (Field) | CFS VA HRD PRA DC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PRA DC- BAU SUSTAIN PROJECT - MEDIUM | VA | HRD | PRA | Critical Facilities Sustaining (Field) | CFS VA HRD PRA DC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PRA RF- BAU SUSTAIN PROJECT - LARGE | VA | HRD | PRA | Critical Facilities Sustaining (Field) | CFS VA HRD PRA RF-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PRA RF- BAU SUSTAIN PROJECT - LARGE | VA | HRD | PRA | Critical Facilities Sustaining (Field) | CFS VA HRD PRA RF-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS GCR DC- BAU SUSTAIN PROJECT - MEDIUM | VA | NVA | GCR | Critical Facilities Sustaining (Field) | CFS VA NVA GCR DC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS GCR DC- BAU SUSTAIN PROJECT - MEDIUM | VA | NVA | GCR | Critical Facilities Sustaining (Field) | CFS VA NVA GCR DC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS GCR BS- BAU SUSTAIN PROJECT - LARGE | VA | NVA | GCR | Critical Facilities Sustaining (Field) | CFS VA NVA GCR BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS GCR BS- BAU SUSTAIN PROJECT - LARGE | VA | NVA | GCR | Critical Facilities Sustaining (Field) | CFS VA NVA GCR BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS MFD DC- BAU SUSTAIN PROJECT - MEDIUM | VA | NVA | MFD | Critical Facilities Sustaining (Field) | CFS VA NVA MFD DC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS MFD DC- BAU SUSTAIN PROJECT - MEDIUM | VA | NVA | MFD | Critical Facilities Sustaining (Field) | CFS VA NVA MFD DC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS MFD BD- BAU SUSTAIN PROJECT - MEDIUM | VA | NVA | MFD | Critical Facilities Sustaining (Field) | CFS VA NVA MFD BD-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS MFD BD- BAU SUSTAIN PROJECT - MEDIUM | VA | NVA | MFD | Critical Facilities Sustaining (Field) | CFS VA NVA MFD BD-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS RHL DC- BAU SUSTAIN PROJECT - MEDIUM | VA | NVA | RHL | Critical Facilities Sustaining (Field) | CFS VA NVA RHL DC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS RHL DC- BAU SUSTAIN PROJECT - MEDIUM | VA | NVA | RHL | Critical Facilities Sustaining (Field) | CFS VA NVA RHL DC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS RNK DC- BAU SUSTAIN PROJECT - MEDIUM | VA | ROA | RON | Critical Facilities Sustaining (Field) | CFS VA ROA RON DC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS RNK DC- BAU SUSTAIN PROJECT - MEDIUM | VA | ROA | RON | Critical Facilities Sustaining (Field) | CFS VA ROA RON DC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS RNK DC- BAU SUSTAIN PROJECT - MEDIUM2 | VA | ROA | RON | Critical Facilities Sustaining (Field) | CFS VA ROA RON DC-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS RNK DC- BAU SUSTAIN PROJECT - MEDIUM2 | VA | ROA | RON | Critical Facilities Sustaining (Field) | CFS VA ROA RON DC-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS MSA BAT BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | MSA | Critical Facilities Sustaining (Field) | CFS SW ARZ MSA BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS MSA BAT BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | MSA | Critical Facilities Sustaining (Field) | CFS SW ARZ MSA BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS FWL BAT BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | FWL | Critical Facilities Sustaining (Field) | CFS SW ARZ FWL BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS FWL BAT BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | FWL | Critical Facilities Sustaining (Field) | CFS SW ARZ FWL BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS GVA BAT BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | GVA | Critical Facilities Sustaining (Field) | CFS SW ARZ GVA BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS GVA BAT BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | GVA | Critical Facilities Sustaining (Field) | CFS SW ARZ GVA BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS NSC SEC BAU SUSTAIN PROJECT - SMALL | SW | ARZ | NSC | Critical Facilities Sustaining (Field) | CFS SW ARZ NSC SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS NSC SEC BAU SUSTAIN PROJECT - SMALL | SW | ARZ | NSC | Critical Facilities Sustaining (Field) | CFS SW ARZ NSC SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PEO SEC BAU SUSTAIN PROJECT - SMALL | SW | ARZ | PEO | Critical Facilities Sustaining (Field) | CFS SW ARZ PEO SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PEO SEC BAU SUSTAIN PROJECT - SMALL | SW | ARZ | PEO | Critical Facilities Sustaining (Field) | CFS SW ARZ PEO SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PNL SEC BAU SUSTAIN PROJECT - SMALL | SW | ARZ | PNL | Critical Facilities Sustaining (Field) | CFS SW ARZ PNL SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PNL SEC BAU SUSTAIN PROJECT - SMALL | SW | ARZ | PNL | Critical Facilities Sustaining (Field) | CFS SW ARZ PNL SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PNL BAT BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | PNL | Critical Facilities Sustaining (Field) | CFS SW ARZ PNL BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PNL BAT BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | PNL | Critical Facilities Sustaining (Field) | CFS SW ARZ PNL BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PNL HVC BAU SUSTAIN PROJECT - MEDIUM2 | SW | ARZ | PNL | Critical Facilities Sustaining (Field) | CFS SW ARZ PNL HV-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PNL HVC BAU SUSTAIN PROJECT - MEDIUM2 | SW | ARZ | PNL | Critical Facilities Sustaining (Field) | CFS SW ARZ PNL HV-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PNL LMI BAU SUSTAIN PROJECT - LARGE | SW | ARZ | PNL | Critical Facilities Sustaining (Field) | CFS SW ARZ PNL LM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PNL LMI BAU SUSTAIN PROJECT - LARGE | SW | ARZ | PNL | Critical Facilities Sustaining (Field) | CFS SW ARZ PNL LM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS SVA SEC BAU SUSTAIN PROJECT - SMALL | SW | ARZ | SVA | Critical Facilities Sustaining (Field) | CFS SW ARZ SVA SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS SVA SEC BAU SUSTAIN PROJECT - SMALL | SW | ARZ | SVA | Critical Facilities Sustaining (Field) | CFS SW ARZ SVA SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS SVA BAT BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | SVA | Critical Facilities Sustaining (Field) | CFS SW ARZ SVA BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS SVA BAT BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | SVA | Critical Facilities Sustaining (Field) | CFS SW ARZ SVA BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS SVA HVC BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | SVA | Critical Facilities Sustaining (Field) | CFS SW ARZ SVA HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS SVA HVC BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | SVA | Critical Facilities Sustaining (Field) | CFS SW ARZ SVA HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS SSC SEC BAU SUSTAIN PROJECT - SMALL | SW | ARZ | SSC | Critical Facilities Sustaining (Field) | CFS SW ARZ SSC SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS SSC SEC BAU SUSTAIN PROJECT - SMALL | SW | ARZ | SSC | Critical Facilities Sustaining (Field) | CFS SW ARZ SSC SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS TUC HVC BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | TUC | Critical Facilities Sustaining (Field) | CFS SW ARZ TUC HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS TUC HVC BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | TUC | Critical Facilities Sustaining (Field) | CFS SW ARZ TUC HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS TUC SEC BAU SUSTAIN PROJECT - SMALL | SW | ARZ | TUC | Critical Facilities Sustaining (Field) | CFS SW ARZ TUC SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS TUC SEC BAU SUSTAIN PROJECT - SMALL | SW | ARZ | TUC | Critical Facilities Sustaining (Field) | CFS SW ARZ TUC SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS TUC BAT BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | TUC | Critical Facilities Sustaining (Field) | CFS SW ARZ TUC BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS TUC BAT BAU SUSTAIN PROJECT - MEDIUM | SW | ARZ | TUC | Critical Facilities Sustaining (Field) | CFS SW ARZ TUC BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS BLU BAT BAU SUSTAIN PROJECT - MEDIUM | SW | LAS | BLU | Critical Facilities Sustaining (Field) | CFS SW LAS BLU BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS BLU BAT BAU SUSTAIN PROJECT - MEDIUM | SW | LAS | BLU | Critical Facilities Sustaining (Field) | CFS SW LAS BLU BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CEN BAT BAU SUSTAIN PROJECT - MEDIUM | SW | LAS | CEN | Critical Facilities Sustaining (Field) | CFS SW LAS CEN BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS CEN BAT BAU SUSTAIN PROJECT - MEDIUM | SW | LAS | CEN | Critical Facilities Sustaining (Field) | CFS SW LAS CEN BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS HEN HVC BAU SUSTAIN PROJECT - MEDIUM | SW | LAS | HEN | Critical Facilities Sustaining (Field) | CFS SW LAS HEN HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS HEN HVC BAU SUSTAIN PROJECT - MEDIUM | SW | LAS | HEN | Critical Facilities Sustaining (Field) | CFS SW LAS HEN HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS HEN BAT BAU SUSTAIN PROJECT - MEDIUM | SW | LAS | HEN | Critical Facilities Sustaining (Field) | CFS SW LAS HEN BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS HEN BAT BAU SUSTAIN PROJECT - MEDIUM | SW | LAS | HEN | Critical Facilities Sustaining (Field) | CFS SW LAS HEN BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS TEN HVC BAU SUSTAIN PROJECT - MEDIUM | SW | LAS | TEN | Critical Facilities Sustaining (Field) | CFS SW LAS TEN HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS TEN HVC BAU SUSTAIN PROJECT - MEDIUM | SW | LAS | TEN | Critical Facilities Sustaining (Field) | CFS SW LAS TEN HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VBC BS- BAU SUSTAIN PROJECT - MEDIUM | VA | HRD | VBC | Critical Facilities Sustaining (Field) | CFS VA HRD VBC BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS VBC BS- BAU SUSTAIN PROJECT - MEDIUM | VA | HRD | VBC | Critical Facilities Sustaining (Field) | CFS VA HRD VBC BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS AVJ BM BAU SUSTAIN PROJECT - SMALL | CA | ORG | AVJ | Critical Facilities Sustaining (Field) | CFS CA ORG AVJ BM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS AVJ BM BAU SUSTAIN PROJECT - SMALL | CA | ORG | AVJ | Critical Facilities Sustaining (Field) | CFS CA ORG AVJ BM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS DNP BM BAU SUSTAIN PROJECT - SMALL | CA | ORG | DNP | Critical Facilities Sustaining (Field) | CFS CA ORG DNP BM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS DNP BM BAU SUSTAIN PROJECT - SMALL | CA | ORG | DNP | Critical Facilities Sustaining (Field) | CFS CA ORG DNP BM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS IRV BM BAU SUSTAIN PROJECT - SMALL | CA | ORG | IRV | Critical Facilities Sustaining (Field) | CFS CA ORG IRV BM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS IRV BM BAU SUSTAIN PROJECT - SMALL | CA | ORG | IRV | Critical Facilities Sustaining (Field) | CFS CA ORG IRV BM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS ORG BL BAU SUSTAIN PROJECT - LARGE | CA | ORG | ORG | Critical Facilities Sustaining (Field) | CFS CA ORG ORG BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS ORG BL BAU SUSTAIN PROJECT - LARGE | CA | ORG | ORG | Critical Facilities Sustaining (Field) | CFS CA ORG ORG BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS RSM BM BAU SUSTAIN PROJECT - SMALL | CA | ORG | RSM | Critical Facilities Sustaining (Field) | CFS CA ORG RSM BM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS RSM BM BAU SUSTAIN PROJECT - SMALL | CA | ORG | RSM | Critical Facilities Sustaining (Field) | CFS CA ORG RSM BM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS RSM HV BAU SUSTAIN PROJECT - LARGE | CA | ORG | RSM | Critical Facilities Sustaining (Field) | CFS CA ORG RSM HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS RSM HV BAU SUSTAIN PROJECT - LARGE | CA | ORG | RSM | Critical Facilities Sustaining (Field) | CFS CA ORG RSM HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS SAN HV BAU SUSTAIN PROJECT - MEDIUM | CA | SAN | DWN | Critical Facilities Sustaining (Field) | CFS CA SAN DWN HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS SAN HV BAU SUSTAIN PROJECT - MEDIUM | CA | SAN | DWN | Critical Facilities Sustaining (Field) | CFS CA SAN DWN HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS BVL BUP BAU SUSTAIN PROJECT - SMALL | CE | NWA | BVL | Critical Facilities Sustaining (Field) | CFS CE NWA BVL BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS BVL BUP BAU SUSTAIN PROJECT - SMALL | CE | NWA | BVL | Critical Facilities Sustaining (Field) | CFS CE NWA BVL BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS BVL LMI BAU SUSTAIN PROJECT - MEDIUM | CE | NWA | BVL | Critical Facilities Sustaining (Field) | CFS CE NWA BVL LM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS BVL LMI BAU SUSTAIN PROJECT - MEDIUM | CE | NWA | BVL | Critical Facilities Sustaining (Field) | CFS CE NWA BVL LM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS DCY HVC BAU SUSTAIN PROJECT - MEDIUM | CE | KAN | DCY | Critical Facilities Sustaining (Field) | CFS CE KAN DCY HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS DCY HVC BAU SUSTAIN PROJECT - MEDIUM | CE | KAN | DCY | Critical Facilities Sustaining (Field) | CFS CE KAN DCY HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS FSC BUP BAU SUSTAIN PROJECT - SMALL | CE | KAN | FSC | Critical Facilities Sustaining (Field) | CFS CE KAN FSC BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS FSC BUP BAU SUSTAIN PROJECT - SMALL | CE | KAN | FSC | Critical Facilities Sustaining (Field) | CFS CE KAN FSC BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PSN LGT BAU SUSTAIN PROJECT - SMALL | CE | KAN | PSN | Critical Facilities Sustaining (Field) | CFS CE KAN PSN FF-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PSN LGT BAU SUSTAIN PROJECT - SMALL | CE | KAN | PSN | Critical Facilities Sustaining (Field) | CFS CE KAN PSN FF-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PSN HVC BAU SUSTAIN PROJECT - MEDIUM | CE | KAN | PSN | Critical Facilities Sustaining (Field) | CFS CE KAN PSN HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PSN HVC BAU SUSTAIN PROJECT - MEDIUM | CE | KAN | PSN | Critical Facilities Sustaining (Field) | CFS CE KAN PSN HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PSN LMI BAU SUSTAIN PROJECT - SMALL | CE | KAN | PSN | Critical Facilities Sustaining (Field) | CFS CE KAN PSN LM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PSN LMI BAU SUSTAIN PROJECT - SMALL | CE | KAN | PSN | Critical Facilities Sustaining (Field) | CFS CE KAN PSN LM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PSN SEC BAU SUSTAIN PROJECT - SMALL | CE | KAN | PSN | Critical Facilities Sustaining (Field) | CFS CE KAN PSN SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PSN SEC BAU SUSTAIN PROJECT - SMALL | CE | KAN | PSN | Critical Facilities Sustaining (Field) | CFS CE KAN PSN SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PIT HVC BAU SUSTAIN PROJECT - MEDIUM | CE | KAN | PIT | Critical Facilities Sustaining (Field) | CFS CE KAN PIT HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PIT HVC BAU SUSTAIN PROJECT - MEDIUM | CE | KAN | PIT | Critical Facilities Sustaining (Field) | CFS CE KAN PIT HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PIT RUF BAU SUSTAIN PROJECT - SMALL | CE | KAN | PIT | Critical Facilities Sustaining (Field) | CFS CE KAN PIT RF-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PIT RUF BAU SUSTAIN PROJECT - SMALL | CE | KAN | PIT | Critical Facilities Sustaining (Field) | CFS CE KAN PIT RF-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PIT SEC BAU SUSTAIN PROJECT - SMALL | CE | KAN | PIT | Critical Facilities Sustaining (Field) | CFS CE KAN PIT SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PIT SEC BAU SUSTAIN PROJECT - SMALL | CE | KAN | PIT | Critical Facilities Sustaining (Field) | CFS CE KAN PIT SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS SDN HVC BAU SUSTAIN PROJECT - SMALL | CE | KAN | SDN | Critical Facilities Sustaining (Field) | CFS CE KAN SDN HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS SDN HVC BAU SUSTAIN PROJECT - SMALL | CE | KAN | SDN | Critical Facilities Sustaining (Field) | CFS CE KAN SDN HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS WIC HVC BAU SUSTAIN PROJECT - MEDIUM | CE | KAN | WIC | Critical Facilities Sustaining (Field) | CFS CE KAN WIC HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS WIC HVC BAU SUSTAIN PROJECT - MEDIUM | CE | KAN | WIC | Critical Facilities Sustaining (Field) | CFS CE KAN WIC HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS NOR GEN BAU SUSTAIN PROJECT - LARGE | CE | OKC | NOR | Critical Facilities Sustaining (Field) | CFS CE OKC NOR GN-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS NOR GEN BAU SUSTAIN PROJECT - LARGE | CE | OKC | NOR | Critical Facilities Sustaining (Field) | CFS CE OKC NOR GN-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS OKC HVC BAU SUSTAIN PROJECT - MEDIUM2 | CE | OKC | OKC | Critical Facilities Sustaining (Field) | CFS CE OKC OKC HV-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS OKC HVC BAU SUSTAIN PROJECT - MEDIUM2 | CE | OKC | OKC | Critical Facilities Sustaining (Field) | CFS CE OKC OKC HV-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS OWA BUP BAU SUSTAIN PROJECT - SMALL | CE | TUL | OWA | Critical Facilities Sustaining (Field) | CFS CE TUL OWA BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS OWA BUP BAU SUSTAIN PROJECT - SMALL | CE | TUL | OWA | Critical Facilities Sustaining (Field) | CFS CE TUL OWA BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS OWA GEN BAU SUSTAIN PROJECT - MEDIUM | CE | TUL | OWA | Critical Facilities Sustaining (Field) | CFS CE TUL OWA GN-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS OWA GEN BAU SUSTAIN PROJECT - MEDIUM | CE | TUL | OWA | Critical Facilities Sustaining (Field) | CFS CE TUL OWA GN-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS OWA BUP BAU SUSTAIN PROJECT - SMALL2 | CE | TUL | OWA | Critical Facilities Sustaining (Field) | CFS CE TUL OWA BU-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS OWA BUP BAU SUSTAIN PROJECT - SMALL2 | CE | TUL | OWA | Critical Facilities Sustaining (Field) | CFS CE TUL OWA BU-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS QNC BUP BAU SUSTAIN PROJECT - SMALL | CE | TUL | QNC | Critical Facilities Sustaining (Field) | CFS CE TUL QNC BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS QNC BUP BAU SUSTAIN PROJECT - SMALL | CE | TUL | QNC | Critical Facilities Sustaining (Field) | CFS CE TUL QNC BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS SAP BUP BAU SUSTAIN PROJECT - SMALL | CE | TUL | SAP | Critical Facilities Sustaining (Field) | CFS CE TUL SAP BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS SAP BUP BAU SUSTAIN PROJECT - SMALL | CE | TUL | SAP | Critical Facilities Sustaining (Field) | CFS CE TUL SAP BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS BLV HVC BAU SUSTAIN PROJECT - MEDIUM | CE | OMA | BLV | Critical Facilities Sustaining (Field) | CFS CE OMA BLV HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS BLV HVC BAU SUSTAIN PROJECT - MEDIUM | CE | OMA | BLV | Critical Facilities Sustaining (Field) | CFS CE OMA BLV HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS ELK HVC BAU SUSTAIN PROJECT - MEDIUM | CE | OMA | ELK | Critical Facilities Sustaining (Field) | CFS CE OMA ELK HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS ELK HVC BAU SUSTAIN PROJECT - MEDIUM | CE | OMA | ELK | Critical Facilities Sustaining (Field) | CFS CE OMA ELK HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS ONA LGT BAU SUSTAIN PROJECT - MEDIUM | CE | OMA | ONA | Critical Facilities Sustaining (Field) | CFS CE OMA ONA FF-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS ONA LGT BAU SUSTAIN PROJECT - MEDIUM | CE | OMA | ONA | Critical Facilities Sustaining (Field) | CFS CE OMA ONA FF-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS WES HVC BAU SUSTAIN PROJECT - MEDIUM | CE | OMA | WES | Critical Facilities Sustaining (Field) | CFS CE OMA WES HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS WES HVC BAU SUSTAIN PROJECT - MEDIUM | CE | OMA | WES | Critical Facilities Sustaining (Field) | CFS CE OMA WES HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS ENF HVC BAU SUSTAIN PROJECT - MEDIUM | NE | CON | ENF | Critical Facilities Sustaining (Field) | CFS NE CON ENF HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS ENF HVC BAU SUSTAIN PROJECT - MEDIUM | NE | CON | ENF | Critical Facilities Sustaining (Field) | CFS NE CON ENF HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS ENF BU- BAU SUSTAIN PROJECT - SMALL | NE | CON | ENF | Critical Facilities Sustaining (Field) | CFS NE CON ENF BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS ENF BU- BAU SUSTAIN PROJECT - SMALL | NE | CON | ENF | Critical Facilities Sustaining (Field) | CFS NE CON ENF BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS ENF FIR BAU SUSTAIN PROJECT - SMALL3 | NE | CON | ENF | Critical Facilities Sustaining (Field) | CFS NE CON ENF FS-CFS Augment POR20 - 3 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS ENF FIR BAU SUSTAIN PROJECT - SMALL3 | NE | CON | ENF | Critical Facilities Sustaining (Field) | CFS NE CON ENF FS-CFS Augment POR20 - 3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS ENF SEC BAU SUSTAIN PROJECT - SMALL | NE | CON | ENF | Critical Facilities Sustaining (Field) | CFS NE CON ENF SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS ENF SEC BAU SUSTAIN PROJECT - SMALL | NE | CON | ENF | Critical Facilities Sustaining (Field) | CFS NE CON ENF SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS GLB BU- BAU SUSTAIN PROJECT - SMALL | NE | CON | GLB | Critical Facilities Sustaining (Field) | CFS NE CON GLB BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS GLB BU- BAU SUSTAIN PROJECT - SMALL | NE | CON | GLB | Critical Facilities Sustaining (Field) | CFS NE CON GLB BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS FSC HVC BAU SUSTAIN PROJECT - MEDIUM | CE | KAN | FSC | Critical Facilities Sustaining (Field) | CFS CE KAN FSC HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS FSC HVC BAU SUSTAIN PROJECT - MEDIUM | CE | KAN | FSC | Critical Facilities Sustaining (Field) | CFS CE KAN FSC HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS FSC SEC BAU SUSTAIN PROJECT - SMALL | CE | KAN | FSC | Critical Facilities Sustaining (Field) | CFS CE KAN FSC SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS FSC SEC BAU SUSTAIN PROJECT - SMALL | CE | KAN | FSC | Critical Facilities Sustaining (Field) | CFS CE KAN FSC SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS GBD HVC BAU SUSTAIN PROJECT - MEDIUM | CE | KAN | GBD | Critical Facilities Sustaining (Field) | CFS CE KAN GBD HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS GBD HVC BAU SUSTAIN PROJECT - MEDIUM | CE | KAN | GBD | Critical Facilities Sustaining (Field) | CFS CE KAN GBD HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS GBD LGT BAU SUSTAIN PROJECT - MEDIUM | CE | KAN | GBD | Critical Facilities Sustaining (Field) | CFS CE KAN GBD FF-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS GBD LGT BAU SUSTAIN PROJECT - MEDIUM | CE | KAN | GBD | Critical Facilities Sustaining (Field) | CFS CE KAN GBD FF-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS NWA BUP BAU SUSTAIN PROJECT - MEDIUM | CE | NWA | NWA | Critical Facilities Sustaining (Field) | CFS CE NWA NWA BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS NWA BUP BAU SUSTAIN PROJECT - MEDIUM | CE | NWA | NWA | Critical Facilities Sustaining (Field) | CFS CE NWA NWA BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS JCY HVC BAU SUSTAIN PROJECT - LARGE | CE | KAN | JCY | Critical Facilities Sustaining (Field) | CFS CE KAN JCY HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS JCY HVC BAU SUSTAIN PROJECT - LARGE | CE | KAN | JCY | Critical Facilities Sustaining (Field) | CFS CE KAN JCY HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS KCY RAI BAU SUSTAIN PROJECT - MEDIUM | COR | NAT | KCY | Critical Facilities Sustaining (Field) | CFS CE KAN KCY RK-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS KCY RAI BAU SUSTAIN PROJECT - MEDIUM | COR | NAT | KCY | Critical Facilities Sustaining (Field) | CFS CE KAN KCY RK-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS NWT HVC BAU SUSTAIN PROJECT - MEDIUM | CE | KAN | NWT | Critical Facilities Sustaining (Field) | CFS CE KAN NWT HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS NWT HVC BAU SUSTAIN PROJECT - MEDIUM | CE | KAN | NWT | Critical Facilities Sustaining (Field) | CFS CE KAN NWT HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PSN BUP BAU SUSTAIN PROJECT - MEDIUM | CE | KAN | PSN | Critical Facilities Sustaining (Field) | CFS CE KAN PSN BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PSN BUP BAU SUSTAIN PROJECT - MEDIUM | CE | KAN | PSN | Critical Facilities Sustaining (Field) | CFS CE KAN PSN BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS TUL BUP BAU SUSTAIN PROJECT - MEDIUM | CE | TUL | TUL | Critical Facilities Sustaining (Field) | CFS CE TUL TUL BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS TUL BUP BAU SUSTAIN PROJECT - MEDIUM | CE | TUL | TUL | Critical Facilities Sustaining (Field) | CFS CE TUL TUL BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS WLH GEN BAU SUSTAIN PROJECT - MEDIUM | CE | OKC | WLH | Critical Facilities Sustaining (Field) | CFS CE OKC WLH GN-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS WLH GEN BAU SUSTAIN PROJECT - MEDIUM | CE | OKC | WLH | Critical Facilities Sustaining (Field) | CFS CE OKC WLH GN-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS YAL SEC BAU SUSTAIN PROJECT - SMALL | CE | TUL | YAL | Critical Facilities Sustaining (Field) | CFS CE TUL YAL SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS YAL SEC BAU SUSTAIN PROJECT - SMALL | CE | TUL | YAL | Critical Facilities Sustaining (Field) | CFS CE TUL YAL SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS YAL BUP BAU SUSTAIN PROJECT - SMALL | CE | TUL | YAL | Critical Facilities Sustaining (Field) | CFS CE TUL YAL BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS YAL BUP BAU SUSTAIN PROJECT - SMALL | CE | TUL | YAL | Critical Facilities Sustaining (Field) | CFS CE TUL YAL BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS GRB GEN BAU SUSTAIN PROJECT - MEDIUM | NE | CON | GRB | Critical Facilities Sustaining (Field) | CFS NE CON GRB GN-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS GRB GEN BAU SUSTAIN PROJECT - MEDIUM | NE | CON | GRB | Critical Facilities Sustaining (Field) | CFS NE CON GRB GN-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS GRB SEC BAU SUSTAIN PROJECT - SMALL | NE | CON | GRB | Critical Facilities Sustaining (Field) | CFS NE CON GRB SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS GRB SEC BAU SUSTAIN PROJECT - SMALL | NE | CON | GRB | Critical Facilities Sustaining (Field) | CFS NE CON GRB SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS MAN FIR BAU SUSTAIN PROJECT - SMALL3 | NE | CON | MAN | Critical Facilities Sustaining (Field) | CFS NE CON MAN FS-CFS Augment POR20 - 3 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS MAN FIR BAU SUSTAIN PROJECT - SMALL3 | NE | CON | MAN | Critical Facilities Sustaining (Field) | CFS NE CON MAN FS-CFS Augment POR20 - 3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS MAN SEC BAU SUSTAIN PROJECT - SMALL | NE | CON | MAN | Critical Facilities Sustaining (Field) | CFS NE CON MAN SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS MAN SEC BAU SUSTAIN PROJECT - SMALL | NE | CON | MAN | Critical Facilities Sustaining (Field) | CFS NE CON MAN SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS MER ACP BAU SUSTAIN PROJECT - MEDIUM | NE | CON | MER | Critical Facilities Sustaining (Field) | CFS NE CON MER AC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS MER ACP BAU SUSTAIN PROJECT - MEDIUM | NE | CON | MER | Critical Facilities Sustaining (Field) | CFS NE CON MER AC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS MER ATS BAU SUSTAIN PROJECT - MEDIUM | NE | CON | MER | Critical Facilities Sustaining (Field) | CFS NE CON MER AT-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS MER ATS BAU SUSTAIN PROJECT - MEDIUM | NE | CON | MER | Critical Facilities Sustaining (Field) | CFS NE CON MER AT-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS MER FIR BAU SUSTAIN PROJECT - SMALL3 | NE | CON | MER | Critical Facilities Sustaining (Field) | CFS NE CON MER FS-CFS Augment POR20 - 3 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS MER FIR BAU SUSTAIN PROJECT - SMALL3 | NE | CON | MER | Critical Facilities Sustaining (Field) | CFS NE CON MER FS-CFS Augment POR20 - 3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS MER SEC BAU SUSTAIN PROJECT - SMALL | NE | CON | MER | Critical Facilities Sustaining (Field) | CFS NE CON MER SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS MER SEC BAU SUSTAIN PROJECT - SMALL | NE | CON | MER | Critical Facilities Sustaining (Field) | CFS NE CON MER SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS STF RUF BAU SUSTAIN PROJECT - MEDIUM | NE | CON | STF | Critical Facilities Sustaining (Field) | CFS NE CON STF RF-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS STF RUF BAU SUSTAIN PROJECT - MEDIUM | NE | CON | STF | Critical Facilities Sustaining (Field) | CFS NE CON STF RF-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS STF HVC BAU SUSTAIN PROJECT - MEDIUM | NE | CON | STF | Critical Facilities Sustaining (Field) | CFS NE CON STF HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS STF HVC BAU SUSTAIN PROJECT - MEDIUM | NE | CON | STF | Critical Facilities Sustaining (Field) | CFS NE CON STF HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS RKH GEN BAU SUSTAIN PROJECT - MEDIUM | NE | CON | RKH | Critical Facilities Sustaining (Field) | CFS NE CON RKH GN-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS RKH GEN BAU SUSTAIN PROJECT - MEDIUM | NE | CON | RKH | Critical Facilities Sustaining (Field) | CFS NE CON RKH GN-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS RKH BU- BAU SUSTAIN PROJECT - SMALL | NE | CON | RKH | Critical Facilities Sustaining (Field) | CFS NE CON RKH BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS RKH BU- BAU SUSTAIN PROJECT - SMALL | NE | CON | RKH | Critical Facilities Sustaining (Field) | CFS NE CON RKH BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS RKH FIR BAU SUSTAIN PROJECT - SMALL3 | NE | CON | RKH | Critical Facilities Sustaining (Field) | CFS NE CON RKH FS-CFS Augment POR20 - 3 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS RKH FIR BAU SUSTAIN PROJECT - SMALL3 | NE | CON | RKH | Critical Facilities Sustaining (Field) | CFS NE CON RKH FS-CFS Augment POR20 - 3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS RKH SEC BAU SUSTAIN PROJECT - SMALL | NE | CON | RKH | Critical Facilities Sustaining (Field) | CFS NE CON RKH SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS RKH SEC BAU SUSTAIN PROJECT - SMALL | NE | CON | RKH | Critical Facilities Sustaining (Field) | CFS NE CON RKH SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS STN BAT BAU SUSTAIN PROJECT - MEDIUM | NE | CON | STN | Critical Facilities Sustaining (Field) | CFS NE CON STN BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS STN BAT BAU SUSTAIN PROJECT - MEDIUM | NE | CON | STN | Critical Facilities Sustaining (Field) | CFS NE CON STN BS-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS STN BAT BAU SUSTAIN PROJECT - MEDIUM2 | NE | CON | STN | Critical Facilities Sustaining (Field) | CFS NE CON STN BS-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS STN BAT BAU SUSTAIN PROJECT - MEDIUM2 | NE | CON | STN | Critical Facilities Sustaining (Field) | CFS NE CON STN BS-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PAW HVC BAU SUSTAIN PROJECT - MEDIUM | NE | RHD | PAW | Critical Facilities Sustaining (Field) | CFS NE RHD PAW HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PAW HVC BAU SUSTAIN PROJECT - MEDIUM | NE | RHD | PAW | Critical Facilities Sustaining (Field) | CFS NE RHD PAW HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PAW SEC BAU SUSTAIN PROJECT - SMALL | NE | RHD | PAW | Critical Facilities Sustaining (Field) | CFS NE RHD PAW SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PAW SEC BAU SUSTAIN PROJECT - SMALL | NE | RHD | PAW | Critical Facilities Sustaining (Field) | CFS NE RHD PAW SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS GRB ATS BAU SUSTAIN PROJECT - MEDIUM | NE | CON | GRB | Critical Facilities Sustaining (Field) | CFS NE CON GRB AT-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS GRB ATS BAU SUSTAIN PROJECT - MEDIUM | NE | CON | GRB | Critical Facilities Sustaining (Field) | CFS NE CON GRB AT-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS STN SEC BAU SUSTAIN PROJECT - SMALL | NE | CON | STN | Critical Facilities Sustaining (Field) | CFS NE CON STN SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS STN SEC BAU SUSTAIN PROJECT - SMALL | NE | CON | STN | Critical Facilities Sustaining (Field) | CFS NE CON STN SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS SFD SEC BAU SUSTAIN PROJECT - SMALL | NE | CON | SFD | Critical Facilities Sustaining (Field) | CFS NE CON SFD SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS SFD SEC BAU SUSTAIN PROJECT - SMALL | NE | CON | SFD | Critical Facilities Sustaining (Field) | CFS NE CON SFD SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS BUR BU- BAU SUSTAIN PROJECT - SMALL | NE | RHD | BUR | Critical Facilities Sustaining (Field) | CFS NE RHD BUR BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS BUR BU- BAU SUSTAIN PROJECT - SMALL | NE | RHD | BUR | Critical Facilities Sustaining (Field) | CFS NE RHD BUR BU-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS BUR GEN BAU SUSTAIN PROJECT - MEDIUM | NE | RHD | BUR | Critical Facilities Sustaining (Field) | CFS NE RHD BUR GN-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS BUR GEN BAU SUSTAIN PROJECT - MEDIUM | NE | RHD | BUR | Critical Facilities Sustaining (Field) | CFS NE RHD BUR GN-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS BUR ATS BAU SUSTAIN PROJECT - MEDIUM | NE | RHD | BUR | Critical Facilities Sustaining (Field) | CFS NE RHD BUR AT-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS BUR ATS BAU SUSTAIN PROJECT - MEDIUM | NE | RHD | BUR | Critical Facilities Sustaining (Field) | CFS NE RHD BUR AT-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS BUR SEC BAU SUSTAIN PROJECT - SMALL | NE | RHD | BUR | Critical Facilities Sustaining (Field) | CFS NE RHD BUR SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS BUR SEC BAU SUSTAIN PROJECT - SMALL | NE | RHD | BUR | Critical Facilities Sustaining (Field) | CFS NE RHD BUR SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CRN SEC BAU SUSTAIN PROJECT - SMALL | NE | RHD | CRN | Critical Facilities Sustaining (Field) | CFS NE RHD CRN SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS CRN SEC BAU SUSTAIN PROJECT - SMALL | NE | RHD | CRN | Critical Facilities Sustaining (Field) | CFS NE RHD CRN SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CRN FIR BAU SUSTAIN PROJECT - SMALL2 | NE | RHD | CRN | Critical Facilities Sustaining (Field) | CFS NE RHD CRN FS-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS CRN FIR BAU SUSTAIN PROJECT - SMALL2 | NE | RHD | CRN | Critical Facilities Sustaining (Field) | CFS NE RHD CRN FS-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS EXT LMI BAU SUSTAIN PROJECT - MEDIUM | NE | RHD | EXT | Critical Facilities Sustaining (Field) | CFS NE RHD EXT LM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS EXT LMI BAU SUSTAIN PROJECT - MEDIUM | NE | RHD | EXT | Critical Facilities Sustaining (Field) | CFS NE RHD EXT LM-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS EXT SEC BAU SUSTAIN PROJECT - SMALL | NE | RHD | EXT | Critical Facilities Sustaining (Field) | CFS NE RHD EXT SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS EXT SEC BAU SUSTAIN PROJECT - SMALL | NE | RHD | EXT | Critical Facilities Sustaining (Field) | CFS NE RHD EXT SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS EXT FIR BAU SUSTAIN PROJECT - SMALL3 | NE | RHD | EXT | Critical Facilities Sustaining (Field) | CFS NE RHD EXT FS-CFS Augment POR20 - 3 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS EXT FIR BAU SUSTAIN PROJECT - SMALL3 | NE | RHD | EXT | Critical Facilities Sustaining (Field) | CFS NE RHD EXT FS-CFS Augment POR20 - 3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS LNC GEN BAU SUSTAIN PROJECT - MEDIUM | NE | RHD | LNC | Critical Facilities Sustaining (Field) | CFS NE RHD LNC GN-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS LNC GEN BAU SUSTAIN PROJECT - MEDIUM | NE | RHD | LNC | Critical Facilities Sustaining (Field) | CFS NE RHD LNC GN-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS LNC SEC BAU SUSTAIN PROJECT - SMALL | NE | RHD | LNC | Critical Facilities Sustaining (Field) | CFS NE RHD LNC SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS LNC SEC BAU SUSTAIN PROJECT - SMALL | NE | RHD | LNC | Critical Facilities Sustaining (Field) | CFS NE RHD LNC SC-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS LNC FIR BAU SUSTAIN PROJECT - SMALL3 | NE | RHD | LNC | Critical Facilities Sustaining (Field) | CFS NE RHD LNC FS-CFS Augment POR20 - 3 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS LNC FIR BAU SUSTAIN PROJECT - SMALL3 | NE | RHD | LNC | Critical Facilities Sustaining (Field) | CFS NE RHD LNC FS-CFS Augment POR20 - 3 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS PAW GEN BAU SUSTAIN PROJECT - MEDIUM | NE | RHD | PAW | Critical Facilities Sustaining (Field) | CFS NE RHD PAW GN-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS PAW GEN BAU SUSTAIN PROJECT - MEDIUM | NE | RHD | PAW | Critical Facilities Sustaining (Field) | CFS NE RHD PAW GN-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CE KAN DCY BU-CFS Augment POR20 | CE | KAN | DCY | Critical Facilities Sustaining (Field) | CFS CE KAN DCY BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE KAN DCY BU-CFS Augment POR20 | CE | KAN | DCY | Critical Facilities Sustaining (Field) | CFS CE KAN DCY BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE KAN DCY HV-CFS Augment POR20 | CE | KAN | DCY | Critical Facilities Sustaining (Field) | CFS CE KAN DCY HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE KAN DCY HV-CFS Augment POR20 | CE | KAN | DCY | Critical Facilities Sustaining (Field) | CFS CE KAN DCY HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE KAN GBD FF-CFS Augment POR20 | CE | KAN | GBD | Critical Facilities Sustaining (Field) | CFS CE KAN GBD FF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE KAN GBD FF-CFS Augment POR20 | CE | KAN | GBD | Critical Facilities Sustaining (Field) | CFS CE KAN GBD FF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE KAN GBD HV-CFS Augment POR20 | CE | KAN | GBD | Critical Facilities Sustaining (Field) | CFS CE KAN GBD HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE KAN GBD HV-CFS Augment POR20 | CE | KAN | GBD | Critical Facilities Sustaining (Field) | CFS CE KAN GBD HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE KAN GDY HV-CFS Augment POR20 | CE | KAN | GDY | Critical Facilities Sustaining (Field) | CFS CE KAN GDY HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE KAN GDY HV-CFS Augment POR20 | CE | KAN | GDY | Critical Facilities Sustaining (Field) | CFS CE KAN GDY HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE KAN JCY HV-CFS Augment POR20 | CE | KAN | JCY | Critical Facilities Sustaining (Field) | CFS CE KAN JCY HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE KAN JCY HV-CFS Augment POR20 | CE | KAN | JCY | Critical Facilities Sustaining (Field) | CFS CE KAN JCY HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE KAN NWT HV-CFS Augment POR20 | CE | KAN | NWT | Critical Facilities Sustaining (Field) | CFS CE KAN NWT HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE KAN NWT HV-CFS Augment POR20 | CE | KAN | NWT | Critical Facilities Sustaining (Field) | CFS CE KAN NWT HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE KAN TOP FF-CFS Augment POR20 | CE | KAN | TOP | Critical Facilities Sustaining (Field) | CFS CE KAN TOP FF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE KAN TOP FF-CFS Augment POR20 | CE | KAN | TOP | Critical Facilities Sustaining (Field) | CFS CE KAN TOP FF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE KAN WIC HV-CFS Augment POR20 | CE | KAN | WIC | Critical Facilities Sustaining (Field) | CFS CE KAN WIC HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE KAN WIC HV-CFS Augment POR20 | CE | KAN | WIC | Critical Facilities Sustaining (Field) | CFS CE KAN WIC HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE NWA BVL BU-CFS Augment POR20 | CE | NWA | BVL | Critical Facilities Sustaining (Field) | CFS CE NWA BVL BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE NWA BVL BU-CFS Augment POR20 | CE | NWA | BVL | Critical Facilities Sustaining (Field) | CFS CE NWA BVL BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE NWA BVL HV-CFS Augment POR20 | CE | NWA | BVL | Critical Facilities Sustaining (Field) | CFS CE NWA BVL HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE NWA BVL HV-CFS Augment POR20 | CE | NWA | BVL | Critical Facilities Sustaining (Field) | CFS CE NWA BVL HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE NWA BVL LM-CFS Augment POR20 | CE | NWA | BVL | Critical Facilities Sustaining (Field) | CFS CE NWA BVL LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE NWA BVL LM-CFS Augment POR20 | CE | NWA | BVL | Critical Facilities Sustaining (Field) | CFS CE NWA BVL LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE NWA FAY BD-CFS Augment POR20 | CE | NWA | FAY | Critical Facilities Sustaining (Field) | CFS CE NWA FAY BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE NWA FAY BD-CFS Augment POR20 | CE | NWA | FAY | Critical Facilities Sustaining (Field) | CFS CE NWA FAY BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE KAN FSC BU-CFS Augment POR20 | CE | KAN | FSC | Critical Facilities Sustaining (Field) | CFS CE KAN FSC BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE KAN FSC BU-CFS Augment POR20 | CE | KAN | FSC | Critical Facilities Sustaining (Field) | CFS CE KAN FSC BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE KAN FSC HV-CFS Augment POR20 | CE | KAN | FSC | Critical Facilities Sustaining (Field) | CFS CE KAN FSC HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE KAN FSC HV-CFS Augment POR20 | CE | KAN | FSC | Critical Facilities Sustaining (Field) | CFS CE KAN FSC HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE KAN FSC SC-CFS Augment POR20 | CE | KAN | FSC | Critical Facilities Sustaining (Field) | CFS CE KAN FSC SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE KAN FSC SC-CFS Augment POR20 | CE | KAN | FSC | Critical Facilities Sustaining (Field) | CFS CE KAN FSC SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE NWA NWA BU-CFS Augment POR20 | CE | NWA | NWA | Critical Facilities Sustaining (Field) | CFS CE NWA NWA BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE NWA NWA BU-CFS Augment POR20 | CE | NWA | NWA | Critical Facilities Sustaining (Field) | CFS CE NWA NWA BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE NWA NWA HV-CFS Augment POR20 | CE | NWA | NWA | Critical Facilities Sustaining (Field) | CFS CE NWA NWA HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE NWA NWA HV-CFS Augment POR20 | CE | NWA | NWA | Critical Facilities Sustaining (Field) | CFS CE NWA NWA HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE KAN PIT HV-CFS Augment POR20 | CE | KAN | PIT | Critical Facilities Sustaining (Field) | CFS CE KAN PIT HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE KAN PIT HV-CFS Augment POR20 | CE | KAN | PIT | Critical Facilities Sustaining (Field) | CFS CE KAN PIT HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE KAN PIT RF-CFS Augment POR20 | CE | KAN | PIT | Critical Facilities Sustaining (Field) | CFS CE KAN PIT RF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE KAN PIT RF-CFS Augment POR20 | CE | KAN | PIT | Critical Facilities Sustaining (Field) | CFS CE KAN PIT RF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE KAN PIT SC-CFS Augment POR20 | CE | KAN | PIT | Critical Facilities Sustaining (Field) | CFS CE KAN PIT SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE KAN PIT SC-CFS Augment POR20 | CE | KAN | PIT | Critical Facilities Sustaining (Field) | CFS CE KAN PIT SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE KAN PSN BU-CFS Augment POR20 | CE | KAN | PSN | Critical Facilities Sustaining (Field) | CFS CE KAN PSN BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE KAN PSN BU-CFS Augment POR20 | CE | KAN | PSN | Critical Facilities Sustaining (Field) | CFS CE KAN PSN BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE KAN PSN FF-CFS Augment POR20 | CE | KAN | PSN | Critical Facilities Sustaining (Field) | CFS CE KAN PSN FF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE KAN PSN FF-CFS Augment POR20 | CE | KAN | PSN | Critical Facilities Sustaining (Field) | CFS CE KAN PSN FF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE KAN PSN HV-CFS Augment POR20 | CE | KAN | PSN | Critical Facilities Sustaining (Field) | CFS CE KAN PSN HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE KAN PSN HV-CFS Augment POR20 | CE | KAN | PSN | Critical Facilities Sustaining (Field) | CFS CE KAN PSN HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE KAN PSN LM-CFS Augment POR20 | CE | KAN | PSN | Critical Facilities Sustaining (Field) | CFS CE KAN PSN LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE KAN PSN LM-CFS Augment POR20 | CE | KAN | PSN | Critical Facilities Sustaining (Field) | CFS CE KAN PSN LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE KAN PSN SC-CFS Augment POR20 | CE | KAN | PSN | Critical Facilities Sustaining (Field) | CFS CE KAN PSN SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE KAN PSN SC-CFS Augment POR20 | CE | KAN | PSN | Critical Facilities Sustaining (Field) | CFS CE KAN PSN SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE KAN SDN HV-CFS Augment POR20 | CE | KAN | SDN | Critical Facilities Sustaining (Field) | CFS CE KAN SDN HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE KAN SDN HV-CFS Augment POR20 | CE | KAN | SDN | Critical Facilities Sustaining (Field) | CFS CE KAN SDN HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE OKC CHO BU-CFS Augment POR20 | CE | OKC | CHO | Critical Facilities Sustaining (Field) | CFS CE OKC CHO BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE OKC CHO BU-CFS Augment POR20 | CE | OKC | CHO | Critical Facilities Sustaining (Field) | CFS CE OKC CHO BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE OKC CHO RK-CFS Augment POR20 | CE | OKC | CHO | Critical Facilities Sustaining (Field) | CFS CE OKC CHO RK-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE OKC CHO RK-CFS Augment POR20 | CE | OKC | CHO | Critical Facilities Sustaining (Field) | CFS CE OKC CHO RK-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE OKC MOO BU-CFS Augment POR20 | CE | OKC | MOO | Critical Facilities Sustaining (Field) | CFS CE OKC MOO BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE OKC MOO BU-CFS Augment POR20 | CE | OKC | MOO | Critical Facilities Sustaining (Field) | CFS CE OKC MOO BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE OKC MOO HV-CFS Augment POR20 | CE | OKC | MOO | Critical Facilities Sustaining (Field) | CFS CE OKC MOO HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE OKC MOO HV-CFS Augment POR20 | CE | OKC | MOO | Critical Facilities Sustaining (Field) | CFS CE OKC MOO HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE OKC NEH GN-CFS Augment POR20 | CE | OKC | NEH | Critical Facilities Sustaining (Field) | CFS CE OKC NEH GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE OKC NEH GN-CFS Augment POR20 | CE | OKC | NEH | Critical Facilities Sustaining (Field) | CFS CE OKC NEH GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE OKC NOR GN-CFS Augment POR20 | CE | OKC | NOR | Critical Facilities Sustaining (Field) | CFS CE OKC NOR GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE OKC NOR GN-CFS Augment POR20 | CE | OKC | NOR | Critical Facilities Sustaining (Field) | CFS CE OKC NOR GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE OKC OKC BD-CFS Augment POR20 | CE | OKC | OKC | Critical Facilities Sustaining (Field) | CFS CE OKC OKC BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE OKC OKC BD-CFS Augment POR20 | CE | OKC | OKC | Critical Facilities Sustaining (Field) | CFS CE OKC OKC BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE OKC OKC HV-CFS Augment POR20 | CE | OKC | OKC | Critical Facilities Sustaining (Field) | CFS CE OKC OKC HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE OKC OKC HV-CFS Augment POR20 | CE | OKC | OKC | Critical Facilities Sustaining (Field) | CFS CE OKC OKC HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE OKC OKC HV-CFS Augment POR20 - 2 | CE | OKC | OKC | Critical Facilities Sustaining (Field) | CFS CE OKC OKC HV-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE OKC OKC HV-CFS Augment POR20 - 2 | CE | OKC | OKC | Critical Facilities Sustaining (Field) | CFS CE OKC OKC HV-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE OKC WLH GN-CFS Augment POR20 | CE | OKC | WLH | Critical Facilities Sustaining (Field) | CFS CE OKC WLH GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE OKC WLH GN-CFS Augment POR20 | CE | OKC | WLH | Critical Facilities Sustaining (Field) | CFS CE OKC WLH GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE OMA BLV FF-CFS Augment POR20 | CE | OMA | BLV | Critical Facilities Sustaining (Field) | CFS CE OMA BLV FF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE OMA BLV FF-CFS Augment POR20 | CE | OMA | BLV | Critical Facilities Sustaining (Field) | CFS CE OMA BLV FF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE OMA BLV HV-CFS Augment POR20 | CE | OMA | BLV | Critical Facilities Sustaining (Field) | CFS CE OMA BLV HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE OMA BLV HV-CFS Augment POR20 | CE | OMA | BLV | Critical Facilities Sustaining (Field) | CFS CE OMA BLV HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE OMA CBL FF-CFS Augment POR20 | CE | OMA | CBL | Critical Facilities Sustaining (Field) | CFS CE OMA CBL FF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE OMA CBL FF-CFS Augment POR20 | CE | OMA | CBL | Critical Facilities Sustaining (Field) | CFS CE OMA CBL FF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE OMA ELK FF-CFS Augment POR20 | CE | OMA | ELK | Critical Facilities Sustaining (Field) | CFS CE OMA ELK FF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE OMA ELK FF-CFS Augment POR20 | CE | OMA | ELK | Critical Facilities Sustaining (Field) | CFS CE OMA ELK FF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE OMA ELK HV-CFS Augment POR20 | CE | OMA | ELK | Critical Facilities Sustaining (Field) | CFS CE OMA ELK HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE OMA ELK HV-CFS Augment POR20 | CE | OMA | ELK | Critical Facilities Sustaining (Field) | CFS CE OMA ELK HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE KAN KCY RK-CFS Augment POR20 | COR | NAT | KCY | Critical Facilities Sustaining (Field) | CFS CE KAN KCY RK-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE KAN KCY RK-CFS Augment POR20 | COR | NAT | KCY | Critical Facilities Sustaining (Field) | CFS CE KAN KCY RK-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE OMA OMM BD-CFS Augment POR20 | CE | OMA | OMM | Critical Facilities Sustaining (Field) | CFS CE OMA OMM BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE OMA OMM BD-CFS Augment POR20 | CE | OMA | OMM | Critical Facilities Sustaining (Field) | CFS CE OMA OMM BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE OMA OMM FS-CFS Augment POR20 | CE | OMA | OMM | Critical Facilities Sustaining (Field) | CFS CE OMA OMM FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE OMA OMM FS-CFS Augment POR20 | CE | OMA | OMM | Critical Facilities Sustaining (Field) | CFS CE OMA OMM FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE OMA ONA BD-CFS Augment POR20 | CE | OMA | ONA | Critical Facilities Sustaining (Field) | CFS CE OMA ONA BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE OMA ONA BD-CFS Augment POR20 | CE | OMA | ONA | Critical Facilities Sustaining (Field) | CFS CE OMA ONA BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE OMA ONA BU-CFS Augment POR20 | CE | OMA | ONA | Critical Facilities Sustaining (Field) | CFS CE OMA ONA BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE OMA ONA BU-CFS Augment POR20 | CE | OMA | ONA | Critical Facilities Sustaining (Field) | CFS CE OMA ONA BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE OMA ONA FF-CFS Augment POR20 | CE | OMA | ONA | Critical Facilities Sustaining (Field) | CFS CE OMA ONA FF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE OMA ONA FF-CFS Augment POR20 | CE | OMA | ONA | Critical Facilities Sustaining (Field) | CFS CE OMA ONA FF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE OMA SOU BU-CFS Augment POR20 | CE | OMA | SOU | Critical Facilities Sustaining (Field) | CFS CE OMA SOU BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE OMA SOU BU-CFS Augment POR20 | CE | OMA | SOU | Critical Facilities Sustaining (Field) | CFS CE OMA SOU BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE OMA SOU FF-CFS Augment POR20 | CE | OMA | SOU | Critical Facilities Sustaining (Field) | CFS CE OMA SOU FF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE OMA SOU FF-CFS Augment POR20 | CE | OMA | SOU | Critical Facilities Sustaining (Field) | CFS CE OMA SOU FF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE OMA SOU HV-CFS Augment POR20 | CE | OMA | SOU | Critical Facilities Sustaining (Field) | CFS CE OMA SOU HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE OMA SOU HV-CFS Augment POR20 | CE | OMA | SOU | Critical Facilities Sustaining (Field) | CFS CE OMA SOU HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE OMA WES BU-CFS Augment POR20 | CE | OMA | WES | Critical Facilities Sustaining (Field) | CFS CE OMA WES BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE OMA WES BU-CFS Augment POR20 | CE | OMA | WES | Critical Facilities Sustaining (Field) | CFS CE OMA WES BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE OMA WES HV-CFS Augment POR20 | CE | OMA | WES | Critical Facilities Sustaining (Field) | CFS CE OMA WES HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE OMA WES HV-CFS Augment POR20 | CE | OMA | WES | Critical Facilities Sustaining (Field) | CFS CE OMA WES HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE TUL BRD BS-CFS Augment POR20 | CE | TUL | BRD | Critical Facilities Sustaining (Field) | CFS CE TUL BRD BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE TUL BRD BS-CFS Augment POR20 | CE | TUL | BRD | Critical Facilities Sustaining (Field) | CFS CE TUL BRD BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE TUL DTN BS-CFS Augment POR20 | CE | TUL | DTN | Critical Facilities Sustaining (Field) | CFS CE TUL DTN BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE TUL DTN BS-CFS Augment POR20 | CE | TUL | DTN | Critical Facilities Sustaining (Field) | CFS CE TUL DTN BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE TUL OWA BU-CFS Augment POR20 | CE | TUL | OWA | Critical Facilities Sustaining (Field) | CFS CE TUL OWA BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE TUL OWA BU-CFS Augment POR20 | CE | TUL | OWA | Critical Facilities Sustaining (Field) | CFS CE TUL OWA BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE TUL OWA BU-CFS Augment POR20 - 2 | CE | TUL | OWA | Critical Facilities Sustaining (Field) | CFS CE TUL OWA BU-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE TUL OWA BU-CFS Augment POR20 - 2 | CE | TUL | OWA | Critical Facilities Sustaining (Field) | CFS CE TUL OWA BU-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE TUL OWA GN-CFS Augment POR20 | CE | TUL | OWA | Critical Facilities Sustaining (Field) | CFS CE TUL OWA GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE TUL OWA GN-CFS Augment POR20 | CE | TUL | OWA | Critical Facilities Sustaining (Field) | CFS CE TUL OWA GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE TUL QNC BU-CFS Augment POR20 | CE | TUL | QNC | Critical Facilities Sustaining (Field) | CFS CE TUL QNC BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE TUL QNC BU-CFS Augment POR20 | CE | TUL | QNC | Critical Facilities Sustaining (Field) | CFS CE TUL QNC BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE TUL QNC BD-CFS Augment POR20 | CE | TUL | QNC | Critical Facilities Sustaining (Field) | CFS CE TUL QNC BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE TUL QNC BD-CFS Augment POR20 | CE | TUL | QNC | Critical Facilities Sustaining (Field) | CFS CE TUL QNC BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE TUL SAP BU-CFS Augment POR20 | CE | TUL | SAP | Critical Facilities Sustaining (Field) | CFS CE TUL SAP BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE TUL SAP BU-CFS Augment POR20 | CE | TUL | SAP | Critical Facilities Sustaining (Field) | CFS CE TUL SAP BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE TUL TUL BS-CFS Augment POR20 | CE | TUL | TUL | Critical Facilities Sustaining (Field) | CFS CE TUL TUL BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE TUL TUL BS-CFS Augment POR20 | CE | TUL | TUL | Critical Facilities Sustaining (Field) | CFS CE TUL TUL BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE TUL TUL BU-CFS Augment POR20 | CE | TUL | TUL | Critical Facilities Sustaining (Field) | CFS CE TUL TUL BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE TUL TUL BU-CFS Augment POR20 | CE | TUL | TUL | Critical Facilities Sustaining (Field) | CFS CE TUL TUL BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE TUL YAL BU-CFS Augment POR20 | CE | TUL | YAL | Critical Facilities Sustaining (Field) | CFS CE TUL YAL BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE TUL YAL BU-CFS Augment POR20 | CE | TUL | YAL | Critical Facilities Sustaining (Field) | CFS CE TUL YAL BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE TUL YAL SC-CFS Augment POR20 | CE | TUL | YAL | Critical Facilities Sustaining (Field) | CFS CE TUL YAL SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE TUL YAL SC-CFS Augment POR20 | CE | TUL | YAL | Critical Facilities Sustaining (Field) | CFS CE TUL YAL SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD WWK BU-CFS Augment POR20 | NE | RHD | WWK | Critical Facilities Sustaining (Field) | CFS NE RHD WWK BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD WWK BU-CFS Augment POR20 | NE | RHD | WWK | Critical Facilities Sustaining (Field) | CFS NE RHD WWK BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD WWK FS-CFS Augment POR20 - 1 | NE | RHD | WWK | Critical Facilities Sustaining (Field) | CFS NE RHD WWK FS-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD WWK FS-CFS Augment POR20 - 1 | NE | RHD | WWK | Critical Facilities Sustaining (Field) | CFS NE RHD WWK FS-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD WWK LM-CFS Augment POR20 | NE | RHD | WWK | Critical Facilities Sustaining (Field) | CFS NE RHD WWK LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD WWK LM-CFS Augment POR20 | NE | RHD | WWK | Critical Facilities Sustaining (Field) | CFS NE RHD WWK LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD WWK FS-CFS Augment POR20 - 2 | NE | RHD | WWK | Critical Facilities Sustaining (Field) | CFS NE RHD WWK FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD WWK FS-CFS Augment POR20 - 2 | NE | RHD | WWK | Critical Facilities Sustaining (Field) | CFS NE RHD WWK FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD WWK FS-CFS Augment POR20 - 3 | NE | RHD | WWK | Critical Facilities Sustaining (Field) | CFS NE RHD WWK FS-CFS Augment POR20 - 3 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD WWK FS-CFS Augment POR20 - 3 | NE | RHD | WWK | Critical Facilities Sustaining (Field) | CFS NE RHD WWK FS-CFS Augment POR20 - 3 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD WWK SC-CFS Augment POR20 | NE | RHD | WWK | Critical Facilities Sustaining (Field) | CFS NE RHD WWK SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD WWK SC-CFS Augment POR20 | NE | RHD | WWK | Critical Facilities Sustaining (Field) | CFS NE RHD WWK SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD PRV BU-CFS Augment POR20 | NE | RHD | PRV | Critical Facilities Sustaining (Field) | CFS NE RHD PRV BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD PRV BU-CFS Augment POR20 | NE | RHD | PRV | Critical Facilities Sustaining (Field) | CFS NE RHD PRV BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD PRV FS-CFS Augment POR20 | NE | RHD | PRV | Critical Facilities Sustaining (Field) | CFS NE RHD PRV FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD PRV FS-CFS Augment POR20 | NE | RHD | PRV | Critical Facilities Sustaining (Field) | CFS NE RHD PRV FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD PRV LM-CFS Augment POR20 | NE | RHD | PRV | Critical Facilities Sustaining (Field) | CFS NE RHD PRV LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD PRV LM-CFS Augment POR20 | NE | RHD | PRV | Critical Facilities Sustaining (Field) | CFS NE RHD PRV LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD PRV FS-CFS Augment POR20 - 2 | NE | RHD | PRV | Critical Facilities Sustaining (Field) | CFS NE RHD PRV FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD PRV FS-CFS Augment POR20 - 2 | NE | RHD | PRV | Critical Facilities Sustaining (Field) | CFS NE RHD PRV FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD PRV AC-CFS Augment POR20 | NE | RHD | PRV | Critical Facilities Sustaining (Field) | CFS NE RHD PRV AC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD PRV AC-CFS Augment POR20 | NE | RHD | PRV | Critical Facilities Sustaining (Field) | CFS NE RHD PRV AC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD EXT FS-CFS Augment POR20 - 1 | NE | RHD | EXT | Critical Facilities Sustaining (Field) | CFS NE RHD EXT FS-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD EXT FS-CFS Augment POR20 - 1 | NE | RHD | EXT | Critical Facilities Sustaining (Field) | CFS NE RHD EXT FS-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD BUR AT-CFS Augment POR19 | NE | RHD | EXT | Critical Facilities Sustaining (Field) | CFS NE RHD BUR AT-CFS Augment POR19 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS NE RHD BUR AT-CFS Augment POR19 | NE | RHD | EXT | Critical Facilities Sustaining (Field) | CFS NE RHD BUR AT-CFS Augment POR19 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Deleted | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD BUR AT-CFS Augment POR19 | NE | RHD | EXT | Critical Facilities Sustaining (Field) | CFS NE RHD BUR AT-CFS Augment POR19 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS NE RHD EXT FS-CFS Augment POR20 - 2 | NE | RHD | EXT | Critical Facilities Sustaining (Field) | CFS NE RHD EXT FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD EXT FS-CFS Augment POR20 - 2 | NE | RHD | EXT | Critical Facilities Sustaining (Field) | CFS NE RHD EXT FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD EXT RK-CFS Augment POR20 | NE | RHD | EXT | Critical Facilities Sustaining (Field) | CFS NE RHD EXT RK-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD EXT RK-CFS Augment POR20 | NE | RHD | EXT | Critical Facilities Sustaining (Field) | CFS NE RHD EXT RK-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD EXT SC-CFS Augment POR20 | NE | RHD | EXT | Critical Facilities Sustaining (Field) | CFS NE RHD EXT SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD EXT SC-CFS Augment POR20 | NE | RHD | EXT | Critical Facilities Sustaining (Field) | CFS NE RHD EXT SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD EXT FS-CFS Augment POR20 - 3 | NE | RHD | EXT | Critical Facilities Sustaining (Field) | CFS NE RHD EXT FS-CFS Augment POR20 - 3 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD EXT FS-CFS Augment POR20 - 3 | NE | RHD | EXT | Critical Facilities Sustaining (Field) | CFS NE RHD EXT FS-CFS Augment POR20 - 3 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD RMD FS-CFS Augment POR20 - 1 | NE | RHD | RMD | Critical Facilities Sustaining (Field) | CFS NE RHD RMD FS-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD RMD FS-CFS Augment POR20 - 1 | NE | RHD | RMD | Critical Facilities Sustaining (Field) | CFS NE RHD RMD FS-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD RMD FS-CFS Augment POR20 - 2 | NE | RHD | RMD | Critical Facilities Sustaining (Field) | CFS NE RHD RMD FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD RMD FS-CFS Augment POR20 - 2 | NE | RHD | RMD | Critical Facilities Sustaining (Field) | CFS NE RHD RMD FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD RMD GN-CFS Augment POR20 | NE | RHD | RMD | Critical Facilities Sustaining (Field) | CFS NE RHD RMD GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD RMD GN-CFS Augment POR20 | NE | RHD | RMD | Critical Facilities Sustaining (Field) | CFS NE RHD RMD GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD RMD SC-CFS Augment POR20 | NE | RHD | RMD | Critical Facilities Sustaining (Field) | CFS NE RHD RMD SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD RMD SC-CFS Augment POR20 | NE | RHD | RMD | Critical Facilities Sustaining (Field) | CFS NE RHD RMD SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD RMD FS-CFS Augment POR20 - 3 | NE | RHD | RMD | Critical Facilities Sustaining (Field) | CFS NE RHD RMD FS-CFS Augment POR20 - 3 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD RMD FS-CFS Augment POR20 - 3 | NE | RHD | RMD | Critical Facilities Sustaining (Field) | CFS NE RHD RMD FS-CFS Augment POR20 - 3 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD CRN HV-CFS Augment POR20 | NE | RHD | CRN | Critical Facilities Sustaining (Field) | CFS NE RHD CRN HV-CFS Augment POR20 - 3 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD CRN HV-CFS Augment POR20 | NE | RHD | CRN | Critical Facilities Sustaining (Field) | CFS NE RHD CRN HV-CFS Augment POR20 - 3 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD CRN HV-CFS Augment POR20 | NE | RHD | CRN | Critical Facilities Sustaining (Field) | CFS NE RHD CRN HV-CFS Augment POR20 - 3 | Labor | No Equipment |  |  |  |  | Active | Log | Del | SB-0105 | New | Canceled | 2020-04-17 13:54 | Project names need to be updated
CFS NE RHD CRN FS-CFS Augment POR20 | NE | RHD | CRN | Critical Facilities Sustaining (Field) | CFS NE RHD CRN FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD CRN FS-CFS Augment POR20 | NE | RHD | CRN | Critical Facilities Sustaining (Field) | CFS NE RHD CRN FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD CRN FS-CFS Augment POR20 - 2 | NE | RHD | CRN | Critical Facilities Sustaining (Field) | CFS NE RHD CRN FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD CRN FS-CFS Augment POR20 - 2 | NE | RHD | CRN | Critical Facilities Sustaining (Field) | CFS NE RHD CRN FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD CRN SC-CFS Augment POR20 | NE | RHD | CRN | Critical Facilities Sustaining (Field) | CFS NE RHD CRN SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD CRN SC-CFS Augment POR20 | NE | RHD | CRN | Critical Facilities Sustaining (Field) | CFS NE RHD CRN SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD LNC FS-CFS Augment POR20 - 1 | NE | RHD | LNC | Critical Facilities Sustaining (Field) | CFS NE RHD LNC FS-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD LNC FS-CFS Augment POR20 - 1 | NE | RHD | LNC | Critical Facilities Sustaining (Field) | CFS NE RHD LNC FS-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD LNC FS-CFS Augment POR20 - 2 | NE | RHD | LNC | Critical Facilities Sustaining (Field) | CFS NE RHD LNC FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD LNC FS-CFS Augment POR20 - 2 | NE | RHD | LNC | Critical Facilities Sustaining (Field) | CFS NE RHD LNC FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD LNC GN-CFS Augment POR20 | NE | RHD | LNC | Critical Facilities Sustaining (Field) | CFS NE RHD LNC GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD LNC GN-CFS Augment POR20 | NE | RHD | LNC | Critical Facilities Sustaining (Field) | CFS NE RHD LNC GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD LNC SC-CFS Augment POR20 | NE | RHD | LNC | Critical Facilities Sustaining (Field) | CFS NE RHD LNC SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD LNC SC-CFS Augment POR20 | NE | RHD | LNC | Critical Facilities Sustaining (Field) | CFS NE RHD LNC SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD LNC FS-CFS Augment POR20 - 3 | NE | RHD | LNC | Critical Facilities Sustaining (Field) | CFS NE RHD LNC FS-CFS Augment POR20 - 3 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD LNC FS-CFS Augment POR20 - 3 | NE | RHD | LNC | Critical Facilities Sustaining (Field) | CFS NE RHD LNC FS-CFS Augment POR20 - 3 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD PAW HV-CFS Augment POR20 | NE | RHD | PAW | Critical Facilities Sustaining (Field) | CFS NE RHD PAW HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD PAW HV-CFS Augment POR20 | NE | RHD | PAW | Critical Facilities Sustaining (Field) | CFS NE RHD PAW HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD PAW FS-CFS Augment POR20 | NE | RHD | PAW | Critical Facilities Sustaining (Field) | CFS NE RHD PAW FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD PAW FS-CFS Augment POR20 | NE | RHD | PAW | Critical Facilities Sustaining (Field) | CFS NE RHD PAW FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD PAW LM-CFS Augment POR20 | NE | RHD | PAW | Critical Facilities Sustaining (Field) | CFS NE RHD PAW LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD PAW LM-CFS Augment POR20 | NE | RHD | PAW | Critical Facilities Sustaining (Field) | CFS NE RHD PAW LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD PAW FS-CFS Augment POR20 - 2 | NE | RHD | PAW | Critical Facilities Sustaining (Field) | CFS NE RHD PAW FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD PAW FS-CFS Augment POR20 - 2 | NE | RHD | PAW | Critical Facilities Sustaining (Field) | CFS NE RHD PAW FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD PAW GN-CFS Augment POR20 | NE | RHD | PAW | Critical Facilities Sustaining (Field) | CFS NE RHD PAW GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD PAW GN-CFS Augment POR20 | NE | RHD | PAW | Critical Facilities Sustaining (Field) | CFS NE RHD PAW GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD PAW SC-CFS Augment POR20 | NE | RHD | PAW | Critical Facilities Sustaining (Field) | CFS NE RHD PAW SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD PAW SC-CFS Augment POR20 | NE | RHD | PAW | Critical Facilities Sustaining (Field) | CFS NE RHD PAW SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD PTH FS-CFS Augment POR20 | NE | RHD | PTH | Critical Facilities Sustaining (Field) | CFS NE RHD PTH FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD PTH FS-CFS Augment POR20 | NE | RHD | PTH | Critical Facilities Sustaining (Field) | CFS NE RHD PTH FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD PTH LM-CFS Augment POR20 | NE | RHD | PTH | Critical Facilities Sustaining (Field) | CFS NE RHD PTH LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD PTH LM-CFS Augment POR20 | NE | RHD | PTH | Critical Facilities Sustaining (Field) | CFS NE RHD PTH LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD PTH FS-CFS Augment POR20 - 2 | NE | RHD | PTH | Critical Facilities Sustaining (Field) | CFS NE RHD PTH FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD PTH FS-CFS Augment POR20 - 2 | NE | RHD | PTH | Critical Facilities Sustaining (Field) | CFS NE RHD PTH FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD PTH SC-CFS Augment POR20 | NE | RHD | PTH | Critical Facilities Sustaining (Field) | CFS NE RHD PTH SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD PTH SC-CFS Augment POR20 | NE | RHD | PTH | Critical Facilities Sustaining (Field) | CFS NE RHD PTH SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD BUR BU-CFS Augment POR20 | NE | RHD | BUR | Critical Facilities Sustaining (Field) | CFS NE RHD BUR BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD BUR BU-CFS Augment POR20 | NE | RHD | BUR | Critical Facilities Sustaining (Field) | CFS NE RHD BUR BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD BUR GN-CFS Augment POR20 | NE | RHD | BUR | Critical Facilities Sustaining (Field) | CFS NE RHD BUR GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD BUR GN-CFS Augment POR20 | NE | RHD | BUR | Critical Facilities Sustaining (Field) | CFS NE RHD BUR GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD BUR SC-CFS Augment POR20 | NE | RHD | BUR | Critical Facilities Sustaining (Field) | CFS NE RHD BUR SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD BUR SC-CFS Augment POR20 | NE | RHD | BUR | Critical Facilities Sustaining (Field) | CFS NE RHD BUR SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD BUR AT-CFS Augment POR20 | NE | RHD | BUR | Critical Facilities Sustaining (Field) | CFS NE RHD BUR AT-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD BUR AT-CFS Augment POR20 | NE | RHD | BUR | Critical Facilities Sustaining (Field) | CFS NE RHD BUR AT-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD BUR FS-CFS Augment POR20 | NE | RHD | BUR | Critical Facilities Sustaining (Field) | CFS NE RHD BUR FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD BUR FS-CFS Augment POR20 | NE | RHD | BUR | Critical Facilities Sustaining (Field) | CFS NE RHD BUR FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD SCT RF-CFS Augment POR20 | NE | RHD | SCT | Critical Facilities Sustaining (Field) | CFS NE RHD SCT RF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD SCT RF-CFS Augment POR20 | NE | RHD | SCT | Critical Facilities Sustaining (Field) | CFS NE RHD SCT RF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD SCT GN-CFS Augment POR20 | NE | RHD | SCT | Critical Facilities Sustaining (Field) | CFS NE RHD SCT GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD SCT GN-CFS Augment POR20 | NE | RHD | SCT | Critical Facilities Sustaining (Field) | CFS NE RHD SCT GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD SCT SC-CFS Augment POR20 | NE | RHD | SCT | Critical Facilities Sustaining (Field) | CFS NE RHD SCT SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD SCT SC-CFS Augment POR20 | NE | RHD | SCT | Critical Facilities Sustaining (Field) | CFS NE RHD SCT SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD SCT AT-CFS Augment POR20 | NE | RHD | SCT | Critical Facilities Sustaining (Field) | CFS NE RHD SCT AT-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD SCT AT-CFS Augment POR20 | NE | RHD | SCT | Critical Facilities Sustaining (Field) | CFS NE RHD SCT AT-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON MAN FS-CFS Augment POR20 - 1 | NE | CON | MAN | Critical Facilities Sustaining (Field) | CFS NE CON MAN FS-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON MAN FS-CFS Augment POR20 - 1 | NE | CON | MAN | Critical Facilities Sustaining (Field) | CFS NE CON MAN FS-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON MAN FS-CFS Augment POR20 - 2 | NE | CON | MAN | Critical Facilities Sustaining (Field) | CFS NE CON MAN FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON MAN FS-CFS Augment POR20 - 2 | NE | CON | MAN | Critical Facilities Sustaining (Field) | CFS NE CON MAN FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON MAN AC-CFS Augment POR20 | NE | CON | MAN | Critical Facilities Sustaining (Field) | CFS NE CON MAN AC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON MAN AC-CFS Augment POR20 | NE | CON | MAN | Critical Facilities Sustaining (Field) | CFS NE CON MAN AC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON MAN SC-CFS Augment POR20 | NE | CON | MAN | Critical Facilities Sustaining (Field) | CFS NE CON MAN SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON MAN SC-CFS Augment POR20 | NE | CON | MAN | Critical Facilities Sustaining (Field) | CFS NE CON MAN SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON MAN FS-CFS Augment POR20 - 3 | NE | CON | MAN | Critical Facilities Sustaining (Field) | CFS NE CON MAN FS-CFS Augment POR20 - 3 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON MAN FS-CFS Augment POR20 - 3 | NE | CON | MAN | Critical Facilities Sustaining (Field) | CFS NE CON MAN FS-CFS Augment POR20 - 3 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON MER BU-CFS Augment POR20 | NE | CON | MER | Critical Facilities Sustaining (Field) | CFS NE CON MER BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON MER BU-CFS Augment POR20 | NE | CON | MER | Critical Facilities Sustaining (Field) | CFS NE CON MER BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON MER FS-CFS Augment POR20 - 1 | NE | CON | MER | Critical Facilities Sustaining (Field) | CFS NE CON MER FS-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON MER FS-CFS Augment POR20 - 1 | NE | CON | MER | Critical Facilities Sustaining (Field) | CFS NE CON MER FS-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON MER FS-CFS Augment POR20 - 2 | NE | CON | MER | Critical Facilities Sustaining (Field) | CFS NE CON MER FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON MER FS-CFS Augment POR20 - 2 | NE | CON | MER | Critical Facilities Sustaining (Field) | CFS NE CON MER FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON MER AC-CFS Augment POR20 | NE | CON | MER | Critical Facilities Sustaining (Field) | CFS NE CON MER AC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON MER AC-CFS Augment POR20 | NE | CON | MER | Critical Facilities Sustaining (Field) | CFS NE CON MER AC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON MER FS-CFS Augment POR20 - 3 | NE | CON | MER | Critical Facilities Sustaining (Field) | CFS NE CON MER FS-CFS Augment POR20 - 3 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON MER FS-CFS Augment POR20 - 3 | NE | CON | MER | Critical Facilities Sustaining (Field) | CFS NE CON MER FS-CFS Augment POR20 - 3 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON MER SC-CFS Augment POR20 | NE | CON | MER | Critical Facilities Sustaining (Field) | CFS NE CON MER SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON MER SC-CFS Augment POR20 | NE | CON | MER | Critical Facilities Sustaining (Field) | CFS NE CON MER SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON MER AT-CFS Augment POR20 | NE | CON | MER | Critical Facilities Sustaining (Field) | CFS NE CON MER AT-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON MER AT-CFS Augment POR20 | NE | CON | MER | Critical Facilities Sustaining (Field) | CFS NE CON MER AT-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON RKH BU-CFS Augment POR20 | NE | CON | RKH | Critical Facilities Sustaining (Field) | CFS NE CON RKH BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON RKH BU-CFS Augment POR20 | NE | CON | RKH | Critical Facilities Sustaining (Field) | CFS NE CON RKH BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON RKH FS-CFS Augment POR20 - 1 | NE | CON | RKH | Critical Facilities Sustaining (Field) | CFS NE CON RKH FS-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON RKH FS-CFS Augment POR20 - 1 | NE | CON | RKH | Critical Facilities Sustaining (Field) | CFS NE CON RKH FS-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON RKH FS-CFS Augment POR20 - 2 | NE | CON | RKH | Critical Facilities Sustaining (Field) | CFS NE CON RKH FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON RKH FS-CFS Augment POR20 - 2 | NE | CON | RKH | Critical Facilities Sustaining (Field) | CFS NE CON RKH FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON RKH GN-CFS Augment POR20 | NE | CON | RKH | Critical Facilities Sustaining (Field) | CFS NE CON RKH GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON RKH GN-CFS Augment POR20 | NE | CON | RKH | Critical Facilities Sustaining (Field) | CFS NE CON RKH GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON RKH SC-CFS Augment POR20 | NE | CON | RKH | Critical Facilities Sustaining (Field) | CFS NE CON RKH SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON RKH SC-CFS Augment POR20 | NE | CON | RKH | Critical Facilities Sustaining (Field) | CFS NE CON RKH SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON RKH FS-CFS Augment POR20 - 3 | NE | CON | RKH | Critical Facilities Sustaining (Field) | CFS NE CON RKH FS-CFS Augment POR20 - 3 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON RKH FS-CFS Augment POR20 - 3 | NE | CON | RKH | Critical Facilities Sustaining (Field) | CFS NE CON RKH FS-CFS Augment POR20 - 3 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON ENF BU-CFS Augment POR20 | NE | CON | ENF | Critical Facilities Sustaining (Field) | CFS NE CON ENF BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON ENF BU-CFS Augment POR20 | NE | CON | ENF | Critical Facilities Sustaining (Field) | CFS NE CON ENF BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON ENF HV-CFS Augment POR20 | NE | CON | ENF | Critical Facilities Sustaining (Field) | CFS NE CON ENF HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON ENF HV-CFS Augment POR20 | NE | CON | ENF | Critical Facilities Sustaining (Field) | CFS NE CON ENF HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON ENF FS-CFS Augment POR20 - 1 | NE | CON | ENF | Critical Facilities Sustaining (Field) | CFS NE CON ENF FS-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON ENF FS-CFS Augment POR20 - 1 | NE | CON | ENF | Critical Facilities Sustaining (Field) | CFS NE CON ENF FS-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON ENF FS-CFS Augment POR20 - 2 | NE | CON | ENF | Critical Facilities Sustaining (Field) | CFS NE CON ENF FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON ENF FS-CFS Augment POR20 - 2 | NE | CON | ENF | Critical Facilities Sustaining (Field) | CFS NE CON ENF FS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON ENF SC-CFS Augment POR20 | NE | CON | ENF | Critical Facilities Sustaining (Field) | CFS NE CON ENF SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON ENF SC-CFS Augment POR20 | NE | CON | ENF | Critical Facilities Sustaining (Field) | CFS NE CON ENF SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON ENF FS-CFS Augment POR20 - 3 | NE | CON | ENF | Critical Facilities Sustaining (Field) | CFS NE CON ENF FS-CFS Augment POR20 - 3 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON ENF FS-CFS Augment POR20 - 3 | NE | CON | ENF | Critical Facilities Sustaining (Field) | CFS NE CON ENF FS-CFS Augment POR20 - 3 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON SFD SC-CFS Augment POR20 | NE | CON | SFD | Critical Facilities Sustaining (Field) | CFS NE CON SFD SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON SFD SC-CFS Augment POR20 | NE | CON | SFD | Critical Facilities Sustaining (Field) | CFS NE CON SFD SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON SFD FS-CFS Augment POR20 | NE | CON | SFD | Critical Facilities Sustaining (Field) | CFS NE CON SFD FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON SFD FS-CFS Augment POR20 | NE | CON | SFD | Critical Facilities Sustaining (Field) | CFS NE CON SFD FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON STN SC-CFS Augment POR20 | NE | CON | STN | Critical Facilities Sustaining (Field) | CFS NE CON STN SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON STN SC-CFS Augment POR20 | NE | CON | STN | Critical Facilities Sustaining (Field) | CFS NE CON STN SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON STN FS-CFS Augment POR20 | NE | CON | STN | Critical Facilities Sustaining (Field) | CFS NE CON STN FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON STN FS-CFS Augment POR20 | NE | CON | STN | Critical Facilities Sustaining (Field) | CFS NE CON STN FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON GLB BU-CFS Augment POR20 | NE | CON | GLB | Critical Facilities Sustaining (Field) | CFS NE CON GLB BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON GLB BU-CFS Augment POR20 | NE | CON | GLB | Critical Facilities Sustaining (Field) | CFS NE CON GLB BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON GRB RF-CFS Augment POR20 | NE | CON | GRB | Critical Facilities Sustaining (Field) | CFS NE CON GRB RF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON GRB RF-CFS Augment POR20 | NE | CON | GRB | Critical Facilities Sustaining (Field) | CFS NE CON GRB RF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON GRB GN-CFS Augment POR20 | NE | CON | GRB | Critical Facilities Sustaining (Field) | CFS NE CON GRB GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON GRB GN-CFS Augment POR20 | NE | CON | GRB | Critical Facilities Sustaining (Field) | CFS NE CON GRB GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON GRB SC-CFS Augment POR20 | NE | CON | GRB | Critical Facilities Sustaining (Field) | CFS NE CON GRB SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON GRB SC-CFS Augment POR20 | NE | CON | GRB | Critical Facilities Sustaining (Field) | CFS NE CON GRB SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON GRB AT-CFS Augment POR20 | NE | CON | GRB | Critical Facilities Sustaining (Field) | CFS NE CON GRB AT-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON GRB AT-CFS Augment POR20 | NE | CON | GRB | Critical Facilities Sustaining (Field) | CFS NE CON GRB AT-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON GRB FS-CFS Augment POR20 | NE | CON | GRB | Critical Facilities Sustaining (Field) | CFS NE CON GRB FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON GRB FS-CFS Augment POR20 | NE | CON | GRB | Critical Facilities Sustaining (Field) | CFS NE CON GRB FS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON STF RF-CFS Augment POR20 | NE | CON | STF | Critical Facilities Sustaining (Field) | CFS NE CON STF RF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON STF RF-CFS Augment POR20 | NE | CON | STF | Critical Facilities Sustaining (Field) | CFS NE CON STF RF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON STF HV-CFS Augment POR20 | NE | CON | STF | Critical Facilities Sustaining (Field) | CFS NE CON STF HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON STF HV-CFS Augment POR20 | NE | CON | STF | Critical Facilities Sustaining (Field) | CFS NE CON STF HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE LFY LFY RF-CFS Augment POR20 - 1 | SE | LFY | LFY | Critical Facilities Sustaining (Field) | CFS SE LFY LFY RF-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE LFY LFY RF-CFS Augment POR20 - 1 | SE | LFY | LFY | Critical Facilities Sustaining (Field) | CFS SE LFY LFY RF-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE LFY LFY RF-CFS Augment POR20 - 2 | SE | LFY | LFY | Critical Facilities Sustaining (Field) | CFS SE LFY LFY RF-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE LFY LFY RF-CFS Augment POR20 - 2 | SE | LFY | LFY | Critical Facilities Sustaining (Field) | CFS SE LFY LFY RF-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE BTR NTH BU-CFS Augment POR20 | SE | BTR | NTH | Critical Facilities Sustaining (Field) | CFS SE BTR NTH BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE BTR NTH BU-CFS Augment POR20 | SE | BTR | NTH | Critical Facilities Sustaining (Field) | CFS SE BTR NTH BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE BTR ERW BU-CFS Augment POR20 | SE | BTR | ERW | Critical Facilities Sustaining (Field) | CFS SE BTR ERW BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-02-01 |  | Active | EP
CFS SE BTR ERW BU-CFS Augment POR20 | SE | BTR | ERW | Critical Facilities Sustaining (Field) | CFS SE BTR ERW BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-02-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE BTR STC BU-CFS Augment POR20 | SE | BTR | STC | Critical Facilities Sustaining (Field) | CFS SE BTR STC BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-01 |  | Active | EP
CFS SE BTR STC BU-CFS Augment POR20 | SE | BTR | STC | Critical Facilities Sustaining (Field) | CFS SE BTR STC BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE BTR ERW HV-CFS Augment POR20 | SE | BTR | ERW | Critical Facilities Sustaining (Field) | CFS SE BTR ERW HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-10-01 |  | Active | EP
CFS SE BTR ERW HV-CFS Augment POR20 | SE | BTR | ERW | Critical Facilities Sustaining (Field) | CFS SE BTR ERW HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-10-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE NOR ALG HV-CFS Augment POR20 | SE | NOR | ALG | Critical Facilities Sustaining (Field) | CFS SE NOR ALG HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS SE NOR ALG HV-CFS Augment POR20 | SE | NOR | ALG | Critical Facilities Sustaining (Field) | CFS SE NOR ALG HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE NOR KNN HV-CFS Augment POR20 | SE | NOR | KNN | Critical Facilities Sustaining (Field) | CFS SE NOR KNN HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-10-01 |  | Active | EP
CFS SE NOR KNN HV-CFS Augment POR20 | SE | NOR | KNN | Critical Facilities Sustaining (Field) | CFS SE NOR KNN HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-10-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE GCT PNS HV-CFS Augment POR20 | SE | GCT | PNS | Critical Facilities Sustaining (Field) | CFS SE GCT PNS HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-09-01 |  | Active | EP
CFS SE GCT PNS HV-CFS Augment POR20 | SE | GCT | PNS | Critical Facilities Sustaining (Field) | CFS SE GCT PNS HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-09-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE MGA HLT HV-CFS Augment POR20 - 1 | SE | MGA | HLT | Critical Facilities Sustaining (Field) | CFS SE MGA HLT HV-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS SE MGA HLT HV-CFS Augment POR20 - 1 | SE | MGA | HLT | Critical Facilities Sustaining (Field) | CFS SE MGA HLT HV-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE MGA HLT HV-CFS Augment POR20 - 2 | SE | MGA | HLT | Critical Facilities Sustaining (Field) | CFS SE MGA HLT HV-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS SE MGA HLT HV-CFS Augment POR20 - 2 | SE | MGA | HLT | Critical Facilities Sustaining (Field) | CFS SE MGA HLT HV-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE LFY LFY BD-CFS Augment POR20 | SE | LFY | LFY | Critical Facilities Sustaining (Field) | CFS SE LFY LFY BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS SE LFY LFY BD-CFS Augment POR20 | SE | LFY | LFY | Critical Facilities Sustaining (Field) | CFS SE LFY LFY BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE BTR BTR BD-CFS Augment POR20 | SE | BTR | BTR | Critical Facilities Sustaining (Field) | CFS SE BTR BTR BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-02-01 |  | Active | EP
CFS SE BTR BTR BD-CFS Augment POR20 | SE | BTR | BTR | Critical Facilities Sustaining (Field) | CFS SE BTR BTR BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-02-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE NOR LUL IV-CFS Augment POR20 | SE | NOR | LUL | Critical Facilities Sustaining (Field) | CFS SE NOR LUL IV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-01 |  | Active | EP
CFS SE NOR LUL IV-CFS Augment POR20 | SE | NOR | LUL | Critical Facilities Sustaining (Field) | CFS SE NOR LUL IV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE LFY STM IV-CFS Augment POR20 | SE | LFY | STM | Critical Facilities Sustaining (Field) | CFS SE LFY STM IV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | Active | EP
CFS SE LFY STM IV-CFS Augment POR20 | SE | LFY | STM | Critical Facilities Sustaining (Field) | CFS SE LFY STM IV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE NOR MCY BD-CFS Augment POR20 | SE | NOR | MCY | Critical Facilities Sustaining (Field) | CFS SE NOR MCY BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | Active | EP
CFS SE NOR MCY BD-CFS Augment POR20 | SE | NOR | MCY | Critical Facilities Sustaining (Field) | CFS SE NOR MCY BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE LFY STM BS-CFS Augment POR20 | SE | LFY | STM | Critical Facilities Sustaining (Field) | CFS SE LFY STM BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-09-01 |  | Active | EP
CFS SE LFY STM BS-CFS Augment POR20 | SE | LFY | STM | Critical Facilities Sustaining (Field) | CFS SE LFY STM BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-09-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE NOR CLR BS-CFS Augment POR20 | SE | NOR | CLR | Critical Facilities Sustaining (Field) | CFS SE NOR CLR BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-09-01 |  | Active | EP
CFS SE NOR CLR BS-CFS Augment POR20 | SE | NOR | CLR | Critical Facilities Sustaining (Field) | CFS SE NOR CLR BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-09-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE GCT NCV BS-CFS Augment POR20 | SE | GCT | NCV | Critical Facilities Sustaining (Field) | CFS SE GCT NCV BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-01 |  | Active | EP
CFS SE GCT NCV BS-CFS Augment POR20 | SE | GCT | NCV | Critical Facilities Sustaining (Field) | CFS SE GCT NCV BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE GCT CRV BS-CFS Augment POR20 | SE | GCT | CRV | Critical Facilities Sustaining (Field) | CFS SE GCT CRV BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS SE GCT CRV BS-CFS Augment POR20 | SE | GCT | CRV | Critical Facilities Sustaining (Field) | CFS SE GCT CRV BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE GCT FWB SC-CFS Augment POR20 | SE | GCT | FWB | Critical Facilities Sustaining (Field) | CFS SE GCT FWB SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE GCT FWB SC-CFS Augment POR20 | SE | GCT | FWB | Critical Facilities Sustaining (Field) | CFS SE GCT FWB SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE GCT CRV SC-CFS Augment POR20 | SE | GCT | CRV | Critical Facilities Sustaining (Field) | CFS SE GCT CRV SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE GCT CRV SC-CFS Augment POR20 | SE | GCT | CRV | Critical Facilities Sustaining (Field) | CFS SE GCT CRV SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE GAN GNS SC-CFS Augment POR20 | SE | GAN | GNS | Critical Facilities Sustaining (Field) | CFS SE GAN GNS SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-09-01 |  | Active | EP
CFS SE GAN GNS SC-CFS Augment POR20 | SE | GAN | GNS | Critical Facilities Sustaining (Field) | CFS SE GAN GNS SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-09-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE GCT PNS SC-CFS Augment POR20 | SE | GCT | PNS | Critical Facilities Sustaining (Field) | CFS SE GCT PNS SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-02-01 |  | Active | EP
CFS SE GCT PNS SC-CFS Augment POR20 | SE | GCT | PNS | Critical Facilities Sustaining (Field) | CFS SE GCT PNS SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-02-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE GCT DES SC-CFS Augment POR20 | SE | GCT | DES | Critical Facilities Sustaining (Field) | CFS SE GCT DES SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-01 |  | Active | EP
CFS SE GCT DES SC-CFS Augment POR20 | SE | GCT | DES | Critical Facilities Sustaining (Field) | CFS SE GCT DES SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE GCT NCV SC-CFS Augment POR20 | SE | GCT | NCV | Critical Facilities Sustaining (Field) | CFS SE GCT NCV SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-01 |  | Active | EP
CFS SE GCT NCV SC-CFS Augment POR20 | SE | GCT | NCV | Critical Facilities Sustaining (Field) | CFS SE GCT NCV SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE MGA GRY SC-CFS Augment POR20 | SE | MGA | GRY | Critical Facilities Sustaining (Field) | CFS SE MGA GRY SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-09-01 |  | Active | EP
CFS SE MGA GRY SC-CFS Augment POR20 | SE | MGA | GRY | Critical Facilities Sustaining (Field) | CFS SE MGA GRY SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-09-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE LFY ABV SC-CFS Augment POR20 | SE | LFY | ABV | Critical Facilities Sustaining (Field) | CFS SE LFY ABV SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS SE LFY ABV SC-CFS Augment POR20 | SE | LFY | ABV | Critical Facilities Sustaining (Field) | CFS SE LFY ABV SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE NOR ALG SC-CFS Augment POR20 | SE | NOR | ALG | Critical Facilities Sustaining (Field) | CFS SE NOR ALG SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-02-01 |  | Active | EP
CFS SE NOR ALG SC-CFS Augment POR20 | SE | NOR | ALG | Critical Facilities Sustaining (Field) | CFS SE NOR ALG SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-02-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE BTR BTR SC-CFS Augment POR20 | SE | BTR | BTR | Critical Facilities Sustaining (Field) | CFS SE BTR BTR SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-01 |  | Active | EP
CFS SE BTR BTR SC-CFS Augment POR20 | SE | BTR | BTR | Critical Facilities Sustaining (Field) | CFS SE BTR BTR SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-03-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE BTR DNS SC-CFS Augment POR20 | SE | BTR | DNS | Critical Facilities Sustaining (Field) | CFS SE BTR DNS SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS SE BTR DNS SC-CFS Augment POR20 | SE | BTR | DNS | Critical Facilities Sustaining (Field) | CFS SE BTR DNS SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE BTR DVL SC-CFS Augment POR20 | SE | BTR | DVL | Critical Facilities Sustaining (Field) | CFS SE BTR DVL SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS SE BTR DVL SC-CFS Augment POR20 | SE | BTR | DVL | Critical Facilities Sustaining (Field) | CFS SE BTR DVL SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE NOR ELM SC-CFS Augment POR20 | SE | NOR | ELM | Critical Facilities Sustaining (Field) | CFS SE NOR ELM SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-01 |  | Active | EP
CFS SE NOR ELM SC-CFS Augment POR20 | SE | NOR | ELM | Critical Facilities Sustaining (Field) | CFS SE NOR ELM SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE BTR ERW SC-CFS Augment POR20 | SE | BTR | ERW | Critical Facilities Sustaining (Field) | CFS SE BTR ERW SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-05-01 |  | Active | EP
CFS SE BTR ERW SC-CFS Augment POR20 | SE | BTR | ERW | Critical Facilities Sustaining (Field) | CFS SE BTR ERW SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-05-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE LFY FRK SC-CFS Augment POR20 | SE | LFY | FRK | Critical Facilities Sustaining (Field) | CFS SE LFY FRK SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS SE LFY FRK SC-CFS Augment POR20 | SE | LFY | FRK | Critical Facilities Sustaining (Field) | CFS SE LFY FRK SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE BTR GNZ SC-CFS Augment POR20 | SE | BTR | GNZ | Critical Facilities Sustaining (Field) | CFS SE BTR GNZ SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-05-01 |  | Active | EP
CFS SE BTR GNZ SC-CFS Augment POR20 | SE | BTR | GNZ | Critical Facilities Sustaining (Field) | CFS SE BTR GNZ SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-05-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE BTR LGR SC-CFS Augment POR20 | SE | BTR | LGR | Critical Facilities Sustaining (Field) | CFS SE BTR LGR SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-01 |  | Active | EP
CFS SE BTR LGR SC-CFS Augment POR20 | SE | BTR | LGR | Critical Facilities Sustaining (Field) | CFS SE BTR LGR SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE NOR KNN SC-CFS Augment POR20 | SE | NOR | KNN | Critical Facilities Sustaining (Field) | CFS SE NOR KNN SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | Active | EP
CFS SE NOR KNN SC-CFS Augment POR20 | SE | NOR | KNN | Critical Facilities Sustaining (Field) | CFS SE NOR KNN SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE LFY LFY SC-CFS Augment POR20 | SE | LFY | LFY | Critical Facilities Sustaining (Field) | CFS SE LFY LFY SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-05-01 |  | Active | EP
CFS SE LFY LFY SC-CFS Augment POR20 | SE | LFY | LFY | Critical Facilities Sustaining (Field) | CFS SE LFY LFY SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-05-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE NOR MCY SC-CFS Augment POR20 | SE | NOR | MCY | Critical Facilities Sustaining (Field) | CFS SE NOR MCY SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE NOR MCY SC-CFS Augment POR20 | SE | NOR | MCY | Critical Facilities Sustaining (Field) | CFS SE NOR MCY SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE LFY CRW SC-CFS Augment POR20 | SE | LFY | CRW | Critical Facilities Sustaining (Field) | CFS SE LFY CRW SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-05-01 |  | Active | EP
CFS SE LFY CRW SC-CFS Augment POR20 | SE | LFY | CRW | Critical Facilities Sustaining (Field) | CFS SE LFY CRW SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-05-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE LFY NIB SC-CFS Augment POR20 | SE | LFY | NIB | Critical Facilities Sustaining (Field) | CFS SE LFY NIB SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-01 |  | Active | EP
CFS SE LFY NIB SC-CFS Augment POR20 | SE | LFY | NIB | Critical Facilities Sustaining (Field) | CFS SE LFY NIB SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE LFY STM SC-CFS Augment POR20 | SE | LFY | STM | Critical Facilities Sustaining (Field) | CFS SE LFY STM SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-01 |  | Active | EP
CFS SE LFY STM SC-CFS Augment POR20 | SE | LFY | STM | Critical Facilities Sustaining (Field) | CFS SE LFY STM SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE BTR SPC SC-CFS Augment POR20 | SE | BTR | SPC | Critical Facilities Sustaining (Field) | CFS SE BTR SPC SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-01 |  | Active | EP
CFS SE BTR SPC SC-CFS Augment POR20 | SE | BTR | SPC | Critical Facilities Sustaining (Field) | CFS SE BTR SPC SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE BTR NTH SC-CFS Augment POR20 | SE | BTR | NTH | Critical Facilities Sustaining (Field) | CFS SE BTR NTH SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | Active | EP
CFS SE BTR NTH SC-CFS Augment POR20 | SE | BTR | NTH | Critical Facilities Sustaining (Field) | CFS SE BTR NTH SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE BTR PLQ SC-CFS Augment POR20 | SE | BTR | PLQ | Critical Facilities Sustaining (Field) | CFS SE BTR PLQ SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | Active | EP
CFS SE BTR PLQ SC-CFS Augment POR20 | SE | BTR | PLQ | Critical Facilities Sustaining (Field) | CFS SE BTR PLQ SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE NOR STB SC-CFS Augment POR20 | SE | NOR | STB | Critical Facilities Sustaining (Field) | CFS SE NOR STB SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-02-01 |  | Active | EP
CFS SE NOR STB SC-CFS Augment POR20 | SE | NOR | STB | Critical Facilities Sustaining (Field) | CFS SE NOR STB SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-02-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE NOR DST SC-CFS Augment POR20 | SE | NOR | DST | Critical Facilities Sustaining (Field) | CFS SE NOR DST SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-01 |  | Active | EP
CFS SE NOR DST SC-CFS Augment POR20 | SE | NOR | DST | Critical Facilities Sustaining (Field) | CFS SE NOR DST SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE NOR LUL SC-CFS Augment POR20 | SE | NOR | LUL | Critical Facilities Sustaining (Field) | CFS SE NOR LUL SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-09-01 |  | Active | EP
CFS SE NOR LUL SC-CFS Augment POR20 | SE | NOR | LUL | Critical Facilities Sustaining (Field) | CFS SE NOR LUL SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-09-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE BTR STC SC-CFS Augment POR20 | SE | BTR | STC | Critical Facilities Sustaining (Field) | CFS SE BTR STC SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-01 |  | Active | EP
CFS SE BTR STC SC-CFS Augment POR20 | SE | BTR | STC | Critical Facilities Sustaining (Field) | CFS SE BTR STC SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE GCT CRV SC-CFS Augment POR20 - 2 | SE | GCT | CRV | Critical Facilities Sustaining (Field) | CFS SE GCT CRV SC-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS SE GCT CRV SC-CFS Augment POR20 - 2 | SE | GCT | CRV | Critical Facilities Sustaining (Field) | CFS SE GCT CRV SC-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-02-01 |  | Deleted | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE GCT CRV SC-CFS Augment POR20 - 2 | SE | GCT | CRV | Critical Facilities Sustaining (Field) | CFS SE GCT CRV SC-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS SE GCT NCV SC-CFS Augment POR20 - 2 | SE | GCT | NCV | Critical Facilities Sustaining (Field) | CFS SE GCT NCV SC-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS SE GCT NCV SC-CFS Augment POR20 - 2 | SE | GCT | NCV | Critical Facilities Sustaining (Field) | CFS SE GCT NCV SC-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-02-01 |  | Deleted | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE GCT NCV SC-CFS Augment POR20 - 2 | SE | GCT | NCV | Critical Facilities Sustaining (Field) | CFS SE GCT NCV SC-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS SE LFY CRW SC-CFS Augment POR20 - 2 | SE | LFY | CRW | Critical Facilities Sustaining (Field) | CFS SE LFY CRW SC-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS SE LFY CRW SC-CFS Augment POR20 - 2 | SE | LFY | CRW | Critical Facilities Sustaining (Field) | CFS SE LFY CRW SC-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-03-01 |  | Deleted | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE LFY CRW SC-CFS Augment POR20 - 2 | SE | LFY | CRW | Critical Facilities Sustaining (Field) | CFS SE LFY CRW SC-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS SE NOR KNN SC-CFS Augment POR20 - 2 | SE | NOR | KNN | Critical Facilities Sustaining (Field) | CFS SE NOR KNN SC-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS SE NOR KNN SC-CFS Augment POR20 - 2 | SE | NOR | KNN | Critical Facilities Sustaining (Field) | CFS SE NOR KNN SC-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Deleted | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE NOR KNN SC-CFS Augment POR20 - 2 | SE | NOR | KNN | Critical Facilities Sustaining (Field) | CFS SE NOR KNN SC-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS SW ARZ BEL SC-CFS Augment POR20 | SW | ARZ | BEL | Critical Facilities Sustaining (Field) | CFS SW ARZ BEL SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SW ARZ BEL SC-CFS Augment POR20 | SW | ARZ | BEL | Critical Facilities Sustaining (Field) | CFS SW ARZ BEL SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ BUK SC-CFS Augment POR20 | SW | ARZ | BUK | Critical Facilities Sustaining (Field) | CFS SW ARZ BUK SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SW ARZ BUK SC-CFS Augment POR20 | SW | ARZ | BUK | Critical Facilities Sustaining (Field) | CFS SW ARZ BUK SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ CSG SC-CFS Augment POR20 | SW | ARZ | CSG | Critical Facilities Sustaining (Field) | CFS SW ARZ CSG SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SW ARZ CSG SC-CFS Augment POR20 | SW | ARZ | CSG | Critical Facilities Sustaining (Field) | CFS SW ARZ CSG SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ VSA SC-CFS Augment POR20 | SW | ARZ | VSA | Critical Facilities Sustaining (Field) | CFS SW ARZ VSA SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SW ARZ VSA SC-CFS Augment POR20 | SW | ARZ | VSA | Critical Facilities Sustaining (Field) | CFS SW ARZ VSA SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ WCG SC-CFS Augment POR20 | SW | ARZ | WCG | Critical Facilities Sustaining (Field) | CFS SW ARZ WCG SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SW ARZ WCG SC-CFS Augment POR20 | SW | ARZ | WCG | Critical Facilities Sustaining (Field) | CFS SW ARZ WCG SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ CHD SC-CFS Augment POR20 - 1 | SW | ARZ | CHD | Critical Facilities Sustaining (Field) | CFS SW ARZ CHD SC-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SW ARZ CHD SC-CFS Augment POR20 - 1 | SW | ARZ | CHD | Critical Facilities Sustaining (Field) | CFS SW ARZ CHD SC-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ DGL SC-CFS Augment POR20 | SW | ARZ | DGL | Critical Facilities Sustaining (Field) | CFS SW ARZ DGL SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SW ARZ DGL SC-CFS Augment POR20 | SW | ARZ | DGL | Critical Facilities Sustaining (Field) | CFS SW ARZ DGL SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ MSA SC-CFS Augment POR20 | SW | ARZ | MSA | Critical Facilities Sustaining (Field) | CFS SW ARZ MSA SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SW ARZ MSA SC-CFS Augment POR20 | SW | ARZ | MSA | Critical Facilities Sustaining (Field) | CFS SW ARZ MSA SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ FWL SC-CFS Augment POR20 | SW | ARZ | FWL | Critical Facilities Sustaining (Field) | CFS SW ARZ FWL SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS SW ARZ FWL SC-CFS Augment POR20 | SW | ARZ | FWL | Critical Facilities Sustaining (Field) | CFS SW ARZ FWL SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ GVA SC-CFS Augment POR20 | SW | ARZ | GVA | Critical Facilities Sustaining (Field) | CFS SW ARZ GVA SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS SW ARZ GVA SC-CFS Augment POR20 | SW | ARZ | GVA | Critical Facilities Sustaining (Field) | CFS SW ARZ GVA SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ MCD SC-CFS Augment POR20 | SW | ARZ | MCD | Critical Facilities Sustaining (Field) | CFS SW ARZ MCD SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS SW ARZ MCD SC-CFS Augment POR20 | SW | ARZ | MCD | Critical Facilities Sustaining (Field) | CFS SW ARZ MCD SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ NSC SC-CFS Augment POR20 | SW | ARZ | NSC | Critical Facilities Sustaining (Field) | CFS SW ARZ NSC SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS SW ARZ NSC SC-CFS Augment POR20 | SW | ARZ | NSC | Critical Facilities Sustaining (Field) | CFS SW ARZ NSC SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ PEO SC-CFS Augment POR20 | SW | ARZ | PEO | Critical Facilities Sustaining (Field) | CFS SW ARZ PEO SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS SW ARZ PEO SC-CFS Augment POR20 | SW | ARZ | PEO | Critical Facilities Sustaining (Field) | CFS SW ARZ PEO SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ PNL SC-CFS Augment POR20 | SW | ARZ | PNL | Critical Facilities Sustaining (Field) | CFS SW ARZ PNL SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS SW ARZ PNL SC-CFS Augment POR20 | SW | ARZ | PNL | Critical Facilities Sustaining (Field) | CFS SW ARZ PNL SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ SVA SC-CFS Augment POR20 | SW | ARZ | SVA | Critical Facilities Sustaining (Field) | CFS SW ARZ SVA SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS SW ARZ SVA SC-CFS Augment POR20 | SW | ARZ | SVA | Critical Facilities Sustaining (Field) | CFS SW ARZ SVA SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ SSC SC-CFS Augment POR20 | SW | ARZ | SSC | Critical Facilities Sustaining (Field) | CFS SW ARZ SSC SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS SW ARZ SSC SC-CFS Augment POR20 | SW | ARZ | SSC | Critical Facilities Sustaining (Field) | CFS SW ARZ SSC SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ TUC SC-CFS Augment POR20 | SW | ARZ | TUC | Critical Facilities Sustaining (Field) | CFS SW ARZ TUC SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS SW ARZ TUC SC-CFS Augment POR20 | SW | ARZ | TUC | Critical Facilities Sustaining (Field) | CFS SW ARZ TUC SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ CHD SC-CFS Augment POR20 - 2 | SW | ARZ | CHD | Critical Facilities Sustaining (Field) | CFS SW ARZ CHD SC-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SW ARZ CHD SC-CFS Augment POR20 - 2 | SW | ARZ | CHD | Critical Facilities Sustaining (Field) | CFS SW ARZ CHD SC-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW LAS HEN SC-CFS Augment POR20 | SW | LAS | HEN | Critical Facilities Sustaining (Field) | CFS SW LAS HEN SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SW LAS HEN SC-CFS Augment POR20 | SW | LAS | HEN | Critical Facilities Sustaining (Field) | CFS SW LAS HEN SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ CHD BS-CFS Augment POR20 | SW | ARZ | CHD | Critical Facilities Sustaining (Field) | CFS SW ARZ CHD BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS SW ARZ CHD BS-CFS Augment POR20 | SW | ARZ | CHD | Critical Facilities Sustaining (Field) | CFS SW ARZ CHD BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ FWL BS-CFS Augment POR20 | SW | ARZ | FWL | Critical Facilities Sustaining (Field) | CFS SW ARZ FWL BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS SW ARZ FWL BS-CFS Augment POR20 | SW | ARZ | FWL | Critical Facilities Sustaining (Field) | CFS SW ARZ FWL BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ MSA BS-CFS Augment POR20 | SW | ARZ | MSA | Critical Facilities Sustaining (Field) | CFS SW ARZ MSA BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS SW ARZ MSA BS-CFS Augment POR20 | SW | ARZ | MSA | Critical Facilities Sustaining (Field) | CFS SW ARZ MSA BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ PNL BS-CFS Augment POR20 | SW | ARZ | PNL | Critical Facilities Sustaining (Field) | CFS SW ARZ PNL BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS SW ARZ PNL BS-CFS Augment POR20 | SW | ARZ | PNL | Critical Facilities Sustaining (Field) | CFS SW ARZ PNL BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ DGL BS-CFS Augment POR20 | SW | ARZ | DGL | Critical Facilities Sustaining (Field) | CFS SW ARZ DGL BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 |  | Active | EP
CFS SW ARZ DGL BS-CFS Augment POR20 | SW | ARZ | DGL | Critical Facilities Sustaining (Field) | CFS SW ARZ DGL BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ GVA BS-CFS Augment POR20 | SW | ARZ | GVA | Critical Facilities Sustaining (Field) | CFS SW ARZ GVA BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 |  | Active | EP
CFS SW ARZ GVA BS-CFS Augment POR20 | SW | ARZ | GVA | Critical Facilities Sustaining (Field) | CFS SW ARZ GVA BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ SVA BS-CFS Augment POR20 | SW | ARZ | SVA | Critical Facilities Sustaining (Field) | CFS SW ARZ SVA BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS SW ARZ SVA BS-CFS Augment POR20 | SW | ARZ | SVA | Critical Facilities Sustaining (Field) | CFS SW ARZ SVA BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ TUC BS-CFS Augment POR20 | SW | ARZ | TUC | Critical Facilities Sustaining (Field) | CFS SW ARZ TUC BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 |  | Active | EP
CFS SW ARZ TUC BS-CFS Augment POR20 | SW | ARZ | TUC | Critical Facilities Sustaining (Field) | CFS SW ARZ TUC BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW LAS BLU BS-CFS Augment POR20 | SW | LAS | BLU | Critical Facilities Sustaining (Field) | CFS SW LAS BLU BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS SW LAS BLU BS-CFS Augment POR20 | SW | LAS | BLU | Critical Facilities Sustaining (Field) | CFS SW LAS BLU BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW LAS CEN BS-CFS Augment POR20 | SW | LAS | CEN | Critical Facilities Sustaining (Field) | CFS SW LAS CEN BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS SW LAS CEN BS-CFS Augment POR20 | SW | LAS | CEN | Critical Facilities Sustaining (Field) | CFS SW LAS CEN BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW LAS HEN BS-CFS Augment POR20 | SW | LAS | HEN | Critical Facilities Sustaining (Field) | CFS SW LAS HEN BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 |  | Active | EP
CFS SW LAS HEN BS-CFS Augment POR20 | SW | LAS | HEN | Critical Facilities Sustaining (Field) | CFS SW LAS HEN BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW LAS TEN BS-CFS Augment POR20 | SW | LAS | TEN | Critical Facilities Sustaining (Field) | CFS SW LAS TEN BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 |  | Active | EP
CFS SW LAS TEN BS-CFS Augment POR20 | SW | LAS | TEN | Critical Facilities Sustaining (Field) | CFS SW LAS TEN BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW LAS VLY BS-CFS Augment POR20 | SW | LAS | VLY | Critical Facilities Sustaining (Field) | CFS SW LAS VLY BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 |  | Active | EP
CFS SW LAS VLY BS-CFS Augment POR20 | SW | LAS | VLY | Critical Facilities Sustaining (Field) | CFS SW LAS VLY BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ CSG LM-CFS Augment POR20 | SW | ARZ | CSG | Critical Facilities Sustaining (Field) | CFS SW ARZ CSG LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS SW ARZ CSG LM-CFS Augment POR20 | SW | ARZ | CSG | Critical Facilities Sustaining (Field) | CFS SW ARZ CSG LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ BUK LM-CFS Augment POR20 | SW | ARZ | BUK | Critical Facilities Sustaining (Field) | CFS SW ARZ BUK LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SW ARZ BUK LM-CFS Augment POR20 | SW | ARZ | BUK | Critical Facilities Sustaining (Field) | CFS SW ARZ BUK LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ PNL LM-CFS Augment POR20 | SW | ARZ | PNL | Critical Facilities Sustaining (Field) | CFS SW ARZ PNL LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 |  | Active | EP
CFS SW ARZ PNL LM-CFS Augment POR20 | SW | ARZ | PNL | Critical Facilities Sustaining (Field) | CFS SW ARZ PNL LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-06-30 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ CHD HV-CFS Augment POR20 - 1 | SW | ARZ | CHD | Critical Facilities Sustaining (Field) | CFS SW ARZ CHD HV-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SW ARZ CHD HV-CFS Augment POR20 - 1 | SW | ARZ | CHD | Critical Facilities Sustaining (Field) | CFS SW ARZ CHD HV-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ CHD HV-CFS Augment POR20 - 2 | SW | ARZ | CHD | Critical Facilities Sustaining (Field) | CFS SW ARZ CHD HV-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SW ARZ CHD HV-CFS Augment POR20 - 2 | SW | ARZ | CHD | Critical Facilities Sustaining (Field) | CFS SW ARZ CHD HV-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ BEL HV-CFS Augment POR20 - 1 | SW | ARZ | BEL | Critical Facilities Sustaining (Field) | CFS SW ARZ BEL HV-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SW ARZ BEL HV-CFS Augment POR20 - 1 | SW | ARZ | BEL | Critical Facilities Sustaining (Field) | CFS SW ARZ BEL HV-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ BUK HV-CFS Augment POR20 | SW | ARZ | BUK | Critical Facilities Sustaining (Field) | CFS SW ARZ BUK HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SW ARZ BUK HV-CFS Augment POR20 | SW | ARZ | BUK | Critical Facilities Sustaining (Field) | CFS SW ARZ BUK HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ FWL HV-CFS Augment POR20 - 1 | SW | ARZ | FWL | Critical Facilities Sustaining (Field) | CFS SW ARZ FWL HV-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS SW ARZ FWL HV-CFS Augment POR20 - 1 | SW | ARZ | FWL | Critical Facilities Sustaining (Field) | CFS SW ARZ FWL HV-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ TUC HV-CFS Augment POR20 | SW | ARZ | TUC | Critical Facilities Sustaining (Field) | CFS SW ARZ TUC HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS SW ARZ TUC HV-CFS Augment POR20 | SW | ARZ | TUC | Critical Facilities Sustaining (Field) | CFS SW ARZ TUC HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ SVA HV-CFS Augment POR20 | SW | ARZ | SVA | Critical Facilities Sustaining (Field) | CFS SW ARZ SVA HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS SW ARZ SVA HV-CFS Augment POR20 | SW | ARZ | SVA | Critical Facilities Sustaining (Field) | CFS SW ARZ SVA HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ PNL HV-CFS Augment POR20 | SW | ARZ | PNL | Critical Facilities Sustaining (Field) | CFS SW ARZ PNL HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | Active | EP
CFS SW ARZ PNL HV-CFS Augment POR20 | SW | ARZ | PNL | Critical Facilities Sustaining (Field) | CFS SW ARZ PNL HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ CSG HV-CFS Augment POR20 | SW | ARZ | CSG | Critical Facilities Sustaining (Field) | CFS SW ARZ CSG HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | Active | EP
CFS SW ARZ CSG HV-CFS Augment POR20 | SW | ARZ | CSG | Critical Facilities Sustaining (Field) | CFS SW ARZ CSG HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ MSA HV-CFS Augment POR20 | SW | ARZ | MSA | Critical Facilities Sustaining (Field) | CFS SW ARZ MSA HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SW ARZ MSA HV-CFS Augment POR20 | SW | ARZ | MSA | Critical Facilities Sustaining (Field) | CFS SW ARZ MSA HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ SSC HV-CFS Augment POR20 | SW | ARZ | SSC | Critical Facilities Sustaining (Field) | CFS SW ARZ SSC HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SW ARZ SSC HV-CFS Augment POR20 | SW | ARZ | SSC | Critical Facilities Sustaining (Field) | CFS SW ARZ SSC HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ PNL HV-CFS Augment POR20 - 2 | SW | ARZ | PNL | Critical Facilities Sustaining (Field) | CFS SW ARZ PNL HV-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SW ARZ PNL HV-CFS Augment POR20 - 2 | SW | ARZ | PNL | Critical Facilities Sustaining (Field) | CFS SW ARZ PNL HV-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ MCD HV-CFS Augment POR20 | SW | ARZ | MCD | Critical Facilities Sustaining (Field) | CFS SW ARZ MCD HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS SW ARZ MCD HV-CFS Augment POR20 | SW | ARZ | MCD | Critical Facilities Sustaining (Field) | CFS SW ARZ MCD HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ FWL HV-CFS Augment POR20 - 2 | SW | ARZ | FWL | Critical Facilities Sustaining (Field) | CFS SW ARZ FWL HV-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS SW ARZ FWL HV-CFS Augment POR20 - 2 | SW | ARZ | FWL | Critical Facilities Sustaining (Field) | CFS SW ARZ FWL HV-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ PEO HV-CFS Augment POR20 | SW | ARZ | PEO | Critical Facilities Sustaining (Field) | CFS SW ARZ PEO HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS SW ARZ PEO HV-CFS Augment POR20 | SW | ARZ | PEO | Critical Facilities Sustaining (Field) | CFS SW ARZ PEO HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW LAS VLY HV-CFS Augment POR20 | SW | LAS | VLY | Critical Facilities Sustaining (Field) | CFS SW LAS VLY HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | Active | EP
CFS SW LAS VLY HV-CFS Augment POR20 | SW | LAS | VLY | Critical Facilities Sustaining (Field) | CFS SW LAS VLY HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW LAS HEN HV-CFS Augment POR20 | SW | LAS | HEN | Critical Facilities Sustaining (Field) | CFS SW LAS HEN HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | Active | EP
CFS SW LAS HEN HV-CFS Augment POR20 | SW | LAS | HEN | Critical Facilities Sustaining (Field) | CFS SW LAS HEN HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW LAS TEN HV-CFS Augment POR20 | SW | LAS | TEN | Critical Facilities Sustaining (Field) | CFS SW LAS TEN HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | Active | EP
CFS SW LAS TEN HV-CFS Augment POR20 | SW | LAS | TEN | Critical Facilities Sustaining (Field) | CFS SW LAS TEN HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW LAS BOC HV-CFS Augment POR20 | SW | LAS | BOC | Critical Facilities Sustaining (Field) | CFS SW LAS BOC HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SW LAS BOC HV-CFS Augment POR20 | SW | LAS | BOC | Critical Facilities Sustaining (Field) | CFS SW LAS BOC HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ BEN HV-CFS Augment POR20 | SW | ARZ | BEN | Critical Facilities Sustaining (Field) | CFS SW ARZ BEN HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SW ARZ BEN HV-CFS Augment POR20 | SW | ARZ | BEN | Critical Facilities Sustaining (Field) | CFS SW ARZ BEN HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ WCG HV-CFS Augment POR20 | SW | ARZ | WCG | Critical Facilities Sustaining (Field) | CFS SW ARZ WCG HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SW ARZ WCG HV-CFS Augment POR20 | SW | ARZ | WCG | Critical Facilities Sustaining (Field) | CFS SW ARZ WCG HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ BEL HV-CFS Augment POR20 - 2 | SW | ARZ | BEL | Critical Facilities Sustaining (Field) | CFS SW ARZ BEL HV-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS SW ARZ BEL HV-CFS Augment POR20 - 2 | SW | ARZ | BEL | Critical Facilities Sustaining (Field) | CFS SW ARZ BEL HV-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ NSC HV-CFS Augment POR20 | SW | ARZ | NSC | Critical Facilities Sustaining (Field) | CFS SW ARZ NSC HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SW ARZ NSC HV-CFS Augment POR20 | SW | ARZ | NSC | Critical Facilities Sustaining (Field) | CFS SW ARZ NSC HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ VAL HV-CFS Augment POR20 | SW | ARZ | VAL | Critical Facilities Sustaining (Field) | CFS SW ARZ VAL HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS SW ARZ VAL HV-CFS Augment POR20 | SW | ARZ | VAL | Critical Facilities Sustaining (Field) | CFS SW ARZ VAL HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Deleted | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SW ARZ VAL HV-CFS Augment POR20 | SW | ARZ | VAL | Critical Facilities Sustaining (Field) | CFS SW ARZ VAL HV-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS VA HRD PRA GN-CFS Augment POR20 | VA | HRD | PRA | Critical Facilities Sustaining (Field) | CFS VA HRD PRA GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS VA HRD PRA GN-CFS Augment POR20 | VA | HRD | PRA | Critical Facilities Sustaining (Field) | CFS VA HRD PRA GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS VA HRD LTF GN-CFS Augment POR20 | VA | HRD | LTF | Critical Facilities Sustaining (Field) | CFS VA HRD LTF GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS VA HRD LTF GN-CFS Augment POR20 | VA | HRD | LTF | Critical Facilities Sustaining (Field) | CFS VA HRD LTF GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS VA ROA RON BS-CFS Augment POR20 | VA | ROA | RON | Critical Facilities Sustaining (Field) | CFS VA ROA RON BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS VA ROA RON BS-CFS Augment POR20 | VA | ROA | RON | Critical Facilities Sustaining (Field) | CFS VA ROA RON BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS VA NVA MFD DC-CFS Augment POR20 | VA | NVA | MFD | Critical Facilities Sustaining (Field) | CFS VA NVA MFD DC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS VA NVA MFD DC-CFS Augment POR20 | VA | NVA | MFD | Critical Facilities Sustaining (Field) | CFS VA NVA MFD DC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS VA HRD PTM DC-CFS Augment POR20 | VA | HRD | PTM | Critical Facilities Sustaining (Field) | CFS VA HRD PTM DC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | Active | EP
CFS VA HRD PTM DC-CFS Augment POR20 | VA | HRD | PTM | Critical Facilities Sustaining (Field) | CFS VA HRD PTM DC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS VA ROA RON DC-CFS Augment POR20 | VA | ROA | RON | Critical Facilities Sustaining (Field) | CFS VA ROA RON DC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | Active | EP
CFS VA ROA RON DC-CFS Augment POR20 | VA | ROA | RON | Critical Facilities Sustaining (Field) | CFS VA ROA RON DC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS VA HRD OCN DC-CFS Augment POR20 | VA | HRD | OCN | Critical Facilities Sustaining (Field) | CFS VA HRD OCN DC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | Active | EP
CFS VA HRD OCN DC-CFS Augment POR20 | VA | HRD | OCN | Critical Facilities Sustaining (Field) | CFS VA HRD OCN DC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS VA ROA RON DC-CFS Augment POR20 - 2 | VA | ROA | RON | Critical Facilities Sustaining (Field) | CFS VA ROA RON DC-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-07-01 |  | Active | EP
CFS VA ROA RON DC-CFS Augment POR20 - 2 | VA | ROA | RON | Critical Facilities Sustaining (Field) | CFS VA ROA RON DC-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-07-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS VA HRD PTM DC-CFS Augment POR20 - 2 | VA | HRD | PTM | Critical Facilities Sustaining (Field) | CFS VA HRD PTM DC-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-10-01 |  | Active | EP
CFS VA HRD PTM DC-CFS Augment POR20 - 2 | VA | HRD | PTM | Critical Facilities Sustaining (Field) | CFS VA HRD PTM DC-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-10-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS VA HRD GBR RC-CFS Augment POR20 | NE | CON | GRB | Critical Facilities Sustaining (Field) | CFS VA HRD GBR RC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS VA HRD GBR RC-CFS Augment POR20 | NE | CON | GRB | Critical Facilities Sustaining (Field) | CFS VA HRD GBR RC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS VA HRD JEF BS-CFS Augment POR20 | VA | HRD | JEF | Critical Facilities Sustaining (Field) | CFS VA HRD JEF BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS VA HRD JEF BS-CFS Augment POR20 | VA | HRD | JEF | Critical Facilities Sustaining (Field) | CFS VA HRD JEF BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS VA HRD NRF GN-CFS Augment POR20 | VA | HRD | NRF | Critical Facilities Sustaining (Field) | CFS VA HRD NRF GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-10-01 |  | Active | EP
CFS VA HRD NRF GN-CFS Augment POR20 | VA | HRD | NRF | Critical Facilities Sustaining (Field) | CFS VA HRD NRF GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-10-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS VA HRD NRF DC-CFS Augment POR20 | VA | HRD | NRF | Critical Facilities Sustaining (Field) | CFS VA HRD NRF DC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS VA HRD NRF DC-CFS Augment POR20 | VA | HRD | NRF | Critical Facilities Sustaining (Field) | CFS VA HRD NRF DC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS VA HRD NRF BU-CFS Augment POR20 | VA | HRD | NRF | Critical Facilities Sustaining (Field) | CFS VA HRD NRF BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS VA HRD NRF BU-CFS Augment POR20 | VA | HRD | NRF | Critical Facilities Sustaining (Field) | CFS VA HRD NRF BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS VA HRD PRA DC-CFS Augment POR20 | VA | HRD | PRA | Critical Facilities Sustaining (Field) | CFS VA HRD PRA DC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS VA HRD PRA DC-CFS Augment POR20 | VA | HRD | PRA | Critical Facilities Sustaining (Field) | CFS VA HRD PRA DC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS VA HRD PRA RF-CFS Augment POR20 | VA | HRD | PRA | Critical Facilities Sustaining (Field) | CFS VA HRD PRA RF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS VA HRD PRA RF-CFS Augment POR20 | VA | HRD | PRA | Critical Facilities Sustaining (Field) | CFS VA HRD PRA RF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS VA HRD OCN HV-CFS Augment POR20 | VA | HRD | OCN | Critical Facilities Sustaining (Field) | CFS VA HRD OCN HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS VA HRD OCN HV-CFS Augment POR20 | VA | HRD | OCN | Critical Facilities Sustaining (Field) | CFS VA HRD OCN HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS VA HRD OCN BS-CFS Augment POR20 | VA | HRD | OCN | Critical Facilities Sustaining (Field) | CFS VA HRD OCN BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS VA HRD OCN BS-CFS Augment POR20 | VA | HRD | OCN | Critical Facilities Sustaining (Field) | CFS VA HRD OCN BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS VA HRD VBC BS-CFS Augment POR20 | VA | HRD | VBC | Critical Facilities Sustaining (Field) | CFS VA HRD VBC BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-01 |  | Active | EP
CFS VA HRD VBC BS-CFS Augment POR20 | VA | HRD | VBC | Critical Facilities Sustaining (Field) | CFS VA HRD VBC BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-08-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS VA NVA FLK BU-CFS Augment POR20 | VA | NVA | FLK | Critical Facilities Sustaining (Field) | CFS VA NVA FLK BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS VA NVA FLK BU-CFS Augment POR20 | VA | NVA | FLK | Critical Facilities Sustaining (Field) | CFS VA NVA FLK BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS VA NVA DRA BU-CFS Augment POR20 | VA | NVA | DRA | Critical Facilities Sustaining (Field) | CFS VA NVA DRA BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS VA NVA DRA BU-CFS Augment POR20 | VA | NVA | DRA | Critical Facilities Sustaining (Field) | CFS VA NVA DRA BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS VA NVA TCR BU-CFS Augment POR20 | VA | NVA | TCR | Critical Facilities Sustaining (Field) | CFS VA NVA TCR BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS VA NVA TCR BU-CFS Augment POR20 | VA | NVA | TCR | Critical Facilities Sustaining (Field) | CFS VA NVA TCR BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS VA HRD JEF HV-CFS Augment POR20 | VA | HRD | JEF | Critical Facilities Sustaining (Field) | CFS VA HRD JEF HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS VA HRD JEF HV-CFS Augment POR20 | VA | HRD | JEF | Critical Facilities Sustaining (Field) | CFS VA HRD JEF HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS VA HRD JEF RC-CFS Augment POR20 | VA | HRD | JEF | Critical Facilities Sustaining (Field) | CFS VA HRD JEF RC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS VA HRD JEF RC-CFS Augment POR20 | VA | HRD | JEF | Critical Facilities Sustaining (Field) | CFS VA HRD JEF RC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS VA NVA MFD BU-CFS Augment POR20 | VA | NVA | MFD | Critical Facilities Sustaining (Field) | CFS VA NVA MFD BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS VA NVA MFD BU-CFS Augment POR20 | VA | NVA | MFD | Critical Facilities Sustaining (Field) | CFS VA NVA MFD BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS VA NVA MFD BD-CFS Augment POR20 | VA | NVA | MFD | Critical Facilities Sustaining (Field) | CFS VA NVA MFD BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | Active | EP
CFS VA NVA MFD BD-CFS Augment POR20 | VA | NVA | MFD | Critical Facilities Sustaining (Field) | CFS VA NVA MFD BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS VA HRD CYP BU-CFS Augment POR20 | VA | HRD | CYP | Critical Facilities Sustaining (Field) | CFS VA HRD CYP BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS VA HRD CYP BU-CFS Augment POR20 | VA | HRD | CYP | Critical Facilities Sustaining (Field) | CFS VA HRD CYP BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS VA NVA GCR DC-CFS Augment POR20 | VA | NVA | GCR | Critical Facilities Sustaining (Field) | CFS VA NVA GCR DC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | EP
CFS VA NVA GCR DC-CFS Augment POR20 | VA | NVA | GCR | Critical Facilities Sustaining (Field) | CFS VA NVA GCR DC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-04-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS VA NVA GCR BS-CFS Augment POR20 | VA | NVA | GCR | Critical Facilities Sustaining (Field) | CFS VA NVA GCR BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | Active | EP
CFS VA NVA GCR BS-CFS Augment POR20 | VA | NVA | GCR | Critical Facilities Sustaining (Field) | CFS VA NVA GCR BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-07-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS VA NVA RHL DC-CFS Augment POR20 | VA | NVA | RHL | Critical Facilities Sustaining (Field) | CFS VA NVA RHL DC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-10-01 |  | Active | EP
CFS VA NVA RHL DC-CFS Augment POR20 | VA | NVA | RHL | Critical Facilities Sustaining (Field) | CFS VA NVA RHL DC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-10-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CA ORG AVJ BM-CFS Augment POR20 | CA | ORG | AVJ | Critical Facilities Sustaining (Field) | CFS CA ORG AVJ BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CA ORG AVJ BM-CFS Augment POR20 | CA | ORG | AVJ | Critical Facilities Sustaining (Field) | CFS CA ORG AVJ BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CA ORG CTA BM-CFS Augment POR20 | CA | ORG | CTA | Critical Facilities Sustaining (Field) | CFS CA ORG CTA BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CA ORG CTA BM-CFS Augment POR20 | CA | ORG | CTA | Critical Facilities Sustaining (Field) | CFS CA ORG CTA BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CA ORG DNP BM-CFS Augment POR20 | CA | ORG | DNP | Critical Facilities Sustaining (Field) | CFS CA ORG DNP BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CA ORG DNP BM-CFS Augment POR20 | CA | ORG | DNP | Critical Facilities Sustaining (Field) | CFS CA ORG DNP BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CA ORG DNP HV-CFS Augment POR20 | CA | ORG | DNP | Critical Facilities Sustaining (Field) | CFS CA ORG DNP HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CA ORG DNP HV-CFS Augment POR20 | CA | ORG | DNP | Critical Facilities Sustaining (Field) | CFS CA ORG DNP HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CA ORG DNP HV-CFS Augment POR20 - 2 | CA | ORG | DNP | Critical Facilities Sustaining (Field) | CFS CA ORG DNP HV-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CA ORG DNP HV-CFS Augment POR20 - 2 | CA | ORG | DNP | Critical Facilities Sustaining (Field) | CFS CA ORG DNP HV-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CA ORG IRV BM-CFS Augment POR20 | CA | ORG | IRV | Critical Facilities Sustaining (Field) | CFS CA ORG IRV BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CA ORG IRV BM-CFS Augment POR20 | CA | ORG | IRV | Critical Facilities Sustaining (Field) | CFS CA ORG IRV BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CA ORG IRV HV-CFS Augment POR20 | CA | ORG | IRV | Critical Facilities Sustaining (Field) | CFS CA ORG IRV HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CA ORG IRV HV-CFS Augment POR20 | CA | ORG | IRV | Critical Facilities Sustaining (Field) | CFS CA ORG IRV HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CA ORG ORG BU-CFS Augment POR20 | CA | ORG | ORG | Critical Facilities Sustaining (Field) | CFS CA ORG ORG BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CA ORG ORG BU-CFS Augment POR20 | CA | ORG | ORG | Critical Facilities Sustaining (Field) | CFS CA ORG ORG BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CA ORG RSM BM-CFS Augment POR20 | CA | ORG | RSM | Critical Facilities Sustaining (Field) | CFS CA ORG RSM BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CA ORG RSM BM-CFS Augment POR20 | CA | ORG | RSM | Critical Facilities Sustaining (Field) | CFS CA ORG RSM BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CA ORG RSM HV-CFS Augment POR20 | CA | ORG | RSM | Critical Facilities Sustaining (Field) | CFS CA ORG RSM HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CA ORG RSM HV-CFS Augment POR20 | CA | ORG | RSM | Critical Facilities Sustaining (Field) | CFS CA ORG RSM HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CA SAB SAB BM-CFS Augment POR20 | CA | SAB | SAB | Critical Facilities Sustaining (Field) | CFS CA SAB SAB BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CA SAB SAB BM-CFS Augment POR20 | CA | SAB | SAB | Critical Facilities Sustaining (Field) | CFS CA SAB SAB BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CA SAN CHU HV-CFS Augment POR20 | CA | SAN | CHU | Critical Facilities Sustaining (Field) | CFS CA SAN CHU HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CA SAN CHU HV-CFS Augment POR20 | CA | SAN | CHU | Critical Facilities Sustaining (Field) | CFS CA SAN CHU HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CA SAN DWN BM-CFS Augment POR20 | CA | SAN | DWN | Critical Facilities Sustaining (Field) | CFS CA SAN DWN BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CA SAN DWN BM-CFS Augment POR20 | CA | SAN | DWN | Critical Facilities Sustaining (Field) | CFS CA SAN DWN BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CA SAN DWN HV-CFS Augment POR20 | CA | SAN | DWN | Critical Facilities Sustaining (Field) | CFS CA SAN DWN HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CA SAN DWN HV-CFS Augment POR20 | CA | SAN | DWN | Critical Facilities Sustaining (Field) | CFS CA SAN DWN HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CA SAN ELC AC-CFS Augment POR20 | CA | SAN | ELC | Critical Facilities Sustaining (Field) | CFS CA SAN ELC AC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CA SAN ELC AC-CFS Augment POR20 | CA | SAN | ELC | Critical Facilities Sustaining (Field) | CFS CA SAN ELC AC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CA SAN ESC BM-CFS Augment POR20 | CA | SAN | ESC | Critical Facilities Sustaining (Field) | CFS CA SAN ESC BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CA SAN ESC BM-CFS Augment POR20 | CA | SAN | ESC | Critical Facilities Sustaining (Field) | CFS CA SAN ESC BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CA SAN FED BM-CFS Augment POR20 | CA | SAN | FED | Critical Facilities Sustaining (Field) | CFS CA SAN FED BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CA SAN FED BM-CFS Augment POR20 | CA | SAN | FED | Critical Facilities Sustaining (Field) | CFS CA SAN FED BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CA SAN FED BM-CFS Augment POR20 - 2 | CA | SAN | FED | Critical Facilities Sustaining (Field) | CFS CA SAN FED BM-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CA SAN FED BM-CFS Augment POR20 - 2 | CA | SAN | FED | Critical Facilities Sustaining (Field) | CFS CA SAN FED BM-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CA SAN OCE BM-CFS Augment POR20 | CA | SAN | OCE | Critical Facilities Sustaining (Field) | CFS CA SAN OCE BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CA SAN OCE BM-CFS Augment POR20 | CA | SAN | OCE | Critical Facilities Sustaining (Field) | CFS CA SAN OCE BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CA SAN VST BM-CFS Augment POR20 | CA | SAN | VST | Critical Facilities Sustaining (Field) | CFS CA SAN VST BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CA SAN VST BM-CFS Augment POR20 | CA | SAN | VST | Critical Facilities Sustaining (Field) | CFS CA SAN VST BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE NWA BVL BD-CFS Augment POR20 | CE | NWA | BVL | Critical Facilities Sustaining (Field) | CFS CE NWA BVL BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE NWA BVL BD-CFS Augment POR20 | CE | NWA | BVL | Critical Facilities Sustaining (Field) | CFS CE NWA BVL BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE NWA NWA BD-CFS Augment POR20 | CE | NWA | NWA | Critical Facilities Sustaining (Field) | CFS CE NWA NWA BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | Active | EP
CFS CE NWA NWA BD-CFS Augment POR20 | CE | NWA | NWA | Critical Facilities Sustaining (Field) | CFS CE NWA NWA BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE TUL GAR SC-CFS Augment POR20 | CE | TUL | GAR | Critical Facilities Sustaining (Field) | CFS CE TUL GAR SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE TUL GAR SC-CFS Augment POR20 | CE | TUL | GAR | Critical Facilities Sustaining (Field) | CFS CE TUL GAR SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE TUL OWA BD-CFS Augment POR20 | CE | TUL | OWA | Critical Facilities Sustaining (Field) | CFS CE TUL OWA BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE TUL OWA BD-CFS Augment POR20 | CE | TUL | OWA | Critical Facilities Sustaining (Field) | CFS CE TUL OWA BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE TUL SAP GN-CFS Augment POR20 | CE | TUL | SAP | Critical Facilities Sustaining (Field) | CFS CE TUL SAP GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS CE TUL SAP GN-CFS Augment POR20 | CE | TUL | SAP | Critical Facilities Sustaining (Field) | CFS CE TUL SAP GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE TUL TUL BD-CFS Augment POR20 | CE | TUL | TUL | Critical Facilities Sustaining (Field) | CFS CE TUL TUL BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | Active | EP
CFS CE TUL TUL BD-CFS Augment POR20 | CE | TUL | TUL | Critical Facilities Sustaining (Field) | CFS CE TUL TUL BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE TUL TUL GN-CFS Augment POR20 | CE | TUL | TUL | Critical Facilities Sustaining (Field) | CFS CE TUL TUL GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | Active | EP
CFS CE TUL TUL GN-CFS Augment POR20 | CE | TUL | TUL | Critical Facilities Sustaining (Field) | CFS CE TUL TUL GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS CE TUL TUL SC-CFS Augment POR20 | CE | TUL | TUL | Critical Facilities Sustaining (Field) | CFS CE TUL TUL SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | Active | EP
CFS CE TUL TUL SC-CFS Augment POR20 | CE | TUL | TUL | Critical Facilities Sustaining (Field) | CFS CE TUL TUL SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON GRB RC-CFS Augment POR20 | NE | CON | GRB | Critical Facilities Sustaining (Field) | CFS NE CON GRB RC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON GRB RC-CFS Augment POR20 | NE | CON | GRB | Critical Facilities Sustaining (Field) | CFS NE CON GRB RC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON STN BS-CFS Augment POR20 | NE | CON | STN | Critical Facilities Sustaining (Field) | CFS NE CON STN BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON STN BS-CFS Augment POR20 | NE | CON | STN | Critical Facilities Sustaining (Field) | CFS NE CON STN BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE CON STN BS-CFS Augment POR20 - 2 | NE | CON | STN | Critical Facilities Sustaining (Field) | CFS NE CON STN BS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE CON STN BS-CFS Augment POR20 - 2 | NE | CON | STN | Critical Facilities Sustaining (Field) | CFS NE CON STN BS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD CRN BS-CFS Augment POR20 - 1 | NE | RHD | CRN | Critical Facilities Sustaining (Field) | CFS NE RHD CRN BS-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD CRN BS-CFS Augment POR20 - 1 | NE | RHD | CRN | Critical Facilities Sustaining (Field) | CFS NE RHD CRN BS-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD CRN BS-CFS Augment POR20 - 2 | NE | RHD | CRN | Critical Facilities Sustaining (Field) | CFS NE RHD CRN BS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD CRN BS-CFS Augment POR20 - 2 | NE | RHD | CRN | Critical Facilities Sustaining (Field) | CFS NE RHD CRN BS-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD EXT BU-CFS Augment POR20 | NE | RHD | EXT | Critical Facilities Sustaining (Field) | CFS NE RHD EXT BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD EXT BU-CFS Augment POR20 | NE | RHD | EXT | Critical Facilities Sustaining (Field) | CFS NE RHD EXT BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD EXT LM-CFS Augment POR20 | NE | RHD | EXT | Critical Facilities Sustaining (Field) | CFS NE RHD EXT LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD EXT LM-CFS Augment POR20 | NE | RHD | EXT | Critical Facilities Sustaining (Field) | CFS NE RHD EXT LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS NE RHD WWK BS-CFS Augment POR20 | NE | RHD | WWK | Critical Facilities Sustaining (Field) | CFS NE RHD WWK BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS NE RHD WWK BS-CFS Augment POR20 | NE | RHD | WWK | Critical Facilities Sustaining (Field) | CFS NE RHD WWK BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE BTR BTR BS-CFS Augment POR20 | SE | BTR | BTR | Critical Facilities Sustaining (Field) | CFS SE BTR BTR BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE BTR BTR BS-CFS Augment POR20 | SE | BTR | BTR | Critical Facilities Sustaining (Field) | CFS SE BTR BTR BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE BTR BTR BU-CFS Augment POR20 - 1 | SE | BTR | BTR | Critical Facilities Sustaining (Field) | CFS SE BTR BTR BU-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE BTR BTR BU-CFS Augment POR20 - 1 | SE | BTR | BTR | Critical Facilities Sustaining (Field) | CFS SE BTR BTR BU-CFS Augment POR20 - 1 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE BTR BTR BU-CFS Augment POR20 - 2 | SE | BTR | BTR | Critical Facilities Sustaining (Field) | CFS SE BTR BTR BU-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE BTR BTR BU-CFS Augment POR20 - 2 | SE | BTR | BTR | Critical Facilities Sustaining (Field) | CFS SE BTR BTR BU-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE BTR DNS BU-CFS Augment POR20 | SE | BTR | DNS | Critical Facilities Sustaining (Field) | CFS SE BTR DNS BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE BTR DNS BU-CFS Augment POR20 | SE | BTR | DNS | Critical Facilities Sustaining (Field) | CFS SE BTR DNS BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE BTR DVL BU-CFS Augment POR20 | SE | BTR | DVL | Critical Facilities Sustaining (Field) | CFS SE BTR DVL BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE BTR DVL BU-CFS Augment POR20 | SE | BTR | DVL | Critical Facilities Sustaining (Field) | CFS SE BTR DVL BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE BTR DVL HV-CFS Augment POR20 | SE | BTR | DVL | Critical Facilities Sustaining (Field) | CFS SE BTR DVL HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE BTR DVL HV-CFS Augment POR20 | SE | BTR | DVL | Critical Facilities Sustaining (Field) | CFS SE BTR DVL HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE BTR NTH HV-CFS Augment POR20 | SE | BTR | NTH | Critical Facilities Sustaining (Field) | CFS SE BTR NTH HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE BTR NTH HV-CFS Augment POR20 | SE | BTR | NTH | Critical Facilities Sustaining (Field) | CFS SE BTR NTH HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE BTR SPC BS-CFS Augment POR20 | SE | BTR | SPC | Critical Facilities Sustaining (Field) | CFS SE BTR SPC BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE BTR SPC BS-CFS Augment POR20 | SE | BTR | SPC | Critical Facilities Sustaining (Field) | CFS SE BTR SPC BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE GCT FWB BD-CFS Augment POR20 | SE | GCT | FWB | Critical Facilities Sustaining (Field) | CFS SE GCT FWB BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE GCT FWB BD-CFS Augment POR20 | SE | GCT | FWB | Critical Facilities Sustaining (Field) | CFS SE GCT FWB BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE GCT PNS BD-CFS Augment POR20 | SE | GCT | PNS | Critical Facilities Sustaining (Field) | CFS SE GCT PNS BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE GCT PNS BD-CFS Augment POR20 | SE | GCT | PNS | Critical Facilities Sustaining (Field) | CFS SE GCT PNS BD-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE GCT PNS RC-CFS Augment POR20 | SE | GCT | PNS | Critical Facilities Sustaining (Field) | CFS SE GCT PNS RC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE GCT PNS RC-CFS Augment POR20 | SE | GCT | PNS | Critical Facilities Sustaining (Field) | CFS SE GCT PNS RC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE LFY CRW BS-CFS Augment POR20 | SE | LFY | CRW | Critical Facilities Sustaining (Field) | CFS SE LFY CRW BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE LFY CRW BS-CFS Augment POR20 | SE | LFY | CRW | Critical Facilities Sustaining (Field) | CFS SE LFY CRW BS-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE NOR STB SC-CFS Augment POR20 - 2 | SE | NOR | STB | Critical Facilities Sustaining (Field) | CFS SE NOR STB SC-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS SE NOR STB SC-CFS Augment POR20 - 2 | SE | NOR | STB | Critical Facilities Sustaining (Field) | CFS SE NOR STB SC-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Deleted | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE NOR STB SC-CFS Augment POR20 - 2 | SE | NOR | STB | Critical Facilities Sustaining (Field) | CFS SE NOR STB SC-CFS Augment POR20 - 2 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS SW ARZ CHD DC-CFS Augment POR20 | SW | ARZ | CHD | Critical Facilities Sustaining (Field) | CFS SW ARZ CHD DC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | Active | EP
CFS SW ARZ CHD DC-CFS Augment POR20 | SW | ARZ | CHD | Critical Facilities Sustaining (Field) | CFS SW ARZ CHD DC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS VA HRD OCN BM-CFS Augment POR20 | VA | HRD | OCN | Critical Facilities Sustaining (Field) | CFS VA HRD OCN BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | Active | EP
CFS VA HRD OCN BM-CFS Augment POR20 | VA | HRD | OCN | Critical Facilities Sustaining (Field) | CFS VA HRD OCN BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2019-10-01 |  | Active | Log | New | SB-0023 | New | Approved | 2020-01-30 10:30 | Loading Activity Plan for 2020 Sustain Projects
CFS SE BTR DVL BM-CFS Augment POR20 | SE | BTR | DVL | Critical Facilities Sustaining (Field) | CFS SE BTR DVL BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE BTR DVL BM-CFS Augment POR20 | SE | BTR | DVL | Critical Facilities Sustaining (Field) | CFS SE BTR DVL BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0031 | New | Approved | 2020-01-21 09:44 | There are missing sustaing projects in POR Creating this CR to have them added
CFS SE BTR PLQ BM-CFS Augment POR20 | SE | BTR | PLQ | Critical Facilities Sustaining (Field) | CFS SE BTR PLQ BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE BTR PLQ BM-CFS Augment POR20 | SE | BTR | PLQ | Critical Facilities Sustaining (Field) | CFS SE BTR PLQ BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0031 | New | Approved | 2020-01-21 09:44 | There are missing sustaing projects in POR Creating this CR to have them added
CFS SE BTR PLQ BU-CFS Augment POR20 | SE | BTR | PLQ | Critical Facilities Sustaining (Field) | CFS SE BTR PLQ BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE BTR PLQ BU-CFS Augment POR20 | SE | BTR | PLQ | Critical Facilities Sustaining (Field) | CFS SE BTR PLQ BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0031 | New | Approved | 2020-01-21 09:44 | There are missing sustaing projects in POR Creating this CR to have them added
CFS SE GAN GNS BM-CFS Augment POR20 | SE | GAN | GNS | Critical Facilities Sustaining (Field) | CFS SE GAN GNS BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE GAN GNS BM-CFS Augment POR20 | SE | GAN | GNS | Critical Facilities Sustaining (Field) | CFS SE GAN GNS BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0031 | New | Approved | 2020-01-21 09:44 | There are missing sustaing projects in POR Creating this CR to have them added
CFS SE GAN OCL BM-CFS Augment POR20 | SE | GAN | OCL | Critical Facilities Sustaining (Field) | CFS SE GAN OCL BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE GAN OCL BM-CFS Augment POR20 | SE | GAN | OCL | Critical Facilities Sustaining (Field) | CFS SE GAN OCL BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0031 | New | Approved | 2020-01-21 09:44 | There are missing sustaing projects in POR Creating this CR to have them added
CFS SE GAN OCL SC-CFS Augment POR20 | SE | GAN | OCL | Critical Facilities Sustaining (Field) | CFS SE GAN OCL SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE GAN OCL SC-CFS Augment POR20 | SE | GAN | OCL | Critical Facilities Sustaining (Field) | CFS SE GAN OCL SC-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0031 | New | Approved | 2020-01-21 09:44 | There are missing sustaing projects in POR Creating this CR to have them added
CFS SE GCT CRV BM-CFS Augment POR20 | SE | GCT | CRV | Critical Facilities Sustaining (Field) | CFS SE GCT CRV BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE GCT CRV BM-CFS Augment POR20 | SE | GCT | CRV | Critical Facilities Sustaining (Field) | CFS SE GCT CRV BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0031 | New | Approved | 2020-01-21 09:44 | There are missing sustaing projects in POR Creating this CR to have them added
CFS SE GCT CRV RF-CFS Augment POR20 | SE | GCT | CRV | Critical Facilities Sustaining (Field) | CFS SE GCT CRV RF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE GCT CRV RF-CFS Augment POR20 | SE | GCT | CRV | Critical Facilities Sustaining (Field) | CFS SE GCT CRV RF-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0031 | New | Approved | 2020-01-21 09:44 | There are missing sustaing projects in POR Creating this CR to have them added
CFS SE GCT DES BM-CFS Augment POR20 | SE | GCT | DES | Critical Facilities Sustaining (Field) | CFS SE GCT DES BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE GCT DES BM-CFS Augment POR20 | SE | GCT | DES | Critical Facilities Sustaining (Field) | CFS SE GCT DES BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0031 | New | Approved | 2020-01-21 09:44 | There are missing sustaing projects in POR Creating this CR to have them added
CFS SE GCT NCV LM-CFS Augment POR20 | SE | GCT | NCV | Critical Facilities Sustaining (Field) | CFS SE GCT NCV LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE GCT NCV LM-CFS Augment POR20 | SE | GCT | NCV | Critical Facilities Sustaining (Field) | CFS SE GCT NCV LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0031 | New | Approved | 2020-01-21 09:44 | There are missing sustaing projects in POR Creating this CR to have them added
CFS SE LFY CRW BM-CFS Augment POR20 | SE | LFY | CRW | Critical Facilities Sustaining (Field) | CFS SE LFY CRW BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE LFY CRW BM-CFS Augment POR20 | SE | LFY | CRW | Critical Facilities Sustaining (Field) | CFS SE LFY CRW BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0031 | New | Approved | 2020-01-21 09:44 | There are missing sustaing projects in POR Creating this CR to have them added
CFS SE LFY CRW HV-CFS Augment POR20 | SE | LFY | CRW | Critical Facilities Sustaining (Field) | CFS SE LFY CRW HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE LFY CRW HV-CFS Augment POR20 | SE | LFY | CRW | Critical Facilities Sustaining (Field) | CFS SE LFY CRW HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0031 | New | Approved | 2020-01-21 09:44 | There are missing sustaing projects in POR Creating this CR to have them added
CFS SE LFY CRW LM-CFS Augment POR20 | SE | LFY | CRW | Critical Facilities Sustaining (Field) | CFS SE LFY CRW LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE LFY CRW LM-CFS Augment POR20 | SE | LFY | CRW | Critical Facilities Sustaining (Field) | CFS SE LFY CRW LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0031 | New | Approved | 2020-01-21 09:44 | There are missing sustaing projects in POR Creating this CR to have them added
CFS SE LFY FRK BM-CFS Augment POR20 | SE | LFY | FRK | Critical Facilities Sustaining (Field) | CFS SE LFY FRK BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE LFY FRK BM-CFS Augment POR20 | SE | LFY | FRK | Critical Facilities Sustaining (Field) | CFS SE LFY FRK BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0031 | New | Approved | 2020-01-21 09:44 | There are missing sustaing projects in POR Creating this CR to have them added
CFS SE LFY FRK GN-CFS Augment POR20 | SE | LFY | FRK | Critical Facilities Sustaining (Field) | CFS SE LFY FRK GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE LFY FRK GN-CFS Augment POR20 | SE | LFY | FRK | Critical Facilities Sustaining (Field) | CFS SE LFY FRK GN-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0031 | New | Approved | 2020-01-21 09:44 | There are missing sustaing projects in POR Creating this CR to have them added
CFS SE LFY LFY BU-CFS Augment POR20 | SE | LFY | LFY | Critical Facilities Sustaining (Field) | CFS SE LFY LFY BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE LFY LFY BU-CFS Augment POR20 | SE | LFY | LFY | Critical Facilities Sustaining (Field) | CFS SE LFY LFY BU-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0031 | New | Approved | 2020-01-21 09:44 | There are missing sustaing projects in POR Creating this CR to have them added
CFS SE LFY STM HV-CFS Augment POR20 | SE | LFY | STM | Critical Facilities Sustaining (Field) | CFS SE LFY STM HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE LFY STM HV-CFS Augment POR20 | SE | LFY | STM | Critical Facilities Sustaining (Field) | CFS SE LFY STM HV-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0031 | New | Approved | 2020-01-21 09:44 | There are missing sustaing projects in POR Creating this CR to have them added
CFS SE NOR KNN LM-CFS Augment POR20 | SE | NOR | KNN | Critical Facilities Sustaining (Field) | CFS SE NOR KNN LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE NOR KNN LM-CFS Augment POR20 | SE | NOR | KNN | Critical Facilities Sustaining (Field) | CFS SE NOR KNN LM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0031 | New | Approved | 2020-01-21 09:44 | There are missing sustaing projects in POR Creating this CR to have them added
CFS SE NOR LPL BM-CFS Augment POR20 | SE | NOR | LPL | Critical Facilities Sustaining (Field) | CFS SE NOR LPL BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE NOR LPL BM-CFS Augment POR20 | SE | NOR | LPL | Critical Facilities Sustaining (Field) | CFS SE NOR LPL BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0031 | New | Approved | 2020-01-21 09:44 | There are missing sustaing projects in POR Creating this CR to have them added
CFS SE NOR MCY BM-CFS Augment POR20 | SE | NOR | MCY | Critical Facilities Sustaining (Field) | CFS SE NOR MCY BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE NOR MCY BM-CFS Augment POR20 | SE | NOR | MCY | Critical Facilities Sustaining (Field) | CFS SE NOR MCY BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0031 | New | Approved | 2020-01-21 09:44 | There are missing sustaing projects in POR Creating this CR to have them added
CFS SE NOR MCY SC-CFS Augment POR20 - 2 | SE | NOR | MCY | Critical Facilities Sustaining (Field) | CFS SE NOR MCY SC-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE NOR MCY SC-CFS Augment POR20 - 2 | SE | NOR | MCY | Critical Facilities Sustaining (Field) | CFS SE NOR MCY SC-CFS Augment POR20 - 2 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0031 | New | Approved | 2020-01-21 09:44 | There are missing sustaing projects in POR Creating this CR to have them added
CFS SE NOR NOE BM-CFS Augment POR20 | SE | NOR | NOE | Critical Facilities Sustaining (Field) | CFS SE NOR NOE BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | EP
CFS SE NOR NOE BM-CFS Augment POR20 | SE | NOR | NOE | Critical Facilities Sustaining (Field) | CFS SE NOR NOE BM-CFS Augment POR20 | Labor | No Equipment | 1 |  | 2020-01-01 |  | Active | Log | New | SB-0031 | New | Approved | 2020-01-21 09:44 | There are missing sustaing projects in POR Creating this CR to have them added
CFG SE NOR MCY RK-CFG Deployment POR20 | SE | NOR | MCY | Critical Facilities Sustaining (Field) | CFG SE NOR MCY RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | Active | EP
CFG SE NOR MCY RK-CFG Deployment POR20 | SE | NOR | MCY | Critical Facilities Sustaining (Field) | CFG SE NOR MCY RK-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-15 |  | Active | Log | New | SN-0228 | New | Approved | 2020-02-07 14:33 | Missing 2020 Projects are needed to get added to POR
CFS CA ORG ORG GN-CFS Augment POR20 | CA | ORG | ORG | Critical Facilities Sustaining (Field) | CFS CA ORG ORG GN-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
CFS CA ORG ORG GN-CFS Augment POR20 | CA | ORG | ORG | Critical Facilities Sustaining (Field) | CFS CA ORG ORG GN-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Deleted | Log | New | SB-0046 | New | Approved | 2020-02-07 14:32 | New Projects have been added to EPS and now need to be added to POR
CFS CA ORG ORG GN-CFS Augment POR20 | CA | ORG | ORG | Critical Facilities Sustaining (Field) | CFS CA ORG ORG GN-CFS Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS NE CON STN RF-CFS Augment POR20 | NE | CON | STN | Critical Facilities Sustaining (Field) | CFS NE CON STN RF-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | EP
CFS NE CON STN RF-CFS Augment POR20 | NE | CON | STN | Critical Facilities Sustaining (Field) | CFS NE CON STN RF-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | New | SB-0046 | New | Approved | 2020-02-07 14:32 | New Projects have been added to EPS and now need to be added to POR
CFS VA HRD CHS BS-CFS Augment POR20 | VA | HRD | CHS | Critical Facilities Sustaining (Field) | CFS VA HRD CHS BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-20 |  | Active | EP
CFS VA HRD CHS BS-CFS Augment POR20 | VA | HRD | CHS | Critical Facilities Sustaining (Field) | CFS VA HRD CHS BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-20 |  | Active | Log | New | SB-0046 | New | Approved | 2020-02-07 14:32 | New Projects have been added to EPS and now need to be added to POR
CFS VA HRD CHS BU-CFS Augment POR20 | VA | HRD | CHS | Critical Facilities Sustaining (Field) | CFS VA HRD CHS BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-20 |  | Active | EP
CFS VA HRD CHS BU-CFS Augment POR20 | VA | HRD | CHS | Critical Facilities Sustaining (Field) | CFS VA HRD CHS BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-20 |  | Active | Log | New | SB-0046 | New | Approved | 2020-02-07 14:32 | New Projects have been added to EPS and now need to be added to POR
CFS VA HRD GLO BU-CFS Augment POR20 | VA | HRD | GLO | Critical Facilities Sustaining (Field) | CFS VA HRD GLO BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-20 |  | Active | EP
CFS VA HRD GLO BU-CFS Augment POR20 | VA | HRD | GLO | Critical Facilities Sustaining (Field) | CFS VA HRD GLO BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-01-01 | 2020-01-20 |  | Active | Log | New | SB-0046 | New | Approved | 2020-02-07 14:32 | New Projects have been added to EPS and now need to be added to POR
CFS VA HRD JCC FF-CFS Augment POR20 | VA | HRD | JCC | Critical Facilities Sustaining (Field) | CFS VA HRD JCC FF-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | EP
CFS VA HRD JCC FF-CFS Augment POR20 | VA | HRD | JCC | Critical Facilities Sustaining (Field) | CFS VA HRD JCC FF-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | New | SB-0046 | New | Approved | 2020-02-07 14:32 | New Projects have been added to EPS and now need to be added to POR
CFS VA HRD JEF FF-CFS Augment POR20 | VA | HRD | JEF | Critical Facilities Sustaining (Field) | CFS VA HRD JEF FF-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | EP
CFS VA HRD JEF FF-CFS Augment POR20 | VA | HRD | JEF | Critical Facilities Sustaining (Field) | CFS VA HRD JEF FF-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | New | SB-0046 | New | Approved | 2020-02-07 14:32 | New Projects have been added to EPS and now need to be added to POR
CFS VA HRD LTF FF-CFS Augment POR20 | VA | HRD | LTF | Critical Facilities Sustaining (Field) | CFS VA HRD LTF FF-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-20 |  | Active | EP
CFS VA HRD LTF FF-CFS Augment POR20 | VA | HRD | LTF | Critical Facilities Sustaining (Field) | CFS VA HRD LTF FF-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-20 |  | Active | Log | New | SB-0046 | New | Approved | 2020-02-07 14:32 | New Projects have been added to EPS and now need to be added to POR
CFS VA HRD NKT FF-CFS Augment POR20 | VA | HRD | NKT | Critical Facilities Sustaining (Field) | CFS VA HRD NKT FF-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-20 |  | Active | EP
CFS VA HRD NKT FF-CFS Augment POR20 | VA | HRD | NKT | Critical Facilities Sustaining (Field) | CFS VA HRD NKT FF-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-20 |  | Active | Log | New | SB-0046 | New | Approved | 2020-02-07 14:32 | New Projects have been added to EPS and now need to be added to POR
CFS VA HRD NWP BU-CFS Augment POR20 | VA | HRD | NWP | Critical Facilities Sustaining (Field) | CFS VA HRD NWP BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | EP
CFS VA HRD NWP BU-CFS Augment POR20 | VA | HRD | NWP | Critical Facilities Sustaining (Field) | CFS VA HRD NWP BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | New | SB-0046 | New | Approved | 2020-02-07 14:32 | New Projects have been added to EPS and now need to be added to POR
CFS VA HRD NWP FF-CFS Augment POR20 | VA | HRD | NWP | Critical Facilities Sustaining (Field) | CFS VA HRD NWP FF-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-20 |  | Active | EP
CFS VA HRD NWP FF-CFS Augment POR20 | VA | HRD | NWP | Critical Facilities Sustaining (Field) | CFS VA HRD NWP FF-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-20 |  | Active | Log | New | SB-0046 | New | Approved | 2020-02-07 14:32 | New Projects have been added to EPS and now need to be added to POR
CFS VA HRD PTM FF-CFS Augment POR20 | VA | HRD | PTM | Critical Facilities Sustaining (Field) | CFS VA HRD PTM FF-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-20 |  | Active | EP
CFS VA HRD PTM FF-CFS Augment POR20 | VA | HRD | PTM | Critical Facilities Sustaining (Field) | CFS VA HRD PTM FF-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-20 |  | Active | Log | New | SB-0046 | New | Approved | 2020-02-07 14:32 | New Projects have been added to EPS and now need to be added to POR
CFG SW ARZ BEL BD-CFG Deployment POR20 | SW | ARZ | BEL | Critical Facilities Sustaining (Field) | CFG SW ARZ BEL BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | EP
CFG SW ARZ BEL BD-CFG Deployment POR20 | SW | ARZ | BEL | Critical Facilities Sustaining (Field) | CFG SW ARZ BEL BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | Log | Undel | SN-0262 | New | Approved | 2020-02-28 09:40 | Adding new Grow Projects
CFG SW ARZ BEL BD-CFG Deployment POR20 | SW | ARZ | BEL | Critical Facilities Sustaining (Field) | CFG SW ARZ BEL BD-CFG Deployment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-20 |  | Active | Log | Undel | SN-0411 | New | Approved | 2020-03-27 15:08 | There are missing projects and projects that need to be removed as they are not in EPS or they are duplicates
CFS CA SAB SAB RC-CFS Augment POR20 | CA | SAB | SAB | Critical Facilities Sustaining (Field) | CFS CA SAB SAB RC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | Active | EP
CFS CA SAB SAB RC-CFS Augment POR20 | CA | SAB | SAB | Critical Facilities Sustaining (Field) | CFS CA SAB SAB RC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS CA SAN ESC BS-CFS Augment POR20 | CA | SAN | ESC | Critical Facilities Sustaining (Field) | CFS CA SAN ESC BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | Active | EP
CFS CA SAN ESC BS-CFS Augment POR20 | CA | SAN | ESC | Critical Facilities Sustaining (Field) | CFS CA SAN ESC BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS CE OMA BLV SC-CFS Augment POR20 | CE | OMA | BLV | Critical Facilities Sustaining (Field) | CFS CE OMA BLV SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-06-01 | 2020-06-01 |  | Active | EP
CFS CE OMA BLV SC-CFS Augment POR20 | CE | OMA | BLV | Critical Facilities Sustaining (Field) | CFS CE OMA BLV SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-06-01 | 2020-06-01 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS CE OMA CBL SC-CFS Augment POR20 | CE | OMA | CBL | Critical Facilities Sustaining (Field) | CFS CE OMA CBL SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-06-01 | 2020-06-01 |  | Active | EP
CFS CE OMA CBL SC-CFS Augment POR20 | CE | OMA | CBL | Critical Facilities Sustaining (Field) | CFS CE OMA CBL SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-06-01 | 2020-06-01 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS CE OMA ELK SC-CFS Augment POR20 | CE | OMA | ELK | Critical Facilities Sustaining (Field) | CFS CE OMA ELK SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-06-01 | 2020-06-01 |  | Active | EP
CFS CE OMA ELK SC-CFS Augment POR20 | CE | OMA | ELK | Critical Facilities Sustaining (Field) | CFS CE OMA ELK SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-06-01 | 2020-06-01 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS CE TUL BAR SC-CFS Augment POR20 | CE | TUL | BAR | Critical Facilities Sustaining (Field) | CFS CE TUL BAR SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-01 |  | Active | EP
CFS CE TUL BAR SC-CFS Augment POR20 | CE | TUL | BAR | Critical Facilities Sustaining (Field) | CFS CE TUL BAR SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-01 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS CE TUL CLA SC-CFS Augment POR20 | CE | TUL | CLA | Critical Facilities Sustaining (Field) | CFS CE TUL CLA SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-01 |  | Active | EP
CFS CE TUL CLA SC-CFS Augment POR20 | CE | TUL | CLA | Critical Facilities Sustaining (Field) | CFS CE TUL CLA SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-01 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS CE TUL IND SC-CFS Augment POR20 | CE | TUL | IND | Critical Facilities Sustaining (Field) | CFS CE TUL IND SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-01 |  | Active | EP
CFS CE TUL IND SC-CFS Augment POR20 | CE | TUL | IND | Critical Facilities Sustaining (Field) | CFS CE TUL IND SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-01 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS CE TUL QNC BS-CFS Augment POR20 | CE | TUL | QNC | Critical Facilities Sustaining (Field) | CFS CE TUL QNC BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-01 |  | Active | EP
CFS CE TUL QNC BS-CFS Augment POR20 | CE | TUL | QNC | Critical Facilities Sustaining (Field) | CFS CE TUL QNC BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-01 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS CE TUL TDC SC-CFS Augment POR20 | CE | TUL | TDC | Critical Facilities Sustaining (Field) | CFS CE TUL TDC SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-01 |  | Active | EP
CFS CE TUL TDC SC-CFS Augment POR20 | CE | TUL | TDC | Critical Facilities Sustaining (Field) | CFS CE TUL TDC SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-01 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS CE TUL WST SC-CFS Augment POR20 | CE | TUL | WST | Critical Facilities Sustaining (Field) | CFS CE TUL WST SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-01 |  | Active | EP
CFS CE TUL WST SC-CFS Augment POR20 | CE | TUL | WST | Critical Facilities Sustaining (Field) | CFS CE TUL WST SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-01 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS NE CON RKH HV-CFS Augment POR20 | NE | CON | RKH | Critical Facilities Sustaining (Field) | CFS NE CON RKH HV-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-01 |  | Active | EP
CFS NE CON RKH HV-CFS Augment POR20 | NE | CON | RKH | Critical Facilities Sustaining (Field) | CFS NE CON RKH HV-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-01 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS SW ARZ DGL RF-CFS Augment POR20 | SW | ARZ | DGL | Critical Facilities Sustaining (Field) | CFS SW ARZ DGL RF-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | Active | EP
CFS SW ARZ DGL RF-CFS Augment POR20 | SW | ARZ | DGL | Critical Facilities Sustaining (Field) | CFS SW ARZ DGL RF-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS SW LAS ERN LM-CFS Augment POR20 | SW | LAS | ERN | Critical Facilities Sustaining (Field) | CFS SW LAS ERN LM-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | Active | EP
CFS SW LAS ERN LM-CFS Augment POR20 | SW | LAS | ERN | Critical Facilities Sustaining (Field) | CFS SW LAS ERN LM-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS SW LAS TEN FF-CFS Augment POR20 | SW | LAS | TEN | Critical Facilities Sustaining (Field) | CFS SW LAS TEN FF-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | Active | EP
CFS SW LAS TEN FF-CFS Augment POR20 | SW | LAS | TEN | Critical Facilities Sustaining (Field) | CFS SW LAS TEN FF-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS SW LAS VLY FF-CFS Augment POR20 | SW | LAS | VLY | Critical Facilities Sustaining (Field) | CFS SW LAS VLY FF-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | Active | EP
CFS SW LAS VLY FF-CFS Augment POR20 | SW | LAS | VLY | Critical Facilities Sustaining (Field) | CFS SW LAS VLY FF-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS VA HRD CHS DC-CFS Augment POR20 | VA | HRD | CHS | Critical Facilities Sustaining (Field) | CFS VA HRD CHS DC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | Active | EP
CFS VA HRD CHS DC-CFS Augment POR20 | VA | HRD | CHS | Critical Facilities Sustaining (Field) | CFS VA HRD CHS DC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS VA HRD GBR DC-CFS Augment POR20 | VA | HRD | GBR | Critical Facilities Sustaining (Field) | CFS VA HRD GBR DC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-20 |  | Active | EP
CFS VA HRD GBR DC-CFS Augment POR20 | VA | HRD | GBR | Critical Facilities Sustaining (Field) | CFS VA HRD GBR DC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-05-20 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS VA HRD GBR RC-CFS Deployment POR20 | VA | HRD | GBR | Critical Facilities Sustaining (Field) | CFS VA HRD GBR RC-CFS Deployment POR20 | Labor | No Equipment | 1 | 2020-02-03 | 2020-02-20 |  | Active | EP
CFS VA HRD GBR RC-CFS Deployment POR20 | VA | HRD | GBR | Critical Facilities Sustaining (Field) | CFS VA HRD GBR RC-CFS Deployment POR20 | Labor | No Equipment | 1 | 2020-02-03 | 2020-02-20 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS VA HRD GLO DC-CFS Augment POR20 | VA | HRD | GLO | Critical Facilities Sustaining (Field) | CFS VA HRD GLO DC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | Active | EP
CFS VA HRD GLO DC-CFS Augment POR20 | VA | HRD | GLO | Critical Facilities Sustaining (Field) | CFS VA HRD GLO DC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS VA HRD GLO DC-CFS Augment POR20 | VA | HRD | GLO | Critical Facilities Sustaining (Field) | CFS VA HRD GLO DC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | Upd | SB-0134 | Schedule Change | Canceled | 2020-06-22 11:09 | Need to update the need by date on a few projects
CFS VA HRD HCK DC-CFS Augment POR20 | VA | HRD | HCK | Critical Facilities Sustaining (Field) | CFS VA HRD HCK DC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | Active | EP
CFS VA HRD HCK DC-CFS Augment POR20 | VA | HRD | HCK | Critical Facilities Sustaining (Field) | CFS VA HRD HCK DC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS VA HRD JEF DC-CFS Augment POR20 | VA | HRD | JEF | Critical Facilities Sustaining (Field) | CFS VA HRD JEF DC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | Active | EP
CFS VA HRD JEF DC-CFS Augment POR20 | VA | HRD | JEF | Critical Facilities Sustaining (Field) | CFS VA HRD JEF DC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS VA HRD JEF DC-CFS Augment POR20 | VA | HRD | JEF | Critical Facilities Sustaining (Field) | CFS VA HRD JEF DC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | Upd | SB-0134 | Schedule Change | Canceled | 2020-06-22 11:09 | Need to update the need by date on a few projects
CFS VA HRD LTF DC-CFS Augment POR20 | VA | HRD | LTF | Critical Facilities Sustaining (Field) | CFS VA HRD LTF DC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | Active | EP
CFS VA HRD LTF DC-CFS Augment POR20 | VA | HRD | LTF | Critical Facilities Sustaining (Field) | CFS VA HRD LTF DC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS VA HRD LTF DC-CFS Augment POR20 | VA | HRD | LTF | Critical Facilities Sustaining (Field) | CFS VA HRD LTF DC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | Upd | SB-0134 | Schedule Change | Canceled | 2020-06-22 11:09 | Need to update the need by date on a few projects
CFS VA HRD LTF HV-CFS Augment POR20 | VA | HRD | LTF | Critical Facilities Sustaining (Field) | CFS VA HRD LTF HV-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | Active | EP
CFS VA HRD LTF HV-CFS Augment POR20 | VA | HRD | LTF | Critical Facilities Sustaining (Field) | CFS VA HRD LTF HV-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS VA HRD NKT DC-CFS Augment POR20 | VA | HRD | NKT | Critical Facilities Sustaining (Field) | CFS VA HRD NKT DC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | Active | EP
CFS VA HRD NKT DC-CFS Augment POR20 | VA | HRD | NKT | Critical Facilities Sustaining (Field) | CFS VA HRD NKT DC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS VA HRD NKT DC-CFS Augment POR20 | VA | HRD | NKT | Critical Facilities Sustaining (Field) | CFS VA HRD NKT DC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | Upd | SB-0134 | Schedule Change | Canceled | 2020-06-22 11:09 | Need to update the need by date on a few projects
CFS VA HRD NRF BD-CFS Augment POR20 | VA | HRD | NRF | Critical Facilities Sustaining (Field) | CFS VA HRD NRF BD-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | Active | EP
CFS VA HRD NRF BD-CFS Augment POR20 | VA | HRD | NRF | Critical Facilities Sustaining (Field) | CFS VA HRD NRF BD-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS VA HRD NWP HV-CFS Augment POR20 | VA | HRD | NWP | Critical Facilities Sustaining (Field) | CFS VA HRD NWP HV-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | Active | EP
CFS VA HRD NWP HV-CFS Augment POR20 | VA | HRD | NWP | Critical Facilities Sustaining (Field) | CFS VA HRD NWP HV-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS VA HRD OAK GN-CFS Augment POR20 | VA | HRD | OAK | Critical Facilities Sustaining (Field) | CFS VA HRD OAK GN-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | Active | EP
CFS VA HRD OAK GN-CFS Augment POR20 | VA | HRD | OAK | Critical Facilities Sustaining (Field) | CFS VA HRD OAK GN-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS VA HRD PRA RC-CFS Augment POR20 | VA | HRD | PRA | Critical Facilities Sustaining (Field) | CFS VA HRD PRA RC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | Active | EP
CFS VA HRD PRA RC-CFS Augment POR20 | VA | HRD | PRA | Critical Facilities Sustaining (Field) | CFS VA HRD PRA RC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS VA HRD VBC DC-CFS Augment POR20 | VA | HRD | VBC | Critical Facilities Sustaining (Field) | CFS VA HRD VBC DC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-17 |  | Active | EP
CFS VA HRD VBC DC-CFS Augment POR20 | VA | HRD | VBC | Critical Facilities Sustaining (Field) | CFS VA HRD VBC DC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-17 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS VA HRD VBC DC-CFS Augment POR20 | VA | HRD | VBC | Critical Facilities Sustaining (Field) | CFS VA HRD VBC DC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-17 |  | Active | Log | Upd | SB-0134 | Schedule Change | Canceled | 2020-06-22 11:09 | Need to update the need by date on a few projects
CFS VA NVA DRA SC-CFS Augment POR20 | VA | NVA | DRA | Critical Facilities Sustaining (Field) | CFS VA NVA DRA SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-09 | 2020-03-20 |  | Active | EP
CFS VA NVA DRA SC-CFS Augment POR20 | VA | NVA | DRA | Critical Facilities Sustaining (Field) | CFS VA NVA DRA SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-01 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS VA NVA DRA SC-CFS Augment POR20 | VA | NVA | DRA | Critical Facilities Sustaining (Field) | CFS VA NVA DRA SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-09 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VA NVA DRA SC-CFS Augment POR20 | VA | NVA | DRA | Critical Facilities Sustaining (Field) | CFS VA NVA DRA SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-20 |  | Active | Log | Upd | SB-0134 | Schedule Change | Canceled | 2020-06-22 11:09 | Need to update the need by date on a few projects
CFS VA NVA FLK SC-CFS Augment POR20 | VA | NVA | FLK | Critical Facilities Sustaining (Field) | CFS VA NVA FLK SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-09 | 2020-03-20 |  | Active | EP
CFS VA NVA FLK SC-CFS Augment POR20 | VA | NVA | FLK | Critical Facilities Sustaining (Field) | CFS VA NVA FLK SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS VA NVA FLK SC-CFS Augment POR20 | VA | NVA | FLK | Critical Facilities Sustaining (Field) | CFS VA NVA FLK SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-09 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VA NVA FST SC-CFS Augment POR20 | VA | NVA | FST | Critical Facilities Sustaining (Field) | CFS VA NVA FST SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-09 | 2020-03-20 |  | Active | EP
CFS VA NVA FST SC-CFS Augment POR20 | VA | NVA | FST | Critical Facilities Sustaining (Field) | CFS VA NVA FST SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS VA NVA FST SC-CFS Augment POR20 | VA | NVA | FST | Critical Facilities Sustaining (Field) | CFS VA NVA FST SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-09 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VA NVA FST SC-CFS Augment POR20 | VA | NVA | FST | Critical Facilities Sustaining (Field) | CFS VA NVA FST SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-20 |  | Active | Log | Upd | SB-0134 | Schedule Change | Canceled | 2020-06-22 11:09 | Need to update the need by date on a few projects
CFS VA NVA GCR SC-CFS Augment POR20 | VA | NVA | GCR | Critical Facilities Sustaining (Field) | CFS VA NVA GCR SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-09 | 2020-03-20 |  | Active | EP
CFS VA NVA GCR SC-CFS Augment POR20 | VA | NVA | GCR | Critical Facilities Sustaining (Field) | CFS VA NVA GCR SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS VA NVA GCR SC-CFS Augment POR20 | VA | NVA | GCR | Critical Facilities Sustaining (Field) | CFS VA NVA GCR SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-09 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VA NVA GCR SC-CFS Augment POR20 | VA | NVA | GCR | Critical Facilities Sustaining (Field) | CFS VA NVA GCR SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-20 |  | Active | Log | Upd | SB-0134 | Schedule Change | Canceled | 2020-06-22 11:09 | Need to update the need by date on a few projects
CFS VA NVA MFD AC-CFS Augment POR20 | VA | NVA | MFD | Critical Facilities Sustaining (Field) | CFS VA NVA MFD AC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-09 | 2020-03-20 |  | Active | EP
CFS VA NVA MFD AC-CFS Augment POR20 | VA | NVA | MFD | Critical Facilities Sustaining (Field) | CFS VA NVA MFD AC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS VA NVA MFD AC-CFS Augment POR20 | VA | NVA | MFD | Critical Facilities Sustaining (Field) | CFS VA NVA MFD AC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-09 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VA NVA MFD AC-CFS Augment POR20 | VA | NVA | MFD | Critical Facilities Sustaining (Field) | CFS VA NVA MFD AC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-20 |  | Active | Log | Upd | SB-0134 | Schedule Change | Canceled | 2020-06-22 11:09 | Need to update the need by date on a few projects
CFS VA NVA MFD HV-CFS Augment POR20 | VA | NVA | MFD | Critical Facilities Sustaining (Field) | CFS VA NVA MFD HV-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-26 | 2020-02-20 |  | Active | EP
CFS VA NVA MFD HV-CFS Augment POR20 | VA | NVA | MFD | Critical Facilities Sustaining (Field) | CFS VA NVA MFD HV-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS VA NVA MFD HV-CFS Augment POR20 | VA | NVA | MFD | Critical Facilities Sustaining (Field) | CFS VA NVA MFD HV-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-26 | 2020-02-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VA NVA MFD HV-CFS Augment POR20 | VA | NVA | MFD | Critical Facilities Sustaining (Field) | CFS VA NVA MFD HV-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | Upd | SB-0134 | Schedule Change | Canceled | 2020-06-22 11:09 | Need to update the need by date on a few projects
CFS VA NVA MFD RC-CFS Augment POR20 | VA | NVA | MFD | Critical Facilities Sustaining (Field) | CFS VA NVA MFD RC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-09 | 2020-03-20 |  | Active | EP
CFS VA NVA MFD RC-CFS Augment POR20 | VA | NVA | MFD | Critical Facilities Sustaining (Field) | CFS VA NVA MFD RC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-04-01 | 2020-04-20 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS VA NVA MFD RC-CFS Augment POR20 | VA | NVA | MFD | Critical Facilities Sustaining (Field) | CFS VA NVA MFD RC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-09 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VA NVA MFD RC-CFS Augment POR20 | VA | NVA | MFD | Critical Facilities Sustaining (Field) | CFS VA NVA MFD RC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-20 |  | Active | Log | Upd | SB-0134 | Schedule Change | Canceled | 2020-06-22 11:09 | Need to update the need by date on a few projects
CFS VA NVA RHL HV-CFS Augment POR20 | VA | NVA | RHL | Critical Facilities Sustaining (Field) | CFS VA NVA RHL HV-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-25 | 2020-02-20 |  | Active | EP
CFS VA NVA RHL HV-CFS Augment POR20 | VA | NVA | RHL | Critical Facilities Sustaining (Field) | CFS VA NVA RHL HV-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-02 | 2020-03-02 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS VA NVA RHL HV-CFS Augment POR20 | VA | NVA | RHL | Critical Facilities Sustaining (Field) | CFS VA NVA RHL HV-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-25 | 2020-02-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VA NVA RHL HV-CFS Augment POR20 | VA | NVA | RHL | Critical Facilities Sustaining (Field) | CFS VA NVA RHL HV-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | Upd | SB-0134 | Schedule Change | Canceled | 2020-06-22 11:09 | Need to update the need by date on a few projects
CFS VA NVA WOX BU-CFS Augment POR20 | VA | NVA | WOX | Critical Facilities Sustaining (Field) | CFS VA NVA WOX BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-14 | 2020-02-20 |  | Active | EP
CFS VA NVA WOX BU-CFS Augment POR20 | VA | NVA | WOX | Critical Facilities Sustaining (Field) | CFS VA NVA WOX BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-17 | 2020-02-20 |  | Active | Log | New | SB-0049 | New | Approved | 2020-02-28 09:39 | Adding the new projects that are now in EPS
CFS VA NVA WOX BU-CFS Augment POR20 | VA | NVA | WOX | Critical Facilities Sustaining (Field) | CFS VA NVA WOX BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-14 | 2020-02-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VA NVA WOX BU-CFS Augment POR20 | VA | NVA | WOX | Critical Facilities Sustaining (Field) | CFS VA NVA WOX BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | Upd | SB-0134 | Schedule Change | Canceled | 2020-06-22 11:09 | Need to update the need by date on a few projects
CFS CE KAN DBY SC-CFS Augment POR20 | CE | KAN | DBY | Critical Facilities Sustaining (Field) | CFS CE KAN DBY SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | EP
CFS CE KAN DBY SC-CFS Augment POR20 | CE | KAN | DBY | Critical Facilities Sustaining (Field) | CFS CE KAN DBY SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CE KAN DCY SC-CFS Augment POR20 | CE | KAN | DCY | Critical Facilities Sustaining (Field) | CFS CE KAN DCY SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | EP
CFS CE KAN DCY SC-CFS Augment POR20 | CE | KAN | DCY | Critical Facilities Sustaining (Field) | CFS CE KAN DCY SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CE KAN HUT SC-CFS Augment POR20 | CE | KAN | HUT | Critical Facilities Sustaining (Field) | CFS CE KAN HUT SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | EP
CFS CE KAN HUT SC-CFS Augment POR20 | CE | KAN | HUT | Critical Facilities Sustaining (Field) | CFS CE KAN HUT SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CE KAN MNT SC-CFS Augment POR20 | CE | KAN | MNT | Critical Facilities Sustaining (Field) | CFS CE KAN MNT SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | EP
CFS CE KAN MNT SC-CFS Augment POR20 | CE | KAN | MNT | Critical Facilities Sustaining (Field) | CFS CE KAN MNT SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CE KAN SAL SC-CFS Augment POR20 | CE | KAN | SAL | Critical Facilities Sustaining (Field) | CFS CE KAN SAL SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | EP
CFS CE KAN SAL SC-CFS Augment POR20 | CE | KAN | SAL | Critical Facilities Sustaining (Field) | CFS CE KAN SAL SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CE KAN TOP SC-CFS Augment POR20 | CE | KAN | TOP | Critical Facilities Sustaining (Field) | CFS CE KAN TOP SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | EP
CFS CE KAN TOP SC-CFS Augment POR20 | CE | KAN | TOP | Critical Facilities Sustaining (Field) | CFS CE KAN TOP SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CE TUL BRD SC-CFS Augment POR20 | CE | TUL | BRD | Critical Facilities Sustaining (Field) | CFS CE TUL BRD SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-17 | 2020-03-20 |  | Active | EP
CFS CE TUL BRD SC-CFS Augment POR20 | CE | TUL | BRD | Critical Facilities Sustaining (Field) | CFS CE TUL BRD SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-17 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS CE TUL BRD SC-CFS Augment POR20 | CE | TUL | BRD | Critical Facilities Sustaining (Field) | CFS CE TUL BRD SC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-20 |  | Active | Log | Upd | SB-0134 | Schedule Change | Canceled | 2020-06-22 11:09 | Need to update the need by date on a few projects
CFS NE CON SFD AT-CFS Augment POR20 | NE | CON | SFD | Critical Facilities Sustaining (Field) | CFS NE CON SFD AT-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-28 | 2020-02-20 |  | Active | EP
CFS NE CON SFD AT-CFS Augment POR20 | NE | CON | SFD | Critical Facilities Sustaining (Field) | CFS NE CON SFD AT-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-28 | 2020-02-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS NE CON SFD AT-CFS Augment POR20 | NE | CON | SFD | Critical Facilities Sustaining (Field) | CFS NE CON SFD AT-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | Upd | SB-0134 | Schedule Change | Canceled | 2020-06-22 11:09 | Need to update the need by date on a few projects
CFS NE RHD CRN HV-CFS Augment POR20 - 1 | NE | RHD | CRN | Critical Facilities Sustaining (Field) | CFS NE RHD CRN HV-CFS Augment POR20 - 1 | Labor | No Equipment | 1 | 2020-02-28 | 2020-02-20 |  | Active | EP
CFS NE RHD CRN HV-CFS Augment POR20 - 1 | NE | RHD | CRN | Critical Facilities Sustaining (Field) | CFS NE RHD CRN HV-CFS Augment POR20 - 1 | Labor | No Equipment | 1 | 2020-02-28 | 2020-02-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS NE RHD CRN HV-CFS Augment POR20 - 1 | NE | RHD | CRN | Critical Facilities Sustaining (Field) | CFS NE RHD CRN HV-CFS Augment POR20 - 1 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | Upd | SB-0134 | Schedule Change | Canceled | 2020-06-22 11:09 | Need to update the need by date on a few projects
CFS NE RHD CRN HV-CFS Augment POR20 - 2 | NE | RHD | CRN | Critical Facilities Sustaining (Field) | CFS NE RHD CRN HV-CFS Augment POR20 - 2 | Labor | No Equipment | 1 | 2020-02-28 | 2020-02-20 |  | Active | EP
CFS NE RHD CRN HV-CFS Augment POR20 - 2 | NE | RHD | CRN | Critical Facilities Sustaining (Field) | CFS NE RHD CRN HV-CFS Augment POR20 - 2 | Labor | No Equipment | 1 | 2020-02-28 | 2020-02-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS NE RHD CRN HV-CFS Augment POR20 - 2 | NE | RHD | CRN | Critical Facilities Sustaining (Field) | CFS NE RHD CRN HV-CFS Augment POR20 - 2 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | Upd | SB-0134 | Schedule Change | Canceled | 2020-06-22 11:09 | Need to update the need by date on a few projects
CFS NE RHD CRN HV-CFS Augment POR20 - 3 | NE | RHD | CRN | Critical Facilities Sustaining (Field) | CFS NE RHD CRN HV-CFS Augment POR20 - 3 | Labor | No Equipment | 1 | 2020-03-09 | 2020-03-20 |  | Active | EP
CFS NE RHD CRN HV-CFS Augment POR20 - 3 | NE | RHD | CRN | Critical Facilities Sustaining (Field) | CFS NE RHD CRN HV-CFS Augment POR20 - 3 | Labor | No Equipment | 1 | 2020-03-09 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS NE RHD CRN HV-CFS Augment POR20 - 3 | NE | RHD | CRN | Critical Facilities Sustaining (Field) | CFS NE RHD CRN HV-CFS Augment POR20 - 3 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-20 |  | Active | Log | Upd | SB-0134 | Schedule Change | Canceled | 2020-06-22 11:09 | Need to update the need by date on a few projects
CFS NE RHD PAW HV-CFS Augment POR20 - 1 | NE | RHD | PAW | Critical Facilities Sustaining (Field) | CFS NE RHD PAW HV-CFS Augment POR20 - 1 | Labor | No Equipment | 1 | 2020-02-28 | 2020-02-20 |  | Active | EP
CFS NE RHD PAW HV-CFS Augment POR20 - 1 | NE | RHD | PAW | Critical Facilities Sustaining (Field) | CFS NE RHD PAW HV-CFS Augment POR20 - 1 | Labor | No Equipment | 1 | 2020-02-28 | 2020-02-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS NE RHD PAW HV-CFS Augment POR20 - 1 | NE | RHD | PAW | Critical Facilities Sustaining (Field) | CFS NE RHD PAW HV-CFS Augment POR20 - 1 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | Upd | SB-0134 | Schedule Change | Canceled | 2020-06-22 11:09 | Need to update the need by date on a few projects
CFS NE RHD PAW HV-CFS Augment POR20 - 2 | NE | RHD | PAW | Critical Facilities Sustaining (Field) | CFS NE RHD PAW HV-CFS Augment POR20 - 2 | Labor | No Equipment | 1 | 2020-02-28 | 2020-02-20 |  | Active | EP
CFS NE RHD PAW HV-CFS Augment POR20 - 2 | NE | RHD | PAW | Critical Facilities Sustaining (Field) | CFS NE RHD PAW HV-CFS Augment POR20 - 2 | Labor | No Equipment | 1 | 2020-02-28 | 2020-02-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS NE RHD PAW HV-CFS Augment POR20 - 2 | NE | RHD | PAW | Critical Facilities Sustaining (Field) | CFS NE RHD PAW HV-CFS Augment POR20 - 2 | Labor | No Equipment | 1 | 2020-02-01 | 2020-02-20 |  | Active | Log | Upd | SB-0134 | Schedule Change | Canceled | 2020-06-22 11:09 | Need to update the need by date on a few projects
CFS VA HRD GBR BS-CFS Augment POR20 | VA | HRD | GBR | Critical Facilities Sustaining (Field) | CFS VA HRD GBR BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | EP
CFS VA HRD GBR BS-CFS Augment POR20 | VA | HRD | GBR | Critical Facilities Sustaining (Field) | CFS VA HRD GBR BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VA HRD GLO BS-CFS Augment POR20 | VA | HRD | GLO | Critical Facilities Sustaining (Field) | CFS VA HRD GLO BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | EP
CFS VA HRD GLO BS-CFS Augment POR20 | VA | HRD | GLO | Critical Facilities Sustaining (Field) | CFS VA HRD GLO BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VA HRD HCK BS-CFS Augment POR20 | VA | HRD | HCK | Critical Facilities Sustaining (Field) | CFS VA HRD HCK BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | EP
CFS VA HRD HCK BS-CFS Augment POR20 | VA | HRD | HCK | Critical Facilities Sustaining (Field) | CFS VA HRD HCK BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VA HRD HCK BU-CFS Augment POR20 | VA | HRD | HCK | Critical Facilities Sustaining (Field) | CFS VA HRD HCK BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | EP
CFS VA HRD HCK BU-CFS Augment POR20 | VA | HRD | HCK | Critical Facilities Sustaining (Field) | CFS VA HRD HCK BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VA HRD JCC BS-CFS Augment POR20 | VA | HRD | JCC | Critical Facilities Sustaining (Field) | CFS VA HRD JCC BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | EP
CFS VA HRD JCC BS-CFS Augment POR20 | VA | HRD | JCC | Critical Facilities Sustaining (Field) | CFS VA HRD JCC BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VA HRD JEF BU-CFS Augment POR20 | VA | HRD | JEF | Critical Facilities Sustaining (Field) | CFS VA HRD JEF BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | EP
CFS VA HRD JEF BU-CFS Augment POR20 | VA | HRD | JEF | Critical Facilities Sustaining (Field) | CFS VA HRD JEF BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VA HRD LTF AC-CFS Augment POR20 | VA | HRD | LTF | Critical Facilities Sustaining (Field) | CFS VA HRD LTF AC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-17 | 2020-03-20 |  | Active | EP
CFS VA HRD LTF AC-CFS Augment POR20 | VA | HRD | LTF | Critical Facilities Sustaining (Field) | CFS VA HRD LTF AC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-17 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VA HRD LTF AC-CFS Augment POR20 | VA | HRD | LTF | Critical Facilities Sustaining (Field) | CFS VA HRD LTF AC-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-20 |  | Active | Log | Upd | SB-0134 | Schedule Change | Canceled | 2020-06-22 11:09 | Need to update the need by date on a few projects
CFS VA HRD LTF BS-CFS Augment POR20 | VA | HRD | LTF | Critical Facilities Sustaining (Field) | CFS VA HRD LTF BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | EP
CFS VA HRD LTF BS-CFS Augment POR20 | VA | HRD | LTF | Critical Facilities Sustaining (Field) | CFS VA HRD LTF BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VA HRD NKT BS-CFS Augment POR20 | VA | HRD | NKT | Critical Facilities Sustaining (Field) | CFS VA HRD NKT BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | EP
CFS VA HRD NKT BS-CFS Augment POR20 | VA | HRD | NKT | Critical Facilities Sustaining (Field) | CFS VA HRD NKT BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VA HRD NRF BS-CFS Augment POR20 | VA | HRD | NRF | Critical Facilities Sustaining (Field) | CFS VA HRD NRF BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | EP
CFS VA HRD NRF BS-CFS Augment POR20 | VA | HRD | NRF | Critical Facilities Sustaining (Field) | CFS VA HRD NRF BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VA HRD NWP BS-CFS Augment POR20 | VA | HRD | NWP | Critical Facilities Sustaining (Field) | CFS VA HRD NWP BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | EP
CFS VA HRD NWP BS-CFS Augment POR20 | VA | HRD | NWP | Critical Facilities Sustaining (Field) | CFS VA HRD NWP BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VA HRD PRA BS-CFS Augment POR20 | VA | HRD | PRA | Critical Facilities Sustaining (Field) | CFS VA HRD PRA BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | EP
CFS VA HRD PRA BS-CFS Augment POR20 | VA | HRD | PRA | Critical Facilities Sustaining (Field) | CFS VA HRD PRA BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VA HRD PTM BS-CFS Augment POR20 | VA | HRD | PTM | Critical Facilities Sustaining (Field) | CFS VA HRD PTM BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | EP
CFS VA HRD PTM BS-CFS Augment POR20 | VA | HRD | PTM | Critical Facilities Sustaining (Field) | CFS VA HRD PTM BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VA NAT MCB BU-CFS Augment POR20 | VA | NVA | MFD | Critical Facilities Sustaining (Field) | CFS VA NAT MCB BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-17 | 2020-03-20 |  | Active | EP
CFS VA NAT MCB BU-CFS Augment POR20 | VA | NVA | MFD | Critical Facilities Sustaining (Field) | CFS VA NAT MCB BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-17 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VA NAT MCB BU-CFS Augment POR20 | VA | NVA | MFD | Critical Facilities Sustaining (Field) | CFS VA NAT MCB BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-20 |  | Active | Log | Upd | SB-0134 | Schedule Change | Canceled | 2020-06-22 11:09 | Need to update the need by date on a few projects
CFS VA NVA DRA BS-CFS Augment POR20 | VA | NVA | DRA | Critical Facilities Sustaining (Field) | CFS VA NVA DRA BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | EP
CFS VA NVA DRA BS-CFS Augment POR20 | VA | NVA | DRA | Critical Facilities Sustaining (Field) | CFS VA NVA DRA BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VA NVA FBG BS-CFS Augment POR20 | VA | NVA | FBG | Critical Facilities Sustaining (Field) | CFS VA NVA FBG BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | EP
CFS VA NVA FBG BS-CFS Augment POR20 | VA | NVA | FBG | Critical Facilities Sustaining (Field) | CFS VA NVA FBG BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VA NVA FST BS-CFS Augment POR20 | VA | NVA | FST | Critical Facilities Sustaining (Field) | CFS VA NVA FST BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | EP
CFS VA NVA FST BS-CFS Augment POR20 | VA | NVA | FST | Critical Facilities Sustaining (Field) | CFS VA NVA FST BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VA NVA FST BU-CFS Augment POR20 | VA | NVA | FST | Critical Facilities Sustaining (Field) | CFS VA NVA FST BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-17 | 2020-03-20 |  | Active | EP
CFS VA NVA FST BU-CFS Augment POR20 | VA | NVA | FST | Critical Facilities Sustaining (Field) | CFS VA NVA FST BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-17 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VA NVA GCR BU-CFS Augment POR20 | VA | NVA | GCR | Critical Facilities Sustaining (Field) | CFS VA NVA GCR BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-17 | 2020-03-20 |  | Active | EP
CFS VA NVA GCR BU-CFS Augment POR20 | VA | NVA | GCR | Critical Facilities Sustaining (Field) | CFS VA NVA GCR BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-17 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VA NVA GCR BU-CFS Augment POR20 | VA | NVA | GCR | Critical Facilities Sustaining (Field) | CFS VA NVA GCR BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-20 |  | Active | Log | Upd | SB-0134 | Schedule Change | Canceled | 2020-06-22 11:09 | Need to update the need by date on a few projects
CFS VA NVA RHL BS-CFS Augment POR20 | VA | NVA | RHL | Critical Facilities Sustaining (Field) | CFS VA NVA RHL BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | EP
CFS VA NVA RHL BS-CFS Augment POR20 | VA | NVA | RHL | Critical Facilities Sustaining (Field) | CFS VA NVA RHL BS-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-04 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VA NVA RHL BU-CFS Augment POR20 | VA | NVA | RHL | Critical Facilities Sustaining (Field) | CFS VA NVA RHL BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-17 | 2020-03-20 |  | Active | EP
CFS VA NVA RHL BU-CFS Augment POR20 | VA | NVA | RHL | Critical Facilities Sustaining (Field) | CFS VA NVA RHL BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-17 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CFS VA NVA RHL BU-CFS Augment POR20 | VA | NVA | RHL | Critical Facilities Sustaining (Field) | CFS VA NVA RHL BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-01 | 2020-03-20 |  | Active | Log | Upd | SB-0134 | Schedule Change | Canceled | 2020-06-22 11:09 | Need to update the need by date on a few projects
CFS VA ROA RON BU-CFS Augment POR20 | VA | ROA | RON | Critical Facilities Sustaining (Field) | CFS VA ROA RON BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-06 | 2020-03-20 |  | Active | EP
CFS VA ROA RON BU-CFS Augment POR20 | VA | ROA | RON | Critical Facilities Sustaining (Field) | CFS VA ROA RON BU-CFS Augment POR20 | Labor | No Equipment | 1 | 2020-03-06 | 2020-03-20 |  | Active | Log | New | SB-0091 | New | Approved | 2020-03-27 15:24 | Needing to add missing projects and remove projects that are not in EPS or duplicated
CGN Replacement 3 | CA | ORG | RSM | Data Center Capacity | DTC CA ORG RSM CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2019-12-15 | 2020-09-16 |  | Active | EP
CGN Replacement 3 | CA | ORG | RSM | Data Center Capacity | DTC CA ORG RSM CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2019-12-15 | 2020-05-08 |  | Active | Log | Upd | SN-0322 | Schedule Change | Approved | 2020-03-02 16:18 | Updating POR with new schedule and adding 7 new projects
CGN Replacement 3 | CA | ORG | RSM | Data Center Capacity | DTC CA ORG RSM CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2019-12-15 | 2020-05-28 |  | Active | Log | Upd | SN-0554 | True up | Approved | 2020-05-13 11:45 | Adjusting April Capex variance of 28K to June as some of the activities slowed down due to current situation and will resume again Team is working to finalize the design for Arista deployment and border routers addition Moving 255K to Q3
CGN Replacement 3 | CA | ORG | RSM | Data Center Capacity | DTC CA ORG RSM CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2019-12-15 | 2020-09-16 |  | Active | Log | Upd | SN-0784 | Schedule Change | Approved | 2020-07-27 09:31 | CGN Migration date updates for RSM Elmwood and Wichita
CGN Replacement 6 | CA | SAN | FED | Data Center Capacity | DTC CA SAN FED CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-01-04 | 2020-05-27 |  | Active | EP
CGN Replacement 6 | CA | SAN | FED | Data Center Capacity | DTC CA SAN FED CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-01-04 | 2020-05-08 |  | Active | Log | Upd | SN-0322 | Schedule Change | Approved | 2020-03-02 16:18 | Updating POR with new schedule and adding 7 new projects
CGN Replacement 6 | CA | SAN | FED | Data Center Capacity | DTC CA SAN FED CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-01-04 | 2020-05-27 |  | Active | Log | Upd | SN-0554 | True up | Approved | 2020-05-13 11:45 | Adjusting April Capex variance of 28K to June as some of the activities slowed down due to current situation and will resume again Team is working to finalize the design for Arista deployment and border routers addition Moving 255K to Q3
CGN Replacement 8 | CE | KAN | WIC | Data Center Capacity | DTC CE KAN WIC CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-01-18 | 2020-09-08 |  | Active | EP
CGN Replacement 8 | CE | KAN | WIC | Data Center Capacity | DTC CE KAN WIC CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-01-18 | 2020-05-22 |  | Active | Log | Upd | SN-0322 | Schedule Change | Approved | 2020-03-02 16:18 | Updating POR with new schedule and adding 7 new projects
CGN Replacement 8 | CE | KAN | WIC | Data Center Capacity | DTC CE KAN WIC CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-01-18 | 2020-06-23 |  | Active | Log | Upd | SN-0554 | True up | Approved | 2020-05-13 11:45 | Adjusting April Capex variance of 28K to June as some of the activities slowed down due to current situation and will resume again Team is working to finalize the design for Arista deployment and border routers addition Moving 255K to Q3
CGN Replacement 8 | CE | KAN | WIC | Data Center Capacity | DTC CE KAN WIC CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-01-18 | 2020-09-08 |  | Active | Log | Upd | SN-0784 | Schedule Change | Approved | 2020-07-27 09:31 | CGN Migration date updates for RSM Elmwood and Wichita
CGN Replacement 5 | CE | OKC | OKC | Data Center Capacity | DTC CE OKC OKC CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2019-12-29 | 2020-05-13 |  | Active | EP
CGN Replacement 5 | CE | OKC | OKC | Data Center Capacity | DTC CE OKC OKC CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-12-29 | 2020-04-30 |  | Active | Log | Upd | SN-0322 | Schedule Change | Approved | 2020-03-02 16:18 | Updating POR with new schedule and adding 7 new projects
CGN Replacement 5 | CE | OKC | OKC | Data Center Capacity | DTC CE OKC OKC CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2019-12-29 | 2020-04-01 |  | Active | Log | Upd | SN-0416 | Schedule Change | Approved | 2020-03-31 09:43 | To update CGN Identifier 2, 4, 5 need by dates to 2019 in database only
CGN Replacement 5 | CE | OKC | OKC | Data Center Capacity | DTC CE OKC OKC CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2019-12-29 | 2020-05-13 |  | Active | Log | Upd | SN-0554 | True up | Approved | 2020-05-13 11:45 | Adjusting April Capex variance of 28K to June as some of the activities slowed down due to current situation and will resume again Team is working to finalize the design for Arista deployment and border routers addition Moving 255K to Q3
CGN Replacement 2 | CE | OMA | OMM | Data Center Capacity | DTC CE OMA OMM CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2019-12-08 | 2020-09-22 |  | Active | EP
CGN Replacement 2 | CE | OMA | OMM | Data Center Capacity | DTC CE OMA OMM CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-12-08 | 2020-04-30 |  | Active | Log | Upd | SN-0322 | Schedule Change | Approved | 2020-03-02 16:18 | Updating POR with new schedule and adding 7 new projects
CGN Replacement 2 | CE | OMA | OMM | Data Center Capacity | DTC CE OMA OMM CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2019-12-08 | 2020-04-01 |  | Active | Log | Upd | SN-0416 | Schedule Change | Approved | 2020-03-31 09:43 | To update CGN Identifier 2, 4, 5 need by dates to 2019 in database only
CGN Replacement 2 | CE | OMA | OMM | Data Center Capacity | DTC CE OMA OMM CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2019-12-08 | 2020-05-14 |  | Active | Log | Upd | SN-0554 | True up | Approved | 2020-05-13 11:45 | Adjusting April Capex variance of 28K to June as some of the activities slowed down due to current situation and will resume again Team is working to finalize the design for Arista deployment and border routers addition Moving 255K to Q3
CGN Replacement 2 | CE | OMA | OMM | Data Center Capacity | DTC CE OMA OMM CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2019-12-08 | 2020-09-22 |  | Active | Log | Upd | SN-0856 | Schedule Change | Approved | 2020-08-21 11:35 | CGN Migration date updates for Pensacola and Omaha
CGN Replacement 1 | SE | BTR | BTR | Data Center Capacity | DTC SE BTR BTR CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2019-11-17 | 2020-01-15 |  | Active | EP
CGN Replacement 9 | SE | NOR | ELM | Data Center Capacity | DTC SE NOR ELM CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-01-25 | 2020-12-15 |  | Active | EP
CGN Replacement 9 | SE | NOR | ELM | Data Center Capacity | DTC SE NOR ELM CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-01-25 | 2020-06-05 |  | Active | Log | Upd | SN-0322 | Schedule Change | Approved | 2020-03-02 16:18 | Updating POR with new schedule and adding 7 new projects
CGN Replacement 9 | SE | NOR | ELM | Data Center Capacity | DTC SE NOR ELM CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-01-25 | 2020-06-24 |  | Active | Log | Upd | SN-0554 | True up | Approved | 2020-05-13 11:45 | Adjusting April Capex variance of 28K to June as some of the activities slowed down due to current situation and will resume again Team is working to finalize the design for Arista deployment and border routers addition Moving 255K to Q3
CGN Replacement 9 | SE | NOR | ELM | Data Center Capacity | DTC SE NOR ELM CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-01-25 | 2020-12-15 |  | Active | Log | Upd | SN-0902 | Schedule Change | Approved | 2020-09-18 09:35 | CGN Migration date updates for Elmwood and Providence
CGN Replacement 4 | VA | HRD | NRF | Data Center Capacity | DTC VA HRD NRF CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2019-12-22 | 2020-06-10 |  | Active | EP
CGN Replacement 4 | VA | HRD | NRF | Data Center Capacity | DTC VA HRD NRF CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-12-22 | 2020-05-22 |  | Active | Log | Upd | SN-0322 | Schedule Change | Approved | 2020-03-02 16:18 | Updating POR with new schedule and adding 7 new projects
CGN Replacement 4 | VA | HRD | NRF | Data Center Capacity | DTC VA HRD NRF CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2019-12-22 | 2020-05-01 |  | Active | Log | Upd | SN-0416 | Schedule Change | Approved | 2020-03-31 09:43 | To update CGN Identifier 2, 4, 5 need by dates to 2019 in database only
CGN Replacement 4 | VA | HRD | NRF | Data Center Capacity | DTC VA HRD NRF CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2019-12-22 | 2020-06-10 |  | Active | Log | Upd | SN-0554 | True up | Approved | 2020-05-13 11:45 | Adjusting April Capex variance of 28K to June as some of the activities slowed down due to current situation and will resume again Team is working to finalize the design for Arista deployment and border routers addition Moving 255K to Q3
CGN Replacement 13 | SW | ARZ | CHD | Data Center Capacity | DTC SW ARZ CHD CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-02-22 | 2020-07-22 |  | Active | EP
CGN Replacement 13 | SW | ARZ | CHD | Data Center Capacity | DTC SW ARZ CHD CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-02-22 | 2020-06-19 |  | Active | Log | Upd | SN-0322 | Schedule Change | Approved | 2020-03-02 16:18 | Updating POR with new schedule and adding 7 new projects
CGN Replacement 13 | SW | ARZ | CHD | Data Center Capacity | DTC SW ARZ CHD CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-02-22 | 2020-07-22 |  | Active | Log | Upd | SN-0554 | True up | Approved | 2020-05-13 11:45 | Adjusting April Capex variance of 28K to June as some of the activities slowed down due to current situation and will resume again Team is working to finalize the design for Arista deployment and border routers addition Moving 255K to Q3
CGN Replacement 12 | SW | LAS | TEN | Data Center Capacity | DTC SW LAS TEN CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-02-15 | 2020-07-08 |  | Active | EP
CGN Replacement 12 | SW | LAS | TEN | Data Center Capacity | DTC SW LAS TEN CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-02-15 | 2020-07-08 |  | Active | Log | Upd | SN-0554 | True up | Approved | 2020-05-13 11:45 | Adjusting April Capex variance of 28K to June as some of the activities slowed down due to current situation and will resume again Team is working to finalize the design for Arista deployment and border routers addition Moving 255K to Q3
CGN Replacement 7 | VA | NVA | MFD | Data Center Capacity | DTC VA NVA MFD CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-01-11 | 2020-06-09 |  | Active | EP
CGN Replacement 7 | VA | NVA | MFD | Data Center Capacity | DTC VA NVA MFD CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-01-11 | 2020-05-22 |  | Active | Log | Upd | SN-0322 | Schedule Change | Approved | 2020-03-02 16:18 | Updating POR with new schedule and adding 7 new projects
CGN Replacement 7 | VA | NVA | MFD | Data Center Capacity | DTC VA NVA MFD CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-01-11 | 2020-06-09 |  | Active | Log | Upd | SN-0554 | True up | Approved | 2020-05-13 11:45 | Adjusting April Capex variance of 28K to June as some of the activities slowed down due to current situation and will resume again Team is working to finalize the design for Arista deployment and border routers addition Moving 255K to Q3
CGN Replacement 10 | COR | COR | DDR | Data Center Capacity | DTC CO COR DDR CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 |  |  |  |  | Deleted | EP
CGN Replacement 10 | COR | COR | DDR | Data Center Capacity | DTC CO COR DDR CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 |  |  |  |  | Deleted | Log | Del | SN-0554 | True up | Approved | 2020-05-13 11:45 | Adjusting April Capex variance of 28K to June as some of the activities slowed down due to current situation and will resume again Team is working to finalize the design for Arista deployment and border routers addition Moving 255K to Q3
CGN Replacement 11 | NE | RHD | PRV | Data Center Capacity | DTC NE RHD PRV CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-02-08 | 2020-12-15 |  | Active | EP
CGN Replacement 11 | NE | RHD | PRV | Data Center Capacity | DTC NE RHD PRV CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-02-08 | 2020-06-05 |  | Active | Log | Upd | SN-0322 | Schedule Change | Approved | 2020-03-02 16:18 | Updating POR with new schedule and adding 7 new projects
CGN Replacement 11 | NE | RHD | PRV | Data Center Capacity | DTC NE RHD PRV CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-02-08 | 2020-07-07 |  | Active | Log | Upd | SN-0554 | True up | Approved | 2020-05-13 11:45 | Adjusting April Capex variance of 28K to June as some of the activities slowed down due to current situation and will resume again Team is working to finalize the design for Arista deployment and border routers addition Moving 255K to Q3
CGN Replacement 11 | NE | RHD | PRV | Data Center Capacity | DTC NE RHD PRV CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-02-08 | 2020-12-15 |  | Active | Log | Upd | SN-0902 | Schedule Change | Approved | 2020-09-18 09:35 | CGN Migration date updates for Elmwood and Providence
CGN Replacement 14 | VA | ROA | RON | Data Center Capacity | DTC VA ROA RON CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-04-01 | 2020-07-23 |  | Active | EP
CGN Replacement 14 | VA | ROA | RON | Data Center Capacity | DTC VA ROA RON CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-04-01 | 2020-07-03 |  | Active | Log | New | SN-0322 | Schedule Change | Approved | 2020-03-02 16:18 | Updating POR with new schedule and adding 7 new projects
CGN Replacement 14 | VA | ROA | RON | Data Center Capacity | DTC VA ROA RON CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-04-01 | 2020-07-23 |  | Active | Log | Upd | SN-0554 | True up | Approved | 2020-05-13 11:45 | Adjusting April Capex variance of 28K to June as some of the activities slowed down due to current situation and will resume again Team is working to finalize the design for Arista deployment and border routers addition Moving 255K to Q3
CGN Replacement 15 | SE | GCT | PNS | Data Center Capacity | DTC SE GCT PNS CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-04-01 | 2020-09-02 |  | Active | EP
CGN Replacement 15 | SE | GCT | PNS | Data Center Capacity | DTC SE GCT PNS CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-04-01 | 2020-07-03 |  | Active | Log | New | SN-0322 | Schedule Change | Approved | 2020-03-02 16:18 | Updating POR with new schedule and adding 7 new projects
CGN Replacement 15 | SE | GCT | PNS | Data Center Capacity | DTC SE GCT PNS CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-04-01 | 2020-08-04 |  | Active | Log | Upd | SN-0554 | True up | Approved | 2020-05-13 11:45 | Adjusting April Capex variance of 28K to June as some of the activities slowed down due to current situation and will resume again Team is working to finalize the design for Arista deployment and border routers addition Moving 255K to Q3
CGN Replacement 15 | SE | GCT | PNS | Data Center Capacity | DTC SE GCT PNS CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-04-01 | 2020-09-02 |  | Active | Log | Upd | SN-0856 | Schedule Change | Approved | 2020-08-21 11:35 | CGN Migration date updates for Pensacola and Omaha
CGN Replacement 16 | SE | GAN | GNS | Data Center Capacity | DTC SE GAN GNS CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-04-01 | 2020-08-05 |  | Active | EP
CGN Replacement 16 | SE | GAN | GNS | Data Center Capacity | DTC SE GAN GNS CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-04-01 | 2020-07-17 |  | Active | Log | New | SN-0322 | Schedule Change | Approved | 2020-03-02 16:18 | Updating POR with new schedule and adding 7 new projects
CGN Replacement 16 | SE | GAN | GNS | Data Center Capacity | DTC SE GAN GNS CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-04-01 | 2020-08-05 |  | Active | Log | Upd | SN-0554 | True up | Approved | 2020-05-13 11:45 | Adjusting April Capex variance of 28K to June as some of the activities slowed down due to current situation and will resume again Team is working to finalize the design for Arista deployment and border routers addition Moving 255K to Q3
CGN Replacement 17 | SE | MGA | MCN | Data Center Capacity | DTC SE MGA MCN CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-04-01 | 2020-08-18 |  | Active | EP
CGN Replacement 17 | SE | MGA | MCN | Data Center Capacity | DTC SE MGA MCN CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-04-01 | 2020-07-17 |  | Active | Log | New | SN-0322 | Schedule Change | Approved | 2020-03-02 16:18 | Updating POR with new schedule and adding 7 new projects
CGN Replacement 17 | SE | MGA | MCN | Data Center Capacity | DTC SE MGA MCN CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-04-01 | 2020-08-18 |  | Active | Log | Upd | SN-0554 | True up | Approved | 2020-05-13 11:45 | Adjusting April Capex variance of 28K to June as some of the activities slowed down due to current situation and will resume again Team is working to finalize the design for Arista deployment and border routers addition Moving 255K to Q3
CGN Replacement 18 | CE | TUL | TUL | Data Center Capacity | DTC CE TUL TUL CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-04-15 | 2020-08-19 |  | Active | EP
CGN Replacement 18 | CE | TUL | TUL | Data Center Capacity | DTC CE TUL TUL CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-04-15 | 2020-07-31 |  | Active | Log | New | SN-0322 | Schedule Change | Approved | 2020-03-02 16:18 | Updating POR with new schedule and adding 7 new projects
CGN Replacement 18 | CE | TUL | TUL | Data Center Capacity | DTC CE TUL TUL CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-04-15 | 2020-08-19 |  | Active | Log | Upd | SN-0554 | True up | Approved | 2020-05-13 11:45 | Adjusting April Capex variance of 28K to June as some of the activities slowed down due to current situation and will resume again Team is working to finalize the design for Arista deployment and border routers addition Moving 255K to Q3
CGN Replacement 19 | CE | NWA | NWA | Data Center Capacity | DTC CE NWA NWA CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-04-15 | 2020-09-16 |  | Active | EP
CGN Replacement 19 | CE | NWA | NWA | Data Center Capacity | DTC CE NWA NWA CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-04-15 | 2020-07-31 |  | Active | Log | New | SN-0322 | Schedule Change | Approved | 2020-03-02 16:18 | Updating POR with new schedule and adding 7 new projects
CGN Replacement 19 | CE | NWA | NWA | Data Center Capacity | DTC CE NWA NWA CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-04-15 | 2020-09-08 |  | Active | Log | Upd | SN-0554 | True up | Approved | 2020-05-13 11:45 | Adjusting April Capex variance of 28K to June as some of the activities slowed down due to current situation and will resume again Team is working to finalize the design for Arista deployment and border routers addition Moving 255K to Q3
CGN Replacement 19 | CE | NWA | NWA | Data Center Capacity | DTC CE NWA NWA CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-04-15 | 2020-09-16 |  | Active | Log | Upd | SN-0784 | Schedule Change | Approved | 2020-07-27 09:31 | CGN Migration date updates for RSM Elmwood and Wichita
CGN Replacement 20 | NE | CLE | CLV | Data Center Capacity | DTC NE CLE CLV CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-08-30 | 2020-12-15 |  | Active | EP
CGN Replacement 20 | NE | CLE | CLV | Data Center Capacity | DTC NE CLE CLV CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-08-30 | 2020-09-30 |  | Active | Log | New | SN-0322 | Schedule Change | Approved | 2020-03-02 16:18 | Updating POR with new schedule and adding 7 new projects
CGN Replacement 20 | NE | CLE | CLV | Data Center Capacity | DTC NE CLE CLV CGN Replacement Augment POR20 | Chassis | 1x A10 Thunder TH3040 IN -- 1x A10 Thunder AX3000 | 2 | 2020-08-30 | 2020-12-15 |  | Active | Log | Upd | SN-0963 | Schedule Change | Approved | 2020-10-02 09:33 | CGN Migration date updates for Cleveland
DCFWLC DDR SRX4100 | COR | COR | DDR | Data Center Firewall Lifecycle | DCFWLC COR COR DDR SRX4100 DEPLOYMNET POR20 | Labor | No Equipment | 8 | 2020-06-20 | 2020-07-20 | 2020-10-20 | Active | EP
DCFWLC DDR SRX4100 | COR | COR | DDR | Data Center Firewall Lifecycle | DCFWLC COR COR DDR SRX4100 DEPLOYMNET POR20 | Labor | No Equipment | 12 | 2020-03-20 | 2020-07-20 | 2020-08-20 | Active | Log | New | SN-0085 | Cost Change | Approved | 2020-02-06 10:33 | DC Firewall LifeCycle 2020 load
DCFWLC DDR SRX4100 | COR | COR | DDR | Data Center Firewall Lifecycle | DCFWLC COR COR DDR SRX4100 DEPLOYMNET POR20 | Labor | No Equipment | 8 | 2020-06-20 | 2020-07-20 | 2020-10-20 | Active | Log | Upd | SN-0685 | True up | Approved | 2020-06-17 11:51 | True up for the month of May of 76104 76106 and 76108 budget and POR
DCFWLC DVY SRX4100 | COR | COR | DVY | Data Center Firewall Lifecycle | DCFWLC COR COR DVY SRX4100 Deployment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
DCFWLC DVY SRX4100 | COR | COR | DVY | Data Center Firewall Lifecycle | DCFWLC COR COR DVY SRX4100 Deployment POR20 | Labor | No Equipment | 4 | 2020-06-20 | 2020-08-20 | 2020-10-20 | Deleted | Log | New | SN-0085 | Cost Change | Approved | 2020-02-06 10:33 | DC Firewall LifeCycle 2020 load
DCFWLC DVY SRX4100 | COR | COR | DVY | Data Center Firewall Lifecycle | DCFWLC COR COR DVY SRX4100 Deployment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0685 | True up | Approved | 2020-06-17 11:51 | True up for the month of May of 76104 76106 and 76108 budget and POR
DCFWLC CHD SRX4100 | SW | ARZ | CHD | Data Center Firewall Lifecycle | DCFWLC SW ARZ CHD SRX4100 Deployment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
DCFWLC CHD SRX4100 | SW | ARZ | CHD | Data Center Firewall Lifecycle | DCFWLC SW ARZ CHD SRX4100 Deployment POR20 | Labor | No Equipment | 2 | 2020-07-20 | 2020-09-20 | 2020-11-20 | Deleted | Log | New | SN-0085 | Cost Change | Approved | 2020-02-06 10:33 | DC Firewall LifeCycle 2020 load
DCFWLC CHD SRX4100 | SW | ARZ | CHD | Data Center Firewall Lifecycle | DCFWLC SW ARZ CHD SRX4100 Deployment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0685 | True up | Approved | 2020-06-17 11:51 | True up for the month of May of 76104 76106 and 76108 budget and POR
ELK SRVR DDR | COR | COR | DDR | Data Center Network Health | DCNH COR COR DDR ELK SERVER DEPLOYMENT POR20 | Labor | No Equipment | 1 |  | 2020-07-20 |  | Active | EP
ELK SRVR DDR | COR | COR | DDR | Data Center Network Health | DCNH COR COR DDR ELK SERVER DEPLOYMENT POR20 | Labor | No Equipment | 1 |  | 2020-07-20 |  | Active | Log | New | SN-0129 | New | Approved | 2020-02-06 11:00
TUFIN SRVR DDR | COR | COR | DDR | Data Center Network Health | DCNH COR COR DDR TUFIN Server Deployment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
TUFIN SRVR DDR | COR | COR | DDR | Data Center Network Health | DCNH COR COR DDR TUFIN Server Deployment POR20 | Labor | No Equipment | 1 |  | 2020-10-20 |  | Deleted | Log | New | SN-0129 | New | Approved | 2020-02-06 11:00
TUFIN SRVR DDR | COR | COR | DDR | Data Center Network Health | DCNH COR COR DDR TUFIN Server Deployment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0685 | True up | Approved | 2020-06-17 11:51 | True up for the month of May of 76104 76106 and 76108 budget and POR
Grafana DDR | COR | COR | DDR | Data Center Network Health | DCNH COR COR DDR NetworkHealth POR20 | Labor | No Equipment | 1 |  | 2020-06-01 |  | Active | EP
Grafana DDR | COR | COR | DDR | Data Center Network Health | DCNH COR COR DDR NetworkHealth POR20 | Labor | No Equipment | 1 |  | 2020-06-01 |  | Active | Log | New | SN-0129 | New | Approved | 2020-02-06 11:00
ServiceNow DDR | COR | COR | DDR | Data Center Network Health | DCNH COR COR DDR ServiceNow POR20 | Labor | No Equipment | 1 |  | 2020-07-20 |  | Active | EP
ServiceNow DDR | COR | COR | DDR | Data Center Network Health | DCNH COR COR DDR ServiceNow POR20 | Labor | No Equipment | 1 |  | 2020-07-20 |  | Active | Log | New | SN-0129 | New | Approved | 2020-02-06 11:00
TOS2 DDR | COR | COR | DDR | Data Center Network Health | DCNH COR COR DDR TOS2 POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
TOS2 DDR | COR | COR | DDR | Data Center Network Health | DCNH COR COR DDR TOS2 POR20 | Labor | No Equipment | 1 |  | 2020-05-01 |  | Deleted | Log | New | SN-0129 | New | Approved | 2020-02-06 11:00
TOS2 DDR | COR | COR | DDR | Data Center Network Health | DCNH COR COR DDR TOS2 POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0685 | True up | Approved | 2020-06-17 11:51 | True up for the month of May of 76104 76106 and 76108 budget and POR
DCPS FMC4600 DDR | COR | COR | DDR | Data Center Perimeter Security | DCPS COR COR DDR FMC4600 Deployment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
DCPS FMC4600 DDR | COR | COR | DDR | Data Center Perimeter Security | DCPS COR COR DDR FMC4600 Deployment POR20 | Labor | No Equipment | 1 |  | 2020-04-30 |  | Deleted | Log | New | SN-0086 | New | Approved | 2020-02-06 10:34 | DC Perimeter Security 2020 load
DCPS FMC4600 DDR | COR | COR | DDR | Data Center Perimeter Security | DCPS COR COR DDR FMC4600 Deployment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0425 | Scope Change | Approved | 2020-04-10 14:16 | Update POR April 2020 due to change in Perimeter Security and other projects
DCPS FMC4600 F6L | COR | COR | P6L | Data Center Perimeter Security | DCPS COR COR P6L FP4600 Deployment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
DCPS FMC4600 F6L | COR | COR | P6L | Data Center Perimeter Security | DCPS COR COR P6L FP4600 Deployment POR20 | Labor | No Equipment | 1 |  | 2020-04-30 |  | Deleted | Log | New | SN-0086 | New | Approved | 2020-02-06 10:34 | DC Perimeter Security 2020 load
DCPS FMC4600 F6L | COR | COR | P6L | Data Center Perimeter Security | DCPS COR COR P6L FP4600 Deployment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0425 | Scope Change | Approved | 2020-04-10 14:16 | Update POR April 2020 due to change in Perimeter Security and other projects
DCPS FP9300 DDR | COR | COR | DDR | Data Center Perimeter Security | DCPS COR COR DDR FP9300 Deployment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
DCPS FP9300 DDR | COR | COR | DDR | Data Center Perimeter Security | DCPS COR COR DDR FP9300 Deployment POR20 | Labor | No Equipment | 1 |  | 2020-04-30 |  | Deleted | Log | New | SN-0086 | New | Approved | 2020-02-06 10:34 | DC Perimeter Security 2020 load
DCPS FP9300 DDR | COR | COR | DDR | Data Center Perimeter Security | DCPS COR COR DDR FP9300 Deployment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0425 | Scope Change | Approved | 2020-04-10 14:16 | Update POR April 2020 due to change in Perimeter Security and other projects
DCPS FP9300 DVY | COR | COR | DVY | Data Center Perimeter Security | DCPS COR COR DVY FP9300 Deployment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
DCPS FP9300 DVY | COR | COR | DVY | Data Center Perimeter Security | DCPS COR COR DVY FP9300 Deployment POR20 | Labor | No Equipment | 1 |  | 2020-04-20 |  | Deleted | Log | New | SN-0086 | New | Approved | 2020-02-06 10:34 | DC Perimeter Security 2020 load
DCPS FP9300 DVY | COR | COR | DVY | Data Center Perimeter Security | DCPS COR COR DVY FP9300 Deployment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0425 | Scope Change | Approved | 2020-04-10 14:16 | Update POR April 2020 due to change in Perimeter Security and other projects
DCPS PA3260 DDR | COR | COR | DDR | Data Center Perimeter Security | DCPS COR COR DDR PA3260 Deploy POR20 | Labor | No Equipment | 4 |  | 2020-02-20 | 2020-06-20 | Active | EP
DCPS PA3260 DDR | COR | COR | DDR | Data Center Perimeter Security | DCPS COR COR DDR PA3260 Deploy POR20 | Labor | No Equipment | 4 |  | 2020-02-20 |  | Active | Log | New | SN-0086 | New | Approved | 2020-02-06 10:34 | DC Perimeter Security 2020 load
DCPS PA3260 DDR | COR | COR | DDR | Data Center Perimeter Security | DCPS COR COR DDR PA3260 Deploy POR20 | Labor | No Equipment | 4 |  | 2020-02-20 | 2020-06-20 | Active | Log | Upd | SN-0685 | True up | Approved | 2020-06-17 11:51 | True up for the month of May of 76104 76106 and 76108 budget and POR
DCPS IPS DDR | COR | COR | DDR | Data Center Perimeter Security | DCPS COR COR DDR SRX1500 IPS POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
DCPS IPS DDR | COR | COR | DDR | Data Center Perimeter Security | DCPS COR COR DDR SRX1500 IPS POR20 | Labor | No Equipment | 1 |  | 2020-10-20 | 2020-10-20 | Deleted | Log | New | SN-0086 | New | Approved | 2020-02-06 10:34 | DC Perimeter Security 2020 load
DCPS IPS DDR | COR | COR | DDR | Data Center Perimeter Security | DCPS COR COR DDR SRX1500 IPS POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SN-0685 | True up | Approved | 2020-06-17 11:51 | True up for the month of May of 76104 76106 and 76108 budget and POR
CCAP licenses_AVJ | CA | ORG | AVJ | DOCSIS CMTS/CCAP | CMTS CA ORG AVJ CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_DNP | CA | ORG | DNP | DOCSIS CMTS/CCAP | CMTS CA ORG DNP CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_IRV | CA | ORG | IRV | DOCSIS CMTS/CCAP | CMTS CA ORG IRV CCAP Augment POR20 | License | CCAP license | 3 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_ORG | CA | ORG | ORG | DOCSIS CMTS/CCAP | CMTS CA ORG ORG CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_RSM | CA | ORG | RSM | DOCSIS CMTS/CCAP | CMTS CA ORG RSM CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_SAB | CA | SAB | SAB | DOCSIS CMTS/CCAP | CMTS CA SAB SAB CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_CHU | CA | SAN | CHU | DOCSIS CMTS/CCAP | CMTS CA SAN CHU CCAP Augment POR20 | License | CCAP license | 3 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_DWN | CA | SAN | DWN | DOCSIS CMTS/CCAP | CMTS CA SAN DWN CCAP Augment POR20 | License | CCAP license | 3 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_ELC | CA | SAN | ELC | DOCSIS CMTS/CCAP | CMTS CA SAN ELC CCAP Augment POR20 | License | CCAP license | 3 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_ESC | CA | SAN | ESC | DOCSIS CMTS/CCAP | CMTS CA SAN ESC CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_FED | CA | SAN | FED | DOCSIS CMTS/CCAP | CMTS CA SAN FED CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_OCE | CA | SAN | OCE | DOCSIS CMTS/CCAP | CMTS CA SAN OCE CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_PWY | CA | SAN | PWY | DOCSIS CMTS/CCAP | CMTS CA SAN PWY CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_VST | CA | SAN | VST | DOCSIS CMTS/CCAP | CMTS CA SAN VST CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_BER | CE | NWA | BER | DOCSIS CMTS/CCAP | CMTS CE NWA BER CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP blades_ BVL | CE | NWA | BVL | DOCSIS CMTS/CCAP | CMTS CE NWA BVL CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_FAY | CE | NWA | FAY | DOCSIS CMTS/CCAP | CMTS CE NWA FAY CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_SSP | CE | NWA | SSP | DOCSIS CMTS/CCAP | CMTS CE NWA SSP CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_DBY | CE | KAN | DBY | DOCSIS CMTS/CCAP | CMTS CE KAN DBY CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_MNT | CE | KAN | MNT | DOCSIS CMTS/CCAP | CMTS CE KAN MNT CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_MPN | CE | KAN | MPN | DOCSIS CMTS/CCAP | CMTS CE KAN MPN CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_NWT | CE | KAN | NWT | DOCSIS CMTS/CCAP | CMTS CE KAN NWT CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_WIC | CE | KAN | WIC | DOCSIS CMTS/CCAP | CMTS CE KAN WIC CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP blades_ WIC | CE | KAN | WIC | DOCSIS CMTS/CCAP | CMTS CE KAN WIC CCAP Augment POR20 | Card & Optics | CCAP blade and license | 4 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_BAR | CE | TUL | BAR | DOCSIS CMTS/CCAP | CMTS CE TUL BAR CCAP Augment POR20 | License | CCAP license | 3 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_BRD | CE | TUL | BRD | DOCSIS CMTS/CCAP | CMTS CE TUL BRD CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_CLA | CE | TUL | CLA | DOCSIS CMTS/CCAP | CMTS CE TUL CLA CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_CLH | CE | OKC | CLH | DOCSIS CMTS/CCAP | CMTS CE OKC CLH CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_DSH | CE | OKC | DSH | DOCSIS CMTS/CCAP | CMTS CE OKC DSH CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-02-01 |  | Active | EP
CCAP licenses_DTN | CE | TUL | DTN | DOCSIS CMTS/CCAP | CMTS CE TUL DTN CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_ELR | CE | OKC | ELR | DOCSIS CMTS/CCAP | CMTS CE OKC ELR CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_ILH | CE | OKC | ILH | DOCSIS CMTS/CCAP | CMTS CE OKC ILH CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_MOO | CE | OKC | MOO | DOCSIS CMTS/CCAP | CMTS CE OKC MOO CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_MWC | CE | OKC | MWC | DOCSIS CMTS/CCAP | CMTS CE OKC MWC CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_NCH | CE | OKC | NCH | DOCSIS CMTS/CCAP | CMTS CE OKC NCH CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_NEH | CE | OKC | NEH | DOCSIS CMTS/CCAP | CMTS CE OKC NEH CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_NOR | CE | OKC | NOR | DOCSIS CMTS/CCAP | CMTS CE OKC NOR CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP blades_ OKC 1 | CE | OKC | OKC | DOCSIS CMTS/CCAP | CMTS CE OKC OKC CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_OKC | CE | OKC | OKC | DOCSIS CMTS/CCAP | CMTS CE OKC OKC CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_OWA | CE | TUL | OWA | DOCSIS CMTS/CCAP | CMTS CE TUL OWA CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_QNC | CE | TUL | QNC | DOCSIS CMTS/CCAP | CMTS CE TUL QNC CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP blades_ QNC | CE | TUL | QNC | DOCSIS CMTS/CCAP | CMTS CE TUL QNC CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_SOH | CE | OKC | SOH | DOCSIS CMTS/CCAP | CMTS CE OKC SOH CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-02-01 |  | Active | EP
CCAP licenses_SRH | CE | OKC | SRH | DOCSIS CMTS/CCAP | CMTS CE OKC SRH CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_WEH | CE | OKC | WEH | DOCSIS CMTS/CCAP | CMTS CE OKC WEH CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_WLH | CE | OKC | WLH | DOCSIS CMTS/CCAP | CMTS CE OKC WLH CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP blades_ BLV | CE | OMA | BLV | DOCSIS CMTS/CCAP | CMTS CE OMA BLV CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_BLV | CE | OMA | BLV | DOCSIS CMTS/CCAP | CMTS CE OMA BLV CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_CBL | CE | OMA | CBL | DOCSIS CMTS/CCAP | CMTS CE OMA CBL CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_ELK | CE | OMA | ELK | DOCSIS CMTS/CCAP | CMTS CE OMA ELK CCAP Augment POR20 | License | CCAP license | 4 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_ONA | CE | OMA | ONA | DOCSIS CMTS/CCAP | CMTS CE OMA ONA CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_SOU | CE | OMA | SOU | DOCSIS CMTS/CCAP | CMTS CE OMA SOU CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP blades_ WES | CE | OMA | WES | DOCSIS CMTS/CCAP | CMTS CE OMA WES CCAP Augment POR20 | Card & Optics | CCAP blade and license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_WES | CE | OMA | WES | DOCSIS CMTS/CCAP | CMTS CE OMA WES CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_ENF | NE | CON | ENF | DOCSIS CMTS/CCAP | CMTS NE CON ENF CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_GLB | NE | CON | GLB | DOCSIS CMTS/CCAP | CMTS NE CON GLB CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_MAN | NE | CON | MAN | DOCSIS CMTS/CCAP | CMTS NE CON MAN CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_RKH | NE | CON | RKH | DOCSIS CMTS/CCAP | CMTS NE CON RKH CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_EXT | NE | RHD | EXT | DOCSIS CMTS/CCAP | CMTS NE RHD EXT CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_PAW | NE | RHD | PAW | DOCSIS CMTS/CCAP | CMTS NE RHD PAW CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_PRV | NE | RHD | PRV | DOCSIS CMTS/CCAP | CMTS NE RHD PRV CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_PTH | NE | RHD | PTH | DOCSIS CMTS/CCAP | CMTS NE RHD PTH CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP blades_ PTH | NE | RHD | PTH | DOCSIS CMTS/CCAP | CMTS NE RHD PTH CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_RMD | NE | RHD | RMD | DOCSIS CMTS/CCAP | CMTS NE RHD RMD CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_GNS | SE | GAN | GNS | DOCSIS CMTS/CCAP | CMTS SE GAN GNS CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_CRV | SE | GCT | CRV | DOCSIS CMTS/CCAP | CMTS SE GCT CRV CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_DES | SE | GCT | DES | DOCSIS CMTS/CCAP | CMTS SE GCT DES CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_NCV | SE | GCT | NCV | DOCSIS CMTS/CCAP | CMTS SE GCT NCV CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_PNS | SE | GCT | PNS | DOCSIS CMTS/CCAP | CMTS SE GCT PNS CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP blades_ PNS | SE | GCT | PNS | DOCSIS CMTS/CCAP | CMTS SE GCT PNS CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_BTR | SE | BTR | BTR | DOCSIS CMTS/CCAP | CMTS SE BTR BTR CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP blades_ CLR 1 | SE | NOR | CLR | DOCSIS CMTS/CCAP | CMTS SE NOR CLR CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_DNS | SE | BTR | DNS | DOCSIS CMTS/CCAP | CMTS SE BTR DNS CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_DST | SE | NOR | DST | DOCSIS CMTS/CCAP | CMTS SE NOR DST CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_ELM | SE | NOR | ELM | DOCSIS CMTS/CCAP | CMTS SE NOR ELM CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_GNZ | SE | BTR | GNZ | DOCSIS CMTS/CCAP | CMTS SE BTR GNZ CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_LFY | SE | LFY | LFY | DOCSIS CMTS/CCAP | CMTS SE LFY LFY CCAP Augment POR20 | License | CCAP license | 5 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_MCY | SE | NOR | MCY | DOCSIS CMTS/CCAP | CMTS SE NOR MCY CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_NOE | SE | NOR | NOE | DOCSIS CMTS/CCAP | CMTS SE NOR NOE CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_NTH | SE | BTR | NTH | DOCSIS CMTS/CCAP | CMTS SE BTR NTH CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_PLQ | SE | BTR | PLQ | DOCSIS CMTS/CCAP | CMTS SE BTR PLQ CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_SPC | SE | BTR | SPC | DOCSIS CMTS/CCAP | CMTS SE BTR SPC CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_HLT | SE | MGA | HLT | DOCSIS CMTS/CCAP | CMTS SE MGA HLT CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_MCN | SE | MGA | MCN | DOCSIS CMTS/CCAP | CMTS SE MGA MCN CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_WRB | SE | MGA | WRB | DOCSIS CMTS/CCAP | CMTS SE MGA WRB CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_BEL 1 | SW | ARZ | BEL | DOCSIS CMTS/CCAP | CMTS SW ARZ BEL CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_BEL 2 | SW | ARZ | BEL | DOCSIS CMTS/CCAP | CMTS SW ARZ BEL CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_BEL 3 | SW | ARZ | BEL | DOCSIS CMTS/CCAP | CMTS SW ARZ BEL CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_BEL 4 | SW | ARZ | BEL | DOCSIS CMTS/CCAP | CMTS SW ARZ BEL CCAP Augment POR20 | License | CCAP license | 3 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_CHD | SW | ARZ | CHD | DOCSIS CMTS/CCAP | CMTS SW ARZ CHD CCAP Augment POR20 | License | CCAP license | 7 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_FWL | SW | ARZ | FWL | DOCSIS CMTS/CCAP | CMTS SW ARZ FWL CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_GVA | SW | ARZ | GVA | DOCSIS CMTS/CCAP | CMTS SW ARZ GVA CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_MCD | SW | ARZ | MCD | DOCSIS CMTS/CCAP | CMTS SW ARZ MCD CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_MSA | SW | ARZ | MSA | DOCSIS CMTS/CCAP | CMTS SW ARZ MSA CCAP Augment POR20 | License | CCAP license | 5 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_NSC | SW | ARZ | NSC | DOCSIS CMTS/CCAP | CMTS SW ARZ NSC CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_PEO 1 | SW | ARZ | PEO | DOCSIS CMTS/CCAP | CMTS SW ARZ PEO CCAP Augment POR20 | License | CCAP license | 5 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_PEO 2 | SW | ARZ | PEO | DOCSIS CMTS/CCAP | CMTS SW ARZ PEO CCAP Augment POR20 | License | CCAP license | 3 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_SSC | SW | ARZ | SSC | DOCSIS CMTS/CCAP | CMTS SW ARZ SSC CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_VSA | SW | ARZ | VSA | DOCSIS CMTS/CCAP | CMTS SW ARZ VSA CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_ALI | SW | LAS | ALI | DOCSIS CMTS/CCAP | CMTS SW LAS ALI CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_BLU | SW | LAS | BLU | DOCSIS CMTS/CCAP | CMTS SW LAS BLU CCAP Augment POR20 | License | CCAP license | 7 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_HEN | SW | LAS | HEN | DOCSIS CMTS/CCAP | CMTS SW LAS HEN CCAP Augment POR20 | License | CCAP license | 5 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_TEN | SW | LAS | TEN | DOCSIS CMTS/CCAP | CMTS SW LAS TEN CCAP Augment POR20 | License | CCAP license | 3 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_CHS | VA | HRD | CHS | DOCSIS CMTS/CCAP | CMTS VA HRD CHS CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_GLO | VA | HRD | GLO | DOCSIS CMTS/CCAP | CMTS VA HRD GLO CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_HCK | VA | HRD | HCK | DOCSIS CMTS/CCAP | CMTS VA HRD HCK CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_LTF | VA | HRD | LTF | DOCSIS CMTS/CCAP | CMTS VA HRD LTF CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_NKT | VA | HRD | NKT | DOCSIS CMTS/CCAP | CMTS VA HRD NKT CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_NRF | VA | HRD | NRF | DOCSIS CMTS/CCAP | CMTS VA HRD NRF CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_NWP | VA | HRD | NWP | DOCSIS CMTS/CCAP | CMTS VA HRD NWP CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_OCN | VA | HRD | OCN | DOCSIS CMTS/CCAP | CMTS VA HRD OCN CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_PRA | VA | HRD | PRA | DOCSIS CMTS/CCAP | CMTS VA HRD PRA CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP blades_ PRA | VA | HRD | PRA | DOCSIS CMTS/CCAP | CMTS VA HRD PRA CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-01-06 | 2020-02-01 |  | Active | EP
CCAP licenses_VBC | VA | HRD | VBC | DOCSIS CMTS/CCAP | CMTS VA HRD VBC CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_FBG | VA | NVA | FBG | DOCSIS CMTS/CCAP | CMTS VA NVA FBG CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_FLK | VA | NVA | FLK | DOCSIS CMTS/CCAP | CMTS VA NVA FLK CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_GCR | VA | NVA | GCR | DOCSIS CMTS/CCAP | CMTS VA NVA GCR CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_MFD | VA | NVA | MFD | DOCSIS CMTS/CCAP | CMTS VA NVA MFD CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_RHL | VA | NVA | RHL | DOCSIS CMTS/CCAP | CMTS VA NVA RHL CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_TCR | VA | NVA | TCR | DOCSIS CMTS/CCAP | CMTS VA NVA TCR CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP licenses_RON | VA | ROA | RON | DOCSIS CMTS/CCAP | CMTS VA ROA RON CCAP Augment POR20 | License | CCAP license | 2 | 2020-01-06 | 2020-01-15 |  | Active | EP
CCAP blades_ NOR 2 | CE | OKC | NOR | DOCSIS CMTS/CCAP | CMTS CE OKC NOR CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-08-20 | 2020-09-20 |  | Active | EP
CCAP blades_ NOR 2 | CE | OKC | NOR | DOCSIS CMTS/CCAP | CMTS CE OKC NOR CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-07-06 | 2020-07-15 |  | Active | Log | Upd | SN-0048 | Schedule Change | Approved | 2020-02-06 10:20 | 1 Later quarter projects were showing v1 EPS projects in POR instead of the v2 projects This is being corercted for 18 projects in this CR
CCAP blades_ NOR 2 | CE | OKC | NOR | DOCSIS CMTS/CCAP | CMTS CE OKC NOR CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-08-20 | 2020-09-20 |  | Active | Log | Upd | SN-0799 | Schedule Change | Approved | 2020-07-31 14:25 | DOCSIS Licenses requested for Q3 will be delivered in August Realigning the plan based on the latest delivery schedule
CCAP blades_ OKC 2 | CE | OKC | OKC | DOCSIS CMTS/CCAP | CMTS CE OKC OKC CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-10-05 | 2020-10-15 |  | Active | EP
CCAP blades_ OKC 2 | CE | OKC | OKC | DOCSIS CMTS/CCAP | CMTS CE OKC OKC CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-10-05 | 2020-10-15 |  | Active | Log | Upd | SN-0048 | Schedule Change | Approved | 2020-02-06 10:20 | 1 Later quarter projects were showing v1 EPS projects in POR instead of the v2 projects This is being corercted for 18 projects in this CR
CCAP blades_ NWT | CE | KAN | NWT | DOCSIS CMTS/CCAP | CMTS CE KAN NWT CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-10-05 | 2020-10-15 |  | Active | EP
CCAP blades_ NWT | CE | KAN | NWT | DOCSIS CMTS/CCAP | CMTS CE KAN NWT CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-10-05 | 2020-10-15 |  | Active | Log | Upd | SN-0048 | Schedule Change | Approved | 2020-02-06 10:20 | 1 Later quarter projects were showing v1 EPS projects in POR instead of the v2 projects This is being corercted for 18 projects in this CR
CCAP blades_ SSP | CE | NWA | SSP | DOCSIS CMTS/CCAP | CMTS CE NWA SSP CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-07-06 | 2020-07-15 |  | Active | EP
CCAP blades_ SSP | CE | NWA | SSP | DOCSIS CMTS/CCAP | CMTS CE NWA SSP CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-07-06 | 2020-07-15 |  | Active | Log | Upd | SN-0048 | Schedule Change | Approved | 2020-02-06 10:20 | 1 Later quarter projects were showing v1 EPS projects in POR instead of the v2 projects This is being corercted for 18 projects in this CR
CCAP blades_ BRD 1 | CE | TUL | BRD | DOCSIS CMTS/CCAP | CMTS CE TUL BRD CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-08-20 | 2020-09-20 |  | Active | EP
CCAP blades_ BRD 1 | CE | TUL | BRD | DOCSIS CMTS/CCAP | CMTS CE TUL BRD CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-07-06 | 2020-07-15 |  | Active | Log | Upd | SN-0048 | Schedule Change | Approved | 2020-02-06 10:20 | 1 Later quarter projects were showing v1 EPS projects in POR instead of the v2 projects This is being corercted for 18 projects in this CR
CCAP blades_ BRD 1 | CE | TUL | BRD | DOCSIS CMTS/CCAP | CMTS CE TUL BRD CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-08-20 | 2020-09-20 |  | Active | Log | Upd | SN-0799 | Schedule Change | Approved | 2020-07-31 14:25 | DOCSIS Licenses requested for Q3 will be delivered in August Realigning the plan based on the latest delivery schedule
CCAP blades_ RKH | NE | CON | RKH | DOCSIS CMTS/CCAP | CMTS NE CON RKH CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-08-20 | 2020-09-20 |  | Active | EP
CCAP blades_ RKH | NE | CON | RKH | DOCSIS CMTS/CCAP | CMTS NE CON RKH CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-07-06 | 2020-07-15 |  | Active | Log | Upd | SN-0048 | Schedule Change | Approved | 2020-02-06 10:20 | 1 Later quarter projects were showing v1 EPS projects in POR instead of the v2 projects This is being corercted for 18 projects in this CR
CCAP blades_ RKH | NE | CON | RKH | DOCSIS CMTS/CCAP | CMTS NE CON RKH CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-08-20 | 2020-09-20 |  | Active | Log | Upd | SN-0799 | Schedule Change | Approved | 2020-07-31 14:25 | DOCSIS Licenses requested for Q3 will be delivered in August Realigning the plan based on the latest delivery schedule
CCAP blades_ PAW | NE | RHD | PAW | DOCSIS CMTS/CCAP | CMTS NE RHD PAW CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 2 | 2020-10-05 | 2020-10-15 |  | Active | EP
CCAP blades_ PAW | NE | RHD | PAW | DOCSIS CMTS/CCAP | CMTS NE RHD PAW CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 2 | 2020-10-05 | 2020-10-15 |  | Active | Log | Upd | SN-0048 | Schedule Change | Approved | 2020-02-06 10:20 | 1 Later quarter projects were showing v1 EPS projects in POR instead of the v2 projects This is being corercted for 18 projects in this CR
CCAP blades_ PRV | NE | RHD | PRV | DOCSIS CMTS/CCAP | CMTS NE RHD PRV CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 2 | 2020-10-05 | 2020-10-15 |  | Active | EP
CCAP blades_ PRV | NE | RHD | PRV | DOCSIS CMTS/CCAP | CMTS NE RHD PRV CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 2 | 2020-10-05 | 2020-10-15 |  | Active | Log | Upd | SN-0048 | Schedule Change | Approved | 2020-02-06 10:20 | 1 Later quarter projects were showing v1 EPS projects in POR instead of the v2 projects This is being corercted for 18 projects in this CR
CCAP blades_ GNS 1 | SE | GAN | GNS | DOCSIS CMTS/CCAP | CMTS SE GAN GNS CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-08-20 | 2020-09-20 |  | Active | EP
CCAP blades_ GNS 1 | SE | GAN | GNS | DOCSIS CMTS/CCAP | CMTS SE GAN GNS CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-07-06 | 2020-07-15 |  | Active | Log | Upd | SN-0048 | Schedule Change | Approved | 2020-02-06 10:20 | 1 Later quarter projects were showing v1 EPS projects in POR instead of the v2 projects This is being corercted for 18 projects in this CR
CCAP blades_ GNS 1 | SE | GAN | GNS | DOCSIS CMTS/CCAP | CMTS SE GAN GNS CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-08-20 | 2020-09-20 |  | Active | Log | Upd | SN-0799 | Schedule Change | Approved | 2020-07-31 14:25 | DOCSIS Licenses requested for Q3 will be delivered in August Realigning the plan based on the latest delivery schedule
CCAP blades_ GNS 2 | SE | GAN | GNS | DOCSIS CMTS/CCAP | CMTS SE GAN GNS CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-10-05 | 2020-10-15 |  | Active | EP
CCAP blades_ GNS 2 | SE | GAN | GNS | DOCSIS CMTS/CCAP | CMTS SE GAN GNS CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-10-05 | 2020-10-15 |  | Active | Log | Upd | SN-0048 | Schedule Change | Approved | 2020-02-06 10:20 | 1 Later quarter projects were showing v1 EPS projects in POR instead of the v2 projects This is being corercted for 18 projects in this CR
CCAP blades_ CLR 2 | SE | NOR | CLR | DOCSIS CMTS/CCAP | CMTS SE NOR CLR CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-07-06 | 2020-07-15 |  | Active | EP
CCAP blades_ CLR 2 | SE | NOR | CLR | DOCSIS CMTS/CCAP | CMTS SE NOR CLR CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-07-06 | 2020-07-15 |  | Active | Log | Upd | SN-0048 | Schedule Change | Approved | 2020-02-06 10:20 | 1 Later quarter projects were showing v1 EPS projects in POR instead of the v2 projects This is being corercted for 18 projects in this CR
CCAP blades_ NKT | VA | HRD | NKT | DOCSIS CMTS/CCAP | CMTS VA HRD NKT CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-09-01 | 2020-10-15 |  | Active | EP
CCAP blades_ NKT | VA | HRD | NKT | DOCSIS CMTS/CCAP | CMTS VA HRD NKT CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-09-01 | 2020-10-15 |  | Active | Log | Upd | SN-0048 | Schedule Change | Approved | 2020-02-06 10:20 | 1 Later quarter projects were showing v1 EPS projects in POR instead of the v2 projects This is being corercted for 18 projects in this CR
CCAP blades_ ELK | CE | OMA | ELK | DOCSIS CMTS/CCAP | CMTS CE OMA ELK CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-10-05 | 2020-10-15 |  | Active | EP
CCAP blades_ ELK | CE | OMA | ELK | DOCSIS CMTS/CCAP | CMTS CE OMA ELK CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-10-05 | 2020-10-15 |  | Active | Log | Upd | SN-0048 | Schedule Change | Approved | 2020-02-06 10:20 | 1 Later quarter projects were showing v1 EPS projects in POR instead of the v2 projects This is being corercted for 18 projects in this CR
CCAP blades_ ONA 2 | CE | OMA | ONA | DOCSIS CMTS/CCAP | CMTS CE OMA ONA CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-10-05 | 2020-10-15 |  | Active | EP
CCAP blades_ ONA 2 | CE | OMA | ONA | DOCSIS CMTS/CCAP | CMTS CE OMA ONA CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-10-05 | 2020-10-15 |  | Active | Log | Upd | SN-0048 | Schedule Change | Approved | 2020-02-06 10:20 | 1 Later quarter projects were showing v1 EPS projects in POR instead of the v2 projects This is being corercted for 18 projects in this CR
CCAP blades_ NOE | SE | NOR | NOE | DOCSIS CMTS/CCAP | CMTS SE NOR NOE CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-07-06 | 2020-07-15 |  | Active | EP
CCAP blades_ NOE | SE | NOR | NOE | DOCSIS CMTS/CCAP | CMTS SE NOR NOE CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-07-06 | 2020-07-15 |  | Active | Log | Upd | SN-0048 | Schedule Change | Approved | 2020-02-06 10:20 | 1 Later quarter projects were showing v1 EPS projects in POR instead of the v2 projects This is being corercted for 18 projects in this CR
CCAP blades_ NCV | SE | GCT | NCV | DOCSIS CMTS/CCAP | CMTS SE GCT NCV CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-07-06 | 2020-07-15 |  | Active | EP
CCAP blades_ NCV | SE | GCT | NCV | DOCSIS CMTS/CCAP | CMTS SE GCT NCV CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-07-06 | 2020-07-15 |  | Active | Log | Upd | SN-0048 | Schedule Change | Approved | 2020-02-06 10:20 | 1 Later quarter projects were showing v1 EPS projects in POR instead of the v2 projects This is being corercted for 18 projects in this CR
CCAP blades_ HLT | SE | MGA | HLT | DOCSIS CMTS/CCAP | CMTS SE MGA HLT CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-08-20 | 2020-09-20 |  | Active | EP
CCAP blades_ HLT | SE | MGA | HLT | DOCSIS CMTS/CCAP | CMTS SE MGA HLT CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-07-06 | 2020-07-15 |  | Active | Log | Upd | SN-0048 | Schedule Change | Approved | 2020-02-06 10:20 | 1 Later quarter projects were showing v1 EPS projects in POR instead of the v2 projects This is being corercted for 18 projects in this CR
CCAP blades_ HLT | SE | MGA | HLT | DOCSIS CMTS/CCAP | CMTS SE MGA HLT CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-08-20 | 2020-09-20 |  | Active | Log | Upd | SN-0799 | Schedule Change | Approved | 2020-07-31 14:25 | DOCSIS Licenses requested for Q3 will be delivered in August Realigning the plan based on the latest delivery schedule
CCAP blades_ FBG | VA | NVA | FBG | DOCSIS CMTS/CCAP | CMTS VA NVA FBG CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-06-04 | 2020-07-15 |  | Active | EP
CCAP blades_ FBG | VA | NVA | FBG | DOCSIS CMTS/CCAP | CMTS VA NVA FBG CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-06-04 | 2020-07-15 |  | Active | Log | Upd | SN-0048 | Schedule Change | Approved | 2020-02-06 10:20 | 1 Later quarter projects were showing v1 EPS projects in POR instead of the v2 projects This is being corercted for 18 projects in this CR
CCAP blades_ TCR 1 | VA | NVA | TCR | DOCSIS CMTS/CCAP | CMTS VA NVA TCR CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-06-04 | 2020-07-15 |  | Active | EP
CCAP blades_ TCR 1 | VA | NVA | TCR | DOCSIS CMTS/CCAP | CMTS VA NVA TCR CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-06-04 | 2020-07-15 |  | Active | Log | Upd | SN-0048 | Schedule Change | Approved | 2020-02-06 10:20 | 1 Later quarter projects were showing v1 EPS projects in POR instead of the v2 projects This is being corercted for 18 projects in this CR
CCAP blades_ TCR 2 | VA | NVA | TCR | DOCSIS CMTS/CCAP | CMTS VA NVA TCR CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-08-20 | 2020-09-20 |  | Active | EP
CCAP blades_ TCR 2 | VA | NVA | TCR | DOCSIS CMTS/CCAP | CMTS VA NVA TCR CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-09-04 | 2020-10-15 |  | Active | Log | Upd | SN-0048 | Schedule Change | Approved | 2020-02-06 10:20 | 1 Later quarter projects were showing v1 EPS projects in POR instead of the v2 projects This is being corercted for 18 projects in this CR
CCAP blades_ TCR 2 | VA | NVA | TCR | DOCSIS CMTS/CCAP | CMTS VA NVA TCR CCAP Augment POR20 v2 | Card & Optics | CCAP blade and license | 1 | 2020-08-20 | 2020-09-20 |  | Active | Log | Upd | SN-0799 | Schedule Change | Approved | 2020-07-31 14:25 | DOCSIS Licenses requested for Q3 will be delivered in August Realigning the plan based on the latest delivery schedule
CCAP blades_ NWA | CE | NWA | NWA | DOCSIS CMTS/CCAP | CMTS CE NWA NWA CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-10-05 | 2020-10-15 |  | Active | EP
CCAP blades_ JCY | CE | KAN | JCY | DOCSIS CMTS/CCAP | CMTS CE KAN JCY CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-10-05 | 2020-10-15 |  | Active | EP
CCAP blades_ STN | NE | CON | STN | DOCSIS CMTS/CCAP | CMTS NE CON STN CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-08-20 | 2020-09-20 |  | Active | EP
CCAP blades_ STN | NE | CON | STN | DOCSIS CMTS/CCAP | CMTS NE CON STN CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-08-20 | 2020-09-20 |  | Active | Log | Upd | SN-0799 | Schedule Change | Approved | 2020-07-31 14:25 | DOCSIS Licenses requested for Q3 will be delivered in August Realigning the plan based on the latest delivery schedule
CCAP blades_ CRN | NE | RHD | CRN | DOCSIS CMTS/CCAP | CMTS NE RHD CRN CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-10-05 | 2020-10-15 |  | Active | EP
CCAP blades_ LNC | NE | RHD | LNC | DOCSIS CMTS/CCAP | CMTS NE RHD LNC CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-08-20 | 2020-09-20 |  | Active | EP
CCAP blades_ LNC | NE | RHD | LNC | DOCSIS CMTS/CCAP | CMTS NE RHD LNC CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-08-20 | 2020-09-20 |  | Active | Log | Upd | SN-0799 | Schedule Change | Approved | 2020-07-31 14:25 | DOCSIS Licenses requested for Q3 will be delivered in August Realigning the plan based on the latest delivery schedule
CCAP blades_ NOR 1 | CE | OKC | NOR | DOCSIS CMTS/CCAP | CMTS CE OKC NOR CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-04-06 | 2020-04-15 |  | Active | EP
CCAP blades_ WLH | CE | OKC | WLH | DOCSIS CMTS/CCAP | CMTS CE OKC WLH CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-04-06 | 2020-04-15 |  | Active | EP
CCAP blades_ BRD 2 | CE | TUL | BRD | DOCSIS CMTS/CCAP | CMTS CE TUL BRD CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-04-06 | 2020-04-15 |  | Active | EP
CCAP blades_ ONA 1 | CE | OMA | ONA | DOCSIS CMTS/CCAP | CMTS CE OMA ONA CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-04-06 | 2020-04-15 |  | Active | EP
CCAP blades_ NRF | VA | HRD | NRF | DOCSIS CMTS/CCAP | CMTS VA HRD NRF CCAP Augment POR20 | Card & Optics | CCAP blade and license | 1 | 2020-03-05 | 2020-04-15 |  | Active | EP
FI CA SAN ELC El Cajon Integration POR20 | CA | SAN | ELC | Facilities Integration | FI CA SAN ELC El Cajon Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling |  |  |  |  | Deleted | EP
FI CA SAN ELC El Cajon Integration POR20 | CA | SAN | ELC | Facilities Integration | FI CA SAN ELC El Cajon Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling |  |  |  |  | Deleted | Log | Del | SN-0405 | Schedule Change | Approved | 2020-03-27 15:13 | Adjusting multiple facilities based on current trends and input from business owners in the field
FI CE OKC MWC Midwest City Integration POR20 | CE | OKC | MWC | Facilities Integration | FI CE OKC MWC Midwest City Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling |  |  |  |  | Deleted | EP
FI CE OKC MWC Midwest City Integration POR20 | CE | OKC | MWC | Facilities Integration | FI CE OKC MWC Midwest City Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling | 1 | 2020-03-01 | 2020-04-01 |  | Deleted | Log | Upd | SN-0167 | Schedule Change | Approved | 2020-02-06 11:21 | Oso Blanco and Mid West City were originally scheduled to have material start hitting in Jan and Feb No BOM s have been produced and still following up with the business owners to determine when material will begin to be ordered Pushing material out into
FI CE OKC MWC Midwest City Integration POR20 | CE | OKC | MWC | Facilities Integration | FI CE OKC MWC Midwest City Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling | 1 | 2020-05-01 | 2020-08-31 |  | Deleted | Log | Upd | SN-0333 | Scope Change | Canceled | 2020-03-17 09:55 | This CR moves approxmatiely 1 3M from Q1 into Q2 and Q3 (smoothed over four months) Detailed explanations for both facilities are attached
FI CE OKC MWC Midwest City Integration POR20 | CE | OKC | MWC | Facilities Integration | FI CE OKC MWC Midwest City Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling | 1 | 2020-05-01 | 2020-08-01 |  | Deleted | Log | Upd | SN-0374 | Schedule Change | Approved | 2020-03-19 15:12 | Oso Blanca - PPM 75860 and Midwest City PPM do not need the entire budget Parma Integration will need funds Shifting budget to fund Parma All funds being pushed into Q2 Q3
FI CE OKC MWC Midwest City Integration POR20 | CE | OKC | MWC | Facilities Integration | FI CE OKC MWC Midwest City Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling |  |  |  |  | Deleted | Log | Del | SN-0584 | COVID-19 Related | Approved | 2020-05-14 14:37 | Removing projects from the plan of record
FI NE CLE CLV Parma Integration POR20 | NE | CLE | CLV | Facilities Integration | FI NE CLE CLV Parma Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling | 1 | 2020-04-06 | 2020-12-01 |  | Active | EP
FI NE CLE CLV Parma Integration POR20 | NE | CLE | CLV | Facilities Integration | FI NE CLE CLV Parma Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling | 1 | 2020-04-06 | 2020-05-01 |  | Active | Log | Upd | SN-0109 | Scope Change | Approved | 2020-02-06 10:52 | Give back for (4) facilities Parma - give back of 1 5 M Project pushed into Q2 May need to come back and ask for this money later in the year Henderson - give back of 400K All admin work, nothing needs to be funded out of FI Jomax - Pushed to 2021-
FI NE CLE CLV Parma Integration POR20 | NE | CLE | CLV | Facilities Integration | FI NE CLE CLV Parma Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling | 1 | 2020-04-06 | 2020-12-01 |  | Active | Log | Upd | SN-0704 | Schedule Change | Approved | 2020-06-26 14:58 | This CR serves as an update to the FI financial plan based on forecast after deferrals Major updates to Santa Barbara Material Schedule that pushes out labor Also expect 200K from CF to fund Orange
FI SW LAS OSB Oso Blanca Integration POR20 | SW | LAS | OSB | Facilities Integration | FI SW LAS OSB Oso Blanca Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling | 1 | 2020-05-01 | 2020-08-01 |  | Active | EP
FI SW LAS OSB Oso Blanca Integration POR20 | SW | LAS | OSB | Facilities Integration | FI SW LAS OSB Oso Blanca Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling | 1 | 2020-03-01 | 2020-04-01 |  | Active | Log | Upd | SN-0167 | Schedule Change | Approved | 2020-02-06 11:21 | Oso Blanco and Mid West City were originally scheduled to have material start hitting in Jan and Feb No BOM s have been produced and still following up with the business owners to determine when material will begin to be ordered Pushing material out into
FI SW LAS OSB Oso Blanca Integration POR20 | SW | LAS | OSB | Facilities Integration | FI SW LAS OSB Oso Blanca Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling | 1 | 2020-05-01 | 2020-08-20 |  | Active | Log | Upd | SN-0333 | Scope Change | Canceled | 2020-03-17 09:55 | This CR moves approxmatiely 1 3M from Q1 into Q2 and Q3 (smoothed over four months) Detailed explanations for both facilities are attached
FI SW LAS OSB Oso Blanca Integration POR20 | SW | LAS | OSB | Facilities Integration | FI SW LAS OSB Oso Blanca Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling | 1 | 2020-05-01 | 2020-08-01 |  | Active | Log | Upd | SN-0374 | Schedule Change | Approved | 2020-03-19 15:12 | Oso Blanca - PPM 75860 and Midwest City PPM do not need the entire budget Parma Integration will need funds Shifting budget to fund Parma All funds being pushed into Q2 Q3
FI CA SAN CHU Chula Vista Integration POR20 | CA | SAN | CHU | Facilities Integration | FI CA SAN CHU Chula Vista Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling |  |  |  |  | Deleted | EP
FI CA SAN CHU Chula Vista Integration POR20 | CA | SAN | CHU | Facilities Integration | FI CA SAN CHU Chula Vista Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling | 1 | 2020-09-15 | 2020-12-31 | 2020-05-15 | Deleted | Log | Upd | SN-0405 | Schedule Change | Approved | 2020-03-27 15:13 | Adjusting multiple facilities based on current trends and input from business owners in the field
FI CA SAN CHU Chula Vista Integration POR20 | CA | SAN | CHU | Facilities Integration | FI CA SAN CHU Chula Vista Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling |  |  |  |  | Deleted | Log | Del | SN-0531 | COVID-19 Related | Approved | 2020-05-07 10:54 | updating POR based on Deferrals for Facilities Integration
FI SW LAS HEN Henderson Integration POR20 | NE | CLE | CLV | Facilities Integration | FI NE CLE CLV Parma Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling |  |  |  |  | Deleted | EP
FI SW LAS HEN Henderson Integration POR20 | NE | CLE | CLV | Facilities Integration | FI NE CLE CLV Parma Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling |  |  |  |  | Deleted | Log | Del | SN-1045 | Schedule Change | Approved | 2020-11-13 09:56 | removing deferred projects from the system no financial impact These did not have a PPM associated with them and were causing errors
FI SW LAS ERN CB Product Move POR20 | NE | CLE | CLV | Facilities Integration | FI NE CLE CLV Parma Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling |  |  |  |  | Deleted | EP
FI SW LAS ERN CB Product Move POR20 | NE | CLE | CLV | Facilities Integration | FI NE CLE CLV Parma Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling |  |  |  |  | Deleted | Log | Del | SN-1045 | Schedule Change | Approved | 2020-11-13 09:56 | removing deferred projects from the system no financial impact These did not have a PPM associated with them and were causing errors
FI SW LAS ERN Ernest May Integration POR20 | NE | CLE | CLV | Facilities Integration | FI NE CLE CLV Parma Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling |  |  |  |  | Deleted | EP
FI SW LAS ERN Ernest May Integration POR20 | NE | CLE | CLV | Facilities Integration | FI NE CLE CLV Parma Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling |  |  |  |  | Deleted | Log | Del | SN-1045 | Schedule Change | Approved | 2020-11-13 09:56 | removing deferred projects from the system no financial impact These did not have a PPM associated with them and were causing errors
FI SW LAS CEN CB Product Move POR20 | NE | CLE | CLV | Facilities Integration | FI NE CLE CLV Parma Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling |  |  |  |  | Deleted | EP
FI SW LAS CEN CB Product Move POR20 | NE | CLE | CLV | Facilities Integration | FI NE CLE CLV Parma Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling |  |  |  |  | Deleted | Log | Del | SN-1045 | Schedule Change | Approved | 2020-11-13 09:56 | removing deferred projects from the system no financial impact These did not have a PPM associated with them and were causing errors
FI SW ARZ JMX Jomax Integration POR20 | NE | CLE | CLV | Facilities Integration | FI NE CLE CLV Parma Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling |  |  |  |  | Deleted | EP
FI SW ARZ JMX Jomax Integration POR20 | NE | CLE | CLV | Facilities Integration | FI NE CLE CLV Parma Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling |  |  |  |  | Deleted | Log | Del | SN-1045 | Schedule Change | Approved | 2020-11-13 09:56 | removing deferred projects from the system no financial impact These did not have a PPM associated with them and were causing errors
FI CA SAB SAB Santa Barbara Integration POR20 | CA | SAB | SAB | Facilities Integration | FI CA SAB SAB Santa Barbara Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling | 1 | 2020-07-06 | 2020-12-15 |  | Active | EP
FI CA SAB SAB Santa Barbara Integration POR20 | CA | SAB | SAB | Facilities Integration | FI CA SAB SAB Santa Barbara Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling | 1 | 2020-07-06 | 2020-12-15 |  | Active | Log | Upd | SN-0440 | New | Approved | 2020-04-10 14:17 | Moving Funding from Topside to fund Orange and Santa Barbara PPMs
FI NE CON STN Southington Integration POR20 | NE | CLE | CLV | Facilities Integration | FI NE CLE CLV Parma Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling |  |  |  |  | Deleted | EP
FI NE CON STN Southington Integration POR20 | NE | CLE | CLV | Facilities Integration | FI NE CLE CLV Parma Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling |  |  |  |  | Deleted | Log | Del | SN-1045 | Schedule Change | Approved | 2020-11-13 09:56 | removing deferred projects from the system no financial impact These did not have a PPM associated with them and were causing errors
FI CA ORG ORG Orange Integration POR20 | CA | ORG | ORG | Facilities Integration | FI CA ORG ORG Orange Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling | 1 | 2020-04-08 | 2020-11-15 |  | Active | EP
FI CA ORG ORG Orange Integration POR20 | CA | ORG | ORG | Facilities Integration | FI CA ORG ORG Orange Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling | 1 | 2020-04-08 | 2020-11-15 |  | Active | Log | Upd | SN-0440 | New | Approved | 2020-04-10 14:17 | Moving Funding from Topside to fund Orange and Santa Barbara PPMs
FI NE RHD PRV Providence Integration POR20 | NE | RHD | PRV | Facilities Integration | FI NE RHD PRV Providence Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling |  |  |  |  | Deleted | EP
FI NE RHD PRV Providence Integration POR20 | NE | RHD | PRV | Facilities Integration | FI NE RHD PRV Providence Integration Deployment POR20 | Standard | MTC.MTC Hub Signaling |  |  |  |  | Deleted | Log | Del | SN-0531 | COVID-19 Related | Approved | 2020-05-07 10:54 | updating POR based on Deferrals for Facilities Integration
REP_CE.OKC.OKC.REPACK | CE | OKC | OKC | FCC Repack | FCC CE OKC OKC Channel Move Alignment POR20 | Chassis | Channel Move / Inca 8VSB / Wade WH | 2 | 2020-01-18 | 2020-03-15 |  | Active | EP
REP_NE.CON.SFD.REPACK | NE | CON | SFD | FCC Repack | FCC NE CON SFD Channel Move Alignment POR20 | Chassis | Channel Move / Inca 8VSB / Wade WH | 9 | 2020-01-01 | 2020-03-15 |  | Active | EP
REP_NE.RHD.WWK.REPACK | NE | RHD | WWK | FCC Repack | FCC NE RHD WWK Channel Move Alignment POR20 | Chassis | Channel Move / Inca 8VSB / Wade WH | 8 | 2020-01-01 | 2020-03-15 |  | Active | EP
REP_VA.NVA.FBG.REPACK | VA | NVA | FBG | FCC Repack | FCC VA NVA FBG Channel Move Alignment POR20 | Chassis | Channel Move / Inca 8VSB / Wade WH | 3 | 2020-01-18 | 2020-03-15 |  | Active | EP
REP_VA.NVA.MFD.REPACK | VA | NVA | MFD | FCC Repack | FCC VA NVA MFD Channel Move Alignment POR20 | Chassis | Channel Move / Inca 8VSB / Wade WH | 1 | 2020-01-18 | 2020-03-15 |  | Active | EP
REP_CE.OKC.TUL.REPACK | CE | TUL | TUL | FCC Repack | FCC CE TUL TUL Channel Move Alignment POR20 | Chassis | Channel Move / Inca 8VSB / Wade WH | 2 | 2020-03-14 | 2020-04-15 |  | Active | EP
REP_SE.GCT.FWB.REPACK | SE | GCT | FWB | FCC Repack | FCC SE GCT FWB Channel Move Alignment POR20 | Chassis | Channel Move / Inca 8VSB / Wade WH | 27 | 2020-01-01 | 2020-04-15 |  | Active | EP
REP_VA.HRD.NKT.REPACK | VA | HRD | NKT | FCC Repack | FCC VA HRD NKT Channel Move Alignment POR20 | Chassis | Channel Move / Inca 8VSB / Wade WH | 16 | 2020-01-01 | 2020-04-15 |  | Active | EP
REP_VA.HRD.VBC.REPACK | VA | HRD | VBC | FCC Repack | FCC VA HRD VBC Channel Move Alignment POR20 | Chassis | Channel Move / Inca 8VSB / Wade WH | 16 | 2020-01-01 | 2020-04-15 |  | Active | EP
REP_VA.ROA.RON.REPACK | VA | ROA | RON | FCC Repack | FCC VA ROA RON Channel Move Alignment POR20 | Chassis | Channel Move / Inca 8VSB / Wade WH | 1 | 2020-03-14 | 2020-04-15 |  | Active | EP
REP_NE.CON.MAN.REPACK | SW | ARZ | FWL | FCC Repack | FCC SW ARZ FWL Channel Move Alignment POR20 | Chassis | Channel Move / Inca 8VSB / Wade WH | 2 | 2020-05-02 | 2020-07-15 |  | Active | EP
HY COR COR DDR Voice BTS Decom POR20 | COR | COR | DDR | Harmony | Harmony Temporary | Labor | Cisco BTS switch decom |  |  |  |  | Deleted | EP
HY COR COR DDR Voice BTS Decom POR20 | COR | COR | DDR | Harmony | Harmony Temporary | Labor | Cisco BTS switch decom |  |  |  |  | Deleted | Log | Del | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY COR COR DDR Voice BTS Decom POR20 | COR | COR | DDR | Harmony | Harmony Temporary | Labor | Cisco BTS switch decom |  |  |  |  | Deleted | Log | Del | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY SE GLA BTR Voice BTS Gateway Decom POR20 | SE | BTR | BTR | Harmony | Harmony Temporary | Labor | Cisco BTS gateway decom |  |  |  |  | Deleted | EP
HY SE GLA BTR Voice BTS Gateway Decom POR20 | SE | BTR | BTR | Harmony | Harmony Temporary | Labor | Cisco BTS gateway decom |  |  |  |  | Deleted | Log | Del | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY SE GLA BTR Voice BTS Gateway Decom POR20 | SE | BTR | BTR | Harmony | Harmony Temporary | Labor | Cisco BTS gateway decom |  |  |  |  | Deleted | Log | Del | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY SE GLA LFY Voice BTS Gateway Decom POR20 | SE | LFY | LFY | Harmony | Harmony Temporary | Labor | Cisco BTS gateway decom |  |  |  |  | Deleted | EP
HY SE GLA LFY Voice BTS Gateway Decom POR20 | SE | LFY | LFY | Harmony | Harmony Temporary | Labor | Cisco BTS gateway decom |  |  |  |  | Deleted | Log | Del | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY SE GLA LFY Voice BTS Gateway Decom POR20 | SE | LFY | LFY | Harmony | Harmony Temporary | Labor | Cisco BTS gateway decom |  |  |  |  | Deleted | Log | Del | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY SE GAN GNS Voice BTS Gateway Decom POR20 | SE | GAN | GNS | Harmony | Harmony Temporary | Labor | Cisco BTS gateway decom |  |  |  |  | Deleted | EP
HY SE GAN GNS Voice BTS Gateway Decom POR20 | SE | GAN | GNS | Harmony | Harmony Temporary | Labor | Cisco BTS gateway decom |  |  |  |  | Deleted | Log | Del | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY SE GAN GNS Voice BTS Gateway Decom POR20 | SE | GAN | GNS | Harmony | Harmony Temporary | Labor | Cisco BTS gateway decom |  |  |  |  | Deleted | Log | Del | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY SE MGA MCN Voice BTS Gateway Decom POR20 | SE | MGA | MCN | Harmony | Harmony Temporary | Labor | Cisco BTS gateway decom |  |  |  |  | Deleted | EP
HY SE MGA MCN Voice BTS Gateway Decom POR20 | SE | MGA | MCN | Harmony | Harmony Temporary | Labor | Cisco BTS gateway decom |  |  |  |  | Deleted | Log | Del | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY SE MGA MCN Voice BTS Gateway Decom POR20 | SE | MGA | MCN | Harmony | Harmony Temporary | Labor | Cisco BTS gateway decom |  |  |  |  | Deleted | Log | Del | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY SE GCT PNS Voice BTS Gateway Decom POR20 | SE | GCT | PNS | Harmony | Harmony Temporary | Labor | Cisco BTS gateway decom |  |  |  |  | Deleted | EP
HY SE GCT PNS Voice BTS Gateway Decom POR20 | SE | GCT | PNS | Harmony | Harmony Temporary | Labor | Cisco BTS gateway decom |  |  |  |  | Deleted | Log | Del | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY SE GCT PNS Voice BTS Gateway Decom POR20 | SE | GCT | PNS | Harmony | Harmony Temporary | Labor | Cisco BTS gateway decom |  |  |  |  | Deleted | Log | Del | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY VA HRD CHS Voice DMS Switch Decom POR20 | VA | HRD | CHS | Harmony | Harmony Temporary | Labor | DMS-500 switch decom |  |  |  |  | Deleted | EP
HY VA HRD CHS Voice DMS Switch Decom POR20 | VA | HRD | CHS | Harmony | Harmony Temporary | Labor | DMS-500 switch decom |  |  |  |  | Deleted | Log | Del | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY VA HRD CHS Voice DMS Switch Decom POR20 | VA | HRD | CHS | Harmony | Harmony Temporary | Labor | DMS-500 switch decom |  |  |  |  | Deleted | Log | Del | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY VA ROA RON Voice BTS Gateway Decom POR20 | VA | ROA | RON | Harmony | Harmony Temporary | Labor | Cisco BTS gateway decom |  |  |  |  | Deleted | EP
HY VA ROA RON Voice BTS Gateway Decom POR20 | VA | ROA | RON | Harmony | Harmony Temporary | Labor | Cisco BTS gateway decom |  |  |  |  | Deleted | Log | Del | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY VA ROA RON Voice BTS Gateway Decom POR20 | VA | ROA | RON | Harmony | Harmony Temporary | Labor | Cisco BTS gateway decom |  |  |  |  | Deleted | Log | Del | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY COR COR P6L Voice BTS Switch Decom POR20 | COR | COR | P6L | Harmony | Harmony Temporary | Labor | Cisco BTS switch decom |  |  |  |  | Deleted | EP
HY COR COR P6L Voice BTS Switch Decom POR20 | COR | COR | P6L | Harmony | Harmony Temporary | Labor | Cisco BTS switch decom |  |  |  |  | Deleted | Log | Del | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY COR COR P6L Voice BTS Switch Decom POR20 | COR | COR | P6L | Harmony | Harmony Temporary | Labor | Cisco BTS switch decom |  |  |  |  | Deleted | Log | Del | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY CA ORG RSM Voice DMS Switch Decom POR20 | CA | ORG | RSM | Harmony | Harmony Temporary | Labor | DMS-500 switch decom |  |  |  |  | Deleted | EP
HY CA ORG RSM Voice DMS Switch Decom POR20 | CA | ORG | RSM | Harmony | Harmony Temporary | Labor | DMS-500 switch decom |  |  |  |  | Deleted | Log | Del | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY CA ORG RSM Voice DMS Switch Decom POR20 | CA | ORG | RSM | Harmony | Harmony Temporary | Labor | DMS-500 switch decom |  |  |  |  | Deleted | Log | Del | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY CA ORG AVJ Voice POI Decom POR20 | CA | ORG | AVJ | Harmony | Harmony Temporary | Labor | Point of interface decom |  |  |  |  | Deleted | EP
HY CA ORG AVJ Voice POI Decom POR20 | CA | ORG | AVJ | Harmony | Harmony Temporary | Labor | Point of interface decom |  |  |  |  | Deleted | Log | Del | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY CA ORG AVJ Voice POI Decom POR20 | CA | ORG | AVJ | Harmony | Harmony Temporary | Labor | Point of interface decom |  |  |  |  | Deleted | Log | Del | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY CA SAB SAB Voice Gateway Decom POR20 | CA | SAB | SAB | Harmony | HY CA SAB SAB Voice Gateway Decom POR20 | Labor | Gateway decom |  |  |  |  | Deleted | EP
HY CA SAB SAB Voice Gateway Decom POR20 | CA | SAB | SAB | Harmony | Harmony Temporary | Labor | Gateway decom | 1 | 2020-04-07 | 2020-06-30 |  | Deleted | Log | Upd | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY CA SAB SAB Voice Gateway Decom POR20 | CA | SAB | SAB | Harmony | HY CA SAB SAB Voice Gateway Decom POR20 | Labor | Gateway decom | 1 | 2020-04-07 | 2020-06-30 |  | Deleted | Log | Upd | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY CA SAB SAB Voice Gateway Decom POR20 | CA | SAB | SAB | Harmony | HY CA SAB SAB Voice Gateway Decom POR20 | Labor | Gateway decom |  |  |  |  | Deleted | Log | Del | PB-0003 | New | Approved | 2020-05-07 10:53 | POR Update Only CR to delete 8 legacy Harmony projects from POR
HY SW LAS HEN Voice CS2Kc Gateway Decom POR20 | SW | LAS | HEN | Harmony | Harmony Temporary | Labor | CS2Kc switch and gateway decom |  |  |  |  | Deleted | EP
HY SW LAS HEN Voice CS2Kc Gateway Decom POR20 | SW | LAS | HEN | Harmony | Harmony Temporary | Labor | CS2Kc switch and gateway decom |  |  |  |  | Deleted | Log | Del | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY SW LAS HEN Voice CS2Kc Gateway Decom POR20 | SW | LAS | HEN | Harmony | Harmony Temporary | Labor | CS2Kc switch and gateway decom |  |  |  |  | Deleted | Log | Del | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY SW LAS TEN Voice CS2Kc Decom POR20 | SW | LAS | TEN | Harmony | Harmony Temporary | Labor | CS2kc switch decom |  |  |  |  | Deleted | EP
HY SW LAS TEN Voice CS2Kc Decom POR20 | SW | LAS | TEN | Harmony | Harmony Temporary | Labor | CS2kc switch decom |  |  |  |  | Deleted | Log | Del | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY SW LAS TEN Voice CS2Kc Decom POR20 | SW | LAS | TEN | Harmony | Harmony Temporary | Labor | CS2kc switch decom |  |  |  |  | Deleted | Log | Del | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY SW ARZ TCSNAZMA Voice POI Decomm POR20 | COR | NAT | TCSNAZMA | Harmony | Harmony Temporary | Labor | Point of interface decom |  |  |  |  | Deleted | EP
HY SW ARZ TCSNAZMA Voice POI Decomm POR20 | COR | NAT | TCSNAZMA | Harmony | Harmony Temporary | Labor | Point of interface decom |  |  |  |  | Deleted | Log | Del | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY SW ARZ TCSNAZMA Voice POI Decomm POR20 | COR | NAT | TCSNAZMA | Harmony | Harmony Temporary | Labor | Point of interface decom |  |  |  |  | Deleted | Log | Del | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY CE KAN JCY Voice POI Decom POR20 | CE | KAN | JCY | Harmony | HY CE KAN JCY Voice POI Decom POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
HY CE KAN JCY Voice POI Decom POR20 | CE | KAN | JCY | Harmony | HY CE KAN JCY Voice POI Decom POR20 | Labor | No Equipment | 1 | 2020-07-06 08:00 | 2020-11-30 |  | Deleted | Log | New | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY CE KAN JCY Voice POI Decom POR20 | CE | KAN | JCY | Harmony | HY CE KAN JCY Voice POI Decom POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | PB-0003 | New | Approved | 2020-05-07 10:53 | POR Update Only CR to delete 8 legacy Harmony projects from POR
HY NE CLE CLV Voice Gateway Decom POR20 | NE | CLE | CLV | Harmony | HY NE CLE CLV Voice Gateway Decom POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
HY NE CLE CLV Voice Gateway Decom POR20 | NE | CLE | CLV | Harmony | HY NE CLE CLV Voice Gateway Decom POR20 old | Labor | No Equipment | 1 | 2020-04-06 | 2020-06-30 |  | Deleted | Log | New | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY NE CLE CLV Voice Gateway Decom POR20 | NE | CLE | CLV | Harmony | HY NE CLE CLV Voice Gateway Decom POR20 | Labor | No Equipment | 1 | 2020-04-06 | 2020-06-30 |  | Deleted | Log | Upd | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY NE CLE CLV Voice Gateway Decom POR20 | NE | CLE | CLV | Harmony | HY NE CLE CLV Voice Gateway Decom POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | PB-0003 | New | Approved | 2020-05-07 10:53 | POR Update Only CR to delete 8 legacy Harmony projects from POR
HY SW ARZ MSA Voice HDT Decom POR20 | SW | ARZ | MSA | Harmony | HY SW ARZ MSA Voice HDT Decom POR20 DELETE | Labor | No Equipment |  |  |  |  | Deleted | EP
HY SW ARZ MSA Voice HDT Decom POR20 | SW | ARZ | MSA | Harmony | HY SW ARZ MSA Voice HDT Decom POR20 DELETE | Labor | No Equipment | 37 | 2020-03-06 | 2020-07-31 |  | Deleted | Log | New | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY SW ARZ MSA Voice HDT Decom POR20 | SW | ARZ | MSA | Harmony | HY SW ARZ MSA Voice HDT Decom POR20 DELETE | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | PB-0003 | New | Approved | 2020-05-07 10:53 | POR Update Only CR to delete 8 legacy Harmony projects from POR
HY CE NWA FTS Voice Gateway Decom POR20 | CE | NWA | FTS | Harmony | HY CE NWA FTS Voice Gateway Decom POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
HY CE NWA FTS Voice Gateway Decom POR20 | CE | NWA | FTS | Harmony | HY CE NWA FTS Voice Gateway Decom POR20 | Labor | No Equipment | 1 | 2020-01-06 | 2020-03-31 |  | Deleted | Log | New | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY CE NWA FTS Voice Gateway Decom POR20 | CE | NWA | FTS | Harmony | HY CE NWA FTS Voice Gateway Decom POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | PB-0003 | New | Approved | 2020-05-07 10:53 | POR Update Only CR to delete 8 legacy Harmony projects from POR
HY SE NOR ALG Voice HDT Decom POR20 | SE | NOR | ALG | Harmony | HY SE NOR ALG Voice HDT Decom POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
HY SE NOR ALG Voice HDT Decom POR20 | SE | NOR | ALG | Harmony | HY SE NOR ALG Voice HDT Decom POR20 | Labor | No Equipment | 6 | 2020-08-06 | 2020-10-31 |  | Deleted | Log | New | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY SE NOR ALG Voice HDT Decom POR20 | SE | NOR | ALG | Harmony | HY SE NOR ALG Voice HDT Decom POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | PB-0003 | New | Approved | 2020-05-07 10:53 | POR Update Only CR to delete 8 legacy Harmony projects from POR
HY SE NOR NOE Voice HDT Decom POR20 | SE | NOR | NOE | Harmony | HY SE NOR NOE Voice HDT Decom POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
HY SE NOR NOE Voice HDT Decom POR20 | SE | NOR | NOE | Harmony | HY SE NOR NOE Voice HDT Decom POR20 | Labor | No Equipment | 6 | 2020-08-06 | 2020-10-31 |  | Deleted | Log | New | PB-0001 | Schedule Change | Approved | 2019-12-20 16:12 | This CR updates the 2020 Harmony Legacy Voice Decom plan based on the FE O workshop and addtional updates
HY SE NOR NOE Voice HDT Decom POR20 | SE | NOR | NOE | Harmony | HY SE NOR NOE Voice HDT Decom POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | PB-0003 | New | Approved | 2020-05-07 10:53 | POR Update Only CR to delete 8 legacy Harmony projects from POR
HY CE NWA NWA Voice POI Gateway Decom POR19 | CE | NWA | NWA | Harmony | HY CE NWA NWA Voice POI Gateway Decom POR19 DELETE | Labor | No Equipment |  |  |  |  | Deleted | EP
HY CE NWA NWA Voice POI Gateway Decom POR19 | CE | NWA | NWA | Harmony | HY CE NWA NWA Voice POI Gateway Decom POR19 DELETE | Labor | No Equipment | 4 | 2019-11-06 | 2020-04-30 |  | Deleted | Log | Undel | PB-0002 | Schedule Change | Approved | 2020-01-31 14:54 | This CR updates the Legacy Voice Decom POR based on the latest schedule changes per their Steering Committee
HY CE NWA NWA Voice POI Gateway Decom POR19 | CE | NWA | NWA | Harmony | HY CE NWA NWA Voice POI Gateway Decom POR19 DELETE | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | PB-0003 | New | Approved | 2020-05-07 10:53 | POR Update Only CR to delete 8 legacy Harmony projects from POR
Aruba Controller | SW | LAS | TEN | Hospitality Network | HN SW LAS TEN Aruba Controller Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
Aruba Controller | SW | LAS | TEN | Hospitality Network | HN SW LAS TEN Aruba Controller Augment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-08-31 |  | Deleted | Log | New | SB-0108 | Cost Change | Approved | 2020-04-24 14:40 | Moving 131K in funding from Field PPM to Corp PPM to fund HN Hosts project at Duke Dr and POR change to to add EPS projects to Activity Plan
Aruba Controller | SW | LAS | TEN | Hospitality Network | HN SW LAS TEN Aruba Controller Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0133 | Cost Change | Approved | 2020-05-14 16:39 | Hospitality Network Q2F CR and POR returning 43K for cancelled DNA and Aruba projects and returning 150K for revised cost estimates for SolutionIP
Cardinals DNA | SW | LAS | TEN | Hospitality Network | HN SW LAS TEN Cardinals DNA Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | EP
Cardinals DNA | SW | LAS | TEN | Hospitality Network | HN SW LAS TEN Cardinals DNA Augment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-08-31 |  | Deleted | Log | New | SB-0108 | Cost Change | Approved | 2020-04-24 14:40 | Moving 131K in funding from Field PPM to Corp PPM to fund HN Hosts project at Duke Dr and POR change to to add EPS projects to Activity Plan
Cardinals DNA | SW | LAS | TEN | Hospitality Network | HN SW LAS TEN Cardinals DNA Augment POR20 | Labor | No Equipment |  |  |  |  | Deleted | Log | Del | SB-0133 | Cost Change | Approved | 2020-05-14 16:39 | Hospitality Network Q2F CR and POR returning 43K for cancelled DNA and Aruba projects and returning 150K for revised cost estimates for SolutionIP
Solarwinds | SW | LAS | TEN | Hospitality Network | HN SW LAS TEN Solarwinds Augment POR20 | Labor | No Equipment | 1 | 2020-08-01 | 2020-09-30 |  | Active | EP
Solarwinds | SW | LAS | TEN | Hospitality Network | HN SW LAS TEN Solarwinds Augment POR20 | Labor | No Equipment | 1 | 2020-08-01 | 2020-09-30 |  | Active | Log | New | SB-0108 | Cost Change | Approved | 2020-04-24 14:40 | Moving 131K in funding from Field PPM to Corp PPM to fund HN Hosts project at Duke Dr and POR change to to add EPS projects to Activity Plan
CPI Segment | SW | LAS | TEN | Hospitality Network | HN SW LAS TEN CPI Segment Augment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-07-31 |  | Active | EP
CPI Segment | SW | LAS | TEN | Hospitality Network | HN SW LAS TEN CPI Segment Augment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-08-31 |  | Active | Log | New | SB-0108 | Cost Change | Approved | 2020-04-24 14:40 | Moving 131K in funding from Field PPM to Corp PPM to fund HN Hosts project at Duke Dr and POR change to to add EPS projects to Activity Plan
CPI Segment | SW | LAS | TEN | Hospitality Network | HN SW LAS TEN CPI Segment Augment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-07-31 |  | Active | Log | Upd | SB-0196 | Schedule Change | Approved | 2020-08-14 15:14 | Hospitality Network POR only CR to update three project records Two projects completed ahead of schedule and one project delayed one month
SolutionIP | SW | LAS | TEN | Hospitality Network | HN SW LAS TEN SolutionIP Server Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-07-31 |  | Active | EP
SolutionIP | SW | LAS | TEN | Hospitality Network | HN SW LAS TEN SolutionIP Server Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-12-31 |  | Active | Log | New | SB-0108 | Cost Change | Approved | 2020-04-24 14:40 | Moving 131K in funding from Field PPM to Corp PPM to fund HN Hosts project at Duke Dr and POR change to to add EPS projects to Activity Plan
SolutionIP | SW | LAS | TEN | Hospitality Network | HN SW LAS TEN SolutionIP Server Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-07-31 |  | Active | Log | Upd | SB-0196 | Schedule Change | Approved | 2020-08-14 15:14 | Hospitality Network POR only CR to update three project records Two projects completed ahead of schedule and one project delayed one month
HN Hosts | COR | COR | DDR | Hospitality Network | HN COR COR DDR HN Hosts Augment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-12-31 |  | Active | EP
HN Hosts | COR | COR | DDR | Hospitality Network | HN COR COR DDR HN Hosts Augment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-08-31 |  | Active | Log | New | SB-0108 | Cost Change | Approved | 2020-04-24 14:40 | Moving 131K in funding from Field PPM to Corp PPM to fund HN Hosts project at Duke Dr and POR change to to add EPS projects to Activity Plan
HN Hosts | COR | COR | DDR | Hospitality Network | HN COR COR DDR HN Hosts Augment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-09-30 |  | Active | Log | Upd | SB-0196 | Schedule Change | Approved | 2020-08-14 15:14 | Hospitality Network POR only CR to update three project records Two projects completed ahead of schedule and one project delayed one month
HN Hosts | COR | COR | DDR | Hospitality Network | HN COR COR DDR HN Hosts Augment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-11-30 |  | Active | Log | Upd | SB-0209 | True up | Approved | 2020-09-18 11:03 | Hospitality Network August True up and plan update to adjust HN Corp material spend to October and November based on ESD updates and realign IHL and 3PL labor plans to support build requesting 1 5k in Opex
HN Hosts | COR | COR | DDR | Hospitality Network | HN COR COR DDR HN Hosts Augment POR20 | Labor | No Equipment | 1 | 2020-05-01 | 2020-12-31 |  | Active | Log | Upd | SB-0252 | Cost Change | Approved | 2020-11-19 13:13 | HN Contract Labor charges from Infrastructure Dev Ops cost change CR to account for unplanned 3PL milestone accruals for Corp HN Hosts project and small IHL ask for Dec activity
Granite Automation | COR | COR | ATL | Hospitality Network | HN COR COR ATL HN Granite Automation Deployment POR20 | Labor | No Equipment | 1 | 2020-06-01 | 2020-12-31 |  | Active | EP
Granite Automation | COR | COR | DDR | Hospitality Network | HN COR COR ATL HN Granite Automation Deployment POR20 | Labor | No Equipment | 1 | 2020-06-01 | 2020-09-30 |  | Active | Log | New | SB-0152 | True up | Approved | 2020-06-11 15:18 | Hospitality Network May True Up returning 3K Capex to Risk for over estimated IHL hours for HN Hosts project and Self Solving 3PL and adding Granite project to POR
Granite Automation | COR | COR | ATL | Hospitality Network | HN COR COR ATL HN Granite Automation Deployment POR20 | Labor | No Equipment | 1 | 2020-06-01 | 2020-12-31 |  | Active | Log | Upd | SB-0252 | Cost Change | Approved | 2020-11-19 13:13 | HN Contract Labor charges from Infrastructure Dev Ops cost change CR to account for unplanned 3PL milestone accruals for Corp HN Hosts project and small IHL ask for Dec activity
MRTH-CSG-93180-01 | SW | ARZ | CSG | Metro Nexus Thunder | MNEX SW ARZ CSG Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 2 | 2020-01-20 | 2020-10-13 | 2020-11-11 | Active | EP
MRTH-CSG-93180-01 | SW | ARZ | CSG | Metro Nexus Thunder | MNEX SW ARZ CSG Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 2 | 2020-01-20 | 2020-10-13 | 2020-11-01 | Active | Log | Upd | SB-0216 | Schedule Change | Approved | 2020-09-18 09:37 | Updating POR to reflect current targeted migration dates for Nexus Thunder
MRTH-CSG-93180-01 | SW | ARZ | CSG | Metro Nexus Thunder | MNEX SW ARZ CSG Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 2 | 2020-01-20 | 2020-10-13 | 2020-11-11 | Active | Log | Upd | SB-0237 | Schedule Change | Approved | 2020-11-06 13:49 | Updating install and migration dates This update pushes Nexus into 2021
MRTH-CSG-3048-01 | SW | ARZ | CSG | Metro Nexus Thunder | MNEX SW ARZ CSG Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis |  |  |  |  | Deleted | EP
MRTH-CSG-3048-01 | SW | ARZ | CSG | Metro Nexus Thunder | MNEX SW ARZ CSG Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis |  |  |  |  | Deleted | Log | Del | SB-0132 | Schedule Change | Approved | 2020-05-14 13:45 | Metro Nexus Thunder: POR Update to reflect latest plan
MRTH-CSG-2248-01 | SW | ARZ | CSG | Metro Nexus Thunder | MNEX SW ARZ CSG Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-01-20 | 2020-10-13 | 2020-11-11 | Active | EP
MRTH-CSG-2248-01 | SW | ARZ | CSG | Metro Nexus Thunder | MNEX SW ARZ CSG Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-01-20 | 2020-10-13 | 2020-11-26 | Active | Log | Upd | SB-0216 | Schedule Change | Approved | 2020-09-18 09:37 | Updating POR to reflect current targeted migration dates for Nexus Thunder
MRTH-CSG-2248-01 | SW | ARZ | CSG | Metro Nexus Thunder | MNEX SW ARZ CSG Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-01-20 | 2020-10-13 | 2020-11-11 | Active | Log | Upd | SB-0237 | Schedule Change | Approved | 2020-11-06 13:49 | Updating install and migration dates This update pushes Nexus into 2021
MRTH-FWL-93180-01 | SW | ARZ | FWL | Metro Nexus Thunder | MNEX SW ARZ FWL Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 4 | 2020-01-20 | 2020-09-01 | 2020-11-12 | Active | EP
MRTH-FWL-93180-01 | SW | ARZ | FWL | Metro Nexus Thunder | MNEX SW ARZ FWL Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 4 | 2020-01-20 | 2020-08-20 | 2020-10-20 | Active | Log | Upd | SB-0179 | Schedule Change | Approved | 2020-07-20 09:32 | Align POR migration dates to EPS dates
MRTH-FWL-93180-01 | SW | ARZ | FWL | Metro Nexus Thunder | MNEX SW ARZ FWL Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 4 | 2020-01-20 | 2020-09-01 | 2020-11-04 | Active | Log | Upd | SB-0216 | Schedule Change | Approved | 2020-09-18 09:37 | Updating POR to reflect current targeted migration dates for Nexus Thunder
MRTH-FWL-93180-01 | SW | ARZ | FWL | Metro Nexus Thunder | MNEX SW ARZ FWL Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 4 | 2020-01-20 | 2020-09-01 | 2020-11-12 | Active | Log | Upd | SB-0237 | Schedule Change | Approved | 2020-11-06 13:49 | Updating install and migration dates This update pushes Nexus into 2021
MRTH-FWL-3048-01 | SW | ARZ | FWL | Metro Nexus Thunder | MNEX SW ARZ FWL Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis |  |  |  |  | Deleted | EP
MRTH-FWL-3048-01 | SW | ARZ | FWL | Metro Nexus Thunder | MNEX SW ARZ FWL Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis |  |  |  |  | Deleted | Log | Del | SB-0132 | Schedule Change | Approved | 2020-05-14 13:45 | Metro Nexus Thunder: POR Update to reflect latest plan
MRTH-FWL-2248-01 | SW | ARZ | FWL | Metro Nexus Thunder | MNEX SW ARZ FWL Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 9 | 2020-01-20 | 2020-09-01 | 2020-11-12 | Active | EP
MRTH-FWL-2248-01 | SW | ARZ | FWL | Metro Nexus Thunder | MNEX SW ARZ FWL Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 9 | 2020-01-20 | 2020-08-20 | 2020-10-20 | Active | Log | Upd | SB-0179 | Schedule Change | Approved | 2020-07-20 09:32 | Align POR migration dates to EPS dates
MRTH-FWL-2248-01 | SW | ARZ | FWL | Metro Nexus Thunder | MNEX SW ARZ FWL Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 9 | 2020-01-20 | 2020-09-01 | 2020-11-04 | Active | Log | Upd | SB-0216 | Schedule Change | Approved | 2020-09-18 09:37 | Updating POR to reflect current targeted migration dates for Nexus Thunder
MRTH-FWL-2248-01 | SW | ARZ | FWL | Metro Nexus Thunder | MNEX SW ARZ FWL Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 9 | 2020-01-20 | 2020-09-01 | 2020-11-12 | Active | Log | Upd | SB-0237 | Schedule Change | Approved | 2020-11-06 13:49 | Updating install and migration dates This update pushes Nexus into 2021
MRTH-SSC-93180-01 | SW | ARZ | SSC | Metro Nexus Thunder | MNEX SW ARZ SSC Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 4 | 2020-01-20 | 2021-01-15 | 2021-02-04 | Active | EP
MRTH-SSC-93180-01 | SW | ARZ | SSC | Metro Nexus Thunder | MNEX SW ARZ SSC Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 4 | 2020-01-20 | 2020-09-20 | 2020-10-20 | Active | Log | Upd | SB-0179 | Schedule Change | Approved | 2020-07-20 09:32 | Align POR migration dates to EPS dates
MRTH-SSC-93180-01 | SW | ARZ | SSC | Metro Nexus Thunder | MNEX SW ARZ SSC Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 4 | 2020-01-20 | 2020-10-13 | 2020-11-04 | Active | Log | Upd | SB-0216 | Schedule Change | Approved | 2020-09-18 09:37 | Updating POR to reflect current targeted migration dates for Nexus Thunder
MRTH-SSC-93180-01 | SW | ARZ | SSC | Metro Nexus Thunder | MNEX SW ARZ SSC Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 4 | 2020-01-20 | 2021-01-15 | 2021-02-04 | Active | Log | Upd | SB-0237 | Schedule Change | Approved | 2020-11-06 13:49 | Updating install and migration dates This update pushes Nexus into 2021
MRTH-SSC-3048-01 | SW | ARZ | SSC | Metro Nexus Thunder | MNEX SW ARZ SSC Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis |  |  |  |  | Deleted | EP
MRTH-SSC-3048-01 | SW | ARZ | SSC | Metro Nexus Thunder | MNEX SW ARZ SSC Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis |  |  |  |  | Deleted | Log | Del | SB-0132 | Schedule Change | Approved | 2020-05-14 13:45 | Metro Nexus Thunder: POR Update to reflect latest plan
MRTH-SSC-2248-01 | SW | ARZ | SSC | Metro Nexus Thunder | MNEX SW ARZ SSC Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-01-20 | 2021-01-16 | 2021-02-04 | Active | EP
MRTH-SSC-2248-01 | SW | ARZ | SSC | Metro Nexus Thunder | MNEX SW ARZ SSC Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-01-20 | 2020-09-20 | 2020-10-20 | Active | Log | Upd | SB-0179 | Schedule Change | Approved | 2020-07-20 09:32 | Align POR migration dates to EPS dates
MRTH-SSC-2248-01 | SW | ARZ | SSC | Metro Nexus Thunder | MNEX SW ARZ SSC Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-01-20 | 2020-10-13 | 2020-11-04 | Active | Log | Upd | SB-0216 | Schedule Change | Approved | 2020-09-18 09:37 | Updating POR to reflect current targeted migration dates for Nexus Thunder
MRTH-SSC-2248-01 | SW | ARZ | SSC | Metro Nexus Thunder | MNEX SW ARZ SSC Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-01-20 | 2021-01-16 | 2021-02-04 | Active | Log | Upd | SB-0237 | Schedule Change | Approved | 2020-11-06 13:49 | Updating install and migration dates This update pushes Nexus into 2021
MRTH-TUC-93180-01 | SW | ARZ | TUC | Metro Nexus Thunder | MNEX SW ARZ TUC Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 4 | 2020-01-20 | 2020-09-01 | 2020-12-08 | Active | EP
MRTH-TUC-93180-01 | SW | ARZ | TUC | Metro Nexus Thunder | MNEX SW ARZ TUC Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 4 | 2020-01-20 | 2020-08-20 | 2020-09-20 | Active | Log | Upd | SB-0179 | Schedule Change | Approved | 2020-07-20 09:32 | Align POR migration dates to EPS dates
MRTH-TUC-93180-01 | SW | ARZ | TUC | Metro Nexus Thunder | MNEX SW ARZ TUC Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 4 | 2020-01-20 | 2020-09-01 | 2020-11-04 | Active | Log | Upd | SB-0216 | Schedule Change | Approved | 2020-09-18 09:37 | Updating POR to reflect current targeted migration dates for Nexus Thunder
MRTH-TUC-93180-01 | SW | ARZ | TUC | Metro Nexus Thunder | MNEX SW ARZ TUC Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 4 | 2020-01-20 | 2020-09-01 | 2020-12-08 | Active | Log | Upd | SB-0237 | Schedule Change | Approved | 2020-11-06 13:49 | Updating install and migration dates This update pushes Nexus into 2021
MRTH-TUC-3048-01 | SW | ARZ | TUC | Metro Nexus Thunder | MNEX SW ARZ TUC Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis |  |  |  |  | Deleted | EP
MRTH-TUC-3048-01 | SW | ARZ | TUC | Metro Nexus Thunder | MNEX SW ARZ TUC Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis |  |  |  |  | Deleted | Log | Del | SB-0132 | Schedule Change | Approved | 2020-05-14 13:45 | Metro Nexus Thunder: POR Update to reflect latest plan
MRTH-TUC-2248-01 | SW | ARZ | TUC | Metro Nexus Thunder | MNEX SW ARZ TUC Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 7 | 2020-01-20 | 2020-09-01 | 2020-12-08 | Active | EP
MRTH-TUC-2248-01 | SW | ARZ | TUC | Metro Nexus Thunder | MNEX SW ARZ TUC Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 7 | 2020-01-20 | 2020-08-20 | 2020-09-20 | Active | Log | Upd | SB-0179 | Schedule Change | Approved | 2020-07-20 09:32 | Align POR migration dates to EPS dates
MRTH-TUC-2248-01 | SW | ARZ | TUC | Metro Nexus Thunder | MNEX SW ARZ TUC Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 7 | 2020-01-20 | 2020-09-01 | 2020-11-04 | Active | Log | Upd | SB-0216 | Schedule Change | Approved | 2020-09-18 09:37 | Updating POR to reflect current targeted migration dates for Nexus Thunder
MRTH-TUC-2248-01 | SW | ARZ | TUC | Metro Nexus Thunder | MNEX SW ARZ TUC Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 7 | 2020-01-20 | 2020-09-01 | 2020-12-08 | Active | Log | Upd | SB-0237 | Schedule Change | Approved | 2020-11-06 13:49 | Updating install and migration dates This update pushes Nexus into 2021
MRTH-MCD-93180-01 | SW | ARZ | MCD | Metro Nexus Thunder | MNEX SW ARZ MCD Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 4 | 2020-07-20 | 2020-11-03 | 2020-12-10 | Active | EP
MRTH-MCD-93180-01 | SW | ARZ | MCD | Metro Nexus Thunder | MNEX SW ARZ MCD Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 4 | 2020-07-20 | 2020-09-20 | 2020-10-20 | Active | Log | Upd | SB-0179 | Schedule Change | Approved | 2020-07-20 09:32 | Align POR migration dates to EPS dates
MRTH-MCD-93180-01 | SW | ARZ | MCD | Metro Nexus Thunder | MNEX SW ARZ MCD Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 4 | 2020-07-20 | 2020-10-13 | 2020-11-04 | Active | Log | Upd | SB-0216 | Schedule Change | Approved | 2020-09-18 09:37 | Updating POR to reflect current targeted migration dates for Nexus Thunder
MRTH-MCD-93180-01 | SW | ARZ | MCD | Metro Nexus Thunder | MNEX SW ARZ MCD Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 4 | 2020-07-20 | 2020-11-03 | 2020-12-10 | Active | Log | Upd | SB-0237 | Schedule Change | Approved | 2020-11-06 13:49 | Updating install and migration dates This update pushes Nexus into 2021
MRTH-MCD-3048-01 | SW | ARZ | MCD | Metro Nexus Thunder | MNEX SW ARZ MCD Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis |  |  |  |  | Deleted | EP
MRTH-MCD-3048-01 | SW | ARZ | MCD | Metro Nexus Thunder | MNEX SW ARZ MCD Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis |  |  |  |  | Deleted | Log | Del | SB-0132 | Schedule Change | Approved | 2020-05-14 13:45 | Metro Nexus Thunder: POR Update to reflect latest plan
MRTH-MCD-2248-01 | SW | ARZ | MCD | Metro Nexus Thunder | MNEX SW ARZ MCD Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 6 | 2020-07-20 | 2020-11-03 | 2020-12-10 | Active | EP
MRTH-MCD-2248-01 | SW | ARZ | MCD | Metro Nexus Thunder | MNEX SW ARZ MCD Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 6 | 2020-07-20 | 2020-09-20 | 2020-10-20 | Active | Log | Upd | SB-0179 | Schedule Change | Approved | 2020-07-20 09:32 | Align POR migration dates to EPS dates
MRTH-MCD-2248-01 | SW | ARZ | MCD | Metro Nexus Thunder | MNEX SW ARZ MCD Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 6 | 2020-07-20 | 2020-10-13 | 2020-11-04 | Active | Log | Upd | SB-0216 | Schedule Change | Approved | 2020-09-18 09:37 | Updating POR to reflect current targeted migration dates for Nexus Thunder
MRTH-MCD-2248-01 | SW | ARZ | MCD | Metro Nexus Thunder | MNEX SW ARZ MCD Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 6 | 2020-07-20 | 2020-11-03 | 2020-12-10 | Active | Log | Upd | SB-0237 | Schedule Change | Approved | 2020-11-06 13:49 | Updating install and migration dates This update pushes Nexus into 2021
MRTH-PEO-93180-01 | SW | ARZ | PEO | Metro Nexus Thunder | MNEX SW ARZ PEO Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 6 | 2020-04-20 | 2021-01-15 | 2021-01-29 | Active | EP
MRTH-PEO-93180-01 | SW | ARZ | PEO | Metro Nexus Thunder | MNEX SW ARZ PEO Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 6 | 2020-04-20 | 2020-08-20 | 2020-10-20 | Active | Log | Upd | SB-0179 | Schedule Change | Approved | 2020-07-20 09:32 | Align POR migration dates to EPS dates
MRTH-PEO-93180-01 | SW | ARZ | PEO | Metro Nexus Thunder | MNEX SW ARZ PEO Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 6 | 2020-04-20 | 2020-10-13 | 2020-11-04 | Active | Log | Upd | SB-0216 | Schedule Change | Approved | 2020-09-18 09:37 | Updating POR to reflect current targeted migration dates for Nexus Thunder
MRTH-PEO-93180-01 | SW | ARZ | PEO | Metro Nexus Thunder | MNEX SW ARZ PEO Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 6 | 2020-04-20 | 2021-01-15 | 2021-01-29 | Active | Log | Upd | SB-0237 | Schedule Change | Approved | 2020-11-06 13:49 | Updating install and migration dates This update pushes Nexus into 2021
MRTH-PEO-3048-01 | SW | ARZ | PEO | Metro Nexus Thunder | MNEX SW ARZ PEO Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis |  |  |  |  | Deleted | EP
MRTH-PEO-3048-01 | SW | ARZ | PEO | Metro Nexus Thunder | MNEX SW ARZ PEO Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis |  |  |  |  | Deleted | Log | Del | SB-0132 | Schedule Change | Approved | 2020-05-14 13:45 | Metro Nexus Thunder: POR Update to reflect latest plan
MRTH-PEO-2248-01 | SW | ARZ | PEO | Metro Nexus Thunder | MNEX SW ARZ PEO Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 8 | 2020-04-20 | 2021-01-15 | 2021-01-29 | Active | EP
MRTH-PEO-2248-01 | SW | ARZ | PEO | Metro Nexus Thunder | MNEX SW ARZ PEO Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 8 | 2020-04-20 | 2020-08-20 | 2020-10-20 | Active | Log | Upd | SB-0179 | Schedule Change | Approved | 2020-07-20 09:32 | Align POR migration dates to EPS dates
MRTH-PEO-2248-01 | SW | ARZ | PEO | Metro Nexus Thunder | MNEX SW ARZ PEO Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 8 | 2020-04-20 | 2020-10-13 | 2020-11-04 | Active | Log | Upd | SB-0216 | Schedule Change | Approved | 2020-09-18 09:37 | Updating POR to reflect current targeted migration dates for Nexus Thunder
MRTH-PEO-2248-01 | SW | ARZ | PEO | Metro Nexus Thunder | MNEX SW ARZ PEO Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 8 | 2020-04-20 | 2021-01-15 | 2021-01-29 | Active | Log | Upd | SB-0237 | Schedule Change | Approved | 2020-11-06 13:49 | Updating install and migration dates This update pushes Nexus into 2021
MRTH-SVA-93180-01 | SW | ARZ | SVA | Metro Nexus Thunder | MNEX SW ARZ SVA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 2 | 2020-07-20 | 2020-10-13 | 2020-11-19 | Active | EP
MRTH-SVA-93180-01 | SW | ARZ | SVA | Metro Nexus Thunder | MNEX SW ARZ SVA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 2 | 2020-07-20 | 2020-09-20 | 2020-10-20 | Active | Log | Upd | SB-0179 | Schedule Change | Approved | 2020-07-20 09:32 | Align POR migration dates to EPS dates
MRTH-SVA-93180-01 | SW | ARZ | SVA | Metro Nexus Thunder | MNEX SW ARZ SVA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 2 | 2020-07-20 | 2020-10-13 | 2020-11-04 | Active | Log | Upd | SB-0216 | Schedule Change | Approved | 2020-09-18 09:37 | Updating POR to reflect current targeted migration dates for Nexus Thunder
MRTH-SVA-93180-01 | SW | ARZ | SVA | Metro Nexus Thunder | MNEX SW ARZ SVA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 2 | 2020-07-20 | 2020-10-13 | 2020-11-19 | Active | Log | Upd | SB-0237 | Schedule Change | Approved | 2020-11-06 13:49 | Updating install and migration dates This update pushes Nexus into 2021
MRTH-SVA-3048-01 | SW | ARZ | SVA | Metro Nexus Thunder | MNEX SW ARZ SVA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis |  |  |  |  | Deleted | EP
MRTH-SVA-3048-01 | SW | ARZ | SVA | Metro Nexus Thunder | MNEX SW ARZ SVA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis |  |  |  |  | Deleted | Log | Del | SB-0132 | Schedule Change | Approved | 2020-05-14 13:45 | Metro Nexus Thunder: POR Update to reflect latest plan
MRTH-SVA-2248-01 | SW | ARZ | SVA | Metro Nexus Thunder | MNEX SW ARZ SVA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-07-20 | 2020-10-13 | 2020-11-19 | Active | EP
MRTH-SVA-2248-01 | SW | ARZ | SVA | Metro Nexus Thunder | MNEX SW ARZ SVA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-07-20 | 2020-09-20 | 2020-10-20 | Active | Log | Upd | SB-0179 | Schedule Change | Approved | 2020-07-20 09:32 | Align POR migration dates to EPS dates
MRTH-SVA-2248-01 | SW | ARZ | SVA | Metro Nexus Thunder | MNEX SW ARZ SVA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-07-20 | 2020-10-13 | 2020-11-04 | Active | Log | Upd | SB-0216 | Schedule Change | Approved | 2020-09-18 09:37 | Updating POR to reflect current targeted migration dates for Nexus Thunder
MRTH-SVA-2248-01 | SW | ARZ | SVA | Metro Nexus Thunder | MNEX SW ARZ SVA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-07-20 | 2020-10-13 | 2020-11-19 | Active | Log | Upd | SB-0237 | Schedule Change | Approved | 2020-11-06 13:49 | Updating install and migration dates This update pushes Nexus into 2021
MRTH-VAL-93180-01 | SW | ARZ | VAL | Metro Nexus Thunder | MNEX SW ARZ VAL Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX |  |  |  |  | Deleted | EP
MRTH-VAL-93180-01 | SW | ARZ | VAL | Metro Nexus Thunder | MNEX SW ARZ VAL Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX |  |  |  |  | Deleted | Log | Del | SB-0132 | Schedule Change | Approved | 2020-05-14 13:45 | Metro Nexus Thunder: POR Update to reflect latest plan
MRTH-VAL-2248-01 | SW | ARZ | VAL | Metro Nexus Thunder | MNEX SW ARZ VAL Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Deleted | EP
MRTH-VAL-2248-01 | SW | ARZ | VAL | Metro Nexus Thunder | MNEX SW ARZ VAL Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Deleted | Log | Del | SB-0132 | Schedule Change | Approved | 2020-05-14 13:45 | Metro Nexus Thunder: POR Update to reflect latest plan
MRTH-VSA-93180-01 | SW | ARZ | VSA | Metro Nexus Thunder | MNEX SW ARZ VSA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 2 | 2020-04-20 | 2020-10-01 | 2020-12-08 | Active | EP
MRTH-VSA-93180-01 | SW | ARZ | VSA | Metro Nexus Thunder | MNEX SW ARZ VSA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 2 | 2020-04-20 | 2020-09-20 | 2020-10-20 | Active | Log | Upd | SB-0179 | Schedule Change | Approved | 2020-07-20 09:32 | Align POR migration dates to EPS dates
MRTH-VSA-93180-01 | SW | ARZ | VSA | Metro Nexus Thunder | MNEX SW ARZ VSA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 2 | 2020-04-20 | 2020-10-01 | 2020-12-01 | Active | Log | Upd | SB-0216 | Schedule Change | Approved | 2020-09-18 09:37 | Updating POR to reflect current targeted migration dates for Nexus Thunder
MRTH-VSA-93180-01 | SW | ARZ | VSA | Metro Nexus Thunder | MNEX SW ARZ VSA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 2 | 2020-04-20 | 2020-10-01 | 2020-12-08 | Active | Log | Upd | SB-0237 | Schedule Change | Approved | 2020-11-06 13:49 | Updating install and migration dates This update pushes Nexus into 2021
MRTH-VSA-3048-01 | SW | ARZ | VSA | Metro Nexus Thunder | MNEX SW ARZ VSA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis |  |  |  |  | Deleted | EP
MRTH-VSA-3048-01 | SW | ARZ | VSA | Metro Nexus Thunder | MNEX SW ARZ VSA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis |  |  |  |  | Deleted | Log | Del | SB-0132 | Schedule Change | Approved | 2020-05-14 13:45 | Metro Nexus Thunder: POR Update to reflect latest plan
MRTH-VSA-2248-01 | SW | ARZ | VSA | Metro Nexus Thunder | MNEX SW ARZ VSA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-04-20 | 2020-10-01 | 2020-12-08 | Active | EP
MRTH-VSA-2248-01 | SW | ARZ | VSA | Metro Nexus Thunder | MNEX SW ARZ VSA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-04-20 | 2020-09-20 | 2020-10-20 | Active | Log | Upd | SB-0179 | Schedule Change | Approved | 2020-07-20 09:32 | Align POR migration dates to EPS dates
MRTH-VSA-2248-01 | SW | ARZ | VSA | Metro Nexus Thunder | MNEX SW ARZ VSA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-04-20 | 2020-10-01 | 2020-12-01 | Active | Log | Upd | SB-0216 | Schedule Change | Approved | 2020-09-18 09:37 | Updating POR to reflect current targeted migration dates for Nexus Thunder
MRTH-VSA-2248-01 | SW | ARZ | VSA | Metro Nexus Thunder | MNEX SW ARZ VSA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-04-20 | 2020-10-01 | 2020-12-08 | Active | Log | Upd | SB-0237 | Schedule Change | Approved | 2020-11-06 13:49 | Updating install and migration dates This update pushes Nexus into 2021
MRTH-BEN-93180-01 | SW | ARZ | BEN | Metro Nexus Thunder | MNEX SW ARZ BEN Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 2 | 2020-07-15 | 2020-10-28 | 2020-11-19 | Active | EP
MRTH-BEN-93180-01 | SW | ARZ | BEN | Metro Nexus Thunder | MNEX SW ARZ BEN Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 2 | 2020-07-15 | 2020-10-15 | 2020-12-20 | Active | Log | Upd | SB-0179 | Schedule Change | Approved | 2020-07-20 09:32 | Align POR migration dates to EPS dates
MRTH-BEN-93180-01 | SW | ARZ | BEN | Metro Nexus Thunder | MNEX SW ARZ BEN Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 2 | 2020-07-15 | 2020-10-13 | 2020-11-26 | Active | Log | Upd | SB-0216 | Schedule Change | Approved | 2020-09-18 09:37 | Updating POR to reflect current targeted migration dates for Nexus Thunder
MRTH-BEN-93180-01 | SW | ARZ | BEN | Metro Nexus Thunder | MNEX SW ARZ BEN Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 2 | 2020-07-15 | 2020-10-28 | 2020-11-19 | Active | Log | Upd | SB-0237 | Schedule Change | Approved | 2020-11-06 13:49 | Updating install and migration dates This update pushes Nexus into 2021
MRTH-BEN-3048-01 | SW | ARZ | BEN | Metro Nexus Thunder | MNEX SW ARZ BEN Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis |  |  |  |  | Deleted | EP
MRTH-BEN-3048-01 | SW | ARZ | BEN | Metro Nexus Thunder | MNEX SW ARZ BEN Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis |  |  |  |  | Deleted | Log | Del | SB-0132 | Schedule Change | Approved | 2020-05-14 13:45 | Metro Nexus Thunder: POR Update to reflect latest plan
MRTH-BEN-2248-01 | SW | ARZ | BEN | Metro Nexus Thunder | MNEX SW ARZ BEN Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-07-27 | 2020-10-28 | 2020-11-19 | Active | EP
MRTH-BEN-2248-01 | SW | ARZ | BEN | Metro Nexus Thunder | MNEX SW ARZ BEN Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-07-27 | 2020-10-15 | 2020-12-20 | Active | Log | Upd | SB-0179 | Schedule Change | Approved | 2020-07-20 09:32 | Align POR migration dates to EPS dates
MRTH-BEN-2248-01 | SW | ARZ | BEN | Metro Nexus Thunder | MNEX SW ARZ BEN Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-07-27 | 2020-10-13 | 2020-11-26 | Active | Log | Upd | SB-0216 | Schedule Change | Approved | 2020-09-18 09:37 | Updating POR to reflect current targeted migration dates for Nexus Thunder
MRTH-BEN-2248-01 | SW | ARZ | BEN | Metro Nexus Thunder | MNEX SW ARZ BEN Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-07-27 | 2020-10-28 | 2020-11-19 | Active | Log | Upd | SB-0237 | Schedule Change | Approved | 2020-11-06 13:49 | Updating install and migration dates This update pushes Nexus into 2021
MRTH-DGL-93180-01 | SW | ARZ | DGL | Metro Nexus Thunder | MNEX SW ARZ DGL Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 2 | 2020-07-14 | 2021-01-21 | 2021-01-30 | Active | EP
MRTH-DGL-93180-01 | SW | ARZ | DGL | Metro Nexus Thunder | MNEX SW ARZ DGL Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 2 | 2020-07-14 | 2020-09-20 | 2020-10-20 | Active | Log | Upd | SB-0179 | Schedule Change | Approved | 2020-07-20 09:32 | Align POR migration dates to EPS dates
MRTH-DGL-93180-01 | SW | ARZ | DGL | Metro Nexus Thunder | MNEX SW ARZ DGL Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 2 | 2020-07-14 | 2020-10-13 | 2020-11-03 | Active | Log | Upd | SB-0216 | Schedule Change | Approved | 2020-09-18 09:37 | Updating POR to reflect current targeted migration dates for Nexus Thunder
MRTH-DGL-93180-01 | SW | ARZ | DGL | Metro Nexus Thunder | MNEX SW ARZ DGL Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 2 | 2020-07-14 | 2021-01-21 | 2021-01-30 | Active | Log | Upd | SB-0237 | Schedule Change | Approved | 2020-11-06 13:49 | Updating install and migration dates This update pushes Nexus into 2021
MRTH-DGL-2248-01 | SW | ARZ | DGL | Metro Nexus Thunder | MNEX SW ARZ DGL Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-07-14 | 2021-01-20 | 2021-01-29 | Active | EP
MRTH-DGL-2248-01 | SW | ARZ | DGL | Metro Nexus Thunder | MNEX SW ARZ DGL Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-07-14 | 2020-09-20 | 2020-10-20 | Active | Log | Upd | SB-0179 | Schedule Change | Approved | 2020-07-20 09:32 | Align POR migration dates to EPS dates
MRTH-DGL-2248-01 | SW | ARZ | DGL | Metro Nexus Thunder | MNEX SW ARZ DGL Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-07-14 | 2020-10-13 | 2020-11-02 | Active | Log | Upd | SB-0216 | Schedule Change | Approved | 2020-09-18 09:37 | Updating POR to reflect current targeted migration dates for Nexus Thunder
MRTH-DGL-2248-01 | SW | ARZ | DGL | Metro Nexus Thunder | MNEX SW ARZ DGL Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-07-14 | 2021-01-20 | 2021-01-29 | Active | Log | Upd | SB-0237 | Schedule Change | Approved | 2020-11-06 13:49 | Updating install and migration dates This update pushes Nexus into 2021
MRTH-MSA-93180-01 | SW | ARZ | MSA | Metro Nexus Thunder | MNEX SW ARZ MSA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 6 | 2020-03-20 | 2020-10-26 | 2020-12-15 | Active | EP
MRTH-MSA-93180-01 | SW | ARZ | MSA | Metro Nexus Thunder | MNEX SW ARZ MSA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 6 | 2020-03-20 | 2020-08-20 | 2020-09-20 | Active | Log | Upd | SB-0179 | Schedule Change | Approved | 2020-07-20 09:32 | Align POR migration dates to EPS dates
MRTH-MSA-93180-01 | SW | ARZ | MSA | Metro Nexus Thunder | MNEX SW ARZ MSA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 6 | 2020-03-20 | 2020-10-13 | 2020-11-04 | Active | Log | Upd | SB-0216 | Schedule Change | Approved | 2020-09-18 09:37 | Updating POR to reflect current targeted migration dates for Nexus Thunder
MRTH-MSA-93180-01 | SW | ARZ | MSA | Metro Nexus Thunder | MNEX SW ARZ MSA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 6 | 2020-03-20 | 2020-10-26 | 2020-12-15 | Active | Log | Upd | SB-0237 | Schedule Change | Approved | 2020-11-06 13:49 | Updating install and migration dates This update pushes Nexus into 2021
MRTH-MSA-3048-01 | SW | ARZ | MSA | Metro Nexus Thunder | MNEX SW ARZ MSA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis |  |  |  |  | Deleted | EP
MRTH-MSA-3048-01 | SW | ARZ | MSA | Metro Nexus Thunder | MNEX SW ARZ MSA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis |  |  |  |  | Deleted | Log | Del | SB-0132 | Schedule Change | Approved | 2020-05-14 13:45 | Metro Nexus Thunder: POR Update to reflect latest plan
MRTH-MSA-2248-01 | SW | ARZ | MSA | Metro Nexus Thunder | MNEX SW ARZ MSA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 9 | 2020-03-20 | 2020-10-26 | 2020-12-15 | Active | EP
MRTH-MSA-2248-01 | SW | ARZ | MSA | Metro Nexus Thunder | MNEX SW ARZ MSA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 9 | 2020-03-20 | 2020-08-20 | 2020-09-20 | Active | Log | Upd | SB-0179 | Schedule Change | Approved | 2020-07-20 09:32 | Align POR migration dates to EPS dates
MRTH-MSA-2248-01 | SW | ARZ | MSA | Metro Nexus Thunder | MNEX SW ARZ MSA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 9 | 2020-03-20 | 2020-10-13 | 2020-11-04 | Active | Log | Upd | SB-0216 | Schedule Change | Approved | 2020-09-18 09:37 | Updating POR to reflect current targeted migration dates for Nexus Thunder
MRTH-MSA-2248-01 | SW | ARZ | MSA | Metro Nexus Thunder | MNEX SW ARZ MSA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 9 | 2020-03-20 | 2020-10-26 | 2020-12-15 | Active | Log | Upd | SB-0237 | Schedule Change | Approved | 2020-11-06 13:49 | Updating install and migration dates This update pushes Nexus into 2021
MRTH-GVA-93180-01 | SW | ARZ | GVA | Metro Nexus Thunder | MNEX SW ARZ GVA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 2 | 2020-04-20 | 2020-10-01 | 2020-12-14 | Active | EP
MRTH-GVA-93180-01 | SW | ARZ | GVA | Metro Nexus Thunder | MNEX SW ARZ GVA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 2 | 2020-04-20 | 2020-08-20 | 2020-09-20 | Active | Log | Upd | SB-0179 | Schedule Change | Approved | 2020-07-20 09:32 | Align POR migration dates to EPS dates
MRTH-GVA-93180-01 | SW | ARZ | GVA | Metro Nexus Thunder | MNEX SW ARZ GVA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 2 | 2020-04-20 | 2020-10-01 | 2020-12-01 | Active | Log | Upd | SB-0216 | Schedule Change | Approved | 2020-09-18 09:37 | Updating POR to reflect current targeted migration dates for Nexus Thunder
MRTH-GVA-93180-01 | SW | ARZ | GVA | Metro Nexus Thunder | MNEX SW ARZ GVA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX | 2 | 2020-04-20 | 2020-10-01 | 2020-12-14 | Active | Log | Upd | SB-0237 | Schedule Change | Approved | 2020-11-06 13:49 | Updating install and migration dates This update pushes Nexus into 2021
MRTH-GVA-3048-01 | SW | ARZ | GVA | Metro Nexus Thunder | MNEX SW ARZ GVA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis |  |  |  |  | Deleted | EP
MRTH-GVA-3048-01 | SW | ARZ | GVA | Metro Nexus Thunder | MNEX SW ARZ GVA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis |  |  |  |  | Deleted | Log | Del | SB-0132 | Schedule Change | Approved | 2020-05-14 13:45 | Metro Nexus Thunder: POR Update to reflect latest plan
MRTH-GVA-2248-01 | SW | ARZ | GVA | Metro Nexus Thunder | MNEX SW ARZ GVA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-04-20 | 2020-10-01 | 2020-12-14 | Active | EP
MRTH-GVA-2248-01 | SW | ARZ | GVA | Metro Nexus Thunder | MNEX SW ARZ GVA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-04-20 | 2020-08-20 | 2020-09-20 | Active | Log | Upd | SB-0179 | Schedule Change | Approved | 2020-07-20 09:32 | Align POR migration dates to EPS dates
MRTH-GVA-2248-01 | SW | ARZ | GVA | Metro Nexus Thunder | MNEX SW ARZ GVA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-04-20 | 2020-10-01 | 2020-12-01 | Active | Log | Upd | SB-0216 | Schedule Change | Approved | 2020-09-18 09:37 | Updating POR to reflect current targeted migration dates for Nexus Thunder
MRTH-GVA-2248-01 | SW | ARZ | GVA | Metro Nexus Thunder | MNEX SW ARZ GVA Nexus Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-04-20 | 2020-10-01 | 2020-12-14 | Active | Log | Upd | SB-0237 | Schedule Change | Approved | 2020-11-06 13:49 | Updating install and migration dates This update pushes Nexus into 2021
MRTR NCS-Growth-AVJ-100G Grow | CA | ORG | AVJ | Metro Routers | MRTR CA ORG AVJ 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 03:01 | 2020-03-31 | 2020-05-30 | Active | EP
MRTR NCS-Growth-AVJ-100G Grow | CA | ORG | AVJ | Metro Routers | MRTR CA ORG AVJ 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 03:01 | 2020-03-31 | 2020-05-30 | Active | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-DNP-NCS Line Card | CA | ORG | DNP | Metro Routers | MRTR CA ORG DNP NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR NCS-Growth-DNP-NCS Line Card | CA | ORG | DNP | Metro Routers | MRTR CA ORG DNP NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-IRV-NCS Line Card | CA | ORG | IRV | Metro Routers | MRTR CA ORG IRV NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-01-01 03:01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR NCS-Growth-IRV-NCS Line Card | CA | ORG | IRV | Metro Routers | MRTR CA ORG IRV NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-01-01 03:01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-ORG-100G Grow | CA | ORG | ORG | Metro Routers | MRTR CA ORG ORG 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR NCS-Growth-ORG-100G Grow | CA | ORG | ORG | Metro Routers | MRTR CA ORG ORG 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-ORG-NCS Line Card | CA | ORG | ORG | Metro Routers | MRTR CA ORG ORG NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR NCS-Growth-ORG-NCS Line Card | CA | ORG | ORG | Metro Routers | MRTR CA ORG ORG NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-RSM-NCS Line Card | CA | ORG | RSM | Metro Routers | MRTR CA ORG RSM NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR NCS-Growth-RSM-NCS Line Card | CA | ORG | RSM | Metro Routers | MRTR CA ORG RSM NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-CHU-100G Grow | CA | SAN | CHU | Metro Routers | MRTR CA SAN CHU 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR NCS-Growth-CHU-100G Grow | CA | SAN | CHU | Metro Routers | MRTR CA SAN CHU 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-CHU-NCS Line Card | CA | SAN | CHU | Metro Routers | MRTR CA SAN CHU NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR NCS-Growth-CHU-NCS Line Card | CA | SAN | CHU | Metro Routers | MRTR CA SAN CHU NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-ELC-100G Grow | CA | SAN | ELC | Metro Routers | MRTR CA SAN ELC 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 03:01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR NCS-Growth-ELC-100G Grow | CA | SAN | ELC | Metro Routers | MRTR CA SAN ELC 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 03:01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-ELC-NCS Line Card | CA | SAN | ELC | Metro Routers | MRTR CA SAN ELC NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-01-01 03:01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR NCS-Growth-ELC-NCS Line Card | CA | SAN | ELC | Metro Routers | MRTR CA SAN ELC NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-01-01 03:01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-FED-100G Grow | CA | SAN | FED | Metro Routers | MRTR CA SAN FED 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-01-30 | 2020-01-30 | Active | EP
MRTR NCS-Growth-FED-100G Grow | CA | SAN | FED | Metro Routers | MRTR CA SAN FED 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-01-30 | 2020-01-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-VST-100G Grow | CA | SAN | VST | Metro Routers | MRTR CA SAN VST 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR NCS-Growth-VST-100G Grow | CA | SAN | VST | Metro Routers | MRTR CA SAN VST 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-VST-NCS Line Card | CA | SAN | VST | Metro Routers | MRTR CA SAN VST NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-01-01 03:01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR NCS-Growth-VST-NCS Line Card | CA | SAN | VST | Metro Routers | MRTR CA SAN VST NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-01-01 03:01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-FAY-OOB Server | CE | NWA | FAY | Metro Routers | MRTR CE NWA FAY OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR OOB-New-FAY-OOB Server | CE | NWA | FAY | Metro Routers | MRTR CE NWA FAY OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-FAY-SLR-ASR9906 | CE | NWA | FAY | Metro Routers | MRTR CE NWA FAY SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-05 | 2021-02-28 | 2021-02-28 | Active | EP
MRTR SLR-New-FAY-SLR-ASR9906 | CE | NWA | FAY | Metro Routers | MRTR CE NWA FAY SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | Upd | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
MRTR SLR-New-FAY-SLR-ASR9906 | CE | NWA | FAY | Metro Routers | MRTR CE NWA FAY SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-15 | 2020-06-15 | Active | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR SLR-New-FAY-SLR-ASR9906 | CE | NWA | FAY | Metro Routers | MRTR CE NWA FAY SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-05 | 2020-08-31 | 2020-11-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-FAY-SLR-ASR9906 | CE | NWA | FAY | Metro Routers | MRTR CE NWA FAY SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-05 | 2021-02-28 | 2021-02-28 | Active | Log | Upd | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR NCS-Growth-FTS-100G Grow | CE | NWA | FTS | Metro Routers | MRTR CE NWA FTS 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | EP
MRTR NCS-Growth-TOP-100G Grow | CE | KAN | TOP | Metro Routers | MRTR CE KAN TOP 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | EP
MRTR NCS-Growth-WIC-100G Grow | CE | KAN | WIC | Metro Routers | MRTR CE KAN WIC 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | EP
MRTR NCS-Growth-IND-NCS Line Card | CE | TUL | IND | Metro Routers | MRTR CE TUL IND NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR NCS-Growth-IND-NCS Line Card | CE | TUL | IND | Metro Routers | MRTR CE TUL IND NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-09-05 | 2020-11-30 | 2021-02-28 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-IND-NCS Line Card | CE | TUL | IND | Metro Routers | MRTR CE TUL IND NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR OOB-New-IND-OOB Server | CE | TUL | IND | Metro Routers | MRTR CE TUL IND NCS Augment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Active | EP
MRTR OOB-New-IND-OOB Server | CE | TUL | IND | Metro Routers | MRTR CE TUL IND NCS Augment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-IND-OOB Server | CE | TUL | IND | Metro Routers | MRTR CE TUL IND NCS Augment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Active | Log | Upd | SN-1037 | Schedule Change | Approved | 2020-11-06 09:51 | Alignment of POR based on feedback from the field
MRTR SLR-New-IND-SLR-ASR9906 | CE | TUL | IND | Metro Routers | MRTR CE TUL IND SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR SLR-New-IND-SLR-ASR9906 | CE | TUL | IND | Metro Routers | MRTR CE TUL IND SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Deleted | Log | Upd | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
MRTR SLR-New-IND-SLR-ASR9906 | CE | TUL | IND | Metro Routers | MRTR CE TUL IND SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-01 | 2020-12-15 | 2020-12-15 | Deleted | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR SLR-New-IND-SLR-ASR9906 | CE | TUL | IND | Metro Routers | MRTR CE TUL IND SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-IND-SLR-ASR9906 | CE | TUL | IND | Metro Routers | MRTR CE TUL IND SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR OOB-New-NCH-OOB Server | CE | OKC | NCH | Metro Routers | MRTR CE OKC NCH OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR OOB-New-NCH-OOB Server | CE | OKC | NCH | Metro Routers | MRTR CE OKC NCH OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-NEH-100G Grow | CE | OKC | NEH | Metro Routers | MRTR CE OKC NEH 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | EP
MRTR NCS-Growth-NOR-100G Grow | CE | OKC | NOR | Metro Routers | MRTR CE OKC NOR 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR NCS-Growth-NOR-100G Grow | CE | OKC | NOR | Metro Routers | MRTR CE OKC NOR 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-NOR-OOB Server | CE | OKC | NOR | Metro Routers | MRTR CE OKC NOR 100G Grow Augment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR OOB-New-NOR-OOB Server | CE | OKC | NOR | Metro Routers | MRTR CE OKC NOR 100G Grow Augment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-OKC-OOB Server | CE | OKC | OKC | Metro Routers | MRTR CE OKC OKC OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 7 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR OOB-New-OKC-OOB Server | CE | OKC | OKC | Metro Routers | MRTR CE OKC OKC OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 7 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-OKC-SLR-ASR9906 | CE | OKC | OKC | Metro Routers | MRTR CE OKC OKC SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-09-30 | 2020-09-30 | Active | EP
MRTR SLR-New-OKC-SLR-ASR9906 | CE | OKC | OKC | Metro Routers | MRTR CE OKC OKC SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | Upd | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
MRTR SLR-New-OKC-SLR-ASR9906 | CE | OKC | OKC | Metro Routers | MRTR CE OKC OKC SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-OKC-SLR-ASR9906 | CE | OKC | OKC | Metro Routers | MRTR CE OKC OKC SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR OOB-New-OWA-OOB Server | CE | TUL | OWA | Metro Routers | MRTR CE TUL OWA OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR OOB-New-OWA-OOB Server | CE | TUL | OWA | Metro Routers | MRTR CE TUL OWA OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 |  | 2020-01-15 |  | Active | Log | Upd | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
MRTR OOB-New-OWA-OOB Server | CE | TUL | OWA | Metro Routers | MRTR CE TUL OWA OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-OWA-SLR-ASR9906 | CE | TUL | OWA | Metro Routers | MRTR CE TUL OWA SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-01 | 2020-09-30 | 2020-09-30 | Active | EP
MRTR SLR-New-OWA-SLR-ASR9906 | CE | TUL | OWA | Metro Routers | MRTR CE TUL OWA SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | Upd | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
MRTR SLR-New-OWA-SLR-ASR9906 | CE | TUL | OWA | Metro Routers | MRTR CE TUL OWA SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-OWA-SLR-ASR9906 | CE | TUL | OWA | Metro Routers | MRTR CE TUL OWA SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Active | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-OWA-SLR-ASR9906 | CE | TUL | OWA | Metro Routers | MRTR CE TUL OWA SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-01 | 2020-09-30 | 2020-09-30 | Active | Log | Undel | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR OOB-New-QNC-OOB Server | CE | TUL | QNC | Metro Routers | MRTR CE TUL QNC OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR OOB-New-QNC-OOB Server | CE | TUL | QNC | Metro Routers | MRTR CE TUL QNC OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-QNC-SLR-ASR9906 | CE | TUL | QNC | Metro Routers | MRTR CE TUL QNC SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-09-30 | 2020-09-30 | Active | EP
MRTR SLR-New-QNC-SLR-ASR9906 | CE | TUL | QNC | Metro Routers | MRTR CE TUL QNC SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | Upd | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
MRTR SLR-New-QNC-SLR-ASR9906 | CE | TUL | QNC | Metro Routers | MRTR CE TUL QNC SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-QNC-SLR-ASR9906 | CE | TUL | QNC | Metro Routers | MRTR CE TUL QNC SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
RPHY MRTR-New-SOH-CIN MGMT-2K | CE | OKC | SOH | Metro Routers | MRTR CE OKC SOH SLR Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-New-SOH-CIN MGMT-2K | CE | OKC | SOH | Metro Routers | MRTR CE OKC SOH SLR Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Deleted | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-SOH-CIN-DPA-5200 | CE | OKC | SOH | Metro Routers | MRTR CE OKC SOH SLR Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-New-SOH-CIN-DPA-5200 | CE | OKC | SOH | Metro Routers | MRTR CE OKC SOH SLR Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Deleted | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-SOH-CIN-RPA-5110 | CE | OKC | SOH | Metro Routers | MRTR CE OKC SOH SLR Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-New-SOH-CIN-RPA-5110 | CE | OKC | SOH | Metro Routers | MRTR CE OKC SOH SLR Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
MRTR SLR-New-SOH-SLR-ASR9906 | CE | OKC | SOH | Metro Routers | MRTR CE OKC SOH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR SLR-New-SOH-SLR-ASR9906 | CE | OKC | SOH | Metro Routers | MRTR CE OKC SOH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 1 |  | 2020-01-01 |  | Deleted | Log | Upd | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
MRTR SLR-New-SOH-SLR-ASR9906 | CE | OKC | SOH | Metro Routers | MRTR CE OKC SOH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
RPHY MRTR-New-SRH-CIN MGMT-2K | CE | OKC | SRH | Metro Routers | MRTR CE OKC SRH OOB Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-New-SRH-CIN MGMT-2K | CE | OKC | SRH | Metro Routers | MRTR CE OKC SRH OOB Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Deleted | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-SRH-CIN-DPA-5200 | CE | OKC | SRH | Metro Routers | MRTR CE OKC SRH OOB Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-New-SRH-CIN-DPA-5200 | CE | OKC | SRH | Metro Routers | MRTR CE OKC SRH OOB Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Deleted | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-SRH-CIN-RPA-5110 | CE | OKC | SRH | Metro Routers | MRTR CE OKC SRH OOB Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-New-SRH-CIN-RPA-5110 | CE | OKC | SRH | Metro Routers | MRTR CE OKC SRH OOB Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
MRTR OOB-New-SRH-OOB Server | CE | OKC | SRH | Metro Routers | MRTR CE OKC SRH OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Active | EP
MRTR OOB-New-SRH-OOB Server | CE | OKC | SRH | Metro Routers | MRTR CE OKC SRH OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 |  | 2020-01-15 |  | Active | Log | Upd | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
MRTR OOB-New-SRH-OOB Server | CE | OKC | SRH | Metro Routers | MRTR CE OKC SRH OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-SRH-SLR-ASR9906 | CE | OKC | SRH | Metro Routers | MRTR CE OKC SRH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR SLR-New-SRH-SLR-ASR9906 | CE | OKC | SRH | Metro Routers | MRTR CE OKC SRH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-01-15 | 2020-03-15 | Deleted | Log | Upd | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
MRTR SLR-New-SRH-SLR-ASR9906 | CE | OKC | SRH | Metro Routers | MRTR CE OKC SRH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-01 | 2020-12-15 | 2020-12-15 | Deleted | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR SLR-New-SRH-SLR-ASR9906 | CE | OKC | SRH | Metro Routers | MRTR CE OKC SRH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-SRH-SLR-ASR9906 | CE | OKC | SRH | Metro Routers | MRTR CE OKC SRH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR OOB-New-TUL-OOB Server | CE | TUL | TUL | Metro Routers | MRTR CE TUL TUL OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR OOB-New-TUL-OOB Server | CE | TUL | TUL | Metro Routers | MRTR CE TUL TUL OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-TUL-SLR-ASR9906 | CE | TUL | TUL | Metro Routers | MRTR CE TUL TUL SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-09-30 | 2020-09-30 | Active | EP
MRTR SLR-New-TUL-SLR-ASR9906 | CE | TUL | TUL | Metro Routers | MRTR CE TUL TUL SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | Upd | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
MRTR SLR-New-TUL-SLR-ASR9906 | CE | TUL | TUL | Metro Routers | MRTR CE TUL TUL SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-TUL-SLR-ASR9906 | CE | TUL | TUL | Metro Routers | MRTR CE TUL TUL SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR OOB-New-WLH-OOB Server | CE | OKC | WLH | Metro Routers | MRTR CE OKC WLH OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR OOB-New-WLH-OOB Server | CE | OKC | WLH | Metro Routers | MRTR CE OKC WLH OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-WLK-SLR-ASR9906 | CE | OKC | WLK | Metro Routers | MRTR CE OKC WLK SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-09-30 | 2020-09-30 | Active | EP
MRTR SLR-New-WLK-SLR-ASR9906 | CE | OKC | WLK | Metro Routers | MRTR CE OKC WLK SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-WLK-SLR-ASR9906 | CE | OKC | WLK | Metro Routers | MRTR CE OKC WLK SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR OOB-New-YAL-OOB Server | CE | TUL | YAL | Metro Routers | MRTR CE TUL YAL OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR OOB-New-YAL-OOB Server | CE | TUL | YAL | Metro Routers | MRTR CE TUL YAL OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-YAL-SLR-ASR9906 | CE | TUL | YAL | Metro Routers | MRTR CE TUL YAL SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-09-30 | 2020-09-30 | Active | EP
MRTR SLR-New-YAL-SLR-ASR9906 | CE | TUL | YAL | Metro Routers | MRTR CE TUL YAL SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | Upd | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
MRTR SLR-New-YAL-SLR-ASR9906 | CE | TUL | YAL | Metro Routers | MRTR CE TUL YAL SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-YAL-SLR-ASR9906 | CE | TUL | YAL | Metro Routers | MRTR CE TUL YAL SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR NCS-Growth-ELK-100G Grow | CE | OMA | ELK | Metro Routers | MRTR CE OMA ELK 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Active | EP
MRTR NCS-Growth-ELK-100G Grow | CE | OMA | ELK | Metro Routers | MRTR CE OMA ELK 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-06-01 | 2020-08-01 | 2020-11-01 | Active | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR NCS-Growth-ELK-100G Grow | CE | OMA | ELK | Metro Routers | MRTR CE OMA ELK 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-ELK-OOB Server | CE | OMA | ELK | Metro Routers | MRTR CE OMA ELK 100G Grow Augment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR OOB-New-ELK-OOB Server | CE | OMA | ELK | Metro Routers | MRTR CE OMA ELK 100G Grow Augment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-ELK-SLR-ASR9906 | CE | OMA | ELK | Metro Routers | MRTR CE OMA ELK SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-09-30 | Active | EP
MRTR SLR-New-ELK-SLR-ASR9906 | CE | OMA | ELK | Metro Routers | MRTR CE OMA ELK SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | Upd | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
MRTR SLR-New-ELK-SLR-ASR9906 | CE | OMA | ELK | Metro Routers | MRTR CE OMA ELK SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-ELK-SLR-ASR9906 | CE | OMA | ELK | Metro Routers | MRTR CE OMA ELK SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-12-31 | 2020-12-31 | Active | Log | Upd | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR SLR-New-ELK-SLR-ASR9906 | CE | OMA | ELK | Metro Routers | MRTR CE OMA ELK SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-09-30 | Active | Log | Upd | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
MRTR NCS-Growth-CLV-100G Grow | NE | CLE | CLV | Metro Routers | MRTR NE CLE CLV 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR NCS-Growth-CLV-100G Grow | NE | CLE | CLV | Metro Routers | MRTR NE CLE CLV 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
NEXUS-CLV-93180-01 | NE | CLE | CLV | Metro Routers | MRTR NE CLE CLV 100G Grow Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | EP
NEXUS-CLV-2248-01 | NE | CLE | CLV | Metro Routers | MRTR NE CLE CLV 100G Grow Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 4 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | EP
MRTR NCS-Growth-PAW-100G Grow | NE | RHD | PAW | Metro Routers | MRTR NE RHD PAW 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR NCS-Growth-PAW-100G Grow | NE | RHD | PAW | Metro Routers | MRTR NE RHD PAW 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-PRV-100G Grow | NE | RHD | PRV | Metro Routers | MRTR NE RHD PRV 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-01-30 | 2020-01-30 | Active | EP
MRTR NCS-Growth-PRV-100G Grow | NE | RHD | PRV | Metro Routers | MRTR NE RHD PRV 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-01-30 | 2020-01-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-PTM-100G Grow | VA | HRD | PTM | Metro Routers | MRTR VA HRD PTM OOB Deployment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR NCS-Growth-PTM-100G Grow | VA | HRD | PTM | Metro Routers | MRTR VA HRD PTM OOB Deployment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR NCS-Growth-PTM-100G Grow | VA | HRD | PTM | Metro Routers | MRTR VA HRD PTM OOB Deployment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-WWK-100G Grow | NE | RHD | WWK | Metro Routers | MRTR NE RHD WWK 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | EP
MRTR NCS-Growth-GNS-100G Grow | SE | GAN | GNS | Metro Routers | MRTR SE GAN GNS 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-06-30 | 2020-06-30 | Active | EP
MRTR NCS-Growth-GNS-100G Grow | SE | GAN | GNS | Metro Routers | MRTR SE GAN GNS 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR NCS-Growth-OCL-100G Grow | SE | GAN | OCL | Metro Routers | MRTR SE GAN OCL 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-06-30 | 2020-06-30 | Active | EP
MRTR NCS-Growth-OCL-100G Grow | SE | GAN | OCL | Metro Routers | MRTR SE GAN OCL 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-BTR-SLR-ASR9906 | SE | BTR | BTR | Metro Routers | MRTR SE BTR BTR SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-11-30 | Active | EP
MRTR SLR-New-BTR-SLR-ASR9906 | SE | BTR | BTR | Metro Routers | MRTR SE BTR BTR SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-BTR-SLR-ASR9906 | SE | BTR | BTR | Metro Routers | MRTR SE BTR BTR SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-11-30 | 2020-11-30 | Active | Log | Upd | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR SLR-New-BTR-SLR-ASR9906 | SE | BTR | BTR | Metro Routers | MRTR SE BTR BTR SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-11-30 | Active | Log | Upd | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
MRTR NCS-Growth-LPL-100G Grow | SE | NOR | LPL | Metro Routers | MRTR SE NOR LPL 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | EP
MRTR NCS-Growth-MCY-100G Grow | SE | NOR | MCY | Metro Routers | MRTR SE NOR MCY 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | EP
MRTR NCS-Growth-SPC-100G Grow | SE | BTR | SPC | Metro Routers | MRTR SE BTR SPC 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-06-30 | 2020-06-30 | Active | EP
MRTR NCS-Growth-SPC-100G Grow | SE | BTR | SPC | Metro Routers | MRTR SE BTR SPC 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR NCS-Growth-WRB-100G Grow | SE | MGA | WRB | Metro Routers | MRTR SE MGA WRB 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | EP
MRTR NCS-Growth-BEL-100G Grow | SW | ARZ | BEL | Metro Routers | MRTR SW ARZ BEL 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | EP
MRTR NCS-Growth-BEL-100G Grow | SW | ARZ | BEL | Metro Routers | MRTR SW ARZ BEL 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR NCS-Growth-BEL-NCS Line Card | SW | ARZ | BEL | Metro Routers | MRTR SW ARZ BEL NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-01-01 03:01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR NCS-Growth-BEL-NCS Line Card | SW | ARZ | BEL | Metro Routers | MRTR SW ARZ BEL NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-01-01 03:01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-CHD-100G Grow | SW | ARZ | CHD | Metro Routers | MRTR SW ARZ CHD 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-09-01 | 2020-11-15 | 2020-12-31 | Active | EP
MRTR NCS-Growth-CHD-100G Grow | SW | ARZ | CHD | Metro Routers | MRTR SW ARZ CHD 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-10-01 | 2020-12-15 | 2020-07-15 | Active | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR NCS-Growth-CHD-100G Grow | SW | ARZ | CHD | Metro Routers | MRTR SW ARZ CHD 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-09-01 | 2020-11-15 | 2020-12-31 | Active | Log | Upd | SN-0588 | Schedule Change | Approved | 2020-05-14 14:36 | 1 Some of the corrections listed by Solutions team in the initial submission
MRTR NCS-Growth-FWL-100G Grow | SW | ARZ | FWL | Metro Routers | MRTR SW ARZ FWL 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-07-01 | 2020-09-30 | 2021-03-31 | Active | EP
MRTR NCS-Growth-FWL-100G Grow | SW | ARZ | FWL | Metro Routers | MRTR SW ARZ FWL 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-09-01 | 2020-11-15 | 2020-07-15 | Active | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR NCS-Growth-FWL-100G Grow | SW | ARZ | FWL | Metro Routers | MRTR SW ARZ FWL 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-07-01 | 2020-09-30 | 2021-03-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-MCD-100G Grow | SW | ARZ | MCD | Metro Routers | MRTR SW ARZ MCD 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-09-01 | 2020-11-15 | 2020-12-31 | Active | EP
MRTR NCS-Growth-MCD-100G Grow | SW | ARZ | MCD | Metro Routers | MRTR SW ARZ MCD 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-09-01 | 2020-11-15 | 2020-07-15 | Active | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR NCS-Growth-MCD-100G Grow | SW | ARZ | MCD | Metro Routers | MRTR SW ARZ MCD 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-09-01 | 2020-11-15 | 2020-12-31 | Active | Log | Upd | SN-0588 | Schedule Change | Approved | 2020-05-14 14:36 | 1 Some of the corrections listed by Solutions team in the initial submission
MRTR NCS-Growth-MSA-100G Grow | SW | ARZ | MSA | Metro Routers | MRTR SW ARZ MSA 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | EP
MRTR NCS-Growth-TUC-100G Grow | SW | ARZ | TUC | Metro Routers | MRTR SW ARZ TUC 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-09-01 | 2020-11-15 | 2020-11-15 | Active | EP
MRTR NCS-Growth-TUC-100G Grow | SW | ARZ | TUC | Metro Routers | MRTR SW ARZ TUC 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-09-01 | 2020-11-15 | 2020-11-15 | Active | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR NCS-Growth-BLU-NCS Line Card | SW | LAS | BLU | Metro Routers | MRTR SW LAS BLU NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-01-01 03:01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR NCS-Growth-BLU-NCS Line Card | SW | LAS | BLU | Metro Routers | MRTR SW LAS BLU NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-09-01 | 2020-11-15 | 2020-11-15 | Active | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR NCS-Growth-BLU-NCS Line Card | SW | LAS | BLU | Metro Routers | MRTR SW LAS BLU NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-01-01 03:01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-BLU-SLR-ASR9906 | SW | LAS | BLU | Metro Routers | MRTR SW LAS BLU SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR SLR-New-BLU-SLR-ASR9906 | SW | LAS | BLU | Metro Routers | MRTR SW LAS BLU SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | Upd | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
MRTR SLR-New-BLU-SLR-ASR9906 | SW | LAS | BLU | Metro Routers | MRTR SW LAS BLU SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-15 | 2020-11-15 | Active | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR SLR-New-BLU-SLR-ASR9906 | SW | LAS | BLU | Metro Routers | MRTR SW LAS BLU SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-HEN-100G Grow | SW | LAS | HEN | Metro Routers | MRTR SW LAS HEN 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | EP
MRTR NCS-Growth-HEN-NCS Line Card | SW | LAS | HEN | Metro Routers | MRTR SW LAS HEN NCS Augment POR20 | Card & Optics | NCS Line Card | 4 | 2020-01-01 03:01 | 2021-03-31 | 2021-03-31 | Active | EP
MRTR NCS-Growth-HEN-NCS Line Card | SW | LAS | HEN | Metro Routers | MRTR SW LAS HEN NCS Augment POR20 | Card & Optics | NCS Line Card | 4 | 2020-01-01 03:01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-HEN-NCS Line Card | SW | LAS | HEN | Metro Routers | MRTR SW LAS HEN NCS Augment POR20 | Card & Optics | NCS Line Card | 4 | 2020-01-01 03:01 | 2021-03-31 | 2021-03-31 | Active | Log | Upd | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR SLR-New-HEN-SLR-ASR9906 | SW | LAS | HEN | Metro Routers | MRTR SW LAS HEN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR SLR-New-HEN-SLR-ASR9906 | SW | LAS | HEN | Metro Routers | MRTR SW LAS HEN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | Upd | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
MRTR SLR-New-HEN-SLR-ASR9906 | SW | LAS | HEN | Metro Routers | MRTR SW LAS HEN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-TEN-100G Grow | SW | LAS | TEN | Metro Routers | MRTR SW LAS TEN 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | EP
MRTR SLR-New-TEN-SLR-ASR9906 | SW | LAS | TEN | Metro Routers | MRTR SW LAS TEN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR SLR-New-TEN-SLR-ASR9906 | SW | LAS | TEN | Metro Routers | MRTR SW LAS TEN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | Upd | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
MRTR SLR-New-TEN-SLR-ASR9906 | SW | LAS | TEN | Metro Routers | MRTR SW LAS TEN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-VLY-100G Grow | SW | LAS | VLY | Metro Routers | MRTR SW LAS VLY 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | EP
NEXUS-CHS-2248-01 | VA | HRD | CHS | Metro Routers | MRTR VA HRD CHS Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-04-20 | 2020-06-30 | 2020-06-30 | Active | EP
NEXUS-CHS-2248-01 | VA | HRD | CHS | Metro Routers | MRTR VA HRD CHS Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-04-20 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0588 | Schedule Change | Approved | 2020-05-14 14:36 | 1 Some of the corrections listed by Solutions team in the initial submission
NEXUS-GLO-2248-01 | VA | HRD | GLO | Metro Routers | MRTR VA HRD GLO Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-04-15 | 2020-06-30 | 2020-06-30 | Active | EP
NEXUS-GLO-2248-01 | VA | HRD | GLO | Metro Routers | MRTR VA HRD GLO Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
NEXUS-GLO-2248-01 | VA | HRD | GLO | Metro Routers | MRTR VA HRD GLO Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-04-15 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0588 | Schedule Change | Approved | 2020-05-14 14:36 | 1 Some of the corrections listed by Solutions team in the initial submission
MRTR NCS-Growth-LTF-100G Grow | VA | HRD | LTF | Metro Routers | MRTR VA HRD LTF 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-06-30 | 2020-06-30 | Active | EP
MRTR NCS-Growth-LTF-100G Grow | VA | HRD | LTF | Metro Routers | MRTR VA HRD LTF 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-NRF-100G Grow | VA | HRD | NRF | Metro Routers | MRTR VA HRD NRF 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR NCS-Growth-NRF-100G Grow | VA | HRD | NRF | Metro Routers | MRTR VA HRD NRF 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-NRF-OOB Server | VA | HRD | NRF | Metro Routers | MRTR VA HRD NRF OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 4 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR OOB-New-NRF-OOB Server | VA | HRD | NRF | Metro Routers | MRTR VA HRD NRF OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 4 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-NWP-100G Grow | VA | HRD | NWP | Metro Routers | MRTR VA HRD NWP 100G Grow Augment POR20 | Card & Optics | 100G Grow | 1 | 2020-07-01 | 2020-09-30 | 2021-03-31 | Active | EP
MRTR NCS-Growth-NWP-100G Grow | VA | HRD | NWP | Metro Routers | MRTR VA HRD NWP 100G Grow Augment POR20 | Card & Optics | 100G Grow | 1 | 2020-07-01 | 2020-09-30 | 2021-03-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-NWP-OOB Server | VA | HRD | NWP | Metro Routers | MRTR VA HRD NWP OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 4 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR OOB-New-NWP-OOB Server | VA | HRD | NWP | Metro Routers | MRTR VA HRD NWP OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 4 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-NWP-SLR-ASR9906 | VA | HRD | NWP | Metro Routers | MRTR VA HRD NWP SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-12-31 | Active | EP
MRTR SLR-New-NWP-SLR-ASR9906 | VA | HRD | NWP | Metro Routers | MRTR VA HRD NWP 100G Grow Augment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-NWP-SLR-ASR9906 | VA | HRD | NWP | Metro Routers | MRTR VA HRD NWP SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0773 | Scope Change | Approved | 2020-07-27 09:32 | Updating POR and aligning activity plans based on feedback from the field
MRTR SLR-New-NWP-SLR-ASR9906 | VA | HRD | NWP | Metro Routers | MRTR VA HRD NWP SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-12-31 | Active | Log | Upd | SN-1037 | Schedule Change | Approved | 2020-11-06 09:51 | Alignment of POR based on feedback from the field
NEXUS-NWP-2248-01 | VA | HRD | NWP | Metro Routers | MRTR VA HRD NWP 100G Grow Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-04-20 | 2020-06-30 | 2020-06-30 | Active | EP
NEXUS-NWP-2248-01 | VA | HRD | NWP | Metro Routers | MRTR VA HRD NWP 100G Grow Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-04-20 | 2020-03-15 | 2020-04-15 | Active | Log | Upd | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
NEXUS-NWP-2248-01 | VA | HRD | NWP | Metro Routers | MRTR VA HRD NWP 100G Grow Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-04-20 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0588 | Schedule Change | Approved | 2020-05-14 14:36 | 1 Some of the corrections listed by Solutions team in the initial submission
MRTR NCS-Growth-OCN-100G Grow | VA | HRD | OCN | Metro Routers | MRTR VA HRD OCN 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR NCS-Growth-OCN-100G Grow | VA | HRD | OCN | Metro Routers | MRTR VA HRD OCN 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-PRA-OOB Server | VA | HRD | PRA | Metro Routers | MRTR VA HRD PRA OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR OOB-New-PRA-OOB Server | VA | HRD | PRA | Metro Routers | MRTR VA HRD PRA OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-PRM-OOB Server | VA | HRD | PTM | Metro Routers | MRTR VA HRD PTM OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis |  |  |  |  | Deleted | EP
MRTR OOB-New-PRM-OOB Server | VA | HRD | PTM | Metro Routers | MRTR VA HRD PTM OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis |  |  |  |  | Deleted | Log | Del | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-VBC-OOB Server | VA | HRD | VBC | Metro Routers | MRTR VA HRD VBC OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 4 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR OOB-New-VBC-OOB Server | VA | HRD | VBC | Metro Routers | MRTR VA HRD VBC OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 4 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-VBC-SLR-ASR9906 | VA | HRD | VBC | Metro Routers | MRTR VA HRD VBC SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-12-31 | Active | EP
MRTR SLR-New-VBC-SLR-ASR9906 | VA | HRD | VBC | Metro Routers | MRTR VA HRD VBC SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | Upd | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
MRTR SLR-New-VBC-SLR-ASR9906 | VA | HRD | VBC | Metro Routers | MRTR VA HRD VBC SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-VBC-SLR-ASR9906 | VA | HRD | VBC | Metro Routers | MRTR VA HRD VBC SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-12-31 | Active | Log | Upd | SN-1037 | Schedule Change | Approved | 2020-11-06 09:51 | Alignment of POR based on feedback from the field
MRTR NCS-Growth-FLK-100G Grow | VA | NVA | FLK | Metro Routers | MRTR VA NVA FLK 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR NCS-Growth-FLK-100G Grow | VA | NVA | FLK | Metro Routers | MRTR VA NVA FLK 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-MFD-100G Grow | VA | NVA | MFD | Metro Routers | MRTR VA NVA MFD 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | EP
MRTR OOB-New-RON-OOB Server | VA | ROA | RON | Metro Routers | MRTR VA ROA RON OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR OOB-New-RON-OOB Server | VA | ROA | RON | Metro Routers | MRTR VA ROA RON OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-New-SAB-NCS-5504-250 Sup Card | CA | SAB | SAB | Metro Routers | MRTR CA SAB SAB NCS Deployment POR20 | Card & Optics | NCS-5504-250 Sup Card | 2 | 2020-07-05 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR NCS-New-SAB-NCS-5504-250 Sup Card | CA | SAB | SAB | Metro Routers | MRTR CA SAB SAB NCS Deployment POR20 | Card & Optics | NCS-5504-250 Sup Card | 2 | 2020-07-05 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
NEXUS-VBC-93180-01 | VA | HRD | VBC | Metro Routers | MRTR VA HRD VBC Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-04-20 | 2020-06-01 |  | Active | EP
NEXUS-MFD-3048-01 | VA | NVA | MFD | Metro Routers | MRTR VA NVA MFD Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 | 2020-04-20 | 2020-06-01 |  | Active | EP
NEXUS-MFD-93180-01 | VA | NVA | MFD | Metro Routers | MRTR VA NVA MFD Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 4 | 2020-04-20 | 2020-06-01 | 2020-06-01 | Active | EP
NEXUS-MFD-93180-01 | VA | NVA | MFD | Metro Routers | MRTR VA NVA MFD Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 4 | 2020-04-20 | 2020-06-01 | 2020-06-01 | Active | Log | Upd | SN-0239 | Schedule Change | Approved | 2020-02-07 14:34 | 1 Updating Plan to reflect the Financials per the BOM 2 This subset had Raid Risk raised as the Plan was not aligned to the final version of the BOM 3 INP and PDG were re conciling on if any changes needs to be made on top of the existing BOM;s placed
NEXUS-RON-2248-01 | VA | ROA | RON | Metro Routers | MRTR VA ROA RON Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 3 | 2020-04-20 | 2020-06-01 | 2020-06-01 | Active | EP
NEXUS-RON-2248-01 | VA | ROA | RON | Metro Routers | MRTR VA ROA RON Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 3 | 2020-04-20 | 2020-06-01 | 2020-06-01 | Active | Log | Upd | SN-0239 | Schedule Change | Approved | 2020-02-07 14:34 | 1 Updating Plan to reflect the Financials per the BOM 2 This subset had Raid Risk raised as the Plan was not aligned to the final version of the BOM 3 INP and PDG were re conciling on if any changes needs to be made on top of the existing BOM;s placed
NEXUS-RON-3048-01 | VA | ROA | RON | Metro Routers | MRTR VA ROA RON Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis |  |  |  |  | Deleted | EP
NEXUS-RON-3048-01 | VA | ROA | RON | Metro Routers | MRTR VA ROA RON Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis |  |  |  |  | Deleted | Log | Del | SN-0239 | Schedule Change | Approved | 2020-02-07 14:34 | 1 Updating Plan to reflect the Financials per the BOM 2 This subset had Raid Risk raised as the Plan was not aligned to the final version of the BOM 3 INP and PDG were re conciling on if any changes needs to be made on top of the existing BOM;s placed
NEXUS-RON-93108-01 | VA | ROA | RON | Metro Routers | MRTR VA ROA RON Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 2 | 2020-04-20 | 2020-06-01 | 2020-06-01 | Active | EP
NEXUS-RON-93108-01 | VA | ROA | RON | Metro Routers | MRTR VA ROA RON Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis |  |  |  |  | Active | Log | Del | SN-0239 | Schedule Change | Approved | 2020-02-07 14:34 | 1 Updating Plan to reflect the Financials per the BOM 2 This subset had Raid Risk raised as the Plan was not aligned to the final version of the BOM 3 INP and PDG were re conciling on if any changes needs to be made on top of the existing BOM;s placed
NEXUS-RON-93108-01 | VA | ROA | RON | Metro Routers | MRTR VA ROA RON Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 2 | 2020-04-20 | 2020-06-01 | 2020-06-01 | Active | Log | Undel | SN-0588 | Schedule Change | Approved | 2020-05-14 14:36 | 1 Some of the corrections listed by Solutions team in the initial submission
NEXUS-RON-93180-01 | VA | ROA | RON | Metro Routers | MRTR VA ROA RON Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 4 | 2020-04-20 | 2020-06-01 | 2020-06-01 | Active | EP
NEXUS-RON-93180-01 | VA | ROA | RON | Metro Routers | MRTR VA ROA RON Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 4 | 2020-04-20 | 2020-06-01 | 2020-06-01 | Active | Log | Upd | SN-0239 | Schedule Change | Approved | 2020-02-07 14:34 | 1 Updating Plan to reflect the Financials per the BOM 2 This subset had Raid Risk raised as the Plan was not aligned to the final version of the BOM 3 INP and PDG were re conciling on if any changes needs to be made on top of the existing BOM;s placed
MRTR NCS-Growth-PEO-NCS Line Card | SW | ARZ | PEO | Metro Routers | MRTR SW ARZ PEO NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-09-01 | 2020-11-30 | 2021-02-28 | Active | EP
MRTR NCS-Growth-PEO-NCS Line Card | SW | ARZ | PEO | Metro Routers | MRTR SW ARZ PEO NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-09-01 | 2020-11-15 | 2020-11-15 | Active | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR NCS-Growth-PEO-NCS Line Card | SW | ARZ | PEO | Metro Routers | MRTR SW ARZ PEO NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-09-01 | 2020-11-30 | 2021-02-28 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-TUC-NCS Line Card | SW | ARZ | TUC | Metro Routers | MRTR SW ARZ TUC NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR NCS-Growth-TUC-NCS Line Card | SW | ARZ | TUC | Metro Routers | MRTR SW ARZ TUC NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-09-01 | 2020-11-30 | 2021-02-28 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-TUC-NCS Line Card | SW | ARZ | TUC | Metro Routers | MRTR SW ARZ TUC NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR NCS-Growth-TEN-NCS Line Card | SW | LAS | TEN | Metro Routers | MRTR SW LAS TEN NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR NCS-Growth-TEN-NCS Line Card | SW | LAS | TEN | Metro Routers | MRTR SW LAS TEN NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-09-01 | 2020-11-30 | 2021-02-28 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-TEN-NCS Line Card | SW | LAS | TEN | Metro Routers | MRTR SW LAS TEN NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR OOB-New-VLY-OOB Server | SW | LAS | VLY | Metro Routers | MRTR SW LAS VLY OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-10-01 | 2020-12-15 | 2020-12-15 | Active | EP
MRTR OOB-New-CHS-OOB Server | VA | HRD | CHS | Metro Routers | MRTR VA HRD CHS OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-04-01 03:01 | 2020-06-30 | 2020-09-30 | Active | EP
MRTR OOB-New-CHS-OOB Server | VA | HRD | CHS | Metro Routers | MRTR VA HRD CHS OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-04-01 03:01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-GLO-OOB Server | VA | HRD | GLO | Metro Routers | MRTR VA HRD GLO OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | EP
MRTR OOB-New-GLO-OOB Server | VA | HRD | GLO | Metro Routers | MRTR VA HRD GLO OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-HCK-OOB Server | VA | HRD | HCK | Metro Routers | MRTR VA HRD HCK OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | EP
MRTR OOB-New-HCK-OOB Server | VA | HRD | HCK | Metro Routers | MRTR VA HRD HCK OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-LTF-OOB Server | VA | HRD | LTF | Metro Routers | MRTR VA HRD LTF OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | EP
MRTR OOB-New-LTF-OOB Server | VA | HRD | LTF | Metro Routers | MRTR VA HRD LTF OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-NKT-OOB Server | VA | HRD | NKT | Metro Routers | MRTR VA HRD NKT OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | EP
MRTR OOB-New-NKT-OOB Server | VA | HRD | NKT | Metro Routers | MRTR VA HRD NKT OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
NEXUS-NRF-2248-01 | VA | HRD | NRF | Metro Routers | MRTR VA HRD NRF Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-04-20 | 2020-06-01 | 2020-06-01 | Active | EP
NEXUS-NRF-2248-01 | VA | HRD | NRF | Metro Routers | MRTR VA HRD NRF Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-04-20 | 2020-06-01 | 2020-06-01 | Active | Log | Upd | SN-0239 | Schedule Change | Approved | 2020-02-07 14:34 | 1 Updating Plan to reflect the Financials per the BOM 2 This subset had Raid Risk raised as the Plan was not aligned to the final version of the BOM 3 INP and PDG were re conciling on if any changes needs to be made on top of the existing BOM;s placed
MRTR OOB-New-OCN-OOB Server | VA | HRD | OCN | Metro Routers | MRTR VA HRD OCN OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | EP
MRTR OOB-New-OCN-OOB Server | VA | HRD | OCN | Metro Routers | MRTR VA HRD OCN OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-LTF-SLR-ASR9906 | VA | HRD | LTF | Metro Routers | MRTR VA HRD LTF SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR SLR-New-LTF-SLR-ASR9906 | VA | HRD | LTF | Metro Routers | MRTR VA HRD LTF SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-LTF-SLR-ASR9906 | VA | HRD | LTF | Metro Routers | MRTR VA HRD LTF SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-NRF-SLR-ASR9906 | VA | HRD | NRF | Metro Routers | MRTR VA HRD NRF SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR SLR-New-NRF-SLR-ASR9906 | VA | HRD | NRF | Metro Routers | MRTR VA HRD NRF SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-PRM-SLR-ASR9906 | VA | HRD | PTM | Metro Routers | MRTR VA HRD PTM SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR SLR-New-PRM-SLR-ASR9906 | VA | HRD | PTM | Metro Routers | MRTR VA HRD PTM SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-PTM-SLR-ASR9906 | VA | HRD | PTM | Metro Routers | MRTR VA HRD PTM SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR SLR-New-PTM-SLR-ASR9906 | VA | HRD | PTM | Metro Routers | MRTR VA HRD PTM SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-PRA-SLR-ASR9906 | VA | HRD | PRA | Metro Routers | MRTR VA HRD PRA SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR SLR-New-PRA-SLR-ASR9906 | VA | HRD | PRA | Metro Routers | MRTR VA HRD PRA SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-FBG-SLR-ASR9906 | VA | NVA | FBG | Metro Routers | MRTR VA NVA FBG SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR SLR-New-FBG-SLR-ASR9906 | VA | NVA | FBG | Metro Routers | MRTR VA NVA FBG SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-FBG-SLR-ASR9906 | VA | NVA | FBG | Metro Routers | MRTR VA NVA FBG SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-RON-SLR-ASR9906 | VA | ROA | RON | Metro Routers | MRTR VA ROA RON SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR SLR-New-RON-SLR-ASR9906 | VA | ROA | RON | Metro Routers | MRTR VA ROA RON SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-RON-SLR-ASR9906 | VA | ROA | RON | Metro Routers | MRTR VA ROA RON SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR NCS-Growth-ERN-NCS Line Card | SW | LAS | ERN | Metro Routers | MRTR SW LAS ERN NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR NCS-Growth-ERN-NCS Line Card | SW | LAS | ERN | Metro Routers | MRTR SW LAS ERN NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-09-01 | 2020-11-30 | 2021-02-28 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-ERN-NCS Line Card | SW | LAS | ERN | Metro Routers | MRTR SW LAS ERN NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
NEXUS-PTM-2248-01 | VA | HRD | PTM | Metro Routers | MRTR VA HRD PTM Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-07-15 | 2020-09-30 | 2020-09-30 | Active | EP
NEXUS-PTM-2248-01 | VA | HRD | PTM | Metro Routers | MRTR VA HRD PTM Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-07-15 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0588 | Schedule Change | Approved | 2020-05-14 14:36 | 1 Some of the corrections listed by Solutions team in the initial submission
NEXUS-PRA-2248-01 | VA | HRD | PRA | Metro Routers | MRTR VA HRD PRA Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-04-20 | 2020-06-01 |  | Active | EP
MRTR OOB-New-DRA-OOB Server | VA | NVA | DRA | Metro Routers | MRTR VA NVA DRA OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-05-01 | 2020-07-31 | 2020-10-31 | Active | EP
MRTR OOB-New-DRA-OOB Server | VA | NVA | DRA | Metro Routers | MRTR VA NVA DRA OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-05-01 | 2020-07-31 | 2020-10-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-FLK-OOB Server | VA | NVA | FLK | Metro Routers | MRTR VA NVA FLK OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-05-01 | 2020-07-31 | 2020-10-31 | Active | EP
MRTR OOB-New-FLK-OOB Server | VA | NVA | FLK | Metro Routers | MRTR VA NVA FLK OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-05-01 | 2020-07-31 | 2020-10-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-FST-OOB Server | VA | NVA | FST | Metro Routers | MRTR VA NVA FST OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-05-01 | 2020-07-31 | 2020-10-31 | Active | EP
MRTR OOB-New-FST-OOB Server | VA | NVA | FST | Metro Routers | MRTR VA NVA FST OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-05-01 | 2020-07-31 | 2020-10-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-FBG-OOB Server | VA | NVA | FBG | Metro Routers | MRTR VA NVA FBG OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-10-01 | 2020-12-15 | 2020-12-15 | Active | EP
MRTR OOB-New-GCR-OOB Server | VA | NVA | GCR | Metro Routers | MRTR VA NVA GCR OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-05-01 | 2020-07-31 | 2020-10-31 | Active | EP
MRTR OOB-New-GCR-OOB Server | VA | NVA | GCR | Metro Routers | MRTR VA NVA GCR OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-05-01 | 2020-07-31 | 2020-10-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-MFD-OOB Server | VA | NVA | MFD | Metro Routers | MRTR VA NVA MFD OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 4 | 2020-05-01 | 2020-07-31 | 2020-10-31 | Active | EP
MRTR OOB-New-MFD-OOB Server | VA | NVA | MFD | Metro Routers | MRTR VA NVA MFD OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 4 | 2020-05-01 | 2020-07-31 | 2020-10-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-RHL-OOB Server | VA | NVA | RHL | Metro Routers | MRTR VA NVA RHL OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-05-01 | 2020-07-31 | 2020-10-31 | Active | EP
MRTR OOB-New-RHL-OOB Server | VA | NVA | RHL | Metro Routers | MRTR VA NVA RHL OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-05-01 | 2020-07-31 | 2020-10-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-TCR-OOB Server | VA | NVA | TCR | Metro Routers | MRTR VA NVA TCR OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-05-01 | 2020-07-31 | 2020-10-31 | Active | EP
MRTR OOB-New-TCR-OOB Server | VA | NVA | TCR | Metro Routers | MRTR VA NVA TCR OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-05-01 | 2020-07-31 | 2020-10-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-MCD-NEW-AAR | SW | ARZ | MCD | Metro Routers | MRTR SW ARZ MCD AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-MCD-NEW-AAR | SW | ARZ | MCD | Metro Routers | MRTR SW ARZ MCD AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-01 | 2020-07-15 | 2020-07-15 | Active | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-MCD-NEW-AAR | SW | ARZ | MCD | Metro Routers | MRTR SW ARZ MCD AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-05 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-MCD-NEW-AAR | SW | ARZ | MCD | Metro Routers | MRTR SW ARZ MCD AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR VSR-New-MCD-VSR-ASR9906 | SW | ARZ | MCD | Metro Routers | MRTR SW ARZ MCD VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR VSR-New-MCD-VSR-ASR9906 | SW | ARZ | MCD | Metro Routers | MRTR SW ARZ MCD VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-15 | 2020-07-15 | Deleted | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR VSR-New-MCD-VSR-ASR9906 | SW | ARZ | MCD | Metro Routers | MRTR SW ARZ MCD VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2021-03-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR VSR-New-MCD-VSR-ASR9906 | SW | ARZ | MCD | Metro Routers | MRTR SW ARZ MCD VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-NSC-NEW-AAR | SW | ARZ | NSC | Metro Routers | MRTR SW ARZ NSC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-NSC-NEW-AAR | SW | ARZ | NSC | Metro Routers | MRTR SW ARZ NSC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-01 | 2020-07-15 | 2020-07-15 | Active | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-NSC-NEW-AAR | SW | ARZ | NSC | Metro Routers | MRTR SW ARZ NSC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-05 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-NSC-NEW-AAR | SW | ARZ | NSC | Metro Routers | MRTR SW ARZ NSC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-PEO-NEW-AAR | SW | ARZ | PEO | Metro Routers | MRTR SW ARZ PEO AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-PEO-NEW-AAR | SW | ARZ | PEO | Metro Routers | MRTR SW ARZ PEO AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-01 | 2020-07-15 | 2020-07-15 | Active | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-PEO-NEW-AAR | SW | ARZ | PEO | Metro Routers | MRTR SW ARZ PEO AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-05 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-PEO-NEW-AAR | SW | ARZ | PEO | Metro Routers | MRTR SW ARZ PEO AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-PNL-NEW-AAR | SW | ARZ | PNL | Metro Routers | MRTR SW ARZ PNL AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-PNL-NEW-AAR | SW | ARZ | PNL | Metro Routers | MRTR SW ARZ PNL AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-01 | 2020-07-15 | 2020-07-15 | Active | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-PNL-NEW-AAR | SW | ARZ | PNL | Metro Routers | MRTR SW ARZ PNL AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-05 | 2020-08-31 | 2020-11-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-PNL-NEW-AAR | SW | ARZ | PNL | Metro Routers | MRTR SW ARZ PNL AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-SSC-NEW-AAR | SW | ARZ | SSC | Metro Routers | MRTR SW ARZ SSC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-SSC-NEW-AAR | SW | ARZ | SSC | Metro Routers | MRTR SW ARZ SSC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-01 | 2020-07-15 | 2020-07-15 | Active | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-SSC-NEW-AAR | SW | ARZ | SSC | Metro Routers | MRTR SW ARZ SSC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-05 | 2020-08-31 | 2020-11-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-SSC-NEW-AAR | SW | ARZ | SSC | Metro Routers | MRTR SW ARZ SSC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-TUC-NEW-AAR | SW | ARZ | TUC | Metro Routers | MRTR SW ARZ TUC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-TUC-NEW-AAR | SW | ARZ | TUC | Metro Routers | MRTR SW ARZ TUC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-01 | 2020-07-15 | 2020-07-15 | Active | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-TUC-NEW-AAR | SW | ARZ | TUC | Metro Routers | MRTR SW ARZ TUC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-05 | 2020-08-31 | 2020-11-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-TUC-NEW-AAR | SW | ARZ | TUC | Metro Routers | MRTR SW ARZ TUC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR VSR-New-TUC-VSR-ASR9906 | SW | ARZ | TUC | Metro Routers | MRTR SW ARZ TUC VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR VSR-New-TUC-VSR-ASR9906 | SW | ARZ | TUC | Metro Routers | MRTR SW ARZ TUC VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2021-03-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR VSR-New-TUC-VSR-ASR9906 | SW | ARZ | TUC | Metro Routers | MRTR SW ARZ TUC VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-ALI-NEW-AAR | SW | LAS | ALI | Metro Routers | MRTR SW LAS ALI AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-ALI-NEW-AAR | SW | LAS | ALI | Metro Routers | MRTR SW LAS ALI AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-01 | 2020-07-15 | 2020-07-15 | Active | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-ALI-NEW-AAR | SW | LAS | ALI | Metro Routers | MRTR SW LAS ALI AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-05 | 2020-08-31 | 2020-11-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-ALI-NEW-AAR | SW | LAS | ALI | Metro Routers | MRTR SW LAS ALI AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-ERN-NEW-AAR | SW | LAS | ERN | Metro Routers | MRTR SW LAS ERN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-ERN-NEW-AAR | SW | LAS | ERN | Metro Routers | MRTR SW LAS ERN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-01 | 2020-07-15 | 2020-07-15 | Active | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-ERN-NEW-AAR | SW | LAS | ERN | Metro Routers | MRTR SW LAS ERN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-05 | 2020-08-31 | 2020-11-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-ERN-NEW-AAR | SW | LAS | ERN | Metro Routers | MRTR SW LAS ERN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR VSR-New-HEN-VSR-ASR9906 | SW | LAS | HEN | Metro Routers | MRTR SW LAS HEN VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR VSR-New-HEN-VSR-ASR9906 | SW | LAS | HEN | Metro Routers | MRTR SW LAS HEN VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2021-03-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR VSR-New-HEN-VSR-ASR9906 | SW | LAS | HEN | Metro Routers | MRTR SW LAS HEN VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-VLY-NEW-AAR | SW | LAS | VLY | Metro Routers | MRTR SW LAS VLY AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-11-30 | Active | EP
MRTR AAR-New-VLY-NEW-AAR | SW | LAS | VLY | Metro Routers | MRTR SW LAS VLY AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Active | Log | Del | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-VLY-NEW-AAR | SW | LAS | VLY | Metro Routers | MRTR SW LAS VLY AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Active | Log | Del | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-VLY-NEW-AAR | SW | LAS | VLY | Metro Routers | MRTR SW LAS VLY AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-11-30 | Active | Log | Undel | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR VSR-New-NRF-VSR-ASR9906 | VA | HRD | VBC | Metro Routers | MRTR VA HRD VBC VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-01 | 2020-12-31 | 2021-03-31 | Active | EP
MRTR VSR-New-NRF-VSR-ASR9906 | VA | HRD | NRF | Metro Routers | MRTR VA HRD NRF VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2021-03-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR VSR-New-NRF-VSR-ASR9906 | VA | HRD | NRF | Metro Routers | MRTR VA HRD NRF VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-01 | 2020-12-31 | 2021-03-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR VSR-New-NRF-VSR-ASR9906 | VA | HRD | VBC | Metro Routers | MRTR VA HRD VBC VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-01 | 2020-12-31 | 2021-03-31 | Active | Log | Upd | SN-1037 | Schedule Change | Approved | 2020-11-06 09:51 | Alignment of POR based on feedback from the field
MRTR VSR-New-VBC-VSR-ASR9906 | VA | HRD | VBC | Metro Routers | MRTR VA HRD VBC VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR VSR-New-VBC-VSR-ASR9906 | VA | HRD | VBC | Metro Routers | MRTR VA HRD VBC VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2021-03-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR VSR-New-VBC-VSR-ASR9906 | VA | HRD | VBC | Metro Routers | MRTR VA HRD VBC VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR VSR-New-RON-VSR-ASR9906 | VA | ROA | RON | Metro Routers | MRTR VA ROA RON VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR VSR-New-RON-VSR-ASR9906 | VA | ROA | RON | Metro Routers | MRTR VA ROA RON VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2021-03-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR VSR-New-RON-VSR-ASR9906 | VA | ROA | RON | Metro Routers | MRTR VA ROA RON VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-DNP-NEW-AAR | CA | ORG | DNP | Metro Routers | MRTR CA ORG DNP AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | EP
MRTR AAR-New-DNP-NEW-AAR | CA | ORG | DNP | Metro Routers | MRTR CA ORG DNP AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-15 | 2020-06-15 | Active | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-DNP-NEW-AAR | CA | ORG | DNP | Metro Routers | MRTR CA ORG DNP AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-DNP-NEW-AAR | CA | ORG | DNP | Metro Routers | MRTR CA ORG DNP AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Active | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-DNP-NEW-AAR | CA | ORG | DNP | Metro Routers | MRTR CA ORG DNP AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Undel | SN-0651 | Scope Change | Approved | 2020-06-14 18:38 | 1 AAR SLR Alignment to support new PON site list new PON roll out and align SLR with AAR deliveries were misaligned post deferrals 2 Total 15 AAR s and 6 SLR s have been added to the Plan 3 Amount is Self Solved as the net addition to plan in Covid 19 and
MRTR VSR-New-RSM-VSR-ASR9906 | CA | ORG | RSM | Metro Routers | MRTR CA ORG RSM VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR VSR-New-RSM-VSR-ASR9906 | CA | ORG | RSM | Metro Routers | MRTR CA ORG RSM VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-01 | 2020-12-31 | 2021-06-30 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR VSR-New-RSM-VSR-ASR9906 | CA | ORG | RSM | Metro Routers | MRTR CA ORG RSM VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-CHU-NEW-AAR | CA | SAN | CHU | Metro Routers | MRTR CA SAN CHU AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-CHU-NEW-AAR | CA | SAN | CHU | Metro Routers | MRTR CA SAN CHU AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-15 | 2020-06-15 | Active | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-CHU-NEW-AAR | CA | SAN | CHU | Metro Routers | MRTR CA SAN CHU AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-05 | 2020-08-31 | 2020-11-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-CHU-NEW-AAR | CA | SAN | CHU | Metro Routers | MRTR CA SAN CHU AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-DWN-NEW-AAR | CA | SAN | DWN | Metro Routers | MRTR CA SAN DWN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-DWN-NEW-AAR | CA | SAN | DWN | Metro Routers | MRTR CA SAN DWN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-15 | 2020-06-15 | Active | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-DWN-NEW-AAR | CA | SAN | DWN | Metro Routers | MRTR CA SAN DWN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-05 | 2020-08-31 | 2020-11-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-DWN-NEW-AAR | CA | SAN | DWN | Metro Routers | MRTR CA SAN DWN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-ELC-NEW-AAR | CA | SAN | ELC | Metro Routers | MRTR CA SAN ELC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-ELC-NEW-AAR | CA | SAN | ELC | Metro Routers | MRTR CA SAN ELC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-15 | 2020-06-15 | Active | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-ELC-NEW-AAR | CA | SAN | ELC | Metro Routers | MRTR CA SAN ELC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-05 | 2020-08-31 | 2020-11-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-ELC-NEW-AAR | CA | SAN | ELC | Metro Routers | MRTR CA SAN ELC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-ESC-NEW-AAR | CA | SAN | ESC | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-ESC-NEW-AAR | CA | SAN | ESC | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-15 | 2020-06-15 | Active | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-ESC-NEW-AAR | CA | SAN | ESC | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-05 | 2020-08-31 | 2020-11-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-ESC-NEW-AAR | CA | SAN | ESC | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-FED-NEW-AAR | CA | SAN | FED | Metro Routers | MRTR CA SAN FED AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | EP
MRTR AAR-New-FED-NEW-AAR | CA | SAN | FED | Metro Routers | MRTR CA SAN FED AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Active | Log | Del | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-FED-NEW-AAR | CA | SAN | FED | Metro Routers | MRTR CA SAN FED AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Active | Log | Del | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-FED-NEW-AAR | CA | SAN | FED | Metro Routers | MRTR CA SAN FED AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Undel | SN-0651 | Scope Change | Approved | 2020-06-14 18:38 | 1 AAR SLR Alignment to support new PON site list new PON roll out and align SLR with AAR deliveries were misaligned post deferrals 2 Total 15 AAR s and 6 SLR s have been added to the Plan 3 Amount is Self Solved as the net addition to plan in Covid 19 and
MRTR AAR-New-OCE-NEW-AAR | CA | SAN | OCE | Metro Routers | MRTR CA SAN OCE AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-OCE-NEW-AAR | CA | SAN | OCE | Metro Routers | MRTR CA SAN OCE AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-15 | 2020-06-15 | Active | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-OCE-NEW-AAR | CA | SAN | OCE | Metro Routers | MRTR CA SAN OCE AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-05 | 2020-08-31 | 2020-11-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-OCE-NEW-AAR | CA | SAN | OCE | Metro Routers | MRTR CA SAN OCE AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR VSR-New-SAB-VSR-ASR9906 | CA | SAB | SAB | Metro Routers | MRTR CA SAB SAB VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR VSR-New-SAB-VSR-ASR9906 | CA | SAB | SAB | Metro Routers | MRTR CA SAB SAB VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-01 | 2020-12-31 | 2021-06-30 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR VSR-New-SAB-VSR-ASR9906 | CA | SAB | SAB | Metro Routers | MRTR CA SAB SAB VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR OOB-New-BER-OOB Server | CE | NWA | BER | Metro Routers | MRTR CE NWA BER OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | EP
MRTR OOB-New-BER-OOB Server | CE | NWA | BER | Metro Routers | MRTR CE NWA BER OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-DBY-SLR-ASR9906 | CE | KAN | DBY | Metro Routers | MRTR CE KAN DBY SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2021-03-31 | 2021-03-31 | Active | EP
MRTR SLR-New-DBY-SLR-ASR9906 | CE | KAN | DBY | Metro Routers | MRTR CE KAN DBY SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-01 | 2020-12-31 | 2021-03-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-DBY-SLR-ASR9906 | CE | KAN | DBY | Metro Routers | MRTR CE KAN DBY SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-DBY-SLR-ASR9906 | CE | KAN | DBY | Metro Routers | MRTR CE KAN DBY SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2021-03-31 | 2021-03-31 | Active | Log | Upd | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR SLR-New-FTS-SLR-ASR9906 | CE | NWA | FTS | Metro Routers | MRTR CE NWA FTS SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-15 | 2020-12-31 | 2020-12-31 | Active | EP
MRTR SLR-New-FTS-SLR-ASR9906 | CE | NWA | FTS | Metro Routers | MRTR CE NWA FTS SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-05 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-FTS-SLR-ASR9906 | CE | NWA | FTS | Metro Routers | MRTR CE NWA FTS SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0502 | Schedule Change | Approved | 2020-04-29 16:33 | 1 Updating CR 395 Financials 2 Pushing out the AAR in the Q2 Plan out to June 3 Will wait for final decision based on Equipment delivery and Deferrals to align back
MRTR SLR-New-FTS-SLR-ASR9906 | CE | NWA | FTS | Metro Routers | MRTR CE NWA FTS SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-15 | 2020-12-31 | 2020-12-31 | Active | Log | Upd | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR OOB-New-FTS-OOB Server | CE | NWA | FTS | Metro Routers | MRTR CE NWA FTS OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-09-01 | 2020-11-30 | 2021-02-28 | Active | EP
MRTR OOB-New-FTS-OOB Server | CE | NWA | FTS | Metro Routers | MRTR CE NWA FTS OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-09-01 | 2020-11-30 | 2021-02-28 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-MPN-SLR-ASR9906 | CE | KAN | MPN | Metro Routers | MRTR CE KAN MPN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR SLR-New-MPN-SLR-ASR9906 | CE | KAN | MPN | Metro Routers | MRTR CE KAN MPN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-MPN-SLR-ASR9906 | CE | KAN | MPN | Metro Routers | MRTR CE KAN MPN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR OOB-New-WIC-OOB Server | CE | KAN | WIC | Metro Routers | MRTR CE KAN WIC OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-09-05 | 2020-11-30 | 2021-02-28 | Active | EP
MRTR OOB-New-WIC-OOB Server | CE | KAN | WIC | Metro Routers | MRTR CE KAN WIC OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-09-05 | 2020-11-30 | 2021-02-28 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-WIC-SLR-ASR9906 | CE | KAN | WIC | Metro Routers | MRTR CE KAN WIC SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR SLR-New-WIC-SLR-ASR9906 | CE | KAN | WIC | Metro Routers | MRTR CE KAN WIC SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-05 | 2020-11-30 | 2021-02-28 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-WIC-SLR-ASR9906 | CE | KAN | WIC | Metro Routers | MRTR CE KAN WIC SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR VSR-New-WIC-VSR-ASR9906 | CE | KAN | WIC | Metro Routers | MRTR CE KAN WIC VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR VSR-New-WIC-VSR-ASR9906 | CE | KAN | WIC | Metro Routers | MRTR CE KAN WIC VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2021-03-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR VSR-New-WIC-VSR-ASR9906 | CE | KAN | WIC | Metro Routers | MRTR CE KAN WIC VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR OOB-New-BRD-OOB Server | CE | TUL | BRD | Metro Routers | MRTR CE TUL BRD OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR OOB-New-BRD-OOB Server | CE | TUL | BRD | Metro Routers | MRTR CE TUL BRD OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-BRD-SLR-ASR9906 | CE | TUL | BRD | Metro Routers | MRTR CE TUL BRD SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR SLR-New-BRD-SLR-ASR9906 | CE | TUL | BRD | Metro Routers | MRTR CE TUL BRD SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-BRD-SLR-ASR9906 | CE | TUL | BRD | Metro Routers | MRTR CE TUL BRD SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-BRD-SLR-ASR9906 | CE | TUL | BRD | Metro Routers | MRTR CE TUL BRD SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-01 | 2020-10-31 | 2020-12-31 | Deleted | Log | Undel | SN-0651 | Scope Change | Approved | 2020-06-14 18:38 | 1 AAR SLR Alignment to support new PON site list new PON roll out and align SLR with AAR deliveries were misaligned post deferrals 2 Total 15 AAR s and 6 SLR s have been added to the Plan 3 Amount is Self Solved as the net addition to plan in Covid 19 and
MRTR SLR-New-BRD-SLR-ASR9906 | CE | TUL | BRD | Metro Routers | MRTR CE TUL BRD SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0750 | Scope Change | Approved | 2020-07-15 17:23 | This CR removes 6 SLR s from the plan It also adds 11 AAR s to the plan self solve Removal of SLR s nets a 451K giveback to risk
MRTR OOB-New-BAR-OOB Server | CE | TUL | BAR | Metro Routers | MRTR CE TUL BAR OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | EP
MRTR OOB-New-BAR-OOB Server | CE | TUL | BAR | Metro Routers | MRTR CE TUL BAR OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-CHO-OOB Server | CE | OKC | CHO | Metro Routers | MRTR CE OKC CHO OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-08-05 | 2020-10-31 | 2021-04-30 | Active | EP
MRTR OOB-New-CHO-OOB Server | CE | OKC | CHO | Metro Routers | MRTR CE OKC CHO OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-08-05 | 2020-10-31 | 2021-04-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-CLA-OOB Server | CE | TUL | CLA | Metro Routers | MRTR CE TUL CLA OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-09-05 | 2020-11-30 | 2021-02-28 | Active | EP
MRTR OOB-New-CLA-OOB Server | CE | TUL | CLA | Metro Routers | MRTR CE TUL CLA OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-09-05 | 2020-11-30 | 2021-02-28 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-CLH-OOB Server | CE | OKC | CLH | Metro Routers | MRTR CE OKC CLH OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-08-05 | 2020-10-31 | 2021-04-30 | Active | EP
MRTR OOB-New-CLH-OOB Server | CE | OKC | CLH | Metro Routers | MRTR CE OKC CLH OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-08-05 | 2020-10-31 | 2021-04-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-CLH-SLR-ASR9906 | CE | OKC | CLH | Metro Routers | MRTR CE OKC CLH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR SLR-New-CLH-SLR-ASR9906 | CE | OKC | CLH | Metro Routers | MRTR CE OKC CLH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-CLH-SLR-ASR9906 | CE | OKC | CLH | Metro Routers | MRTR CE OKC CLH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-CLH-SLR-ASR9906 | CE | OKC | CLH | Metro Routers | MRTR CE OKC CLH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-01 | 2020-10-31 | 2020-12-31 | Deleted | Log | Undel | SN-0651 | Scope Change | Approved | 2020-06-14 18:38 | 1 AAR SLR Alignment to support new PON site list new PON roll out and align SLR with AAR deliveries were misaligned post deferrals 2 Total 15 AAR s and 6 SLR s have been added to the Plan 3 Amount is Self Solved as the net addition to plan in Covid 19 and
MRTR SLR-New-CLH-SLR-ASR9906 | CE | OKC | CLH | Metro Routers | MRTR CE OKC CLH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0750 | Scope Change | Approved | 2020-07-15 17:23 | This CR removes 6 SLR s from the plan It also adds 11 AAR s to the plan self solve Removal of SLR s nets a 451K giveback to risk
MRTR NCS-Growth-DTN-100G Grow | CE | TUL | DTN | Metro Routers | MRTR CE TUL DTN 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | EP
MRTR NCS-Growth-DTN-100G Grow | CE | TUL | DTN | Metro Routers | MRTR CE TUL DTN 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-06-01 | 2020-08-01 | 2020-11-01 | Active | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR NCS-Growth-DTN-100G Grow | CE | TUL | DTN | Metro Routers | MRTR CE TUL DTN 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-DTN-NCS Line Card | CE | TUL | DTN | Metro Routers | MRTR CE TUL DTN NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-01-01 03:01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR NCS-Growth-DTN-NCS Line Card | CE | TUL | DTN | Metro Routers | MRTR CE TUL DTN NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-01-01 03:01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-DTN-OOB Server | CE | TUL | DTN | Metro Routers | MRTR CE TUL DTN OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-10-01 03:01 | 2020-12-31 | 2021-03-31 | Active | EP
MRTR OOB-New-DTN-OOB Server | CE | TUL | DTN | Metro Routers | MRTR CE TUL DTN OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-10-01 03:01 | 2020-12-31 | 2021-03-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-ELR-OOB Server | CE | OKC | ELR | Metro Routers | MRTR CE OKC ELR OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 3 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR OOB-New-ELR-OOB Server | CE | OKC | ELR | Metro Routers | MRTR CE OKC ELR OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 3 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-GAR-OOB Server | CE | TUL | GAR | Metro Routers | MRTR CE TUL GAR OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-09-05 | 2020-11-30 | 2021-02-28 | Active | EP
MRTR OOB-New-GAR-OOB Server | CE | TUL | GAR | Metro Routers | MRTR CE TUL GAR OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-09-05 | 2020-11-30 | 2021-02-28 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-GAR-SLR-ASR9906 | CE | TUL | GAR | Metro Routers | MRTR CE TUL GAR SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2021-03-31 | 2021-03-31 | Active | EP
MRTR SLR-New-GAR-SLR-ASR9906 | CE | TUL | GAR | Metro Routers | MRTR CE TUL GAR SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-05 | 2020-11-30 | 2021-02-28 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-GAR-SLR-ASR9906 | CE | TUL | GAR | Metro Routers | MRTR CE TUL GAR SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-GAR-SLR-ASR9906 | CE | TUL | GAR | Metro Routers | MRTR CE TUL GAR SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2021-03-31 | 2021-03-31 | Active | Log | Upd | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR SLR-New-MWC-SLR-ASR9906 | CE | OKC | MWC | Metro Routers | MRTR CE OKC MWC SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR SLR-New-MWC-SLR-ASR9906 | CE | OKC | MWC | Metro Routers | MRTR CE OKC MWC SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-01 | 2020-12-31 | 2021-03-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-MWC-SLR-ASR9906 | CE | OKC | MWC | Metro Routers | MRTR CE OKC MWC SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR OOB-New-MWC-OOB Server | CE | OKC | MWC | Metro Routers | MRTR CE OKC MWC OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-09-05 | 2020-11-30 | 2021-02-28 | Active | EP
MRTR OOB-New-MWC-OOB Server | CE | OKC | MWC | Metro Routers | MRTR CE OKC MWC OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-09-05 | 2020-11-30 | 2021-02-28 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-MOO-OOB Server | CE | OKC | MOO | Metro Routers | MRTR CE OKC MOO OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-09-05 | 2020-11-30 | 2021-02-28 | Active | EP
MRTR OOB-New-MOO-OOB Server | CE | OKC | MOO | Metro Routers | MRTR CE OKC MOO OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-09-05 | 2020-11-30 | 2021-02-28 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-NOR-SLR-ASR9906 | CE | OKC | NOR | Metro Routers | MRTR CE OKC NOR SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR SLR-New-NOR-SLR-ASR9906 | CE | OKC | NOR | Metro Routers | MRTR CE OKC NOR SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-01 | 2020-12-31 | 2021-03-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-NOR-SLR-ASR9906 | CE | OKC | NOR | Metro Routers | MRTR CE OKC NOR SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-NEH-SLR-ASR9906 | CE | OKC | NEH | Metro Routers | MRTR CE OKC NEH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR SLR-New-NEH-SLR-ASR9906 | CE | OKC | NEH | Metro Routers | MRTR CE OKC NEH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-05 | 2020-11-30 | 2021-02-28 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-NEH-SLR-ASR9906 | CE | OKC | NEH | Metro Routers | MRTR CE OKC NEH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-NEH-SLR-ASR9906 | CE | OKC | NEH | Metro Routers | MRTR CE OKC NEH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-01 | 2020-10-31 | 2020-12-31 | Deleted | Log | Undel | SN-0651 | Scope Change | Approved | 2020-06-14 18:38 | 1 AAR SLR Alignment to support new PON site list new PON roll out and align SLR with AAR deliveries were misaligned post deferrals 2 Total 15 AAR s and 6 SLR s have been added to the Plan 3 Amount is Self Solved as the net addition to plan in Covid 19 and
MRTR SLR-New-NEH-SLR-ASR9906 | CE | OKC | NEH | Metro Routers | MRTR CE OKC NEH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0750 | Scope Change | Approved | 2020-07-15 17:23 | This CR removes 6 SLR s from the plan It also adds 11 AAR s to the plan self solve Removal of SLR s nets a 451K giveback to risk
MRTR VSR-New-OKC-VSR-ASR9906 | CE | OKC | OKC | Metro Routers | MRTR CE OKC OKC VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-01 | 2020-12-31 | 2021-03-31 | Active | EP
MRTR VSR-New-OKC-VSR-ASR9906 | CE | OKC | OKC | Metro Routers | MRTR CE OKC OKC VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 1 |  | 2020-01-15 |  | Active | Log | Upd | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
MRTR VSR-New-OKC-VSR-ASR9906 | CE | OKC | OKC | Metro Routers | MRTR CE OKC OKC VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2021-03-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR VSR-New-OKC-VSR-ASR9906 | CE | OKC | OKC | Metro Routers | MRTR CE OKC OKC VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-01 | 2020-12-31 | 2021-03-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR OOB-New-SAP-OOB Server | CE | TUL | SAP | Metro Routers | MRTR CE TUL SAP OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR OOB-New-SAP-OOB Server | CE | TUL | SAP | Metro Routers | MRTR CE TUL SAP OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-SAP-SLR-ASR9906 | CE | TUL | SAP | Metro Routers | MRTR CE TUL SAP SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR SLR-New-SAP-SLR-ASR9906 | CE | TUL | SAP | Metro Routers | MRTR CE TUL SAP SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-SAP-SLR-ASR9906 | CE | TUL | SAP | Metro Routers | MRTR CE TUL SAP SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-SAP-SLR-ASR9906 | CE | TUL | SAP | Metro Routers | MRTR CE TUL SAP SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-01 | 2020-10-31 | 2020-12-31 | Deleted | Log | Undel | SN-0651 | Scope Change | Approved | 2020-06-14 18:38 | 1 AAR SLR Alignment to support new PON site list new PON roll out and align SLR with AAR deliveries were misaligned post deferrals 2 Total 15 AAR s and 6 SLR s have been added to the Plan 3 Amount is Self Solved as the net addition to plan in Covid 19 and
MRTR SLR-New-SAP-SLR-ASR9906 | CE | TUL | SAP | Metro Routers | MRTR CE TUL SAP SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0750 | Scope Change | Approved | 2020-07-15 17:23 | This CR removes 6 SLR s from the plan It also adds 11 AAR s to the plan self solve Removal of SLR s nets a 451K giveback to risk
MRTR SLR-New-BUR-SLR-ASR9906 | NE | RHD | BUR | Metro Routers | MRTR NE RHD BUR SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2021-01-31 | Active | EP
MRTR SLR-New-BUR-SLR-ASR9906 | NE | RHD | BUR | Metro Routers | MRTR NE RHD BUR SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2021-01-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-BUR-SLR-ASR9906 | NE | RHD | BUR | Metro Routers | MRTR NE RHD BUR SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-BUR-SLR-ASR9906 | NE | RHD | BUR | Metro Routers | MRTR NE RHD BUR SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2021-01-31 | Active | Log | Upd | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
MRTR SLR-New-EXT-SLR-ASR9906 | NE | RHD | EXT | Metro Routers | MRTR NE RHD EXT SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-01 | 2020-07-31 | 2020-10-31 | Active | EP
MRTR SLR-New-EXT-SLR-ASR9906 | NE | RHD | EXT | Metro Routers | MRTR NE RHD EXT SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-EXT-SLR-ASR9906 | NE | RHD | EXT | Metro Routers | MRTR NE RHD EXT SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-01 | 2020-07-31 | 2020-10-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-PAW-SLR-ASR9906 | NE | RHD | PAW | Metro Routers | MRTR NE RHD PAW SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2021-01-31 | Active | EP
MRTR SLR-New-PAW-SLR-ASR9906 | NE | RHD | PAW | Metro Routers | MRTR NE RHD PAW SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2021-01-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-PAW-SLR-ASR9906 | NE | RHD | PAW | Metro Routers | MRTR NE RHD PAW SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-PAW-SLR-ASR9906 | NE | RHD | PAW | Metro Routers | MRTR NE RHD PAW SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2021-01-31 | Active | Log | Upd | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
MRTR SLR-New-WWK-SLR-ASR9906 | NE | RHD | WWK | Metro Routers | MRTR NE RHD WWK SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2021-03-31 | Active | EP
MRTR SLR-New-WWK-SLR-ASR9906 | NE | RHD | WWK | Metro Routers | MRTR NE RHD WWK SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-WWK-SLR-ASR9906 | NE | RHD | WWK | Metro Routers | MRTR NE RHD WWK SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-WWK-SLR-ASR9906 | NE | RHD | WWK | Metro Routers | MRTR NE RHD WWK SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2021-03-31 | Active | Log | Upd | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
MRTR VSR-New-WWK-VSR-ASR9906 | NE | RHD | WWK | Metro Routers | MRTR NE RHD WWK VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR VSR-New-WWK-VSR-ASR9906 | NE | RHD | WWK | Metro Routers | MRTR NE RHD WWK VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2021-04-30 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR VSR-New-WWK-VSR-ASR9906 | NE | RHD | WWK | Metro Routers | MRTR NE RHD WWK VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-ABV-SLR-ASR9906 | SE | LFY | ABV | Metro Routers | MRTR SE LFY ABV SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-08-31 | 2020-12-31 | Active | EP
MRTR SLR-New-ABV-SLR-ASR9906 | SE | LFY | ABV | Metro Routers | MRTR SE LFY ABV SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-ABV-SLR-ASR9906 | SE | LFY | ABV | Metro Routers | MRTR SE LFY ABV SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-12-31 | 2020-12-31 | Active | Log | Upd | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR SLR-New-ABV-SLR-ASR9906 | SE | LFY | ABV | Metro Routers | MRTR SE LFY ABV SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-08-31 | 2020-12-31 | Active | Log | Upd | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
MRTR NCS-Growth-CLR-100G Grow | SE | NOR | CLR | Metro Routers | MRTR SE NOR CLR 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-06-30 | 2020-06-30 | Active | EP
MRTR NCS-Growth-CLR-100G Grow | SE | NOR | CLR | Metro Routers | MRTR SE NOR CLR 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-CLR-SLR-ASR9906 | SE | NOR | CLR | Metro Routers | MRTR SE NOR CLR SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR SLR-New-CLR-SLR-ASR9906 | SE | NOR | CLR | Metro Routers | MRTR SE NOR CLR SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-CLR-SLR-ASR9906 | SE | NOR | CLR | Metro Routers | MRTR SE NOR CLR SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-CLR-SLR-ASR9906 | SE | NOR | CLR | Metro Routers | MRTR SE NOR CLR SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2021-03-31 | 2021-03-31 | Active | Log | Upd | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR SLR-New-CLR-SLR-ASR9906 | SE | NOR | CLR | Metro Routers | MRTR SE NOR CLR SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
MRTR SLR-New-ELM-SLR-ASR9906 | SE | NOR | ELM | Metro Routers | MRTR SE NOR ELM SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR SLR-New-ELM-SLR-ASR9906 | SE | NOR | ELM | Metro Routers | MRTR SE NOR ELM SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-ELM-SLR-ASR9906 | SE | NOR | ELM | Metro Routers | MRTR SE NOR ELM SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2021-03-31 | 2021-03-31 | Active | Log | Upd | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR SLR-New-ELM-SLR-ASR9906 | SE | NOR | ELM | Metro Routers | MRTR SE NOR ELM SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
MRTR SLR-New-KNN-SLR-ASR9906 | SE | NOR | KNN | Metro Routers | MRTR SE NOR KNN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR SLR-New-KNN-SLR-ASR9906 | SE | NOR | KNN | Metro Routers | MRTR SE NOR KNN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-KNN-SLR-ASR9906 | SE | NOR | KNN | Metro Routers | MRTR SE NOR KNN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-KNN-SLR-ASR9906 | SE | NOR | KNN | Metro Routers | MRTR SE NOR KNN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2021-03-31 | 2021-03-31 | Active | Log | Upd | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR SLR-New-KNN-SLR-ASR9906 | SE | NOR | KNN | Metro Routers | MRTR SE NOR KNN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
MRTR SLR-New-LFY-SLR-ASR9906 | SE | LFY | LFY | Metro Routers | MRTR SE LFY LFY SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-08-31 | 2020-12-31 | Active | EP
MRTR SLR-New-LFY-SLR-ASR9906 | SE | LFY | LFY | Metro Routers | MRTR SE LFY LFY SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-LFY-SLR-ASR9906 | SE | LFY | LFY | Metro Routers | MRTR SE LFY LFY SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-08-31 | 2020-12-31 | Active | Log | Upd | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
MRTR VSR-New-LFY-VSR-ASR9906 | SE | LFY | LFY | Metro Routers | MRTR SE LFY LFY VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR VSR-New-LFY-VSR-ASR9906 | SE | LFY | LFY | Metro Routers | MRTR SE LFY LFY VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-LPL-SLR-ASR9906 | SE | NOR | LPL | Metro Routers | MRTR SE NOR LPL SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR SLR-New-LPL-SLR-ASR9906 | SE | NOR | LPL | Metro Routers | MRTR SE NOR LPL SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-LPL-SLR-ASR9906 | SE | NOR | LPL | Metro Routers | MRTR SE NOR LPL SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-LPL-SLR-ASR9906 | SE | NOR | LPL | Metro Routers | MRTR SE NOR LPL SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2021-03-31 | 2021-03-31 | Active | Log | Upd | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR SLR-New-LPL-SLR-ASR9906 | SE | NOR | LPL | Metro Routers | MRTR SE NOR LPL SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
MRTR SLR-New-LUL-SLR-ASR9906 | SE | NOR | LUL | Metro Routers | MRTR SE NOR LUL SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR SLR-New-LUL-SLR-ASR9906 | SE | NOR | LUL | Metro Routers | MRTR SE NOR LUL SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-01 | 2020-10-31 | 2021-01-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-LUL-SLR-ASR9906 | SE | NOR | LUL | Metro Routers | MRTR SE NOR LUL SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-LUL-SLR-ASR9906 | SE | NOR | LUL | Metro Routers | MRTR SE NOR LUL SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2021-03-31 | 2021-03-31 | Active | Log | Upd | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR SLR-New-LUL-SLR-ASR9906 | SE | NOR | LUL | Metro Routers | MRTR SE NOR LUL SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
MRTR NCS-Growth-FWL-NCS Line Card | SW | ARZ | FWL | Metro Routers | MRTR SW ARZ FWL NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR NCS-Growth-FWL-NCS Line Card | SW | ARZ | FWL | Metro Routers | MRTR SW ARZ FWL NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-09-01 | 2020-11-15 | 2020-07-15 | Active | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR NCS-Growth-FWL-NCS Line Card | SW | ARZ | FWL | Metro Routers | MRTR SW ARZ FWL NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-09-01 | 2020-11-30 | 2021-02-28 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-FWL-NCS Line Card | SW | ARZ | FWL | Metro Routers | MRTR SW ARZ FWL NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-FWL-NEW-AAR | SW | ARZ | FWL | Metro Routers | MRTR SW ARZ FWL AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-FWL-NEW-AAR | SW | ARZ | FWL | Metro Routers | MRTR SW ARZ FWL AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-01 | 2020-07-15 | 2020-07-15 | Active | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-FWL-NEW-AAR | SW | ARZ | FWL | Metro Routers | MRTR SW ARZ FWL AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2021-03-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-FWL-NEW-AAR | SW | ARZ | FWL | Metro Routers | MRTR SW ARZ FWL AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR OOB-New-SHE-OOB Server | CE | OKC | SEH | Metro Routers | MRTR CE OKC SEH OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR OOB-New-SHE-OOB Server | CE | OKC | SEH | Metro Routers | MRTR CE OKC SEH OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 |  | 2020-01-15 |  | Active | Log | Upd | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
MRTR OOB-New-SHE-OOB Server | CE | OKC | SEH | Metro Routers | MRTR CE OKC SEH OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-SHE-SLR-ASR9906 | CE | OKC | SEH | Metro Routers | MRTR CE OKC SEH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR SLR-New-SHE-SLR-ASR9906 | CE | OKC | SEH | Metro Routers | MRTR CE OKC SEH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 1 |  | 2020-01-01 |  | Deleted | Log | Upd | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
MRTR SLR-New-SHE-SLR-ASR9906 | CE | OKC | SEH | Metro Routers | MRTR CE OKC SEH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-01 | 2020-09-30 | Deleted | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR SLR-New-SHE-SLR-ASR9906 | CE | OKC | SEH | Metro Routers | MRTR CE OKC SEH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-SHE-SLR-ASR9906 | CE | OKC | SEH | Metro Routers | MRTR CE OKC SEH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-WLH-SLR-ASR9906 | CE | OKC | WLH | Metro Routers | MRTR CE OKC WLH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR SLR-New-WLH-SLR-ASR9906 | CE | OKC | WLH | Metro Routers | MRTR CE OKC WLH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-WLH-SLR-ASR9906 | CE | OKC | WLH | Metro Routers | MRTR CE OKC WLH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-WEH-SLR-ASR9906 | CE | OKC | WEH | Metro Routers | MRTR CE OKC WEH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR SLR-New-WEH-SLR-ASR9906 | CE | OKC | WEH | Metro Routers | MRTR CE OKC WEH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-05 | 2020-11-30 | 2021-02-28 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-WEH-SLR-ASR9906 | CE | OKC | WEH | Metro Routers | MRTR CE OKC WEH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR OOB-New-WEH-OOB Server | CE | OKC | WEH | Metro Routers | MRTR CE OKC WEH OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR OOB-New-WEH-OOB Server | CE | OKC | WEH | Metro Routers | MRTR CE OKC WEH OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-BLV-OOB Server | CE | OMA | BLV | Metro Routers | MRTR CE OMA BLV OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis |  |  |  |  | Deleted | EP
MRTR OOB-New-BLV-OOB Server | CE | OMA | BLV | Metro Routers | MRTR CE OMA BLV OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-09-05 | 2020-11-30 | 2021-02-28 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-BLV-OOB Server | CE | OMA | BLV | Metro Routers | MRTR CE OMA BLV OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis |  |  |  |  | Deleted | Log | Del | SN-1037 | Schedule Change | Approved | 2020-11-06 09:51 | Alignment of POR based on feedback from the field
MRTR SLR-New-BLV-SLR-ASR9906 | CE | OMA | BLV | Metro Routers | MRTR CE OMA BLV SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR SLR-New-BLV-SLR-ASR9906 | CE | OMA | BLV | Metro Routers | MRTR CE OMA BLV SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-BLV-SLR-ASR9906 | CE | OMA | BLV | Metro Routers | MRTR CE OMA BLV SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR OOB-New-ONA-OOB Server | CE | OMA | ONA | Metro Routers | MRTR CE OMA ONA OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-09-01 | 2020-11-30 | 2021-02-28 | Active | EP
MRTR OOB-New-ONA-OOB Server | CE | OMA | ONA | Metro Routers | MRTR CE OMA ONA OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-09-01 | 2020-11-30 | 2021-02-28 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-New-JMX-NCS-5504-250 Sup Card | SW | ARZ | JMX | Metro Routers | MRTR SW ARZ JMX NCS Deployment POR20 | Card & Optics | NCS-5504-250 Sup Card | 2 | 2020-04-01 03:01 | 2020-06-30 | 2020-09-30 | Active | EP
MRTR NCS-New-JMX-NCS-5504-250 Sup Card | SW | ARZ | JMX | Metro Routers | MRTR SW ARZ JMX NCS Deployment POR20 | Card & Optics | NCS-5504-250 Sup Card | 2 | 2020-09-01 | 2020-11-15 | 2020-07-15 | Active | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR NCS-New-JMX-NCS-5504-250 Sup Card | SW | ARZ | JMX | Metro Routers | MRTR SW ARZ JMX NCS Deployment POR20 | Card & Optics | NCS-5504-250 Sup Card | 2 | 2020-04-01 03:01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-MCD-NCS Line Card | SW | ARZ | MCD | Metro Routers | MRTR SW ARZ MCD NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR NCS-Growth-MCD-NCS Line Card | SW | ARZ | MCD | Metro Routers | MRTR SW ARZ MCD NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-09-01 | 2020-11-15 | 2020-07-15 | Active | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR NCS-Growth-MCD-NCS Line Card | SW | ARZ | MCD | Metro Routers | MRTR SW ARZ MCD NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-09-01 | 2020-11-30 | 2021-02-28 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-MCD-NCS Line Card | SW | ARZ | MCD | Metro Routers | MRTR SW ARZ MCD NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-ONA-SLR-ASR9906 | CE | OMA | ONA | Metro Routers | MRTR CE OMA ONA SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR SLR-New-ONA-SLR-ASR9906 | CE | OMA | ONA | Metro Routers | MRTR CE OMA ONA SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-ONA-SLR-ASR9906 | CE | OMA | ONA | Metro Routers | MRTR CE OMA ONA SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR OOB-New-OMM-OOB Server | CE | OMA | OMM | Metro Routers | MRTR CE OMA OMM OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR OOB-New-OMM-OOB Server | CE | OMA | OMM | Metro Routers | MRTR CE OMA OMM OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-OMM-SLR-ASR9906 | CE | OMA | OMM | Metro Routers | MRTR CE OMA OMM SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR SLR-New-OMM-SLR-ASR9906 | CE | OMA | OMM | Metro Routers | MRTR CE OMA OMM SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-OMM-SLR-ASR9906 | CE | OMA | OMM | Metro Routers | MRTR CE OMA OMM SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR VSR-New-OMM-VSR-ASR9906 | CE | OMA | OMM | Metro Routers | MRTR CE OMA OMM VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR VSR-New-OMM-VSR-ASR9906 | CE | OMA | OMM | Metro Routers | MRTR CE OMA OMM VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2021-03-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR VSR-New-OMM-VSR-ASR9906 | CE | OMA | OMM | Metro Routers | MRTR CE OMA OMM VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR OOB-New-SOU-OOB Server | CE | OMA | SOU | Metro Routers | MRTR CE OMA SOU OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR OOB-New-SOU-OOB Server | CE | OMA | SOU | Metro Routers | MRTR CE OMA SOU OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-SOU-SLR-ASR9906 | CE | OMA | SOU | Metro Routers | MRTR CE OMA SOU SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR SLR-New-SOU-SLR-ASR9906 | CE | OMA | SOU | Metro Routers | MRTR CE OMA SOU SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-SOU-SLR-ASR9906 | CE | OMA | SOU | Metro Routers | MRTR CE OMA SOU SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-SOU-SLR-ASR9906 | CE | OMA | SOU | Metro Routers | MRTR CE OMA SOU SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-01 | 2020-10-31 | 2020-12-31 | Deleted | Log | Undel | SN-0651 | Scope Change | Approved | 2020-06-14 18:38 | 1 AAR SLR Alignment to support new PON site list new PON roll out and align SLR with AAR deliveries were misaligned post deferrals 2 Total 15 AAR s and 6 SLR s have been added to the Plan 3 Amount is Self Solved as the net addition to plan in Covid 19 and
MRTR SLR-New-SOU-SLR-ASR9906 | CE | OMA | SOU | Metro Routers | MRTR CE OMA SOU SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0750 | Scope Change | Approved | 2020-07-15 17:23 | This CR removes 6 SLR s from the plan It also adds 11 AAR s to the plan self solve Removal of SLR s nets a 451K giveback to risk
MRTR OOB-New-SVI-OOB Server | CE | SUN | SVI | Metro Routers | MRTR CE SUN SVI OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | EP
MRTR OOB-New-SVI-OOB Server | CE | SUN | SVI | Metro Routers | MRTR CE SUN SVI OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-WES-OOB Server | CE | OMA | WES | Metro Routers | MRTR CE OMA WES OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR OOB-New-WES-OOB Server | CE | OMA | WES | Metro Routers | MRTR CE OMA WES OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-WES-SLR-ASR9906 | CE | OMA | WES | Metro Routers | MRTR CE OMA WES SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR SLR-New-WES-SLR-ASR9906 | CE | OMA | WES | Metro Routers | MRTR CE OMA WES SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-05 | 2020-11-30 | 2021-02-28 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-WES-SLR-ASR9906 | CE | OMA | WES | Metro Routers | MRTR CE OMA WES SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-CLV-SLR-ASR9906 | NE | CLE | CLV | Metro Routers | MRTR NE CLE CLV SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR SLR-New-CLV-SLR-ASR9906 | NE | CLE | CLV | Metro Routers | MRTR NE CLE CLV SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-CLV-SLR-ASR9906 | NE | CLE | CLV | Metro Routers | MRTR NE CLE CLV SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR VSR-New-MAN-VSR-ASR9906 | NE | CON | MAN | Metro Routers | MRTR NE CON MAN VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR VSR-New-MAN-VSR-ASR9906 | NE | CON | MAN | Metro Routers | MRTR NE CON MAN VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2021-04-30 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR VSR-New-MAN-VSR-ASR9906 | NE | CON | MAN | Metro Routers | MRTR NE CON MAN VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-MCY-SLR-ASR9906 | SE | NOR | MCY | Metro Routers | MRTR SE NOR MCY SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR SLR-New-MCY-SLR-ASR9906 | SE | NOR | MCY | Metro Routers | MRTR SE NOR MCY SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-MCY-SLR-ASR9906 | SE | NOR | MCY | Metro Routers | MRTR SE NOR MCY SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-12-31 | 2020-12-31 | Active | Log | Upd | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR SLR-New-MCY-SLR-ASR9906 | SE | NOR | MCY | Metro Routers | MRTR SE NOR MCY SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
MRTR SLR-New-SPC-SLR-ASR9906 | SE | BTR | SPC | Metro Routers | MRTR SE BTR SPC SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-12-31 | Active | EP
MRTR SLR-New-SPC-SLR-ASR9906 | SE | BTR | SPC | Metro Routers | MRTR SE BTR SPC SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-SPC-SLR-ASR9906 | SE | BTR | SPC | Metro Routers | MRTR SE BTR SPC SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-12-31 | 2020-12-31 | Active | Log | Upd | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR SLR-New-SPC-SLR-ASR9906 | SE | BTR | SPC | Metro Routers | MRTR SE BTR SPC SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-12-31 | Active | Log | Upd | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
MRTR NCS-Growth-PNS-100G Grow | SE | GCT | PNS | Metro Routers | MRTR SE GCT PNS 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-04-01 | 2020-05-01 |  | Active | EP
MRTR SLR-New-PNS-SLR-ASR9906 | SE | GCT | PNS | Metro Routers | MRTR SE GCT PNS SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR SLR-New-PNS-SLR-ASR9906 | SE | GCT | PNS | Metro Routers | MRTR SE GCT PNS SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-PNS-SLR-ASR9906 | SE | GCT | PNS | Metro Routers | MRTR SE GCT PNS SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2021-03-31 | 2021-03-31 | Active | Log | Upd | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR SLR-New-PNS-SLR-ASR9906 | SE | GCT | PNS | Metro Routers | MRTR SE GCT PNS SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
MRTR SLR-New-WRB-SLR-ASR9906 | SE | MGA | WRB | Metro Routers | MRTR SE MGA WRB SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-12-31 | Active | EP
MRTR SLR-New-WRB-SLR-ASR9906 | SE | MGA | WRB | Metro Routers | MRTR SE MGA WRB SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-WRB-SLR-ASR9906 | SE | MGA | WRB | Metro Routers | MRTR SE MGA WRB SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-12-31 | Active | Log | Upd | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
MRTR AAR-New-BUK-NEW-AAR | SW | ARZ | BUK | Metro Routers | MRTR SW ARZ BUK AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-BUK-NEW-AAR | SW | ARZ | BUK | Metro Routers | MRTR SW ARZ BUK AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-01 | 2020-07-15 | 2020-07-15 | Active | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-BUK-NEW-AAR | SW | ARZ | BUK | Metro Routers | MRTR SW ARZ BUK AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-05 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-BUK-NEW-AAR | SW | ARZ | BUK | Metro Routers | MRTR SW ARZ BUK AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-CHD-NEW-AAR | SW | ARZ | CHD | Metro Routers | MRTR SW ARZ CHD AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-CHD-NEW-AAR | SW | ARZ | CHD | Metro Routers | MRTR SW ARZ CHD AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-01 | 2020-07-15 | 2020-07-15 | Active | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-CHD-NEW-AAR | SW | ARZ | CHD | Metro Routers | MRTR SW ARZ CHD AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-05 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-CHD-NEW-AAR | SW | ARZ | CHD | Metro Routers | MRTR SW ARZ CHD AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR VSR-New-CHD-VSR-ASR9906 | SW | ARZ | CHD | Metro Routers | MRTR SW ARZ CHD VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR VSR-New-CHD-VSR-ASR9906 | SW | ARZ | CHD | Metro Routers | MRTR SW ARZ CHD VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-15 | 2020-07-15 | Deleted | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR VSR-New-CHD-VSR-ASR9906 | SW | ARZ | CHD | Metro Routers | MRTR SW ARZ CHD VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2021-03-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR VSR-New-CHD-VSR-ASR9906 | SW | ARZ | CHD | Metro Routers | MRTR SW ARZ CHD VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR NCS-Growth-MSA-NCS Line Card | SW | ARZ | MSA | Metro Routers | MRTR SW ARZ MSA NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-09-01 | 2020-11-30 | 2021-02-28 | Active | EP
MRTR NCS-Growth-MSA-NCS Line Card | SW | ARZ | MSA | Metro Routers | MRTR SW ARZ MSA NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-09-01 | 2020-11-15 | 2020-11-15 | Active | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR NCS-Growth-MSA-NCS Line Card | SW | ARZ | MSA | Metro Routers | MRTR SW ARZ MSA NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-09-01 | 2020-11-30 | 2021-02-28 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-MSA-NEW-AAR | SW | ARZ | MSA | Metro Routers | MRTR SW ARZ MSA AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-MSA-NEW-AAR | SW | ARZ | MSA | Metro Routers | MRTR SW ARZ MSA AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-01 | 2020-07-15 | 2020-07-15 | Active | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-MSA-NEW-AAR | SW | ARZ | MSA | Metro Routers | MRTR SW ARZ MSA AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-05 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-MSA-NEW-AAR | SW | ARZ | MSA | Metro Routers | MRTR SW ARZ MSA AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-ORG-SLR-ASR9906 | CA | ORG | ORG | Metro Routers | MRTR CA ORG ORG SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR SLR-New-ORG-SLR-ASR9906 | CA | ORG | ORG | Metro Routers | MRTR CA ORG ORG SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 03:01 | 2020-03-31 | 2020-06-30 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-ORG-SLR-ASR9906 | CA | ORG | ORG | Metro Routers | MRTR CA ORG ORG SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
NEXUS-RSM-93108-01 | CA | ORG | RSM | Metro Routers | MRTR CA ORG RSM Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-01-01 03:01 | 2020-03-31 | 2020-06-30 | Active | EP
NEXUS-RSM-93108-01 | CA | ORG | RSM | Metro Routers | MRTR CA ORG RSM Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-01-01 03:01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-KCY-OOB Server | COR | NAT | KCY | Metro Routers | MRTR CE KAN KCY OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 3 | 2020-02-01 | 2020-04-30 | 2020-07-31 | Active | EP
MRTR OOB-New-KCY-OOB Server | COR | NAT | KCY | Metro Routers | MRTR CE KAN KCY OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 3 | 2020-02-01 | 2020-04-30 | 2020-07-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-SSP-OOB Server | CE | NWA | SSP | Metro Routers | MRTR CE NWA SSP OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-02-01 | 2020-04-30 | 2020-07-31 | Active | EP
MRTR OOB-New-SSP-OOB Server | CE | NWA | SSP | Metro Routers | MRTR CE NWA SSP OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-02-01 | 2020-04-30 | 2020-07-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-BAR-SLR-ASR9906 | CE | TUL | BAR | Metro Routers | MRTR CE TUL BAR SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-05 | 2021-02-28 | 2021-02-28 | Active | EP
MRTR SLR-New-BAR-SLR-ASR9906 | CE | TUL | BAR | Metro Routers | MRTR CE TUL BAR SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-05 | 2020-08-31 | 2020-11-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-BAR-SLR-ASR9906 | CE | TUL | BAR | Metro Routers | MRTR CE TUL BAR SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-05 | 2021-02-28 | 2021-02-28 | Active | Log | Upd | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR SLR-New-MER-SLR-ASR9906 | NE | CON | MER | Metro Routers | MRTR NE CON MER SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2021-01-31 | Active | EP
MRTR SLR-New-MER-SLR-ASR9906 | NE | CON | MER | Metro Routers | MRTR NE CON MER SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2021-01-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-MER-SLR-ASR9906 | NE | CON | MER | Metro Routers | MRTR NE CON MER SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-MER-SLR-ASR9906 | NE | CON | MER | Metro Routers | MRTR NE CON MER SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2021-01-31 | Active | Log | Upd | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
NEXUS-RKH-3048-01 | NE | CON | RKH | Metro Routers | MRTR NE CON RKH Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 | 2020-01-01 | 2020-03-30 | 2020-03-30 | Active | EP
NEXUS-RKH-3048-01 | NE | CON | RKH | Metro Routers | MRTR NE CON RKH Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 | 2020-01-01 | 2020-03-30 | 2020-03-30 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
NEXUS-RKH-93108-01 | NE | CON | RKH | Metro Routers | MRTR NE CON RKH Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-01-01 | 2020-03-30 | 2020-03-30 | Active | EP
NEXUS-RKH-93108-01 | NE | CON | RKH | Metro Routers | MRTR NE CON RKH Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-01-01 | 2020-03-30 | 2020-03-30 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-STN-SLR-ASR9906 | NE | CON | STN | Metro Routers | MRTR NE CON STN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2021-03-31 | Active | EP
MRTR SLR-New-STN-SLR-ASR9906 | NE | CON | STN | Metro Routers | MRTR NE CON STN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-STN-SLR-ASR9906 | NE | CON | STN | Metro Routers | MRTR NE CON STN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-STN-SLR-ASR9906 | NE | CON | STN | Metro Routers | MRTR NE CON STN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2021-03-31 | Active | Log | Upd | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
NEXUS-BUR-3048-01 | NE | RHD | BUR | Metro Routers | MRTR NE RHD BUR Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 | 2020-04-20 | 2020-06-01 |  | Active | EP
NEXUS-BUR-93108-01 | NE | RHD | BUR | Metro Routers | MRTR NE RHD BUR Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 2 | 2020-04-20 | 2020-06-01 |  | Active | EP
NEXUS-BUR-93180-01 | NE | RHD | BUR | Metro Routers | MRTR NE RHD BUR Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-04-20 | 2020-06-01 |  | Active | EP
NEXUS-RMD-3048-01 | NE | RHD | RMD | Metro Routers | MRTR NE RHD RMD Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 |  | 2020-01-15 | 2020-01-15 | Active | EP
NEXUS-RMD-3048-01 | NE | RHD | RMD | Metro Routers | MRTR NE RHD RMD Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 |  | 2020-01-15 | 2020-01-15 | Active | Log | Upd | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
NEXUS-RMD-93108-01 | NE | RHD | RMD | Metro Routers | MRTR NE RHD RMD Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-01-05 | 2020-03-31 | 2020-03-31 | Active | EP
NEXUS-RMD-93108-01 | NE | RHD | RMD | Metro Routers | MRTR NE RHD RMD Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 1 |  | 2020-01-15 | 2020-01-15 | Active | Log | Upd | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
NEXUS-RMD-93108-01 | NE | RHD | RMD | Metro Routers | MRTR NE RHD RMD Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-01-05 | 2020-03-31 | 2020-03-31 | Active | Log | Upd | SN-0239 | Schedule Change | Approved | 2020-02-07 14:34 | 1 Updating Plan to reflect the Financials per the BOM 2 This subset had Raid Risk raised as the Plan was not aligned to the final version of the BOM 3 INP and PDG were re conciling on if any changes needs to be made on top of the existing BOM;s placed
MRTR SLR-New-PWY-SLR-ASR9906 | CA | SAN | PWY | Metro Routers | MRTR CA SAN PWY SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | EP
MRTR SLR-New-PWY-SLR-ASR9906 | CA | SAN | PWY | Metro Routers | MRTR CA SAN PWY SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-30 | 2020-12-31 | 2021-03-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-PWY-SLR-ASR9906 | CA | SAN | PWY | Metro Routers | MRTR CA SAN PWY SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Active | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-PWY-SLR-ASR9906 | CA | SAN | PWY | Metro Routers | MRTR CA SAN PWY SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Undel | SN-0866 | Scope Change | Approved | 2020-08-21 15:19 | Adding Federal and Poway SLR s to the POR and removing Indy SLR to align with deferrals and the financial plan
MRTR NCS-Growth-SAB-NCS Line Card | CA | SAB | SAB | Metro Routers | MRTR CA SAB SAB NCS Deployment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-05 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR NCS-Growth-SAB-NCS Line Card | CA | SAB | SAB | Metro Routers | MRTR CA SAB SAB NCS Deployment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-05 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-SAB-SLR-ASR9906 | CA | SAB | SAB | Metro Routers | MRTR CA SAB SAB SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-05 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR SLR-New-SAB-SLR-ASR9906 | CA | SAB | SAB | Metro Routers | MRTR CA SAB SAB SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-05 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-BVL-SLR-ASR9906 | CE | NWA | BVL | Metro Routers | MRTR CE NWA BVL SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2021-03-31 | 2021-03-31 | Active | EP
MRTR SLR-New-BVL-SLR-ASR9906 | CE | NWA | BVL | Metro Routers | MRTR CE NWA BVL SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-BVL-SLR-ASR9906 | CE | NWA | BVL | Metro Routers | MRTR CE NWA BVL SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2021-03-31 | 2021-03-31 | Active | Log | Upd | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR OOB-New-HRN-OOB Server | CE | NWA | HRN | Metro Routers | MRTR CE NWA HRN OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-02-01 | 2020-04-30 | 2020-07-31 | Active | EP
MRTR OOB-New-HRN-OOB Server | CE | NWA | HRN | Metro Routers | MRTR CE NWA HRN OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-02-01 | 2020-04-30 | 2020-07-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-NWA-100G Grow | CE | NWA | NWA | Metro Routers | MRTR CE NWA NWA 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-02-01 | 2020-04-30 | 2020-07-31 | Active | EP
MRTR NCS-Growth-NWA-100G Grow | CE | NWA | NWA | Metro Routers | MRTR CE NWA NWA 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-02-01 | 2020-04-30 | 2020-07-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-NWA-OOB Server | CE | NWA | NWA | Metro Routers | MRTR CE NWA NWA OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-02-01 | 2020-04-30 | 2020-07-31 | Active | EP
MRTR OOB-New-NWA-OOB Server | CE | NWA | NWA | Metro Routers | MRTR CE NWA NWA OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-02-01 | 2020-04-30 | 2020-07-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-ENF-SLR-ASR9906 | NE | CON | ENF | Metro Routers | MRTR NE CON ENF SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | EP
MRTR SLR-New-ENF-SLR-ASR9906 | NE | CON | ENF | Metro Routers | MRTR NE CON ENF SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
NEXUS-GLB-3048-01 | NE | CON | GLB | Metro Routers | MRTR NE CON GLB Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis |  |  |  |  | Deleted | EP
NEXUS-GLB-3048-01 | NE | CON | GLB | Metro Routers | MRTR NE CON GLB Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis |  |  |  |  | Deleted | Log | Del | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
NEXUS-GLB-93108-01 | NE | CON | GLB | Metro Routers | MRTR NE CON GLB Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis |  |  |  |  | Deleted | EP
NEXUS-GLB-93108-01 | NE | CON | GLB | Metro Routers | MRTR NE CON GLB Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
NEXUS-GLB-93180-01 | NE | CON | GLB | Metro Routers | MRTR NE CON GLB Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis |  |  |  |  | Deleted | EP
NEXUS-GLB-93180-01 | NE | CON | GLB | Metro Routers | MRTR NE CON GLB Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis |  |  |  |  | Deleted | Log | Del | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
NEXUS-GRB-3048-01 | NE | CON | GRB | Metro Routers | MRTR NE CON GRB Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 | 2020-05-18 | 2020-07-01 |  | Active | EP
NEXUS-GRB-93108-01 | NE | CON | GRB | Metro Routers | MRTR NE CON GRB Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 2 | 2020-05-18 | 2020-07-01 |  | Active | EP
NEXUS-GRB-93180-01 | NE | CON | GRB | Metro Routers | MRTR NE CON GRB Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-05-18 | 2020-07-01 |  | Active | EP
NEXUS-MAN-3048-01 | NE | CON | MAN | Metro Routers | MRTR NE CON MAN Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
NEXUS-MAN-3048-01 | NE | CON | MAN | Metro Routers | MRTR NE CON MAN Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
NEXUS-MAN-93108-01 | NE | CON | MAN | Metro Routers | MRTR NE CON MAN Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 4 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
NEXUS-MAN-93108-01 | NE | CON | MAN | Metro Routers | MRTR NE CON MAN Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 4 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
NEXUS-MAN-93180-01 | NE | CON | MAN | Metro Routers | MRTR NE CON MAN Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 4 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
NEXUS-MAN-93180-01 | NE | CON | MAN | Metro Routers | MRTR NE CON MAN Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 4 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-MAN-SLR-ASR9906 | NE | CON | MAN | Metro Routers | MRTR NE CON MAN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | EP
MRTR SLR-New-MAN-SLR-ASR9906 | NE | CON | MAN | Metro Routers | MRTR NE CON MAN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
NEXUS-MER-3048-01 | NE | CON | MER | Metro Routers | MRTR NE CON MER Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 | 2020-01-05 | 2020-03-31 | 2020-03-31 | Active | EP
NEXUS-MER-3048-01 | NE | CON | MER | Metro Routers | MRTR NE CON MER Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 | 2020-08-05 | 2020-10-31 | 2021-04-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
NEXUS-MER-3048-01 | NE | CON | MER | Metro Routers | MRTR NE CON MER Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 | 2020-01-05 | 2020-03-31 | 2020-03-31 | Active | Log | Upd | SN-0239 | Schedule Change | Approved | 2020-02-07 14:34 | 1 Updating Plan to reflect the Financials per the BOM 2 This subset had Raid Risk raised as the Plan was not aligned to the final version of the BOM 3 INP and PDG were re conciling on if any changes needs to be made on top of the existing BOM;s placed
NEXUS-MER-93108-01 | NE | CON | MER | Metro Routers | MRTR NE CON MER Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-01-05 | 2020-03-31 | 2020-03-31 | Active | EP
NEXUS-MER-93108-01 | NE | CON | MER | Metro Routers | MRTR NE CON MER Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 1 | 2020-08-05 | 2020-10-31 | 2021-04-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
NEXUS-MER-93108-01 | NE | CON | MER | Metro Routers | MRTR NE CON MER Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-01-05 | 2020-03-31 | 2020-03-31 | Active | Log | Upd | SN-0239 | Schedule Change | Approved | 2020-02-07 14:34 | 1 Updating Plan to reflect the Financials per the BOM 2 This subset had Raid Risk raised as the Plan was not aligned to the final version of the BOM 3 INP and PDG were re conciling on if any changes needs to be made on top of the existing BOM;s placed
NEXUS-SCT-3048-01 | NE | RHD | SCT | Metro Routers | MRTR NE RHD SCT Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 | 2020-04-01 | 2020-06-30 | 2020-06-30 | Active | EP
NEXUS-SCT-3048-01 | NE | RHD | SCT | Metro Routers | MRTR NE RHD SCT Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 |  | 2020-01-01 |  | Active | Log | Upd | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
NEXUS-SCT-3048-01 | NE | RHD | SCT | Metro Routers | MRTR NE RHD SCT Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 | 2020-04-01 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0239 | Schedule Change | Approved | 2020-02-07 14:34 | 1 Updating Plan to reflect the Financials per the BOM 2 This subset had Raid Risk raised as the Plan was not aligned to the final version of the BOM 3 INP and PDG were re conciling on if any changes needs to be made on top of the existing BOM;s placed
NEXUS-SCT-93108-01 | NE | RHD | SCT | Metro Routers | MRTR NE RHD SCT Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 1 | 2020-04-01 | 2020-06-30 | 2020-06-30 | Active | EP
NEXUS-SCT-93108-01 | NE | RHD | SCT | Metro Routers | MRTR NE RHD SCT Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 1 |  | 2020-01-01 |  | Active | Log | Upd | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
NEXUS-SCT-93108-01 | NE | RHD | SCT | Metro Routers | MRTR NE RHD SCT Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 1 | 2020-04-01 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0239 | Schedule Change | Approved | 2020-02-07 14:34 | 1 Updating Plan to reflect the Financials per the BOM 2 This subset had Raid Risk raised as the Plan was not aligned to the final version of the BOM 3 INP and PDG were re conciling on if any changes needs to be made on top of the existing BOM;s placed
NEXUS-SCT-93180-01 | NE | RHD | SCT | Metro Routers | MRTR NE RHD SCT Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-04-20 | 2020-06-01 |  | Active | EP
NEXUS-WWK-3048-01 | NE | RHD | WWK | Metro Routers | MRTR NE RHD WWK Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 | 2020-04-20 | 2020-06-01 |  | Active | EP
NEXUS-WWK-93108-01 | NE | RHD | WWK | Metro Routers | MRTR NE RHD WWK Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 4 | 2020-04-20 | 2020-06-01 |  | Active | EP
NEXUS-WWK-93180-01 | NE | RHD | WWK | Metro Routers | MRTR NE RHD WWK Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 4 | 2020-04-20 | 2020-06-01 |  | Active | EP
NEXUS-GNS-93180-01 | SE | GAN | GNS | Metro Routers | MRTR SE GAN GNS Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 5 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | EP
NEXUS-PNS-93180-01 | SE | GCT | PNS | Metro Routers | MRTR SE GCT PNS Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | EP
MRTR NCS-Growth-CHD-NCS Line Card | SW | ARZ | CHD | Metro Routers | MRTR SW ARZ CHD NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2019-10-01 | 2019-12-31 | 2020-03-31 | Active | EP
MRTR NCS-Growth-CHD-NCS Line Card | SW | ARZ | CHD | Metro Routers | MRTR SW ARZ CHD NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-09-01 | 2020-11-15 | 2020-07-15 | Active | Log | Upd | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR NCS-Growth-CHD-NCS Line Card | SW | ARZ | CHD | Metro Routers | MRTR SW ARZ CHD NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2019-10-01 | 2019-12-31 | 2020-03-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-OSB-SLR-ASR9906 | SW | LAS | OSB | Metro Routers | MRTR SW LAS OSB SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-02-05 | 2020-04-30 | 2020-07-31 | Active | EP
MRTR SLR-New-OSB-SLR-ASR9906 | SW | LAS | OSB | Metro Routers | MRTR SW LAS OSB SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-02-05 | 2020-04-30 | 2020-07-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-CHS-SLR-ASR9906 | VA | HRD | CHS | Metro Routers | MRTR VA HRD CHS SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-12-31 | Active | EP
MRTR SLR-New-CHS-SLR-ASR9906 | VA | HRD | CHS | Metro Routers | MRTR VA HRD CHS SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 03:01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-CHS-SLR-ASR9906 | VA | HRD | CHS | Metro Routers | MRTR VA HRD CHS SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0502 | Schedule Change | Approved | 2020-04-29 16:33 | 1 Updating CR 395 Financials 2 Pushing out the AAR in the Q2 Plan out to June 3 Will wait for final decision based on Equipment delivery and Deferrals to align back
MRTR SLR-New-CHS-SLR-ASR9906 | VA | HRD | CHS | Metro Routers | MRTR VA HRD CHS SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-12-31 | Active | Log | Upd | SN-1037 | Schedule Change | Approved | 2020-11-06 09:51 | Alignment of POR based on feedback from the field
MRTR SLR-New-OCN-SLR-ASR9906 | VA | HRD | OCN | Metro Routers | MRTR VA HRD OCN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-12-31 | Active | EP
MRTR SLR-New-OCN-SLR-ASR9906 | VA | HRD | OCN | Metro Routers | MRTR VA HRD OCN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 03:01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-OCN-SLR-ASR9906 | VA | HRD | OCN | Metro Routers | MRTR VA HRD OCN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0502 | Schedule Change | Approved | 2020-04-29 16:33 | 1 Updating CR 395 Financials 2 Pushing out the AAR in the Q2 Plan out to June 3 Will wait for final decision based on Equipment delivery and Deferrals to align back
MRTR SLR-New-OCN-SLR-ASR9906 | VA | HRD | OCN | Metro Routers | MRTR VA HRD OCN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-12-31 | Active | Log | Upd | SN-1037 | Schedule Change | Approved | 2020-11-06 09:51 | Alignment of POR based on feedback from the field
MRTR SLR-New-ALP-SLR-ASR9906 | CA | SAN | ALP | Metro Routers | MRTR CA SAN ALP SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR SLR-New-ALP-SLR-ASR9906 | CA | SAN | ALP | Metro Routers | MRTR CA SAN ALP SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-BLU-100G Grow | SW | LAS | BLU | Metro Routers | MRTR SW LAS BLU NCS Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-04-01 | 2020-05-15 | 2020-06-15 | Active | EP
MRTR NCS-Growth-BLU-100G Grow | SW | LAS | BLU | Metro Routers | MRTR SW LAS BLU NCS Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-04-01 | 2020-05-15 | 2020-06-15 | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR SLR-New-NWT-SLR-ASR9906 | CE | KAN | NWT | Metro Routers | MRTR CE KAN NWT SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR SLR-New-NWT-SLR-ASR9906 | CE | KAN | NWT | Metro Routers | MRTR CE KAN MPN SLR Deployment POR20_0 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-15 | 2020-09-15 | Deleted | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR SLR-New-NWT-SLR-ASR9906 | CE | KAN | NWT | Metro Routers | MRTR CE KAN NWT SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-NWT-SLR-ASR9906 | CE | KAN | NWT | Metro Routers | MRTR CE KAN NWT SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-PIT-SLR-ASR9906 | CE | KAN | PIT | Metro Routers | MRTR CE KAN PIT SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR SLR-New-PIT-SLR-ASR9906 | CE | KAN | PIT | Metro Routers | MRTR CE KAN MPN SLR Deployment POR20_0 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-15 | 2020-09-15 | Deleted | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR SLR-New-PIT-SLR-ASR9906 | CE | KAN | PIT | Metro Routers | MRTR CE KAN PIT SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-PIT-SLR-ASR9906 | CE | KAN | PIT | Metro Routers | MRTR CE KAN PIT SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-TOP-SLR-ASR9906 | CE | KAN | TOP | Metro Routers | MRTR CE KAN TOP SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR SLR-New-TOP-SLR-ASR9906 | CE | KAN | TOP | Metro Routers | MRTR CE KAN MPN SLR Deployment POR20_0 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-15 | 2020-09-15 | Deleted | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR SLR-New-TOP-SLR-ASR9906 | CE | KAN | TOP | Metro Routers | MRTR CE KAN TOP SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-TOP-SLR-ASR9906 | CE | KAN | TOP | Metro Routers | MRTR CE KAN TOP SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-BER-SLR-ASR9906 | CE | NWA | BER | Metro Routers | MRTR CE NWA BER SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR SLR-New-BER-SLR-ASR9906 | CE | NWA | BER | Metro Routers | MRTR CE KAN MPN SLR Deployment POR20_0 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-15 | 2020-09-15 | Deleted | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR SLR-New-BER-SLR-ASR9906 | CE | NWA | BER | Metro Routers | MRTR CE NWA BER SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2021-03-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-BER-SLR-ASR9906 | CE | NWA | BER | Metro Routers | MRTR CE NWA BER SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-ILH-SLR-ASR9906 | CE | OKC | ILH | Metro Routers | MRTR CE OKC ILH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR SLR-New-ILH-SLR-ASR9906 | CE | OKC | ILH | Metro Routers | MRTR CE KAN MPN SLR Deployment POR20_0 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-15 | 2020-09-15 | Deleted | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR SLR-New-ILH-SLR-ASR9906 | CE | OKC | ILH | Metro Routers | MRTR CE OKC ILH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-01 | 2020-12-31 | 2021-03-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-ILH-SLR-ASR9906 | CE | OKC | ILH | Metro Routers | MRTR CE OKC ILH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-MOO-SLR-ASR9906 | CE | OKC | MOO | Metro Routers | MRTR CE OKC MOO SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR SLR-New-MOO-SLR-ASR9906 | CE | OKC | MOO | Metro Routers | MRTR CE KAN MPN SLR Deployment POR20_0 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-15 | 2020-09-15 | Deleted | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR SLR-New-MOO-SLR-ASR9906 | CE | OKC | MOO | Metro Routers | MRTR CE OKC MOO SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-01 | 2020-12-31 | 2021-03-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-MOO-SLR-ASR9906 | CE | OKC | MOO | Metro Routers | MRTR CE OKC MOO SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-PTH-SLR-ASR9906 | NE | RHD | PTH | Metro Routers | MRTR NE RHD PTH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-01 | 2020-07-31 | 2020-09-30 | Active | EP
MRTR SLR-New-PTH-SLR-ASR9906 | NE | RHD | PTH | Metro Routers | MRTR NE RHD PAW SLR Deployment POR20_0 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-15 | 2020-09-15 | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR SLR-New-PTH-SLR-ASR9906 | NE | RHD | PTH | Metro Routers | MRTR NE RHD PTH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-PTH-SLR-ASR9906 | NE | RHD | PTH | Metro Routers | MRTR NE RHD PTH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-03-01 | 2020-03-15 | 2020-03-31 | Active | Log | Upd | SN-0233 | Schedule Change | Approved | 2020-01-31 15:01 | 1 We have all the Clock, Test racks, OCML everything except the SLR to complete the node action in March 2 Portsmouth SLR is planned in April and need to pull into March 3 Total pull IN 67K
MRTR SLR-New-PTH-SLR-ASR9906 | NE | RHD | PTH | Metro Routers | MRTR NE RHD PTH SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-01 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-HRN-SLR-ASR9906 | CE | NWA | HRN | Metro Routers | MRTR CE NWA HRN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-05 | 2020-12-31 | 2020-12-31 | Active | EP
MRTR SLR-New-HRN-SLR-ASR9906 | CE | NWA | HRN | Metro Routers | MRTR CE KAN MPN SLR Deployment POR20_0 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-01 | 2020-06-30 | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR SLR-New-HRN-SLR-ASR9906 | CE | NWA | HRN | Metro Routers | MRTR CE NWA HRN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-05 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-HRN-SLR-ASR9906 | CE | NWA | HRN | Metro Routers | MRTR CE NWA HRN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-05 | 2020-12-31 | 2020-12-31 | Active | Log | Upd | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR SLR-New-DTN-SLR-ASR9906 | CE | TUL | DTN | Metro Routers | MRTR CE TUL DTN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | EP
MRTR SLR-New-DTN-SLR-ASR9906 | CA | SAN | DWN | Metro Routers | MRTR CE KAN MPN SLR Deployment POR20_0 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-01 | 2020-06-30 | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR SLR-New-DTN-SLR-ASR9906 | CA | SAN | DWN | Metro Routers | MRTR CE KAN MPN SLR Deployment POR20_0 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Active | Log | Del | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-DTN-SLR-ASR9906 | CE | TUL | DTN | Metro Routers | MRTR CE TUL DTN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Undel | SN-1037 | Schedule Change | Approved | 2020-11-06 09:51 | Alignment of POR based on feedback from the field
MRTR NCS-Growth-RSM-100G Grow | CA | ORG | RSM | Metro Routers | MRTR CA ORG RSM NCS Augment POR20 | Card & Optics | 100G Grow |  |  |  |  | Deleted | EP
MRTR NCS-Growth-RSM-100G Grow | CA | ORG | RSM | Metro Routers | MRTR CA ORG RSM NCS Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Deleted | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR NCS-Growth-RSM-100G Grow | CA | ORG | RSM | Metro Routers | MRTR CA ORG RSM NCS Augment POR20 | Card & Optics | 100G Grow |  |  |  |  | Deleted | Log | Del | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-FED-SLR-ASR9906 | CA | SAN | FED | Metro Routers | MRTR CA SAN FED AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR SLR-New-FED-SLR-ASR9906 | CA | SAN | FED | Metro Routers | MRTR CA SAN FED AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-01 | 2020-07-15 | 2020-09-15 | Deleted | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR SLR-New-FED-SLR-ASR9906 | CA | SAN | FED | Metro Routers | MRTR CA SAN FED AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-30 | 2020-12-31 | 2021-03-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-FED-SLR-ASR9906 | CA | SAN | FED | Metro Routers | MRTR CA SAN FED AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-12-31 | Deleted | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-FED-SLR-ASR9906 | CA | SAN | FED | Metro Routers | MRTR CA SAN FED AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0651 | Scope Change | Approved | 2020-06-14 18:38 | 1 AAR SLR Alignment to support new PON site list new PON roll out and align SLR with AAR deliveries were misaligned post deferrals 2 Total 15 AAR s and 6 SLR s have been added to the Plan 3 Amount is Self Solved as the net addition to plan in Covid 19 and
MRTR SLR-New-FED-SLR-ASR9906 | CA | SAN | FED | Metro Routers | MRTR CA SAN FED AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Deleted | Log | Undel | SN-0866 | Scope Change | Approved | 2020-08-21 15:19 | Adding Federal and Poway SLR s to the POR and removing Indy SLR to align with deferrals and the financial plan
MRTR SLR-New-FED-SLR-ASR9906 | CA | SAN | FED | Metro Routers | MRTR CA SAN FED AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-1037 | Schedule Change | Approved | 2020-11-06 09:51 | Alignment of POR based on feedback from the field
MRTR AAR-New-DBY-NEW-AAR | CE | KAN | DBY | Metro Routers | MRTR CE KAN DBY AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-DBY-NEW-AAR | CE | KAN | DBY | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-DBY-NEW-AAR | CE | KAN | DBY | Metro Routers | MRTR CE KAN DBY AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-DBY-NEW-AAR | CE | KAN | DBY | Metro Routers | MRTR CE KAN DBY AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0502 | Schedule Change | Approved | 2020-04-29 16:33 | 1 Updating CR 395 Financials 2 Pushing out the AAR in the Q2 Plan out to June 3 Will wait for final decision based on Equipment delivery and Deferrals to align back
MRTR AAR-New-DBY-NEW-AAR | CE | KAN | DBY | Metro Routers | MRTR CE KAN DBY AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-MPN-NEW-AAR | CE | KAN | MPN | Metro Routers | MRTR CE KAN MPN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR AAR-New-MPN-NEW-AAR | CE | KAN | MPN | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 |  | Deleted | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-MPN-NEW-AAR | CE | KAN | MPN | Metro Routers | MRTR CE KAN MPN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-MPN-NEW-AAR | CE | KAN | MPN | Metro Routers | MRTR CE KAN MPN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-WIC-NEW-AAR | CE | KAN | WIC | Metro Routers | MRTR CE KAN WIC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR AAR-New-WIC-NEW-AAR | CE | KAN | WIC | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-05 | 2020-11-30 |  | Deleted | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-WIC-NEW-AAR | CE | KAN | WIC | Metro Routers | MRTR CE KAN WIC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-05 | 2020-11-30 | 2021-02-28 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-WIC-NEW-AAR | CE | KAN | WIC | Metro Routers | MRTR CE KAN WIC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-BVL-NEW-AAR | CE | NWA | BVL | Metro Routers | MRTR CE NWA BVL AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-BVL-NEW-AAR | CE | NWA | BVL | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 03:01 | 2020-06-30 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-BVL-NEW-AAR | CE | NWA | BVL | Metro Routers | MRTR CE NWA BVL AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-05 | 2020-08-31 | 2020-11-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-BVL-NEW-AAR | CE | NWA | BVL | Metro Routers | MRTR CE NWA BVL AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-FAY-NEW-AAR | CE | NWA | FAY | Metro Routers | MRTR CE NWA FAY AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-FAY-NEW-AAR | CE | NWA | FAY | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-05 | 2020-06-30 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-FAY-NEW-AAR | CE | NWA | FAY | Metro Routers | MRTR CE NWA FAY AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-05 | 2020-08-31 | 2020-11-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-FAY-NEW-AAR | CE | NWA | FAY | Metro Routers | MRTR CE NWA FAY AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-CLH-NEW-AAR | CE | OKC | CLH | Metro Routers | MRTR CE OKC CLH AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR AAR-New-CLH-NEW-AAR | CE | OKC | CLH | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 |  | Deleted | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-CLH-NEW-AAR | CE | OKC | CLH | Metro Routers | MRTR CE OKC CLH AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-CLH-NEW-AAR | CE | OKC | CLH | Metro Routers | MRTR CE OKC CLH AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-ILH-NEW-AAR | CE | OKC | ILH | Metro Routers | MRTR CE OKC ILH AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR AAR-New-ILH-NEW-AAR | CE | OKC | ILH | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 |  | Deleted | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-ILH-NEW-AAR | CE | OKC | ILH | Metro Routers | MRTR CE OKC ILH AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-01 | 2020-12-31 | 2021-03-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-ILH-NEW-AAR | CE | OKC | ILH | Metro Routers | MRTR CE OKC ILH AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-MWC-NEW-AAR | CE | OKC | MWC | Metro Routers | MRTR CE OKC MWC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR AAR-New-MWC-NEW-AAR | CE | OKC | MWC | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 |  | Deleted | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-MWC-NEW-AAR | CE | OKC | MWC | Metro Routers | MRTR CE OKC MWC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-01 | 2020-12-31 | 2021-03-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-MWC-NEW-AAR | CE | OKC | MWC | Metro Routers | MRTR CE OKC MWC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-MOO-NEW-AAR | CE | OKC | MOO | Metro Routers | MRTR CE OKC MOO AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR AAR-New-MOO-NEW-AAR | CE | OKC | MOO | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 |  | Deleted | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-MOO-NEW-AAR | CE | OKC | MOO | Metro Routers | MRTR CE OKC MOO AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-01 | 2020-12-31 | 2021-03-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-MOO-NEW-AAR | CE | OKC | MOO | Metro Routers | MRTR CE OKC MOO AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-NOR-NEW-AAR | CE | OKC | NOR | Metro Routers | MRTR CE OKC NOR AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR AAR-New-NOR-NEW-AAR | CE | OKC | NOR | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 |  | Deleted | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-NOR-NEW-AAR | CE | OKC | NOR | Metro Routers | MRTR CE OKC NOR AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-01 | 2020-12-31 | 2021-03-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-NOR-NEW-AAR | CE | OKC | NOR | Metro Routers | MRTR CE OKC NOR AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-NEH-NEW-AAR | CE | OKC | NEH | Metro Routers | MRTR CE OKC NEH AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR AAR-New-NEH-NEW-AAR | CE | OKC | NEH | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-05 | 2020-11-30 |  | Deleted | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-NEH-NEW-AAR | CE | OKC | NEH | Metro Routers | MRTR CE OKC NEH AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-05 | 2020-11-30 | 2021-02-28 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-NEH-NEW-AAR | CE | OKC | NEH | Metro Routers | MRTR CE OKC NEH AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-OKC-NEW-AAR | CE | OKC | OKC | Metro Routers | MRTR CE OKC OKC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | EP
MRTR AAR-New-OKC-NEW-AAR | CE | OKC | OKC | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-05 | 2020-06-30 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-OKC-NEW-AAR | CE | OKC | OKC | Metro Routers | MRTR CE OKC OKC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-OKC-NEW-AAR | CE | OKC | OKC | Metro Routers | MRTR CE OKC OKC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Active | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-OKC-NEW-AAR | CE | OKC | OKC | Metro Routers | MRTR CE OKC OKC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Undel | SN-0651 | Scope Change | Approved | 2020-06-14 18:38 | 1 AAR SLR Alignment to support new PON site list new PON roll out and align SLR with AAR deliveries were misaligned post deferrals 2 Total 15 AAR s and 6 SLR s have been added to the Plan 3 Amount is Self Solved as the net addition to plan in Covid 19 and
MRTR AAR-New-SRH-NEW-AAR | CE | OKC | SRH | Metro Routers | MRTR CE OKC SRH AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR AAR-New-SRH-NEW-AAR | CE | OKC | SRH | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 |  | Deleted | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-SRH-NEW-AAR | CE | OKC | SRH | Metro Routers | MRTR CE OKC SRH AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-SRH-NEW-AAR | CE | OKC | SRH | Metro Routers | MRTR CE OKC SRH AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-SEH-NEW-AAR | CE | OKC | SEH | Metro Routers | MRTR CE OKC SEH AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR AAR-New-SEH-NEW-AAR | CE | OKC | SEH | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 |  | Deleted | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-SEH-NEW-AAR | CE | OKC | SEH | Metro Routers | MRTR CE OKC SEH AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-SEH-NEW-AAR | CE | OKC | SEH | Metro Routers | MRTR CE OKC SEH AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-WLK-NEW-AAR | CE | OKC | WLK | Metro Routers | MRTR CE OKC WLK AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | EP
MRTR AAR-New-WLK-NEW-AAR | CE | OKC | WLK | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-05 | 2020-06-30 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-WLK-NEW-AAR | CE | OKC | WLK | Metro Routers | MRTR CE OKC WLK AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-WLK-NEW-AAR | CE | OKC | WLK | Metro Routers | MRTR CE OKC WLK AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Active | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-WLK-NEW-AAR | CE | OKC | WLK | Metro Routers | MRTR CE OKC WLK AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Undel | SN-0651 | Scope Change | Approved | 2020-06-14 18:38 | 1 AAR SLR Alignment to support new PON site list new PON roll out and align SLR with AAR deliveries were misaligned post deferrals 2 Total 15 AAR s and 6 SLR s have been added to the Plan 3 Amount is Self Solved as the net addition to plan in Covid 19 and
MRTR AAR-New-WLH-NEW-AAR | CE | OKC | WLH | Metro Routers | MRTR CE OKC WLH AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR AAR-New-WLH-NEW-AAR | CE | OKC | WLH | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 |  | Deleted | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-WLH-NEW-AAR | CE | OKC | WLH | Metro Routers | MRTR CE OKC WLH AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-WLH-NEW-AAR | CE | OKC | WLH | Metro Routers | MRTR CE OKC WLH AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-WEH-NEW-AAR | CE | OKC | WEH | Metro Routers | MRTR CE OKC WEH AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR AAR-New-WEH-NEW-AAR | CE | OKC | WEH | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 |  | Deleted | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-WEH-NEW-AAR | CE | OKC | WEH | Metro Routers | MRTR CE OKC WEH AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-05 | 2020-11-30 | 2021-02-28 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-WEH-NEW-AAR | CE | OKC | WEH | Metro Routers | MRTR CE OKC WEH AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-BLV-NEW-AAR | CE | OMA | BLV | Metro Routers | MRTR CE OMA BLV AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-BLV-NEW-AAR | CE | OMA | BLV | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-BLV-NEW-AAR | CE | OMA | BLV | Metro Routers | MRTR CE OMA BLV AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-BLV-NEW-AAR | CE | OMA | BLV | Metro Routers | MRTR CE OMA BLV AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Active | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-BLV-NEW-AAR | CE | OMA | BLV | Metro Routers | MRTR CE OMA BLV AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Undel | SN-0939 | Scope Change | Approved | 2020-09-18 09:34 | Robert Kuse s group funded 4 AAR s for the PON trials that need to be added to the POR North South and West OM and BLV No financial impact
MRTR AAR-New-ELK-NEW-AAR | CE | OMA | ELK | Metro Routers | MRTR CE OMA ELK AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-ELK-NEW-AAR | CE | OMA | ELK | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-05 | 2020-06-30 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-ELK-NEW-AAR | CE | OMA | ELK | Metro Routers | MRTR CE OMA ELK AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-05 | 2020-08-31 | 2020-11-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-ELK-NEW-AAR | CE | OMA | ELK | Metro Routers | MRTR CE OMA ELK AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-ONA-NEW-AAR | CE | OMA | ONA | Metro Routers | MRTR CE OMA ONA AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-ONA-NEW-AAR | CE | OMA | ONA | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-ONA-NEW-AAR | CE | OMA | ONA | Metro Routers | MRTR CE OMA ONA AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-ONA-NEW-AAR | CE | OMA | ONA | Metro Routers | MRTR CE OMA ONA AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Active | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-ONA-NEW-AAR | CE | OMA | ONA | Metro Routers | MRTR CE OMA ONA AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Undel | SN-0939 | Scope Change | Approved | 2020-09-18 09:34 | Robert Kuse s group funded 4 AAR s for the PON trials that need to be added to the POR North South and West OM and BLV No financial impact
MRTR AAR-New-SOU-NEW-AAR | CE | OMA | SOU | Metro Routers | MRTR CE OMA SOU AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-SOU-NEW-AAR | CE | OMA | SOU | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-SOU-NEW-AAR | CE | OMA | SOU | Metro Routers | MRTR CE OMA SOU AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-SOU-NEW-AAR | CE | OMA | SOU | Metro Routers | MRTR CE OMA SOU AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Active | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-SOU-NEW-AAR | CE | OMA | SOU | Metro Routers | MRTR CE OMA SOU AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Undel | SN-0939 | Scope Change | Approved | 2020-09-18 09:34 | Robert Kuse s group funded 4 AAR s for the PON trials that need to be added to the POR North South and West OM and BLV No financial impact
MRTR AAR-New-WES-NEW-AAR | CE | OMA | WES | Metro Routers | MRTR CE OMA WES AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-WES-NEW-AAR | CE | OMA | WES | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-05 | 2020-11-30 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-WES-NEW-AAR | CE | OMA | WES | Metro Routers | MRTR CE OMA WES AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-WES-NEW-AAR | CE | OMA | WES | Metro Routers | MRTR CE OMA WES AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Active | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-WES-NEW-AAR | CE | OMA | WES | Metro Routers | MRTR CE OMA WES AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Undel | SN-0939 | Scope Change | Approved | 2020-09-18 09:34 | Robert Kuse s group funded 4 AAR s for the PON trials that need to be added to the POR North South and West OM and BLV No financial impact
MRTR AAR-New-BRD-NEW-AAR | CE | TUL | BRD | Metro Routers | MRTR CE TUL BRD AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-15 | 2020-11-30 | 2020-12-31 | Active | EP
MRTR AAR-New-BRD-NEW-AAR | CE | TUL | BRD | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-BRD-NEW-AAR | CE | TUL | BRD | Metro Routers | MRTR CE TUL BRD AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-BRD-NEW-AAR | CE | TUL | BRD | Metro Routers | MRTR CE TUL BRD AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Active | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-BRD-NEW-AAR | CE | TUL | BRD | Metro Routers | MRTR CE TUL BRD AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-15 | 2020-11-30 | 2020-12-31 | Active | Log | Undel | SN-0750 | Scope Change | Approved | 2020-07-15 17:23 | This CR removes 6 SLR s from the plan It also adds 11 AAR s to the plan self solve Removal of SLR s nets a 451K giveback to risk
MRTR AAR-New-BAR-NEW-AAR | CE | TUL | BAR | Metro Routers | MRTR CE TUL BAR AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-BAR-NEW-AAR | CE | TUL | BAR | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 03:01 | 2020-06-30 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-BAR-NEW-AAR | CE | TUL | BAR | Metro Routers | MRTR CE TUL BAR AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-05 | 2020-08-31 | 2020-11-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-BAR-NEW-AAR | CE | TUL | BAR | Metro Routers | MRTR CE TUL BAR AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-OWA-NEW-AAR | CE | TUL | OWA | Metro Routers | MRTR CE TUL OWA AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-15 | 2020-11-30 | 2020-12-31 | Active | EP
MRTR AAR-New-OWA-NEW-AAR | CE | TUL | OWA | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-05 | 2020-06-30 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-OWA-NEW-AAR | CE | TUL | OWA | Metro Routers | MRTR CE TUL OWA AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-OWA-NEW-AAR | CE | TUL | OWA | Metro Routers | MRTR CE TUL OWA AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Active | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-OWA-NEW-AAR | CE | TUL | OWA | Metro Routers | MRTR CE TUL OWA AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-15 | 2020-11-30 | 2020-12-31 | Active | Log | Undel | SN-0750 | Scope Change | Approved | 2020-07-15 17:23 | This CR removes 6 SLR s from the plan It also adds 11 AAR s to the plan self solve Removal of SLR s nets a 451K giveback to risk
MRTR AAR-New-QNC-NEW-AAR | CE | TUL | QNC | Metro Routers | MRTR CE TUL QNC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | EP
MRTR AAR-New-QNC-NEW-AAR | CE | TUL | QNC | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-05 | 2020-06-30 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-QNC-NEW-AAR | CE | TUL | QNC | Metro Routers | MRTR CE TUL QNC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-QNC-NEW-AAR | CE | TUL | QNC | Metro Routers | MRTR CE TUL QNC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Active | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-QNC-NEW-AAR | CE | TUL | QNC | Metro Routers | MRTR CE TUL QNC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Undel | SN-0651 | Scope Change | Approved | 2020-06-14 18:38 | 1 AAR SLR Alignment to support new PON site list new PON roll out and align SLR with AAR deliveries were misaligned post deferrals 2 Total 15 AAR s and 6 SLR s have been added to the Plan 3 Amount is Self Solved as the net addition to plan in Covid 19 and
MRTR AAR-New-TUL-NEW-AAR | CE | TUL | TUL | Metro Routers | MRTR CE TUL TUL AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-TUL-NEW-AAR | CE | TUL | TUL | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-05 | 2020-06-30 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-TUL-NEW-AAR | CE | TUL | TUL | Metro Routers | MRTR CE TUL TUL AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-TUL-NEW-AAR | CE | TUL | TUL | Metro Routers | MRTR CE TUL TUL AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-CLV-NEW-AAR | NE | CLE | CLV | Metro Routers | MRTR NE CLE CLV AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Active | EP
MRTR AAR-New-CLV-NEW-AAR | NE | CLE | CLV | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-01 03:01 | 2020-12-31 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-CLV-NEW-AAR | NE | CLE | CLV | Metro Routers | MRTR NE CLE CLV AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-ENF-NEW-AAR | NE | CON | ENF | Metro Routers | MRTR NE CON ENF AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | EP
MRTR AAR-New-ENF-NEW-AAR | NE | CON | ENF | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-ENF-NEW-AAR | NE | CON | ENF | Metro Routers | MRTR NE CON ENF AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-MAN-NEW-AAR | NE | CON | MAN | Metro Routers | MRTR NE CON MAN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | EP
MRTR AAR-New-MAN-NEW-AAR | NE | CON | MAN | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-MAN-NEW-AAR | NE | CON | MAN | Metro Routers | MRTR NE CON MAN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-STN-NEW-AAR | NE | CON | STN | Metro Routers | MRTR NE CON STN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Active | EP
MRTR AAR-New-STN-NEW-AAR | NE | CON | STN | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-STN-NEW-AAR | NE | CON | STN | Metro Routers | MRTR NE CON STN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-EXT-NEW-AAR | NE | RHD | EXT | Metro Routers | MRTR NE RHD EXT AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | EP
MRTR AAR-New-EXT-NEW-AAR | NE | RHD | EXT | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-EXT-NEW-AAR | NE | RHD | EXT | Metro Routers | MRTR NE RHD EXT AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-PTH-NEW-AAR | NE | RHD | PTH | Metro Routers | MRTR NE RHD PTH AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | EP
MRTR AAR-New-PTH-NEW-AAR | NE | RHD | PTH | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-PTH-NEW-AAR | NE | RHD | PTH | Metro Routers | MRTR NE RHD PTH AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-WWK-NEW-AAR | NE | RHD | WWK | Metro Routers | MRTR NE RHD WWK AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Active | EP
MRTR AAR-New-WWK-NEW-AAR | NE | RHD | WWK | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-WWK-NEW-AAR | NE | RHD | WWK | Metro Routers | MRTR NE RHD WWK AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-BTR-NEW-AAR | SE | BTR | BTR | Metro Routers | MRTR SE BTR BTR AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-BTR-NEW-AAR | SE | BTR | BTR | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-05 | 2020-06-30 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-BTR-NEW-AAR | SE | BTR | BTR | Metro Routers | MRTR SE BTR BTR AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-05 | 2020-08-31 | 2020-11-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-BTR-NEW-AAR | SE | BTR | BTR | Metro Routers | MRTR SE BTR BTR AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-BTR-NEW-AAR | SE | BTR | BTR | Metro Routers | MRTR SE BTR BTR AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2021-04-30 | 2021-04-30 | Active | Log | Upd | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR AAR-New-BTR-NEW-AAR | SE | BTR | BTR | Metro Routers | MRTR SE BTR BTR AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
MRTR AAR-New-PNS-NEW-AAR | SE | GCT | PNS | Metro Routers | MRTR SE GCT PNS AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-PNS-NEW-AAR | SE | GCT | PNS | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-PNS-NEW-AAR | SE | GCT | PNS | Metro Routers | MRTR SE GCT PNS AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-PNS-NEW-AAR | SE | GCT | PNS | Metro Routers | MRTR SE GCT PNS AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-PNS-NEW-AAR | SE | GCT | PNS | Metro Routers | MRTR SE GCT PNS AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2021-04-30 | 2021-04-30 | Active | Log | Upd | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR AAR-New-PNS-NEW-AAR | SE | GCT | PNS | Metro Routers | MRTR SE GCT PNS AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
MRTR AAR-New-LFY-NEW-AAR | SE | LFY | LFY | Metro Routers | MRTR SE LFY LFY AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-LFY-NEW-AAR | SE | LFY | LFY | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-LFY-NEW-AAR | SE | LFY | LFY | Metro Routers | MRTR SE LFY LFY AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-LFY-NEW-AAR | SE | LFY | LFY | Metro Routers | MRTR SE LFY LFY AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0502 | Schedule Change | Approved | 2020-04-29 16:33 | 1 Updating CR 395 Financials 2 Pushing out the AAR in the Q2 Plan out to June 3 Will wait for final decision based on Equipment delivery and Deferrals to align back
MRTR AAR-New-LFY-NEW-AAR | SE | LFY | LFY | Metro Routers | MRTR SE LFY LFY AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-LFY-NEW-AAR | SE | LFY | LFY | Metro Routers | MRTR SE LFY LFY AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2021-04-30 | 2021-04-30 | Active | Log | Upd | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR AAR-New-LFY-NEW-AAR | SE | LFY | LFY | Metro Routers | MRTR SE LFY LFY AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
MRTR AAR-New-WRB-NEW-AAR | SE | MGA | WRB | Metro Routers | MRTR SE MGA WRB AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-WRB-NEW-AAR | SE | MGA | WRB | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-WRB-NEW-AAR | SE | MGA | WRB | Metro Routers | MRTR SE MGA WRB AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-WRB-NEW-AAR | SE | MGA | WRB | Metro Routers | MRTR SE MGA WRB AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0502 | Schedule Change | Approved | 2020-04-29 16:33 | 1 Updating CR 395 Financials 2 Pushing out the AAR in the Q2 Plan out to June 3 Will wait for final decision based on Equipment delivery and Deferrals to align back
MRTR AAR-New-WRB-NEW-AAR | SE | MGA | WRB | Metro Routers | MRTR SE MGA WRB AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-WRB-NEW-AAR | SE | MGA | WRB | Metro Routers | MRTR SE MGA WRB AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2021-04-30 | 2021-04-30 | Active | Log | Upd | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR AAR-New-WRB-NEW-AAR | SE | MGA | WRB | Metro Routers | MRTR SE MGA WRB AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
MRTR AAR-New-ELM-NEW-AAR | SE | NOR | ELM | Metro Routers | MRTR SE NOR ELM AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-ELM-NEW-AAR | SE | NOR | ELM | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-ELM-NEW-AAR | SE | NOR | ELM | Metro Routers | MRTR SE NOR ELM AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-ELM-NEW-AAR | SE | NOR | ELM | Metro Routers | MRTR SE NOR ELM AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-ELM-NEW-AAR | SE | NOR | ELM | Metro Routers | MRTR SE NOR ELM AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2021-04-30 | 2021-04-30 | Active | Log | Upd | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR AAR-New-ELM-NEW-AAR | SE | NOR | ELM | Metro Routers | MRTR SE NOR ELM AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
MRTR AAR-New-LPL-NEW-AAR | SE | NOR | LPL | Metro Routers | MRTR SE NOR LPL AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-LPL-NEW-AAR | SE | NOR | LPL | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-01 03:01 | 2020-12-31 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-LPL-NEW-AAR | SE | NOR | LPL | Metro Routers | MRTR SE NOR LPL AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-LPL-NEW-AAR | SE | NOR | LPL | Metro Routers | MRTR SE NOR LPL AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-LPL-NEW-AAR | SE | NOR | LPL | Metro Routers | MRTR SE NOR LPL AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2021-04-30 | 2021-04-30 | Active | Log | Upd | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR AAR-New-LPL-NEW-AAR | SE | NOR | LPL | Metro Routers | MRTR SE NOR LPL AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
MRTR AAR-New-CLR-NEW-AAR | SE | NOR | CLR | Metro Routers | MRTR SE NOR CLR AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-CLR-NEW-AAR | SE | NOR | CLR | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-01 03:01 | 2020-12-31 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-CLR-NEW-AAR | SE | NOR | CLR | Metro Routers | MRTR SE NOR CLR AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-CLR-NEW-AAR | SE | NOR | CLR | Metro Routers | MRTR SE NOR CLR AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-CLR-NEW-AAR | SE | NOR | CLR | Metro Routers | MRTR SE NOR CLR AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2021-04-30 | 2021-04-30 | Active | Log | Upd | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR AAR-New-CLR-NEW-AAR | SE | NOR | CLR | Metro Routers | MRTR SE NOR CLR AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
MRTR AAR-New-MCY-NEW-AAR | SE | NOR | MCY | Metro Routers | MRTR SE NOR MCY AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-MCY-NEW-AAR | SE | NOR | MCY | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-01 | 2020-10-31 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-MCY-NEW-AAR | SE | NOR | MCY | Metro Routers | MRTR SE NOR MCY AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-30 | 2020-09-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-MCY-NEW-AAR | SE | NOR | MCY | Metro Routers | MRTR SE NOR MCY AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0502 | Schedule Change | Approved | 2020-04-29 16:33 | 1 Updating CR 395 Financials 2 Pushing out the AAR in the Q2 Plan out to June 3 Will wait for final decision based on Equipment delivery and Deferrals to align back
MRTR AAR-New-MCY-NEW-AAR | SE | NOR | MCY | Metro Routers | MRTR SE NOR MCY AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-MCY-NEW-AAR | SE | NOR | MCY | Metro Routers | MRTR SE NOR MCY AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2021-04-30 | 2021-04-30 | Active | Log | Upd | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR AAR-New-MCY-NEW-AAR | SE | NOR | MCY | Metro Routers | MRTR SE NOR MCY AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
MRTR AAR-New-LTF-NEW-AAR | VA | HRD | LTF | Metro Routers | MRTR VA HRD LTF AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-LTF-NEW-AAR | VA | HRD | LTF | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-01 03:01 | 2020-12-31 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-LTF-NEW-AAR | VA | HRD | LTF | Metro Routers | MRTR VA HRD LTF AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-LTF-NEW-AAR | VA | HRD | LTF | Metro Routers | MRTR VA HRD LTF AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-NWP-NEW-AAR | VA | HRD | NWP | Metro Routers | MRTR VA HRD NWP AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-NWP-NEW-AAR | VA | HRD | NWP | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-05 | 2020-06-30 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-NWP-NEW-AAR | VA | HRD | NWP | Metro Routers | MRTR VA HRD NWP AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-05 | 2020-08-31 | 2020-11-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-NWP-NEW-AAR | VA | HRD | NWP | Metro Routers | MRTR VA HRD NWP AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-NRF-NEW-AAR | VA | HRD | NRF | Metro Routers | MRTR VA HRD NRF AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-NRF-NEW-AAR | VA | HRD | NRF | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-NRF-NEW-AAR | VA | HRD | NRF | Metro Routers | MRTR VA HRD NRF AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-NRF-NEW-AAR | VA | HRD | NRF | Metro Routers | MRTR VA HRD NRF AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-OCN-NEW-AAR | VA | HRD | OCN | Metro Routers | MRTR VA HRD OCN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-OCN-NEW-AAR | VA | HRD | OCN | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 03:01 | 2020-06-30 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-OCN-NEW-AAR | VA | HRD | OCN | Metro Routers | MRTR VA HRD OCN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-05 | 2020-08-31 | 2020-11-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-OCN-NEW-AAR | VA | HRD | OCN | Metro Routers | MRTR VA HRD OCN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-PTM-NEW-AAR | VA | HRD | PTM | Metro Routers | MRTR VA HRD PTM AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-PTM-NEW-AAR | VA | HRD | PTM | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-PTM-NEW-AAR | VA | HRD | PTM | Metro Routers | MRTR VA HRD PTM AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-PTM-NEW-AAR | VA | HRD | PTM | Metro Routers | MRTR VA HRD PTM AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-PRA-NEW-AAR | VA | HRD | PRA | Metro Routers | MRTR VA HRD PRA AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-PRA-NEW-AAR | VA | HRD | PRA | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-PRA-NEW-AAR | VA | HRD | PRA | Metro Routers | MRTR VA HRD PRA AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-PRA-NEW-AAR | VA | HRD | PRA | Metro Routers | MRTR VA HRD PRA AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-VBC-NEW-AAR | VA | HRD | VBC | Metro Routers | MRTR VA HRD VBC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-VBC-NEW-AAR | VA | HRD | VBC | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-05 | 2020-06-30 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-VBC-NEW-AAR | VA | HRD | VBC | Metro Routers | MRTR VA HRD VBC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-05 | 2020-08-31 | 2020-11-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-VBC-NEW-AAR | VA | HRD | VBC | Metro Routers | MRTR VA HRD VBC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-FBG-NEW-AAR | VA | NVA | FBG | Metro Routers | MRTR VA NVA FBG AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-FBG-NEW-AAR | VA | NVA | FBG | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-01 03:01 | 2020-12-31 |  | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-FBG-NEW-AAR | VA | NVA | FBG | Metro Routers | MRTR VA NVA FBG AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-FBG-NEW-AAR | VA | NVA | FBG | Metro Routers | MRTR VA NVA FBG AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-RON-NEW-AAR | VA | ROA | RON | Metro Routers | MRTR VA ROA RON AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR AAR-New-RON-NEW-AAR | VA | ROA | RON | Metro Routers | MRTR CA SAN ESC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 |  | Deleted | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-RON-NEW-AAR | VA | ROA | RON | Metro Routers | MRTR VA ROA RON AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Deleted | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-RON-NEW-AAR | VA | ROA | RON | Metro Routers | MRTR VA ROA RON AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-IRV-NEW-AAR | CA | ORG | IRV | Metro Routers | MRTR CA SAN OCE AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | EP
MRTR AAR-New-IRV-NEW-AAR | CA | ORG | IRV | Metro Routers | MRTR CA SAN OCE AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-15 | 2020-06-15 | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-IRV-NEW-AAR | CA | ORG | IRV | Metro Routers | MRTR CA SAN OCE AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 03:01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-IRV-NEW-AAR | CA | ORG | IRV | Metro Routers | MRTR CA SAN OCE AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0502 | Schedule Change | Approved | 2020-04-29 16:33 | 1 Updating CR 395 Financials 2 Pushing out the AAR in the Q2 Plan out to June 3 Will wait for final decision based on Equipment delivery and Deferrals to align back
MRTR AAR-New-IRV-NEW-AAR | CA | ORG | IRV | Metro Routers | MRTR CA SAN OCE AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Active | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-IRV-NEW-AAR | CA | ORG | IRV | Metro Routers | MRTR CA SAN OCE AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Undel | SN-0651 | Scope Change | Approved | 2020-06-14 18:38 | 1 AAR SLR Alignment to support new PON site list new PON roll out and align SLR with AAR deliveries were misaligned post deferrals 2 Total 15 AAR s and 6 SLR s have been added to the Plan 3 Amount is Self Solved as the net addition to plan in Covid 19 and
MRTR AAR-New-ORG-NEW-AAR | CA | ORG | ORG | Metro Routers | MRTR CA ORG ORG AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 1 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | EP
MRTR AAR-New-ORG-NEW-AAR | CA | ORG | ORG | Metro Routers | MRTR CA SAN OCE AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-15 | 2020-06-15 | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-ORG-NEW-AAR | CA | ORG | ORG | Metro Routers | MRTR CA SAN OCE AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 03:01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-ORG-NEW-AAR | CA | ORG | ORG | Metro Routers | MRTR CA SAN OCE AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0502 | Schedule Change | Approved | 2020-04-29 16:33 | 1 Updating CR 395 Financials 2 Pushing out the AAR in the Q2 Plan out to June 3 Will wait for final decision based on Equipment delivery and Deferrals to align back
MRTR AAR-New-ORG-NEW-AAR | CA | ORG | ORG | Metro Routers | MRTR CA SAN OCE AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Active | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-ORG-NEW-AAR | CA | ORG | ORG | Metro Routers | MRTR CA ORG ORG AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 1 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | New | SN-0750 | Scope Change | Approved | 2020-07-15 17:23 | This CR removes 6 SLR s from the plan It also adds 11 AAR s to the plan self solve Removal of SLR s nets a 451K giveback to risk
MRTR AAR-New-ORG-NEW-AAR | CA | ORG | ORG | Metro Routers | MRTR CA ORG ORG AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0867 | Scope Change | Canceled | 2020-10-16 08:53 | Adding projects to the POR based on audit in the field
MRTR AAR-New-PAV-NEW-AAR | CA | ORG | PAV | Metro Routers | MRTR CA ORG PAV AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | EP
MRTR AAR-New-PAV-NEW-AAR | CA | ORG | PAV | Metro Routers | MRTR CA SAN OCE AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-15 | 2020-06-15 | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-PAV-NEW-AAR | CA | ORG | PAV | Metro Routers | MRTR CA SAN OCE AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-01-01 03:01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-PAV-NEW-AAR | CA | ORG | PAV | Metro Routers | MRTR CA SAN OCE AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0502 | Schedule Change | Approved | 2020-04-29 16:33 | 1 Updating CR 395 Financials 2 Pushing out the AAR in the Q2 Plan out to June 3 Will wait for final decision based on Equipment delivery and Deferrals to align back
MRTR AAR-New-PAV-NEW-AAR | CA | ORG | PAV | Metro Routers | MRTR CA SAN OCE AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Active | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-PAV-NEW-AAR | CA | ORG | PAV | Metro Routers | MRTR CA SAN OCE AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Undel | SN-0651 | Scope Change | Approved | 2020-06-14 18:38 | 1 AAR SLR Alignment to support new PON site list new PON roll out and align SLR with AAR deliveries were misaligned post deferrals 2 Total 15 AAR s and 6 SLR s have been added to the Plan 3 Amount is Self Solved as the net addition to plan in Covid 19 and
MRTR AAR-New-PAV-NEW-AAR | CA | ORG | PAV | Metro Routers | MRTR CA ORG PAV AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0750 | Scope Change | Approved | 2020-07-15 17:23 | This CR removes 6 SLR s from the plan It also adds 11 AAR s to the plan self solve Removal of SLR s nets a 451K giveback to risk
MRTR AAR-New-RSM-NEW-AAR | CA | ORG | RSM | Metro Routers | MRTR CA ORG RSM AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-RSM-NEW-AAR | CA | ORG | RSM | Metro Routers | MRTR CA SAN OCE AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-15 | 2020-06-15 | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-RSM-NEW-AAR | CA | ORG | RSM | Metro Routers | MRTR CA SAN OCE AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-05 | 2020-08-31 | 2020-11-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-RSM-NEW-AAR | CA | ORG | RSM | Metro Routers | MRTR CA SAN OCE AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-RSM-NEW-AAR | CA | ORG | RSM | Metro Routers | MRTR CA ORG RSM AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR AAR-New-PWY-NEW-AAR | CA | SAN | PWY | Metro Routers | MRTR CA SAN PWY AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | EP
MRTR AAR-New-PWY-NEW-AAR | CA | SAN | PWY | Metro Routers | MRTR CA SAN OCE AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-05 | 2020-07-31 | 2020-07-31 | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-PWY-NEW-AAR | CA | SAN | PWY | Metro Routers | MRTR CA SAN PWY AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-30 | 2020-12-31 | 2021-03-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-PWY-NEW-AAR | CA | SAN | PWY | Metro Routers | MRTR CA SAN PWY AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Active | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-PWY-NEW-AAR | CA | SAN | PWY | Metro Routers | MRTR CA SAN PWY AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Undel | SN-0651 | Scope Change | Approved | 2020-06-14 18:38 | 1 AAR SLR Alignment to support new PON site list new PON roll out and align SLR with AAR deliveries were misaligned post deferrals 2 Total 15 AAR s and 6 SLR s have been added to the Plan 3 Amount is Self Solved as the net addition to plan in Covid 19 and
MRTR AAR-New-VST-NEW-AAR | CA | SAN | VST | Metro Routers | MRTR CA SAN VST AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-VST-NEW-AAR | CA | SAN | VST | Metro Routers | MRTR CA SAN OCE AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-05 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-VST-NEW-AAR | CA | SAN | VST | Metro Routers | MRTR CA SAN VST AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-05 | 2020-08-31 | 2020-11-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-VST-NEW-AAR | CA | SAN | VST | Metro Routers | MRTR CA SAN VST AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-SAB-NEW-AAR | CA | SAB | SAB | Metro Routers | MRTR CA SAB SAB AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-15 | 2020-11-30 | 2020-12-31 | Active | EP
MRTR AAR-New-SAB-NEW-AAR | CA | SAB | SAB | Metro Routers | MRTR CA SAN OCE AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-05 | 2020-10-05 | 2020-10-05 | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-SAB-NEW-AAR | CA | SAB | SAB | Metro Routers | MRTR CA SAN OCE AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Active | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-SAB-NEW-AAR | CA | SAB | SAB | Metro Routers | MRTR CA SAB SAB AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-15 | 2020-11-30 | 2020-12-31 | Active | Log | New | SN-0750 | Scope Change | Approved | 2020-07-15 17:23 | This CR removes 6 SLR s from the plan It also adds 11 AAR s to the plan self solve Removal of SLR s nets a 451K giveback to risk
MRTR AAR-New-BEL-NEW-AAR | SW | ARZ | BEL | Metro Routers | MRTR SW ARZ BEL AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-BEL-NEW-AAR | SW | ARZ | BEL | Metro Routers | MRTR SW ARZ BUK AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-01 | 2020-07-15 | 2020-07-15 | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-BEL-NEW-AAR | SW | ARZ | BEL | Metro Routers | MRTR SW ARZ BEL AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-05 | 2020-09-30 | 2020-12-31 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-BEL-NEW-AAR | SW | ARZ | BEL | Metro Routers | MRTR SW ARZ BEL AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-BLU-NEW-AAR | SW | LAS | BLU | Metro Routers | MRTR SW LAS BLU AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-BLU-NEW-AAR | SW | LAS | BLU | Metro Routers | MRTR SW ARZ BUK AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-15 | 2020-06-15 | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-BLU-NEW-AAR | SW | LAS | BLU | Metro Routers | MRTR SW LAS BLU AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-05 | 2020-08-31 | 2020-11-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-BLU-NEW-AAR | SW | LAS | BLU | Metro Routers | MRTR SW LAS BLU AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-TEN-NEW-AAR | SW | LAS | TEN | Metro Routers | MRTR SW LAS TEN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR AAR-New-TEN-NEW-AAR | SW | LAS | TEN | Metro Routers | MRTR SW ARZ BUK AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-04-01 | 2020-06-15 | 2020-06-15 | Active | Log | New | SN-0099 | Schedule Change | Approved | 2020-02-06 10:47
MRTR AAR-New-TEN-NEW-AAR | SW | LAS | TEN | Metro Routers | MRTR SW LAS TEN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-05 | 2020-08-31 | 2020-11-30 | Active | Log | Upd | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-TEN-NEW-AAR | SW | LAS | TEN | Metro Routers | MRTR SW LAS TEN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-AVJ-NEW-AAR | CA | ORG | AVJ | Metro Routers | MRTR CA ORG AVJ AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | EP
MRTR AAR-New-AVJ-NEW-AAR | CA | ORG | AVJ | Metro Routers | MRTR CA ORG AVJ AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR AAR-New-AVJ-NEW-AAR | CA | ORG | AVJ | Metro Routers | MRTR CA ORG AVJ AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Active | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-AVJ-NEW-AAR | CA | ORG | AVJ | Metro Routers | MRTR CA ORG AVJ AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Undel | SN-0651 | Scope Change | Approved | 2020-06-14 18:38 | 1 AAR SLR Alignment to support new PON site list new PON roll out and align SLR with AAR deliveries were misaligned post deferrals 2 Total 15 AAR s and 6 SLR s have been added to the Plan 3 Amount is Self Solved as the net addition to plan in Covid 19 and
MRTR SLR-New-AVJ-SLR-ASR9906 | CA | ORG | AVJ | Metro Routers | MRTR CA ORG AVJ SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR SLR-New-AVJ-SLR-ASR9906 | CA | ORG | AVJ | Metro Routers | MRTR CA ORG AVJ SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2021-03-31 | Deleted | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-AVJ-SLR-ASR9906 | CA | ORG | AVJ | Metro Routers | MRTR CA ORG AVJ SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-DNP-SLR-ASR9906 | CA | ORG | DNP | Metro Routers | MRTR CA ORG DNP SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR SLR-New-DNP-SLR-ASR9906 | CA | ORG | DNP | Metro Routers | MRTR CA ORG DNP SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2021-03-31 | Deleted | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR SLR-New-DNP-SLR-ASR9906 | CA | ORG | DNP | Metro Routers | MRTR CA ORG DNP SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR VSR-New-ELC-VSR-ASR9906 | CA | SAN | ELC | Metro Routers | MRTR CA SAN ELC VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR VSR-New-ELC-VSR-ASR9906 | CA | SAN | ELC | Metro Routers | MRTR CA SAN ELC VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-01 | 2020-12-31 | 2021-06-30 | Deleted | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR VSR-New-ELC-VSR-ASR9906 | CA | SAN | ELC | Metro Routers | MRTR CA SAN ELC VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR VSR-New-CLV-VSR-ASR9906 | NE | CLE | CLV | Metro Routers | MRTR NE CLE CLV VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR VSR-New-CLV-VSR-ASR9906 | NE | CLE | CLV | Metro Routers | MRTR NE CLE CLV VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2021-04-30 | Deleted | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR VSR-New-CLV-VSR-ASR9906 | NE | CLE | CLV | Metro Routers | MRTR NE CLE CLV VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR VSR-New-BTR-VSR-ASR9906 | SE | BTR | BTR | Metro Routers | MRTR SE BTR BTR VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR VSR-New-BTR-VSR-ASR9906 | SE | BTR | BTR | Metro Routers | MRTR SE BTR BTR VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2021-03-31 | Deleted | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR VSR-New-BTR-VSR-ASR9906 | SE | BTR | BTR | Metro Routers | MRTR SE BTR BTR VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR VSR-New-GNS-VSR-ASR9906 | SE | GAN | GNS | Metro Routers | MRTR SE GAN GNS VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR VSR-New-GNS-VSR-ASR9906 | SE | GAN | GNS | Metro Routers | MRTR SE GAN GNS VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2021-03-31 | Deleted | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR VSR-New-GNS-VSR-ASR9906 | SE | GAN | GNS | Metro Routers | MRTR SE GAN GNS VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR VSR-New-PNS-VSR-ASR9906 | SE | GCT | PNS | Metro Routers | MRTR SE GCT PNS VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR VSR-New-PNS-VSR-ASR9906 | SE | GCT | PNS | Metro Routers | MRTR SE GCT PNS VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2021-03-31 | Deleted | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR VSR-New-PNS-VSR-ASR9906 | SE | GCT | PNS | Metro Routers | MRTR SE GCT PNS VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR VSR-New-MCN-VSR-ASR9906 | SE | MGA | MCN | Metro Routers | MRTR SE MGA MCN VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-01 | 2020-12-31 | 2021-03-31 | Active | EP
MRTR VSR-New-MCN-VSR-ASR9906 | SE | MGA | MCN | Metro Routers | MRTR SE MGA MCN VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2021-03-31 | Active | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR VSR-New-MCN-VSR-ASR9906 | SE | MGA | MCN | Metro Routers | MRTR SE MGA MCN VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-01 | 2020-12-31 | 2021-03-31 | Active | Log | Upd | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR VSR-New-ELM-VSR-ASR9906 | SE | NOR | ELM | Metro Routers | MRTR SE NOR ELM VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR VSR-New-ELM-VSR-ASR9906 | SE | NOR | ELM | Metro Routers | MRTR SE NOR ELM VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2021-03-31 | Deleted | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR VSR-New-ELM-VSR-ASR9906 | SE | NOR | ELM | Metro Routers | MRTR SE NOR ELM VSR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR OOB-New-PTH-OOB Server | NE | RHD | PTH | Metro Routers | MRTR NE RHD PTH OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR OOB-New-PTH-OOB Server | NE | RHD | PTH | Metro Routers | MRTR NE RHD PTH OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-AVJ-OOB Server | CA | ORG | AVJ | Metro Routers | MRTR CA ORG AVJ OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-07-01 | 2020-07-01 | Active | EP
MRTR OOB-New-AVJ-OOB Server | CA | ORG | AVJ | Metro Routers | MRTR CA ORG AVJ OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-07-01 | 2020-07-01 | Active | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-DNP-OOB Server | CA | ORG | DNP | Metro Routers | MRTR CA ORG DNP OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-06-30 | 2020-09-30 | Active | EP
MRTR OOB-New-DNP-OOB Server | CA | ORG | DNP | Metro Routers | MRTR CA ORG DNP OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-06-30 | 2020-09-30 | Active | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-IRV-OOB Server | CA | ORG | IRV | Metro Routers | MRTR CA ORG IRV OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-06-30 | 2020-09-30 | Active | EP
MRTR OOB-New-IRV-OOB Server | CA | ORG | IRV | Metro Routers | MRTR CA ORG IRV OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-06-30 | 2020-09-30 | Active | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-ORG-OOB Server | CA | ORG | ORG | Metro Routers | MRTR CA ORG ORG OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-06-30 | 2020-09-30 | Active | EP
MRTR OOB-New-ORG-OOB Server | CA | ORG | ORG | Metro Routers | MRTR CA ORG ORG OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-06-30 | 2020-09-30 | Active | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-PAV-OOB Server | CA | ORG | PAV | Metro Routers | MRTR CA ORG PAV OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-06-30 | 2020-09-30 | Active | EP
MRTR OOB-New-PAV-OOB Server | CA | ORG | PAV | Metro Routers | MRTR CA ORG PAV OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-06-30 | 2020-09-30 | Active | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-RSM-OOB Server | CA | ORG | RSM | Metro Routers | MRTR CA ORG RSM OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 4 | 2020-04-05 | 2020-06-30 | 2020-09-30 | Active | EP
MRTR OOB-New-RSM-OOB Server | CA | ORG | RSM | Metro Routers | MRTR CA ORG RSM OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 4 | 2020-04-05 | 2020-06-30 | 2020-09-30 | Active | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-ALP-OOB Server | CA | SAN | ALP | Metro Routers | MRTR CA SAN ALP OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-06-30 | 2020-09-30 | Active | EP
MRTR OOB-New-ALP-OOB Server | CA | SAN | ALP | Metro Routers | MRTR CA SAN ALP OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-06-30 | 2020-09-30 | Active | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-CHU-OOB Server | CA | SAN | CHU | Metro Routers | MRTR CA SAN CHU OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-06-30 | 2020-09-30 | Active | EP
MRTR OOB-New-CHU-OOB Server | CA | SAN | CHU | Metro Routers | MRTR CA SAN CHU OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-06-30 | 2020-09-30 | Active | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-DWN-OOB Server | CA | SAN | DWN | Metro Routers | MRTR CA SAN DWN OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-06-30 | 2020-09-30 | Active | EP
MRTR OOB-New-DWN-OOB Server | CA | SAN | DWN | Metro Routers | MRTR CA SAN DWN OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-06-30 | 2020-09-30 | Active | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-ELC-OOB Server | CA | SAN | ELC | Metro Routers | MRTR CA SAN ELC OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-04-05 | 2020-06-30 | 2020-09-30 | Active | EP
MRTR OOB-New-ELC-OOB Server | CA | SAN | ELC | Metro Routers | MRTR CA SAN ELC OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-04-05 | 2020-06-30 | 2020-09-30 | Active | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-ESC-OOB Server | CA | SAN | ESC | Metro Routers | MRTR CA SAN ESC OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-06-30 | 2020-09-30 | Active | EP
MRTR OOB-New-ESC-OOB Server | CA | SAN | ESC | Metro Routers | MRTR CA SAN ESC OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-06-30 | 2020-09-30 | Active | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-FED-OOB Server | CA | SAN | FED | Metro Routers | MRTR CA SAN FED OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-04-05 | 2020-06-30 | 2020-09-30 | Active | EP
MRTR OOB-New-FED-OOB Server | CA | SAN | FED | Metro Routers | MRTR CA SAN FED OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 2 | 2020-04-05 | 2020-06-30 | 2020-09-30 | Active | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-OCE-OOB Server | CA | SAN | OCE | Metro Routers | MRTR CA SAN OCE OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-06-30 | 2020-09-30 | Active | EP
MRTR OOB-New-OCE-OOB Server | CA | SAN | OCE | Metro Routers | MRTR CA SAN OCE OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-06-30 | 2020-09-30 | Active | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-PWY-OOB Server | CA | SAN | PWY | Metro Routers | MRTR CA SAN PWY OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-06-30 | 2020-09-30 | Active | EP
MRTR OOB-New-PWY-OOB Server | CA | SAN | PWY | Metro Routers | MRTR CA SAN PWY OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-06-30 | 2020-09-30 | Active | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR OOB-New-VST-OOB Server | CA | SAN | VST | Metro Routers | MRTR CA SAN VST OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-06-30 | 2020-09-30 | Active | EP
MRTR OOB-New-VST-OOB Server | CA | SAN | VST | Metro Routers | MRTR CA SAN VST OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-04-05 | 2020-06-30 | 2020-09-30 | Active | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-PAV-100G Grow | CA | ORG | PAV | Metro Routers | MRTR CA ORG AVJ 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-04-01 | 2020-05-01 | 2020-09-01 | Active | EP
MRTR NCS-Growth-PAV-100G Grow | CA | ORG | PAV | Metro Routers | MRTR CA ORG AVJ 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-04-01 | 2020-05-01 | 2020-09-01 | Active | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-OCE-100G Grow | VA | HRD | OCN | Metro Routers | MRTR CA ORG AVJ 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-04-01 | 2020-05-30 | 2020-09-30 | Deleted | EP
MRTR NCS-Growth-RSM2-100G Grow | CA | ORG | RSM | Metro Routers | MRTR CA ORG RSM NCS Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR NCS-Growth-RSM2-100G Grow | CA | ORG | RSM | Metro Routers | MRTR CA ORG RSM NCS Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Undel | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-PTH-100G Grow | NE | RHD | PTH | Metro Routers | MRTR NE RHD WWK 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
MRTR NCS-Growth-PTH-100G Grow | NE | RHD | PTH | Metro Routers | MRTR NE RHD WWK 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-MAN-100G Grow | NE | CON | MAN | Metro Routers | MRTR NE RHD WWK 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-04-01 | 2020-04-30 | 2020-05-30 | Active | EP
MRTR NCS-Growth-MAN-100G Grow | NE | CON | MAN | Metro Routers | MRTR NE RHD WWK 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-04-01 | 2020-04-30 | 2020-05-30 | Active | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-FWB-100G Grow | SE | GCT | FWB | Metro Routers | MRTR SE MGA WRB 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-07-01 | 2020-08-01 | 2020-09-30 | Active | EP
MRTR NCS-Growth-FWB-100G Grow | SE | GCT | FWB | Metro Routers | MRTR SE MGA WRB 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-07-01 | 2020-08-01 | 2020-09-30 | Active | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-PEO-100G Grow | SW | ARZ | PEO | Metro Routers | MRTR SW ARZ MSA 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-04-30 | Active | EP
MRTR NCS-Growth-PEO-100G Grow | SW | ARZ | PEO | Metro Routers | MRTR SW ARZ MSA 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-01-01 | 2020-03-31 | 2020-04-30 | Active | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-ALI-100G Grow | SW | LAS | ALI | Metro Routers | MRTR SW ARZ MSA 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-07-01 | 2020-08-30 | 2020-09-30 | Active | EP
MRTR NCS-Growth-ALI-100G Grow | SW | LAS | ALI | Metro Routers | MRTR SW ARZ MSA 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-07-01 | 2020-08-30 | 2020-09-30 | Active | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
MRTR NCS-Growth-ERN-100G Grow | SW | LAS | ERN | Metro Routers | MRTR SW ARZ MSA 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-08-01 | 2020-09-30 | 2020-10-30 | Active | EP
MRTR NCS-Growth-ERN-100G Grow | SW | LAS | ERN | Metro Routers | MRTR SW ARZ MSA 100G Grow Augment POR20 | Card & Optics | 100G Grow | 2 | 2020-08-01 | 2020-09-30 | 2020-10-30 | Active | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
NEXUS-FBG-93180-01 | VA | NVA | FBG | Metro Routers | MRTR VA NVA FBG Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-04-20 | 2020-06-01 | 2020-06-01 | Active | EP
NEXUS-FBG-93180-01 | VA | NVA | FBG | Metro Routers | MRTR VA NVA FBG Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-04-20 | 2020-06-01 | 2020-06-01 | Active | Log | New | SN-0239 | Schedule Change | Approved | 2020-02-07 14:34 | 1 Updating Plan to reflect the Financials per the BOM 2 This subset had Raid Risk raised as the Plan was not aligned to the final version of the BOM 3 INP and PDG were re conciling on if any changes needs to be made on top of the existing BOM;s placed
NEXUS-FBG-2248-01 | VA | NVA | FBG | Metro Routers | MRTR VA NVA FBG Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-04-20 | 2020-06-01 | 2020-06-01 | Active | EP
NEXUS-FBG-2248-01 | VA | NVA | FBG | Metro Routers | MRTR VA NVA FBG Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-04-20 | 2020-06-01 | 2020-06-01 | Active | Log | New | SN-0239 | Schedule Change | Approved | 2020-02-07 14:34 | 1 Updating Plan to reflect the Financials per the BOM 2 This subset had Raid Risk raised as the Plan was not aligned to the final version of the BOM 3 INP and PDG were re conciling on if any changes needs to be made on top of the existing BOM;s placed
MRTR AAR-New-SSC-NEW-SLR | SW | ARZ | SSC | Metro Routers | MRTR SW ARZ SSC SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-01 | 2020-08-31 | 2020-09-30 | Deleted | EP
MRTR AAR-New-PEO-NEW-SLR | SW | ARZ | PEO | Metro Routers | MRTR SW ARZ PEO SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-06-01 | 2020-08-31 | 2020-09-30 | Deleted | EP
MRTR SLR-New-SSC-NEW-SLR | SW | ARZ | SSC | Metro Routers | MRTR SW ARZ SSC SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR SLR-New-SSC-NEW-SLR | SW | ARZ | SSC | Metro Routers | MRTR SW ARZ SSC SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | New | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SLR-New-PEO-NEW-SLR | SW | ARZ | PEO | Metro Routers | MRTR SW ARZ PEO SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR SLR-New-PEO-NEW-SLR | SW | ARZ | PEO | Metro Routers | MRTR SW ARZ PEO SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Active | Log | New | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR AAR-New-MAN-AAR-ASR9906 | NE | CON | MAN | Metro Routers | MRTR NE CON MAN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Deleted | EP
MRTR AAR-New-PTH-AAR-ASR9906 | NE | RHD | PTH | Metro Routers | MRTR NE RHD PTH AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Deleted | EP
MRTR AAR-New-WWK-AAR-ASR9906 | NE | RHD | WWK | Metro Routers | MRTR NE RHD WWK AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Deleted | EP
MRTR SLR-New-PRV-SLR-ASR9906 | NE | RHD | PRV | Metro Routers | MRTR NE RHD PRV SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-12-31 | Active | EP
MRTR SLR-New-PRV-SLR-ASR9906 | NE | RHD | PRV | Metro Routers | MRTR NE RHD PRV SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-12-31 | Active | Log | New | SN-1037 | Schedule Change | Approved | 2020-11-06 09:51 | Alignment of POR based on feedback from the field
MRTR NCS-Growth-OCN-NCS Line Card | VA | HRD | OCN | Metro Routers | MRTR VA HRD OCN 100G Grow Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR NCS-Growth-OCN-NCS Line Card | VA | HRD | OCN | Metro Routers | MRTR VA HRD OCN 100G Grow Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR NCS-Growth-CHD-NCS Line Card 2 | SW | ARZ | CHD | Metro Routers | MRTR SW ARZ CHD NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR NCS-Growth-CHD-NCS Line Card 2 | SW | ARZ | CHD | Metro Routers | MRTR SW ARZ CHD NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR SW LAS VLY 100G Grow Augment POR20 | SW | LAS | VLY | Metro Routers | MRTR SW LAS VLY 100G Grow Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR SW LAS VLY 100G Grow Augment POR20 | SW | LAS | VLY | Metro Routers | MRTR SW LAS VLY 100G Grow Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR NCS-Growth-DWN-NCS Line Card | CA | SAN | DWN | Metro Routers | MRTR CA SAN DWN NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-05 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR NCS-Growth-DWN-NCS Line Card | CA | SAN | DWN | Metro Routers | MRTR CA SAN DWN NCS Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-05 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR NCS-Growth-FED-NCS Line Card | CA | SAN | FED | Metro Routers | MRTR CA SAN FED 100G Grow Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-05 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR NCS-Growth-FED-NCS Line Card | CA | SAN | FED | Metro Routers | MRTR CA SAN FED 100G Grow Augment POR20 | Card & Optics | NCS Line Card | 2 | 2020-07-05 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
NEXUS-GLB-93108-02 | NE | CON | GLB | Metro Routers | MRTR NE CON GLB Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis |  |  |  |  | Deleted | EP
NEXUS-GLB-93108-02 | NE | CON | GLB | Metro Routers | MRTR NE CON GLB Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Deleted | Log | New | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
NEXUS-GLB-93108-02 | NE | CON | GLB | Metro Routers | MRTR NE CON GLB Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis |  |  |  |  | Deleted | Log | Del | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
NEXUS-GLB-93180-02 | NE | CON | GLB | Metro Routers | MRTR NE CON GLB Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis |  |  |  |  | Deleted | EP
NEXUS-GLB-93180-02 | NE | CON | GLB | Metro Routers | MRTR NE CON GLB Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Deleted | Log | New | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
NEXUS-GLB-93180-02 | NE | CON | GLB | Metro Routers | MRTR NE CON GLB Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis |  |  |  |  | Deleted | Log | Del | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
NEXUS-GLB-3048-02 | NE | CON | GLB | Metro Routers | MRTR NE CON GLB Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | EP
NEXUS-GLB-3048-02 | NE | CON | GLB | Metro Routers | MRTR NE CON GLB Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | Log | New | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
NEXUS-BUR-3048-02 | NE | RHD | BUR | Metro Routers | MRTR NE RHD BUR Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | EP
NEXUS-BUR-3048-02 | NE | RHD | BUR | Metro Routers | MRTR NE RHD BUR Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | Log | New | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
NEXUS-BUR-93108-02 | NE | RHD | BUR | Metro Routers | MRTR NE RHD BUR Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | EP
NEXUS-BUR-93108-02 | NE | RHD | BUR | Metro Routers | MRTR NE RHD BUR Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | Log | New | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
NEXUS-BUR-93180-02 | NE | RHD | BUR | Metro Routers | MRTR NE RHD BUR Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | EP
NEXUS-BUR-93180-02 | NE | RHD | BUR | Metro Routers | MRTR NE RHD BUR Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | Log | New | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
NEXUS-EXT-3048-01 | NE | RHD | EXT | Metro Routers | MRTR NE RHD EXT Metro Nexus Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | EP
NEXUS-EXT-3048-01 | NE | RHD | EXT | Metro Routers | MRTR NE RHD EXT Metro Nexus Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | Log | New | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
NEXUS-GRB-3048-02 | NE | CON | GRB | Metro Routers | MRTR NE CON GRB Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 | 2020-07-01 | 2020-08-31 | 2020-09-30 | Active | EP
NEXUS-GRB-3048-02 | NE | CON | GRB | Metro Routers | MRTR NE CON GRB Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 | 2020-07-01 | 2020-08-31 | 2020-09-30 | Active | Log | New | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
NEXUS-GRB-93108-02 | NE | CON | GRB | Metro Routers | MRTR NE CON GRB Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 2 | 2020-07-01 | 2020-08-31 | 2020-09-30 | Active | EP
NEXUS-GRB-93108-02 | NE | CON | GRB | Metro Routers | MRTR NE CON GRB Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 2 | 2020-07-01 | 2020-08-31 | 2020-09-30 | Active | Log | New | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
NEXUS-GRB-93180-02 | NE | CON | GRB | Metro Routers | MRTR NE CON GRB Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-07-01 | 2020-08-31 | 2020-09-30 | Active | EP
NEXUS-GRB-93180-02 | NE | CON | GRB | Metro Routers | MRTR NE CON GRB Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-07-01 | 2020-08-31 | 2020-09-30 | Active | Log | New | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
NEXUS-MAN-3048-02 | NE | CON | MAN | Metro Routers | MRTR NE CON MAN Metro Nexus Augment POR20 | Labor | No Equipment | 3 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | EP
NEXUS-MAN-3048-02 | NE | CON | MAN | Metro Routers | MRTR NE CON MAN Metro Nexus Augment POR20 | Labor | No Equipment | 3 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | Log | New | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
NEXUS-MAN-93108-02 | NE | CON | MAN | Metro Routers | MRTR NE CON MAN Metro Nexus Augment POR20 | Labor | No Equipment | 6 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | EP
NEXUS-MAN-93108-02 | NE | CON | MAN | Metro Routers | MRTR NE CON MAN Metro Nexus Augment POR20 | Labor | No Equipment | 6 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | Log | New | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
NEXUS-MAN-93180-02 | NE | CON | MAN | Metro Routers | MRTR NE CON MAN Metro Nexus Augment POR20 | Labor | No Equipment | 12 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | EP
NEXUS-MAN-93180-02 | NE | CON | MAN | Metro Routers | MRTR NE CON MAN Metro Nexus Augment POR20 | Labor | No Equipment | 12 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | Log | New | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
NEXUS-RMD-3048-02 | NE | RHD | RMD | Metro Routers | MRTR NE RHD RMD Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | EP
NEXUS-RMD-3048-02 | NE | RHD | RMD | Metro Routers | MRTR NE RHD RMD Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | Log | New | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
NEXUS-RKH-3048-02 | NE | CON | RKH | Metro Routers | MRTR NE CON RKH Metro Nexus Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | EP
NEXUS-RKH-3048-02 | NE | CON | RKH | Metro Routers | MRTR NE CON RKH Metro Nexus Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | Log | New | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
NEXUS-SCT-3048-02 | NE | RHD | SCT | Metro Routers | MRTR NE RHD SCT Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | EP
NEXUS-SCT-3048-02 | NE | RHD | SCT | Metro Routers | MRTR NE RHD SCT Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 1 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | Log | New | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
NEXUS-SCT-93108-02 | NE | RHD | SCT | Metro Routers | MRTR NE RHD SCT Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | EP
NEXUS-SCT-93108-02 | NE | RHD | SCT | Metro Routers | MRTR NE RHD SCT Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | Log | New | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
NEXUS-SCT-93180-02 | NE | RHD | SCT | Metro Routers | MRTR NE RHD SCT Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | EP
NEXUS-SCT-93180-02 | NE | RHD | SCT | Metro Routers | MRTR NE RHD SCT Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | Log | New | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
NEXUS-WWK-3048-02 | NE | RHD | WWK | Metro Routers | MRTR NE RHD WWK Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 3 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | EP
NEXUS-WWK-3048-02 | NE | RHD | WWK | Metro Routers | MRTR NE RHD WWK Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 3048 Chassis | 3 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | Log | New | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
NEXUS-WWK-93108-02 | NE | RHD | WWK | Metro Routers | MRTR NE RHD WWK Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 6 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | EP
NEXUS-WWK-93108-02 | NE | RHD | WWK | Metro Routers | MRTR NE RHD WWK Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 6 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | Log | New | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
NEXUS-WWK-93180-02 | NE | RHD | WWK | Metro Routers | MRTR NE RHD WWK Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 12 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | EP
NEXUS-WWK-93180-02 | NE | RHD | WWK | Metro Routers | MRTR NE RHD WWK Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 12 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | Log | New | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
NEXUS-WWK-2248-01 | NE | RHD | WWK | Metro Routers | MRTR NE RHD WWK Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 16 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | EP
NEXUS-WWK-2248-01 | NE | RHD | WWK | Metro Routers | MRTR NE RHD WWK Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 16 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | Log | New | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
NEXUS-GNS-93108-01 | SE | GAN | GNS | Metro Routers | MRTR SE GAN GNS Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | EP
NEXUS-GNS-93108-01 | SE | GAN | GNS | Metro Routers | MRTR SE GAN GNS Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | Log | New | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
NEXUS-GNS-2248-01 | SE | GAN | GNS | Metro Routers | MRTR SE GAN GNS Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | EP
NEXUS-GNS-2248-01 | SE | GAN | GNS | Metro Routers | MRTR SE GAN GNS Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | Log | New | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
NEXUS-PNS-93108-01 | SE | GAN | GNS | Metro Routers | MRTR SE GCT PNS Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis |  |  |  |  | Deleted | EP
NEXUS-PNS-93108-01 | SE | GAN | GNS | Metro Routers | MRTR SE GCT PNS Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Deleted | Log | New | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
NEXUS-PNS-93108-01 | SE | GAN | GNS | Metro Routers | MRTR SE GCT PNS Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis |  |  |  |  | Deleted | Log | Del | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
NEXUS-PNS-2248-01 | SE | GCT | PNS | Metro Routers | MRTR SE GCT PNS Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | EP
NEXUS-PNS-2248-01 | SE | GCT | PNS | Metro Routers | MRTR SE GCT PNS Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | Log | New | SN-0555 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 AAR in Q3 Q4 has been deferred 2 SLR in Q3 Q4 has been deferred 3 VSR for 3 FOA sites 4 Additional SLR sites missed in POR to be added
MRTR NCS-Growth-ALI-CIN- 2K | SW | LAS | ALI | Metro Routers | MRTR SW LAS ALI Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
MRTR NCS-Growth-ALI-CIN- 2K | SW | LAS | ALI | Metro Routers | MRTR SW LAS ALI Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0608 | Schedule Change | Approved | 2020-05-23 14:32 | Metro Routers: POR update Adding Aliante Valley and North Scottsdale Nexus 2K s
MRTR NCS-Growth-VLY-CIN- 2K | SW | LAS | VLY | Metro Routers | MRTR SW LAS VLY Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | EP
MRTR NCS-Growth-VLY-CIN- 2K | SW | LAS | VLY | Metro Routers | MRTR SW LAS VLY Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-05-15 | 2020-07-31 | 2020-08-31 | Active | Log | New | SN-0608 | Schedule Change | Approved | 2020-05-23 14:32 | Metro Routers: POR update Adding Aliante Valley and North Scottsdale Nexus 2K s
MRTR SLR-New-BLU-Nexus Th-2248 | SW | LAS | BLU | Metro Routers | MRTR SW LAS BLU Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-07-31 | Active | EP
MRTR SLR-New-BLU-Nexus Th-2248 | SW | LAS | BLU | Metro Routers | MRTR SW LAS BLU Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-07-31 | Active | Log | New | SN-0616 | Schedule Change | Approved | 2020-05-29 15:06 | 1 Updating sites missing in Metro Nexus for SouthWest 2 6 sites in Las Vegas for 2248 are part of the POR in Metro Nexus Growth 3 This needs to be updated into the plan
MRTR SLR-New-ERN-Nexus Th-2248 | SW | LAS | ERN | Metro Routers | MRTR SW LAS ERN Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-07-31 | Active | EP
MRTR SLR-New-ERN-Nexus Th-2248 | SW | LAS | ERN | Metro Routers | MRTR SW LAS ERN Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-07-31 | Active | Log | New | SN-0616 | Schedule Change | Approved | 2020-05-29 15:06 | 1 Updating sites missing in Metro Nexus for SouthWest 2 6 sites in Las Vegas for 2248 are part of the POR in Metro Nexus Growth 3 This needs to be updated into the plan
MRTR SLR-New-HEN-Nexus Th-2248 | SW | LAS | HEN | Metro Routers | MRTR SW LAS HEN Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-07-31 | Active | EP
MRTR SLR-New-HEN-Nexus Th-2248 | SW | LAS | HEN | Metro Routers | MRTR SW LAS HEN Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-07-31 | Active | Log | New | SN-0616 | Schedule Change | Approved | 2020-05-29 15:06 | 1 Updating sites missing in Metro Nexus for SouthWest 2 6 sites in Las Vegas for 2248 are part of the POR in Metro Nexus Growth 3 This needs to be updated into the plan
MRTR SLR-New-TEN-Nexus Th-2248 | SW | LAS | TEN | Metro Routers | MRTR SW LAS TEN Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-07-31 | Active | EP
MRTR SLR-New-TEN-Nexus Th-2248 | SW | LAS | TEN | Metro Routers | MRTR SW LAS TEN Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-07-31 | Active | Log | New | SN-0616 | Schedule Change | Approved | 2020-05-29 15:06 | 1 Updating sites missing in Metro Nexus for SouthWest 2 6 sites in Las Vegas for 2248 are part of the POR in Metro Nexus Growth 3 This needs to be updated into the plan
MRTR NCS-Growth-ALI-Nexus Th- 2248 | SW | LAS | ALI | Metro Routers | MRTR SW LAS ALI Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-07-31 | Active | EP
MRTR NCS-Growth-ALI-Nexus Th- 2248 | SW | LAS | ALI | Metro Routers | MRTR SW LAS ALI Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-07-31 | Active | Log | New | SN-0616 | Schedule Change | Approved | 2020-05-29 15:06 | 1 Updating sites missing in Metro Nexus for SouthWest 2 6 sites in Las Vegas for 2248 are part of the POR in Metro Nexus Growth 3 This needs to be updated into the plan
MRTR NCS-Nexus Th-VLY-2248 | SW | LAS | VLY | Metro Routers | MRTR SW LAS VLY Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-07-31 | Active | EP
MRTR NCS-Nexus Th-VLY-2248 | SW | LAS | VLY | Metro Routers | MRTR SW LAS VLY Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-07-31 | Active | Log | New | SN-0616 | Schedule Change | Approved | 2020-05-29 15:06 | 1 Updating sites missing in Metro Nexus for SouthWest 2 6 sites in Las Vegas for 2248 are part of the POR in Metro Nexus Growth 3 This needs to be updated into the plan
MRTR VSR-New-PTH-AAR-ASR9906 | NE | RHD | PTH | Metro Routers | MRTR NE RHD PTH AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2021-02-21 | 2021-02-21 | Deleted | EP
MRTR VSR-New-PTH-AAR-ASR9906 | NE | RHD | PTH | Metro Routers | MRTR NE RHD PTH AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2021-02-21 | 2021-02-21 | Deleted | Log | New | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR VSR-New-ENF-AAR-ASR9906 | NE | CON | ENF | Metro Routers | MRTR NE CON ENF AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2021-02-21 | 2021-02-21 | Deleted | EP
MRTR VSR-New-ENF-AAR-ASR9906 | NE | CON | ENF | Metro Routers | MRTR NE CON ENF AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2021-02-21 | 2021-02-21 | Deleted | Log | New | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR VSR-New-EXT-AAR-ASR9906 | NE | RHD | EXT | Metro Routers | MRTR NE RHD EXT AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2021-02-21 | 2021-02-21 | Deleted | EP
MRTR VSR-New-EXT-AAR-ASR9906 | NE | RHD | EXT | Metro Routers | MRTR NE RHD EXT AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2021-02-21 | 2021-02-21 | Deleted | Log | New | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR VSR-New-MAN-AAR-ASR9906 | NE | CON | MAN | Metro Routers | MRTR NE CON MAN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2021-02-21 | 2021-02-21 | Deleted | EP
MRTR VSR-New-MAN-AAR-ASR9906 | NE | CON | MAN | Metro Routers | MRTR NE CON MAN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-05 | 2021-02-21 | 2021-02-21 | Deleted | Log | New | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR AAR-New-WWK-NEW-AAR-ASR9906 | NE | RHD | WWK | Metro Routers | MRTR NE RHD WWK AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Deleted | EP
MRTR AAR-New-WWK-NEW-AAR-ASR9906 | NE | RHD | WWK | Metro Routers | MRTR NE RHD WWK AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Deleted | Log | New | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR AAR-New-STN-NEW-AAR-ASR9906 | NE | CON | STN | Metro Routers | MRTR NE CON STN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Deleted | EP
MRTR AAR-New-STN-NEW-AAR-ASR9906 | NE | CON | STN | Metro Routers | MRTR NE CON STN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Deleted | Log | New | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR AAR-New-CLV-NEW-AAR-ASR9906 | NE | CLE | CLV | Metro Routers | MRTR NE CLE CLV AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Deleted | EP
MRTR AAR-New-CLV-NEW-AAR-ASR9906 | NE | CLE | CLV | Metro Routers | MRTR NE CLE CLV AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-10-05 | 2020-12-31 | 2021-03-31 | Deleted | Log | New | SN-0638 | Schedule Change | Approved | 2020-06-05 14:50 | Metro Routers POR Update based on Field Migration Dates
MRTR AAR-New-FTS-NEW-AAR | CE | NWA | FTS | Metro Routers | MRTR CE NWA FTS AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | EP
MRTR AAR-New-FTS-NEW-AAR | CE | NWA | FTS | Metro Routers | MRTR CE NWA FTS AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | New | SN-0651 | Scope Change | Approved | 2020-06-14 18:38 | 1 AAR SLR Alignment to support new PON site list new PON roll out and align SLR with AAR deliveries were misaligned post deferrals 2 Total 15 AAR s and 6 SLR s have been added to the Plan 3 Amount is Self Solved as the net addition to plan in Covid 19 and
MRTR SLR-New-CLA-SLR-ASR9906 | CE | TUL | CLA | Metro Routers | MRTR CE TUL CLA SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | EP
MRTR SLR-New-CLA-SLR-ASR9906 | CE | TUL | CLA | Metro Routers | MRTR CE TUL CLA SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-01 | 2020-10-31 | 2020-12-31 | Deleted | Log | New | SN-0651 | Scope Change | Approved | 2020-06-14 18:38 | 1 AAR SLR Alignment to support new PON site list new PON roll out and align SLR with AAR deliveries were misaligned post deferrals 2 Total 15 AAR s and 6 SLR s have been added to the Plan 3 Amount is Self Solved as the net addition to plan in Covid 19 and
MRTR SLR-New-CLA-SLR-ASR9906 | CE | TUL | CLA | Metro Routers | MRTR CE TUL CLA SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis |  |  |  |  | Deleted | Log | Del | SN-0750 | Scope Change | Approved | 2020-07-15 17:23 | This CR removes 6 SLR s from the plan It also adds 11 AAR s to the plan self solve Removal of SLR s nets a 451K giveback to risk
MRTR AAR-New-GAR-NEW-AAR | CE | TUL | GAR | Metro Routers | MRTR CE TUL GAR AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | EP
MRTR AAR-New-GAR-NEW-AAR | CE | TUL | GAR | Metro Routers | MRTR CE TUL GAR AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | New | SN-0651 | Scope Change | Approved | 2020-06-14 18:38 | 1 AAR SLR Alignment to support new PON site list new PON roll out and align SLR with AAR deliveries were misaligned post deferrals 2 Total 15 AAR s and 6 SLR s have been added to the Plan 3 Amount is Self Solved as the net addition to plan in Covid 19 and
MRTR AAR-New-YAL-NEW-AAR | CE | TUL | YAL | Metro Routers | MRTR CE TUL YAL AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | EP
MRTR AAR-New-YAL-NEW-AAR | CE | TUL | YAL | Metro Routers | MRTR CE TUL YAL AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | New | SN-0651 | Scope Change | Approved | 2020-06-14 18:38 | 1 AAR SLR Alignment to support new PON site list new PON roll out and align SLR with AAR deliveries were misaligned post deferrals 2 Total 15 AAR s and 6 SLR s have been added to the Plan 3 Amount is Self Solved as the net addition to plan in Covid 19 and
MRTR AAR-New-SPC-NEW-AAR | SE | BTR | SPC | Metro Routers | MRTR SE BTR SPC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | EP
MRTR AAR-New-SPC-NEW-AAR | SE | BTR | SPC | Metro Routers | MRTR SE BTR SPC AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | New | SN-0651 | Scope Change | Approved | 2020-06-14 18:38 | 1 AAR SLR Alignment to support new PON site list new PON roll out and align SLR with AAR deliveries were misaligned post deferrals 2 Total 15 AAR s and 6 SLR s have been added to the Plan 3 Amount is Self Solved as the net addition to plan in Covid 19 and
MRTR AAR-New-CHS-NEW-AAR | VA | HRD | CHS | Metro Routers | MRTR VA HRD CHS AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | EP
MRTR AAR-New-CHS-NEW-AAR | VA | HRD | CHS | Metro Routers | MRTR VA HRD CHS AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | New | SN-0651 | Scope Change | Approved | 2020-06-14 18:38 | 1 AAR SLR Alignment to support new PON site list new PON roll out and align SLR with AAR deliveries were misaligned post deferrals 2 Total 15 AAR s and 6 SLR s have been added to the Plan 3 Amount is Self Solved as the net addition to plan in Covid 19 and
MRTR AAR-New-DTN-NEW-AAR | CE | TUL | DTN | Metro Routers | MRTR CE TUL DTN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | EP
MRTR AAR-New-DTN-NEW-AAR | CE | TUL | DTN | Metro Routers | MRTR CE TUL DTN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | New | SN-0651 | Scope Change | Approved | 2020-06-14 18:38 | 1 AAR SLR Alignment to support new PON site list new PON roll out and align SLR with AAR deliveries were misaligned post deferrals 2 Total 15 AAR s and 6 SLR s have been added to the Plan 3 Amount is Self Solved as the net addition to plan in Covid 19 and
NEXUS-PNS-2248-02 | SE | GCT | PNS | Metro Routers | MRTR SE GCT PNS Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2021-03-30 | Active | EP
NEXUS-PNS-2248-02 | SE | GCT | PNS | Metro Routers | MRTR SE GCT PNS Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
NEXUS-PNS-2248-02 | SE | GCT | PNS | Metro Routers | MRTR SE GCT PNS Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2020-07-01 | 2020-09-30 | 2021-03-30 | Active | Log | Upd | SN-1037 | Schedule Change | Approved | 2020-11-06 09:51 | Alignment of POR based on feedback from the field
NEXUS-PAR-93180-01 | NE | CLE | PAR | Metro Routers | MRTR NE CLE PAR Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 6 | 2020-08-01 | 2020-10-31 | 2020-12-31 | Active | EP
NEXUS-PAR-93180-01 | NE | CLE | PAR | Metro Routers | MRTR NE CLE PAR Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93180YC-EX Chassis | 6 | 2020-08-01 | 2020-10-31 | 2020-12-31 | Active | Log | New | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
NEXUS-PAR-2248-01 | NE | CLE | PAR | Metro Routers | MRTR NE CLE PAR Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 8 | 2020-08-01 | 2020-10-31 | 2020-12-31 | Active | EP
NEXUS-PAR-2248-01 | NE | CLE | PAR | Metro Routers | MRTR NE CLE PAR Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis | 8 | 2020-08-01 | 2020-10-31 | 2020-12-31 | Active | Log | New | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
MRTR OOB-New-PAR-OOB Server | NE | CLE | PAR | Metro Routers | MRTR NE CLE PAR OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-08-01 | 2020-10-31 | 2020-12-31 | Active | EP
MRTR OOB-New-PAR-OOB Server | NE | CLE | PAR | Metro Routers | MRTR NE CLE PAR OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-08-01 | 2020-10-31 | 2020-12-31 | Active | Log | New | SN-0662 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Changing Activation dates to dates from 5 15 2 Pulling in Migration dates to 2020 3 Adding Pensacola into Nexus Plan 4 Adding Parma plan into Metro outers 5 Elkhorn date change to September
MRTR SLR-New-PAW-AAR-ASR9906 | NE | RHD | PAW | Metro Routers | MRTR NE RHD PAW AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-15 | 2020-11-30 | 2020-12-30 | Active | EP
MRTR SLR-New-PAW-AAR-ASR9906 | NE | RHD | PAW | Metro Routers | MRTR NE RHD PAW AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-15 | 2020-11-30 | 2020-12-30 | Active | Log | New | SN-0750 | Scope Change | Approved | 2020-07-15 17:23 | This CR removes 6 SLR s from the plan It also adds 11 AAR s to the plan self solve Removal of SLR s nets a 451K giveback to risk
MRTR SLR-New-PAW-AAR-ASR9906 | NE | RHD | PAW | Metro Routers | MRTR NE RHD PAW AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-15 | 2020-11-30 | 2020-12-30 | Active | Log | Upd | SN-1037 | Schedule Change | Approved | 2020-11-06 09:51 | Alignment of POR based on feedback from the field
MRTR SLR-New-HEN-AAR-ASR9906 | SW | LAS | HEN | Metro Routers | MRTR SW LAS HEN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-15 | 2020-11-30 | 2020-12-31 | Active | EP
MRTR SLR-New-HEN-AAR-ASR9906 | SW | LAS | HEN | Metro Routers | MRTR SW LAS HEN AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-15 | 2020-11-30 | 2020-12-31 | Active | Log | New | SN-0750 | Scope Change | Approved | 2020-07-15 17:23 | This CR removes 6 SLR s from the plan It also adds 11 AAR s to the plan self solve Removal of SLR s nets a 451K giveback to risk
MRTR SLR-New-IND-AAR-ASR9906 | CE | TUL | IND | Metro Routers | MRTR CE TUL IND AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-15 | 2020-11-30 | 2020-12-31 | Active | EP
MRTR SLR-New-IND-AAR-ASR9906 | CE | TUL | IND | Metro Routers | MRTR CE TUL IND AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-15 | 2020-11-30 | 2020-12-31 | Active | Log | New | SN-0750 | Scope Change | Approved | 2020-07-15 17:23 | This CR removes 6 SLR s from the plan It also adds 11 AAR s to the plan self solve Removal of SLR s nets a 451K giveback to risk
MRTR SLR-New-IND-AAR-ASR9906 | CE | TUL | IND | Metro Routers | MRTR CE TUL IND AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-15 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-1037 | Schedule Change | Approved | 2020-11-06 09:51 | Alignment of POR based on feedback from the field
MRTR SLR-New-CLA-AAR-ASR9906 | CE | TUL | CLA | Metro Routers | MRTR CE TUL CLA AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-15 | 2020-11-30 | 2020-12-31 | Active | EP
MRTR SLR-New-CLA-AAR-ASR9906 | CE | TUL | CLA | Metro Routers | MRTR CE TUL CLA AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-15 | 2020-11-30 | 2020-12-31 | Active | Log | New | SN-0750 | Scope Change | Approved | 2020-07-15 17:23 | This CR removes 6 SLR s from the plan It also adds 11 AAR s to the plan self solve Removal of SLR s nets a 451K giveback to risk
MRTR SLR-New-CLA-AAR-ASR9906 | CE | TUL | CLA | Metro Routers | MRTR CE TUL CLA AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-15 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-1037 | Schedule Change | Approved | 2020-11-06 09:51 | Alignment of POR based on feedback from the field
MRTR SLR-New-SAP-AAR-ASR9906 | CE | TUL | SAP | Metro Routers | MRTR CE TUL SAP AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-15 | 2020-11-30 | 2020-12-31 | Active | EP
MRTR SLR-New-SAP-AAR-ASR9906 | CE | TUL | SAP | Metro Routers | MRTR CE TUL SAP AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-15 | 2020-11-30 | 2020-12-31 | Active | Log | New | SN-0750 | Scope Change | Approved | 2020-07-15 17:23 | This CR removes 6 SLR s from the plan It also adds 11 AAR s to the plan self solve Removal of SLR s nets a 451K giveback to risk
MRTR SLR-New-SAP-AAR-ASR9906 | CE | TUL | SAP | Metro Routers | MRTR CE TUL SAP AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-09-15 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-1037 | Schedule Change | Approved | 2020-11-06 09:51 | Alignment of POR based on feedback from the field
MRTR OOB-New-WRB-OOB Server | SE | MGA | WRB | Metro Routers | MRTR SE MGA WRB OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-31 | 2020-10-31 | 2020-11-30 | Active | EP
MRTR OOB-New-WRB-OOB Server | SE | MGA | WRB | Metro Routers | MRTR SE MGA WRB OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-31 | 2020-10-31 | 2020-11-30 | Active | Log | New | SN-0864 | Scope Change | Approved | 2020-08-21 11:34 | Adding OOB projects to the POR to align with financial plan No monetary updates
MRTR OOB-New-MCN-OOB Server | SE | MGA | MCN | Metro Routers | MRTR SE MGA MCN OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-31 | 2020-10-31 | 2020-11-30 | Active | EP
MRTR OOB-New-MCN-OOB Server | SE | MGA | MCN | Metro Routers | MRTR SE MGA MCN OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-31 | 2020-10-31 | 2020-11-30 | Active | Log | New | SN-0864 | Scope Change | Approved | 2020-08-21 11:34 | Adding OOB projects to the POR to align with financial plan No monetary updates
MRTR OOB-New-CLR-OOB Server | SE | NOR | CLR | Metro Routers | MRTR SE NOR CLR OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-31 | 2020-10-31 | 2020-11-30 | Active | EP
MRTR OOB-New-CLR-OOB Server | SE | NOR | CLR | Metro Routers | MRTR SE NOR CLR OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-31 | 2020-10-31 | 2020-11-30 | Active | Log | New | SN-0864 | Scope Change | Approved | 2020-08-21 11:34 | Adding OOB projects to the POR to align with financial plan No monetary updates
MRTR OOB-New-LPL-OOB Server | SE | NOR | LPL | Metro Routers | MRTR SE NOR LPL OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-31 | 2020-10-31 | 2020-11-30 | Active | EP
MRTR OOB-New-LPL-OOB Server | SE | NOR | LPL | Metro Routers | MRTR SE NOR LPL OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-31 | 2020-10-31 | 2020-11-30 | Active | Log | New | SN-0864 | Scope Change | Approved | 2020-08-21 11:34 | Adding OOB projects to the POR to align with financial plan No monetary updates
MRTR OOB-New-LUL-OOB Server | SE | NOR | LUL | Metro Routers | MRTR SE NOR LUL OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-31 | 2020-10-31 | 2020-11-30 | Active | EP
MRTR OOB-New-LUL-OOB Server | SE | NOR | LUL | Metro Routers | MRTR SE NOR LUL OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-31 | 2020-10-31 | 2020-11-30 | Active | Log | New | SN-0864 | Scope Change | Approved | 2020-08-21 11:34 | Adding OOB projects to the POR to align with financial plan No monetary updates
MRTR OOB-New-NOE-OOB Server | SE | NOR | NOE | Metro Routers | MRTR SE NOR NOE OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-31 | 2020-10-31 | 2020-11-30 | Active | EP
MRTR OOB-New-NOE-OOB Server | SE | NOR | NOE | Metro Routers | MRTR SE NOR NOE OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-31 | 2020-10-31 | 2020-11-30 | Active | Log | New | SN-0864 | Scope Change | Approved | 2020-08-21 11:34 | Adding OOB projects to the POR to align with financial plan No monetary updates
MRTR OOB-New-SPC-OOB Server | SE | BTR | SPC | Metro Routers | MRTR SE BTR SPC OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-31 | 2020-10-31 | 2020-11-30 | Active | EP
MRTR OOB-New-SPC-OOB Server | SE | BTR | SPC | Metro Routers | MRTR SE BTR SPC OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-31 | 2020-10-31 | 2020-11-30 | Active | Log | New | SN-0864 | Scope Change | Approved | 2020-08-21 11:34 | Adding OOB projects to the POR to align with financial plan No monetary updates
MRTR OOB-New-FWB-OOB Server | SE | GCT | FWB | Metro Routers | MRTR SE GCT FWB OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-31 | 2020-10-31 | 2020-11-30 | Active | EP
MRTR OOB-New-FWB-OOB Server | SE | GCT | FWB | Metro Routers | MRTR SE GCT FWB OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-31 | 2020-10-31 | 2020-11-30 | Active | Log | New | SN-0864 | Scope Change | Approved | 2020-08-21 11:34 | Adding OOB projects to the POR to align with financial plan No monetary updates
MRTR SLR-New-PRV-AAR-ASR9906 | NE | RHD | PRV | Metro Routers | MRTR NE RHD PRV AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-15 | 2020-11-30 | 2020-12-30 | Deleted | EP
MRTR SLR-New-PRV-AAR-ASR9906 | NE | RHD | PRV | Metro Routers | MRTR NE RHD PRV AAR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-08-15 | 2020-11-30 | 2020-12-30 | Deleted | Log | New | SN-0867 | Scope Change | Canceled | 2020-10-16 08:53 | Adding projects to the POR based on audit in the field
NEXUS-SPC-2248-01 | SE | BTR | SPC | Metro Routers | MRTR SE BTR SPC Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Deleted | EP
NEXUS-SPC-2248-01 | SE | BTR | SPC | Metro Routers | MRTR SE BTR SPC Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Deleted | Log | New | SN-0893 | Schedule Change | Canceled | 2020-10-16 08:52 | POR updates based on feedback from the field
NEXUS-LFY-2248-01 | SE | LFY | LFY | Metro Routers | MRTR SE LFY LFY Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Deleted | EP
NEXUS-LFY-2248-01 | SE | LFY | LFY | Metro Routers | MRTR SE LFY LFY Metro Nexus Augment POR20 | Chassis | 1x Cisco Nexus 93108TC-EX Chassis | 2 | 2020-08-05 | 2020-10-31 | 2020-12-31 | Deleted | Log | New | SN-0893 | Schedule Change | Canceled | 2020-10-16 08:52 | POR updates based on feedback from the field
MRTR SLR-New-MCN-SLR-ASR9906 | SE | MGA | MCN | Metro Routers | MRTR SE MGA MCN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-12-31 | Active | EP
MRTR SLR-New-MCN-SLR-ASR9906 | SE | MGA | MCN | Metro Routers | MRTR SE MGA MCN SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-12-31 | Active | Log | New | SN-1037 | Schedule Change | Approved | 2020-11-06 09:51 | Alignment of POR based on feedback from the field
MRTR SLR-New-DGL-SLR-ASR9906 | SW | ARZ | DGL | Metro Routers | MRTR SW ARZ DGL SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-12-31 | Active | EP
MRTR SLR-New-DGL-SLR-ASR9906 | SW | ARZ | DGL | Metro Routers | MRTR SW ARZ DGL SLR Deployment POR20 | Chassis | 1x Cisco ASR 9906 Chassis | 2 | 2020-05-15 | 2020-07-31 | 2020-12-31 | Active | Log | New | SN-1037 | Schedule Change | Approved | 2020-11-06 09:51 | Alignment of POR based on feedback from the field
MTRN-AVJ-TNCS/TNCSO-01 | CA | ORG | AVJ | Metro Transport | MTRN CA ORG AVJ DWDM Deployment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-02-03 | 2020-05-01 | 2020-06-01 | Active | EP
MTRN-AVJ-TNCS/TNCSO-01 | CA | ORG | AVJ | Metro Transport | MTRN CA ORG AVJ DWDM Deployment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-02-03 | 2020-05-01 | 2020-06-01 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-DNP-TNCS/TNCSO-01 | CA | ORG | DNP | Metro Transport | MTRN CA ORG DNP DWDM Deployment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-02-03 | 2020-05-01 | 2020-06-01 | Active | EP
MTRN-DNP-TNCS/TNCSO-01 | CA | ORG | DNP | Metro Transport | MTRN CA ORG DNP DWDM Deployment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-02-03 | 2020-05-01 | 2020-06-01 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-IRV-TNCS/TNCSO-01 | CA | ORG | IRV | Metro Transport | MTRN CA ORG IRV DWDM Deployment POR20 | Card & Optics | TNCS/TNCSO | 4 | 2020-02-03 | 2020-05-01 | 2020-06-01 | Active | EP
MTRN-IRV-TNCS/TNCSO-01 | CA | ORG | IRV | Metro Transport | MTRN CA ORG IRV DWDM Deployment POR20 | Card & Optics | TNCS/TNCSO | 4 | 2020-02-03 | 2020-05-01 | 2020-06-01 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-ORG-TNCS/TNCSO-01 | CA | ORG | ORG | Metro Transport | MTRN CA ORG ORG T5 Card Augment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-02-03 | 2020-05-01 | 2020-06-01 | Active | EP
MTRN-ORG-TNCS/TNCSO-01 | CA | ORG | ORG | Metro Transport | MTRN CA ORG ORG T5 Card Augment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-02-03 | 2020-05-01 | 2020-06-01 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-RSM-TNCS/TNCSO-01 | CA | ORG | RSM | Metro Transport | MTRN CA ORG RSM T5 Card Augment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-02-03 | 2020-05-01 | 2020-06-01 | Active | EP
MTRN-RSM-TNCS/TNCSO-01 | CA | ORG | RSM | Metro Transport | MTRN CA ORG RSM T5 Card Augment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-02-03 | 2020-05-01 | 2020-06-01 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-ALP-TNCS/TNCSO-01 | CA | SAN | ALP | Metro Transport | MTRN CA SAN ALP DWDM Deployment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-02-03 | 2020-05-01 | 2020-06-01 | Active | EP
MTRN-ALP-TNCS/TNCSO-01 | CA | SAN | ALP | Metro Transport | MTRN CA SAN ALP DWDM Deployment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-02-03 | 2020-05-01 | 2020-06-01 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-CHU-TNCS/TNCSO-01 | CA | SAN | CHU | Metro Transport | MTRN CA SAN CHU DWDM-OLS Deployment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-02-03 | 2020-05-01 | 2020-06-01 | Active | EP
MTRN-CHU-TNCS/TNCSO-01 | CA | SAN | CHU | Metro Transport | MTRN CA SAN CHU DWDM-OLS Deployment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-02-03 | 2020-05-01 | 2020-06-01 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-DWN-TNCS/TNCSO-01 | CA | SAN | DWN | Metro Transport | MTRN CA SAN DWN DWDM-OLS Deployment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | EP
MTRN-DWN-TNCS/TNCSO-01 | CA | SAN | DWN | Metro Transport | MTRN CA SAN DWN DWDM-OLS Deployment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-ELC-TNCS/TNCSO-01 | CA | SAN | ELC | Metro Transport | MTRN CA SAN ELC DWDM-OLS Deployment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | EP
MTRN-ELC-TNCS/TNCSO-01 | CA | SAN | ELC | Metro Transport | MTRN CA SAN ELC DWDM-OLS Deployment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-ESC-TNCS/TNCSO-01 | CA | SAN | ESC | Metro Transport | MTRN CA SAN ESC DWDM-OLS Deployment POR20 | Card & Optics | TNCS/TNCSO | 3 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | EP
MTRN-ESC-TNCS/TNCSO-01 | CA | SAN | ESC | Metro Transport | MTRN CA SAN ESC DWDM-OLS Deployment POR20 | Card & Optics | TNCS/TNCSO | 3 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-FED-TNCS/TNCSO-01 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED DWDM-OLS Deployment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | EP
MTRN-FED-TNCS/TNCSO-01 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED DWDM-OLS Deployment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-OCE-TNCS/TNCSO-01 | CA | SAN | OCE | Metro Transport | MTRN CA SAN OCE DWDM-OLS Deployment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | EP
MTRN-OCE-TNCS/TNCSO-01 | CA | SAN | OCE | Metro Transport | MTRN CA SAN OCE DWDM-OLS Deployment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-PWY-TNCS/TNCSO-01 | CA | SAN | PWY | Metro Transport | MTRN CA SAN PWY DWDM-OLS Deployment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | EP
MTRN-PWY-TNCS/TNCSO-01 | CA | SAN | PWY | Metro Transport | MTRN CA SAN PWY DWDM-OLS Deployment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-VST-TNCS/TNCSO-01 | CA | SAN | VST | Metro Transport | MTRN CA SAN VST DWDM-OLS Deployment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | EP
MTRN-VST-TNCS/TNCSO-01 | CA | SAN | VST | Metro Transport | MTRN CA SAN VST DWDM-OLS Deployment POR20 | Card & Optics | TNCS/TNCSO | 2 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-BER-M15 | CE | NWA | BER | Metro Transport | MTRN CE NWA BER DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-BER-M15 | CE | NWA | BER | Metro Transport | MTRN CE NWA BER DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-BER-M15 | CE | NWA | BER | Metro Transport | MTRN CE NWA BER DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-BER-M15 | CE | NWA | BER | Metro Transport | MTRN CE NWA BER DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-BER-M15 | CE | NWA | BER | Metro Transport | MTRN CE NWA BER DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-BER-M6 | CE | NWA | BER | Metro Transport | MTRN CE NWA BER DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-BER-M6 | CE | NWA | BER | Metro Transport | MTRN CE NWA BER DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-BER-M6 | CE | NWA | BER | Metro Transport | MTRN CE NWA BER DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-BER-M6 | CE | NWA | BER | Metro Transport | MTRN CE NWA BER DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-BER-M6 | CE | NWA | BER | Metro Transport | MTRN CE NWA BER DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-BVL-M15 | CE | NWA | BVL | Metro Transport | MTRN CE NWA BVL DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-BVL-M15 | CE | NWA | BVL | Metro Transport | MTRN CE NWA BVL DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-BVL-M15 | CE | NWA | BVL | Metro Transport | MTRN CE NWA BVL DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-BVL-M15 | CE | NWA | BVL | Metro Transport | MTRN CE NWA BVL DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-BVL-M15 | CE | NWA | BVL | Metro Transport | MTRN CE NWA BVL DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-BVL-M6 | CE | NWA | BVL | Metro Transport | MTRN CE NWA BVL DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 3 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-BVL-M6 | CE | NWA | BVL | Metro Transport | MTRN CE NWA BVL DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-BVL-M6 | CE | NWA | BVL | Metro Transport | MTRN CE NWA BVL DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-BVL-M6 | CE | NWA | BVL | Metro Transport | MTRN CE NWA BVL DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 3 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-BVL-M6 | CE | NWA | BVL | Metro Transport | MTRN CE NWA BVL DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 3 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-FAY-M15 | CE | NWA | FAY | Metro Transport | MTRN CE NWA FAY DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-FAY-M15 | CE | NWA | FAY | Metro Transport | MTRN CE NWA FAY DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-FAY-M15 | CE | NWA | FAY | Metro Transport | MTRN CE NWA FAY DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-FAY-M15 | CE | NWA | FAY | Metro Transport | MTRN CE NWA FAY DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-FAY-M15 | CE | NWA | FAY | Metro Transport | MTRN CE NWA FAY DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-FAY-M6 | CE | NWA | FAY | Metro Transport | MTRN CE NWA FAY DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 3 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-FAY-M6 | CE | NWA | FAY | Metro Transport | MTRN CE NWA FAY DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 3 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-FAY-M6 | CE | NWA | FAY | Metro Transport | MTRN CE NWA FAY DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 3 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-FAY-M6 | CE | NWA | FAY | Metro Transport | MTRN CE NWA FAY DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 3 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-FAY-M6 | CE | NWA | FAY | Metro Transport | MTRN CE NWA FAY DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 3 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-FTS-M15 | CE | NWA | FTS | Metro Transport | MTRN CE NWA FTS DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-FTS-M15 | CE | NWA | FTS | Metro Transport | MTRN CE NWA FTS DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-FTS-M15 | CE | NWA | FTS | Metro Transport | MTRN CE NWA FTS DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-FTS-M15 | CE | NWA | FTS | Metro Transport | MTRN CE NWA FTS DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-FTS-M15 | CE | NWA | FTS | Metro Transport | MTRN CE NWA FTS DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-FTS-M6 | CE | NWA | FTS | Metro Transport | MTRN CE NWA FTS DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-FTS-M6 | CE | NWA | FTS | Metro Transport | MTRN CE NWA FTS DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-FTS-M6 | CE | NWA | FTS | Metro Transport | MTRN CE NWA FTS DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-FTS-M6 | CE | NWA | FTS | Metro Transport | MTRN CE NWA FTS DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-FTS-M6 | CE | NWA | FTS | Metro Transport | MTRN CE NWA FTS DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-HRN-M15 | CE | NWA | HRN | Metro Transport | MTRN CE NWA HRN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-HRN-M15 | CE | NWA | HRN | Metro Transport | MTRN CE NWA HRN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-HRN-M15 | CE | NWA | HRN | Metro Transport | MTRN CE NWA HRN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-HRN-M15 | CE | NWA | HRN | Metro Transport | MTRN CE NWA HRN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-HRN-M15 | CE | NWA | HRN | Metro Transport | MTRN CE NWA HRN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-HRN-M6 | CE | NWA | HRN | Metro Transport | MTRN CE NWA HRN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-HRN-M6 | CE | NWA | HRN | Metro Transport | MTRN CE NWA HRN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-HRN-M6 | CE | NWA | HRN | Metro Transport | MTRN CE NWA HRN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-HRN-M6 | CE | NWA | HRN | Metro Transport | MTRN CE NWA HRN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-HRN-M6 | CE | NWA | HRN | Metro Transport | MTRN CE NWA HRN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-NWA-M15 | CE | NWA | NWA | Metro Transport | MTRN CE NWA NWA DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 3 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-NWA-M15 | CE | NWA | NWA | Metro Transport | MTRN CE NWA NWA DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 4 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-NWA-M15 | CE | NWA | NWA | Metro Transport | MTRN CE NWA NWA DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 4 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-NWA-M15 | CE | NWA | NWA | Metro Transport | MTRN CE NWA NWA DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 3 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-NWA-M15 | CE | NWA | NWA | Metro Transport | MTRN CE NWA NWA DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 3 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-NWA-M6 | CE | NWA | NWA | Metro Transport | MTRN CE NWA NWA DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 4 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-NWA-M6 | CE | NWA | NWA | Metro Transport | MTRN CE NWA NWA DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 3 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-NWA-M6 | CE | NWA | NWA | Metro Transport | MTRN CE NWA NWA DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 3 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-NWA-M6 | CE | NWA | NWA | Metro Transport | MTRN CE NWA NWA DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 4 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-NWA-M6 | CE | NWA | NWA | Metro Transport | MTRN CE NWA NWA DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 4 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-SSP-M15 | CE | NWA | SSP | Metro Transport | MTRN CE NWA SSP DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-SSP-M15 | CE | NWA | SSP | Metro Transport | MTRN CE NWA SSP DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-SSP-M15 | CE | NWA | SSP | Metro Transport | MTRN CE NWA SSP DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-SSP-M15 | CE | NWA | SSP | Metro Transport | MTRN CE NWA SSP DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-SSP-M15 | CE | NWA | SSP | Metro Transport | MTRN CE NWA SSP DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-SSP-M6 | CE | NWA | SSP | Metro Transport | MTRN CE NWA SSP DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-SSP-M6 | CE | NWA | SSP | Metro Transport | MTRN CE NWA SSP DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-SSP-M6 | CE | NWA | SSP | Metro Transport | MTRN CE NWA SSP DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-SSP-M6 | CE | NWA | SSP | Metro Transport | MTRN CE NWA SSP DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-SSP-M6 | CE | NWA | SSP | Metro Transport | MTRN CE NWA SSP DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-VBN-M15 | CE | NWA | VBN | Metro Transport | MTRN CE NWA VBN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-VBN-M15 | CE | NWA | VBN | Metro Transport | MTRN CE NWA VBN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-VBN-M15 | CE | NWA | VBN | Metro Transport | MTRN CE NWA VBN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-VBN-M15 | CE | NWA | VBN | Metro Transport | MTRN CE NWA VBN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-VBN-M15 | CE | NWA | VBN | Metro Transport | MTRN CE NWA VBN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-VBN-M6 | CE | NWA | VBN | Metro Transport | MTRN CE NWA VBN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-VBN-M6 | CE | NWA | VBN | Metro Transport | MTRN CE NWA VBN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-VBN-M6 | CE | NWA | VBN | Metro Transport | MTRN CE NWA VBN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-VBN-M6 | CE | NWA | VBN | Metro Transport | MTRN CE NWA VBN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-VBN-M6 | CE | NWA | VBN | Metro Transport | MTRN CE NWA VBN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Metro OTN-CLH-Ciena 6500 S2 | CE | OKC | CLH | Metro Transport | MTRN CE OKC CLH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | EP
Metro OTN-CLH-Ciena 6500 S2 | CE | OKC | CLH | Metro Transport | MTRN CE OKC CLH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-CLH-Ciena 6500 S14 | CE | OKC | CLH | Metro Transport | MTRN CE OKC CLH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | EP
Metro OTN-CLH-Ciena 6500 S14 | CE | OKC | CLH | Metro Transport | MTRN CE OKC CLH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-STNGVASU-Ciena 6500 S2 | VA | NVA | STNGVASU | Metro Transport | MTRN CA SAN VST AIS OTN_OLS Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis |  |  |  |  | Deleted | EP
Metro OTN-STNGVASU-Ciena 6500 S2 | VA | NVA | STNGVASU | Metro Transport | MTRN CA SAN VST AIS OTN_OLS Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-03 | 2020-05-01 | 2020-06-01 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-STNGVASU-Ciena 6500 S2 | VA | NVA | STNGVASU | Metro Transport | MTRN CA SAN VST AIS OTN_OLS Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis |  |  |  |  | Deleted | Log | Del | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-STNGVASU-Ciena 6500 S14 | VA | NVA | STNGVASU | Metro Transport | MTRN CA SAN VST AIS OTN_OLS Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis |  |  |  |  | Deleted | EP
Metro OTN-STNGVASU-Ciena 6500 S14 | VA | NVA | STNGVASU | Metro Transport | MTRN CA SAN VST AIS OTN_OLS Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 2 | 2020-02-03 | 2020-05-01 | 2020-06-01 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-STNGVASU-Ciena 6500 S14 | VA | NVA | STNGVASU | Metro Transport | MTRN CA SAN VST AIS OTN_OLS Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis |  |  |  |  | Deleted | Log | Del | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-MCLNVA23-Ciena 6500 S14 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED EdgeConnex OTN_OLS Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | EP
Metro OTN-MCLNVA23-Ciena 6500 S14 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED EdgeConnex OTN_OLS Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-MCLNVA23-Ciena 6500 S2 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED EdgeConnex OTN_OLS Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | EP
Metro OTN-MCLNVA23-Ciena 6500 S2 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED EdgeConnex OTN_OLS Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-KGGRVAAS-Ciena 6500 S14 | VA | NVA | KGGRVAAS | Metro Transport | MTRN CA SAN FED Level-3 OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis |  |  |  |  | Deleted | EP
Metro OTN-KGGRVAAS-Ciena 6500 S14 | VA | NVA | KGGRVAAS | Metro Transport | MTRN CA SAN FED Level-3 OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 2 | 2020-02-03 | 2020-05-15 | 2020-06-15 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-KGGRVAAS-Ciena 6500 S14 | VA | NVA | KGGRVAAS | Metro Transport | MTRN CA SAN FED Level-3 OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis |  |  |  |  | Deleted | Log | Del | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-KGGRVAAS-Ciena 6500 S2 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED Level-3 OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis |  |  |  |  | Deleted | EP
Metro OTN-KGGRVAAS-Ciena 6500 S2 | VA | NVA | KGGRVAAS | Metro Transport | MTRN CA SAN FED Level-3 OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-03 | 2020-05-15 | 2020-06-15 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-KGGRVAAS-Ciena 6500 S2 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED Level-3 OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-03 | 2020-05-15 | 2020-06-15 | Deleted | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-KGGRVAAS-Ciena 6500 S2 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED Level-3 OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis |  |  |  |  | Deleted | Log | Del | SN-0774 | Scope Change | Approved | 2020-07-27 09:32 | Aligning POR based on feedback from FTPMs
Metro OTN-ASBNVADZ-Ciena 6500 S14 | VA | NVA | ASBNVADZ | Metro Transport | MTRN CA SAN FED SharpHlth OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis |  |  |  |  | Deleted | EP
Metro OTN-ASBNVADZ-Ciena 6500 S14 | VA | NVA | ASBNVADZ | Metro Transport | MTRN CA SAN FED SharpHlth OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 2 | 2020-02-03 | 2020-05-15 | 2020-06-15 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-ASBNVADZ-Ciena 6500 S14 | VA | NVA | ASBNVADZ | Metro Transport | MTRN CA SAN FED SharpHlth OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis |  |  |  |  | Deleted | Log | Del | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-ASBNVADZ-Ciena 6500 S2 | VA | NVA | ASBNVADZ | Metro Transport | MTRN CA SAN FED SharpHlth OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis |  |  |  |  | Deleted | EP
Metro OTN-ASBNVADZ-Ciena 6500 S2 | VA | NVA | ASBNVADZ | Metro Transport | MTRN CA SAN FED SharpHlth OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-03 | 2020-05-15 | 2020-06-15 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-ASBNVADZ-Ciena 6500 S2 | VA | NVA | ASBNVADZ | Metro Transport | MTRN CA SAN FED SharpHlth OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis |  |  |  |  | Deleted | Log | Del | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Photonic-OTN-LV2-AAA-M15 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN LSVRNV12 DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-LV2-AAA-M15 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN LSVRNV12 DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV2-AAA-M15 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN LSVRNV12 DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Deleted | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV2-AAA-M15 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN LSVRNV12 DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-LV2-AAA-M6 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN LSVRNV12 DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-LV2-AAA-M6 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN LSVRNV12 DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV2-AAA-M6 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN LSVRNV12 DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Deleted | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV2-AAA-M6 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN LSVRNV12 DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-LV2-BBB-M15 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN ATTM-Core DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-LV2-BBB-M15 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN ATTM-Core DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV2-BBB-M15 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN ATTM-Core DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Deleted | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV2-BBB-M15 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN ATTM-Core DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-LV2-BBB-M6 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN ATTM-Core DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-LV2-BBB-M6 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN ATTM-Core DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV2-BBB-M6 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN ATTM-Core DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Deleted | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV2-BBB-M6 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN ATTM-Core DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-LV2-CCC-M15 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN LSVUNV01 DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-LV2-CCC-M15 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN LSVUNV01 DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV2-CCC-M15 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN LSVUNV01 DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Deleted | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV2-CCC-M15 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN LSVUNV01 DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-LV2-CCC-M6 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN LSVUNV01 DWDM Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-LV2-CCC-M6 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN LSVUNV01 DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV2-CCC-M6 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN LSVUNV01 DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Deleted | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV2-CCC-M6 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN LSVUNV01 DWDM Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis |  |  |  |  | Deleted | Log | Del | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-LV2-DDD-M15 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN LSVONVGK DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-LV2-DDD-M15 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN LSVONVGK DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV2-DDD-M15 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN LSVONVGK DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Deleted | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV2-DDD-M15 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN LSVONVGK DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-LV2-DDD-M6 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN LSVONVGK DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-LV2-DDD-M6 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN LSVONVGK DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 3 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV2-DDD-M6 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN LSVONVGK DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 3 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Deleted | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV2-DDD-M6 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN LSVONVGK DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-III-M15 | CE | NWA | FAY | Metro Transport | MTRN CE NWA FAY Evansville DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 1 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-III-M15 | CE | NWA | FAY | Metro Transport | MTRN CE NWA FAY Evansville DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 0 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-III-M15 | CE | NWA | FAY | Metro Transport | MTRN CE NWA FAY Evansville DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 0 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-III-M15 | CE | NWA | FAY | Metro Transport | MTRN CE NWA FAY Evansville DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 1 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0589 | Schedule Change | Approved | 2020-05-14 14:36 | Cleaning up one Entry in POR for Transport that was submitted
Photonic-OTN-III-M15 | CE | NWA | FAY | Metro Transport | MTRN CE NWA FAY Evansville DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 1 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-III-M15 | CE | NWA | FAY | Metro Transport | MTRN CE NWA FAY Evansville DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 1 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-III-M6 | CE | NWA | FAY | Metro Transport | MTRN CE NWA FAY Evansville DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-III-M6 | CE | NWA | FAY | Metro Transport | MTRN CE NWA FAY Evansville DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-III-M6 | CE | NWA | FAY | Metro Transport | MTRN CE NWA FAY Evansville DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-III-M6 | CE | NWA | FAY | Metro Transport | MTRN CE NWA FAY Evansville DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-III-M6 | CE | NWA | FAY | Metro Transport | MTRN CE NWA FAY Evansville DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-JJJ-M15 | CE | NWA | FAY | Metro Transport | MTRN CE NWA FAY Kingston DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-JJJ-M15 | CE | NWA | FAY | Metro Transport | MTRN CE NWA FAY Kingston DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-JJJ-M15 | CE | NWA | FAY | Metro Transport | MTRN CE NWA FAY Kingston DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-JJJ-M15 | CE | NWA | FAY | Metro Transport | MTRN CE NWA FAY Kingston DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-JJJ-M15 | CE | NWA | FAY | Metro Transport | MTRN CE NWA FAY Kingston DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-JJJ-M6 | CE | NWA | FAY | Metro Transport | MTRN CE NWA FAY Kingston DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 1 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-JJJ-M6 | CE | NWA | FAY | Metro Transport | MTRN CE NWA FAY Kingston DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-JJJ-M6 | CE | NWA | FAY | Metro Transport | MTRN CE NWA FAY Kingston DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-JJJ-M6 | CE | NWA | FAY | Metro Transport | MTRN CE NWA FAY Kingston DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 1 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-JJJ-M6 | CE | NWA | FAY | Metro Transport | MTRN CE NWA FAY Kingston DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 1 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Metro OTN-ILH-Ciena 6500 S14 | CE | OKC | ILH | Metro Transport | MTRN CE OKC ILH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | EP
Metro OTN-ILH-Ciena 6500 S14 | CE | OKC | ILH | Metro Transport | MTRN CE OKC ILH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-ILH-Ciena 6500 S2 | CE | OKC | ILH | Metro Transport | MTRN CE OKC ILH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | EP
Metro OTN-ILH-Ciena 6500 S2 | CE | OKC | ILH | Metro Transport | MTRN CE OKC ILH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-MOO-Ciena 6500 S14 | CE | OKC | MOO | Metro Transport | MTRN CE OKC MOO OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | EP
Metro OTN-MOO-Ciena 6500 S14 | CE | OKC | MOO | Metro Transport | MTRN CE OKC MOO OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-MOO-Ciena 6500 S2 | CE | OKC | MOO | Metro Transport | MTRN CE OKC MOO OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | EP
Metro OTN-MOO-Ciena 6500 S2 | CE | OKC | MOO | Metro Transport | MTRN CE OKC MOO OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-MWC-Ciena 6500 S14 | CE | OKC | MWC | Metro Transport | MTRN CE OKC MWC OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | EP
Metro OTN-MWC-Ciena 6500 S14 | CE | OKC | MWC | Metro Transport | MTRN CE OKC MWC OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-MWC-Ciena 6500 S2 | CE | OKC | MWC | Metro Transport | MTRN CE OKC MWC OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | EP
Metro OTN-MWC-Ciena 6500 S2 | CE | OKC | MWC | Metro Transport | MTRN CE OKC MWC OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-NCH-Ciena 6500 S14 | CE | OKC | NCH | Metro Transport | MTRN CE OKC NCH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | EP
Metro OTN-NCH-Ciena 6500 S14 | CE | OKC | NCH | Metro Transport | MTRN CE OKC NCH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-NCH-Ciena 6500 S2 | CE | OKC | NCH | Metro Transport | MTRN CE OKC NCH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | EP
Metro OTN-NCH-Ciena 6500 S2 | CE | OKC | NCH | Metro Transport | MTRN CE OKC NCH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-NEH-Ciena 6500 S14 | CE | OKC | NEH | Metro Transport | MTRN CE OKC NEH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | EP
Metro OTN-NEH-Ciena 6500 S14 | CE | OKC | NEH | Metro Transport | MTRN CE OKC NEH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-NEH-Ciena 6500 S14 | CE | OKC | NEH | Metro Transport | MTRN CE OKC NEH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-NEH-Ciena 6500 S2 | CE | OKC | NEH | Metro Transport | MTRN CE OKC NEH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | EP
Metro OTN-NEH-Ciena 6500 S2 | CE | OKC | NEH | Metro Transport | MTRN CE OKC NEH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-NEH-Ciena 6500 S2 | CE | OKC | NEH | Metro Transport | MTRN CE OKC NEH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-NOR-Ciena 6500 S14 | CE | OKC | NOR | Metro Transport | MTRN CE OKC NOR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | EP
Metro OTN-NOR-Ciena 6500 S14 | CE | OKC | NOR | Metro Transport | MTRN CE OKC NOR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-NOR-Ciena 6500 S14 | CE | OKC | NOR | Metro Transport | MTRN CE OKC NOR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-NOR-Ciena 6500 S2 | CE | OKC | NOR | Metro Transport | MTRN CE OKC NOR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 4 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | EP
Metro OTN-NOR-Ciena 6500 S2 | CE | OKC | NOR | Metro Transport | MTRN CE OKC NOR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 4 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-NOR-Ciena 6500 S2 | CE | OKC | NOR | Metro Transport | MTRN CE OKC NOR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 4 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-OKC-Ciena 6500 S14 | CE | OKC | OKC | Metro Transport | MTRN CE OKC OKC OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis |  |  |  |  | Deleted | EP
Metro OTN-OKC-Ciena 6500 S14 | CE | OKC | OKC | Metro Transport | MTRN CE OKC OKC OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis |  |  |  |  | Deleted | Log | Del | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-OKC-Ciena 6500 S2 | CE | OKC | OKC | Metro Transport | MTRN CE OKC OKC OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 1 | 2020-01-31 | 2020-03-15 | 2020-05-15 | Active | EP
Metro OTN-SEH-Ciena 6500 S14 | CE | OKC | SEH | Metro Transport | MTRN CE OKC SEH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | EP
Metro OTN-SEH-Ciena 6500 S14 | CE | OKC | SEH | Metro Transport | MTRN CE OKC SEH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-SEH-Ciena 6500 S2 | CE | OKC | SEH | Metro Transport | MTRN CE OKC SEH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | EP
Metro OTN-SEH-Ciena 6500 S2 | CE | OKC | SEH | Metro Transport | MTRN CE OKC SEH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-SRH-Ciena 6500 S14 | CE | OKC | SRH | Metro Transport | MTRN CE OKC SRH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis |  |  |  |  | Deleted | EP
Metro OTN-SRH-Ciena 6500 S14 | CE | OKC | SRH | Metro Transport | MTRN CE OKC SRH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis |  |  |  |  | Deleted | Log | Del | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-SRH-Ciena 6500 S2 | CE | OKC | SRH | Metro Transport | MTRN CE OKC SRH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | EP
Metro OTN-SRH-Ciena 6500 S2 | CE | OKC | SRH | Metro Transport | MTRN CE OKC SRH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-WEH-Ciena 6500 S14 | CE | OKC | WEH | Metro Transport | MTRN CE OKC WEH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis |  |  |  |  | Deleted | EP
Metro OTN-WEH-Ciena 6500 S14 | CE | OKC | WEH | Metro Transport | MTRN CE OKC WEH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis |  |  |  |  | Deleted | Log | Del | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-WEH-Ciena 6500 S2 | CE | OKC | WEH | Metro Transport | MTRN CE OKC WEH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis |  |  |  |  | Deleted | EP
Metro OTN-WEH-Ciena 6500 S2 | CE | OKC | WEH | Metro Transport | MTRN CE OKC WEH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis |  |  |  |  | Deleted | Log | Del | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-WLH-Ciena 6500 S14 | CE | OKC | WLH | Metro Transport | MTRN CE OKC WLH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | EP
Metro OTN-WLH-Ciena 6500 S14 | CE | OKC | WLH | Metro Transport | MTRN CE OKC WLH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-WLH-Ciena 6500 S14 | CE | OKC | WLH | Metro Transport | MTRN CE OKC WLH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-WLH-Ciena 6500 S2 | CE | OKC | WLH | Metro Transport | MTRN CE OKC WLH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | EP
Metro OTN-WLH-Ciena 6500 S2 | CE | OKC | WLH | Metro Transport | MTRN CE OKC WLH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-WLH-Ciena 6500 S2 | CE | OKC | WLH | Metro Transport | MTRN CE OKC WLH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-WLK-Ciena 6500 S14 | CE | OKC | WLK | Metro Transport | MTRN CE OKC WLK OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | EP
Metro OTN-WLK-Ciena 6500 S14 | CE | OKC | WLK | Metro Transport | MTRN CE OKC WLK OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-WLK-Ciena 6500 S2 | CE | OKC | WLK | Metro Transport | MTRN CE OKC WLK OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 4 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | EP
Metro OTN-WLK-Ciena 6500 S2 | CE | OKC | WLK | Metro Transport | MTRN CE OKC WLK OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 4 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-ENF-Ciena 6500 S2 | NE | CON | ENF | Metro Transport | MTRN NE CON ENF OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | EP
Metro OTN-ENF-Ciena 6500 S2 | NE | CON | ENF | Metro Transport | MTRN NE CON ENF OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-01-20 | 2020-03-01 | 2020-05-01 | Active | Log | Upd | SN-0053 | New | Approved | 2020-02-06 10:22 | Metro Transport POR Correction to align with Initial POI
Metro OTN-ENF-Ciena 6500 S2 | NE | CON | ENF | Metro Transport | MTRN NE CON ENF OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-ENF-Ciena 6500 S2 | NE | CON | ENF | Metro Transport | MTRN NE CON ENF OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-ENF-Ciena 6500 S14 | NE | CON | ENF | Metro Transport | MTRN NE CON ENF OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | EP
Metro OTN-ENF-Ciena 6500 S14 | NE | CON | ENF | Metro Transport | MTRN NE CON ENF OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-01-20 | 2020-03-01 | 2020-05-01 | Active | Log | Upd | SN-0053 | New | Approved | 2020-02-06 10:22 | Metro Transport POR Correction to align with Initial POI
Metro OTN-ENF-Ciena 6500 S14 | NE | CON | ENF | Metro Transport | MTRN NE CON ENF OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-ENF-Ciena 6500 S14 | NE | CON | ENF | Metro Transport | MTRN NE CON ENF OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Photonic-OTN-ENF-M15 | NE | CON | ENF | Metro Transport | MTRN NE CON ENF DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-ENF-M15 | NE | CON | ENF | Metro Transport | MTRN NE CON ENF DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-ENF-M15 | NE | CON | ENF | Metro Transport | MTRN NE CON ENF DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-ENF-M6 | NE | CON | ENF | Metro Transport | MTRN NE CON ENF DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-ENF-M6 | NE | CON | ENF | Metro Transport | MTRN NE CON ENF DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 3 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-ENF-M6 | NE | CON | ENF | Metro Transport | MTRN NE CON ENF DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-GLB-M15 | NE | CON | GLB | Metro Transport | MTRN NE CON GLB DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-GLB-M15 | NE | CON | GLB | Metro Transport | MTRN NE CON GLB DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-GLB-M15 | NE | CON | GLB | Metro Transport | MTRN NE CON GLB DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-GLB-M6 | NE | CON | GLB | Metro Transport | MTRN NE CON GLB DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-GLB-M6 | NE | CON | GLB | Metro Transport | MTRN NE CON GLB DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-GLB-M6 | NE | CON | GLB | Metro Transport | MTRN NE CON GLB DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Metro OTN-GLB-Ciena 6500 S2 | NE | CON | GLB | Metro Transport | MTRN NE CON GLB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | EP
Metro OTN-GLB-Ciena 6500 S2 | NE | CON | GLB | Metro Transport | MTRN NE CON GLB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-01-20 | 2020-03-01 | 2020-05-01 | Active | Log | Upd | SN-0053 | New | Approved | 2020-02-06 10:22 | Metro Transport POR Correction to align with Initial POI
Metro OTN-GLB-Ciena 6500 S2 | NE | CON | GLB | Metro Transport | MTRN NE CON GLB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-GLB-Ciena 6500 S2 | NE | CON | GLB | Metro Transport | MTRN NE CON GLB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-GLB-Ciena 6500 S14 | NE | CON | GLB | Metro Transport | MTRN NE CON GLB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | EP
Metro OTN-GLB-Ciena 6500 S14 | NE | CON | GLB | Metro Transport | MTRN NE CON GLB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-01-20 | 2020-03-01 | 2020-05-01 | Active | Log | Upd | SN-0053 | New | Approved | 2020-02-06 10:22 | Metro Transport POR Correction to align with Initial POI
Metro OTN-GLB-Ciena 6500 S14 | NE | CON | GLB | Metro Transport | MTRN NE CON GLB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-GLB-Ciena 6500 S14 | NE | CON | GLB | Metro Transport | MTRN NE CON GLB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-GRB-Ciena 6500 S2 | NE | CON | GRB | Metro Transport | MTRN NE CON GRB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | EP
Metro OTN-GRB-Ciena 6500 S2 | NE | CON | GRB | Metro Transport | MTRN NE CON GRB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-01-20 | 2020-03-01 | 2020-05-01 | Active | Log | Upd | SN-0053 | New | Approved | 2020-02-06 10:22 | Metro Transport POR Correction to align with Initial POI
Metro OTN-GRB-Ciena 6500 S2 | NE | CON | GRB | Metro Transport | MTRN NE CON GRB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-03-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-GRB-Ciena 6500 S2 | NE | CON | GRB | Metro Transport | MTRN NE CON GRB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-GRB-Ciena 6500 S14 | NE | CON | GRB | Metro Transport | MTRN NE CON GRB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | EP
Metro OTN-GRB-Ciena 6500 S14 | NE | CON | GRB | Metro Transport | MTRN NE CON GRB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-01-20 | 2020-03-01 | 2020-05-01 | Active | Log | Upd | SN-0053 | New | Approved | 2020-02-06 10:22 | Metro Transport POR Correction to align with Initial POI
Metro OTN-GRB-Ciena 6500 S14 | NE | CON | GRB | Metro Transport | MTRN NE CON GRB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-03-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-GRB-Ciena 6500 S14 | NE | CON | GRB | Metro Transport | MTRN NE CON GRB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Photonic-OTN-GRB-M15 | NE | CON | GRB | Metro Transport | MTRN NE CON GRB DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-GRB-M15 | NE | CON | GRB | Metro Transport | MTRN NE CON GRB DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-GRB-M15 | NE | CON | GRB | Metro Transport | MTRN NE CON GRB DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-GRB-M6 | NE | CON | GRB | Metro Transport | MTRN NE CON GRB DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-GRB-M6 | NE | CON | GRB | Metro Transport | MTRN NE CON GRB DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-GRB-M6 | NE | CON | GRB | Metro Transport | MTRN NE CON GRB DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-MAN-M15 | NE | CON | MAN | Metro Transport | MTRN NE CON MAN 100 Gig Grow Augment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-MAN-M15 | NE | CON | MAN | Metro Transport | MTRN NE CON MAN 100 Gig Grow Augment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-MAN-M15 | NE | CON | MAN | Metro Transport | MTRN NE CON MAN 100 Gig Grow Augment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-MAN-M6 | NE | CON | MAN | Metro Transport | MTRN NE CON MAN 100 Gig Grow Augment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-MAN-M6 | NE | CON | MAN | Metro Transport | MTRN NE CON MAN 100 Gig Grow Augment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 4 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-MAN-M6 | NE | CON | MAN | Metro Transport | MTRN NE CON MAN 100 Gig Grow Augment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Metro OTN-MAN-Ciena 6500 S32 | NE | CON | MAN | Metro Transport | MTRN NE CON MAN OTN Deployment POR20 | Chassis | 1x Ciena 6500 S32 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | EP
Metro OTN-MAN-Ciena 6500 S32 | NE | CON | MAN | Metro Transport | MTRN NE CON MAN OTN Deployment POR20 | Chassis | 1x Ciena 6500 S32 Chassis | 1 | 2020-01-20 | 2020-03-01 | 2020-05-01 | Active | Log | Upd | SN-0053 | New | Approved | 2020-02-06 10:22 | Metro Transport POR Correction to align with Initial POI
Metro OTN-MAN-Ciena 6500 S32 | NE | CON | MAN | Metro Transport | MTRN NE CON MAN OTN Deployment POR20 | Chassis | 1x Ciena 6500 S32 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-MAN-Ciena 6500 S32 | NE | CON | MAN | Metro Transport | MTRN NE CON MAN OTN Deployment POR20 | Chassis | 1x Ciena 6500 S32 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-MAN-Ciena 6500 S2 | NE | CON | MAN | Metro Transport | MTRN NE CON MAN OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 4 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | EP
Metro OTN-MAN-Ciena 6500 S2 | NE | CON | MAN | Metro Transport | MTRN NE CON MAN OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 4 | 2020-01-20 | 2020-03-01 | 2020-05-01 | Active | Log | Upd | SN-0053 | New | Approved | 2020-02-06 10:22 | Metro Transport POR Correction to align with Initial POI
Metro OTN-MAN-Ciena 6500 S2 | NE | CON | MAN | Metro Transport | MTRN NE CON MAN OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 4 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-MAN-Ciena 6500 S2 | NE | CON | MAN | Metro Transport | MTRN NE CON MAN OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 4 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
MTRN-MCY- T5-01 | SE | NOR | MCY | Metro Transport | MTRN SE NOR MCY T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-04-15 | 2020-05-15 | Active | EP
MTRN-MCY- T5-01 | SE | NOR | MCY | Metro Transport | MTRN SE NOR MCY T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-01 | 2020-02-01 | 2020-02-01 | Active | Log | Upd | SN-0053 | New | Approved | 2020-02-06 10:22 | Metro Transport POR Correction to align with Initial POI
MTRN-MCY- T5-01 | SE | NOR | MCY | Metro Transport | MTRN SE NOR MCY T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-MCY- T5-01 | SE | NOR | MCY | Metro Transport | MTRN SE NOR MCY T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-04-15 | 2020-05-15 | Active | Log | Upd | SN-0154 | Schedule Change | Approved | 2020-02-06 11:13 | 1 INP had initially the growth request against PAPA forecast from September 2 May of these have changed and in order to meet the demand before capacity exhaust we need to accelerate several projects from Q2 to Q1 3 780K pulled in from Q2 to Q1 4 Workin
MTRN-SPC- T5-01 | SE | BTR | SPC | Metro Transport | MTRN SE BTR SPC T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-04-01 | 2020-05-01 | Active | EP
MTRN-SPC- T5-01 | SE | BTR | SPC | Metro Transport | MTRN SE BTR SPC T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-01 | 2020-03-01 | 2020-03-01 | Active | Log | Upd | SN-0053 | New | Approved | 2020-02-06 10:22 | Metro Transport POR Correction to align with Initial POI
MTRN-SPC- T5-01 | SE | BTR | SPC | Metro Transport | MTRN SE BTR SPC T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-02-17 | 2020-04-01 | 2020-05-01 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-SPC- T5-01 | SE | BTR | SPC | Metro Transport | MTRN SE BTR SPC T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-04-01 | 2020-05-01 | Active | Log | Upd | SN-0154 | Schedule Change | Approved | 2020-02-06 11:13 | 1 INP had initially the growth request against PAPA forecast from September 2 May of these have changed and in order to meet the demand before capacity exhaust we need to accelerate several projects from Q2 to Q1 3 780K pulled in from Q2 to Q1 4 Workin
MTRN-LPL- T5-01 | SE | NOR | LPL | Metro Transport | MTRN SE NOR LPL T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-05-15 | 2020-06-15 | Active | EP
MTRN-LPL- T5-01 | SE | NOR | LPL | Metro Transport | MTRN SE NOR LPL T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-01 | 2020-02-01 | 2020-02-01 | Active | Log | Upd | SN-0053 | New | Approved | 2020-02-06 10:22 | Metro Transport POR Correction to align with Initial POI
MTRN-LPL- T5-01 | SE | NOR | LPL | Metro Transport | MTRN SE NOR LPL T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-LPL- T5-01 | SE | NOR | LPL | Metro Transport | MTRN SE NOR LPL T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0154 | Schedule Change | Approved | 2020-02-06 11:13 | 1 INP had initially the growth request against PAPA forecast from September 2 May of these have changed and in order to meet the demand before capacity exhaust we need to accelerate several projects from Q2 to Q1 3 780K pulled in from Q2 to Q1 4 Workin
MTRN-GNS- T5-01 | SE | GAN | GNS | Metro Transport | MTRN SE GAN GNS T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-01 | 2020-02-01 | 2020-02-01 | Active | EP
MTRN-GNS- T5-01 | SE | GAN | GNS | Metro Transport | MTRN SE GAN GNS T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-01 | 2020-02-01 | 2020-02-01 | Active | Log | Upd | SN-0053 | New | Approved | 2020-02-06 10:22 | Metro Transport POR Correction to align with Initial POI
MTRN-OCL- T5-01 | SE | GAN | OCL | Metro Transport | MTRN SE GAN OCL T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-01 | 2020-02-01 | 2020-02-01 | Active | EP
MTRN-OCL- T5-01 | SE | GAN | OCL | Metro Transport | MTRN SE GAN OCL T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-01 | 2020-02-01 | 2020-02-01 | Active | Log | Upd | SN-0053 | New | Approved | 2020-02-06 10:22 | Metro Transport POR Correction to align with Initial POI
MTRN-BTR- T5-01 | SE | BTR | BTR | Metro Transport | MTRN SE BTR BTR T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-04-15 | 2020-05-15 | Active | EP
MTRN-BTR- T5-01 | SE | BTR | BTR | Metro Transport | MTRN SE BTR BTR T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-01 | 2020-02-01 | 2020-02-01 | Active | Log | Upd | SN-0053 | New | Approved | 2020-02-06 10:22 | Metro Transport POR Correction to align with Initial POI
MTRN-BTR- T5-01 | SE | BTR | BTR | Metro Transport | MTRN SE BTR BTR T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-02-17 | 2020-04-01 | 2020-05-01 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-BTR- T5-01 | SE | BTR | BTR | Metro Transport | MTRN SE BTR BTR T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-04-15 | 2020-05-15 | Active | Log | Upd | SN-0154 | Schedule Change | Approved | 2020-02-06 11:13 | 1 INP had initially the growth request against PAPA forecast from September 2 May of these have changed and in order to meet the demand before capacity exhaust we need to accelerate several projects from Q2 to Q1 3 780K pulled in from Q2 to Q1 4 Workin
MTRN-ELM- T5-01 | SE | NOR | ELM | Metro Transport | MTRN SE NOR ELM T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-05-15 | 2020-06-15 | Active | EP
MTRN-ELM- T5-01 | SE | NOR | ELM | Metro Transport | MTRN SE NOR ELM T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-01 | 2020-02-01 | 2020-02-01 | Active | Log | Upd | SN-0053 | New | Approved | 2020-02-06 10:22 | Metro Transport POR Correction to align with Initial POI
MTRN-ELM- T5-01 | SE | NOR | ELM | Metro Transport | MTRN SE NOR ELM T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-ELM- T5-01 | SE | NOR | ELM | Metro Transport | MTRN SE NOR ELM T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0154 | Schedule Change | Approved | 2020-02-06 11:13 | 1 INP had initially the growth request against PAPA forecast from September 2 May of these have changed and in order to meet the demand before capacity exhaust we need to accelerate several projects from Q2 to Q1 3 780K pulled in from Q2 to Q1 4 Workin
Photonic-OTN-LV2-ALI-M15 | SW | LAS | ALI | Metro Transport | MTRN SW LAS ALI DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-LV2-ALI-M15 | SW | LAS | ALI | Metro Transport | MTRN SW LAS ALI DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV2-ALI-M15 | SW | LAS | ALI | Metro Transport | MTRN SW LAS ALI DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV2-ALI-M15 | SW | LAS | ALI | Metro Transport | MTRN SW LAS ALI DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-LV2-ALI-M15 | SW | LAS | ALI | Metro Transport | MTRN SW LAS ALI DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-LV2-ALI-M6 | SW | LAS | ALI | Metro Transport | MTRN SW LAS ALI DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-LV2-ALI-M6 | SW | LAS | ALI | Metro Transport | MTRN SW LAS ALI DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV2-ALI-M6 | SW | LAS | ALI | Metro Transport | MTRN SW LAS ALI DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV2-ALI-M6 | SW | LAS | ALI | Metro Transport | MTRN SW LAS ALI DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-LV2-ALI-M6 | SW | LAS | ALI | Metro Transport | MTRN SW LAS ALI DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-LV2-BLU-M15 | SW | LAS | BLU | Metro Transport | MTRN SW LAS BLU DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-LV2-BLU-M15 | SW | LAS | BLU | Metro Transport | MTRN SW LAS BLU DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV2-BLU-M15 | SW | LAS | BLU | Metro Transport | MTRN SW LAS BLU DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Deleted | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV2-BLU-M15 | SW | LAS | BLU | Metro Transport | MTRN SW LAS BLU DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-LV2-BLU-M6 | SW | LAS | BLU | Metro Transport | MTRN SW LAS BLU DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-LV2-BLU-M6 | SW | LAS | BLU | Metro Transport | MTRN SW LAS BLU DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 3 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV2-BLU-M6 | SW | LAS | BLU | Metro Transport | MTRN SW LAS BLU DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 3 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Deleted | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV2-BLU-M6 | SW | LAS | BLU | Metro Transport | MTRN SW LAS BLU DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-LV2-CEN-M15 | SW | LAS | CEN | Metro Transport | MTRN SW LAS CEN DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-LV2-CEN-M15 | SW | LAS | CEN | Metro Transport | MTRN SW LAS CEN DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV2-CEN-M15 | SW | LAS | CEN | Metro Transport | MTRN SW LAS CEN DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Deleted | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV2-CEN-M15 | SW | LAS | CEN | Metro Transport | MTRN SW LAS CEN DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-LV2-CEN-M6 | SW | LAS | CEN | Metro Transport | MTRN SW LAS CEN DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-LV2-CEN-M6 | SW | LAS | CEN | Metro Transport | MTRN SW LAS CEN DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 4 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV2-CEN-M6 | SW | LAS | CEN | Metro Transport | MTRN SW LAS CEN DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 4 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Deleted | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV2-CEN-M6 | SW | LAS | CEN | Metro Transport | MTRN SW LAS CEN DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-LV2-CEST3-M15 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-LV2-CEST3-M15 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV2-CEST3-M15 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Deleted | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV2-CEST3-M15 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-LV2-CEST3-M6 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-LV2-CEST3-M6 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 1 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV2-CEST3-M6 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 1 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Deleted | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV2-CEST3-M6 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-LV2-ERN-M15 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-LV2-ERN-M15 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV2-ERN-M15 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Deleted | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV2-ERN-M15 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-LV2-ERN-M6 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-LV2-ERN-M6 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV2-ERN-M6 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Deleted | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV2-ERN-M6 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-LV2-HEN-M15 | SW | LAS | HEN | Metro Transport | MTRN SW LAS HEN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-LV2-HEN-M15 | SW | LAS | HEN | Metro Transport | MTRN SW LAS HEN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 3 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV2-HEN-M15 | SW | LAS | HEN | Metro Transport | MTRN SW LAS HEN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 3 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Deleted | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV2-HEN-M15 | SW | LAS | HEN | Metro Transport | MTRN SW LAS HEN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-LV2-HEN-M6 | SW | LAS | HEN | Metro Transport | MTRN SW LAS HEN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-LV2-HEN-M6 | SW | LAS | HEN | Metro Transport | MTRN SW LAS HEN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV2-HEN-M6 | SW | LAS | HEN | Metro Transport | MTRN SW LAS HEN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Deleted | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV2-HEN-M6 | SW | LAS | HEN | Metro Transport | MTRN SW LAS HEN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-LV2-TEN-M15 | SW | LAS | TEN | Metro Transport | MTRN SW LAS TEN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-LV2-TEN-M15 | SW | LAS | TEN | Metro Transport | MTRN SW LAS TEN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV2-TEN-M15 | SW | LAS | TEN | Metro Transport | MTRN SW LAS TEN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Deleted | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV2-TEN-M15 | SW | LAS | TEN | Metro Transport | MTRN SW LAS TEN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-LV2-TEN-M6 | SW | LAS | TEN | Metro Transport | MTRN SW LAS TEN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-LV2-TEN-M6 | SW | LAS | TEN | Metro Transport | MTRN SW LAS TEN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 3 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV2-TEN-M6 | SW | LAS | TEN | Metro Transport | MTRN SW LAS TEN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 3 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Deleted | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV2-TEN-M6 | SW | LAS | TEN | Metro Transport | MTRN SW LAS TEN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-LV2-VLY-M15 | SW | LAS | VLY | Metro Transport | MTRN SW LAS VLY DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-LV2-VLY-M15 | SW | LAS | VLY | Metro Transport | MTRN SW LAS VLY DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV2-VLY-M15 | SW | LAS | VLY | Metro Transport | MTRN SW LAS VLY DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Deleted | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV2-VLY-M15 | SW | LAS | VLY | Metro Transport | MTRN SW LAS VLY DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-LV2-VLY-M6 | SW | LAS | VLY | Metro Transport | MTRN SW LAS VLY DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-LV2-VLY-M6 | SW | LAS | VLY | Metro Transport | MTRN SW LAS VLY DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 3 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV2-VLY-M6 | SW | LAS | VLY | Metro Transport | MTRN SW LAS VLY DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 3 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Deleted | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV2-VLY-M6 | SW | LAS | VLY | Metro Transport | MTRN SW LAS VLY DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
MTRN-nrf-DWDM-upgrade-01 | VA | HRD | NRF | Metro Transport | MTRN VA HRD NRF DWDM Deployment POR20 | Card & Optics | DWDM-upgrade | 2 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | EP
MTRN-nrf-DWDM-upgrade-01 | VA | HRD | NRF | Metro Transport | MTRN VA HRD NRF DWDM Deployment POR20 | Card & Optics | DWDM-upgrade | 2 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | Log | Upd | SN-0774 | Scope Change | Approved | 2020-07-27 09:32 | Aligning POR based on feedback from FTPMs
MTRN-vbc-DWDM-upgrade-01 | VA | HRD | VBC | Metro Transport | MTRN VA HRD VBC DWDM Deployment POR20 | Card & Optics | DWDM-upgrade | 2 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | EP
MTRN-vbc-DWDM-upgrade-01 | VA | HRD | VBC | Metro Transport | MTRN VA HRD VBC DWDM Deployment POR20 | Card & Optics | DWDM-upgrade | 2 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | Log | Upd | SN-0774 | Scope Change | Approved | 2020-07-27 09:32 | Aligning POR based on feedback from FTPMs
Metro OTN-DRA-Ciena 6500 S14 | VA | NVA | DRA | Metro Transport | MTRN VA NVA DRA OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | EP
Metro OTN-DRA-Ciena 6500 S14 | VA | NVA | DRA | Metro Transport | MTRN VA NVA DRA OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-DRA-Ciena 6500 S14 | VA | NVA | DRA | Metro Transport | MTRN VA NVA DRA OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-DRA-Ciena 6500 S2 | VA | NVA | DRA | Metro Transport | MTRN VA NVA DRA OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | EP
Metro OTN-DRA-Ciena 6500 S2 | VA | NVA | DRA | Metro Transport | MTRN VA NVA DRA OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-DRA-Ciena 6500 S2 | VA | NVA | DRA | Metro Transport | MTRN VA NVA DRA OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-FBG-Ciena 6500 S2 | VA | NVA | FBG | Metro Transport | MTRN VA NVA FBG OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | EP
Metro OTN-FBG-Ciena 6500 S2 | VA | NVA | FBG | Metro Transport | MTRN VA NVA FBG OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-FBG-Ciena 6500 S14 | VA | NVA | FBG | Metro Transport | MTRN VA NVA FBG OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | EP
Metro OTN-FBG-Ciena 6500 S14 | VA | NVA | FBG | Metro Transport | MTRN VA NVA FBG OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-FLK-Ciena 6500 S2 | VA | NVA | FLK | Metro Transport | MTRN VA NVA FLK OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 4 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | EP
Metro OTN-FLK-Ciena 6500 S2 | VA | NVA | FLK | Metro Transport | MTRN VA NVA FLK OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 4 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-FLK-Ciena 6500 S14 | VA | NVA | FLK | Metro Transport | MTRN VA NVA FLK OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | EP
Metro OTN-FLK-Ciena 6500 S14 | VA | NVA | FLK | Metro Transport | MTRN VA NVA FLK OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-FST-Ciena 6500 S2 | VA | NVA | FST | Metro Transport | MTRN VA NVA FST OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | EP
Metro OTN-FST-Ciena 6500 S2 | VA | NVA | FST | Metro Transport | MTRN VA NVA FST OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-FST-Ciena 6500 S2 | VA | NVA | FST | Metro Transport | MTRN VA NVA FST OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-FST-Ciena 6500 S14 | VA | NVA | FST | Metro Transport | MTRN VA NVA FST OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | EP
Metro OTN-FST-Ciena 6500 S14 | VA | NVA | FST | Metro Transport | MTRN VA NVA FST OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-FST-Ciena 6500 S14 | VA | NVA | FST | Metro Transport | MTRN VA NVA FST OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-GCR-Ciena 6500 S14 | VA | NVA | GCR | Metro Transport | MTRN VA NVA GCR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | EP
Metro OTN-GCR-Ciena 6500 S14 | VA | NVA | GCR | Metro Transport | MTRN VA NVA GCR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-GCR-Ciena 6500 S2 | VA | NVA | GCR | Metro Transport | MTRN VA NVA GCR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | EP
Metro OTN-GCR-Ciena 6500 S2 | VA | NVA | GCR | Metro Transport | MTRN VA NVA GCR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-RHL-Ciena 6500 S14 | VA | NVA | RHL | Metro Transport | MTRN VA NVA RHL OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | EP
Metro OTN-RHL-Ciena 6500 S14 | VA | NVA | RHL | Metro Transport | MTRN VA NVA RHL OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-RHL-Ciena 6500 S2 | VA | NVA | RHL | Metro Transport | MTRN VA NVA RHL OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | EP
Metro OTN-RHL-Ciena 6500 S2 | VA | NVA | RHL | Metro Transport | MTRN VA NVA RHL OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-TCR-Ciena 6500 S14 | VA | NVA | TCR | Metro Transport | MTRN VA NVA TCR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | EP
Metro OTN-TCR-Ciena 6500 S14 | VA | NVA | TCR | Metro Transport | MTRN VA NVA TCR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-TCR-Ciena 6500 S2 | VA | NVA | TCR | Metro Transport | MTRN VA NVA TCR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | EP
Metro OTN-TCR-Ciena 6500 S2 | VA | NVA | TCR | Metro Transport | MTRN VA NVA TCR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
MTRN-TEN- T5-01 | SW | LAS | TEN | Metro Transport | MTRN SW LAS TEN T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-20 | 2020-02-01 | 2020-02-01 | Active | EP
MTRN-TEN- T5-01 | SW | LAS | TEN | Metro Transport | MTRN SW LAS TEN T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-20 | 2020-02-01 | 2020-02-01 | Active | Log | Upd | SN-0154 | Schedule Change | Approved | 2020-02-06 11:13 | 1 INP had initially the growth request against PAPA forecast from September 2 May of these have changed and in order to meet the demand before capacity exhaust we need to accelerate several projects from Q2 to Q1 3 780K pulled in from Q2 to Q1 4 Workin
MTRN-TEN- T5-03 | SW | LAS | TEN | Metro Transport | MTRN SW LAS TEN T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-20 | 2020-02-01 | 2020-02-01 | Active | EP
MTRN-TEN- T5-03 | SW | LAS | TEN | Metro Transport | MTRN SW LAS TEN T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-06-20 | 2020-07-01 |  | Active | Log | Upd | SN-0053 | New | Approved | 2020-02-06 10:22 | Metro Transport POR Correction to align with Initial POI
MTRN-TEN- T5-03 | SW | LAS | TEN | Metro Transport | MTRN SW LAS TEN T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-20 | 2020-02-01 | 2020-02-01 | Active | Log | Upd | SN-0154 | Schedule Change | Approved | 2020-02-06 11:13 | 1 INP had initially the growth request against PAPA forecast from September 2 May of these have changed and in order to meet the demand before capacity exhaust we need to accelerate several projects from Q2 to Q1 3 780K pulled in from Q2 to Q1 4 Workin
MTRN-TEN- T5-04 | SW | LAS | TEN | Metro Transport | MTRN SW LAS TEN T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-20 | 2020-02-01 | 2020-02-01 | Active | EP
MTRN-TEN- T5-04 | SW | LAS | TEN | Metro Transport | MTRN SW LAS TEN T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-20 | 2020-02-01 | 2020-02-01 | Active | Log | Upd | SN-0154 | Schedule Change | Approved | 2020-02-06 11:13 | 1 INP had initially the growth request against PAPA forecast from September 2 May of these have changed and in order to meet the demand before capacity exhaust we need to accelerate several projects from Q2 to Q1 3 780K pulled in from Q2 to Q1 4 Workin
Photonic-OTN-LV1-TEN-M15 | SW | LAS | TEN | Metro Transport | MTRN SW LAS TEN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 4 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-LV1-TEN-M15 | SW | LAS | TEN | Metro Transport | MTRN SW LAS TEN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV1-TEN-M15 | SW | LAS | TEN | Metro Transport | MTRN SW LAS TEN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV1-TEN-M15 | SW | LAS | TEN | Metro Transport | MTRN SW LAS TEN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 4 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-LV1-TEN-M15 | SW | LAS | TEN | Metro Transport | MTRN SW LAS TEN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 4 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-LV1-TEN-M6 | SW | LAS | TEN | Metro Transport | MTRN SW LAS TEN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 3 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-LV1-TEN-M6 | SW | LAS | TEN | Metro Transport | MTRN SW LAS TEN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV1-TEN-M6 | SW | LAS | TEN | Metro Transport | MTRN SW LAS TEN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV1-TEN-M6 | SW | LAS | TEN | Metro Transport | MTRN SW LAS TEN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 3 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-LV1-TEN-M6 | SW | LAS | TEN | Metro Transport | MTRN SW LAS TEN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 3 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-LV1-VLY-M15 | SW | LAS | VLY | Metro Transport | MTRN SW LAS VLY DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-LV1-VLY-M15 | SW | LAS | VLY | Metro Transport | MTRN SW LAS VLY DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV1-VLY-M15 | SW | LAS | VLY | Metro Transport | MTRN SW LAS VLY DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV1-VLY-M15 | SW | LAS | VLY | Metro Transport | MTRN SW LAS VLY DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-LV1-VLY-M15 | SW | LAS | VLY | Metro Transport | MTRN SW LAS VLY DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-LV1-VLY-M6 | SW | LAS | VLY | Metro Transport | MTRN SW LAS VLY DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-LV1-VLY-M6 | SW | LAS | VLY | Metro Transport | MTRN SW LAS VLY DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV1-VLY-M6 | SW | LAS | VLY | Metro Transport | MTRN SW LAS VLY DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV1-VLY-M6 | SW | LAS | VLY | Metro Transport | MTRN SW LAS VLY DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-LV1-VLY-M6 | SW | LAS | VLY | Metro Transport | MTRN SW LAS VLY DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
MTRN-NRF- T5-01 | VA | HRD | NRF | Metro Transport | MTRN VA HRD NRF T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | EP
MTRN-NRF- T5-01 | VA | HRD | NRF | Metro Transport | MTRN VA HRD NRF T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0053 | New | Approved | 2020-02-06 10:22 | Metro Transport POR Correction to align with Initial POI
MTRN-NRF- T5-01 | VA | HRD | NRF | Metro Transport | MTRN VA HRD NRF T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-NRF- T5-02 | VA | HRD | NRF | Metro Transport | MTRN VA HRD NRF T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | EP
MTRN-NRF- T5-02 | VA | HRD | NRF | Metro Transport | MTRN VA HRD NRF T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0053 | New | Approved | 2020-02-06 10:22 | Metro Transport POR Correction to align with Initial POI
MTRN-NRF- T5-02 | VA | HRD | NRF | Metro Transport | MTRN VA HRD NRF T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-vbc- T5-01 | VA | HRD | VBC | Metro Transport | MTRN VA HRD VBC T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | EP
MTRN-vbc- T5-01 | VA | HRD | VBC | Metro Transport | MTRN VA HRD VBC T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0053 | New | Approved | 2020-02-06 10:22 | Metro Transport POR Correction to align with Initial POI
MTRN-vbc- T5-01 | VA | HRD | VBC | Metro Transport | MTRN VA HRD VBC T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-VBC- T5-02 | VA | HRD | VBC | Metro Transport | MTRN VA HRD VBC T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | EP
MTRN-VBC- T5-02 | VA | HRD | VBC | Metro Transport | MTRN VA HRD VBC T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0053 | New | Approved | 2020-02-06 10:22 | Metro Transport POR Correction to align with Initial POI
MTRN-VBC- T5-02 | VA | HRD | VBC | Metro Transport | MTRN VA HRD VBC T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-FED-M15 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 4 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-FED-M15 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-FED-M15 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-FED-M15 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 4 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-FED-M15 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 4 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-FED-M6 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 4 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-FED-M6 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 4 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-FED-M6 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 4 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-FED-M6 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 4 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-FED-M6 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 4 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-OCE-M15 | CA | SAN | OCE | Metro Transport | MTRN CA SAN OCE DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-OCE-M15 | CA | SAN | OCE | Metro Transport | MTRN CA SAN OCE DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-OCE-M15 | CA | SAN | OCE | Metro Transport | MTRN CA SAN OCE DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-OCE-M15 | CA | SAN | OCE | Metro Transport | MTRN CA SAN OCE DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-OCE-M15 | CA | SAN | OCE | Metro Transport | MTRN CA SAN OCE DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-OCE-M6 | CA | SAN | OCE | Metro Transport | MTRN CA SAN OCE DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-OCE-M6 | CA | SAN | OCE | Metro Transport | MTRN CA SAN OCE DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-OCE-M6 | CA | SAN | OCE | Metro Transport | MTRN CA SAN OCE DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-OCE-M6 | CA | SAN | OCE | Metro Transport | MTRN CA SAN OCE DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-OCE-M6 | CA | SAN | OCE | Metro Transport | MTRN CA SAN OCE DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-PWY-M15 | CA | SAN | PWY | Metro Transport | MTRN CA SAN PWY DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-PWY-M15 | CA | SAN | PWY | Metro Transport | MTRN CA SAN PWY DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-PWY-M15 | CA | SAN | PWY | Metro Transport | MTRN CA SAN PWY DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-PWY-M15 | CA | SAN | PWY | Metro Transport | MTRN CA SAN PWY DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-PWY-M15 | CA | SAN | PWY | Metro Transport | MTRN CA SAN PWY DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-PWY-M6 | CA | SAN | PWY | Metro Transport | MTRN CA SAN PWY DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-PWY-M6 | CA | SAN | PWY | Metro Transport | MTRN CA SAN PWY DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-PWY-M6 | CA | SAN | PWY | Metro Transport | MTRN CA SAN PWY DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-PWY-M6 | CA | SAN | PWY | Metro Transport | MTRN CA SAN PWY DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-PWY-M6 | CA | SAN | PWY | Metro Transport | MTRN CA SAN PWY DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-VST-M15 | CA | SAN | VST | Metro Transport | MTRN CA SAN VST DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-VST-M15 | CA | SAN | VST | Metro Transport | MTRN CA SAN VST DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-VST-M15 | CA | SAN | VST | Metro Transport | MTRN CA SAN VST DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-VST-M15 | CA | SAN | VST | Metro Transport | MTRN CA SAN VST DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-VST-M15 | CA | SAN | VST | Metro Transport | MTRN CA SAN VST DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-VST-M6 | CA | SAN | VST | Metro Transport | MTRN CA SAN VST DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-VST-M6 | CA | SAN | VST | Metro Transport | MTRN CA SAN VST DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-VST-M6 | CA | SAN | VST | Metro Transport | MTRN CA SAN VST DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-VST-M6 | CA | SAN | VST | Metro Transport | MTRN CA SAN VST DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-VST-M6 | CA | SAN | VST | Metro Transport | MTRN CA SAN VST DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Metro OTN-BRD-Ciena 6500 S14 | CE | TUL | BRD | Metro Transport | MTRN CE TUL BRD OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-06-30 | 2020-08-30 | Active | EP
Metro OTN-BRD-Ciena 6500 S14 | CE | TUL | BRD | Metro Transport | MTRN CE TUL BRD OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-01-31 | 2020-03-15 | 2020-05-15 | Active | Log | Upd | SN-0053 | New | Approved | 2020-02-06 10:22 | Metro Transport POR Correction to align with Initial POI
Metro OTN-BRD-Ciena 6500 S14 | CE | TUL | BRD | Metro Transport | MTRN CE TUL BRD OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-06-30 | 2020-08-30 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-BRD-Ciena 6500 S2 | CE | TUL | BRD | Metro Transport | MTRN CE TUL BRD OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-06-30 | 2020-08-30 | Active | EP
Metro OTN-BRD-Ciena 6500 S2 | CE | TUL | BRD | Metro Transport | MTRN CE TUL BRD OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-01-31 | 2020-03-15 | 2020-05-15 | Active | Log | Upd | SN-0053 | New | Approved | 2020-02-06 10:22 | Metro Transport POR Correction to align with Initial POI
Metro OTN-BRD-Ciena 6500 S2 | CE | TUL | BRD | Metro Transport | MTRN CE TUL BRD OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-06-30 | 2020-08-30 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-BAR-Ciena 6500 S14 | CE | TUL | BAR | Metro Transport | MTRN CE TUL BAR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-06-30 | 2020-08-30 | Active | EP
Metro OTN-BAR-Ciena 6500 S14 | CE | TUL | BAR | Metro Transport | MTRN CE TUL BAR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-01-31 | 2020-03-15 | 2020-05-15 | Active | Log | Upd | SN-0053 | New | Approved | 2020-02-06 10:22 | Metro Transport POR Correction to align with Initial POI
Metro OTN-BAR-Ciena 6500 S14 | CE | TUL | BAR | Metro Transport | MTRN CE TUL BAR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-06-30 | 2020-08-30 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-BAR-Ciena 6500 S2 | CE | TUL | BAR | Metro Transport | MTRN CE TUL BAR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-06-30 | 2020-08-30 | Active | EP
Metro OTN-BAR-Ciena 6500 S2 | CE | TUL | BAR | Metro Transport | MTRN CE TUL BAR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-01-31 | 2020-03-15 | 2020-05-15 | Active | Log | Upd | SN-0053 | New | Approved | 2020-02-06 10:22 | Metro Transport POR Correction to align with Initial POI
Metro OTN-BAR-Ciena 6500 S2 | CE | TUL | BAR | Metro Transport | MTRN CE TUL BAR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-06-30 | 2020-08-30 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-CLA-Ciena 6500 S14 | CE | TUL | CLA | Metro Transport | MTRN CE TUL CLA OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-06-30 | 2020-08-30 | Active | EP
Metro OTN-CLA-Ciena 6500 S14 | CE | TUL | CLA | Metro Transport | MTRN CE TUL CLA OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-01-31 | 2020-03-01 | 2020-05-01 | Active | Log | Upd | SN-0053 | New | Approved | 2020-02-06 10:22 | Metro Transport POR Correction to align with Initial POI
Metro OTN-CLA-Ciena 6500 S14 | CE | TUL | CLA | Metro Transport | MTRN CE TUL CLA OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-06-30 | 2020-08-30 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-CLA-Ciena 6500 S2 | CE | TUL | CLA | Metro Transport | MTRN CE TUL CLA OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-06-30 | 2020-08-30 | Active | EP
Metro OTN-CLA-Ciena 6500 S2 | CE | TUL | CLA | Metro Transport | MTRN CE TUL CLA OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-01-31 | 2020-03-01 | 2020-05-01 | Active | Log | Upd | SN-0053 | New | Approved | 2020-02-06 10:22 | Metro Transport POR Correction to align with Initial POI
Metro OTN-CLA-Ciena 6500 S2 | CE | TUL | CLA | Metro Transport | MTRN CE TUL CLA OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-06-30 | 2020-08-30 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-GAR-Ciena 6500 S14 | CE | TUL | GAR | Metro Transport | MTRN CE TUL GAR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-06-01 | 2020-08-01 | Active | EP
Metro OTN-GAR-Ciena 6500 S2 | CE | TUL | GAR | Metro Transport | MTRN CE TUL GAR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-06-01 | 2020-08-01 | Active | EP
Metro OTN-IND-Ciena 6500 S14 | CE | TUL | IND | Metro Transport | MTRN CE TUL IND OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-06-01 | 2020-08-01 | Active | EP
Metro OTN-IND-Ciena 6500 S2 | CE | TUL | IND | Metro Transport | MTRN CE TUL IND OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-04-15 | 2020-06-01 | 2020-08-01 | Active | EP
MTRN-RSM- T5-02 | CA | ORG | RSM | Metro Transport | MTRN CA ORG RSM T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-02-03 | 2020-05-01 | 2020-06-01 | Active | EP
MTRN-RSM- T5-02 | CA | ORG | RSM | Metro Transport | MTRN CA ORG RSM T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-06-01 | 2020-06-01 | Active | Log | Upd | SN-0053 | New | Approved | 2020-02-06 10:22 | Metro Transport POR Correction to align with Initial POI
MTRN-RSM- T5-02 | CA | ORG | RSM | Metro Transport | MTRN CA ORG RSM T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-02-03 | 2020-05-01 | 2020-06-01 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-CHU-M15 | CA | SAN | CHU | Metro Transport | MTRN CA SAN CHU DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-CHU-M15 | CA | SAN | CHU | Metro Transport | MTRN CA SAN CHU DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-CHU-M15 | CA | SAN | CHU | Metro Transport | MTRN CA SAN CHU DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-CHU-M15 | CA | SAN | CHU | Metro Transport | MTRN CA SAN CHU DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-CHU-M15 | CA | SAN | CHU | Metro Transport | MTRN CA SAN CHU DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-CHU-M6 | CA | SAN | CHU | Metro Transport | MTRN CA SAN CHU DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-CHU-M6 | CA | SAN | CHU | Metro Transport | MTRN CA SAN CHU DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-CHU-M6 | CA | SAN | CHU | Metro Transport | MTRN CA SAN CHU DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-CHU-M6 | CA | SAN | CHU | Metro Transport | MTRN CA SAN CHU DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-CHU-M6 | CA | SAN | CHU | Metro Transport | MTRN CA SAN CHU DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-DWN-M15 | CA | SAN | DWN | Metro Transport | MTRN CA SAN DWN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-DWN-M15 | CA | SAN | DWN | Metro Transport | MTRN CA SAN DWN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-DWN-M15 | CA | SAN | DWN | Metro Transport | MTRN CA SAN DWN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-DWN-M15 | CA | SAN | DWN | Metro Transport | MTRN CA SAN DWN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-DWN-M15 | CA | SAN | DWN | Metro Transport | MTRN CA SAN DWN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-DWN-M6 | CA | SAN | DWN | Metro Transport | MTRN CA SAN DWN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-DWN-M6 | CA | SAN | DWN | Metro Transport | MTRN CA SAN DWN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-DWN-M6 | CA | SAN | DWN | Metro Transport | MTRN CA SAN DWN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-DWN-M6 | CA | SAN | DWN | Metro Transport | MTRN CA SAN DWN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-DWN-M6 | CA | SAN | DWN | Metro Transport | MTRN CA SAN DWN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-ELC-M15 | CA | SAN | ELC | Metro Transport | MTRN CA SAN ELC DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 5 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-ELC-M15 | CA | SAN | ELC | Metro Transport | MTRN CA SAN ELC DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-ELC-M15 | CA | SAN | ELC | Metro Transport | MTRN CA SAN ELC DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-ELC-M15 | CA | SAN | ELC | Metro Transport | MTRN CA SAN ELC DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 5 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-ELC-M15 | CA | SAN | ELC | Metro Transport | MTRN CA SAN ELC DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 5 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-ELC-M6 | CA | SAN | ELC | Metro Transport | MTRN CA SAN ELC DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 6 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-ELC-M6 | CA | SAN | ELC | Metro Transport | MTRN CA SAN ELC DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 6 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-ELC-M6 | CA | SAN | ELC | Metro Transport | MTRN CA SAN ELC DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 6 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-ELC-M6 | CA | SAN | ELC | Metro Transport | MTRN CA SAN ELC DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 6 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-ELC-M6 | CA | SAN | ELC | Metro Transport | MTRN CA SAN ELC DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 6 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-ESC-M15 | CA | SAN | ESC | Metro Transport | MTRN CA SAN ESC DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-ESC-M15 | CA | SAN | ESC | Metro Transport | MTRN CA SAN ESC DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-ESC-M15 | CA | SAN | ESC | Metro Transport | MTRN CA SAN ESC DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-ESC-M15 | CA | SAN | ESC | Metro Transport | MTRN CA SAN ESC DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-ESC-M15 | CA | SAN | ESC | Metro Transport | MTRN CA SAN ESC DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-ESC-M6 | CA | SAN | ESC | Metro Transport | MTRN CA SAN ESC DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-ESC-M6 | CA | SAN | ESC | Metro Transport | MTRN CA SAN ESC DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-ESC-M6 | CA | SAN | ESC | Metro Transport | MTRN CA SAN ESC DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-ESC-M6 | CA | SAN | ESC | Metro Transport | MTRN CA SAN ESC DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-ESC-M6 | CA | SAN | ESC | Metro Transport | MTRN CA SAN ESC DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Metro OTN-DTN-Ciena 6500 S14 | CE | TUL | DTN | Metro Transport | MTRN CE TUL DTN OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-06-01 | 2020-08-01 | Active | EP
Metro OTN-DTN-Ciena 6500 S2 | CE | TUL | DTN | Metro Transport | MTRN CE TUL DTN OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-04-15 | 2020-06-01 | 2020-08-01 | Active | EP
Metro OTN-OWA-Ciena 6500 S14 | CE | TUL | OWA | Metro Transport | MTRN CE TUL OWA OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-06-01 | 2020-08-01 | Active | EP
Metro OTN-OWA-Ciena 6500 S2 | CE | TUL | OWA | Metro Transport | MTRN CE TUL OWA OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-06-01 | 2020-08-01 | Active | EP
Metro OTN-QNC-Ciena 6500 S14 | CE | TUL | QNC | Metro Transport | MTRN CE TUL QNC OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-06-01 | 2020-08-01 | Active | EP
Metro OTN-QNC-Ciena 6500 S2 | CE | TUL | QNC | Metro Transport | MTRN CE TUL QNC OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-06-01 | 2020-08-01 | Active | EP
Metro OTN-SAP-Ciena 6500 S14 | CE | TUL | SAP | Metro Transport | MTRN CE TUL SAP OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-06-01 | 2020-08-01 | Active | EP
Metro OTN-SAP-Ciena 6500 S2 | CE | TUL | SAP | Metro Transport | MTRN CE TUL SAP OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-06-01 | 2020-08-01 | Active | EP
Metro OTN-WST-Ciena 6500 S14 | CE | TUL | WST | Metro Transport | MTRN CE TUL WST OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-06-01 | 2020-08-01 | Active | EP
Metro OTN-WST-Ciena 6500 S2 | CE | TUL | WST | Metro Transport | MTRN CE TUL WST OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-06-01 | 2020-08-01 | Active | EP
Metro OTN-YAL-Ciena 6500 S14 | CE | TUL | YAL | Metro Transport | MTRN CE TUL YAL OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-06-01 | 2020-08-01 | Active | EP
Metro OTN-YAL-Ciena 6500 S2 | CE | TUL | YAL | Metro Transport | MTRN CE TUL YAL OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-06-01 | 2020-08-01 | Active | EP
Metro OTN-MER-Ciena 6500 S14 | NE | CON | MER | Metro Transport | MTRN NE CON MER OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | EP
Metro OTN-MER-Ciena 6500 S14 | NE | CON | MER | Metro Transport | MTRN NE CON MER OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-05-01 | 2020-06-01 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-MER-Ciena 6500 S14 | NE | CON | MER | Metro Transport | MTRN NE CON MER OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-MER-Ciena 6500 S2 | NE | CON | MER | Metro Transport | MTRN NE CON MER OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | EP
Metro OTN-MER-Ciena 6500 S2 | NE | CON | MER | Metro Transport | MTRN NE CON MER OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-05-01 | 2020-06-01 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-MER-Ciena 6500 S2 | NE | CON | MER | Metro Transport | MTRN NE CON MER OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Photonic-OTN-MER-M15 | NE | CON | MER | Metro Transport | MTRN NE CON MER DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-MER-M15 | NE | CON | MER | Metro Transport | MTRN NE CON MER DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-MER-M15 | NE | CON | MER | Metro Transport | MTRN NE CON MER DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-MER-M6 | NE | CON | MER | Metro Transport | MTRN NE CON MER DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-MER-M6 | NE | CON | MER | Metro Transport | MTRN NE CON MER DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-MER-M6 | NE | CON | MER | Metro Transport | MTRN NE CON MER DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Metro OTN-RKH-Ciena 6500 S14 | NE | CON | RKH | Metro Transport | MTRN NE CON RKH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | EP
Metro OTN-RKH-Ciena 6500 S14 | NE | CON | RKH | Metro Transport | MTRN NE CON RKH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-05-01 | 2020-06-01 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-RKH-Ciena 6500 S14 | NE | CON | RKH | Metro Transport | MTRN NE CON RKH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-RKH-Ciena 6500 S2 | NE | CON | RKH | Metro Transport | MTRN NE CON RKH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | EP
Metro OTN-RKH-Ciena 6500 S2 | NE | CON | RKH | Metro Transport | MTRN NE CON RKH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-05-01 | 2020-06-01 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-RKH-Ciena 6500 S2 | NE | CON | RKH | Metro Transport | MTRN NE CON RKH OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Photonic-OTN-RKH-M15 | NE | CON | RKH | Metro Transport | MTRN NE CON RKH DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-RKH-M15 | NE | CON | RKH | Metro Transport | MTRN NE CON RKH DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-RKH-M15 | NE | CON | RKH | Metro Transport | MTRN NE CON RKH DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-RKH-M6 | NE | CON | RKH | Metro Transport | MTRN NE CON RKH DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-RKH-M6 | NE | CON | RKH | Metro Transport | MTRN NE CON RKH DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-RKH-M6 | NE | CON | RKH | Metro Transport | MTRN NE CON RKH DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Metro OTN-STN-Ciena 6500 S14 | NE | CON | STN | Metro Transport | MTRN NE CON STN OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | EP
Metro OTN-STN-Ciena 6500 S14 | NE | CON | STN | Metro Transport | MTRN NE CON STN OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-05-01 | 2020-06-01 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-STN-Ciena 6500 S14 | NE | CON | STN | Metro Transport | MTRN NE CON STN OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-STN-Ciena 6500 S2 | NE | CON | STN | Metro Transport | MTRN NE CON STN OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | EP
Metro OTN-STN-Ciena 6500 S2 | NE | CON | STN | Metro Transport | MTRN NE CON STN OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-02-17 | 2020-05-01 | 2020-06-01 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-STN-Ciena 6500 S2 | NE | CON | STN | Metro Transport | MTRN NE CON STN OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Photonic-OTN-STN-M15 | NE | CON | STN | Metro Transport | MTRN NE CON STN DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-STN-M15 | NE | CON | STN | Metro Transport | MTRN NE CON STN DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-STN-M15 | NE | CON | STN | Metro Transport | MTRN NE CON STN DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-STN-M6 | NE | CON | STN | Metro Transport | MTRN NE CON STN DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-STN-M6 | NE | CON | STN | Metro Transport | MTRN NE CON STN DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 3 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-STN-M6 | NE | CON | STN | Metro Transport | MTRN NE CON STN DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Metro OTN-SFD-Ciena 6500 S14 | NE | CON | SFD | Metro Transport | MTRN NE CON SFD OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | EP
Metro OTN-SFD-Ciena 6500 S14 | NE | CON | SFD | Metro Transport | MTRN NE CON SFD OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-05-01 | 2020-06-01 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-SFD-Ciena 6500 S14 | NE | CON | SFD | Metro Transport | MTRN NE CON SFD OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-SFD-Ciena 6500 S2 | NE | CON | SFD | Metro Transport | MTRN NE CON SFD OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | EP
Metro OTN-SFD-Ciena 6500 S2 | NE | CON | SFD | Metro Transport | MTRN NE CON SFD OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-05-01 | 2020-06-01 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-SFD-Ciena 6500 S2 | NE | CON | SFD | Metro Transport | MTRN NE CON SFD OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-02-17 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Photonic-OTN-SFD-M15 | NE | CON | SFD | Metro Transport | MTRN NE CON SFD OTN Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-SFD-M15 | NE | CON | SFD | Metro Transport | MTRN NE CON SFD OTN Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-SFD-M15 | NE | CON | SFD | Metro Transport | MTRN NE CON SFD OTN Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-SFD-M6 | NE | CON | SFD | Metro Transport | MTRN NE CON SFD OTN Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-SFD-M6 | NE | CON | SFD | Metro Transport | MTRN NE CON SFD OTN Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-SFD-M6 | NE | CON | SFD | Metro Transport | MTRN NE CON SFD OTN Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
MTRN-PRV- T5-01 | NE | RHD | PRV | Metro Transport | MTRN NE RHD PRV T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | EP
MTRN-PRV- T5-01 | NE | RHD | PRV | Metro Transport | MTRN NE RHD PRV T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0053 | New | Approved | 2020-02-06 10:22 | Metro Transport POR Correction to align with Initial POI
MTRN-PRV- T5-01 | NE | RHD | PRV | Metro Transport | MTRN NE RHD PRV T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 4 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-PRV- T5-01 | NE | RHD | PRV | Metro Transport | MTRN NE RHD PRV T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0154 | Schedule Change | Approved | 2020-02-06 11:13 | 1 INP had initially the growth request against PAPA forecast from September 2 May of these have changed and in order to meet the demand before capacity exhaust we need to accelerate several projects from Q2 to Q1 3 780K pulled in from Q2 to Q1 4 Workin
Photonic-OTN-LV1-BLU-M15 | SW | LAS | BLU | Metro Transport | MTRN SW LAS BLU DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-LV1-BLU-M15 | SW | LAS | BLU | Metro Transport | MTRN SW LAS BLU DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV1-BLU-M15 | SW | LAS | BLU | Metro Transport | MTRN SW LAS BLU DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV1-BLU-M15 | SW | LAS | BLU | Metro Transport | MTRN SW LAS BLU DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-LV1-BLU-M15 | SW | LAS | BLU | Metro Transport | MTRN SW LAS BLU DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-LV1-BLU-M6 | SW | LAS | BLU | Metro Transport | MTRN SW LAS BLU DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-LV1-BLU-M6 | SW | LAS | BLU | Metro Transport | MTRN SW LAS BLU DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV1-BLU-M6 | SW | LAS | BLU | Metro Transport | MTRN SW LAS BLU DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV1-BLU-M6 | SW | LAS | BLU | Metro Transport | MTRN SW LAS BLU DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-LV1-BLU-M6 | SW | LAS | BLU | Metro Transport | MTRN SW LAS BLU DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-LV1-CEN-M15 | SW | LAS | CEN | Metro Transport | MTRN SW LAS CEN DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-LV1-CEN-M15 | SW | LAS | CEN | Metro Transport | MTRN SW LAS CEN DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV1-CEN-M15 | SW | LAS | CEN | Metro Transport | MTRN SW LAS CEN DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Deleted | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV1-CEN-M15 | SW | LAS | CEN | Metro Transport | MTRN SW LAS CEN DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-LV1-CEN-M6 | SW | LAS | CEN | Metro Transport | MTRN SW LAS CEN DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-LV1-CEN-M6 | SW | LAS | CEN | Metro Transport | MTRN SW LAS CEN DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV1-CEN-M6 | SW | LAS | CEN | Metro Transport | MTRN SW LAS CEN DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Deleted | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV1-CEN-M6 | SW | LAS | CEN | Metro Transport | MTRN SW LAS CEN DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-LV1-ERN-M15 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-LV1-ERN-M15 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV1-ERN-M15 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV1-ERN-M15 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-LV1-ERN-M15 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-LV1-ERN-M6 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 3 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-LV1-ERN-M6 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV1-ERN-M6 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV1-ERN-M6 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 3 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-LV1-ERN-M6 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 3 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
MTRN-HEN- T5-01 | SW | LAS | HEN | Metro Transport | MTRN SW LAS HEN T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-20 | 2020-02-01 | 2020-03-31 | Active | EP
MTRN-HEN- T5-01 | SW | LAS | HEN | Metro Transport | MTRN SW LAS HEN T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-20 | 2020-02-01 | 2020-03-31 | Active | Log | Upd | SN-0154 | Schedule Change | Approved | 2020-02-06 11:13 | 1 INP had initially the growth request against PAPA forecast from September 2 May of these have changed and in order to meet the demand before capacity exhaust we need to accelerate several projects from Q2 to Q1 3 780K pulled in from Q2 to Q1 4 Workin
MTRN-HEN- T5-03 | SW | LAS | HEN | Metro Transport | MTRN SW LAS HEN T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-20 | 2020-02-01 | 2020-03-31 | Active | EP
MTRN-HEN- T5-03 | SW | LAS | HEN | Metro Transport | MTRN SW LAS HEN T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-06-20 | 2020-07-01 |  | Active | Log | Upd | SN-0053 | New | Approved | 2020-02-06 10:22 | Metro Transport POR Correction to align with Initial POI
MTRN-HEN- T5-03 | SW | LAS | HEN | Metro Transport | MTRN SW LAS HEN T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-20 | 2020-02-01 | 2020-03-31 | Active | Log | Upd | SN-0154 | Schedule Change | Approved | 2020-02-06 11:13 | 1 INP had initially the growth request against PAPA forecast from September 2 May of these have changed and in order to meet the demand before capacity exhaust we need to accelerate several projects from Q2 to Q1 3 780K pulled in from Q2 to Q1 4 Workin
MTRN-HEN- T5-04 | SW | LAS | HEN | Metro Transport | MTRN SW LAS HEN T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-20 | 2020-02-01 | 2020-03-31 | Active | EP
MTRN-HEN- T5-04 | SW | LAS | HEN | Metro Transport | MTRN SW LAS HEN T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-01-20 | 2020-02-01 | 2020-03-31 | Active | Log | Upd | SN-0154 | Schedule Change | Approved | 2020-02-06 11:13 | 1 INP had initially the growth request against PAPA forecast from September 2 May of these have changed and in order to meet the demand before capacity exhaust we need to accelerate several projects from Q2 to Q1 3 780K pulled in from Q2 to Q1 4 Workin
Photonic-OTN-LV1-HEN-M15 | SW | LAS | HEN | Metro Transport | MTRN SW LAS HEN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 4 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-LV1-HEN-M15 | SW | LAS | HEN | Metro Transport | MTRN SW LAS HEN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV1-HEN-M15 | SW | LAS | HEN | Metro Transport | MTRN SW LAS HEN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV1-HEN-M15 | SW | LAS | HEN | Metro Transport | MTRN SW LAS HEN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 4 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-LV1-HEN-M15 | SW | LAS | HEN | Metro Transport | MTRN SW LAS HEN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 4 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-LV1-HEN-M6 | SW | LAS | HEN | Metro Transport | MTRN SW LAS HEN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 4 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-LV1-HEN-M6 | SW | LAS | HEN | Metro Transport | MTRN SW LAS HEN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-LV1-HEN-M6 | SW | LAS | HEN | Metro Transport | MTRN SW LAS HEN DWDM-OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-LV1-HEN-M6 | SW | LAS | HEN | Metro Transport | MTRN SW LAS HEN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 4 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-LV1-HEN-M6 | SW | LAS | HEN | Metro Transport | MTRN SW LAS HEN DWDM-OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 4 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-EEE-M15 | CA | SAN | VST | Metro Transport | MTRN CA SAN VST AIS OTN_OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-EEE-M15 | CA | SAN | VST | Metro Transport | MTRN CA SAN VST AIS OTN_OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-EEE-M15 | CA | SAN | VST | Metro Transport | MTRN CA SAN VST AIS OTN_OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-EEE-M15 | CA | SAN | VST | Metro Transport | MTRN CA SAN VST AIS OTN_OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-EEE-M15 | CA | SAN | VST | Metro Transport | MTRN CA SAN VST AIS OTN_OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-EEE-M6 | CA | SAN | VST | Metro Transport | MTRN CA SAN VST AIS OTN_OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-EEE-M6 | CA | SAN | VST | Metro Transport | MTRN CA SAN VST AIS OTN_OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-EEE-M6 | CA | SAN | VST | Metro Transport | MTRN CA SAN VST AIS OTN_OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-EEE-M6 | CA | SAN | VST | Metro Transport | MTRN CA SAN VST AIS OTN_OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-EEE-M6 | CA | SAN | VST | Metro Transport | MTRN CA SAN VST AIS OTN_OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-FFF-M15 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED EdgeConnex OTN_OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 1 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-FFF-M15 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED EdgeConnex OTN_OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-FFF-M15 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED EdgeConnex OTN_OLS Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-FFF-M15 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED EdgeConnex OTN_OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 1 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-FFF-M15 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED EdgeConnex OTN_OLS Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 1 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-FFF-M6 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED EdgeConnex OTN_OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
Photonic-OTN-FFF-M6 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED EdgeConnex OTN_OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 4 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-FFF-M6 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED EdgeConnex OTN_OLS Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 4 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-FFF-M6 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED EdgeConnex OTN_OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-FFF-M6 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED EdgeConnex OTN_OLS Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
Photonic-OTN-GGG-M15 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED Level-3 OTN Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-GGG-M15 | CA | SAN | SNDACAGL | Metro Transport | MTRN CA SAN FED Level-3 OTN Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-GGG-M15 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED Level-3 OTN Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 1 |  | 2020-05-15 | 2020-06-15 | Deleted | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Photonic-OTN-GGG-M15 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED Level-3 OTN Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 1 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Deleted | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-GGG-M15 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED Level-3 OTN Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0774 | Scope Change | Approved | 2020-07-27 09:32 | Aligning POR based on feedback from FTPMs
Photonic-OTN-GGG-M6 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED Level-3 OTN Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-GGG-M6 | CA | SAN | SNDACAGL | Metro Transport | MTRN CA SAN FED Level-3 OTN Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-GGG-M6 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED Level-3 OTN Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 1 |  | 2020-05-15 | 2020-06-15 | Deleted | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Photonic-OTN-GGG-M6 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED Level-3 OTN Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 1 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Deleted | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-GGG-M6 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED Level-3 OTN Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0774 | Scope Change | Approved | 2020-07-27 09:32 | Aligning POR based on feedback from FTPMs
Photonic-OTN-HHH-M15 | CA | SAN | FED | Metro Transport | MTRN CA SAN ALP DWDM Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | EP
Photonic-OTN-HHH-M15 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED SharpHlth OTN Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-HHH-M15 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED SharpHlth OTN Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-HHH-M15 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED SharpHlth OTN Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Active | Log | Del | SN-0774 | Scope Change | Approved | 2020-07-27 09:32 | Aligning POR based on feedback from FTPMs
Photonic-OTN-HHH-M15 | CA | SAN | FED | Metro Transport | MTRN CA SAN ALP DWDM Deployment POR20 | Chassis | 1x Nokia PSI-M Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Undel | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
Photonic-OTN-HHH-M6 | CA | SAN | FED | Metro Transport | MTRN CA SAN ALP DWDM Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | EP
Photonic-OTN-HHH-M6 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED SharpHlth OTN Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-HHH-M6 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED SharpHlth OTN Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-HHH-M6 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED SharpHlth OTN Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Active | Log | Del | SN-0774 | Scope Change | Approved | 2020-07-27 09:32 | Aligning POR based on feedback from FTPMs
Photonic-OTN-HHH-M6 | CA | SAN | FED | Metro Transport | MTRN CA SAN ALP DWDM Deployment POR20 | Chassis | 1x Nokia PSI-8L Chassis | 2 | 2020-09-01 | 2020-11-30 | 2020-12-31 | Active | Log | Undel | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
MTRN-AVJ- T5-01 | CA | ORG | AVJ | Metro Transport | MTRN CA ORG AVJ T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-02-03 | 2020-05-01 | 2020-06-01 | Active | EP
MTRN-AVJ- T5-01 | CA | ORG | AVJ | Metro Transport | MTRN CA ORG AVJ T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-02-03 | 2020-05-01 | 2020-06-01 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-CHU- T5-01 | CA | SAN | CHU | Metro Transport | MTRN CA SAN CHU T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | EP
MTRN-CHU- T5-01 | CA | SAN | CHU | Metro Transport | MTRN CA SAN CHU T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-ELC- T5-01 | CA | SAN | ELC | Metro Transport | MTRN CA SAN ELC T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | EP
MTRN-ELC- T5-01 | CA | SAN | ELC | Metro Transport | MTRN CA SAN ELC T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-FED- T5-01 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 3 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | EP
MTRN-FED- T5-01 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 3 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-VST- T5-01 | CA | SAN | VST | Metro Transport | MTRN CA SAN VST T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | EP
MTRN-VST- T5-01 | CA | SAN | VST | Metro Transport | MTRN CA SAN VST T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-03-15 | 2020-04-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-VST- T5-01 | CA | SAN | VST | Metro Transport | MTRN CA SAN VST T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0154 | Schedule Change | Approved | 2020-02-06 11:13 | 1 INP had initially the growth request against PAPA forecast from September 2 May of these have changed and in order to meet the demand before capacity exhaust we need to accelerate several projects from Q2 to Q1 3 780K pulled in from Q2 to Q1 4 Workin
MTRN-FTS- T5-01 | CE | NWA | FTS | Metro Transport | MTRN CE NWA FTS T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | EP
MTRN-FTS- T5-01 | CE | NWA | FTS | Metro Transport | MTRN CE NWA FTS T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-03-15 | 2020-03-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-FTS- T5-01 | CE | NWA | FTS | Metro Transport | MTRN CE NWA FTS T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0154 | Schedule Change | Approved | 2020-02-06 11:13 | 1 INP had initially the growth request against PAPA forecast from September 2 May of these have changed and in order to meet the demand before capacity exhaust we need to accelerate several projects from Q2 to Q1 3 780K pulled in from Q2 to Q1 4 Workin
MTRN-NWA- T5-01 | CE | NWA | NWA | Metro Transport | MTRN CE NWA NWA T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-01 | 2020-06-01 | Active | EP
MTRN-NWA- T5-01 | CE | NWA | NWA | Metro Transport | MTRN CE NWA NWA T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-02-17 | 2020-04-01 | 2020-05-01 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-NWA- T5-01 | CE | NWA | NWA | Metro Transport | MTRN CE NWA NWA T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-01 | 2020-06-01 | Active | Log | Upd | SN-0154 | Schedule Change | Approved | 2020-02-06 11:13 | 1 INP had initially the growth request against PAPA forecast from September 2 May of these have changed and in order to meet the demand before capacity exhaust we need to accelerate several projects from Q2 to Q1 3 780K pulled in from Q2 to Q1 4 Workin
MTRN-TOP- T5-01 | CE | KAN | TOP | Metro Transport | MTRN CE KAN TOP T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-02-15 | 2020-02-28 | Active | EP
MTRN-TOP- T5-01 | CE | KAN | TOP | Metro Transport | MTRN CE KAN TOP T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-03-15 | 2020-03-31 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-TOP- T5-01 | CE | KAN | TOP | Metro Transport | MTRN CE KAN TOP T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-02-15 | 2020-02-28 | Active | Log | Upd | SN-0154 | Schedule Change | Approved | 2020-02-06 11:13 | 1 INP had initially the growth request against PAPA forecast from September 2 May of these have changed and in order to meet the demand before capacity exhaust we need to accelerate several projects from Q2 to Q1 3 780K pulled in from Q2 to Q1 4 Workin
MTRN-WIC- T5-01 | CE | KAN | WIC | Metro Transport | MTRN CE KAN WIC T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-03-15 | 2020-03-15 | Active | EP
MTRN-WIC- T5-01 | CE | KAN | WIC | Metro Transport | MTRN CE KAN WIC T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-03-15 | 2020-03-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-DTN- T5-01 | CE | TUL | DTN | Metro Transport | MTRN CE TUL DTN T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | EP
MTRN-NOR- T5-01 | CE | OKC | NOR | Metro Transport | MTRN CE OKC NOR T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | EP
MTRN-NEH- T5-01 | CE | OKC | NEH | Metro Transport | MTRN CE OKC NEH T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | EP
MTRN-OKC- T5-01 | CE | OKC | OKC | Metro Transport | MTRN CE OKC OKC T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | EP
MTRN-TUL- T5-01 | CE | TUL | TUL | Metro Transport | MTRN CE TUL TUL T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | EP
MTRN-PAW- T5-01 | NE | RHD | PAW | Metro Transport | MTRN NE RHD PAW T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | EP
MTRN-WWK- T5-01 | NE | RHD | WWK | Metro Transport | MTRN NE RHD WWK T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-03-01 | 2020-04-15 | 2020-05-15 | Active | EP
MTRN-WWK- T5-01 | NE | RHD | WWK | Metro Transport | MTRN NE RHD WWK T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-03-01 | 2020-04-15 | 2020-05-15 | Active | Log | Upd | SN-0154 | Schedule Change | Approved | 2020-02-06 11:13 | 1 INP had initially the growth request against PAPA forecast from September 2 May of these have changed and in order to meet the demand before capacity exhaust we need to accelerate several projects from Q2 to Q1 3 780K pulled in from Q2 to Q1 4 Workin
MTRN-CLR- T5-01 | SE | NOR | CLR | Metro Transport | MTRN SE NOR CLR T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-01 | 2020-02-01 | 2020-03-01 | Active | EP
MTRN-CLR- T5-01 | SE | NOR | CLR | Metro Transport | MTRN SE NOR CLR T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-01 | 2020-02-01 | 2020-03-01 | Active | Log | Upd | SN-0154 | Schedule Change | Approved | 2020-02-06 11:13 | 1 INP had initially the growth request against PAPA forecast from September 2 May of these have changed and in order to meet the demand before capacity exhaust we need to accelerate several projects from Q2 to Q1 3 780K pulled in from Q2 to Q1 4 Workin
MTRN-BEL- T5-01 | SW | ARZ | BEL | Metro Transport | MTRN SW ARZ BEL T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-03-01 | 2020-04-01 | Active | EP
MTRN-BEL- T5-01 | SW | ARZ | BEL | Metro Transport | MTRN SW ARZ BEL T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-03-01 | 2020-04-01 | Active | Log | Upd | SN-0154 | Schedule Change | Approved | 2020-02-06 11:13 | 1 INP had initially the growth request against PAPA forecast from September 2 May of these have changed and in order to meet the demand before capacity exhaust we need to accelerate several projects from Q2 to Q1 3 780K pulled in from Q2 to Q1 4 Workin
MTRN-CHD- T5-03 | SW | ARZ | CHD | Metro Transport | MTRN SW ARZ CHD T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-01 |  | Active | EP
MTRN-MSA- T5-01 | SW | ARZ | MSA | Metro Transport | MTRN SW ARZ MSA T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-03-20 | 2020-04-01 | 2020-05-01 | Active | EP
MTRN-MSA- T5-01 | SW | ARZ | MSA | Metro Transport | MTRN SW ARZ MSA T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-03-20 | 2020-04-01 | 2020-05-01 | Active | Log | Upd | SN-0154 | Schedule Change | Approved | 2020-02-06 11:13 | 1 INP had initially the growth request against PAPA forecast from September 2 May of these have changed and in order to meet the demand before capacity exhaust we need to accelerate several projects from Q2 to Q1 3 780K pulled in from Q2 to Q1 4 Workin
MTRN-FWL- T5-02 | SW | ARZ | FWL | Metro Transport | MTRN SW ARZ FWL T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | Active | EP
MTRN-FWL- T5-02 | SW | ARZ | FWL | Metro Transport | MTRN SW ARZ FWL T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics |  |  |  |  | Active | Log | Del | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-FWL- T5-02 | SW | ARZ | FWL | Metro Transport | MTRN SW ARZ FWL T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | Active | Log | Undel | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
MTRN-MCD- T5-03 | SW | ARZ | MCD | Metro Transport | MTRN SW ARZ MCD T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 4 | 2020-04-20 | 2020-05-01 |  | Active | EP
MTRN-MCD- T5-03 | SW | ARZ | MCD | Metro Transport | MTRN SW ARZ MCD T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 4 | 2020-04-20 | 2020-05-01 |  | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-TUC- T5-01 | SW | ARZ | TUC | Metro Transport | MTRN SW ARZ TUC T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-02-15 | 2020-06-15 | Active | EP
MTRN-TUC- T5-01 | SW | ARZ | TUC | Metro Transport | MTRN SW ARZ TUC T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-02-15 | 2020-06-15 | Active | Log | Upd | SN-0154 | Schedule Change | Approved | 2020-02-06 11:13 | 1 INP had initially the growth request against PAPA forecast from September 2 May of these have changed and in order to meet the demand before capacity exhaust we need to accelerate several projects from Q2 to Q1 3 780K pulled in from Q2 to Q1 4 Workin
MTRN-VLY- T5-01 | SW | LAS | VLY | Metro Transport | MTRN SW LAS VLY T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | Active | EP
MTRN-VLY- T5-01 | SW | LAS | VLY | Metro Transport | MTRN SW LAS VLY T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics |  |  |  |  | Active | Log | Del | SN-0154 | Schedule Change | Approved | 2020-02-06 11:13 | 1 INP had initially the growth request against PAPA forecast from September 2 May of these have changed and in order to meet the demand before capacity exhaust we need to accelerate several projects from Q2 to Q1 3 780K pulled in from Q2 to Q1 4 Workin
MTRN-VLY- T5-01 | SW | LAS | VLY | Metro Transport | MTRN SW LAS VLY T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | Active | Log | Undel | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
MTRN-VLY- T5-02 | SW | LAS | VLY | Metro Transport | MTRN SW LAS VLY T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-02-15 | 2020-03-31 | Active | EP
MTRN-VLY- T5-02 | SW | LAS | VLY | Metro Transport | MTRN SW LAS VLY T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-02-15 | 2020-03-31 | Active | Log | Upd | SN-0154 | Schedule Change | Approved | 2020-02-06 11:13 | 1 INP had initially the growth request against PAPA forecast from September 2 May of these have changed and in order to meet the demand before capacity exhaust we need to accelerate several projects from Q2 to Q1 3 780K pulled in from Q2 to Q1 4 Workin
MTRN-NWP- T5-01 | VA | HRD | NWP | Metro Transport | MTRN VA HRD NWP T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-12-31 | 2020-12-31 | Active | EP
MTRN-NWP- T5-01 | VA | HRD | NWP | Metro Transport | MTRN VA HRD NWP T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-03-31 | 2020-04-30 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-NWP- T5-01 | VA | HRD | NWP | Metro Transport | MTRN VA HRD NWP T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-12-31 | 2020-12-31 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
MTRN-OCN- T5-01 | VA | HRD | OCN | Metro Transport | MTRN VA HRD OCN T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | EP
MTRN-PTM- T5-01 | VA | HRD | PTM | Metro Transport | MTRN VA HRD PTM T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | EP
MTRN-FLK- T5-01 | VA | NVA | FLK | Metro Transport | MTRN VA NVA FLK T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-02-15 | 2020-06-15 | Active | EP
MTRN-FLK- T5-01 | VA | NVA | FLK | Metro Transport | MTRN VA NVA FLK T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-02-15 | 2020-06-15 | Active | Log | Upd | SN-0154 | Schedule Change | Approved | 2020-02-06 11:13 | 1 INP had initially the growth request against PAPA forecast from September 2 May of these have changed and in order to meet the demand before capacity exhaust we need to accelerate several projects from Q2 to Q1 3 780K pulled in from Q2 to Q1 4 Workin
MTRN-MFD- T5-01 | VA | NVA | MFD | Metro Transport | MTRN VA NVA MFD T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-02-15 | 2020-03-15 | Active | EP
MTRN-MFD- T5-01 | VA | NVA | MFD | Metro Transport | MTRN VA NVA MFD T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-02-15 | 2020-03-15 | Active | Log | Upd | SN-0154 | Schedule Change | Approved | 2020-02-06 11:13 | 1 INP had initially the growth request against PAPA forecast from September 2 May of these have changed and in order to meet the demand before capacity exhaust we need to accelerate several projects from Q2 to Q1 3 780K pulled in from Q2 to Q1 4 Workin
Photonic-OTN-CHO-M15 | CE | OKC | CHO | Metro Transport | MTRN CE OKC CHO DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-CHO-M15 | CE | OKC | CHO | Metro Transport | MTRN CE OKC CHO DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-CHO-M15 | CE | OKC | CHO | Metro Transport | MTRN CE OKC CHO DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-CHO-M6 | CE | OKC | CHO | Metro Transport | MTRN CE OKC CHO DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-CHO-M6 | CE | OKC | CHO | Metro Transport | MTRN CE OKC CHO DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-CHO-M6 | CE | OKC | CHO | Metro Transport | MTRN CE OKC CHO DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-CLH-M15 | CE | OKC | CLH | Metro Transport | MTRN CE OKC CLH DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-CLH-M15 | CE | OKC | CLH | Metro Transport | MTRN CE OKC CLH DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-CLH-M15 | CE | OKC | CLH | Metro Transport | MTRN CE OKC CLH DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-CLH-M6 | CE | OKC | CLH | Metro Transport | MTRN CE OKC CLH DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-CLH-M6 | CE | OKC | CLH | Metro Transport | MTRN CE OKC CLH DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-CLH-M6 | CE | OKC | CLH | Metro Transport | MTRN CE OKC CLH DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-ELR-M15 | CE | OKC | ELR | Metro Transport | MTRN CE OKC ELR DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-ELR-M15 | CE | OKC | ELR | Metro Transport | MTRN CE OKC ELR DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-ELR-M15 | CE | OKC | ELR | Metro Transport | MTRN CE OKC ELR DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-ELR-M6 | CE | OKC | ELR | Metro Transport | MTRN CE OKC ELR DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-ELR-M6 | CE | OKC | ELR | Metro Transport | MTRN CE OKC ELR DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 3 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-ELR-M6 | CE | OKC | ELR | Metro Transport | MTRN CE OKC ELR DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-ILH-M15 | CE | OKC | ILH | Metro Transport | MTRN CE OKC ILH DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-ILH-M15 | CE | OKC | ILH | Metro Transport | MTRN CE OKC ILH DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-ILH-M15 | CE | OKC | ILH | Metro Transport | MTRN CE OKC ILH DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-ILH-M6 | CE | OKC | ILH | Metro Transport | MTRN CE OKC ILH DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-ILH-M6 | CE | OKC | ILH | Metro Transport | MTRN CE OKC ILH DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-ILH-M6 | CE | OKC | ILH | Metro Transport | MTRN CE OKC ILH DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-MWC-M15 | CE | OKC | MWC | Metro Transport | MTRN CE OKC MWC DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-MWC-M15 | CE | OKC | MWC | Metro Transport | MTRN CE OKC MWC DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-MWC-M15 | CE | OKC | MWC | Metro Transport | MTRN CE OKC MWC DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-MWC-M6 | CE | OKC | MWC | Metro Transport | MTRN CE OKC MWC DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-MWC-M6 | CE | OKC | MWC | Metro Transport | MTRN CE OKC MWC DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 3 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-MWC-M6 | CE | OKC | MWC | Metro Transport | MTRN CE OKC MWC DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-MOO-M15 | CE | OKC | MOO | Metro Transport | MTRN CE OKC MOO DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-MOO-M15 | CE | OKC | MOO | Metro Transport | MTRN CE OKC MOO DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-MOO-M15 | CE | OKC | MOO | Metro Transport | MTRN CE OKC MOO DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-MOO-M6 | CE | OKC | MOO | Metro Transport | MTRN CE OKC MOO DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-MOO-M6 | CE | OKC | MOO | Metro Transport | MTRN CE OKC MOO DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-MOO-M6 | CE | OKC | MOO | Metro Transport | MTRN CE OKC MOO DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-NOR-M15 | CE | OKC | NOR | Metro Transport | MTRN CE OKC NOR DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-NOR-M15 | CE | OKC | NOR | Metro Transport | MTRN CE OKC NOR DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-NOR-M15 | CE | OKC | NOR | Metro Transport | MTRN CE OKC NOR DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-NOR-M6 | CE | OKC | NOR | Metro Transport | MTRN CE OKC NOR DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-NOR-M6 | CE | OKC | NOR | Metro Transport | MTRN CE OKC NOR DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 4 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-NOR-M6 | CE | OKC | NOR | Metro Transport | MTRN CE OKC NOR DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-NCH-M15 | CE | OKC | NCH | Metro Transport | MTRN CE OKC NCH DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-NCH-M15 | CE | OKC | NCH | Metro Transport | MTRN CE OKC NCH DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-NCH-M15 | CE | OKC | NCH | Metro Transport | MTRN CE OKC NCH DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-NCH-M6 | CE | OKC | NCH | Metro Transport | MTRN CE OKC NCH DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-NCH-M6 | CE | OKC | NCH | Metro Transport | MTRN CE OKC NCH DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-NCH-M6 | CE | OKC | NCH | Metro Transport | MTRN CE OKC NCH DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-NEH-M15 | CE | OKC | NEH | Metro Transport | MTRN CE OKC NEH DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-NEH-M15 | CE | OKC | NEH | Metro Transport | MTRN CE OKC NEH DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-NEH-M15 | CE | OKC | NEH | Metro Transport | MTRN CE OKC NEH DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-NEH-M6 | CE | OKC | NEH | Metro Transport | MTRN CE OKC NEH DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-NEH-M6 | CE | OKC | NEH | Metro Transport | MTRN CE OKC NEH DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-NEH-M6 | CE | OKC | NEH | Metro Transport | MTRN CE OKC NEH DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-OKC-M15 | CE | OKC | OKC | Metro Transport | MTRN CE OKC OKC DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-OKC-M15 | CE | OKC | OKC | Metro Transport | MTRN CE OKC OKC DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 8 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-OKC-M15 | CE | OKC | OKC | Metro Transport | MTRN CE OKC OKC DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-OKC-M6 | CE | OKC | OKC | Metro Transport | MTRN CE OKC OKC DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-OKC-M6 | CE | OKC | OKC | Metro Transport | MTRN CE OKC OKC DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 6 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-OKC-M6 | CE | OKC | OKC | Metro Transport | MTRN CE OKC OKC DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-SEH-M15 | CE | OKC | SRH | Metro Transport | MTRN CE OKC SRH DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-SEH-M15 | CE | OKC | SRH | Metro Transport | MTRN CE OKC SRH DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-SEH-M15 | CE | OKC | SRH | Metro Transport | MTRN CE OKC SRH DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-SEH-M6 | CE | OKC | SRH | Metro Transport | MTRN CE OKC SRH DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-SEH-M6 | CE | OKC | SRH | Metro Transport | MTRN CE OKC SRH DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 4 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-SEH-M6 | CE | OKC | SRH | Metro Transport | MTRN CE OKC SRH DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-SRH-M15 | CE | OKC | SRH | Metro Transport | MTRN CE OKC SRH DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-SRH-M15 | CE | OKC | SRH | Metro Transport | MTRN CE OKC SRH DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-SRH-M15 | CE | OKC | SRH | Metro Transport | MTRN CE OKC SRH DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-SRH-M6 | CE | OKC | SRH | Metro Transport | MTRN CE OKC SRH DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-SRH-M6 | CE | OKC | SRH | Metro Transport | MTRN CE OKC SRH DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-SRH-M6 | CE | OKC | SRH | Metro Transport | MTRN CE OKC SRH DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-WLK-M15 | CE | OKC | WLK | Metro Transport | MTRN CE OKC WLK DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-WLK-M15 | CE | OKC | WLK | Metro Transport | MTRN CE OKC WLK DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-WLK-M15 | CE | OKC | WLK | Metro Transport | MTRN CE OKC WLK DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-WLK-M6 | CE | OKC | WLK | Metro Transport | MTRN CE OKC WLK DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-WLK-M6 | CE | OKC | WLK | Metro Transport | MTRN CE OKC WLK DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 5 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-WLK-M6 | CE | OKC | WLK | Metro Transport | MTRN CE OKC WLK DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-WEH-M15 | CE | OKC | WEH | Metro Transport | MTRN CE OKC WEH DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-WEH-M15 | CE | OKC | WEH | Metro Transport | MTRN CE OKC WEH DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-WEH-M15 | CE | OKC | WEH | Metro Transport | MTRN CE OKC WEH DWDM Deployment POR20 | Chassis | 1x Cisco M15 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Photonic-OTN-WEH-M6 | CE | OKC | WEH | Metro Transport | MTRN CE OKC WEH DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | EP
Photonic-OTN-WEH-M6 | CE | OKC | WEH | Metro Transport | MTRN CE OKC WEH DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis | 3 | 2020-06-01 | 2020-06-30 | 2020-07-31 | Deleted | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Photonic-OTN-WEH-M6 | CE | OKC | WEH | Metro Transport | MTRN CE OKC WEH DWDM Deployment POR20 | Chassis | 1x Cisco M6 Transport Chassis |  |  |  |  | Deleted | Log | Del | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Metro OTN-CNY-Ciena 6500 S14 | CE | KAN | CNY | Metro Transport | MTRN CE KAN CNY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-07-15 | 2020-09-15 | 2020-11-15 | Active | EP
Metro OTN-CNY-Ciena 6500 S14 | CE | KAN | CNY | Metro Transport | MTRN CE KAN CNY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-CNY-Ciena 6500 S14 | CE | KAN | CNY | Metro Transport | MTRN CE KAN CNY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-07-15 | 2020-09-15 | 2020-11-15 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-CNY-Ciena 6500 S2 | CE | KAN | CNY | Metro Transport | MTRN CE KAN CNY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-07-15 | 2020-09-15 | 2020-11-15 | Active | EP
Metro OTN-CNY-Ciena 6500 S2 | CE | KAN | CNY | Metro Transport | MTRN CE KAN CNY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-CNY-Ciena 6500 S2 | CE | KAN | CNY | Metro Transport | MTRN CE KAN CNY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-07-15 | 2020-09-15 | 2020-11-15 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-DCY2-Ciena 6500 S14 | CE | KAN | DCY | Metro Transport | MTRN CE KAN DCY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-07-15 | 2020-09-30 | 2020-11-30 | Active | EP
Metro OTN-DCY2-Ciena 6500 S14 | CE | KAN | DCY | Metro Transport | MTRN CE KAN DCY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 2 | 2020-01-20 | 2020-03-15 | 2020-03-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-DCY2-Ciena 6500 S14 | CE | KAN | DCY | Metro Transport | MTRN CE KAN DCY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-07-15 | 2020-09-30 | 2020-11-30 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-DCY2-Ciena 6500 S2 | CE | KAN | DCY | Metro Transport | MTRN CE KAN DCY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-07-15 | 2020-09-30 | 2020-11-30 | Active | EP
Metro OTN-DCY2-Ciena 6500 S2 | CE | KAN | DCY | Metro Transport | MTRN CE KAN DCY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-01-20 | 2020-03-15 | 2020-03-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-DCY2-Ciena 6500 S2 | CE | KAN | DCY | Metro Transport | MTRN CE KAN DCY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-07-15 | 2020-09-30 | 2020-11-30 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-DCY-Ciena 6500 S14 | CE | KAN | DCY | Metro Transport | MTRN CE KAN DCY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-07-15 | 2020-09-30 | 2020-11-30 | Active | EP
Metro OTN-DCY-Ciena 6500 S14 | CE | KAN | DCY | Metro Transport | MTRN CE KAN DCY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-DCY-Ciena 6500 S14 | CE | KAN | DCY | Metro Transport | MTRN CE KAN DCY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-07-15 | 2020-09-30 | 2020-11-30 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-DCY-Ciena 6500 S2 | CE | KAN | DCY | Metro Transport | MTRN CE KAN DCY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-11-30 | Active | EP
Metro OTN-DCY-Ciena 6500 S2 | CE | KAN | DCY | Metro Transport | MTRN CE KAN DCY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-DCY-Ciena 6500 S2 | CE | KAN | DCY | Metro Transport | MTRN CE KAN DCY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-11-30 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-GCY-Ciena 6500 S14 | CE | KAN | GDY | Metro Transport | MTRN CE KAN GDY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-07-15 | 2020-09-30 | 2020-11-30 | Active | EP
Metro OTN-GCY-Ciena 6500 S14 | CE | KAN | GDY | Metro Transport | MTRN CE KAN GDY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-GCY-Ciena 6500 S14 | CE | KAN | GDY | Metro Transport | MTRN CE KAN GDY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-07-15 | 2020-09-30 | 2020-11-30 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-GCY-Ciena 6500 S2 | CE | KAN | GDY | Metro Transport | MTRN CE KAN GDY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-11-30 | Active | EP
Metro OTN-GCY-Ciena 6500 S2 | CE | KAN | GDY | Metro Transport | MTRN CE KAN GDY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-GCY-Ciena 6500 S2 | CE | KAN | GDY | Metro Transport | MTRN CE KAN GDY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-11-30 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-GBD-Ciena 6500 S2 | CE | KAN | GBD | Metro Transport | MTRN CE KAN GBD OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-11-30 | Active | EP
Metro OTN-GBD-Ciena 6500 S2 | CE | KAN | GBD | Metro Transport | MTRN CE KAN GBD OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-01-20 | 2020-03-15 | 2020-03-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-GBD-Ciena 6500 S2 | CE | KAN | GBD | Metro Transport | MTRN CE KAN GBD OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-11-30 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-GBD-Ciena 6500 S32 | CE | KAN | GBD | Metro Transport | MTRN CE KAN GBD OTN Deployment POR20 | Chassis | 1x Ciena 6500 S32 Chassis | 1 | 2020-07-15 | 2020-09-30 | 2020-11-30 | Active | EP
Metro OTN-GBD-Ciena 6500 S32 | CE | KAN | GBD | Metro Transport | MTRN CE KAN GBD OTN Deployment POR20 | Chassis | 1x Ciena 6500 S32 Chassis | 4 | 2020-01-20 | 2020-03-15 | 2020-03-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-GBD-Ciena 6500 S32 | CE | KAN | GBD | Metro Transport | MTRN CE KAN GBD OTN Deployment POR20 | Chassis | 1x Ciena 6500 S32 Chassis | 1 | 2020-07-15 | 2020-09-30 | 2020-11-30 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-HUT-Ciena 6500 S14 | CE | KAN | HUT | Metro Transport | MTRN CE KAN HUT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-07-15 | 2020-09-30 | 2020-11-01 | Active | EP
Metro OTN-HUT-Ciena 6500 S14 | CE | KAN | HUT | Metro Transport | MTRN CE KAN HUT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 2 | 2020-01-20 | 2020-03-15 | 2020-03-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-HUT-Ciena 6500 S14 | CE | KAN | HUT | Metro Transport | MTRN CE KAN HUT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-07-15 | 2020-09-30 | 2020-11-01 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-HUT-Ciena 6500 S2 | CE | KAN | HUT | Metro Transport | MTRN CE KAN HUT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-11-01 | Active | EP
Metro OTN-HUT-Ciena 6500 S2 | CE | KAN | HUT | Metro Transport | MTRN CE KAN HUT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 1 | 2020-01-20 | 2020-03-15 | 2020-03-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-HUT-Ciena 6500 S2 | CE | KAN | HUT | Metro Transport | MTRN CE KAN HUT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-11-01 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-KLY-Ciena 6500 S14 | CE | KAN | KLY | Metro Transport | MTRN CE KAN KLY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-07-15 | 2020-09-30 | 2020-11-30 | Active | EP
Metro OTN-KLY-Ciena 6500 S14 | CE | KAN | KLY | Metro Transport | MTRN CE KAN KLY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 2 | 2020-01-20 | 2020-03-15 | 2020-03-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-KLY-Ciena 6500 S14 | CE | KAN | KLY | Metro Transport | MTRN CE KAN KLY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-07-15 | 2020-09-30 | 2020-11-30 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-KLY-Ciena 6500 S2 | CE | KAN | KLY | Metro Transport | MTRN CE KAN KLY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-11-30 | Active | EP
Metro OTN-KLY-Ciena 6500 S2 | CE | KAN | KLY | Metro Transport | MTRN CE KAN KLY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-01-20 | 2020-03-15 | 2020-03-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-KLY-Ciena 6500 S2 | CE | KAN | KLY | Metro Transport | MTRN CE KAN KLY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-11-30 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-NWT-Ciena 6500 S14 | CE | KAN | NWT | Metro Transport | MTRN CE KAN NWT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-07-15 | 2020-09-30 | 2020-11-30 | Active | EP
Metro OTN-NWT-Ciena 6500 S14 | CE | KAN | NWT | Metro Transport | MTRN CE KAN NWT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-NWT-Ciena 6500 S14 | CE | KAN | NWT | Metro Transport | MTRN CE KAN NWT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-07-15 | 2020-09-30 | 2020-11-30 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-NWT-Ciena 6500 S2 | CE | KAN | NWT | Metro Transport | MTRN CE KAN NWT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-11-30 | Active | EP
Metro OTN-NWT-Ciena 6500 S2 | CE | KAN | NWT | Metro Transport | MTRN CE KAN NWT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-NWT-Ciena 6500 S2 | CE | KAN | NWT | Metro Transport | MTRN CE KAN NWT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-11-30 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-PRT-Ciena 6500 S14 | CE | KAN | PRT | Metro Transport | MTRN CE KAN PRT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-07-15 | 2020-09-30 | 2020-11-30 | Active | EP
Metro OTN-PRT-Ciena 6500 S14 | CE | KAN | PRT | Metro Transport | MTRN CE KAN PRT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 3 | 2020-01-20 | 2020-03-15 | 2020-03-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-PRT-Ciena 6500 S14 | CE | KAN | PRT | Metro Transport | MTRN CE KAN PRT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-07-15 | 2020-09-30 | 2020-11-30 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-PRT-Ciena 6500 S2 | CE | KAN | PRT | Metro Transport | MTRN CE KAN PRT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-11-30 | Active | EP
Metro OTN-PRT-Ciena 6500 S2 | CE | KAN | PRT | Metro Transport | MTRN CE KAN PRT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-01-20 | 2020-03-15 | 2020-03-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-PRT-Ciena 6500 S2 | CE | KAN | PRT | Metro Transport | MTRN CE KAN PRT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-11-30 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-WIC-Ciena 6500 S2 | CE | KAN | WIC | Metro Transport | MTRN CE KAN WIC OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-11-30 | Active | EP
Metro OTN-WIC-Ciena 6500 S2 | CE | KAN | WIC | Metro Transport | MTRN CE KAN WIC OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-WIC-Ciena 6500 S2 | CE | KAN | WIC | Metro Transport | MTRN CE KAN WIC OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-07-15 | 2020-09-30 | 2020-11-30 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-ALG-Ciena 6500 S14 | SE | NOR | ALG | Metro Transport | MTRN SE NOR ALG OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | EP
Metro OTN-ALG-Ciena 6500 S14 | SE | NOR | ALG | Metro Transport | MTRN SE NOR ALG OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-06-30 | 2020-08-15 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Metro OTN-ALG-Ciena 6500 S14 | SE | NOR | ALG | Metro Transport | MTRN SE NOR ALG OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-08-31 | 2020-09-30 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-ALG-Ciena 6500 S14 | SE | NOR | ALG | Metro Transport | MTRN SE NOR ALG OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0665 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Updating SE Activation dates to July based on field feedback
Metro OTN-ALG-Ciena 6500 S2 | SE | NOR | ALG | Metro Transport | MTRN SE NOR ALG OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | EP
Metro OTN-ALG-Ciena 6500 S2 | SE | NOR | ALG | Metro Transport | MTRN SE NOR ALG OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-06-30 | 2020-08-15 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Metro OTN-ALG-Ciena 6500 S2 | SE | NOR | ALG | Metro Transport | MTRN SE NOR ALG OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-08-31 | 2020-09-30 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-ALG-Ciena 6500 S2 | SE | NOR | ALG | Metro Transport | MTRN SE NOR ALG OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0665 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Updating SE Activation dates to July based on field feedback
Metro OTN-CLR-Ciena 6500 S14 | SE | NOR | CLR | Metro Transport | MTRN SE NOR CLR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | EP
Metro OTN-CLR-Ciena 6500 S14 | SE | NOR | CLR | Metro Transport | MTRN SE NOR CLR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-06-30 | 2020-08-15 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Metro OTN-CLR-Ciena 6500 S14 | SE | NOR | CLR | Metro Transport | MTRN SE NOR CLR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-08-31 | 2020-09-30 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-CLR-Ciena 6500 S14 | SE | NOR | CLR | Metro Transport | MTRN SE NOR CLR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0665 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Updating SE Activation dates to July based on field feedback
Metro OTN-CLR-Ciena 6500 S2 | SE | NOR | CLR | Metro Transport | MTRN SE NOR CLR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | EP
Metro OTN-CLR-Ciena 6500 S2 | SE | NOR | CLR | Metro Transport | MTRN SE NOR CLR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-06-30 | 2020-08-15 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Metro OTN-CLR-Ciena 6500 S2 | SE | NOR | CLR | Metro Transport | MTRN SE NOR CLR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-08-31 | 2020-09-30 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-CLR-Ciena 6500 S2 | SE | NOR | CLR | Metro Transport | MTRN SE NOR CLR OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0665 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Updating SE Activation dates to July based on field feedback
Metro OTN-DST-Ciena 6500 S14 | SE | NOR | DST | Metro Transport | MTRN SE NOR DST OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | EP
Metro OTN-DST-Ciena 6500 S14 | SE | NOR | DST | Metro Transport | MTRN SE NOR DST OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-08-31 | 2020-09-30 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-DST-Ciena 6500 S14 | SE | NOR | DST | Metro Transport | MTRN SE NOR DST OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0665 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Updating SE Activation dates to July based on field feedback
Metro OTN-DST-Ciena 6500 S2 | SE | NOR | DST | Metro Transport | MTRN SE NOR DST OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | EP
Metro OTN-DST-Ciena 6500 S2 | SE | NOR | DST | Metro Transport | MTRN SE NOR DST OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-08-31 | 2020-09-30 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-DST-Ciena 6500 S2 | SE | NOR | DST | Metro Transport | MTRN SE NOR DST OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0665 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Updating SE Activation dates to July based on field feedback
Metro OTN-KNN-Ciena 6500 S14 | SE | NOR | KNN | Metro Transport | MTRN SE NOR KNN OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | EP
Metro OTN-KNN-Ciena 6500 S14 | SE | NOR | KNN | Metro Transport | MTRN SE NOR KNN OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-06-30 | 2020-08-15 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Metro OTN-KNN-Ciena 6500 S14 | SE | NOR | KNN | Metro Transport | MTRN SE NOR KNN OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-08-31 | 2020-09-30 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-KNN-Ciena 6500 S14 | SE | NOR | KNN | Metro Transport | MTRN SE NOR KNN OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0665 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Updating SE Activation dates to July based on field feedback
Metro OTN-KNN-Ciena 6500 S2 | SE | NOR | KNN | Metro Transport | MTRN SE NOR KNN OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | EP
Metro OTN-KNN-Ciena 6500 S2 | SE | NOR | KNN | Metro Transport | MTRN SE NOR KNN OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-06-30 | 2020-08-15 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Metro OTN-KNN-Ciena 6500 S2 | SE | NOR | KNN | Metro Transport | MTRN SE NOR KNN OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-08-31 | 2020-09-30 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-KNN-Ciena 6500 S2 | SE | NOR | KNN | Metro Transport | MTRN SE NOR KNN OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0665 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Updating SE Activation dates to July based on field feedback
Metro OTN-LPL-Ciena 6500 S14 | SE | NOR | LPL | Metro Transport | MTRN SE NOR LPL OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | EP
Metro OTN-LPL-Ciena 6500 S14 | SE | NOR | LPL | Metro Transport | MTRN SE NOR LPL OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-08-31 | 2020-09-30 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-LPL-Ciena 6500 S14 | SE | NOR | LPL | Metro Transport | MTRN SE NOR LPL OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0665 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Updating SE Activation dates to July based on field feedback
Metro OTN-LPL-Ciena 6500 S2 | SE | NOR | LPL | Metro Transport | MTRN SE NOR LPL OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | EP
Metro OTN-LPL-Ciena 6500 S2 | SE | NOR | LPL | Metro Transport | MTRN SE NOR LPL OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-08-31 | 2020-09-30 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-LPL-Ciena 6500 S2 | SE | NOR | LPL | Metro Transport | MTRN SE NOR LPL OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0665 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Updating SE Activation dates to July based on field feedback
Metro OTN-LUL-Ciena 6500 S14 | SE | NOR | LUL | Metro Transport | MTRN SE NOR LUL OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | EP
Metro OTN-LUL-Ciena 6500 S14 | SE | NOR | LUL | Metro Transport | MTRN SE NOR LUL OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-06-30 | 2020-08-15 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Metro OTN-LUL-Ciena 6500 S14 | SE | NOR | LUL | Metro Transport | MTRN SE NOR LUL OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-08-31 | 2020-09-30 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-LUL-Ciena 6500 S14 | SE | NOR | LUL | Metro Transport | MTRN SE NOR LUL OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0665 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Updating SE Activation dates to July based on field feedback
Metro OTN-LUL-Ciena 6500 S2 | SE | NOR | LUL | Metro Transport | MTRN SE NOR LUL OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | EP
Metro OTN-LUL-Ciena 6500 S2 | SE | NOR | LUL | Metro Transport | MTRN SE NOR LUL OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-06-30 | 2020-08-15 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Metro OTN-LUL-Ciena 6500 S2 | SE | NOR | LUL | Metro Transport | MTRN SE NOR LUL OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-08-31 | 2020-09-30 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-LUL-Ciena 6500 S2 | SE | NOR | LUL | Metro Transport | MTRN SE NOR LUL OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0665 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Updating SE Activation dates to July based on field feedback
Metro OTN-MCY-Ciena 6500 S14 | SE | NOR | MCY | Metro Transport | MTRN SE NOR MCY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | EP
Metro OTN-MCY-Ciena 6500 S14 | SE | NOR | MCY | Metro Transport | MTRN SE NOR MCY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-08-31 | 2020-09-30 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-MCY-Ciena 6500 S14 | SE | NOR | MCY | Metro Transport | MTRN SE NOR MCY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0665 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Updating SE Activation dates to July based on field feedback
Metro OTN-MCY-Ciena 6500 S2 | SE | NOR | MCY | Metro Transport | MTRN SE NOR MCY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | EP
Metro OTN-MCY-Ciena 6500 S2 | SE | NOR | MCY | Metro Transport | MTRN SE NOR MCY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-04-15 | 2020-08-31 | 2020-09-30 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-MCY-Ciena 6500 S2 | SE | NOR | MCY | Metro Transport | MTRN SE NOR MCY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0665 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Updating SE Activation dates to July based on field feedback
Metro OTN-NOE-Ciena 6500 S14 | SE | NOR | NOE | Metro Transport | MTRN SE NOR NOE OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | EP
Metro OTN-NOE-Ciena 6500 S14 | SE | NOR | NOE | Metro Transport | MTRN SE NOR NOE OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-08-31 | 2020-09-30 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-NOE-Ciena 6500 S14 | SE | NOR | NOE | Metro Transport | MTRN SE NOR NOE OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0665 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Updating SE Activation dates to July based on field feedback
Metro OTN-NOE-Ciena 6500 S2 | SE | NOR | NOE | Metro Transport | MTRN SE NOR NOE OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | EP
Metro OTN-NOE-Ciena 6500 S2 | SE | NOR | NOE | Metro Transport | MTRN SE NOR NOE OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-08-31 | 2020-09-30 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-NOE-Ciena 6500 S2 | SE | NOR | NOE | Metro Transport | MTRN SE NOR NOE OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0665 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Updating SE Activation dates to July based on field feedback
Metro OTN-STB-Ciena 6500 S14 | SE | NOR | STB | Metro Transport | MTRN SE NOR STB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | EP
Metro OTN-STB-Ciena 6500 S14 | SE | NOR | STB | Metro Transport | MTRN SE NOR STB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-06-30 | 2020-08-15 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Metro OTN-STB-Ciena 6500 S14 | SE | NOR | STB | Metro Transport | MTRN SE NOR STB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-08-31 | 2020-09-30 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-STB-Ciena 6500 S14 | SE | NOR | STB | Metro Transport | MTRN SE NOR STB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0665 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Updating SE Activation dates to July based on field feedback
Metro OTN-STB-Ciena 6500 S2 | SE | NOR | STB | Metro Transport | MTRN SE NOR STB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | EP
Metro OTN-STB-Ciena 6500 S2 | SE | NOR | STB | Metro Transport | MTRN SE NOR STB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-06-30 | 2020-08-15 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Metro OTN-STB-Ciena 6500 S2 | SE | NOR | STB | Metro Transport | MTRN SE NOR STB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-08-31 | 2020-09-30 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-STB-Ciena 6500 S2 | SE | NOR | STB | Metro Transport | MTRN SE NOR STB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0665 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Updating SE Activation dates to July based on field feedback
Metro OTN-CRV-Ciena 6500 S14 | SE | GCT | CRV | Metro Transport | MTRN SE GCT CRV OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | EP
Metro OTN-CRV-Ciena 6500 S14 | SE | GCT | CRV | Metro Transport | MTRN SE GCT CRV OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 3 | 2020-02-17 | 2020-04-01 | 2020-05-01 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-CRV-Ciena 6500 S14 | SE | GCT | CRV | Metro Transport | MTRN SE GCT CRV OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-01 | 2020-08-01 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-CRV-Ciena 6500 S14 | SE | GCT | CRV | Metro Transport | MTRN SE GCT CRV OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-08-31 | 2020-09-30 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-CRV-Ciena 6500 S14 | SE | GCT | CRV | Metro Transport | MTRN SE GCT CRV OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0665 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Updating SE Activation dates to July based on field feedback
Metro OTN-CRV-Ciena 6500 S2 | SE | GCT | CRV | Metro Transport | MTRN SE GCT CRV OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | EP
Metro OTN-CRV-Ciena 6500 S2 | SE | GCT | CRV | Metro Transport | MTRN SE GCT CRV OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-CRV-Ciena 6500 S2 | SE | GCT | CRV | Metro Transport | MTRN SE GCT CRV OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-01 | 2020-08-01 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-CRV-Ciena 6500 S2 | SE | GCT | CRV | Metro Transport | MTRN SE GCT CRV OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-08-31 | 2020-09-30 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-CRV-Ciena 6500 S2 | SE | GCT | CRV | Metro Transport | MTRN SE GCT CRV OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0665 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Updating SE Activation dates to July based on field feedback
Metro OTN-DES-Ciena 6500 S14 | SE | GCT | DES | Metro Transport | MTRN SE GCT DES OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | EP
Metro OTN-DES-Ciena 6500 S14 | SE | GCT | DES | Metro Transport | MTRN SE GCT DES OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-DES-Ciena 6500 S14 | SE | GCT | DES | Metro Transport | MTRN SE GCT DES OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-DES-Ciena 6500 S14 | SE | GCT | DES | Metro Transport | MTRN SE GCT DES OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-08-31 | 2020-09-30 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-DES-Ciena 6500 S14 | SE | GCT | DES | Metro Transport | MTRN SE GCT DES OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0665 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Updating SE Activation dates to July based on field feedback
Metro OTN-DES-Ciena 6500 S2 | SE | GCT | DES | Metro Transport | MTRN SE GCT DES OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | EP
Metro OTN-DES-Ciena 6500 S2 | SE | GCT | DES | Metro Transport | MTRN SE GCT DES OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-DES-Ciena 6500 S2 | SE | GCT | DES | Metro Transport | MTRN SE GCT DES OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-DES-Ciena 6500 S2 | SE | GCT | DES | Metro Transport | MTRN SE GCT DES OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-08-31 | 2020-09-30 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-DES-Ciena 6500 S2 | SE | GCT | DES | Metro Transport | MTRN SE GCT DES OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0665 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Updating SE Activation dates to July based on field feedback
Metro OTN-FWB-Ciena 6500 S14 | SE | GCT | FWB | Metro Transport | MTRN SE GCT FWB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | EP
Metro OTN-FWB-Ciena 6500 S14 | SE | GCT | FWB | Metro Transport | MTRN SE GCT FWB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-FWB-Ciena 6500 S14 | SE | GCT | FWB | Metro Transport | MTRN SE GCT FWB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-FWB-Ciena 6500 S14 | SE | GCT | FWB | Metro Transport | MTRN SE GCT FWB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-08-31 | 2020-09-30 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-FWB-Ciena 6500 S14 | SE | GCT | FWB | Metro Transport | MTRN SE GCT FWB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0665 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Updating SE Activation dates to July based on field feedback
Metro OTN-FWB-Ciena 6500 S2 | SE | GCT | FWB | Metro Transport | MTRN SE GCT FWB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | EP
Metro OTN-FWB-Ciena 6500 S2 | SE | GCT | FWB | Metro Transport | MTRN SE GCT FWB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-FWB-Ciena 6500 S2 | SE | GCT | FWB | Metro Transport | MTRN SE GCT FWB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-FWB-Ciena 6500 S2 | SE | GCT | FWB | Metro Transport | MTRN SE GCT FWB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-08-31 | 2020-09-30 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-FWB-Ciena 6500 S2 | SE | GCT | FWB | Metro Transport | MTRN SE GCT FWB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0665 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Updating SE Activation dates to July based on field feedback
Metro OTN-NCV-Ciena 6500 S14 | SE | GCT | NCV | Metro Transport | MTRN SE GCT NCV OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | EP
Metro OTN-NCV-Ciena 6500 S14 | SE | GCT | NCV | Metro Transport | MTRN SE GCT NCV OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-NCV-Ciena 6500 S14 | SE | GCT | NCV | Metro Transport | MTRN SE GCT NCV OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-NCV-Ciena 6500 S14 | SE | GCT | NCV | Metro Transport | MTRN SE GCT NCV OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-08-31 | 2020-09-30 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-NCV-Ciena 6500 S14 | SE | GCT | NCV | Metro Transport | MTRN SE GCT NCV OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0665 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Updating SE Activation dates to July based on field feedback
Metro OTN-NCV-Ciena 6500 S2 | SE | GCT | NCV | Metro Transport | MTRN SE GCT NCV OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | EP
Metro OTN-NCV-Ciena 6500 S2 | SE | GCT | NCV | Metro Transport | MTRN SE GCT NCV OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-NCV-Ciena 6500 S2 | SE | GCT | NCV | Metro Transport | MTRN SE GCT NCV OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-NCV-Ciena 6500 S2 | SE | GCT | NCV | Metro Transport | MTRN SE GCT NCV OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-08-31 | 2020-09-30 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-NCV-Ciena 6500 S2 | SE | GCT | NCV | Metro Transport | MTRN SE GCT NCV OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0665 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Updating SE Activation dates to July based on field feedback
Metro OTN-GRY-Ciena 6500 S14 | SE | MGA | GRY | Metro Transport | MTRN SE MGA GRY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | EP
Metro OTN-GRY-Ciena 6500 S14 | SE | MGA | GRY | Metro Transport | MTRN SE MGA GRY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-GRY-Ciena 6500 S14 | SE | MGA | GRY | Metro Transport | MTRN SE MGA GRY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-06-30 | 2020-08-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-GRY-Ciena 6500 S14 | SE | MGA | GRY | Metro Transport | MTRN SE MGA GRY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-08-31 | 2020-09-30 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-GRY-Ciena 6500 S14 | SE | MGA | GRY | Metro Transport | MTRN SE MGA GRY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0665 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Updating SE Activation dates to July based on field feedback
Metro OTN-GRY-Ciena 6500 S2 | SE | MGA | GRY | Metro Transport | MTRN SE MGA GRY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | EP
Metro OTN-GRY-Ciena 6500 S2 | SE | MGA | GRY | Metro Transport | MTRN SE MGA GRY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-GRY-Ciena 6500 S2 | SE | MGA | GRY | Metro Transport | MTRN SE MGA GRY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-06-30 | 2020-08-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-GRY-Ciena 6500 S2 | SE | MGA | GRY | Metro Transport | MTRN SE MGA GRY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-08-31 | 2020-09-30 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-GRY-Ciena 6500 S2 | SE | MGA | GRY | Metro Transport | MTRN SE MGA GRY OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0665 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Updating SE Activation dates to July based on field feedback
Metro OTN-HLT-Ciena 6500 S14 | SE | MGA | HLT | Metro Transport | MTRN SE MGA HLT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | EP
Metro OTN-HLT-Ciena 6500 S14 | SE | MGA | HLT | Metro Transport | MTRN SE MGA HLT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-HLT-Ciena 6500 S14 | SE | MGA | HLT | Metro Transport | MTRN SE MGA HLT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-06-30 | 2020-08-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-HLT-Ciena 6500 S14 | SE | MGA | HLT | Metro Transport | MTRN SE MGA HLT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-08-31 | 2020-09-30 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-HLT-Ciena 6500 S14 | SE | MGA | HLT | Metro Transport | MTRN SE MGA HLT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0665 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Updating SE Activation dates to July based on field feedback
Metro OTN-HLT-Ciena 6500 S2 | SE | MGA | HLT | Metro Transport | MTRN SE MGA HLT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | EP
Metro OTN-HLT-Ciena 6500 S2 | SE | MGA | HLT | Metro Transport | MTRN SE MGA HLT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-HLT-Ciena 6500 S2 | SE | MGA | HLT | Metro Transport | MTRN SE MGA HLT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-06-30 | 2020-08-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-HLT-Ciena 6500 S2 | SE | MGA | HLT | Metro Transport | MTRN SE MGA HLT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-08-31 | 2020-09-30 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-HLT-Ciena 6500 S2 | SE | MGA | HLT | Metro Transport | MTRN SE MGA HLT OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0665 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Updating SE Activation dates to July based on field feedback
Metro OTN-WRB-Ciena 6500 S14 | SE | MGA | WRB | Metro Transport | MTRN SE MGA WRB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | EP
Metro OTN-WRB-Ciena 6500 S14 | SE | MGA | WRB | Metro Transport | MTRN SE MGA WRB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 2 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-WRB-Ciena 6500 S14 | SE | MGA | WRB | Metro Transport | MTRN SE MGA WRB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-06-30 | 2020-08-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-WRB-Ciena 6500 S14 | SE | MGA | WRB | Metro Transport | MTRN SE MGA WRB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-08-30 | 2020-09-30 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Metro OTN-WRB-Ciena 6500 S14 | SE | MGA | WRB | Metro Transport | MTRN SE MGA WRB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-08-31 | 2020-09-30 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-WRB-Ciena 6500 S14 | SE | MGA | WRB | Metro Transport | MTRN SE MGA WRB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S14 Chassis | 1 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0665 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Updating SE Activation dates to July based on field feedback
Metro OTN-WRB-Ciena 6500 S2 | SE | MGA | WRB | Metro Transport | MTRN SE MGA WRB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | EP
Metro OTN-WRB-Ciena 6500 S2 | SE | MGA | WRB | Metro Transport | MTRN SE MGA WRB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 3 | 2020-04-20 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
Metro OTN-WRB-Ciena 6500 S2 | SE | MGA | WRB | Metro Transport | MTRN SE MGA WRB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-06-30 | 2020-08-31 | Active | Log | Upd | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
Metro OTN-WRB-Ciena 6500 S2 | SE | MGA | WRB | Metro Transport | MTRN SE MGA WRB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-08-30 | 2020-09-30 | Active | Log | Upd | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
Metro OTN-WRB-Ciena 6500 S2 | SE | MGA | WRB | Metro Transport | MTRN SE MGA WRB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-08-31 | 2020-09-30 | Active | Log | Upd | SN-0639 | Schedule Change | Approved | 2020-06-05 15:48 | Metro Transport : POR changes based on field date changes
Metro OTN-WRB-Ciena 6500 S2 | SE | MGA | WRB | Metro Transport | MTRN SE MGA WRB OTN Deployment POR20 | Chassis | 1x Ciena 6500 S2 Chassis | 2 | 2020-04-15 | 2020-07-31 | 2020-09-30 | Active | Log | Upd | SN-0665 | Schedule Change | Approved | 2020-06-14 18:39 | 1 Updating SE Activation dates to July based on field feedback
MTRN-SSC- T5-01 | SW | ARZ | SSC | Metro Transport | MTRN SW ARZ SSC T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics |  |  |  |  | Deleted | EP
MTRN-SSC- T5-01 | SW | ARZ | SSC | Metro Transport | MTRN SW ARZ SSC T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-01 | 2020-06-01 | Deleted | Log | New | SN-0053 | New | Approved | 2020-02-06 10:22 | Metro Transport POR Correction to align with Initial POI
MTRN-SSC- T5-01 | SW | ARZ | SSC | Metro Transport | MTRN SW ARZ SSC T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics |  |  |  |  | Deleted | Log | Del | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-PEO- T5-01 | SW | ARZ | BEL | Metro Transport | MTRN SW ARZ BEL T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-01 |  | Active | EP
MTRN-PEO- T5-01 | SW | ARZ | BEL | Metro Transport | MTRN SW ARZ BEL T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-04-20 | 2020-05-01 |  | Active | Log | New | SN-0098 | Schedule Change | Approved | 2020-02-06 10:46 | 1 Photonic Layer financial was in Q2 , plan updated to reflect that 2 Norfolk, VBC and Newport news moved to Jan per BOM 3 Count in Providence updated 4 Peoria newly added and Mcdowell count updated 5 Wichita and Topeka moved to Q1
MTRN-PRV- T5-02 | NE | RHD | PRV | Metro Transport | MTRN NE RHD PRV T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-03-01 | 2020-04-15 | 2020-04-15 | Active | EP
MTRN-PRV- T5-02 | NE | RHD | PRV | Metro Transport | MTRN NE RHD PRV T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-03-01 | 2020-04-15 | 2020-04-15 | Active | Log | New | SN-0154 | Schedule Change | Approved | 2020-02-06 11:13 | 1 INP had initially the growth request against PAPA forecast from September 2 May of these have changed and in order to meet the demand before capacity exhaust we need to accelerate several projects from Q2 to Q1 3 780K pulled in from Q2 to Q1 4 Workin
MTRN-FED- T5-02 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | Active | EP
MTRN-FED- T5-02 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 1 | 2020-04-20 | 2020-05-01 | 2020-05-01 | Active | Log | New | SN-0154 | Schedule Change | Approved | 2020-02-06 11:13 | 1 INP had initially the growth request against PAPA forecast from September 2 May of these have changed and in order to meet the demand before capacity exhaust we need to accelerate several projects from Q2 to Q1 3 780K pulled in from Q2 to Q1 4 Workin
MTRN-FED- T5-02 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | Active | Log | New | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
MTRN-MCD- T5-04 | SW | ARZ | MCD | Metro Transport | MTRN SW ARZ MCD T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 4 | 2020-01-20 | 2020-02-01 |  | Active | EP
MTRN-MCD- T5-04 | SW | ARZ | MCD | Metro Transport | MTRN SW ARZ MCD T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 4 | 2020-01-20 | 2020-02-01 |  | Active | Log | Undel | SN-0154 | Schedule Change | Approved | 2020-02-06 11:13 | 1 INP had initially the growth request against PAPA forecast from September 2 May of these have changed and in order to meet the demand before capacity exhaust we need to accelerate several projects from Q2 to Q1 3 780K pulled in from Q2 to Q1 4 Workin
MTRN-MCD- T5-05 | SW | ARZ | MCD | Metro Transport | MTRN SW ARZ MCD T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 4 | 2020-03-01 | 2020-04-01 |  | Active | EP
MTRN-MCD- T5-05 | SW | ARZ | MCD | Metro Transport | MTRN SW ARZ MCD T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 4 | 2020-03-01 | 2020-04-01 |  | Active | Log | Undel | SN-0154 | Schedule Change | Approved | 2020-02-06 11:13 | 1 INP had initially the growth request against PAPA forecast from September 2 May of these have changed and in order to meet the demand before capacity exhaust we need to accelerate several projects from Q2 to Q1 3 780K pulled in from Q2 to Q1 4 Workin
MTRN-CHD- T5-04 | SW | ARZ | CHD | Metro Transport | MTRN SW ARZ CHD T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-02-28 |  | Active | EP
MTRN-CHD- T5-04 | SW | ARZ | CHD | Metro Transport | MTRN SW ARZ CHD T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-01-20 | 2020-02-28 |  | Active | Log | Undel | SN-0154 | Schedule Change | Approved | 2020-02-06 11:13 | 1 INP had initially the growth request against PAPA forecast from September 2 May of these have changed and in order to meet the demand before capacity exhaust we need to accelerate several projects from Q2 to Q1 3 780K pulled in from Q2 to Q1 4 Workin
MTRN-CHD- T5-05 | SW | ARZ | CHD | Metro Transport | MTRN SW ARZ CHD T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-03-01 | 2020-04-28 |  | Active | EP
MTRN-CHD- T5-05 | SW | ARZ | CHD | Metro Transport | MTRN SW ARZ CHD T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-03-01 | 2020-04-28 |  | Active | Log | Undel | SN-0154 | Schedule Change | Approved | 2020-02-06 11:13 | 1 INP had initially the growth request against PAPA forecast from September 2 May of these have changed and in order to meet the demand before capacity exhaust we need to accelerate several projects from Q2 to Q1 3 780K pulled in from Q2 to Q1 4 Workin
Metro OTN-OKC-Ciena 6500 S32 | CE | OKC | OKC | Metro Transport | MTRN CE OKC OKC OTN Deployment POR20 | Chassis | 1x Ciena 6500 S32 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | EP
Metro OTN-OKC-Ciena 6500 S32 | CE | OKC | OKC | Metro Transport | MTRN CE OKC OKC OTN Deployment POR20 | Chassis | 1x Ciena 6500 S32 Chassis | 1 | 2020-02-17 | 2020-04-30 | 2020-05-31 | Active | Log | New | SN-0161 | Scope Change | Approved | 2020-02-18 11:32 | 1 Ciena has informed the Metro OTN Materials would move out from Jan to Feb 2 This moves 3 4M from Jan to Feb 3 Additional 562K has been incurred on the latest BOM changes because of redesign in OTN 4 Updating plan to reflect the changes
MTRN-ORG-T5-Augment | CA | ORG | ORG | Metro Transport | MTRN CA ORG ORG T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | Active | EP
MTRN-ORG-T5-Augment | CA | ORG | ORG | Metro Transport | MTRN CA ORG ORG T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | Active | Log | New | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
MTRN-RSM- T5-03 | CA | ORG | RSM | Metro Transport | MTRN CA ORG RSM T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | Active | EP
MTRN-RSM- T5-03 | CA | ORG | RSM | Metro Transport | MTRN CA ORG RSM T5 Card Augment POR20 v2 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | Active | Log | New | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
MTRN-CHU- T5-02 | CA | SAN | CHU | Metro Transport | MTRN CA SAN CHU T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | Active | EP
MTRN-CHU- T5-02 | CA | SAN | CHU | Metro Transport | MTRN CA SAN CHU T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | Active | Log | New | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
MTRN-ELC- T5-02 | CA | SAN | ELC | Metro Transport | MTRN CA SAN ELC T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | Active | EP
MTRN-ELC- T5-02 | CA | SAN | ELC | Metro Transport | MTRN CA SAN ELC T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | Active | Log | New | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
MTRN-PWY-T5 | CA | SAN | PWY | Metro Transport | MTRN CA SAN PWY DWDM-OLS Deployment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
MTRN-PWY-T5 | CA | SAN | PWY | Metro Transport | MTRN CA SAN PWY DWDM-OLS Deployment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | Active | Log | New | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
MTRN-PWY-T5 | CA | SAN | PWY | Metro Transport | MTRN CA SAN PWY DWDM-OLS Deployment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
MTRN-OMM- T5-01 | CE | OMA | OMM | Metro Transport | MTRN CE OMA OMM T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | Active | EP
MTRN-OMM- T5-01 | CE | OMA | OMM | Metro Transport | MTRN CE OMA OMM T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | Active | Log | New | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
MTRN-T5-BLU-01 | SW | LAS | BLU | Metro Transport | MTRN SW LAS BLU T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | Active | EP
MTRN-T5-BLU-01 | SW | LAS | BLU | Metro Transport | MTRN SW LAS BLU T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | Active | Log | New | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
MTRN-HEN- T5-05 | SW | LAS | HEN | Metro Transport | MTRN SW LAS HEN T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | Active | EP
MTRN-HEN- T5-05 | SW | LAS | HEN | Metro Transport | MTRN SW LAS HEN T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | Active | Log | New | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
MTRN-TEN- T5-05 | SW | LAS | TEN | Metro Transport | MTRN SW LAS TEN T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | Active | EP
MTRN-TEN- T5-05 | SW | LAS | TEN | Metro Transport | MTRN SW LAS TEN T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | Active | Log | New | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
MTRN-OSB- T5-01 | SW | LAS | OSB | Metro Transport | MTRN SW LAS OSB DWDM Deployment POR19 | Chassis | 1x Nokia PSI-M Chassis |  |  |  |  | Deleted | EP
MTRN-OSB- T5-01 | SW | LAS | OSB | Metro Transport | MTRN SW LAS OSB DWDM Deployment POR19 | Chassis | 1x Cisco M15 Transport Chassis | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | Deleted | Log | New | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
MTRN-OSB- T5-01 | SW | LAS | OSB | Metro Transport | MTRN SW LAS OSB DWDM Deployment POR19 | Chassis | 1x Nokia PSI-M Chassis |  |  |  |  | Deleted | Log | Del | SN-0805 | Scope Change | Approved | 2020-08-07 09:42 | Projects that were originally scheduled as DWDM OTN are now moving to the OLS solution Quantities are also changing This will not impact that budget Changes are net zero
MTRN-OSB- T5-02 | SW | LAS | OSB | Metro Transport | MTRN SW LAS OSB DWDM Deployment POR19 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | Active | EP
MTRN-OSB- T5-02 | SW | LAS | OSB | Metro Transport | MTRN SW LAS OSB DWDM Deployment POR19 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | Active | Log | New | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
MTRN-FED- T5-03 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | Active | EP
MTRN-FED- T5-03 | CA | SAN | FED | Metro Transport | MTRN CA SAN FED T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | Active | Log | New | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
MTRN-ALI- T5-03 | SW | LAS | ALI | Metro Transport | MTRN SW LAS ALI DWDM-OLS Deployment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
MTRN-ALI- T5-03 | SW | LAS | ALI | Metro Transport | MTRN SW LAS ALI DWDM-OLS Deployment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | Active | Log | New | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
MTRN-ALI- T5-03 | SW | LAS | ALI | Metro Transport | MTRN SW LAS ALI DWDM-OLS Deployment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
MTRN-OCN- T5-02 | VA | HRD | OCN | Metro Transport | MTRN VA HRD OCN T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | Active | EP
MTRN-OCN- T5-02 | VA | HRD | OCN | Metro Transport | MTRN VA HRD OCN T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | Active | Log | New | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
MTRN-T5-ERN-01 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN DWDM-OLS Deployment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | EP
MTRN-T5-ERN-01 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN DWDM-OLS Deployment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | Active | Log | New | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
MTRN-T5-ERN-01 | SW | LAS | ERN | Metro Transport | MTRN SW LAS ERN DWDM-OLS Deployment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-11-01 | 2020-12-30 | 2021-03-30 | Active | Log | Upd | SN-0953 | Scope Change | Approved | 2020-09-25 14:15 | This CR aligns the POR and financials to the expected ship and migration dates for Transport OLS
MTRN-TUC- T5-02 | SW | ARZ | TUC | Metro Transport | MTRN SW ARZ TUC T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | Active | EP
MTRN-TUC- T5-02 | SW | ARZ | TUC | Metro Transport | MTRN SW ARZ TUC T5 Card Augment POR20 | Card & Optics | Cisco T5 Card and Optics | 2 | 2020-06-01 | 2020-07-31 | 2020-09-30 | Active | Log | New | SN-0562 | COVID-19 Related | Approved | 2020-05-12 17:58 | 1 Deferring OLS Projects into 2021 2 Adding Growth Projects because of COVID 3 Updating Plan
MTCS CA ORG RSM MPEG4 Field Transitions Deployment POR20 | CA | ORG | RSM | MTC - Servers and Software | MTCS CA ORG RSM MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15 | Active | EP
MTCS CA ORG RSM Channel Growth Deployment POR20 | CA | ORG | RSM | MTC - Servers and Software | MTCS CA ORG RSM Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS CA ORG RSM Remote Video Monitoring Expansion Augment POR20 | CA | ORG | RSM | MTC - Servers and Software | MTCS CA ORG RSM Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS CA SAB SAB Channel Growth Deployment POR20 | CA | SAB | SAB | MTC - Servers and Software | MTCS CA SAB SAB Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS CA SAB SAB Remote Video Monitoring Expansion Augment POR20 | CA | SAB | SAB | MTC - Servers and Software | MTCS CA SAB SAB Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS CA SAB SAB MPEG4 Field Transitions Deployment POR20 | CA | SAB | SAB | MTC - Servers and Software | MTCS CA SAB SAB MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15 | Active | EP
MTCS CA SAN ELC MPEG4 Field Transitions Deployment POR20 | CA | SAN | ELC | MTC - Servers and Software | MTCS CA SAN ELC MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15 | Active | EP
MTCS CA SAN ELC Remote Video Monitoring Expansion Augment POR20 | CA | SAN | ELC | MTC - Servers and Software | MTCS CA SAN ELC Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS CA SAN ELC Channel Growth Deployment POR20 | CA | SAN | ELC | MTC - Servers and Software | MTCS CA SAN ELC Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS CE ARK NWA MPEG4 Field Transitions Deployment POR20 | CE | NWA | NWA | MTC - Servers and Software | MTCS CE NWA NWA MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15 | Active | EP
MTCS CE ARK NWA Remote Video Monitoring Expansion Augment POR20 | CE | NWA | NWA | MTC - Servers and Software | MTCS CE NWA NWA Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS CE ARK NWA Channel Growth Deployment POR20 | CE | NWA | NWA | MTC - Servers and Software | MTCS CE NWA NWA Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS CE KAN WIC PDC Tear Down Deployment POR20 | CE | KAN | WIC | MTC - Servers and Software | MTCS CE KAN WIC PDC Tear Down Deployment POR20 | Labor | Power down, unrack, scrap, and uncable racks | 1 | 2020-01-06 | 2020-02-15 | 2020-10-15 | Active | EP
MTCS CE KAN WIC Channel Growth Deployment POR20 | CE | KAN | WIC | MTC - Servers and Software | MTCS CE KAN WIC Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS CE KAN WIC Remote Video Monitoring Expansion Augment POR20 | CE | KAN | WIC | MTC - Servers and Software | MTCS CE KAN WIC Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS CE KAN WIC MPEG4 Field Transitions Deployment POR20 | CE | KAN | WIC | MTC - Servers and Software | MTCS CE KAN WIC MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15 | Active | EP
MTCS CE OKC OKC Channel Growth Deployment POR20 | CE | OKC | OKC | MTC - Servers and Software | MTCS CE OKC OKC Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS CE OKC OKC Remote Video Monitoring Expansion Augment POR20 | CE | OKC | OKC | MTC - Servers and Software | MTCS CE OKC OKC Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS CE OKC OKC MPEG4 Field Transitions Deployment POR20 | CE | OKC | OKC | MTC - Servers and Software | MTCS CE OKC OKC MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15 | Active | EP
MTCS CE OKC TUL MPEG4 Field Transitions Deployment POR20 | CE | TUL | TUL | MTC - Servers and Software | MTCS CE TUL TUL MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15 | Active | EP
MTCS CE OKC TUL Remote Video Monitoring Expansion Augment POR20 | CE | TUL | TUL | MTC - Servers and Software | MTCS CE TUL TUL Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS CE OKC TUL Channel Growth Deployment POR20 | CE | TUL | TUL | MTC - Servers and Software | MTCS CE TUL TUL Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS CE OMA OMM MPEG4 Field Transitions Deployment POR20 | CE | OMA | OMM | MTC - Servers and Software | MTCS CE OMA OMM MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15 | Active | EP
MTCS CE OMA OMM Remote Video Monitoring Expansion Augment POR20 | CE | OMA | OMM | MTC - Servers and Software | MTCS CE OMA OMM Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS CE OMA OMM Channel Growth Deployment POR20 | CE | OMA | OMM | MTC - Servers and Software | MTCS CE OMA OMM Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS COR COR ATL KPI Operations Dashboard Deployment POR20 | COR | COR | ATL | MTC - Servers and Software | MTCS CO COR ATL KPI Operations Dashboard Deployment POR20 | Critical Facilities | MTC Hub Signaling |  |  |  |  | Deleted | EP
MTCS COR COR ATL KPI Operations Dashboard Deployment POR20 | COR | COR | ATL | MTC - Servers and Software | MTCS CO COR ATL KPI Operations Dashboard Deployment POR20 | Critical Facilities | MTC Hub Signaling |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS COR COR ATL Lab Equipment Deployment POR20 | COR | COR | ATL | MTC - Servers and Software | MTCS CO COR ATL Lab Equipment Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-09-15 | Active | EP
MTCS COR COR P6L Lab NSG Deployment POR20 | COR | COR | P6L | MTC - Servers and Software | MTCS CO COR P6L Lab NSG Deployment POR20 | Chassis | NSG | 1 | 2020-02-06 | 2020-03-15 | 2020-04-15 | Active | EP
MTCS COR COR P6L Lab NE3000 Deployment POR20 | COR | COR | P6L | MTC - Servers and Software | MTCS CO COR P6L Lab NE3000 Deployment POR20 | Chassis | NE3000 | 1 | 2020-02-06 | 2020-03-15 | 2020-04-15 | Active | EP
MTCS NE CLE CLV MPEG4 Field Transitions Deployment POR20 | NE | CLE | CLV | MTC - Servers and Software | MTCS NE CLE CLV MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15 | Active | EP
MTCS NE CLE CLV Channel Growth Deployment POR20 | NE | CLE | CLV | MTC - Servers and Software | MTCS NE CLE CLV Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS NE CLE CLV Remote Video Monitoring Expansion Augment POR20 | NE | CLE | CLV | MTC - Servers and Software | MTCS NE CLE CLV Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS NE CON MAN Remote Video Monitoring Expansion Augment POR20 | NE | CON | MAN | MTC - Servers and Software | MTCS NE CON MAN Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS NE CON MAN Channel Growth Deployment POR20 | NE | CON | MAN | MTC - Servers and Software | MTCS NE CON MAN Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS NE CON MAN MPEG4 Field Transitions Deployment POR20 | NE | CON | MAN | MTC - Servers and Software | MTCS NE CON MAN MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15 | Active | EP
MTCS NE RHD WWK MPEG4 Field Transitions Deployment POR20 | NE | RHD | WWK | MTC - Servers and Software | MTCS NE RHD WWK MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15 | Active | EP
MTCS NE RHD WWK Channel Growth Deployment POR20 | NE | RHD | WWK | MTC - Servers and Software | MTCS NE RHD WWK Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS NE RHD WWK Remote Video Monitoring Expansion Augment POR20 | NE | RHD | WWK | MTC - Servers and Software | MTCS NE RHD WWK Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS SE GAN GNS Channel Growth Deployment POR20 | SE | GAN | GNS | MTC - Servers and Software | MTCS SE GAN GNS Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS SE GAN GNS Remote Video Monitoring Expansion Augment POR20 | SE | GAN | GNS | MTC - Servers and Software | MTCS SE GAN GNS Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS SE GAN GNS MPEG4 Field Transitions Deployment POR20 | SE | GAN | GNS | MTC - Servers and Software | MTCS SE GAN GNS MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15 | Active | EP
MTCS SE GCT PNS MPEG4 Field Transitions Deployment POR20 | SE | GCT | PNS | MTC - Servers and Software | MTCS SE GCT PNS MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15 | Active | EP
MTCS SE GCT PNS Remote Video Monitoring Expansion Augment POR20 | SE | GCT | PNS | MTC - Servers and Software | MTCS SE GCT PNS Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS SE GCT PNS Channel Growth Deployment POR20 | SE | GCT | PNS | MTC - Servers and Software | MTCS SE GCT PNS Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS SE GLA BTR MPEG4 Field Transitions Deployment POR20 | SE | BTR | BTR | MTC - Servers and Software | MTCS SE BTR BTR MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15 | Active | EP
MTCS SE GLA BTR Remote Video Monitoring Expansion Augment POR20 | SE | BTR | BTR | MTC - Servers and Software | MTCS SE BTR BTR Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS SE GLA BTR Channel Growth Deployment POR20 | SE | BTR | BTR | MTC - Servers and Software | MTCS SE BTR BTR Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS SE GLA BTR PDC Tear Down Deployment POR20 | SE | BTR | BTR | MTC - Servers and Software | MTCS SE BTR BTR PDC Tear Down Deployment POR20 | Labor | Power down, unrack, scrap, and uncable racks | 1 | 2020-01-06 | 2020-02-15 | 2020-10-15 | Active | EP
MTCS SE GLA ELM MPEG4 Field Transitions Deployment POR20 | SE | NOR | ELM | MTC - Servers and Software | MTCS SE NOR ELM MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15 | Active | EP
MTCS SE GLA ELM Channel Growth Deployment POR20 | SE | NOR | ELM | MTC - Servers and Software | MTCS SE NOR ELM Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS SE GLA ELM Remote Video Monitoring Expansion Augment POR20 | SE | NOR | ELM | MTC - Servers and Software | MTCS SE NOR ELM Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS SE MGA MCN MPEG4 Field Transitions Deployment POR20 | SE | MGA | MCN | MTC - Servers and Software | MTCS SE MGA MCN MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15 | Active | EP
MTCS SE MGA MCN Remote Video Monitoring Expansion Augment POR20 | SE | MGA | MCN | MTC - Servers and Software | MTCS SE MGA MCN Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS SE MGA MCN Channel Growth Deployment POR20 | SE | MGA | MCN | MTC - Servers and Software | MTCS SE MGA MCN Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS SW ARZ CHD MPEG4 Field Transitions Deployment POR20 | SW | ARZ | CHD | MTC - Servers and Software | MTCS SW ARZ CHD MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15 | Active | EP
MTCS SW ARZ CHD PDC Tear Down Deployment POR20 | SW | ARZ | CHD | MTC - Servers and Software | MTCS SW ARZ CHD PDC Tear Down Deployment POR20 | Labor | Power down, unrack, scrap, and uncable racks | 1 | 2020-01-06 | 2020-02-15 | 2020-10-15 | Active | EP
MTCS SW ARZ CHD Channel Growth Deployment POR20 | SW | ARZ | CHD | MTC - Servers and Software | MTCS SW ARZ CHD Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS SW ARZ CHD Remote Video Monitoring Expansion Augment POR20 | SW | ARZ | CHD | MTC - Servers and Software | MTCS SW ARZ CHD Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS SW LAS HEN Remote Video Monitoring Expansion Augment POR20 | SW | LAS | HEN | MTC - Servers and Software | MTCS SW LAS HEN Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS SW LAS HEN Channel Growth Deployment POR20 | SW | LAS | HEN | MTC - Servers and Software | MTCS SW LAS HEN Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS SW LAS HEN MPEG4 Field Transitions Deployment POR20 | SW | LAS | HEN | MTC - Servers and Software | MTCS SW LAS HEN MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15 | Active | EP
MTCS VA HRD VBC Channel Growth Deployment POR20 | VA | HRD | VBC | MTC - Servers and Software | MTCS VA HRD VBC Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS VA HRD VBC PDC Tear Down Deployment POR20 | VA | HRD | VBC | MTC - Servers and Software | MTCS VA HRD VBC PDC Tear Down Deployment POR20 | Labor | Power down, unrack, scrap, and uncable racks | 1 | 2020-01-06 | 2020-02-15 | 2020-10-15 | Active | EP
MTCS VA HRD VBC MPEG4 Field Transitions Deployment POR20 | VA | HRD | VBC | MTC - Servers and Software | MTCS VA HRD VBC MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15 | Active | EP
MTCS VA HRD VBC Remote Video Monitoring Expansion Augment POR20 | VA | HRD | VBC | MTC - Servers and Software | MTCS VA HRD VBC Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS VA NVA MFD Channel Growth Deployment POR20 | VA | NVA | MFD | MTC - Servers and Software | MTCS VA NVA MFD Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS VA NVA MFD MPEG4 Field Transitions Deployment POR20 | VA | NVA | MFD | MTC - Servers and Software | MTCS VA NVA MFD MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15 | Active | EP
MTCS VA NVA MFD Remote Video Monitoring Expansion Augment POR20 | VA | NVA | MFD | MTC - Servers and Software | MTCS VA NVA MFD Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS VA ROA RON Remote Video Monitoring Expansion Augment POR20 | VA | ROA | RON | MTC - Servers and Software | MTCS VA ROA RON Remote Video Monitoring Expansion Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS VA ROA RON Channel Growth Deployment POR20 | VA | ROA | RON | MTC - Servers and Software | MTCS VA ROA RON Channel Growth Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-01-15 | 2020-02-15 | 2020-12-15 | Active | EP
MTCS VA ROA RON MPEG4 Field Transitions Deployment POR20 | VA | ROA | RON | MTC - Servers and Software | MTCS VA ROA RON MPEG4 Field Transitions Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-02-06 | 2020-03-15 | 2020-10-15 | Active | EP
MTCS CE OKC OKC EC 9.0 DTAC 5.2 Centralization Deployment POR20 | CE | OKC | OKC | MTC - Servers and Software | MTCS CE OKC OKC EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS CE OKC OKC PCG VSM Refresh Deployment POR20 | CE | OKC | OKC | MTC - Servers and Software | MTCS CE OKC OKC PCG VSM Refresh Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-03-06 | 2020-04-15 | 2020-07-15 | Active | EP
MTCS CE OKC OKC 1 Way UDCP OOB Deployment POR20 | CE | OKC | OKC | MTC - Servers and Software | MTCS CE OKC OKC 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS CE OKC TUL EC 9.0 DTAC 5.2 Centralization Deployment POR20 | CE | TUL | TUL | MTC - Servers and Software | MTCS CE TUL TUL EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS CE OKC TUL 1 Way UDCP OOB Deployment POR20 | CE | TUL | TUL | MTC - Servers and Software | MTCS CE TUL TUL 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS CA ORG RSM EC 9.0 DTAC 5.2 Centralization Deployment POR20 | CA | ORG | RSM | MTC - Servers and Software | MTCS CA ORG RSM EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS CA ORG RSM 1 Way UDCP OOB Deployment POR20 | CA | ORG | RSM | MTC - Servers and Software | MTCS CA ORG RSM 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS CE KAN WIC EC 9.0 DTAC 5.2 Centralization Deployment POR20 | CE | KAN | WIC | MTC - Servers and Software | MTCS CE KAN WIC EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS CE KAN WIC 1 Way UDCP OOB Deployment POR20 | CE | KAN | WIC | MTC - Servers and Software | MTCS CE KAN WIC 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS CE OMA OMM EC 9.0 DTAC 5.2 Centralization Deployment POR20 | CE | OMA | OMM | MTC - Servers and Software | MTCS CE OMA OMM EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS CE OMA OMM 1 Way UDCP OOB Deployment POR20 | CE | OMA | OMM | MTC - Servers and Software | MTCS CE OMA OMM 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS COR COR ATL MPEG4 VOD Transition Deployment POR20 | COR | COR | ATL | MTC - Servers and Software | MTCS CO COR ATL MPEG4 VOD Transition Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-03-06 | 2020-04-15 | 2020-10-15 | Active | EP
MTCS COR COR ATL Local VOD Packaging Deployment POR20 | COR | COR | ATL | MTC - Servers and Software | MTCS CO COR ATL Local VOD Packaging Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-03-06 | 2020-04-15 | 2020-10-15 | Active | EP
MTCS COR COR ATL VOD Obsolescence Deployment POR20 | COR | COR | ATL | MTC - Servers and Software | MTCS CO COR ATL VOD Obsolescence Deployment POR20 | Critical Facilities | MTC Hub Signaling |  |  |  |  | Deleted | EP
MTCS COR COR ATL VOD Obsolescence Deployment POR20 | COR | COR | ATL | MTC - Servers and Software | MTCS CO COR ATL VOD Obsolescence Deployment POR20 | Critical Facilities | MTC Hub Signaling |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS COR COR ATL Expand Automation Deployment POR20 | COR | COR | ATL | MTC - Servers and Software | MTCS CO COR ATL Expand Automation Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-03-06 | 2020-04-15 | 2020-10-15 | Active | EP
MTCS COR COR ATL SVA Replacement Deployment POR20 | COR | COR | ATL | MTC - Servers and Software | MTCS CO COR ATL SVA Replacement Deployment POR20 | Critical Facilities | MTC Hub Signaling |  |  |  |  | Deleted | EP
MTCS COR COR ATL SVA Replacement Deployment POR20 | COR | COR | ATL | MTC - Servers and Software | MTCS CO COR ATL SVA Replacement Deployment POR20 | Critical Facilities | MTC Hub Signaling |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS COR COR ATL ECS Deployment POR20 | COR | COR | ATL | MTC - Servers and Software | MTCS CO COR ATL ECS Deployment POR20 | Critical Facilities | MTC Hub Signaling |  |  |  |  | Deleted | EP
MTCS COR COR ATL ECS Deployment POR20 | COR | COR | ATL | MTC - Servers and Software | MTCS CO COR ATL ECS Deployment POR20 | Critical Facilities | MTC Hub Signaling |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS NE CON MAN EC 9.0 DTAC 5.2 Centralization Deployment POR20 | NE | CON | MAN | MTC - Servers and Software | MTCS NE CON MAN EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS NE CON MAN 1 Way UDCP OOB Deployment POR20 | NE | CON | MAN | MTC - Servers and Software | MTCS NE CON MAN 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS CA SAN ELC EC 9.0 DTAC 5.2 Centralization Deployment POR20 | CA | SAN | ELC | MTC - Servers and Software | MTCS CA SAN ELC EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS CA SAN ELC PCG VSM Refresh Deployment POR20 | CA | SAN | ELC | MTC - Servers and Software | MTCS CA SAN ELC PCG VSM Refresh Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-03-06 | 2020-04-15 | 2020-07-15 | Active | EP
MTCS COR COR DDR Service Gateway to Regional Servers Deployment POR20 | COR | COR | DDR | MTC - Servers and Software | MTCS CO COR DDR Service Gateway to Regional Servers Deployment POR20 | Labor | Rack and config servers | 1 | 2020-03-06 | 2020-04-15 | 2020-11-15 | Active | EP
MTCS COR COR P6L Lab Firewall Deployment POR20 | COR | COR | P6L | MTC - Servers and Software | MTCS CO COR P6L Lab Firewall Deployment POR20 | Labor | Firewall | 1 | 2020-03-06 | 2020-04-15 | 2020-09-15 | Active | EP
MTCS COR COR P6L Lab Automation Deployment POR20 | COR | COR | P6L | MTC - Servers and Software | MTCS CO COR P6L Lab Automation Deployment POR20 | Labor | IHL |  |  |  |  | Deleted | EP
MTCS COR COR P6L Lab Automation Deployment POR20 | COR | COR | P6L | MTC - Servers and Software | MTCS CO COR P6L Lab Automation Deployment POR20 | Labor | IHL |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS NE CLE CLV EC 9.0 DTAC 5.2 Centralization Deployment POR20 | NE | CLE | CLV | MTC - Servers and Software | MTCS NE CLE CLV EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS NE CLE CLV PCG VSM Refresh Deployment POR20 | NE | CLE | CLV | MTC - Servers and Software | MTCS NE CLE CLV PCG VSM Refresh Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-03-06 | 2020-04-15 | 2020-07-15 | Active | EP
MTCS NE CLE CLV 1 Way UDCP OOB Deployment POR20 | NE | CLE | CLV | MTC - Servers and Software | MTCS NE CLE CLV 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS CA SAN ELC 1 Way UDCP OOB Deployment POR20 | CA | SAN | ELC | MTC - Servers and Software | MTCS CA SAN ELC 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS CA SAB SAB EC 9.0 DTAC 5.2 Centralization Deployment POR20 | CA | SAB | SAB | MTC - Servers and Software | MTCS CA SAB SAB EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS CA SAB SAB PCG VSM Refresh Deployment POR20 | CA | SAB | SAB | MTC - Servers and Software | MTCS CA SAB SAB PCG VSM Refresh Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-03-06 | 2020-04-15 | 2020-07-15 | Active | EP
MTCS CA SAB SAB 1 Way UDCP OOB Deployment POR20 | CA | SAB | SAB | MTC - Servers and Software | MTCS CA SAB SAB 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS CE ARK NWA EC 9.0 DTAC 5.2 Centralization Deployment POR20 | CE | NWA | NWA | MTC - Servers and Software | MTCS CE NWA NWA EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS CE ARK NWA 1 Way UDCP OOB Deployment POR20 | CE | NWA | NWA | MTC - Servers and Software | MTCS CE NWA NWA 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS SE GAN GNS EC 9.0 DTAC 5.2 Centralization Deployment POR20 | SE | GAN | GNS | MTC - Servers and Software | MTCS SE GAN GNS EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS SE GAN GNS PCG VSM Refresh Deployment POR20 | SE | GAN | GNS | MTC - Servers and Software | MTCS SE GAN GNS PCG VSM Refresh Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-03-06 | 2020-04-15 | 2020-07-15 | Active | EP
MTCS SE GAN GNS 1 Way UDCP OOB Deployment POR20 | SE | GAN | GNS | MTC - Servers and Software | MTCS SE GAN GNS 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS SE GLA BTR EC 9.0 DTAC 5.2 Centralization Deployment POR20 | SE | BTR | BTR | MTC - Servers and Software | MTCS SE BTR BTR EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS SE GLA BTR 1 Way UDCP OOB Deployment POR20 | SE | BTR | BTR | MTC - Servers and Software | MTCS SE BTR BTR 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS SW ARZ CHD EC 9.0 DTAC 5.2 Centralization Deployment POR20 | SW | ARZ | CHD | MTC - Servers and Software | MTCS SW ARZ CHD EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS SW ARZ CHD PCG VSM Refresh Deployment POR20 | SW | ARZ | CHD | MTC - Servers and Software | MTCS SW ARZ CHD PCG VSM Refresh Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-03-06 | 2020-04-15 | 2020-07-15 | Active | EP
MTCS SW ARZ CHD 1 Way UDCP OOB Deployment POR20 | SW | ARZ | CHD | MTC - Servers and Software | MTCS SW ARZ CHD 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS SW LAS HEN EC 9.0 DTAC 5.2 Centralization Deployment POR20 | SW | LAS | HEN | MTC - Servers and Software | MTCS SW LAS HEN EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS SW LAS HEN PCG VSM Refresh Deployment POR20 | SW | LAS | HEN | MTC - Servers and Software | MTCS SW LAS HEN PCG VSM Refresh Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-03-06 | 2020-04-15 | 2020-07-15 | Active | EP
MTCS SW LAS HEN 1 Way UDCP OOB Deployment POR20 | SW | LAS | HEN | MTC - Servers and Software | MTCS SW LAS HEN 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS NE RHD WWK EC 9.0 DTAC 5.2 Centralization Deployment POR20 | NE | RHD | WWK | MTC - Servers and Software | MTCS NE RHD WWK EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS NE RHD WWK 1 Way UDCP OOB Deployment POR20 | NE | RHD | WWK | MTC - Servers and Software | MTCS NE RHD WWK 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS SE GLA ELM EC 9.0 DTAC 5.2 Centralization Deployment POR20 | SE | NOR | ELM | MTC - Servers and Software | MTCS SE NOR ELM EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS SE GLA ELM 1 Way UDCP OOB Deployment POR20 | SE | NOR | ELM | MTC - Servers and Software | MTCS SE NOR ELM 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS SE GCT PNS EC 9.0 DTAC 5.2 Centralization Deployment POR20 | SE | GCT | PNS | MTC - Servers and Software | MTCS SE GCT PNS EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS SE GCT PNS PCG VSM Refresh Deployment POR20 | SE | GCT | PNS | MTC - Servers and Software | MTCS SE GCT PNS PCG VSM Refresh Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-03-06 | 2020-04-15 | 2020-07-15 | Active | EP
MTCS SE GCT PNS 1 Way UDCP OOB Deployment POR20 | SE | GCT | PNS | MTC - Servers and Software | MTCS SE GCT PNS 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS SE MGA MCN EC 9.0 DTAC 5.2 Centralization Deployment POR20 | SE | MGA | MCN | MTC - Servers and Software | MTCS SE MGA MCN EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS SE MGA MCN 1 Way UDCP OOB Deployment POR20 | SE | MGA | MCN | MTC - Servers and Software | MTCS SE MGA MCN 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS VA ROA RON EC 9.0 DTAC 5.2 Centralization Deployment POR20 | VA | ROA | RON | MTC - Servers and Software | MTCS VA ROA RON EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS VA ROA RON 1 Way UDCP OOB Deployment POR20 | VA | ROA | RON | MTC - Servers and Software | MTCS VA ROA RON 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS VA HRD VBC EC 9.0 DTAC 5.2 Centralization Deployment POR20 | VA | HRD | VBC | MTC - Servers and Software | MTCS VA HRD VBC EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS VA HRD VBC 1 Way UDCP OOB Deployment POR20 | VA | HRD | VBC | MTC - Servers and Software | MTCS VA HRD VBC 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS VA NVA MFD EC 9.0 DTAC 5.2 Centralization Deployment POR20 | VA | NVA | MFD | MTC - Servers and Software | MTCS VA NVA MFD EC 9_0 DTAC 5_2 Centralization Deployment POR20 | Labor | IHL and contract labor | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS VA NVA MFD PCG VSM Refresh Deployment POR20 | VA | NVA | MFD | MTC - Servers and Software | MTCS VA NVA MFD PCG VSM Refresh Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-03-06 | 2020-04-15 | 2020-07-15 | Active | EP
MTCS VA NVA MFD 1 Way UDCP OOB Deployment POR20 | VA | NVA | MFD | MTC - Servers and Software | MTCS VA NVA MFD 1 Way UDCP OOB Deployment POR20 | Labor | Collapse/combine RF returns, OOB collapse | 1 | 2020-03-06 | 2020-04-15 | 2020-12-15 | Active | EP
MTCS CE OKC OKC EOS Testing Hardware Deployment POR20 | CE | OKC | OKC | MTC - Servers and Software | MTCS CE OKC OKC EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | EP
MTCS CE OKC OKC Hardware Spares Deployment POR20 | CE | OKC | OKC | MTC - Servers and Software | MTCS CE OKC OKC Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | EP
MTCS CE OKC OKC Hardware Spares Deployment POR20 | CE | OKC | OKC | MTC - Servers and Software | MTCS CE OKC OKC Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS CE OKC OKC ATX Centralized Tools Deployment POR20 | CE | OKC | OKC | MTC - Servers and Software | MTCS CE OKC OKC ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | EP
MTCS CE OKC OKC ATX Centralized Tools Deployment POR20 | CE | OKC | OKC | MTC - Servers and Software | MTCS CE OKC OKC ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS CE OKC TUL EOS Testing Hardware Deployment POR20 | CE | TUL | TUL | MTC - Servers and Software | MTCS CE TUL TUL EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | EP
MTCS CE OKC TUL Hardware Spares Deployment POR20 | CE | TUL | TUL | MTC - Servers and Software | MTCS CE TUL TUL Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | EP
MTCS CE OKC TUL Hardware Spares Deployment POR20 | CE | TUL | TUL | MTC - Servers and Software | MTCS CE TUL TUL Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS CE OKC TUL ATX Centralized Tools Deployment POR20 | CE | TUL | TUL | MTC - Servers and Software | MTCS CE TUL TUL ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | EP
MTCS CE OKC TUL ATX Centralized Tools Deployment POR20 | CE | TUL | TUL | MTC - Servers and Software | MTCS CE TUL TUL ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS CA ORG RSM EOS Testing Hardware Deployment POR20 | CA | ORG | RSM | MTC - Servers and Software | MTCS CA ORG RSM EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | EP
MTCS CA ORG RSM Hardware Spares Deployment POR20 | CA | ORG | RSM | MTC - Servers and Software | MTCS CA ORG RSM Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | EP
MTCS CA ORG RSM Hardware Spares Deployment POR20 | CA | ORG | RSM | MTC - Servers and Software | MTCS CA ORG RSM Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS CA ORG RSM ATX Centralized Tools Deployment POR20 | CA | ORG | RSM | MTC - Servers and Software | MTCS CA ORG RSM ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | EP
MTCS CA ORG RSM ATX Centralized Tools Deployment POR20 | CA | ORG | RSM | MTC - Servers and Software | MTCS CA ORG RSM ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS CE KAN WIC EOS Testing Hardware Deployment POR20 | CE | KAN | WIC | MTC - Servers and Software | MTCS CE KAN WIC EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | EP
MTCS CE KAN WIC Hardware Spares Deployment POR20 | CE | KAN | WIC | MTC - Servers and Software | MTCS CE KAN WIC Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | EP
MTCS CE KAN WIC Hardware Spares Deployment POR20 | CE | KAN | WIC | MTC - Servers and Software | MTCS CE KAN WIC Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS CE CAN WIC ATX Centralized Tools Deployment POR20 | CE | KAN | WIC | MTC - Servers and Software | MTCS CE KAN WIC ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | EP
MTCS CE CAN WIC ATX Centralized Tools Deployment POR20 | CE | KAN | WIC | MTC - Servers and Software | MTCS CE KAN WIC ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS CE OMA OMM EOS Testing Hardware Deployment POR20 | CE | OMA | OMM | MTC - Servers and Software | MTCS CE OMA OMM EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | EP
MTCS CE OMA OMM Hardware Spares Deployment POR20 | CE | OMA | OMM | MTC - Servers and Software | MTCS CE OMA OMM Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | EP
MTCS CE OMA OMM Hardware Spares Deployment POR20 | CE | OMA | OMM | MTC - Servers and Software | MTCS CE OMA OMM Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS CE OMA OMM ATX Centralized Tools Deployment POR20 | CE | OMA | OMM | MTC - Servers and Software | MTCS CE OMA OMM ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | EP
MTCS CE OMA OMM ATX Centralized Tools Deployment POR20 | CE | OMA | OMM | MTC - Servers and Software | MTCS CE OMA OMM ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS NE CLE CLV ATX Centralized Tools Deployment POR20 | NE | CLE | CLV | MTC - Servers and Software | MTCS NE CLE CLV ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | EP
MTCS NE CLE CLV ATX Centralized Tools Deployment POR20 | NE | CLE | CLV | MTC - Servers and Software | MTCS NE CLE CLV ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS NE CON MAN EOS Testing Hardware Deployment POR20 | NE | CON | MAN | MTC - Servers and Software | MTCS NE CON MAN EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | EP
MTCS COR COR P6L Lab Remote Phy Deployment POR20 | COR | COR | P6L | MTC - Servers and Software | MTCS CO COR P6L Lab Remote Phy Deployment POR20 | Standard | RPHY | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | EP
MTCS COR COR P6L Lab APEX3000 Deployment POR20 | COR | COR | P6L | MTC - Servers and Software | MTCS CO COR P6L Lab APEX3000 Deployment POR20 | Chassis | APEX3000 | 1 | 2020-07-06 | 2020-08-15 | 2020-09-15 | Active | EP
MTCS COR COR P6L Lab vDCM Deployment POR20 | COR | COR | P6L | MTC - Servers and Software | MTCS CO COR P6L Lab vDCM Deployment POR20 | Chassis | 1x Synamedia D9902 DCM Chassis | 1 | 2020-06-06 | 2020-07-15 | 2020-08-15 | Active | EP
MTCS NE CLE CLV EOS Testing Hardware Deployment POR20 | NE | CLE | CLV | MTC - Servers and Software | MTCS NE CLE CLV EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | EP
MTCS NE CLE CLV Hardware Spares Deployment POR20 | NE | CLE | CLV | MTC - Servers and Software | MTCS NE CLE CLV Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | EP
MTCS NE CLE CLV Hardware Spares Deployment POR20 | NE | CLE | CLV | MTC - Servers and Software | MTCS NE CLE CLV Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS CA SAN ELC EOS Testing Hardware Deployment POR20 | CA | SAN | ELC | MTC - Servers and Software | MTCS CA SAN ELC EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | EP
MTCS CA SAN ELC Hardware Spares Deployment POR20 | CA | SAN | ELC | MTC - Servers and Software | MTCS CA SAN ELC Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | EP
MTCS CA SAN ELC Hardware Spares Deployment POR20 | CA | SAN | ELC | MTC - Servers and Software | MTCS CA SAN ELC Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS CA SAN ELC ATX Centralized Tools Deployment POR20 | CA | SAN | ELC | MTC - Servers and Software | MTCS CA SAN ELC ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | EP
MTCS CA SAN ELC ATX Centralized Tools Deployment POR20 | CA | SAN | ELC | MTC - Servers and Software | MTCS CA SAN ELC ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS CA SAB SAB EOS Testing Hardware Deployment POR20 | CA | SAB | SAB | MTC - Servers and Software | MTCS CA SAB SAB EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-12-15 | Active | EP
MTCS CA SAB SAB Hardware Spares Deployment POR20 | CA | SAB | SAB | MTC - Servers and Software | MTCS CA SAB SAB Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | EP
MTCS CA SAB SAB Hardware Spares Deployment POR20 | CA | SAB | SAB | MTC - Servers and Software | MTCS CA SAB SAB Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS CA SAB SAB ATX Centralized Tools Deployment POR20 | CA | SAB | SAB | MTC - Servers and Software | MTCS CA SAB SAB ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | EP
MTCS CA SAB SAB ATX Centralized Tools Deployment POR20 | CA | SAB | SAB | MTC - Servers and Software | MTCS CA SAB SAB ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS CE ARK NWA EOS Testing Hardware Deployment POR20 | CE | NWA | NWA | MTC - Servers and Software | MTCS CE NWA NWA EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | EP
MTCS CE ARK NWA Hardware Spares Deployment POR20 | CE | NWA | NWA | MTC - Servers and Software | MTCS CE NWA NWA Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | EP
MTCS CE ARK NWA Hardware Spares Deployment POR20 | CE | NWA | NWA | MTC - Servers and Software | MTCS CE NWA NWA Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS CE ARK NWA ATX Centralized Tools Deployment POR20 | CE | NWA | NWA | MTC - Servers and Software | MTCS CE NWA NWA ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | EP
MTCS CE ARK NWA ATX Centralized Tools Deployment POR20 | CE | NWA | NWA | MTC - Servers and Software | MTCS CE NWA NWA ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS SE GAN GNS EOS Testing Hardware Deployment POR20 | SE | GAN | GNS | MTC - Servers and Software | MTCS SE GAN GNS EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | EP
MTCS SE GAN GNS Hardware Spares Deployment POR20 | SE | GAN | GNS | MTC - Servers and Software | MTCS SE GAN GNS Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | EP
MTCS SE GAN GNS Hardware Spares Deployment POR20 | SE | GAN | GNS | MTC - Servers and Software | MTCS SE GAN GNS Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS SE GAN GNS ATX Centralized Tools Deployment POR20 | SE | GAN | GNS | MTC - Servers and Software | MTCS SE GAN GNS ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | EP
MTCS SE GAN GNS ATX Centralized Tools Deployment POR20 | SE | GAN | GNS | MTC - Servers and Software | MTCS SE GAN GNS ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS SE MGA MCN ATX Centralized Tools Deployment POR20 | SE | MGA | MCN | MTC - Servers and Software | MTCS SE MGA MCN ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | EP
MTCS SE MGA MCN ATX Centralized Tools Deployment POR20 | SE | MGA | MCN | MTC - Servers and Software | MTCS SE MGA MCN ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS SW ARZ CHD EOS Testing Hardware Deployment POR20 | SW | ARZ | CHD | MTC - Servers and Software | MTCS SW ARZ CHD EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | EP
MTCS SW ARZ CHD Hardware Spares Deployment POR20 | SW | ARZ | CHD | MTC - Servers and Software | MTCS SW ARZ CHD Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | EP
MTCS SW ARZ CHD Hardware Spares Deployment POR20 | SW | ARZ | CHD | MTC - Servers and Software | MTCS SW ARZ CHD Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS SW ARZ CHD ATX Centralized Tools Deployment POR20 | SW | ARZ | CHD | MTC - Servers and Software | MTCS SW ARZ CHD ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | EP
MTCS SW ARZ CHD ATX Centralized Tools Deployment POR20 | SW | ARZ | CHD | MTC - Servers and Software | MTCS SW ARZ CHD ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS NE CON MAN Hardware Spares Deployment POR20 | NE | CON | MAN | MTC - Servers and Software | MTCS NE CON MAN Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | EP
MTCS NE CON MAN Hardware Spares Deployment POR20 | NE | CON | MAN | MTC - Servers and Software | MTCS NE CON MAN Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS NE CON MAN ATX Centralized Tools Deployment POR20 | NE | CON | MAN | MTC - Servers and Software | MTCS NE CON MAN ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | EP
MTCS NE CON MAN ATX Centralized Tools Deployment POR20 | NE | CON | MAN | MTC - Servers and Software | MTCS NE CON MAN ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS NE RHD WWK EOS Testing Hardware Deployment POR20 | NE | RHD | WWK | MTC - Servers and Software | MTCS NE RHD WWK EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | EP
MTCS NE RHD WWK Hardware Spares Deployment POR20 | NE | RHD | WWK | MTC - Servers and Software | MTCS NE RHD WWK Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | EP
MTCS NE RHD WWK Hardware Spares Deployment POR20 | NE | RHD | WWK | MTC - Servers and Software | MTCS NE RHD WWK Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS NE RHD WWK ATX Centralized Tools Deployment POR20 | NE | RHD | WWK | MTC - Servers and Software | MTCS NE RHD WWK ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | EP
MTCS NE RHD WWK ATX Centralized Tools Deployment POR20 | NE | RHD | WWK | MTC - Servers and Software | MTCS NE RHD WWK ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS SE GLA BTR EOS Testing Hardware Deployment POR20 | SE | BTR | BTR | MTC - Servers and Software | MTCS SE BTR BTR EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | EP
MTCS SE GLA BTR Hardware Spares Deployment POR20 | SE | BTR | BTR | MTC - Servers and Software | MTCS SE BTR BTR Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | EP
MTCS SE GLA BTR Hardware Spares Deployment POR20 | SE | BTR | BTR | MTC - Servers and Software | MTCS SE BTR BTR Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS SE GLA BTR ATX Centralized Tools Deployment POR20 | SE | BTR | BTR | MTC - Servers and Software | MTCS SE BTR BTR ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | EP
MTCS SE GLA BTR ATX Centralized Tools Deployment POR20 | SE | BTR | BTR | MTC - Servers and Software | MTCS SE BTR BTR ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS SE GLA ELM EOS Testing Hardware Deployment POR20 | SE | NOR | ELM | MTC - Servers and Software | MTCS SE NOR ELM EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | EP
MTCS SE GLA ELM Hardware Spares Deployment POR20 | SE | NOR | ELM | MTC - Servers and Software | MTCS SE NOR ELM Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | EP
MTCS SE GLA ELM Hardware Spares Deployment POR20 | SE | NOR | ELM | MTC - Servers and Software | MTCS SE NOR ELM Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS SE GLA ELM ATX Centralized Tools Deployment POR20 | SE | NOR | ELM | MTC - Servers and Software | MTCS SE NOR ELM ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | EP
MTCS SE GLA ELM ATX Centralized Tools Deployment POR20 | SE | NOR | ELM | MTC - Servers and Software | MTCS SE NOR ELM ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS SE GCT PNS EOS Testing Hardware Deployment POR20 | SE | GCT | PNS | MTC - Servers and Software | MTCS SE GCT PNS EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | EP
MTCS SE GCT PNS Hardware Spares Deployment POR20 | SE | GCT | PNS | MTC - Servers and Software | MTCS SE GCT PNS Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | EP
MTCS SE GCT PNS Hardware Spares Deployment POR20 | SE | GCT | PNS | MTC - Servers and Software | MTCS SE GCT PNS Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS SE GCT PNS ATX Centralized Tools Deployment POR20 | SE | GCT | PNS | MTC - Servers and Software | MTCS SE GCT PNS ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | EP
MTCS SE GCT PNS ATX Centralized Tools Deployment POR20 | SE | GCT | PNS | MTC - Servers and Software | MTCS SE GCT PNS ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS SE MGA MCN EOS Testing Hardware Deployment POR20 | SE | MGA | MCN | MTC - Servers and Software | MTCS SE MGA MCN EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | EP
MTCS SE MGA MCN Hardware Spares Deployment POR20 | SE | MGA | MCN | MTC - Servers and Software | MTCS SE MGA MCN Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | EP
MTCS SE MGA MCN Hardware Spares Deployment POR20 | SE | MGA | MCN | MTC - Servers and Software | MTCS SE MGA MCN Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS SW LAS HEN EOS Testing Hardware Deployment POR20 | SW | LAS | HEN | MTC - Servers and Software | MTCS SW LAS HEN EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | EP
MTCS SW LAS HEN Hardware Spares Deployment POR20 | SW | LAS | HEN | MTC - Servers and Software | MTCS SW LAS HEN Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | EP
MTCS SW LAS HEN Hardware Spares Deployment POR20 | SW | LAS | HEN | MTC - Servers and Software | MTCS SW LAS HEN Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS SW LAS HEN ATX Centralized Tools Deployment POR20 | SW | LAS | HEN | MTC - Servers and Software | MTCS SW LAS HEN ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | EP
MTCS SW LAS HEN ATX Centralized Tools Deployment POR20 | SW | LAS | HEN | MTC - Servers and Software | MTCS SW LAS HEN ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS VA NVA MFD ATX Centralized Tools Deployment POR20 | VA | NVA | MFD | MTC - Servers and Software | MTCS VA NVA MFD ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | EP
MTCS VA NVA MFD ATX Centralized Tools Deployment POR20 | VA | NVA | MFD | MTC - Servers and Software | MTCS VA NVA MFD ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS VA HRD VBC EOS Testing Hardware Deployment POR20 | VA | HRD | VBC | MTC - Servers and Software | MTCS VA HRD VBC EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | EP
MTCS VA HRD VBC Hardware Spares Deployment POR20 | VA | HRD | VBC | MTC - Servers and Software | MTCS VA HRD VBC Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | EP
MTCS VA HRD VBC Hardware Spares Deployment POR20 | VA | HRD | VBC | MTC - Servers and Software | MTCS VA HRD VBC Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS VA HRD VBC ATX Centralized Tools Deployment POR20 | VA | HRD | VBC | MTC - Servers and Software | MTCS VA HRD VBC ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | EP
MTCS VA HRD VBC ATX Centralized Tools Deployment POR20 | VA | HRD | VBC | MTC - Servers and Software | MTCS VA HRD VBC ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS VA NVA MFD EOS Testing Hardware Deployment POR20 | VA | NVA | MFD | MTC - Servers and Software | MTCS VA NVA MFD EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | EP
MTCS VA NVA MFD Hardware Spares Deployment POR20 | VA | NVA | MFD | MTC - Servers and Software | MTCS VA NVA MFD Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | EP
MTCS VA NVA MFD Hardware Spares Deployment POR20 | VA | NVA | MFD | MTC - Servers and Software | MTCS VA NVA MFD Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS VA ROA RON EOS Testing Hardware Deployment POR20 | VA | ROA | RON | MTC - Servers and Software | MTCS VA ROA RON EOS Testing Hardware Deployment POR20 | Chassis | EOS testing hardware | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | EP
MTCS VA ROA RON Hardware Spares Deployment POR20 | VA | ROA | RON | MTC - Servers and Software | MTCS VA ROA RON Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | EP
MTCS VA ROA RON Hardware Spares Deployment POR20 | VA | ROA | RON | MTC - Servers and Software | MTCS VA ROA RON Hardware Spares Deployment POR20 | Standard | HW spares |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
MTCS VA ROA RON ATX Centralized Tools Deployment POR20 | VA | ROA | RON | MTC - Servers and Software | MTCS VA ROA RON ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | EP
MTCS VA ROA RON ATX Centralized Tools Deployment POR20 | VA | ROA | RON | MTC - Servers and Software | MTCS VA ROA RON ATX Centralized Tools Deployment POR20 | Labor | Software and 3PL |  |  |  |  | Deleted | Log | Del | SN-0569 | COVID-19 Related | Approved | 2020-05-13 11:46 | Update to POR to align to COVID Deferrals
NR WIC MTC 48 Node Cell | CE | KAN | WIC | MTC 48 Node Cell | NR CE KAN WIC MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-15 | 2020-10-30 | 2020-10-30 | Active | EP
NR WIC MTC 48 Node Cell | CE | KAN | WIC | MTC 48 Node Cell | NR CE KAN WIC MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-15 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR WIC MTC 48 Node Cell | CE | KAN | WIC | MTC 48 Node Cell | NR CE KAN WIC MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-15 | 2020-08-30 | 2020-08-30 | Active | Log | Upd | SN-0733 | New | Approved | 2020-07-10 10:11 | POR update to reflect moving the dollars out of June into August SN 0699 for SWR and CE Dates moved from June to Aug due to ATX backorder of materials
NR WIC MTC 48 Node Cell | CE | KAN | WIC | MTC 48 Node Cell | NR CE KAN WIC MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-15 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0854 | Schedule Change | Approved | 2020-08-21 14:37 | Due to ATX material backlog moving SWR CE CA funding as follows: CE material delivery date 9 9 move dollars into Sept and Oct SWR material delivery date is 9 18 move dollars into Sept and Oct CA material delivery 10 5 moved dollars to October
NR WIC MTC 48 Node Cell | CE | KAN | WIC | MTC 48 Node Cell | NR CE KAN WIC MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-15 | 2020-10-30 | 2020-10-30 | Active | Log | Upd | SN-0946 | Schedule Change | Approved | 2020-09-25 14:18 | Due to ATX constraints the delivery dates have been extended to early to mid October for SWR and Mid Oct to early Nov for CE NE has requested materials for an late November migration
NR BVL MTC 48 Node Cell | CE | NWA | BVL | MTC 48 Node Cell | NR CE NWA BVL MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-15 | 2020-10-30 | 2020-10-30 | Active | EP
NR BVL MTC 48 Node Cell | CE | NWA | BVL | MTC 48 Node Cell | NR CE NWA BVL MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-15 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR BVL MTC 48 Node Cell | CE | NWA | BVL | MTC 48 Node Cell | NR CE NWA BVL MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-15 | 2020-08-30 | 2020-08-30 | Active | Log | Upd | SN-0733 | New | Approved | 2020-07-10 10:11 | POR update to reflect moving the dollars out of June into August SN 0699 for SWR and CE Dates moved from June to Aug due to ATX backorder of materials
NR BVL MTC 48 Node Cell | CE | NWA | BVL | MTC 48 Node Cell | NR CE NWA BVL MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-15 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0854 | Schedule Change | Approved | 2020-08-21 14:37 | Due to ATX material backlog moving SWR CE CA funding as follows: CE material delivery date 9 9 move dollars into Sept and Oct SWR material delivery date is 9 18 move dollars into Sept and Oct CA material delivery 10 5 moved dollars to October
NR BVL MTC 48 Node Cell | CE | NWA | BVL | MTC 48 Node Cell | NR CE NWA BVL MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-15 | 2020-10-30 | 2020-10-30 | Active | Log | Upd | SN-0946 | Schedule Change | Approved | 2020-09-25 14:18 | Due to ATX constraints the delivery dates have been extended to early to mid October for SWR and Mid Oct to early Nov for CE NE has requested materials for an late November migration
NR BLV MTC 48 Node Cell | CE | OMA | BLV | MTC 48 Node Cell | NR CE OMA BLV MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-15 | 2020-10-30 | 2020-10-30 | Active | EP
NR BLV MTC 48 Node Cell | CE | OMA | BLV | MTC 48 Node Cell | NR CE OMA BLV MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-15 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR BLV MTC 48 Node Cell | CE | OMA | BLV | MTC 48 Node Cell | NR CE OMA BLV MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-15 | 2020-08-30 | 2020-08-30 | Active | Log | Upd | SN-0733 | New | Approved | 2020-07-10 10:11 | POR update to reflect moving the dollars out of June into August SN 0699 for SWR and CE Dates moved from June to Aug due to ATX backorder of materials
NR BLV MTC 48 Node Cell | CE | OMA | BLV | MTC 48 Node Cell | NR CE OMA BLV MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-15 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0854 | Schedule Change | Approved | 2020-08-21 14:37 | Due to ATX material backlog moving SWR CE CA funding as follows: CE material delivery date 9 9 move dollars into Sept and Oct SWR material delivery date is 9 18 move dollars into Sept and Oct CA material delivery 10 5 moved dollars to October
NR BLV MTC 48 Node Cell | CE | OMA | BLV | MTC 48 Node Cell | NR CE OMA BLV MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-15 | 2020-10-30 | 2020-10-30 | Active | Log | Upd | SN-0946 | Schedule Change | Approved | 2020-09-25 14:18 | Due to ATX constraints the delivery dates have been extended to early to mid October for SWR and Mid Oct to early Nov for CE NE has requested materials for an late November migration
NR ELK MTC 48 Node Cell | CE | OMA | ELK | MTC 48 Node Cell | NR CE OMA ELK MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-15 | 2020-10-30 | 2020-10-30 | Active | EP
NR ELK MTC 48 Node Cell | CE | OMA | ELK | MTC 48 Node Cell | NR CE OMA ELK MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-15 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR ELK MTC 48 Node Cell | CE | OMA | ELK | MTC 48 Node Cell | NR CE OMA ELK MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-15 | 2020-08-30 | 2020-08-30 | Active | Log | Upd | SN-0733 | New | Approved | 2020-07-10 10:11 | POR update to reflect moving the dollars out of June into August SN 0699 for SWR and CE Dates moved from June to Aug due to ATX backorder of materials
NR ELK MTC 48 Node Cell | CE | OMA | ELK | MTC 48 Node Cell | NR CE OMA ELK MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-15 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0854 | Schedule Change | Approved | 2020-08-21 14:37 | Due to ATX material backlog moving SWR CE CA funding as follows: CE material delivery date 9 9 move dollars into Sept and Oct SWR material delivery date is 9 18 move dollars into Sept and Oct CA material delivery 10 5 moved dollars to October
NR ELK MTC 48 Node Cell | CE | OMA | ELK | MTC 48 Node Cell | NR CE OMA ELK MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-15 | 2020-10-30 | 2020-10-30 | Active | Log | Upd | SN-0946 | Schedule Change | Approved | 2020-09-25 14:18 | Due to ATX constraints the delivery dates have been extended to early to mid October for SWR and Mid Oct to early Nov for CE NE has requested materials for an late November migration
NR ONA MTC 48 Node Cell | CE | OMA | ONA | MTC 48 Node Cell | NR CE OMA ONA MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-15 | 2020-10-30 | 2020-10-30 | Active | EP
NR ONA MTC 48 Node Cell | CE | OMA | ONA | MTC 48 Node Cell | NR CE OMA ONA MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-15 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR ONA MTC 48 Node Cell | CE | OMA | ONA | MTC 48 Node Cell | NR CE OMA ONA MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-15 | 2020-08-30 | 2020-08-30 | Active | Log | Upd | SN-0733 | New | Approved | 2020-07-10 10:11 | POR update to reflect moving the dollars out of June into August SN 0699 for SWR and CE Dates moved from June to Aug due to ATX backorder of materials
NR ONA MTC 48 Node Cell | CE | OMA | ONA | MTC 48 Node Cell | NR CE OMA ONA MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-15 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0854 | Schedule Change | Approved | 2020-08-21 14:37 | Due to ATX material backlog moving SWR CE CA funding as follows: CE material delivery date 9 9 move dollars into Sept and Oct SWR material delivery date is 9 18 move dollars into Sept and Oct CA material delivery 10 5 moved dollars to October
NR ONA MTC 48 Node Cell | CE | OMA | ONA | MTC 48 Node Cell | NR CE OMA ONA MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-15 | 2020-10-30 | 2020-10-30 | Active | Log | Upd | SN-0946 | Schedule Change | Approved | 2020-09-25 14:18 | Due to ATX constraints the delivery dates have been extended to early to mid October for SWR and Mid Oct to early Nov for CE NE has requested materials for an late November migration
NR BEL MTC 48 Node Cell | SW | ARZ | BEL | MTC 48 Node Cell | NR SW ARZ BEL MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-11-30 | 2020-11-30 | Active | EP
NR BEL MTC 48 Node Cell | SW | ARZ | BEL | MTC 48 Node Cell | NR SW ARZ BEL MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR BEL MTC 48 Node Cell | SW | ARZ | BEL | MTC 48 Node Cell | NR SW ARZ BEL MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-08-30 | 2020-08-30 | Active | Log | Upd | SN-0733 | New | Approved | 2020-07-10 10:11 | POR update to reflect moving the dollars out of June into August SN 0699 for SWR and CE Dates moved from June to Aug due to ATX backorder of materials
NR BEL MTC 48 Node Cell | SW | ARZ | BEL | MTC 48 Node Cell | NR SW ARZ BEL MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0854 | Schedule Change | Approved | 2020-08-21 14:37 | Due to ATX material backlog moving SWR CE CA funding as follows: CE material delivery date 9 9 move dollars into Sept and Oct SWR material delivery date is 9 18 move dollars into Sept and Oct CA material delivery 10 5 moved dollars to October
NR BEL MTC 48 Node Cell | SW | ARZ | BEL | MTC 48 Node Cell | NR SW ARZ BEL MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-11-30 | 2020-11-30 | Active | Log | Upd | SN-0946 | Schedule Change | Approved | 2020-09-25 14:18 | Due to ATX constraints the delivery dates have been extended to early to mid October for SWR and Mid Oct to early Nov for CE NE has requested materials for an late November migration
NR BUK MTC 48 Node Cell | SW | ARZ | BUK | MTC 48 Node Cell | NR SW ARZ BUK MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-11-30 | 2020-11-30 | Active | EP
NR BUK MTC 48 Node Cell | SW | ARZ | BUK | MTC 48 Node Cell | NR SW ARZ BUK MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR BUK MTC 48 Node Cell | SW | ARZ | BUK | MTC 48 Node Cell | NR SW ARZ BUK MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-08-30 | 2020-08-30 | Active | Log | Upd | SN-0733 | New | Approved | 2020-07-10 10:11 | POR update to reflect moving the dollars out of June into August SN 0699 for SWR and CE Dates moved from June to Aug due to ATX backorder of materials
NR BUK MTC 48 Node Cell | SW | ARZ | BUK | MTC 48 Node Cell | NR SW ARZ BUK MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0854 | Schedule Change | Approved | 2020-08-21 14:37 | Due to ATX material backlog moving SWR CE CA funding as follows: CE material delivery date 9 9 move dollars into Sept and Oct SWR material delivery date is 9 18 move dollars into Sept and Oct CA material delivery 10 5 moved dollars to October
NR BUK MTC 48 Node Cell | SW | ARZ | BUK | MTC 48 Node Cell | NR SW ARZ BUK MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-11-30 | 2020-11-30 | Active | Log | Upd | SN-0946 | Schedule Change | Approved | 2020-09-25 14:18 | Due to ATX constraints the delivery dates have been extended to early to mid October for SWR and Mid Oct to early Nov for CE NE has requested materials for an late November migration
NR CHD MTC 48 Node Cell | SW | ARZ | CHD | MTC 48 Node Cell | NR SW ARZ CHD MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-11-30 | 2020-11-30 | Active | EP
NR CHD MTC 48 Node Cell | SW | ARZ | CHD | MTC 48 Node Cell | NR SW ARZ CHD MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR CHD MTC 48 Node Cell | SW | ARZ | CHD | MTC 48 Node Cell | NR SW ARZ CHD MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-08-30 | 2020-08-30 | Active | Log | Upd | SN-0733 | New | Approved | 2020-07-10 10:11 | POR update to reflect moving the dollars out of June into August SN 0699 for SWR and CE Dates moved from June to Aug due to ATX backorder of materials
NR CHD MTC 48 Node Cell | SW | ARZ | CHD | MTC 48 Node Cell | NR SW ARZ CHD MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0854 | Schedule Change | Approved | 2020-08-21 14:37 | Due to ATX material backlog moving SWR CE CA funding as follows: CE material delivery date 9 9 move dollars into Sept and Oct SWR material delivery date is 9 18 move dollars into Sept and Oct CA material delivery 10 5 moved dollars to October
NR CHD MTC 48 Node Cell | SW | ARZ | CHD | MTC 48 Node Cell | NR SW ARZ CHD MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-11-30 | 2020-11-30 | Active | Log | Upd | SN-0946 | Schedule Change | Approved | 2020-09-25 14:18 | Due to ATX constraints the delivery dates have been extended to early to mid October for SWR and Mid Oct to early Nov for CE NE has requested materials for an late November migration
NR FWL MTC 48 Node Cell | SW | ARZ | FWL | MTC 48 Node Cell | NR SW ARZ FWL MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-09-30 | 2020-09-30 | Active | EP
NR FWL MTC 48 Node Cell | SW | ARZ | FWL | MTC 48 Node Cell | NR SW ARZ FWL MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR FWL MTC 48 Node Cell | SW | ARZ | FWL | MTC 48 Node Cell | NR SW ARZ FWL MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-08-30 | 2020-08-30 | Active | Log | Upd | SN-0733 | New | Approved | 2020-07-10 10:11 | POR update to reflect moving the dollars out of June into August SN 0699 for SWR and CE Dates moved from June to Aug due to ATX backorder of materials
NR FWL MTC 48 Node Cell | SW | ARZ | FWL | MTC 48 Node Cell | NR SW ARZ FWL MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0854 | Schedule Change | Approved | 2020-08-21 14:37 | Due to ATX material backlog moving SWR CE CA funding as follows: CE material delivery date 9 9 move dollars into Sept and Oct SWR material delivery date is 9 18 move dollars into Sept and Oct CA material delivery 10 5 moved dollars to October
NR MCD MTC 48 Node Cell | SW | ARZ | MCD | MTC 48 Node Cell | NR SW ARZ MCD MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-11-30 | 2020-11-30 | Active | EP
NR MCD MTC 48 Node Cell | SW | ARZ | MCD | MTC 48 Node Cell | NR SW ARZ MCD MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR MCD MTC 48 Node Cell | SW | ARZ | MCD | MTC 48 Node Cell | NR SW ARZ MCD MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-08-30 | 2020-08-30 | Active | Log | Upd | SN-0733 | New | Approved | 2020-07-10 10:11 | POR update to reflect moving the dollars out of June into August SN 0699 for SWR and CE Dates moved from June to Aug due to ATX backorder of materials
NR MCD MTC 48 Node Cell | SW | ARZ | MCD | MTC 48 Node Cell | NR SW ARZ MCD MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0854 | Schedule Change | Approved | 2020-08-21 14:37 | Due to ATX material backlog moving SWR CE CA funding as follows: CE material delivery date 9 9 move dollars into Sept and Oct SWR material delivery date is 9 18 move dollars into Sept and Oct CA material delivery 10 5 moved dollars to October
NR MCD MTC 48 Node Cell | SW | ARZ | MCD | MTC 48 Node Cell | NR SW ARZ MCD MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-11-30 | 2020-11-30 | Active | Log | Upd | SN-0946 | Schedule Change | Approved | 2020-09-25 14:18 | Due to ATX constraints the delivery dates have been extended to early to mid October for SWR and Mid Oct to early Nov for CE NE has requested materials for an late November migration
NR MSA MTC 48 Node Cell | SW | ARZ | MSA | MTC 48 Node Cell | NR SW ARZ MSA MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-09-30 | 2020-09-30 | Active | EP
NR MSA MTC 48 Node Cell | SW | ARZ | MSA | MTC 48 Node Cell | NR SW ARZ MSA MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR MSA MTC 48 Node Cell | SW | ARZ | MSA | MTC 48 Node Cell | NR SW ARZ MSA MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-08-30 | 2020-08-30 | Active | Log | Upd | SN-0733 | New | Approved | 2020-07-10 10:11 | POR update to reflect moving the dollars out of June into August SN 0699 for SWR and CE Dates moved from June to Aug due to ATX backorder of materials
NR MSA MTC 48 Node Cell | SW | ARZ | MSA | MTC 48 Node Cell | NR SW ARZ MSA MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0854 | Schedule Change | Approved | 2020-08-21 14:37 | Due to ATX material backlog moving SWR CE CA funding as follows: CE material delivery date 9 9 move dollars into Sept and Oct SWR material delivery date is 9 18 move dollars into Sept and Oct CA material delivery 10 5 moved dollars to October
NR NSC MTC 48 Node Cell | SW | ARZ | NSC | MTC 48 Node Cell | NR SW ARZ NSC MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-11-30 | 2020-11-30 | Active | EP
NR NSC MTC 48 Node Cell | SW | ARZ | NSC | MTC 48 Node Cell | NR SW ARZ NSC MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR NSC MTC 48 Node Cell | SW | ARZ | NSC | MTC 48 Node Cell | NR SW ARZ NSC MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-08-30 | 2020-08-30 | Active | Log | Upd | SN-0733 | New | Approved | 2020-07-10 10:11 | POR update to reflect moving the dollars out of June into August SN 0699 for SWR and CE Dates moved from June to Aug due to ATX backorder of materials
NR NSC MTC 48 Node Cell | SW | ARZ | NSC | MTC 48 Node Cell | NR SW ARZ NSC MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0854 | Schedule Change | Approved | 2020-08-21 14:37 | Due to ATX material backlog moving SWR CE CA funding as follows: CE material delivery date 9 9 move dollars into Sept and Oct SWR material delivery date is 9 18 move dollars into Sept and Oct CA material delivery 10 5 moved dollars to October
NR NSC MTC 48 Node Cell | SW | ARZ | NSC | MTC 48 Node Cell | NR SW ARZ NSC MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-11-30 | 2020-11-30 | Active | Log | Upd | SN-0946 | Schedule Change | Approved | 2020-09-25 14:18 | Due to ATX constraints the delivery dates have been extended to early to mid October for SWR and Mid Oct to early Nov for CE NE has requested materials for an late November migration
NR PEO MTC 48 Node Cell | SW | ARZ | PEO | MTC 48 Node Cell | NR SW ARZ PEO MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-11-30 | 2020-11-30 | Active | EP
NR PEO MTC 48 Node Cell | SW | ARZ | PEO | MTC 48 Node Cell | NR SW ARZ PEO MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR PEO MTC 48 Node Cell | SW | ARZ | PEO | MTC 48 Node Cell | NR SW ARZ PEO MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-08-30 | 2020-08-30 | Active | Log | Upd | SN-0733 | New | Approved | 2020-07-10 10:11 | POR update to reflect moving the dollars out of June into August SN 0699 for SWR and CE Dates moved from June to Aug due to ATX backorder of materials
NR PEO MTC 48 Node Cell | SW | ARZ | PEO | MTC 48 Node Cell | NR SW ARZ PEO MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0854 | Schedule Change | Approved | 2020-08-21 14:37 | Due to ATX material backlog moving SWR CE CA funding as follows: CE material delivery date 9 9 move dollars into Sept and Oct SWR material delivery date is 9 18 move dollars into Sept and Oct CA material delivery 10 5 moved dollars to October
NR PEO MTC 48 Node Cell | SW | ARZ | PEO | MTC 48 Node Cell | NR SW ARZ PEO MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-11-30 | 2020-11-30 | Active | Log | Upd | SN-0946 | Schedule Change | Approved | 2020-09-25 14:18 | Due to ATX constraints the delivery dates have been extended to early to mid October for SWR and Mid Oct to early Nov for CE NE has requested materials for an late November migration
NR PNL MTC 48 Node Cell | SW | ARZ | PNL | MTC 48 Node Cell | NR SW ARZ PNL MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-11-30 | 2020-11-30 | Active | EP
NR PNL MTC 48 Node Cell | SW | ARZ | PNL | MTC 48 Node Cell | NR SW ARZ PNL MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR PNL MTC 48 Node Cell | SW | ARZ | PNL | MTC 48 Node Cell | NR SW ARZ PNL MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-08-30 | 2020-08-30 | Active | Log | Upd | SN-0733 | New | Approved | 2020-07-10 10:11 | POR update to reflect moving the dollars out of June into August SN 0699 for SWR and CE Dates moved from June to Aug due to ATX backorder of materials
NR PNL MTC 48 Node Cell | SW | ARZ | PNL | MTC 48 Node Cell | NR SW ARZ PNL MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0854 | Schedule Change | Approved | 2020-08-21 14:37 | Due to ATX material backlog moving SWR CE CA funding as follows: CE material delivery date 9 9 move dollars into Sept and Oct SWR material delivery date is 9 18 move dollars into Sept and Oct CA material delivery 10 5 moved dollars to October
NR PNL MTC 48 Node Cell | SW | ARZ | PNL | MTC 48 Node Cell | NR SW ARZ PNL MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-11-30 | 2020-11-30 | Active | Log | Upd | SN-0946 | Schedule Change | Approved | 2020-09-25 14:18 | Due to ATX constraints the delivery dates have been extended to early to mid October for SWR and Mid Oct to early Nov for CE NE has requested materials for an late November migration
NR SSC MTC 48 Node Cell | SW | ARZ | SSC | MTC 48 Node Cell | NR SW ARZ SSC MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-11-30 | 2020-11-30 | Active | EP
NR SSC MTC 48 Node Cell | SW | ARZ | SSC | MTC 48 Node Cell | NR SW ARZ SSC MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR SSC MTC 48 Node Cell | SW | ARZ | SSC | MTC 48 Node Cell | NR SW ARZ SSC MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-08-30 | 2020-08-30 | Active | Log | Upd | SN-0733 | New | Approved | 2020-07-10 10:11 | POR update to reflect moving the dollars out of June into August SN 0699 for SWR and CE Dates moved from June to Aug due to ATX backorder of materials
NR SSC MTC 48 Node Cell | SW | ARZ | SSC | MTC 48 Node Cell | NR SW ARZ SSC MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0854 | Schedule Change | Approved | 2020-08-21 14:37 | Due to ATX material backlog moving SWR CE CA funding as follows: CE material delivery date 9 9 move dollars into Sept and Oct SWR material delivery date is 9 18 move dollars into Sept and Oct CA material delivery 10 5 moved dollars to October
NR SSC MTC 48 Node Cell | SW | ARZ | SSC | MTC 48 Node Cell | NR SW ARZ SSC MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-11-30 | 2020-11-30 | Active | Log | Upd | SN-0946 | Schedule Change | Approved | 2020-09-25 14:18 | Due to ATX constraints the delivery dates have been extended to early to mid October for SWR and Mid Oct to early Nov for CE NE has requested materials for an late November migration
NR TUC MTC 48 Node Cell | SW | ARZ | TUC | MTC 48 Node Cell | NR SW ARZ TUC MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-11-30 | 2020-11-30 | Active | EP
NR TUC MTC 48 Node Cell | SW | ARZ | TUC | MTC 48 Node Cell | NR SW ARZ TUC MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR TUC MTC 48 Node Cell | SW | ARZ | TUC | MTC 48 Node Cell | NR SW ARZ TUC MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-08-30 | 2020-08-30 | Active | Log | Upd | SN-0733 | New | Approved | 2020-07-10 10:11 | POR update to reflect moving the dollars out of June into August SN 0699 for SWR and CE Dates moved from June to Aug due to ATX backorder of materials
NR TUC MTC 48 Node Cell | SW | ARZ | TUC | MTC 48 Node Cell | NR SW ARZ TUC MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0854 | Schedule Change | Approved | 2020-08-21 14:37 | Due to ATX material backlog moving SWR CE CA funding as follows: CE material delivery date 9 9 move dollars into Sept and Oct SWR material delivery date is 9 18 move dollars into Sept and Oct CA material delivery 10 5 moved dollars to October
NR TUC MTC 48 Node Cell | SW | ARZ | TUC | MTC 48 Node Cell | NR SW ARZ TUC MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-11-30 | 2020-11-30 | Active | Log | Upd | SN-0946 | Schedule Change | Approved | 2020-09-25 14:18 | Due to ATX constraints the delivery dates have been extended to early to mid October for SWR and Mid Oct to early Nov for CE NE has requested materials for an late November migration
NR VSA MTC 48 Node Cell | SW | ARZ | VSA | MTC 48 Node Cell | NR SW ARZ VSA MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-11-30 | 2020-11-30 | Active | EP
NR VSA MTC 48 Node Cell | SW | ARZ | VSA | MTC 48 Node Cell | NR SW ARZ VSA MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR VSA MTC 48 Node Cell | SW | ARZ | VSA | MTC 48 Node Cell | NR SW ARZ VSA MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-08-30 | 2020-08-30 | Active | Log | Upd | SN-0733 | New | Approved | 2020-07-10 10:11 | POR update to reflect moving the dollars out of June into August SN 0699 for SWR and CE Dates moved from June to Aug due to ATX backorder of materials
NR VSA MTC 48 Node Cell | SW | ARZ | VSA | MTC 48 Node Cell | NR SW ARZ VSA MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0854 | Schedule Change | Approved | 2020-08-21 14:37 | Due to ATX material backlog moving SWR CE CA funding as follows: CE material delivery date 9 9 move dollars into Sept and Oct SWR material delivery date is 9 18 move dollars into Sept and Oct CA material delivery 10 5 moved dollars to October
NR VSA MTC 48 Node Cell | SW | ARZ | VSA | MTC 48 Node Cell | NR SW ARZ VSA MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-11-30 | 2020-11-30 | Active | Log | Upd | SN-0946 | Schedule Change | Approved | 2020-09-25 14:18 | Due to ATX constraints the delivery dates have been extended to early to mid October for SWR and Mid Oct to early Nov for CE NE has requested materials for an late November migration
NR ALI MTC 48 Node Cell | SW | LAS | ALI | MTC 48 Node Cell | NR SW LAS ALI MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-09-30 | 2020-09-30 | Active | EP
NR ALI MTC 48 Node Cell | SW | LAS | ALI | MTC 48 Node Cell | NR SW LAS ALI MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR ALI MTC 48 Node Cell | SW | LAS | ALI | MTC 48 Node Cell | NR SW LAS ALI MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-08-30 | 2020-08-30 | Active | Log | Upd | SN-0733 | New | Approved | 2020-07-10 10:11 | POR update to reflect moving the dollars out of June into August SN 0699 for SWR and CE Dates moved from June to Aug due to ATX backorder of materials
NR ALI MTC 48 Node Cell | SW | LAS | ALI | MTC 48 Node Cell | NR SW LAS ALI MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0854 | Schedule Change | Approved | 2020-08-21 14:37 | Due to ATX material backlog moving SWR CE CA funding as follows: CE material delivery date 9 9 move dollars into Sept and Oct SWR material delivery date is 9 18 move dollars into Sept and Oct CA material delivery 10 5 moved dollars to October
NR BLU MTC 48 Node Cell | SW | LAS | BLU | MTC 48 Node Cell | NR SW LAS BLU MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-09-30 | 2020-09-30 | Active | EP
NR BLU MTC 48 Node Cell | SW | LAS | BLU | MTC 48 Node Cell | NR SW LAS BLU MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR BLU MTC 48 Node Cell | SW | LAS | BLU | MTC 48 Node Cell | NR SW LAS BLU MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-08-30 | 2020-08-30 | Active | Log | Upd | SN-0733 | New | Approved | 2020-07-10 10:11 | POR update to reflect moving the dollars out of June into August SN 0699 for SWR and CE Dates moved from June to Aug due to ATX backorder of materials
NR BLU MTC 48 Node Cell | SW | LAS | BLU | MTC 48 Node Cell | NR SW LAS BLU MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0854 | Schedule Change | Approved | 2020-08-21 14:37 | Due to ATX material backlog moving SWR CE CA funding as follows: CE material delivery date 9 9 move dollars into Sept and Oct SWR material delivery date is 9 18 move dollars into Sept and Oct CA material delivery 10 5 moved dollars to October
NR ERN MTC 48 Node Cell | SW | LAS | ERN | MTC 48 Node Cell | NR SW LAS ERN MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-09-30 | 2020-09-30 | Active | EP
NR ERN MTC 48 Node Cell | SW | LAS | ERN | MTC 48 Node Cell | NR SW LAS ERN MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR ERN MTC 48 Node Cell | SW | LAS | ERN | MTC 48 Node Cell | NR SW LAS ERN MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-08-30 | 2020-08-30 | Active | Log | Upd | SN-0733 | New | Approved | 2020-07-10 10:11 | POR update to reflect moving the dollars out of June into August SN 0699 for SWR and CE Dates moved from June to Aug due to ATX backorder of materials
NR ERN MTC 48 Node Cell | SW | LAS | ERN | MTC 48 Node Cell | NR SW LAS ERN MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0854 | Schedule Change | Approved | 2020-08-21 14:37 | Due to ATX material backlog moving SWR CE CA funding as follows: CE material delivery date 9 9 move dollars into Sept and Oct SWR material delivery date is 9 18 move dollars into Sept and Oct CA material delivery 10 5 moved dollars to October
NR HEN MTC 48 Node Cell | SW | LAS | HEN | MTC 48 Node Cell | NR SW LAS HEN MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-09-30 | 2020-09-30 | Active | EP
NR HEN MTC 48 Node Cell | SW | LAS | HEN | MTC 48 Node Cell | NR SW LAS HEN MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR HEN MTC 48 Node Cell | SW | LAS | HEN | MTC 48 Node Cell | NR SW LAS HEN MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-08-30 | 2020-08-30 | Active | Log | Upd | SN-0733 | New | Approved | 2020-07-10 10:11 | POR update to reflect moving the dollars out of June into August SN 0699 for SWR and CE Dates moved from June to Aug due to ATX backorder of materials
NR HEN MTC 48 Node Cell | SW | LAS | HEN | MTC 48 Node Cell | NR SW LAS HEN MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0854 | Schedule Change | Approved | 2020-08-21 14:37 | Due to ATX material backlog moving SWR CE CA funding as follows: CE material delivery date 9 9 move dollars into Sept and Oct SWR material delivery date is 9 18 move dollars into Sept and Oct CA material delivery 10 5 moved dollars to October
NR TEN MTC 48 Node Cell | SW | LAS | TEN | MTC 48 Node Cell | NR SW LAS TEN MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-09-30 | 2020-09-30 | Active | EP
NR TEN MTC 48 Node Cell | SW | LAS | TEN | MTC 48 Node Cell | NR SW LAS TEN MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR TEN MTC 48 Node Cell | SW | LAS | TEN | MTC 48 Node Cell | NR SW LAS TEN MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-08-30 | 2020-08-30 | Active | Log | Upd | SN-0733 | New | Approved | 2020-07-10 10:11 | POR update to reflect moving the dollars out of June into August SN 0699 for SWR and CE Dates moved from June to Aug due to ATX backorder of materials
NR TEN MTC 48 Node Cell | SW | LAS | TEN | MTC 48 Node Cell | NR SW LAS TEN MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0854 | Schedule Change | Approved | 2020-08-21 14:37 | Due to ATX material backlog moving SWR CE CA funding as follows: CE material delivery date 9 9 move dollars into Sept and Oct SWR material delivery date is 9 18 move dollars into Sept and Oct CA material delivery 10 5 moved dollars to October
NR VLY MTC 48 Node Cell | SW | LAS | VLY | MTC 48 Node Cell | NR SW LAS VLY MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-09-30 | 2020-09-30 | Active | EP
NR VLY MTC 48 Node Cell | SW | LAS | VLY | MTC 48 Node Cell | NR SW LAS VLY MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR VLY MTC 48 Node Cell | SW | LAS | VLY | MTC 48 Node Cell | NR SW LAS VLY MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-08-30 | 2020-08-30 | Active | Log | Upd | SN-0733 | New | Approved | 2020-07-10 10:11 | POR update to reflect moving the dollars out of June into August SN 0699 for SWR and CE Dates moved from June to Aug due to ATX backorder of materials
NR VLY MTC 48 Node Cell | SW | LAS | VLY | MTC 48 Node Cell | NR SW LAS VLY MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-05-30 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0854 | Schedule Change | Approved | 2020-08-21 14:37 | Due to ATX material backlog moving SWR CE CA funding as follows: CE material delivery date 9 9 move dollars into Sept and Oct SWR material delivery date is 9 18 move dollars into Sept and Oct CA material delivery 10 5 moved dollars to October
NR SAB Q4 MTC 48 Node Cell | CA | SAB | SAB | MTC 48 Node Cell | NR CA SAB SAB MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-10-01 | 2020-10-30 | 2020-10-30 | Active | EP
NR SAB Q4 MTC 48 Node Cell | CA | SAB | SAB | MTC 48 Node Cell | NR CA SAB SAB MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-10-01 | 2021-04-30 | 2021-04-30 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR SAB Q4 MTC 48 Node Cell | CA | SAB | SAB | MTC 48 Node Cell | NR CA SAB SAB MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-10-01 | 2020-10-30 | 2020-10-30 | Active | Log | Upd | SN-0854 | Schedule Change | Approved | 2020-08-21 14:37 | Due to ATX material backlog moving SWR CE CA funding as follows: CE material delivery date 9 9 move dollars into Sept and Oct SWR material delivery date is 9 18 move dollars into Sept and Oct CA material delivery 10 5 moved dollars to October
NR GDY Q3 MTC 48 Node Cell | CE | KAN | GDY | MTC 48 Node Cell | NR CE KAN GDY MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | EP
NR GDY Q3 MTC 48 Node Cell | CE | KAN | GDY | MTC 48 Node Cell | NR CE KAN GDY MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR GDY Q3 MTC 48 Node Cell | CE | KAN | GDY | MTC 48 Node Cell | NR CE KAN GDY MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0854 | Schedule Change | Approved | 2020-08-21 14:37 | Due to ATX material backlog moving SWR CE CA funding as follows: CE material delivery date 9 9 move dollars into Sept and Oct SWR material delivery date is 9 18 move dollars into Sept and Oct CA material delivery 10 5 moved dollars to October
NR HUT Q3 MTC 48 Node Cell | CE | KAN | HUT | MTC 48 Node Cell | NR CE KAN HUT MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-10-30 | 2020-10-30 | Active | EP
NR HUT Q3 MTC 48 Node Cell | CE | KAN | HUT | MTC 48 Node Cell | NR CE KAN HUT MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR HUT Q3 MTC 48 Node Cell | CE | KAN | HUT | MTC 48 Node Cell | NR CE KAN HUT MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0854 | Schedule Change | Approved | 2020-08-21 14:37 | Due to ATX material backlog moving SWR CE CA funding as follows: CE material delivery date 9 9 move dollars into Sept and Oct SWR material delivery date is 9 18 move dollars into Sept and Oct CA material delivery 10 5 moved dollars to October
NR HUT Q3 MTC 48 Node Cell | CE | KAN | HUT | MTC 48 Node Cell | NR CE KAN HUT MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-10-30 | 2020-10-30 | Active | Log | Upd | SN-0946 | Schedule Change | Approved | 2020-09-25 14:18 | Due to ATX constraints the delivery dates have been extended to early to mid October for SWR and Mid Oct to early Nov for CE NE has requested materials for an late November migration
NR MPN Q3 MTC 48 Node Cell | CE | KAN | MPN | MTC 48 Node Cell | NR CE KAN MPN MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-10-30 | 2020-10-30 | Active | EP
NR MPN Q3 MTC 48 Node Cell | CE | KAN | MPN | MTC 48 Node Cell | NR CE KAN MPN MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR MPN Q3 MTC 48 Node Cell | CE | KAN | MPN | MTC 48 Node Cell | NR CE KAN MPN MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0854 | Schedule Change | Approved | 2020-08-21 14:37 | Due to ATX material backlog moving SWR CE CA funding as follows: CE material delivery date 9 9 move dollars into Sept and Oct SWR material delivery date is 9 18 move dollars into Sept and Oct CA material delivery 10 5 moved dollars to October
NR MPN Q3 MTC 48 Node Cell | CE | KAN | MPN | MTC 48 Node Cell | NR CE KAN MPN MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-10-30 | 2020-10-30 | Active | Log | Upd | SN-0946 | Schedule Change | Approved | 2020-09-25 14:18 | Due to ATX constraints the delivery dates have been extended to early to mid October for SWR and Mid Oct to early Nov for CE NE has requested materials for an late November migration
NR TOP Q3 MTC 48 Node Cell | CE | KAN | TOP | MTC 48 Node Cell | NR CE KAN TOP MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-10-30 | 2020-10-30 | Active | EP
NR TOP Q3 MTC 48 Node Cell | CE | KAN | TOP | MTC 48 Node Cell | NR CE KAN TOP MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR TOP Q3 MTC 48 Node Cell | CE | KAN | TOP | MTC 48 Node Cell | NR CE KAN TOP MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0854 | Schedule Change | Approved | 2020-08-21 14:37 | Due to ATX material backlog moving SWR CE CA funding as follows: CE material delivery date 9 9 move dollars into Sept and Oct SWR material delivery date is 9 18 move dollars into Sept and Oct CA material delivery 10 5 moved dollars to October
NR TOP Q3 MTC 48 Node Cell | CE | KAN | TOP | MTC 48 Node Cell | NR CE KAN TOP MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-10-30 | 2020-10-30 | Active | Log | Upd | SN-0946 | Schedule Change | Approved | 2020-09-25 14:18 | Due to ATX constraints the delivery dates have been extended to early to mid October for SWR and Mid Oct to early Nov for CE NE has requested materials for an late November migration
NR WIC Q3 MTC 48 Node Cell | CE | KAN | WIC | MTC 48 Node Cell | NR CE KAN WIC MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-10-30 | 2020-10-30 | Active | EP
NR WIC Q3 MTC 48 Node Cell | CE | KAN | WIC | MTC 48 Node Cell | NR CE KAN WIC MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR WIC Q3 MTC 48 Node Cell | CE | KAN | WIC | MTC 48 Node Cell | NR CE KAN WIC MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0854 | Schedule Change | Approved | 2020-08-21 14:37 | Due to ATX material backlog moving SWR CE CA funding as follows: CE material delivery date 9 9 move dollars into Sept and Oct SWR material delivery date is 9 18 move dollars into Sept and Oct CA material delivery 10 5 moved dollars to October
NR WIC Q3 MTC 48 Node Cell | CE | KAN | WIC | MTC 48 Node Cell | NR CE KAN WIC MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-10-30 | 2020-10-30 | Active | Log | Upd | SN-0946 | Schedule Change | Approved | 2020-09-25 14:18 | Due to ATX constraints the delivery dates have been extended to early to mid October for SWR and Mid Oct to early Nov for CE NE has requested materials for an late November migration
NR NWA Q3 MTC 48 Node Cell | CE | NWA | NWA | MTC 48 Node Cell | NR CE NWA NWA MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-10-30 | 2020-10-30 | Active | EP
NR NWA Q3 MTC 48 Node Cell | CE | NWA | NWA | MTC 48 Node Cell | NR CE NWA NWA MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR NWA Q3 MTC 48 Node Cell | CE | NWA | NWA | MTC 48 Node Cell | NR CE NWA NWA MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0854 | Schedule Change | Approved | 2020-08-21 14:37 | Due to ATX material backlog moving SWR CE CA funding as follows: CE material delivery date 9 9 move dollars into Sept and Oct SWR material delivery date is 9 18 move dollars into Sept and Oct CA material delivery 10 5 moved dollars to October
NR NWA Q3 MTC 48 Node Cell | CE | NWA | NWA | MTC 48 Node Cell | NR CE NWA NWA MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-10-30 | 2020-10-30 | Active | Log | Upd | SN-0946 | Schedule Change | Approved | 2020-09-25 14:18 | Due to ATX constraints the delivery dates have been extended to early to mid October for SWR and Mid Oct to early Nov for CE NE has requested materials for an late November migration
NR BLV Q3 MTC 48 Node Cell | CE | OMA | BLV | MTC 48 Node Cell | NR CE OMA BLV MTC 48 Node Cell Augment POR20_0 | Labor | No Equipment | 1 | 2020-07-01 | 2020-10-30 | 2020-10-30 | Active | EP
NR BLV Q3 MTC 48 Node Cell | CE | OMA | BLV | MTC 48 Node Cell | NR CE OMA BLV MTC 48 Node Cell Augment POR20_0 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR BLV Q3 MTC 48 Node Cell | CE | OMA | BLV | MTC 48 Node Cell | NR CE OMA BLV MTC 48 Node Cell Augment POR20_0 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0854 | Schedule Change | Approved | 2020-08-21 14:37 | Due to ATX material backlog moving SWR CE CA funding as follows: CE material delivery date 9 9 move dollars into Sept and Oct SWR material delivery date is 9 18 move dollars into Sept and Oct CA material delivery 10 5 moved dollars to October
NR BLV Q3 MTC 48 Node Cell | CE | OMA | BLV | MTC 48 Node Cell | NR CE OMA BLV MTC 48 Node Cell Augment POR20_0 | Labor | No Equipment | 1 | 2020-07-01 | 2020-10-30 | 2020-10-30 | Active | Log | Upd | SN-0946 | Schedule Change | Approved | 2020-09-25 14:18 | Due to ATX constraints the delivery dates have been extended to early to mid October for SWR and Mid Oct to early Nov for CE NE has requested materials for an late November migration
NR ELK Q3 MTC 48 Node Cell | CE | OMA | ELK | MTC 48 Node Cell | NR CE OMA ELK MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-10-30 | 2020-10-30 | Active | EP
NR ELK Q3 MTC 48 Node Cell | CE | OMA | ELK | MTC 48 Node Cell | NR CE OMA ELK MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR ELK Q3 MTC 48 Node Cell | CE | OMA | ELK | MTC 48 Node Cell | NR CE OMA ELK MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0854 | Schedule Change | Approved | 2020-08-21 14:37 | Due to ATX material backlog moving SWR CE CA funding as follows: CE material delivery date 9 9 move dollars into Sept and Oct SWR material delivery date is 9 18 move dollars into Sept and Oct CA material delivery 10 5 moved dollars to October
NR ELK Q3 MTC 48 Node Cell | CE | OMA | ELK | MTC 48 Node Cell | NR CE OMA ELK MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-10-30 | 2020-10-30 | Active | Log | Upd | SN-0946 | Schedule Change | Approved | 2020-09-25 14:18 | Due to ATX constraints the delivery dates have been extended to early to mid October for SWR and Mid Oct to early Nov for CE NE has requested materials for an late November migration
NR ONA Q3 MTC 48 Node Cell | CE | OMA | ONA | MTC 48 Node Cell | NR CE OMA ONA MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-10-30 | 2020-10-30 | Active | EP
NR ONA Q3 MTC 48 Node Cell | CE | OMA | ONA | MTC 48 Node Cell | NR CE OMA ONA MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-08-30 | 2020-08-30 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR ONA Q3 MTC 48 Node Cell | CE | OMA | ONA | MTC 48 Node Cell | NR CE OMA ONA MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0854 | Schedule Change | Approved | 2020-08-21 14:37 | Due to ATX material backlog moving SWR CE CA funding as follows: CE material delivery date 9 9 move dollars into Sept and Oct SWR material delivery date is 9 18 move dollars into Sept and Oct CA material delivery 10 5 moved dollars to October
NR ONA Q3 MTC 48 Node Cell | CE | OMA | ONA | MTC 48 Node Cell | NR CE OMA ONA MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-01 | 2020-10-30 | 2020-10-30 | Active | Log | Upd | SN-0946 | Schedule Change | Approved | 2020-09-25 14:18 | Due to ATX constraints the delivery dates have been extended to early to mid October for SWR and Mid Oct to early Nov for CE NE has requested materials for an late November migration
NR WES Q4 MTC 48 Node Cell | CE | OMA | WES | MTC 48 Node Cell | NR CE OMA WES MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-09-30 | 2020-10-30 | 2020-10-30 | Active | EP
NR WES Q4 MTC 48 Node Cell | CE | OMA | WES | MTC 48 Node Cell | NR CE OMA WES MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-09-30 | 2020-10-30 | 2020-10-30 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR WES Q4 MTC 48 Node Cell | CE | OMA | WES | MTC 48 Node Cell | NR CE OMA WES MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-09-30 | 2020-10-30 | 2020-10-30 | Active | Log | Upd | SN-0946 | Schedule Change | Approved | 2020-09-25 14:18 | Due to ATX constraints the delivery dates have been extended to early to mid October for SWR and Mid Oct to early Nov for CE NE has requested materials for an late November migration
NR NTH MTC 48 Node Cell | SE | BTR | NTH | MTC 48 Node Cell | NR SE BTR NTH MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-15 | 2020-10-31 | 2020-10-31 | Active | EP
NR NTH MTC 48 Node Cell | SE | BTR | NTH | MTC 48 Node Cell | NR SE BTR NTH MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-15 | 2020-10-31 | 2020-10-31 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR CRV MTC 48 Node Cell | SE | GCT | CRV | MTC 48 Node Cell | NR SE GCT CRV MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-15 | 2020-10-31 | 2020-10-31 | Active | EP
NR CRV MTC 48 Node Cell | SE | GCT | CRV | MTC 48 Node Cell | NR SE GCT CRV MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-07-15 | 2020-10-31 | 2020-10-31 | Active | Log | New | SN-0594 | New | Approved | 2020-05-20 16:49 | POR for MTC 48 Node Cell Q2 Q4
NR MAN MTC 48 Node Cell | NE | CON | MAN | MTC 48 Node Cell | NR NE CON MAN MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-10-15 | 2020-11-30 | 2020-11-30 | Active | EP
NR MAN MTC 48 Node Cell | NE | CON | MAN | MTC 48 Node Cell | NR NE CON MAN MTC 48 Node Cell Augment POR20 | Labor | No Equipment | 1 | 2020-10-15 | 2020-11-30 | 2020-11-30 | Active | Log | New | SN-0946 | Schedule Change | Approved | 2020-09-25 14:18 | Due to ATX constraints the delivery dates have been extended to early to mid October for SWR and Mid Oct to early Nov for CE NE has requested materials for an late November migration
MRTR OOB-New-SAB-OOB Server | CA | SAB | SAB | MTC Admin | MRTR CA SAB SAB OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | EP
MRTR OOB-New-SAB-OOB Server | CA | SAB | SAB | MTC Admin | MRTR CA SAB SAB OOB Deployment POR20 | Chassis | 1x Raritan Dominion SXII OOB Server Chassis | 1 | 2020-07-01 | 2020-09-30 | 2020-12-31 | Active | Log | New | SN-0158 | Schedule Change | Approved | 2020-02-06 11:15 | 1 No change financially 2 Updating the plan 3 The AAR projects in EPS has been created and plan update for those 4 Total 99 new EPS projects created
NE RHD CRN VAM Splitter Augment POR20 | NE | RHD | CRN | MTC Fiber and Rack Management | MVFM NE RHD CRN Fiber Bay Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-03-15 | 2020-03-15 | Active | EP
NE RHD LNC VAM Splitter Augment POR20 | NE | RHD | LNC | MTC Fiber and Rack Management | MVFM NE RHD LNC Fiber Bay Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-03-15 | 2020-03-15 | Active | EP
NE RHD PRV VAM Splitter Augment POR20 | NE | RHD | PRV | MTC Fiber and Rack Management | MVFM NE RHD PRV Fiber Bay Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-03-15 | 2020-03-15 | Active | EP
SW ARZ BEL Fiber Get Well Augment POR20 | SW | ARZ | BEL | MTC Fiber and Rack Management | MVFM SW ARZ BEL Fiber Get Well Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | EP
SW ARZ BEL Fiber Get Well Augment POR20 | SW | ARZ | BEL | MTC Fiber and Rack Management | MVFM SW ARZ BEL Fiber Get Well Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-04-06 | 2020-05-15 | 2020-12-15 | Deleted | Log | Upd | SN-0168 | Schedule Change | Approved | 2020-02-06 11:21 | Planning for Bell and McDowell is ongoing Request to push funding out of Q1 until completed and budget can be realigned
SW ARZ BEL Fiber Get Well Augment POR20 | SW | ARZ | BEL | MTC Fiber and Rack Management | MVFM SW ARZ BEL Fiber Get Well Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | Log | Del | SN-0286 | Scope Change | Approved | 2020-02-24 12:38 | Moving funds topside for the Bell Get Well, to be requested for HEHS in CR 287 As per communication from Mike L and Raul M, McDowell Get Well is deferred from 2020
SW ARZ CHD Cabling Refortification Augment POR20 | SW | ARZ | CHD | MTC Fiber and Rack Management | MVFM SW ARZ CHD Cabling Refortification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-04-06 | 2020-05-15 | 2020-05-15 | Active | EP
SW ARZ CHD Cabling Refortification Augment POR20 | SW | ARZ | CHD | MTC Fiber and Rack Management | MVFM SW ARZ CHD Cabling Refortification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2019-04-06 | 2020-05-15 | 2020-09-15 | Active | Log | Upd | SN-0139 | Schedule Change | Approved | 2020-02-06 11:05 | Updating to match schedule provided by Mike Lui Pushed material budget from January to February and smoothing labor through November
SW ARZ CHD Cabling Refortification Augment POR20 | SW | ARZ | CHD | MTC Fiber and Rack Management | MVFM SW ARZ CHD Cabling Refortification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-04-06 | 2020-05-15 | 2020-09-15 | Active | Log | Upd | SN-0223 | Schedule Change | Approved | 2020-02-03 16:49 | Cabling refortification projects need by dates were entered incorrectly as 2019 in CR-139 This is correcting to the appropriate 2020 date
SW ARZ CHD Cabling Refortification Augment POR20 | SW | ARZ | CHD | MTC Fiber and Rack Management | MVFM SW ARZ CHD Cabling Refortification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-04-06 | 2020-05-15 | 2020-05-15 | Active | Log | Upd | SN-0388 | Schedule Change | Approved | 2020-03-30 14:42 | Funding and POR updates to align budget with open orders and feedback provided by field teams
SW ARZ MCD Fiber Get Well Augment POR20 | SW | ARZ | MCD | MTC Fiber and Rack Management | MVFM SW ARZ MCD Fiber Get Well Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | EP
SW ARZ MCD Fiber Get Well Augment POR20 | SW | ARZ | MCD | MTC Fiber and Rack Management | MVFM SW ARZ MCD Fiber Get Well Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-04-06 | 2020-05-15 | 2020-12-15 | Deleted | Log | Upd | SN-0168 | Schedule Change | Approved | 2020-02-06 11:21 | Planning for Bell and McDowell is ongoing Request to push funding out of Q1 until completed and budget can be realigned
SW ARZ MCD Fiber Get Well Augment POR20 | SW | ARZ | MCD | MTC Fiber and Rack Management | MVFM SW ARZ MCD Fiber Get Well Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | Log | Del | SN-0286 | Scope Change | Approved | 2020-02-24 12:38 | Moving funds topside for the Bell Get Well, to be requested for HEHS in CR 287 As per communication from Mike L and Raul M, McDowell Get Well is deferred from 2020
SW ARZ MSA Cabling Refortification Augment POR20 | SW | ARZ | MSA | MTC Fiber and Rack Management | MVFM SW ARZ MSA Cabling Refortification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-04-06 | 2020-05-15 | 2020-05-15 | Active | EP
SW ARZ MSA Cabling Refortification Augment POR20 | SW | ARZ | MSA | MTC Fiber and Rack Management | MVFM SW ARZ MSA Cabling Refortification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-04-15 | 2020-08-15 | Active | Log | Upd | SN-0139 | Schedule Change | Approved | 2020-02-06 11:05 | Updating to match schedule provided by Mike Lui Pushed material budget from January to February and smoothing labor through November
SW ARZ MSA Cabling Refortification Augment POR20 | SW | ARZ | MSA | MTC Fiber and Rack Management | MVFM SW ARZ MSA Cabling Refortification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-04-06 | 2020-05-15 | 2020-05-15 | Active | Log | Upd | SN-0388 | Schedule Change | Approved | 2020-03-30 14:42 | Funding and POR updates to align budget with open orders and feedback provided by field teams
SW ARZ PEO Cabling Refortification Augment POR20 | SW | ARZ | PEO | MTC Fiber and Rack Management | MVFM SW ARZ PEO Cabling Refortification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-05-06 | 2020-06-15 | 2020-06-15 | Active | EP
SW ARZ PEO Cabling Refortification Augment POR20 | SW | ARZ | PEO | MTC Fiber and Rack Management | MVFM SW ARZ PEO Cabling Refortification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-02-06 | 2020-03-15 | 2020-07-15 | Active | Log | Upd | SN-0139 | Schedule Change | Approved | 2020-02-06 11:05 | Updating to match schedule provided by Mike Lui Pushed material budget from January to February and smoothing labor through November
SW ARZ PEO Cabling Refortification Augment POR20 | SW | ARZ | PEO | MTC Fiber and Rack Management | MVFM SW ARZ PEO Cabling Refortification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-05-06 | 2020-06-15 | 2020-06-15 | Active | Log | Upd | SN-0388 | Schedule Change | Approved | 2020-03-30 14:42 | Funding and POR updates to align budget with open orders and feedback provided by field teams
SW ARZ SSC Cabling Refortification Augment POR20 | SW | ARZ | SSC | MTC Fiber and Rack Management | MVFM SW ARZ SSC Cabling Refortification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | EP
SW ARZ SSC Cabling Refortification Augment POR20 | SW | ARZ | SSC | MTC Fiber and Rack Management | MVFM SW ARZ SSC Cabling Refortification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2019-06-06 | 2020-07-15 | 2020-11-15 | Active | Log | Upd | SN-0139 | Schedule Change | Approved | 2020-02-06 11:05 | Updating to match schedule provided by Mike Lui Pushed material budget from January to February and smoothing labor through November
SW ARZ SSC Cabling Refortification Augment POR20 | SW | ARZ | SSC | MTC Fiber and Rack Management | MVFM SW ARZ SSC Cabling Refortification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-06-06 | 2020-07-15 | 2020-11-15 | Active | Log | Upd | SN-0223 | Schedule Change | Approved | 2020-02-03 16:49 | Cabling refortification projects need by dates were entered incorrectly as 2019 in CR-139 This is correcting to the appropriate 2020 date
SW ARZ SSC Cabling Refortification Augment POR20 | SW | ARZ | SSC | MTC Fiber and Rack Management | MVFM SW ARZ SSC Cabling Refortification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0388 | Schedule Change | Approved | 2020-03-30 14:42 | Funding and POR updates to align budget with open orders and feedback provided by field teams
SW LAS BLU Cabling Refortification Augment POR20 | SW | LAS | BLU | MTC Fiber and Rack Management | MVFM SW LAS BLU Cabling Refortification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-07-06 | 2020-08-15 | 2020-08-30 | Active | EP
SW LAS BLU Cabling Refortification Augment POR20 | SW | LAS | BLU | MTC Fiber and Rack Management | MVFM SW LAS BLU Cabling Refortification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2019-05-06 | 2020-06-15 | 2020-10-15 | Active | Log | Upd | SN-0139 | Schedule Change | Approved | 2020-02-06 11:05 | Updating to match schedule provided by Mike Lui Pushed material budget from January to February and smoothing labor through November
SW LAS BLU Cabling Refortification Augment POR20 | SW | LAS | BLU | MTC Fiber and Rack Management | MVFM SW LAS BLU Cabling Refortification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-05-06 | 2020-06-15 | 2020-10-15 | Active | Log | Upd | SN-0223 | Schedule Change | Approved | 2020-02-03 16:49 | Cabling refortification projects need by dates were entered incorrectly as 2019 in CR-139 This is correcting to the appropriate 2020 date
SW LAS BLU Cabling Refortification Augment POR20 | SW | LAS | BLU | MTC Fiber and Rack Management | MVFM SW LAS BLU Cabling Refortification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-07-06 | 2020-08-15 | 2020-10-15 | Active | Log | Upd | SN-0388 | Schedule Change | Approved | 2020-03-30 14:42 | Funding and POR updates to align budget with open orders and feedback provided by field teams
SW LAS BLU Cabling Refortification Augment POR20 | SW | LAS | BLU | MTC Fiber and Rack Management | MVFM SW LAS BLU Cabling Refortification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-07-06 | 2020-08-15 | 2020-08-30 | Active | Log | Upd | SN-0793 | True up | Approved | 2020-08-20 18:09 | Returning excess funds for completed projects in SW and VA Aligning labor spend in NE for facilities still pending site visits Pushing funding for OSB to Nov to accomodate eq lead times
SW LAS HEN Cabling Refortification Augment POR20 | SW | LAS | HEN | MTC Fiber and Rack Management | MVFM SW LAS HEN Cabling Refortification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-04-06 | 2020-05-15 | 2020-05-15 | Active | EP
SW LAS HEN Cabling Refortification Augment POR20 | SW | LAS | HEN | MTC Fiber and Rack Management | MVFM SW LAS HEN Cabling Refortification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-02-06 | 2020-03-15 | 2020-07-15 | Active | Log | Upd | SN-0139 | Schedule Change | Approved | 2020-02-06 11:05 | Updating to match schedule provided by Mike Lui Pushed material budget from January to February and smoothing labor through November
SW LAS HEN Cabling Refortification Augment POR20 | SW | LAS | HEN | MTC Fiber and Rack Management | MVFM SW LAS HEN Cabling Refortification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-18 | 2020-03-30 | 2020-07-30 | Active | Log | Upd | SN-0320 | Schedule Change | Approved | 2020-02-28 18:27 | Partial material backorders for Henderson will push to April
SW LAS HEN Cabling Refortification Augment POR20 | SW | LAS | HEN | MTC Fiber and Rack Management | MVFM SW LAS HEN Cabling Refortification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-04-06 | 2020-05-15 | 2020-05-15 | Active | Log | Upd | SN-0388 | Schedule Change | Approved | 2020-03-30 14:42 | Funding and POR updates to align budget with open orders and feedback provided by field teams
CA ORG IRV Backbone Growth Edge Augment POR20 | CA | ORG | IRV | MTC Fiber and Rack Management | MVFM CA ORG IRV Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-05-06 | 2020-06-15 | 2020-07-15 | Active | EP
CA ORG IRV Backbone Growth Edge Augment POR20 | CA | ORG | IRV | MTC Fiber and Rack Management | MVFM CA ORG IRV Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0230 | Schedule Change | Approved | 2020-01-31 15:02 | Accelerating funding and plans from later in Q2 and Q3 as per the updated plan from Ron and Penny Rescheduling in reaction to node plan Related to EMO risk 268
CA ORG IRV Backbone Growth Edge Augment POR20 | CA | ORG | IRV | MTC Fiber and Rack Management | MVFM CA ORG IRV Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-05-06 | 2020-06-15 | 2020-07-15 | Active | Log | Upd | SN-0388 | Schedule Change | Approved | 2020-03-30 14:42 | Funding and POR updates to align budget with open orders and feedback provided by field teams
CA ORG ORG Backbone Growth Edge Augment POR20 | CA | ORG | ORG | MTC Fiber and Rack Management | MVFM CA ORG ORG Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | EP
CA ORG ORG Backbone Growth Edge Augment POR20 | CA | ORG | ORG | MTC Fiber and Rack Management | MVFM CA ORG ORG Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-02-06 | 2020-04-15 | 2020-05-15 | Deleted | Log | Upd | SN-0187 | Schedule Change | Approved | 2020-01-21 09:43 | Pertaining to EPS risk 268 Planning is delayed and ongoing for all CA facilities fiber projects, due to conflicting priorities with the Node Action activities Field owners are working on a detailed plan and we will likely submit a CR to align funding more
CA ORG ORG Backbone Growth Edge Augment POR20 | CA | ORG | ORG | MTC Fiber and Rack Management | MVFM CA ORG ORG Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | Log | Del | SN-0230 | Schedule Change | Approved | 2020-01-31 15:02 | Accelerating funding and plans from later in Q2 and Q3 as per the updated plan from Ron and Penny Rescheduling in reaction to node plan Related to EMO risk 268
CA ORG PAV Backbone Growth Edge Augment POR20 | CA | ORG | PAV | MTC Fiber and Rack Management | MVFM CA ORG PAV Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-05-06 | 2020-06-15 | 2020-07-15 | Active | EP
CA ORG PAV Backbone Growth Edge Augment POR20 | CA | ORG | PAV | MTC Fiber and Rack Management | MVFM CA ORG PAV Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0230 | Schedule Change | Approved | 2020-01-31 15:02 | Accelerating funding and plans from later in Q2 and Q3 as per the updated plan from Ron and Penny Rescheduling in reaction to node plan Related to EMO risk 268
CA ORG PAV Backbone Growth Edge Augment POR20 | CA | ORG | PAV | MTC Fiber and Rack Management | MVFM CA ORG PAV Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-05-06 | 2020-06-15 | 2020-07-15 | Active | Log | Upd | SN-0388 | Schedule Change | Approved | 2020-03-30 14:42 | Funding and POR updates to align budget with open orders and feedback provided by field teams
CA ORG PAV CB Rack Environment Prep for CB Augment POR20 | CA | ORG | PAV | MTC Fiber and Rack Management | MVFM CA ORG PAV Rack Env Prep for CB Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | EP
CA ORG PAV CB Rack Environment Prep for CB Augment POR20 | CA | ORG | PAV | MTC Fiber and Rack Management | MVFM CA ORG PAV Rack Env Prep for CB Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | Log | Del | SN-0230 | Schedule Change | Approved | 2020-01-31 15:02 | Accelerating funding and plans from later in Q2 and Q3 as per the updated plan from Ron and Penny Rescheduling in reaction to node plan Related to EMO risk 268
CA ORG RSM Backbone Growth Edge Augment POR20 | CA | ORG | RSM | MTC Fiber and Rack Management | MVFM CA ORG RSM Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-04-30 | 2020-05-31 | Active | EP
CA ORG RSM Backbone Growth Edge Augment POR20 | CA | ORG | RSM | MTC Fiber and Rack Management | MVFM CA ORG RSM Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-04-15 | 2020-05-15 | Active | Log | Upd | SN-0187 | Schedule Change | Approved | 2020-01-21 09:43 | Pertaining to EPS risk 268 Planning is delayed and ongoing for all CA facilities fiber projects, due to conflicting priorities with the Node Action activities Field owners are working on a detailed plan and we will likely submit a CR to align funding more
CA ORG RSM Backbone Growth Edge Augment POR20 | CA | ORG | RSM | MTC Fiber and Rack Management | MVFM CA ORG RSM Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0230 | Schedule Change | Approved | 2020-01-31 15:02 | Accelerating funding and plans from later in Q2 and Q3 as per the updated plan from Ron and Penny Rescheduling in reaction to node plan Related to EMO risk 268
CA SAN CHU Backbone Growth Edge Augment POR20 | CA | SAN | CHU | MTC Fiber and Rack Management | MVFM CA SAN CHU OSP Migration Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-05-06 | 2020-07-31 | 2020-07-31 | Active | EP
CA SAN CHU Backbone Growth Edge Augment POR20 | CA | SAN | CHU | MTC Fiber and Rack Management | MVFM CA SAN CHU OSP Migration Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-05-06 | 2020-07-31 | 2020-08-31 | Active | Log | Upd | SN-0230 | Schedule Change | Approved | 2020-01-31 15:02 | Accelerating funding and plans from later in Q2 and Q3 as per the updated plan from Ron and Penny Rescheduling in reaction to node plan Related to EMO risk 268
CA SAN CHU Backbone Growth Edge Augment POR20 | CA | SAN | CHU | MTC Fiber and Rack Management | MVFM CA SAN CHU OSP Migration Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-05-06 | 2020-07-31 | 2020-07-31 | Active | Log | Upd | SN-0793 | True up | Approved | 2020-08-20 18:09 | Returning excess funds for completed projects in SW and VA Aligning labor spend in NE for facilities still pending site visits Pushing funding for OSB to Nov to accomodate eq lead times
CA ORG DNP CB Rack Environment Prep for CB Augment POR20 | CA | ORG | DNP | MTC Fiber and Rack Management | MVFM CA ORG DNP Rack Env Prep for CB Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | EP
CA ORG DNP CB Rack Environment Prep for CB Augment POR20 | CA | ORG | DNP | MTC Fiber and Rack Management | MVFM CA ORG DNP Rack Env Prep for CB Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | Log | Del | SN-0230 | Schedule Change | Approved | 2020-01-31 15:02 | Accelerating funding and plans from later in Q2 and Q3 as per the updated plan from Ron and Penny Rescheduling in reaction to node plan Related to EMO risk 268
CA ORG IRV CB Rack Environment Prep for CB Augment POR20 | CA | ORG | IRV | MTC Fiber and Rack Management | MVFM CA ORG IRV Rack Env Prep for CB Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | EP
CA ORG IRV CB Rack Environment Prep for CB Augment POR20 | CA | ORG | IRV | MTC Fiber and Rack Management | MVFM CA ORG IRV Rack Env Prep for CB Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | Log | Del | SN-0230 | Schedule Change | Approved | 2020-01-31 15:02 | Accelerating funding and plans from later in Q2 and Q3 as per the updated plan from Ron and Penny Rescheduling in reaction to node plan Related to EMO risk 268
CA ORG RSM Backbone GrowthRDC Augment POR20 | CA | ORG | RSM | MTC Fiber and Rack Management | MVFM CA ORG RSM Raceway Reforification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-05-31 | 2020-06-30 | Active | EP
CA ORG RSM Backbone GrowthRDC Augment POR20 | CA | ORG | RSM | MTC Fiber and Rack Management | MVFM CA ORG RSM Raceway Reforification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-05-31 | 2020-06-30 | Active | Log | Upd | SN-0230 | Schedule Change | Approved | 2020-01-31 15:02 | Accelerating funding and plans from later in Q2 and Q3 as per the updated plan from Ron and Penny Rescheduling in reaction to node plan Related to EMO risk 268
CA ORG RSM CB Rack Environment Prep for CB Augment POR20 | CA | ORG | RSM | MTC Fiber and Rack Management | MVFM CA ORG RSM Rack Env Prep for CB Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | EP
CA ORG RSM CB Rack Environment Prep for CB Augment POR20 | CA | ORG | RSM | MTC Fiber and Rack Management | MVFM CA ORG RSM Rack Env Prep for CB Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | Log | Del | SN-0230 | Schedule Change | Approved | 2020-01-31 15:02 | Accelerating funding and plans from later in Q2 and Q3 as per the updated plan from Ron and Penny Rescheduling in reaction to node plan Related to EMO risk 268
CA SAN ALP Backbone Growth Edge Augment POR20 | CA | SAN | ALP | MTC Fiber and Rack Management | MVFM CA SAN ALP Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | EP
CA SAN ALP Backbone Growth Edge Augment POR20 | CA | SAN | ALP | MTC Fiber and Rack Management | MVFM CA SAN ALP Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | Log | Del | SN-0230 | Schedule Change | Approved | 2020-01-31 15:02 | Accelerating funding and plans from later in Q2 and Q3 as per the updated plan from Ron and Penny Rescheduling in reaction to node plan Related to EMO risk 268
CA SAN ALP CB Rack Environment Prep for CB Augment POR20 | CA | SAN | ALP | MTC Fiber and Rack Management | MVFM CA SAN ALP Rack Env Prep for CB Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | EP
CA SAN ALP CB Rack Environment Prep for CB Augment POR20 | CA | SAN | ALP | MTC Fiber and Rack Management | MVFM CA SAN ALP Rack Env Prep for CB Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | Log | Del | SN-0230 | Schedule Change | Approved | 2020-01-31 15:02 | Accelerating funding and plans from later in Q2 and Q3 as per the updated plan from Ron and Penny Rescheduling in reaction to node plan Related to EMO risk 268
CA SAN DWN Backbone Growth Edge Augment POR20 | CA | SAN | DWN | MTC Fiber and Rack Management | MVFM CA SAN DWN Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-05-06 | 2020-06-15 | 2020-07-15 | Active | EP
CA SAN DWN Backbone Growth Edge Augment POR20 | CA | SAN | DWN | MTC Fiber and Rack Management | MVFM CA SAN DWN Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0230 | Schedule Change | Approved | 2020-01-31 15:02 | Accelerating funding and plans from later in Q2 and Q3 as per the updated plan from Ron and Penny Rescheduling in reaction to node plan Related to EMO risk 268
CA SAN DWN Backbone Growth Edge Augment POR20 | CA | SAN | DWN | MTC Fiber and Rack Management | MVFM CA SAN DWN Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-05-06 | 2020-06-15 | 2020-07-15 | Active | Log | Upd | SN-0388 | Schedule Change | Approved | 2020-03-30 14:42 | Funding and POR updates to align budget with open orders and feedback provided by field teams
CA SAN ELC Backbone Growth Edge Augment POR20 | CA | SAN | ELC | MTC Fiber and Rack Management | MVFM CA SAN ELC Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-04-30 | 2020-05-31 | Active | EP
CA SAN ELC Backbone Growth Edge Augment POR20 | CA | SAN | ELC | MTC Fiber and Rack Management | MVFM CA SAN ELC Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0230 | Schedule Change | Approved | 2020-01-31 15:02 | Accelerating funding and plans from later in Q2 and Q3 as per the updated plan from Ron and Penny Rescheduling in reaction to node plan Related to EMO risk 268
CA SAN ELC Backbone GrowthRDC Augment POR20 | CA | SAN | ELC | MTC Fiber and Rack Management | MVFM CA SAN ELC Raceway Reforification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-05-31 | 2020-06-30 | Active | EP
CA SAN ELC Backbone GrowthRDC Augment POR20 | CA | SAN | ELC | MTC Fiber and Rack Management | MVFM CA SAN ELC Raceway Reforification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-05-31 | 2020-06-30 | Active | Log | Upd | SN-0230 | Schedule Change | Approved | 2020-01-31 15:02 | Accelerating funding and plans from later in Q2 and Q3 as per the updated plan from Ron and Penny Rescheduling in reaction to node plan Related to EMO risk 268
CA SAN ESC Backbone Growth Edge Augment POR20 | CA | SAN | ESC | MTC Fiber and Rack Management | MVFM CA SAN ESC Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | EP
CA SAN ESC Backbone Growth Edge Augment POR20 | CA | SAN | ESC | MTC Fiber and Rack Management | MVFM CA SAN ESC Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0230 | Schedule Change | Approved | 2020-01-31 15:02 | Accelerating funding and plans from later in Q2 and Q3 as per the updated plan from Ron and Penny Rescheduling in reaction to node plan Related to EMO risk 268
CA ORG AVJ Backbone Growth Edge Augment POR20 | CA | ORG | AVJ | MTC Fiber and Rack Management | MVFM CA ORG AVJ Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | EP
CA ORG AVJ CB Rack Environment Prep for CB Augment POR20 | CA | ORG | AVJ | MTC Fiber and Rack Management | MVFM CA ORG AVJ Rack Env Prep for CB Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | EP
CA ORG AVJ CB Rack Environment Prep for CB Augment POR20 | CA | ORG | AVJ | MTC Fiber and Rack Management | MVFM CA ORG AVJ Rack Env Prep for CB Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | Log | Del | SN-0230 | Schedule Change | Approved | 2020-01-31 15:02 | Accelerating funding and plans from later in Q2 and Q3 as per the updated plan from Ron and Penny Rescheduling in reaction to node plan Related to EMO risk 268
CA ORG DNP Backbone Growth Edge Augment POR20 | CA | ORG | DNP | MTC Fiber and Rack Management | MVFM CA ORG DNP Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-05-06 | 2020-06-15 | 2020-07-15 | Active | EP
CA ORG DNP Backbone Growth Edge Augment POR20 | CA | ORG | DNP | MTC Fiber and Rack Management | MVFM CA ORG DNP Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-05-06 | 2020-06-15 | 2020-07-15 | Active | Log | Upd | SN-0388 | Schedule Change | Approved | 2020-03-30 14:42 | Funding and POR updates to align budget with open orders and feedback provided by field teams
CA SAN ESC CB Rack Environment Prep for CB Augment POR20 | CA | SAN | ESC | MTC Fiber and Rack Management | MVFM CA SAN ESC Rack Env Prep for CB Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | EP
CA SAN ESC CB Rack Environment Prep for CB Augment POR20 | CA | SAN | ESC | MTC Fiber and Rack Management | MVFM CA SAN ESC Rack Env Prep for CB Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | Log | Del | SN-0230 | Schedule Change | Approved | 2020-01-31 15:02 | Accelerating funding and plans from later in Q2 and Q3 as per the updated plan from Ron and Penny Rescheduling in reaction to node plan Related to EMO risk 268
CA SAN FED Backbone Growth Edge Augment POR20 | CA | SAN | FED | MTC Fiber and Rack Management | MVFM CA SAN FED Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-04-30 | 2020-05-31 | Active | EP
CA SAN FED Backbone Growth Edge Augment POR20 | CA | SAN | FED | MTC Fiber and Rack Management | MVFM CA SAN FED Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0230 | Schedule Change | Approved | 2020-01-31 15:02 | Accelerating funding and plans from later in Q2 and Q3 as per the updated plan from Ron and Penny Rescheduling in reaction to node plan Related to EMO risk 268
CA SAN FED Backbone GrowthRDC Augment POR20 | CA | SAN | FED | MTC Fiber and Rack Management | MVFM CA SAN FED Raceway Reforification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-05-31 | 2020-06-30 | Active | EP
CA SAN FED Backbone GrowthRDC Augment POR20 | CA | SAN | FED | MTC Fiber and Rack Management | MVFM CA SAN FED Raceway Reforification Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-05-31 | 2020-06-30 | Active | Log | Upd | SN-0230 | Schedule Change | Approved | 2020-01-31 15:02 | Accelerating funding and plans from later in Q2 and Q3 as per the updated plan from Ron and Penny Rescheduling in reaction to node plan Related to EMO risk 268
CA SAN FED CB Rack Environment Prep for CB Augment POR20 | CA | SAN | FED | MTC Fiber and Rack Management | MVFM CA SAN FED Rack Env Prep for CB Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | EP
CA SAN FED CB Rack Environment Prep for CB Augment POR20 | CA | SAN | FED | MTC Fiber and Rack Management | MVFM CA SAN FED Rack Env Prep for CB Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | Log | Del | SN-0230 | Schedule Change | Approved | 2020-01-31 15:02 | Accelerating funding and plans from later in Q2 and Q3 as per the updated plan from Ron and Penny Rescheduling in reaction to node plan Related to EMO risk 268
CA SAN OCE Backbone Growth Edge Augment POR20 | CA | SAN | OCE | MTC Fiber and Rack Management | MVFM CA SAN OCE Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | EP
CA SAN OCE Backbone Growth Edge Augment POR20 | CA | SAN | OCE | MTC Fiber and Rack Management | MVFM CA SAN OCE Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0230 | Schedule Change | Approved | 2020-01-31 15:02 | Accelerating funding and plans from later in Q2 and Q3 as per the updated plan from Ron and Penny Rescheduling in reaction to node plan Related to EMO risk 268
NE RHD EXT VAM Splitter Augment POR20 | NE | RHD | EXT | MTC Fiber and Rack Management | MVFM NE RHD EXT Fiber Bay Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-06-08 | 2020-06-15 | 2020-06-15 | Active | EP
NE RHD PRV Meet Me Rack Augment POR20 | NE | RHD | PRV | MTC Fiber and Rack Management | MVFM NE RHD PRV Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | EP
NE RHD PRV Meet Me Rack Augment POR20 | NE | RHD | PRV | MTC Fiber and Rack Management | MVFM NE RHD PRV Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | Log | Del | SN-0537 | COVID-19 Related | Approved | 2020-05-08 14:20 | POR Updates related to Covid 19 deferrals
NE RHD PRV Fiber Entry Point Augment POR20 | NE | RHD | PRV | MTC Fiber and Rack Management | MVFM NE RHD PRV Fiber Entry Point Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | EP
NE RHD PRV Fiber Entry Point Augment POR20 | NE | RHD | PRV | MTC Fiber and Rack Management | MVFM NE RHD PRV Fiber Entry Point Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | Log | Del | SN-0537 | COVID-19 Related | Approved | 2020-05-08 14:20 | POR Updates related to Covid 19 deferrals
NE RHD PRV Rack Spacers Augment POR20 | NE | RHD | PRV | MTC Fiber and Rack Management | MVFM NE RHD PRV Rack Spacers Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | EP
NE RHD PRV Rack Spacers Augment POR20 | NE | RHD | PRV | MTC Fiber and Rack Management | MVFM NE RHD PRV Rack Spacers Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | Log | Del | SN-0537 | COVID-19 Related | Approved | 2020-05-08 14:20 | POR Updates related to Covid 19 deferrals
NE RHD SCT ALU Nokia Fiber Augment POR20 | NE | RHD | SCT | MTC Fiber and Rack Management | MVFM NE RHD SCT ALU Nokia Fiber Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-05-31 | 2020-05-31 | Active | EP
NE RHD SCT ALU Nokia Fiber Augment POR20 | NE | RHD | SCT | MTC Fiber and Rack Management | MVFM NE RHD SCT ALU Nokia Fiber Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-05-31 | 2020-05-31 | Active | Log | Upd | SN-0308 | Schedule Change | Approved | 2020-02-28 18:25 | Accelerated receipt for ALU Upgrades to March and activity to April to July
NE RHD WWK Fiber Panel Augment POR20 | NE | RHD | WWK | MTC Fiber and Rack Management | MVFM NE RHD WWK Fiber Panel Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | EP
NE RHD WWK Fiber Panel Augment POR20 | NE | RHD | WWK | MTC Fiber and Rack Management | MVFM NE RHD WWK Fiber Panel Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | Log | Del | SN-0537 | COVID-19 Related | Approved | 2020-05-08 14:20 | POR Updates related to Covid 19 deferrals
NE RHD WWK Rack Spacers Augment POR20 | NE | RHD | WWK | MTC Fiber and Rack Management | MVFM NE RHD WWK Rack Spacers Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | EP
NE RHD WWK Rack Spacers Augment POR20 | NE | RHD | WWK | MTC Fiber and Rack Management | MVFM NE RHD WWK Rack Spacers Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | Log | Del | SN-0537 | COVID-19 Related | Approved | 2020-05-08 14:20 | POR Updates related to Covid 19 deferrals
SE GAN GNS Meet Me Rack Augment POR20 | SE | GAN | GNS | MTC Fiber and Rack Management | MVFM SE GAN GNS Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-12-04 | 2020-12-31 | 2020-12-31 | Active | EP
SE GAN GNS Meet Me Rack Augment POR20 | SE | GAN | GNS | MTC Fiber and Rack Management | MVFM SE GAN GNS Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-10-07 | 2020-11-30 | 2020-11-30 | Active | Log | Upd | SN-0885 | Schedule Change | Approved | 2020-09-11 10:39 | Aligning funding for the Gainesville Meet Me Rack project based on recent quotes from SRI and updated plans from the field
SE GAN GNS Meet Me Rack Augment POR20 | SE | GAN | GNS | MTC Fiber and Rack Management | MVFM SE GAN GNS Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-12-04 | 2020-12-31 | 2020-12-31 | Active | Log | Upd | SN-1087 | Schedule Change | Approved | 2020-11-20 13:48 | Delays to Gainesville Meet Me projects from SRI and previously cancelled POs in CA now invoicing unexpectedly
SE GLA BTR Meet Me Rack Augment POR20 | SE | BTR | BTR | MTC Fiber and Rack Management | MVFM SE BTR BTR Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | EP
SE GLA BTR Meet Me Rack Augment POR20 | SE | BTR | BTR | MTC Fiber and Rack Management | MVFM SE BTR BTR Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | Log | Del | SN-0537 | COVID-19 Related | Approved | 2020-05-08 14:20 | POR Updates related to Covid 19 deferrals
SE GCT CRV Meet Me Rack Augment POR20 | SE | GCT | CRV | MTC Fiber and Rack Management | MVFM SE GCT CRV Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | EP
SE GCT CRV Meet Me Rack Augment POR20 | SE | GCT | CRV | MTC Fiber and Rack Management | MVFM SE GCT CRV Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | Log | Del | SN-0537 | COVID-19 Related | Approved | 2020-05-08 14:20 | POR Updates related to Covid 19 deferrals
SE MGA MCN Meet Me Rack Augment POR20 | SE | MGA | MCN | MTC Fiber and Rack Management | MVFM SE MGA MCN Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | EP
SE MGA MCN Meet Me Rack Augment POR20 | SE | MGA | MCN | MTC Fiber and Rack Management | MVFM SE MGA MCN Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | Log | Del | SN-0885 | Schedule Change | Approved | 2020-09-11 10:39 | Aligning funding for the Gainesville Meet Me Rack project based on recent quotes from SRI and updated plans from the field
NE CON MAN Fiber Panel Augment POR20 | NE | CON | MAN | MTC Fiber and Rack Management | MVFM NE CON MAN Fiber Panel Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | EP
NE CON MAN Fiber Panel Augment POR20 | NE | CON | MAN | MTC Fiber and Rack Management | MVFM NE CON MAN Fiber Panel Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | Log | Del | SN-0537 | COVID-19 Related | Approved | 2020-05-08 14:20 | POR Updates related to Covid 19 deferrals
NE CON MAN Rack Spacers Augment POR20 | NE | CON | MAN | MTC Fiber and Rack Management | MVFM NE CON MAN Rack Spacers Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | EP
NE CON MAN Rack Spacers Augment POR20 | NE | CON | MAN | MTC Fiber and Rack Management | MVFM NE CON MAN Rack Spacers Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | Log | Del | SN-0537 | COVID-19 Related | Approved | 2020-05-08 14:20 | POR Updates related to Covid 19 deferrals
NE CON STN VAM Splitter Augment POR20 | NE | CON | STN | MTC Fiber and Rack Management | MVFM NE CON STN Fiber Bay Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-06-08 | 2020-06-15 | 2020-06-15 | Active | EP
NE CON STN ALU Nokia Fiber Augment POR20 | NE | CON | STN | MTC Fiber and Rack Management | MVFM NE CON STN ALU Nokia Fiber Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-07-31 | 2020-08-20 | Active | EP
NE CON STN ALU Nokia Fiber Augment POR20 | NE | CON | STN | MTC Fiber and Rack Management | MVFM NE CON STN ALU Nokia Fiber Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-07-31 | 2020-07-31 | Active | Log | Upd | SN-0308 | Schedule Change | Approved | 2020-02-28 18:25 | Accelerated receipt for ALU Upgrades to March and activity to April to July
NE CON STN ALU Nokia Fiber Augment POR20 | NE | CON | STN | MTC Fiber and Rack Management | MVFM NE CON STN ALU Nokia Fiber Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-07-31 | 2020-08-20 | Active | Log | Upd | SN-0793 | True up | Approved | 2020-08-20 18:09 | Returning excess funds for completed projects in SW and VA Aligning labor spend in NE for facilities still pending site visits Pushing funding for OSB to Nov to accomodate eq lead times
NE CON SFD ALU Nokia Fiber Augment POR20 | NE | CON | SFD | MTC Fiber and Rack Management | MVFM NE CON SFD ALU Nokia Fiber Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-06-30 | 2020-06-30 | Active | EP
NE CON SFD ALU Nokia Fiber Augment POR20 | NE | CON | SFD | MTC Fiber and Rack Management | MVFM NE CON SFD ALU Nokia Fiber Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0308 | Schedule Change | Approved | 2020-02-28 18:25 | Accelerated receipt for ALU Upgrades to March and activity to April to July
NE RHD BUR ALU Nokia Fiber Augment POR20 | NE | RHD | BUR | MTC Fiber and Rack Management | MVFM NE RHD BUR ALU Nokia Fiber Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-04-30 | 2020-08-13 | Active | EP
NE RHD BUR ALU Nokia Fiber Augment POR20 | NE | RHD | BUR | MTC Fiber and Rack Management | MVFM NE RHD BUR ALU Nokia Fiber Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-04-30 | 2020-04-30 | Active | Log | Upd | SN-0308 | Schedule Change | Approved | 2020-02-28 18:25 | Accelerated receipt for ALU Upgrades to March and activity to April to July
NE RHD BUR ALU Nokia Fiber Augment POR20 | NE | RHD | BUR | MTC Fiber and Rack Management | MVFM NE RHD BUR ALU Nokia Fiber Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-04-30 | 2020-08-13 | Active | Log | Upd | SN-0793 | True up | Approved | 2020-08-20 18:09 | Returning excess funds for completed projects in SW and VA Aligning labor spend in NE for facilities still pending site visits Pushing funding for OSB to Nov to accomodate eq lead times
VA HRD CHS Meet Me Rack Augment POR20 | VA | HRD | CHS | MTC Fiber and Rack Management | MVFM VA HRD CHS Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | EP
VA HRD CHS Meet Me Rack Augment POR20 | VA | HRD | CHS | MTC Fiber and Rack Management | MVFM VA HRD CHS Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | Log | Del | SN-0311 | Scope Change | Approved | 2020-03-05 13:29 | Descope Chesapeake and Lightfoot as these are covered under the RPHY plan for 2020 Request funding be made available for Newport and Virginia Beach as these sites did not originally go with the Meet-Me Rack model and we would like these to be uniform wi
VA HRD LTF Meet Me Rack Augment POR20 | VA | HRD | LTF | MTC Fiber and Rack Management | MVFM VA HRD LTF Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | EP
VA HRD LTF Meet Me Rack Augment POR20 | VA | HRD | LTF | MTC Fiber and Rack Management | MVFM VA HRD LTF Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | Log | Del | SN-0311 | Scope Change | Approved | 2020-03-05 13:29 | Descope Chesapeake and Lightfoot as these are covered under the RPHY plan for 2020 Request funding be made available for Newport and Virginia Beach as these sites did not originally go with the Meet-Me Rack model and we would like these to be uniform wi
VA NVA MFD Fiber Infrastructure Rebuild Augment POR20 | VA | NVA | MFD | MTC Fiber and Rack Management | MVFM VA NVA MFD Fiber Infrastructure Rebuild Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | EP
VA NVA MFD Fiber Infrastructure Rebuild Augment POR20 | VA | NVA | MFD | MTC Fiber and Rack Management | MVFM VA NVA MFD Fiber Infrastructure Rebuild Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-08-06 | 2020-09-15 | 2020-10-15 | Deleted | Log | Upd | SN-0415 | Schedule Change | Approved | 2020-03-30 15:28 | Fixes to 2 activity plans and equipment IDs to align CCRB database and manual POR
VA NVA MFD Fiber Infrastructure Rebuild Augment POR20 | VA | NVA | MFD | MTC Fiber and Rack Management | MVFM VA NVA MFD Fiber Infrastructure Rebuild Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | Log | Del | SN-0537 | COVID-19 Related | Approved | 2020-05-08 14:20 | POR Updates related to Covid 19 deferrals
CA SAN PWY CB Rack Environment Prep for CB Augment POR20 | CA | SAN | PWY | MTC Fiber and Rack Management | MVFM CA SAN PWY Rack Env Prep for CB Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | EP
CA SAN PWY CB Rack Environment Prep for CB Augment POR20 | CA | SAN | PWY | MTC Fiber and Rack Management | MVFM CA SAN PWY Rack Env Prep for CB Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | Log | Del | SN-0230 | Schedule Change | Approved | 2020-01-31 15:02 | Accelerating funding and plans from later in Q2 and Q3 as per the updated plan from Ron and Penny Rescheduling in reaction to node plan Related to EMO risk 268
CA SAN VST Backbone Growth Edge Augment POR20 | CA | SAN | VST | MTC Fiber and Rack Management | MVFM CA SAN VST Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | EP
CA SAN VST Backbone Growth Edge Augment POR20 | CA | SAN | VST | MTC Fiber and Rack Management | MVFM CA SAN VST Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0230 | Schedule Change | Approved | 2020-01-31 15:02 | Accelerating funding and plans from later in Q2 and Q3 as per the updated plan from Ron and Penny Rescheduling in reaction to node plan Related to EMO risk 268
CA SAN VST CB Rack Environment Prep for CB Augment POR20 | CA | SAN | VST | MTC Fiber and Rack Management | MVFM CA SAN VST Rack Env Prep for CB Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | EP
CA SAN VST CB Rack Environment Prep for CB Augment POR20 | CA | SAN | VST | MTC Fiber and Rack Management | MVFM CA SAN VST Rack Env Prep for CB Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | Log | Del | SN-0230 | Schedule Change | Approved | 2020-01-31 15:02 | Accelerating funding and plans from later in Q2 and Q3 as per the updated plan from Ron and Penny Rescheduling in reaction to node plan Related to EMO risk 268
CA SAB SAB Backbone Growth Edge Augment POR20 | CA | SAB | SAB | MTC Fiber and Rack Management | MVFM CA SAB SAB Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | EP
CA SAB SAB Backbone Growth Edge Augment POR20 | CA | SAB | SAB | MTC Fiber and Rack Management | MVFM CA SAB SAB Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | Log | Del | SN-0230 | Schedule Change | Approved | 2020-01-31 15:02 | Accelerating funding and plans from later in Q2 and Q3 as per the updated plan from Ron and Penny Rescheduling in reaction to node plan Related to EMO risk 268
CA SAB SAB CB Rack Environment Prep for CB Augment POR20 | CA | SAB | SAB | MTC Fiber and Rack Management | MVFM CA SAB SAB Rack Env Prep for CB Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | EP
CA SAB SAB CB Rack Environment Prep for CB Augment POR20 | CA | SAB | SAB | MTC Fiber and Rack Management | MVFM CA SAB SAB Rack Env Prep for CB Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | Log | Del | SN-0230 | Schedule Change | Approved | 2020-01-31 15:02 | Accelerating funding and plans from later in Q2 and Q3 as per the updated plan from Ron and Penny Rescheduling in reaction to node plan Related to EMO risk 268
CE ARK BVL Meet Me Rack Augment POR20 | CE | NWA | BVL | MTC Fiber and Rack Management | MVFM CE NWA BVL Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | EP
CE ARK BVL Meet Me Rack Augment POR20 | CE | NWA | BVL | MTC Fiber and Rack Management | MVFM CE NWA BVL Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-08-06 | 2020-09-15 | 2020-09-15 | Deleted | Log | Upd | SN-0388 | Schedule Change | Approved | 2020-03-30 14:42 | Funding and POR updates to align budget with open orders and feedback provided by field teams
CE ARK BVL Meet Me Rack Augment POR20 | CE | NWA | BVL | MTC Fiber and Rack Management | MVFM CE NWA BVL Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | Log | Del | SN-0537 | COVID-19 Related | Approved | 2020-05-08 14:20 | POR Updates related to Covid 19 deferrals
CE OKC NOR Meet Me Rack Augment POR20 | CE | OKC | NOR | MTC Fiber and Rack Management | MVFM CE OKC NOR Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | EP
CE OKC NOR Meet Me Rack Augment POR20 | CE | OKC | NOR | MTC Fiber and Rack Management | MVFM CE OKC NOR Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-08-06 | 2020-09-15 | 2020-09-15 | Deleted | Log | Upd | SN-0388 | Schedule Change | Approved | 2020-03-30 14:42 | Funding and POR updates to align budget with open orders and feedback provided by field teams
CE OKC NOR Meet Me Rack Augment POR20 | CE | OKC | NOR | MTC Fiber and Rack Management | MVFM CE OKC NOR Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | Log | Del | SN-0537 | COVID-19 Related | Approved | 2020-05-08 14:20 | POR Updates related to Covid 19 deferrals
CE OKC NEH Meet Me Rack Augment POR20 | CE | OKC | NEH | MTC Fiber and Rack Management | MVFM CE OKC NEH Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | EP
CE OKC NEH Meet Me Rack Augment POR20 | CE | OKC | NEH | MTC Fiber and Rack Management | MVFM CE OKC NEH Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-08-06 | 2020-09-15 | 2020-09-15 | Deleted | Log | Upd | SN-0388 | Schedule Change | Approved | 2020-03-30 14:42 | Funding and POR updates to align budget with open orders and feedback provided by field teams
CE OKC NEH Meet Me Rack Augment POR20 | CE | OKC | NEH | MTC Fiber and Rack Management | MVFM CE OKC NEH Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | Log | Del | SN-0537 | COVID-19 Related | Approved | 2020-05-08 14:20 | POR Updates related to Covid 19 deferrals
CE OMA ONA Meet Me Rack Augment POR20 | CE | OMA | ONA | MTC Fiber and Rack Management | MVFM CE OMA ONA Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | EP
CE OMA ONA Meet Me Rack Augment POR20 | CE | OMA | ONA | MTC Fiber and Rack Management | MVFM CE OMA ONA Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | Log | Del | SN-0537 | COVID-19 Related | Approved | 2020-05-08 14:20 | POR Updates related to Covid 19 deferrals
NE CLE CLV Meet Me Rack Augment POR20 | NE | CLE | CLV | MTC Fiber and Rack Management | MVFM NE CLE CLV Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-06-08 | 2020-08-31 | 2020-09-30 | Active | EP
NE CLE CLV Meet Me Rack Augment POR20 | NE | CLE | CLV | MTC Fiber and Rack Management | MVFM NE CLE CLV Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-06-08 | 2020-08-31 | 2020-09-30 | Active | Log | Upd | SN-0793 | True up | Approved | 2020-08-20 18:09 | Returning excess funds for completed projects in SW and VA Aligning labor spend in NE for facilities still pending site visits Pushing funding for OSB to Nov to accomodate eq lead times
NE CON GLB VAM Splitter Augment POR20 | NE | CON | GLB | MTC Fiber and Rack Management | MVFM NE CON GLB Fiber Bay Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-06-08 | 2020-06-15 | 2020-06-15 | Active | EP
NE CON GLB ALU Nokia Fiber Augment POR20 | NE | CON | GLB | MTC Fiber and Rack Management | MVFM NE CON GLB ALU Nokia Fiber Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-05-31 | 2020-05-31 | Active | EP
NE CON GLB ALU Nokia Fiber Augment POR20 | NE | CON | GLB | MTC Fiber and Rack Management | MVFM NE CON GLB ALU Nokia Fiber Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-05-31 | 2020-05-31 | Active | Log | Upd | SN-0308 | Schedule Change | Approved | 2020-02-28 18:25 | Accelerated receipt for ALU Upgrades to March and activity to April to July
NE CON GRB VAM Splitter Augment POR20 | NE | CON | GRB | MTC Fiber and Rack Management | MVFM NE CON GRB Fiber Bay Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-09-07 | 2020-09-15 | 2020-09-15 | Active | EP
NE CON GRB ALU Nokia Fiber Augment POR20 | NE | CON | GRB | MTC Fiber and Rack Management | MVFM NE CON GRB ALU Nokia Fiber Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-06-30 | 2020-06-30 | Active | EP
NE CON GRB ALU Nokia Fiber Augment POR20 | NE | CON | GRB | MTC Fiber and Rack Management | MVFM NE CON GRB ALU Nokia Fiber Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0308 | Schedule Change | Approved | 2020-02-28 18:25 | Accelerated receipt for ALU Upgrades to March and activity to April to July
CA SAN OCE CB Rack Environment Prep for CB Augment POR20 | CA | SAN | OCE | MTC Fiber and Rack Management | MVFM CA SAN OCE Rack Env Prep for CB Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | EP
CA SAN OCE CB Rack Environment Prep for CB Augment POR20 | CA | SAN | OCE | MTC Fiber and Rack Management | MVFM CA SAN OCE Rack Env Prep for CB Augment POR20 | Critical Facilities | Fiber bays, panels, & management system |  |  |  |  | Deleted | Log | Del | SN-0230 | Schedule Change | Approved | 2020-01-31 15:02 | Accelerating funding and plans from later in Q2 and Q3 as per the updated plan from Ron and Penny Rescheduling in reaction to node plan Related to EMO risk 268
CA SAN PWY Backbone Growth Edge Augment POR20 | CA | SAN | PWY | MTC Fiber and Rack Management | MVFM CA SAN PWY Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-05-06 | 2020-06-15 | 2020-07-15 | Active | EP
CA SAN PWY Backbone Growth Edge Augment POR20 | CA | SAN | PWY | MTC Fiber and Rack Management | MVFM CA SAN PWY Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-03-06 | 2020-04-30 | 2020-05-31 | Active | Log | Upd | SN-0230 | Schedule Change | Approved | 2020-01-31 15:02 | Accelerating funding and plans from later in Q2 and Q3 as per the updated plan from Ron and Penny Rescheduling in reaction to node plan Related to EMO risk 268
CA SAN PWY Backbone Growth Edge Augment POR20 | CA | SAN | PWY | MTC Fiber and Rack Management | MVFM CA SAN PWY Fiber Infrastructure Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-05-06 | 2020-06-15 | 2020-07-15 | Active | Log | Upd | SN-0388 | Schedule Change | Approved | 2020-03-30 14:42 | Funding and POR updates to align budget with open orders and feedback provided by field teams
MVFM VA HRD NWP Meet Me Rack Augment POR20 | VA | HRD | NWP | MTC Fiber and Rack Management | MVFM VA HRD NWP Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-05-06 | 2020-06-30 | 2020-07-31 | Active | EP
MVFM VA HRD NWP Meet Me Rack Augment POR20 | VA | HRD | NWP | MTC Fiber and Rack Management | MVFM VA HRD NWP Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-05-06 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0311 | Scope Change | Approved | 2020-03-05 13:29 | Descope Chesapeake and Lightfoot as these are covered under the RPHY plan for 2020 Request funding be made available for Newport and Virginia Beach as these sites did not originally go with the Meet-Me Rack model and we would like these to be uniform wi
MVFM VA HRD NWP Meet Me Rack Augment POR20 | VA | HRD | NWP | MTC Fiber and Rack Management | MVFM VA HRD NWP Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-05-06 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0793 | True up | Approved | 2020-08-20 18:09 | Returning excess funds for completed projects in SW and VA Aligning labor spend in NE for facilities still pending site visits Pushing funding for OSB to Nov to accomodate eq lead times
MVFM VA HRD VBC Meet Me Rack Augment POR20 | VA | HRD | VBC | MTC Fiber and Rack Management | MVFM VA HRD VBC Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-05-06 | 2020-06-30 | 2020-07-31 | Active | EP
MVFM VA HRD VBC Meet Me Rack Augment POR20 | VA | HRD | VBC | MTC Fiber and Rack Management | MVFM VA HRD VBC Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-05-06 | 2020-06-30 | 2020-06-30 | Active | Log | New | SN-0311 | Scope Change | Approved | 2020-03-05 13:29 | Descope Chesapeake and Lightfoot as these are covered under the RPHY plan for 2020 Request funding be made available for Newport and Virginia Beach as these sites did not originally go with the Meet-Me Rack model and we would like these to be uniform wi
MVFM VA HRD VBC Meet Me Rack Augment POR20 | VA | HRD | VBC | MTC Fiber and Rack Management | MVFM VA HRD VBC Meet Me Rack Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-05-06 | 2020-06-30 | 2020-07-31 | Active | Log | Upd | SN-0793 | True up | Approved | 2020-08-20 18:09 | Returning excess funds for completed projects in SW and VA Aligning labor spend in NE for facilities still pending site visits Pushing funding for OSB to Nov to accomodate eq lead times
MVFM SW LAS OSB OCML DLX40 Augment POR20 | SW | LAS | OSB | MTC Fiber and Rack Management | MVFM SW LAS OSB OCML DLX40 Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-09-22 | 2020-12-30 | 2020-12-30 | Active | EP
MVFM SW LAS OSB OCML DLX40 Augment POR20 | SW | LAS | OSB | MTC Fiber and Rack Management | MVFM SW LAS OSB OCML DLX40 Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-11-07 | 2020-12-30 | 2020-12-30 | Active | Log | New | SN-0793 | True up | Approved | 2020-08-20 18:09 | Returning excess funds for completed projects in SW and VA Aligning labor spend in NE for facilities still pending site visits Pushing funding for OSB to Nov to accomodate eq lead times
MVFM SW LAS OSB OCML DLX40 Augment POR20 | SW | LAS | OSB | MTC Fiber and Rack Management | MVFM SW LAS OSB OCML DLX40 Augment POR20 | Critical Facilities | Fiber bays, panels, & management system | 1 | 2020-09-22 | 2020-12-30 | 2020-12-30 | Active | Log | Upd | SN-0968 | Cost Change | Approved | 2020-10-02 14:53 | Determined by TPS that funding for the splicing activites for OSO should charge against CF budget as we don t add OSP tasks for Strat Plat Codes
MTCH COR COR ATL MPEG4 ATX Upgrade Deployment POR20 | COR | COR | ATL | MTC HE - Hub Signaling | MTCH CO COR ATL MPEG4 ATX Upgrade Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-06-10 | 2020-07-15 |  | Active | EP
MTCH COR COR ATL MPEG4 ATX Upgrade Deployment POR20 | COR | COR | ATL | MTC HE - Hub Signaling | MTCH CO COR ATL MPEG4 ATX Upgrade Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-04-06 | 2020-06-15 |  | Active | Log | Upd | SN-0021 | New | Approved | 2020-02-06 09:58 | This CR syncs the MTC HE - Hub Signaling 2020 budget and activity plan
MTCH COR COR ATL MPEG4 ATX Upgrade Deployment POR20 | COR | COR | ATL | MTC HE - Hub Signaling | MTCH CO COR ATL MPEG4 ATX Upgrade Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-05-06 | 2020-07-15 |  | Active | Log | Upd | SN-0296 | Schedule Change | Approved | 2020-03-30 14:43 | Bell Get Well Construction and permitting will delay migrations from April Also updating incorrect POR dates Pushing funding in SE by 1 month No open orders against April plan Deferring HFC receiver funding to Q3 and 4 from CT to RI sites Accellerati
MTCH COR COR ATL MPEG4 ATX Upgrade Deployment POR20 | COR | COR | ATL | MTC HE - Hub Signaling | MTCH CO COR ATL MPEG4 ATX Upgrade Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-06-10 | 2020-07-15 |  | Active | Log | Upd | SN-0680 | True up | Approved | 2020-06-17 11:52 | Missed material receipt: ATX gear for MPEG4 delivered to wrong address on 5 29 needed to be rerouted but are now received in June Various material backorders And Charges from RPHY CCAP hitting HEHS incorrectly and will need reclass
MTCH CA SAN ELC MPEG4 vDCM Install Deployment POR20 | CA | SAN | ELC | MTC HE - Hub Signaling | MTCH CA SAN ELC MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 4 | 2020-03-06 | 2020-10-15 | 2021-03-15 | Active | EP
MTCH CA SAN ELC MPEG4 vDCM Install Deployment POR20 | CA | SAN | ELC | MTC HE - Hub Signaling | MTCH CA SAN ELC MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-03-06 | 2020-04-15 | 2020-06-15 | Active | Log | Upd | SN-0136 | Schedule Change | Approved | 2020-02-06 11:03 | Updating POR and funding schedule to match the deployment schedule for MPEG4 vDCM installs Pulling funding from topside PPM to self solve new quote for 8VSB installs in CEN region
MTCH CA SAN ELC MPEG4 vDCM Install Deployment POR20 | CA | SAN | ELC | MTC HE - Hub Signaling | MTCH CA SAN ELC MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-03-06 | 2020-10-15 | 2021-03-15 | Active | Log | Upd | SN-0227 | Schedule Change | Approved | 2020-03-30 14:43 | Schedule for vDCM installs is being reprioritized, for purposes of accelerating lower impact market(s) and to allow for CB CMI dependencies to be completed
MTCH CA SAN ELC MPEG4 vDCM Install Deployment POR20 | CA | SAN | ELC | MTC HE - Hub Signaling | MTCH CA SAN ELC MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 4 | 2020-03-06 | 2020-10-15 | 2021-03-15 | Active | Log | Upd | SN-0575 | True up | Approved | 2020-05-14 17:56 | April True Up and Q2F April material variances due to vDCM material delays from WWT now received
MTCH CE ARK FAY 8VSB Replacement Deployment POR20 | CE | NWA | FAY | MTC HE - Hub Signaling | MTCH CE NWA FAY 8VSB Replacement Deployment POR20 | Chassis | Inca 4110 (2 RU) | 1 | 2020-02-06 | 2020-04-15 | 2020-05-15 | Active | EP
MTCH CE KAN DCY 8VSB Replacement Deployment POR20 | CE | KAN | DCY | MTC HE - Hub Signaling | MTCH CE KAN DCY 8VSB Replacement Deployment POR20 | Chassis | Inca 4110 (2 RU) | 1 | 2020-02-06 | 2020-04-15 | 2020-05-15 | Active | EP
MTCH CE ARK NWA MPEG4 vDCM Install Deployment POR20 | CE | NWA | NWA | MTC HE - Hub Signaling | MTCH CE NWA NWA MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-03-06 | 2021-02-15 | 2021-06-15 | Active | EP
MTCH CE ARK NWA MPEG4 vDCM Install Deployment POR20 | CE | NWA | NWA | MTC HE - Hub Signaling | MTCH CE NWA NWA MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-03-06 | 2021-02-15 | 2021-06-15 | Active | Log | Upd | SN-0227 | Schedule Change | Approved | 2020-03-30 14:43 | Schedule for vDCM installs is being reprioritized, for purposes of accelerating lower impact market(s) and to allow for CB CMI dependencies to be completed
MTCH CE OMA SVI 8VSB Replacement Deployment POR20 | CE | SUN | SVI | MTC HE - Hub Signaling | MTCH CE SUN SVI 8VSB Replacement Deployment POR20 | Chassis | Inca 4110 (2 RU) | 1 | 2020-02-06 | 2020-04-15 | 2020-05-15 | Active | EP
MTCH SW ARZ CHD MPEG4 vDCM Install Deployment POR20 | SW | ARZ | CHD | MTC HE - Hub Signaling | MTCH SW ARZ CHD MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 4 | 2020-10-15 | 2021-03-15 | 2021-05-15 | Active | EP
MTCH SW ARZ CHD MPEG4 vDCM Install Deployment POR20 | SW | ARZ | CHD | MTC HE - Hub Signaling | MTCH SW ARZ CHD MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 4 | 2020-03-06 | 2021-03-15 | 2021-05-15 | Active | Log | Upd | SN-0227 | Schedule Change | Approved | 2020-03-30 14:43 | Schedule for vDCM installs is being reprioritized, for purposes of accelerating lower impact market(s) and to allow for CB CMI dependencies to be completed
MTCH SW ARZ CHD MPEG4 vDCM Install Deployment POR20 | SW | ARZ | CHD | MTC HE - Hub Signaling | MTCH SW ARZ CHD MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 4 | 2020-10-15 | 2021-03-15 | 2021-05-15 | Active | Log | Upd | SN-0693 | Schedule Change | Approved | 2020-06-30 11:13 | Updates to align with new lead times for equipment from WWT changed to 72 to 80 days
MTCH SW LAS BLU HDRx to PII Receiver Deployment POR20 | SW | LAS | BLU | MTC HE - Hub Signaling | MTCH SW LAS BLU HDRx to PII Receiver Deployment POR20 | Chassis | PRISMA II XD CHASSIS |  |  |  |  | Deleted | EP
MTCH SW LAS BLU HDRx to PII Receiver Deployment POR20 | SW | LAS | BLU | MTC HE - Hub Signaling | MTCH SW LAS BLU HDRx to PII Receiver Deployment POR20 | Chassis | PRISMA II XD CHASSIS |  |  |  |  | Deleted | Log | Del | SN-0046 | Scope Change | Approved | 2020-02-06 10:15 | 680k giveback for the PII installs in the SW Tagged as regrettable spend in 2019, CR-944, but was already included in 2020 submissions
MTCH SW LAS HEN HDRx to PII Receiver Deployment POR20 | SW | LAS | HEN | MTC HE - Hub Signaling | MTCH SW LAS HEN HDRx to PII Receiver Deployment POR20 | Chassis | PRISMA II XD CHASSIS |  |  |  |  | Deleted | EP
MTCH SW LAS HEN HDRx to PII Receiver Deployment POR20 | SW | LAS | HEN | MTC HE - Hub Signaling | MTCH SW LAS HEN HDRx to PII Receiver Deployment POR20 | Chassis | PRISMA II XD CHASSIS |  |  |  |  | Deleted | Log | Del | SN-0046 | Scope Change | Approved | 2020-02-06 10:15 | 680k giveback for the PII installs in the SW Tagged as regrettable spend in 2019, CR-944, but was already included in 2020 submissions
MTCH SW LAS HEN MPEG4 vDCM Install Deployment POR20 | SW | LAS | HEN | MTC HE - Hub Signaling | MTCH SW LAS HEN MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-03-06 | 2021-03-15 | 2021-06-15 | Active | EP
MTCH SW LAS HEN MPEG4 vDCM Install Deployment POR20 | SW | LAS | HEN | MTC HE - Hub Signaling | MTCH SW LAS HEN MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-03-06 | 2021-03-15 | 2021-06-15 | Active | Log | Upd | SN-0227 | Schedule Change | Approved | 2020-03-30 14:43 | Schedule for vDCM installs is being reprioritized, for purposes of accelerating lower impact market(s) and to allow for CB CMI dependencies to be completed
MTCH CE OMA ONA 8VSB Replacement Deployment POR20 | CE | OMA | ONA | MTC HE - Hub Signaling | MTCH CE OMA ONA 8VSB Replacement Deployment POR20 | Chassis | Inca 4110 (2 RU) | 1 | 2020-02-06 | 2020-04-15 | 2020-05-15 | Active | EP
MTCH CA SAN ELC MPEG4 Tektronix Upgrade Deployment POR20 | CA | SAN | ELC | MTC HE - Hub Signaling | MTCH CA SAN ELC MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 4 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | EP
MTCH CA SAN ELC MPEG4 Tektronix Upgrade Deployment POR20 | CA | SAN | ELC | MTC HE - Hub Signaling | MTCH CA SAN ELC MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 4 | 2020-06-15 | 2020-07-15 | 2020-08-15 | Active | Log | Upd | SN-0575 | True up | Approved | 2020-05-14 17:56 | April True Up and Q2F April material variances due to vDCM material delays from WWT now received
MTCH CA SAN ELC MPEG4 Tektronix Upgrade Deployment POR20 | CA | SAN | ELC | MTC HE - Hub Signaling | MTCH CA SAN ELC MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 4 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | Log | Upd | SN-0692 | Schedule Change | Approved | 2020-06-30 11:13 | WATTs MOs now created and all material is on hand with SCM at warehouse in ARZ and expectation is for delivery of all material by EOM July with updates to labor to follow
MTCH CA SAN ELC Dish Upgrades Deployment POR20 | CA | SAN | ELC | MTC HE - Hub Signaling | MTCH CA SAN ELC Dish Upgrades Deployment POR20 | Labor | TVRO | 1 | 2020-08-31 | 2020-08-15 |  | Active | EP
MTCH CA SAN ELC Dish Upgrades Deployment POR20 | CA | SAN | ELC | MTC HE - Hub Signaling | MTCH CA SAN ELC Dish Upgrades Deployment POR20 | Labor | TVRO | 1 | 2020-08-31 | 2020-08-15 |  | Active | Log | Upd | SN-0852 | True up | Approved | 2020-08-20 18:04 | Missed receipt for Telestream orders now received in July Movement of labor funding from topside to field PPMs and 3PL to IHL Credit for WIC vDCM licenses pushing to October
MTCH CA SAN FED Vecima Replacement Deployment POR20 | CA | SAN | FED | MTC HE - Hub Signaling | MTCH CA SAN FED Vecima Replacement Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-04-06 | 2020-06-15 |  | Active | EP
MTCH CE KAN DCY Satellite Farm Move Deployment POR20 | CE | KAN | DCY | MTC HE - Hub Signaling | MTCH CE KAN DCY Satellite Farm Move Deployment POR20 | Labor | TVRO |  |  |  |  | Deleted | EP
MTCH CE KAN DCY Satellite Farm Move Deployment POR20 | CE | KAN | DCY | MTC HE - Hub Signaling | MTCH CE KAN DCY Satellite Farm Move Deployment POR20 | Labor | TVRO |  |  |  |  | Deleted | Log | Del | SN-0058 | Scope Change | Approved | 2020-02-06 10:23 | Work will not be completed at the market level Decision has been made to add this to the list for centralization in 2020 May request additional funding later through V2B, for the same
MTCH CE ARK NWA Dish Upgrades Deployment POR20 | CE | NWA | NWA | MTC HE - Hub Signaling | MTCH CE NWA NWA Dish Upgrades Deployment POR20 | Labor | TVRO |  |  |  |  | Deleted | EP
MTCH CE ARK NWA Dish Upgrades Deployment POR20 | CE | NWA | NWA | MTC HE - Hub Signaling | MTCH CE NWA NWA Dish Upgrades Deployment POR20 | Labor | TVRO |  |  |  |  | Deleted | Log | Del | SN-0536 | COVID-19 Related | Approved | 2020-05-08 14:24 | POR updates related to the Covid 19 deferrals
MTCH CE OMA OMM MPEG4 vDCM Install Deployment POR20 | CE | OMA | OMM | MTC HE - Hub Signaling | MTCH CE OMA OMM MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-05-06 | 2020-11-15 | 2021-03-15 | Active | EP
MTCH CE OMA OMM MPEG4 vDCM Install Deployment POR20 | CE | OMA | OMM | MTC HE - Hub Signaling | MTCH CE OMA OMM MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-05-06 | 2020-11-15 | 2021-03-15 | Active | Log | Upd | SN-0227 | Schedule Change | Approved | 2020-03-30 14:43 | Schedule for vDCM installs is being reprioritized, for purposes of accelerating lower impact market(s) and to allow for CB CMI dependencies to be completed
MTCH CE OMA OMM MPEG4 Tektronix Upgrade Deployment POR20 | CE | OMA | OMM | MTC HE - Hub Signaling | MTCH CE OMA OMM MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 3 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | EP
MTCH CE OMA OMM MPEG4 Tektronix Upgrade Deployment POR20 | CE | OMA | OMM | MTC HE - Hub Signaling | MTCH CE OMA OMM MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 3 | 2020-06-15 | 2020-07-15 | 2020-08-15 | Active | Log | Upd | SN-0575 | True up | Approved | 2020-05-14 17:56 | April True Up and Q2F April material variances due to vDCM material delays from WWT now received
MTCH CE OMA OMM MPEG4 Tektronix Upgrade Deployment POR20 | CE | OMA | OMM | MTC HE - Hub Signaling | MTCH CE OMA OMM MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 3 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | Log | Upd | SN-0692 | Schedule Change | Approved | 2020-06-30 11:13 | WATTs MOs now created and all material is on hand with SCM at warehouse in ARZ and expectation is for delivery of all material by EOM July with updates to labor to follow
MTCH All Channels Automation Deployment POR20 | COR | COR | ATL | MTC HE - Hub Signaling | MTCH CO COR ATL All Channels Automation Deployment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-08-06 | 2020-08-15 |  | Active | EP
MTCH DV6000 Replacement Deployment POR20 | COR | COR | ATL | MTC HE - Hub Signaling | MTCH CO COR ATL DV6000 Replacement Deployment POR20 | Chassis | Artel transceiver (3 RU) | 1 | 2020-08-06 | 2020-08-15 |  | Active | EP
MTCH NE CLE CLV Innotrans Unit Deployment POR20 | NE | CLE | CLV | MTC HE - Hub Signaling | MTCH NE CLE CLV Innotrans Unit Deployment POR20 | Critical Facilities | MTC Hub Signaling | 4 | 2020-07-31 | 2020-09-30 | 2020-10-31 | Active | EP
MTCH NE CLE CLV Innotrans Unit Deployment POR20 | NE | CLE | CLV | MTC HE - Hub Signaling | MTCH NE CLE CLV Innotrans Unit Deployment POR20 | Critical Facilities | MTC Hub Signaling | 4 | 2020-05-15 | 2020-06-30 | 2020-07-30 | Active | Log | Upd | SN-0296 | Schedule Change | Approved | 2020-03-30 14:43 | Bell Get Well Construction and permitting will delay migrations from April Also updating incorrect POR dates Pushing funding in SE by 1 month No open orders against April plan Deferring HFC receiver funding to Q3 and 4 from CT to RI sites Accellerati
MTCH NE CLE CLV Innotrans Unit Deployment POR20 | NE | CLE | CLV | MTC HE - Hub Signaling | MTCH NE CLE CLV Innotrans Unit Deployment POR20 | Critical Facilities | MTC Hub Signaling | 4 | 2020-08-13 | 2020-09-30 | 2020-10-31 | Active | Log | Upd | SN-0607 | Schedule Change | Approved | 2020-05-28 11:35 | Innotrans receiver order backordered from ATX now to August Accelerating funding for new req for additional Synamedia licenses in the lab And requesting schedule shift forward one month for RI HFC receiver replacements
MTCH NE CLE CLV Innotrans Unit Deployment POR20 | NE | CLE | CLV | MTC HE - Hub Signaling | MTCH NE CLE CLV Innotrans Unit Deployment POR20 | Critical Facilities | MTC Hub Signaling | 4 | 2020-07-31 | 2020-09-30 | 2020-10-31 | Active | Log | Upd | SN-0852 | True up | Approved | 2020-08-20 18:04 | Missed receipt for Telestream orders now received in July Movement of labor funding from topside to field PPMs and 3PL to IHL Credit for WIC vDCM licenses pushing to October
MTCH NE CLE CLV Dish Upgrades Deployment POR20 | NE | CLE | CLV | MTC HE - Hub Signaling | MTCH NE CLE CLV Dish Upgrades Deployment POR20 | Labor | TVRO |  |  |  |  | Deleted | EP
MTCH NE CLE CLV Dish Upgrades Deployment POR20 | NE | CLE | CLV | MTC HE - Hub Signaling | MTCH NE CLE CLV Dish Upgrades Deployment POR20 | Labor | TVRO |  |  |  |  | Deleted | Log | Del | SN-0536 | COVID-19 Related | Approved | 2020-05-08 14:24 | POR updates related to the Covid 19 deferrals
MTCH NE CON GLB HFC Receiver Deployment POR20 | NE | CON | GLB | MTC HE - Hub Signaling | MTCH NE CON GLB HFC Receiver Deployment POR20 | Chassis | Receiver (1 RU) | 1 | 2020-03-06 | 2020-04-30 |  | Active | EP
MTCH NE CON GLB HFC Receiver Deployment POR20 | NE | CON | GLB | MTC HE - Hub Signaling | MTCH NE CON GLB HFC Receiver Deployment POR20 | Chassis | Receiver (1 RU) | 1 | 2020-03-06 | 2020-04-30 |  | Active | Log | Upd | SN-0021 | New | Approved | 2020-02-06 09:58 | This CR syncs the MTC HE - Hub Signaling 2020 budget and activity plan
MTCH NE CON GLB HFC Receiver Deployment POR20 | NE | CON | GLB | MTC HE - Hub Signaling | MTCH NE CON GLB HFC Receiver Deployment POR20 | Chassis | Receiver (1 RU) | 1 | 2020-03-06 | 2020-04-30 |  | Active | Log | Upd | SN-0288 | Schedule Change | Approved | 2020-03-05 11:36 | Updating POR for CON projects as orders are in flight and on track for March receipt
MTCH NE CON GLB RF Passive Splitter Deployment POR20 | NE | CON | GLB | MTC HE - Hub Signaling | MTCH NE CON GLB RF Passive Splitter Deployment POR20 | Chassis | 8-way splitter | 1 | 2020-03-06 | 2020-04-30 |  | Active | EP
MTCH NE CON GLB RF Passive Splitter Deployment POR20 | NE | CON | GLB | MTC HE - Hub Signaling | MTCH NE CON GLB RF Passive Splitter Deployment POR20 | Chassis | 8-way splitter | 1 | 2020-03-06 | 2020-04-30 |  | Active | Log | Upd | SN-0021 | New | Approved | 2020-02-06 09:58 | This CR syncs the MTC HE - Hub Signaling 2020 budget and activity plan
MTCH NE CON GRB HFC Receiver Deployment POR20 | NE | CON | GRB | MTC HE - Hub Signaling | MTCH NE CON GRB HFC Receiver Deployment POR20 | Chassis | Receiver (1 RU) | 1 | 2020-03-06 | 2020-04-30 |  | Active | EP
MTCH NE CON GRB HFC Receiver Deployment POR20 | NE | CON | GRB | MTC HE - Hub Signaling | MTCH NE CON GRB HFC Receiver Deployment POR20 | Chassis | Receiver (1 RU) | 1 | 2020-04-06 | 2020-05-31 |  | Active | Log | Upd | SN-0021 | New | Approved | 2020-02-06 09:58 | This CR syncs the MTC HE - Hub Signaling 2020 budget and activity plan
MTCH NE CON GRB HFC Receiver Deployment POR20 | NE | CON | GRB | MTC HE - Hub Signaling | MTCH NE CON GRB HFC Receiver Deployment POR20 | Chassis | Receiver (1 RU) | 1 | 2020-03-06 | 2020-04-30 |  | Active | Log | Upd | SN-0288 | Schedule Change | Approved | 2020-03-05 11:36 | Updating POR for CON projects as orders are in flight and on track for March receipt
MTCH NE CON MAN Innotrans Unit Deployment POR20 | NE | CON | MAN | MTC HE - Hub Signaling | MTCH NE CON MAN Innotrans Unit Deployment POR20 | Critical Facilities | MTC Hub Signaling | 4 | 2020-07-31 | 2020-09-30 | 2020-10-31 | Active | EP
MTCH NE CON MAN Innotrans Unit Deployment POR20 | NE | CON | MAN | MTC HE - Hub Signaling | MTCH NE CON MAN Innotrans Unit Deployment POR20 | Critical Facilities | MTC Hub Signaling | 4 | 2020-05-15 | 2020-06-30 | 2020-07-30 | Active | Log | Upd | SN-0296 | Schedule Change | Approved | 2020-03-30 14:43 | Bell Get Well Construction and permitting will delay migrations from April Also updating incorrect POR dates Pushing funding in SE by 1 month No open orders against April plan Deferring HFC receiver funding to Q3 and 4 from CT to RI sites Accellerati
MTCH NE CON MAN Innotrans Unit Deployment POR20 | NE | CON | MAN | MTC HE - Hub Signaling | MTCH NE CON MAN Innotrans Unit Deployment POR20 | Critical Facilities | MTC Hub Signaling | 4 | 2020-08-13 | 2020-09-30 | 2020-10-31 | Active | Log | Upd | SN-0607 | Schedule Change | Approved | 2020-05-28 11:35 | Innotrans receiver order backordered from ATX now to August Accelerating funding for new req for additional Synamedia licenses in the lab And requesting schedule shift forward one month for RI HFC receiver replacements
MTCH NE CON MAN Innotrans Unit Deployment POR20 | NE | CON | MAN | MTC HE - Hub Signaling | MTCH NE CON MAN Innotrans Unit Deployment POR20 | Critical Facilities | MTC Hub Signaling | 4 | 2020-07-31 | 2020-09-30 | 2020-10-31 | Active | Log | Upd | SN-0852 | True up | Approved | 2020-08-20 18:04 | Missed receipt for Telestream orders now received in July Movement of labor funding from topside to field PPMs and 3PL to IHL Credit for WIC vDCM licenses pushing to October
MTCH NE CON MAN Dish Upgrades Deployment POR20 | NE | CON | MAN | MTC HE - Hub Signaling | MTCH NE CON MAN Dish Upgrades Deployment POR20 | Labor | TVRO |  |  |  |  | Deleted | EP
MTCH NE CON MAN Dish Upgrades Deployment POR20 | NE | CON | MAN | MTC HE - Hub Signaling | MTCH NE CON MAN Dish Upgrades Deployment POR20 | Labor | TVRO |  |  |  |  | Deleted | Log | Del | SN-0536 | COVID-19 Related | Approved | 2020-05-08 14:24 | POR updates related to the Covid 19 deferrals
MTCH NE CON STN RF Passive Splitter Deployment POR20 | NE | CON | STN | MTC HE - Hub Signaling | MTCH NE CON STN RF Passive Splitter Deployment POR20 | Chassis | 8-way splitter | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | EP
MTCH NE CON SFD HFC Receiver Deployment POR20 | NE | CON | SFD | MTC HE - Hub Signaling | MTCH NE CON SFD HFC Receiver Deployment POR20 | Chassis | Receiver (1 RU) | 1 | 2020-03-06 | 2020-04-30 |  | Active | EP
MTCH NE CON SFD HFC Receiver Deployment POR20 | NE | CON | SFD | MTC HE - Hub Signaling | MTCH NE CON SFD HFC Receiver Deployment POR20 | Chassis | Receiver (1 RU) | 1 | 2020-05-06 | 2020-06-30 |  | Active | Log | Upd | SN-0021 | New | Approved | 2020-02-06 09:58 | This CR syncs the MTC HE - Hub Signaling 2020 budget and activity plan
MTCH NE CON SFD HFC Receiver Deployment POR20 | NE | CON | SFD | MTC HE - Hub Signaling | MTCH NE CON SFD HFC Receiver Deployment POR20 | Chassis | Receiver (1 RU) | 1 | 2020-03-06 | 2020-04-30 |  | Active | Log | Upd | SN-0288 | Schedule Change | Approved | 2020-03-05 11:36 | Updating POR for CON projects as orders are in flight and on track for March receipt
MTCH NE CON SFD RF Passive Splitter Deployment POR20 | NE | CON | SFD | MTC HE - Hub Signaling | MTCH NE CON SFD RF Passive Splitter Deployment POR20 | Chassis | 8-way splitter | 1 | 2020-05-06 | 2020-06-30 |  | Active | EP
MTCH NE CON SFD RF Passive Splitter Deployment POR20 | NE | CON | SFD | MTC HE - Hub Signaling | MTCH NE CON SFD RF Passive Splitter Deployment POR20 | Chassis | 8-way splitter | 1 | 2020-05-06 | 2020-06-30 |  | Active | Log | Upd | SN-0021 | New | Approved | 2020-02-06 09:58 | This CR syncs the MTC HE - Hub Signaling 2020 budget and activity plan
MTCH NE RHD LNC HFC Receiver Deployment POR20 | NE | RHD | LNC | MTC HE - Hub Signaling | MTCH NE RHD LNC HFC Receiver Deployment POR20 | Chassis | Receiver (1 RU) | 1 | 2020-07-06 | 2020-08-31 |  | Active | EP
MTCH NE RHD LNC HFC Receiver Deployment POR20 | NE | RHD | LNC | MTC HE - Hub Signaling | MTCH NE RHD LNC HFC Receiver Deployment POR20 | Chassis | Receiver (1 RU) | 1 | 2020-07-06 | 2020-08-31 |  | Active | Log | Upd | SN-0021 | New | Approved | 2020-02-06 09:58 | This CR syncs the MTC HE - Hub Signaling 2020 budget and activity plan
MTCH NE RHD LNC HFC Receiver Deployment POR20 | NE | RHD | LNC | MTC HE - Hub Signaling | MTCH NE RHD LNC HFC Receiver Deployment POR20 | Chassis | Receiver (1 RU) | 1 | 2020-05-06 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0307 | Schedule Change | Canceled | 2020-05-21 12:16 | Accelerating material receipt for Rhode Island sites into May as site walks and plans are now completed Funding previously in Q3 and Q4
MTCH SE GLA MCY Uplink Combining Augment POR20 | SE | NOR | MCY | MTC HE - Hub Signaling | MTCH SE NOR MCY Uplink Combining Augment POR20 | Critical Facilities | MTC Hub Signaling |  |  |  |  | Deleted | EP
MTCH SE GLA MCY Uplink Combining Augment POR20 | SE | NOR | MCY | MTC HE - Hub Signaling | MTCH SE NOR MCY Uplink Combining Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-05-06 | 2020-06-15 | 2020-07-15 | Deleted | Log | Upd | SN-0456 | True up | Approved | 2020-04-17 16:27 | Material variance fueled largely due to unexpected charge to 2019 project code in NE and innacurate initial estimates for the MPEG4 vDCM projects Labor variances accumulated across field PPMs related to RPHY Test Rack projects and labor charging ahead o
MTCH SE GLA MCY Uplink Combining Augment POR20 | SE | NOR | MCY | MTC HE - Hub Signaling | MTCH SE NOR MCY Uplink Combining Augment POR20 | Critical Facilities | MTC Hub Signaling |  |  |  |  | Deleted | Log | Del | SN-0536 | COVID-19 Related | Approved | 2020-05-08 14:24 | POR updates related to the Covid 19 deferrals
MTCH SE GLA NOE Satellite Receiver Deployment POR20 | SE | NOR | NOE | MTC HE - Hub Signaling | MTCH SE NOR NOE Satellite Receiver Deployment POR20 | Chassis | Receiver (1 RU) |  |  |  |  | Deleted | EP
MTCH SE GLA NOE Satellite Receiver Deployment POR20 | SE | NOR | NOE | MTC HE - Hub Signaling | MTCH SE NOR NOE Satellite Receiver Deployment POR20 | Chassis | Receiver (1 RU) | 2 | 2020-06-06 | 2020-07-15 | 2020-08-15 | Deleted | Log | Upd | SN-0456 | True up | Approved | 2020-04-17 16:27 | Material variance fueled largely due to unexpected charge to 2019 project code in NE and innacurate initial estimates for the MPEG4 vDCM projects Labor variances accumulated across field PPMs related to RPHY Test Rack projects and labor charging ahead o
MTCH SE GLA NOE Satellite Receiver Deployment POR20 | SE | NOR | NOE | MTC HE - Hub Signaling | MTCH SE NOR NOE Satellite Receiver Deployment POR20 | Chassis | Receiver (1 RU) |  |  |  |  | Deleted | Log | Del | SN-0536 | COVID-19 Related | Approved | 2020-05-08 14:24 | POR updates related to the Covid 19 deferrals
MTCH SE GLA NOE Uplink Combining Augment POR20 | SE | NOR | NOE | MTC HE - Hub Signaling | MTCH SE NOR NOE Uplink Combining Augment POR20 | Critical Facilities | MTC Hub Signaling |  |  |  |  | Deleted | EP
MTCH SE GLA NOE Uplink Combining Augment POR20 | SE | NOR | NOE | MTC HE - Hub Signaling | MTCH SE NOR NOE Uplink Combining Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-05-06 | 2020-06-15 | 2020-07-15 | Deleted | Log | Upd | SN-0456 | True up | Approved | 2020-04-17 16:27 | Material variance fueled largely due to unexpected charge to 2019 project code in NE and innacurate initial estimates for the MPEG4 vDCM projects Labor variances accumulated across field PPMs related to RPHY Test Rack projects and labor charging ahead o
MTCH SE GLA NOE Uplink Combining Augment POR20 | SE | NOR | NOE | MTC HE - Hub Signaling | MTCH SE NOR NOE Uplink Combining Augment POR20 | Critical Facilities | MTC Hub Signaling |  |  |  |  | Deleted | Log | Del | SN-0536 | COVID-19 Related | Approved | 2020-05-08 14:24 | POR updates related to the Covid 19 deferrals
MTCH SE GCT FWB Uplink Combining Augment POR20 | SE | GCT | FWB | MTC HE - Hub Signaling | MTCH SE GCT FWB Uplink Combining Augment POR20 | Critical Facilities | MTC Hub Signaling |  |  |  |  | Deleted | EP
MTCH SE GCT FWB Uplink Combining Augment POR20 | SE | GCT | FWB | MTC HE - Hub Signaling | MTCH SE GCT FWB Uplink Combining Augment POR20 | Critical Facilities | MTC Hub Signaling |  |  |  |  | Deleted | Log | Del | SN-0536 | COVID-19 Related | Approved | 2020-05-08 14:24 | POR updates related to the Covid 19 deferrals
MTCH SE GCT PNS Satellite Receiver Deployment POR20 | SE | GCT | PNS | MTC HE - Hub Signaling | MTCH SE GCT PNS Satellite Receiver Deployment POR20 | Chassis | Receiver (1 RU) |  |  |  |  | Deleted | EP
MTCH SE GCT PNS Satellite Receiver Deployment POR20 | SE | GCT | PNS | MTC HE - Hub Signaling | MTCH SE GCT PNS Satellite Receiver Deployment POR20 | Chassis | Receiver (1 RU) |  |  |  |  | Deleted | Log | Del | SN-0536 | COVID-19 Related | Approved | 2020-05-08 14:24 | POR updates related to the Covid 19 deferrals
MTCH SE MGA MCN Satellite Receiver Deployment POR20 | SE | MGA | MCN | MTC HE - Hub Signaling | MTCH SE MGA MCN Satellite Receiver Deployment POR20 | Chassis | Receiver (1 RU) |  |  |  |  | Deleted | EP
MTCH SE MGA MCN Satellite Receiver Deployment POR20 | SE | MGA | MCN | MTC HE - Hub Signaling | MTCH SE MGA MCN Satellite Receiver Deployment POR20 | Chassis | Receiver (1 RU) |  |  |  |  | Deleted | Log | Del | SN-0536 | COVID-19 Related | Approved | 2020-05-08 14:24 | POR updates related to the Covid 19 deferrals
MTCH SW ARZ CHD MPEG4 Tektronix Upgrade Deployment POR20 | SW | ARZ | CHD | MTC HE - Hub Signaling | MTCH SW ARZ CHD MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | EP
MTCH SW ARZ CHD MPEG4 Tektronix Upgrade Deployment POR20 | SW | ARZ | CHD | MTC HE - Hub Signaling | MTCH SW ARZ CHD MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-11-15 | 2020-12-15 | 2021-01-15 | Active | Log | Upd | SN-0575 | True up | Approved | 2020-05-14 17:56 | April True Up and Q2F April material variances due to vDCM material delays from WWT now received
MTCH SW ARZ CHD MPEG4 Tektronix Upgrade Deployment POR20 | SW | ARZ | CHD | MTC HE - Hub Signaling | MTCH SW ARZ CHD MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | Log | Upd | SN-0692 | Schedule Change | Approved | 2020-06-30 11:13 | WATTs MOs now created and all material is on hand with SCM at warehouse in ARZ and expectation is for delivery of all material by EOM July with updates to labor to follow
MTCH SW LAS HEN MPEG4 Tektronix Upgrade Deployment POR20 | SW | LAS | HEN | MTC HE - Hub Signaling | MTCH SW LAS HEN MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 2 | 2020-08-07 | 2020-08-30 | 2020-09-30 | Active | EP
MTCH SW LAS HEN MPEG4 Tektronix Upgrade Deployment POR20 | SW | LAS | HEN | MTC HE - Hub Signaling | MTCH SW LAS HEN MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 2 | 2020-06-15 | 2020-07-15 | 2020-08-15 | Active | Log | Upd | SN-0575 | True up | Approved | 2020-05-14 17:56 | April True Up and Q2F April material variances due to vDCM material delays from WWT now received
MTCH SW LAS HEN MPEG4 Tektronix Upgrade Deployment POR20 | SW | LAS | HEN | MTC HE - Hub Signaling | MTCH SW LAS HEN MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 2 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | Log | Upd | SN-0692 | Schedule Change | Approved | 2020-06-30 11:13 | WATTs MOs now created and all material is on hand with SCM at warehouse in ARZ and expectation is for delivery of all material by EOM July with updates to labor to follow
MTCH SW LAS HEN MPEG4 Tektronix Upgrade Deployment POR20 | SW | LAS | HEN | MTC HE - Hub Signaling | MTCH SW LAS HEN MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 2 | 2020-08-07 | 2020-08-30 | 2020-09-30 | Active | Log | Upd | SN-0852 | True up | Approved | 2020-08-20 18:04 | Missed receipt for Telestream orders now received in July Movement of labor funding from topside to field PPMs and 3PL to IHL Credit for WIC vDCM licenses pushing to October
MTCH SW LAS TEN HDRx to PII Receiver Deployment POR20 | SW | LAS | TEN | MTC HE - Hub Signaling | MTCH SW LAS TEN HDRx to PII Receiver Deployment POR20 | Chassis | PRISMA II XD CHASSIS |  |  |  |  | Deleted | EP
MTCH SW LAS TEN HDRx to PII Receiver Deployment POR20 | SW | LAS | TEN | MTC HE - Hub Signaling | MTCH SW LAS TEN HDRx to PII Receiver Deployment POR20 | Chassis | PRISMA II XD CHASSIS |  |  |  |  | Deleted | Log | Del | SN-0046 | Scope Change | Approved | 2020-02-06 10:15 | 680k giveback for the PII installs in the SW Tagged as regrettable spend in 2019, CR-944, but was already included in 2020 submissions
MTCH VA NVA FLK Equipment Consolidation Alignment POR20 | VA | NVA | FLK | MTC HE - Hub Signaling | MTCH VA NVA FLK Equipment Consolidation Alignment POR20 | Critical Facilities | MTC Hub Signaling |  |  |  |  | Deleted | EP
MTCH VA NVA FLK Equipment Consolidation Alignment POR20 | VA | NVA | FLK | MTC HE - Hub Signaling | MTCH VA NVA FLK Equipment Consolidation Alignment POR20 | Critical Facilities | MTC Hub Signaling |  |  |  |  | Deleted | Log | Del | SN-0536 | COVID-19 Related | Approved | 2020-05-08 14:24 | POR updates related to the Covid 19 deferrals
MTCH VA NVA MFD PEG Transport Deployment POR20 | VA | NVA | MFD | MTC HE - Hub Signaling | MTCH VA NVA MFD PEG Transport Deployment POR20 | Chassis | Drake encoder (1 RU) |  |  |  |  | Deleted | EP
MTCH VA NVA MFD PEG Transport Deployment POR20 | VA | NVA | MFD | MTC HE - Hub Signaling | MTCH VA NVA MFD PEG Transport Deployment POR20 | Chassis | Drake encoder (1 RU) |  |  |  |  | Deleted | Log | Del | SN-0536 | COVID-19 Related | Approved | 2020-05-08 14:24 | POR updates related to the Covid 19 deferrals
MTCH VA NVA TCR Equipment Consolidation Alignment POR20 | VA | NVA | TCR | MTC HE - Hub Signaling | MTCH VA NVA TCR Equipment Consolidation Alignment POR20 | Critical Facilities | MTC Hub Signaling |  |  |  |  | Deleted | EP
MTCH VA NVA TCR Equipment Consolidation Alignment POR20 | VA | NVA | TCR | MTC HE - Hub Signaling | MTCH VA NVA TCR Equipment Consolidation Alignment POR20 | Critical Facilities | MTC Hub Signaling |  |  |  |  | Deleted | Log | Del | SN-0536 | COVID-19 Related | Approved | 2020-05-08 14:24 | POR updates related to the Covid 19 deferrals
MTCH VA ROA RON MPEG4 vDCM Install Deployment POR20 | VA | ROA | RON | MTC HE - Hub Signaling | MTCH VA ROA RON MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config |  |  |  |  | Deleted | EP
MTCH VA ROA RON MPEG4 vDCM Install Deployment POR20 | VA | ROA | RON | MTC HE - Hub Signaling | MTCH VA ROA RON MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config |  |  |  |  | Deleted | Log | Del | SN-0227 | Schedule Change | Approved | 2020-03-30 14:43 | Schedule for vDCM installs is being reprioritized, for purposes of accelerating lower impact market(s) and to allow for CB CMI dependencies to be completed
MTCH CE ARK NWA MPEG4 Tektronix Upgrade Deployment POR20 | CE | NWA | NWA | MTC HE - Hub Signaling | MTCH CE NWA NWA MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | EP
MTCH CE ARK NWA MPEG4 Tektronix Upgrade Deployment POR20 | CE | NWA | NWA | MTC HE - Hub Signaling | MTCH CE NWA NWA MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-11-15 | 2020-12-15 | 2021-01-15 | Active | Log | Upd | SN-0575 | True up | Approved | 2020-05-14 17:56 | April True Up and Q2F April material variances due to vDCM material delays from WWT now received
MTCH CE ARK NWA MPEG4 Tektronix Upgrade Deployment POR20 | CE | NWA | NWA | MTC HE - Hub Signaling | MTCH CE NWA NWA MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | Log | Upd | SN-0692 | Schedule Change | Approved | 2020-06-30 11:13 | WATTs MOs now created and all material is on hand with SCM at warehouse in ARZ and expectation is for delivery of all material by EOM July with updates to labor to follow
MTCH CE KAN WIC PEG Transport Deployment POR20 | CE | KAN | WIC | MTC HE - Hub Signaling | MTCH CE KAN WIC PEG Transport Deployment POR20 | Chassis | Drake encoder (1 RU) | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | EP
MTCH CE KAN WIC MPEG4 vDCM Install Deployment POR20 | CE | KAN | WIC | MTC HE - Hub Signaling | MTCH CE KAN WIC MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 4 | 2020-04-15 | 2021-02-15 | 2021-05-15 | Active | EP
MTCH CE KAN WIC MPEG4 vDCM Install Deployment POR20 | CE | KAN | WIC | MTC HE - Hub Signaling | MTCH CE KAN WIC MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 4 | 2020-04-15 | 2021-02-15 | 2021-05-15 | Active | Log | Upd | SN-0227 | Schedule Change | Approved | 2020-03-30 14:43 | Schedule for vDCM installs is being reprioritized, for purposes of accelerating lower impact market(s) and to allow for CB CMI dependencies to be completed
MTCH CE KAN WIC MPEG4 Tektronix Upgrade Deployment POR20 | CE | KAN | WIC | MTC HE - Hub Signaling | MTCH CE KAN WIC MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 2 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | EP
MTCH CE KAN WIC MPEG4 Tektronix Upgrade Deployment POR20 | CE | KAN | WIC | MTC HE - Hub Signaling | MTCH CE KAN WIC MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 2 | 2020-06-15 | 2020-07-15 | 2020-08-15 | Active | Log | Upd | SN-0575 | True up | Approved | 2020-05-14 17:56 | April True Up and Q2F April material variances due to vDCM material delays from WWT now received
MTCH CE KAN WIC MPEG4 Tektronix Upgrade Deployment POR20 | CE | KAN | WIC | MTC HE - Hub Signaling | MTCH CE KAN WIC MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 2 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | Log | Upd | SN-0692 | Schedule Change | Approved | 2020-06-30 11:13 | WATTs MOs now created and all material is on hand with SCM at warehouse in ARZ and expectation is for delivery of all material by EOM July with updates to labor to follow
MTCH CE OKC NOR Signal Rewire Augment POR20 | CE | OKC | NOR | MTC HE - Hub Signaling | MTCH CE OKC NOR Signal Rewire Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-05-06 | 2020-07-15 | 2020-08-15 | Active | EP
MTCH CE OKC NEH Signal Rewire Augment POR20 | CE | OKC | NEH | MTC HE - Hub Signaling | MTCH CE OKC NEH Signal Rewire Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-05-06 | 2020-07-15 | 2020-08-15 | Active | EP
MTCH CE OKC OKC Signal Rewire Augment POR20 | CE | OKC | MOO | MTC HE - Hub Signaling | MTCH CE OKC MOO Signal Rewire Augment POR20 | Critical Facilities | MTC Hub Signaling |  |  |  |  | Deleted | EP
MTCH CE OKC OKC Signal Rewire Augment POR20 | CE | OKC | MOO | MTC HE - Hub Signaling | MTCH CE OKC MOO Signal Rewire Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-05-06 | 2020-07-15 | 2020-08-15 | Deleted | Log | Upd | SN-0415 | Schedule Change | Approved | 2020-03-30 15:28 | Fixes to 2 activity plans and equipment IDs to align CCRB database and manual POR
MTCH CE OKC OKC Signal Rewire Augment POR20 | CE | OKC | MOO | MTC HE - Hub Signaling | MTCH CE OKC MOO Signal Rewire Augment POR20 | Critical Facilities | MTC Hub Signaling |  |  |  |  | Deleted | Log | Del | SN-0368 | Schedule Change | Approved | 2020-04-10 15:22 | POR Updates for solutions team corrections and vDCM site adds related to CR227 for EPS projects that were not created yet No financial impact
MTCH CE OKC OKC MPEG4 vDCM Install Deployment POR20 | CE | OKC | OKC | MTC HE - Hub Signaling | MTCH CE OKC OKC MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-05-06 | 2020-12-15 | 2021-03-15 | Active | EP
MTCH CE OKC OKC MPEG4 vDCM Install Deployment POR20 | CE | OKC | OKC | MTC HE - Hub Signaling | MTCH CE OKC OKC MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-07-06 | 2020-08-15 | 2020-09-15 | Active | Log | Upd | SN-0136 | Schedule Change | Approved | 2020-02-06 11:03 | Updating POR and funding schedule to match the deployment schedule for MPEG4 vDCM installs Pulling funding from topside PPM to self solve new quote for 8VSB installs in CEN region
MTCH CE OKC OKC MPEG4 vDCM Install Deployment POR20 | CE | OKC | OKC | MTC HE - Hub Signaling | MTCH CE OKC OKC MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-05-06 | 2020-12-15 | 2021-03-15 | Active | Log | Upd | SN-0227 | Schedule Change | Approved | 2020-03-30 14:43 | Schedule for vDCM installs is being reprioritized, for purposes of accelerating lower impact market(s) and to allow for CB CMI dependencies to be completed
MTCH CE OKC TUL Dish Upgrades Deployment POR20 | CE | TUL | TUL | MTC HE - Hub Signaling | MTCH CE TUL TUL Dish Upgrades Deployment POR20 | Labor | TVRO |  |  |  |  | Deleted | EP
MTCH CE OKC TUL Dish Upgrades Deployment POR20 | CE | TUL | TUL | MTC HE - Hub Signaling | MTCH CE TUL TUL Dish Upgrades Deployment POR20 | Labor | TVRO |  |  |  |  | Deleted | Log | Del | SN-0536 | COVID-19 Related | Approved | 2020-05-08 14:24 | POR updates related to the Covid 19 deferrals
MTCH CE OKC TUL MPEG4 vDCM Install Deployment POR20 | CE | TUL | TUL | MTC HE - Hub Signaling | MTCH CE TUL TUL MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-06-06 | 2020-11-15 | 2021-03-15 | Active | EP
MTCH CE OKC TUL MPEG4 vDCM Install Deployment POR20 | CE | TUL | TUL | MTC HE - Hub Signaling | MTCH CE TUL TUL MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-07-06 | 2020-08-15 | 2020-09-15 | Active | Log | Upd | SN-0136 | Schedule Change | Approved | 2020-02-06 11:03 | Updating POR and funding schedule to match the deployment schedule for MPEG4 vDCM installs Pulling funding from topside PPM to self solve new quote for 8VSB installs in CEN region
MTCH CE OKC TUL MPEG4 vDCM Install Deployment POR20 | CE | TUL | TUL | MTC HE - Hub Signaling | MTCH CE TUL TUL MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-05-06 | 2020-11-15 | 2021-03-15 | Active | Log | Upd | SN-0227 | Schedule Change | Approved | 2020-03-30 14:43 | Schedule for vDCM installs is being reprioritized, for purposes of accelerating lower impact market(s) and to allow for CB CMI dependencies to be completed
MTCH CE OKC TUL MPEG4 vDCM Install Deployment POR20 | CE | TUL | TUL | MTC HE - Hub Signaling | MTCH CE TUL TUL MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-06-06 | 2020-11-15 | 2021-03-15 | Active | Log | Upd | SN-0575 | True up | Approved | 2020-05-14 17:56 | April True Up and Q2F April material variances due to vDCM material delays from WWT now received
MTCH CE OMA OMM Satellite Farm Move Deployment POR20 | CE | OMA | OMM | MTC HE - Hub Signaling | MTCH CE OMA OMM Satellite Farm Move Deployment POR20 | Labor | TVRO |  |  |  |  | Deleted | EP
MTCH CE OMA OMM Satellite Farm Move Deployment POR20 | CE | OMA | OMM | MTC HE - Hub Signaling | MTCH CE OMA OMM Satellite Farm Move Deployment POR20 | Labor | TVRO |  |  |  |  | Deleted | Log | Del | SN-0058 | Scope Change | Approved | 2020-02-06 10:23 | Work will not be completed at the market level Decision has been made to add this to the list for centralization in 2020 May request additional funding later through V2B, for the same
MTCH NE RHD LNC RF Passive Splitter Deployment POR20 | NE | RHD | LNC | MTC HE - Hub Signaling | MTCH NE RHD LNC RF Passive Splitter Deployment POR20 | Chassis | 8-way splitter | 1 | 2020-07-06 | 2020-08-15 | 2020-09-15 | Active | EP
MTCH NE RHD LNC RF Passive Splitter Deployment POR20 | NE | RHD | LNC | MTC HE - Hub Signaling | MTCH NE RHD LNC RF Passive Splitter Deployment POR20 | Chassis | 8-way splitter | 1 | 2020-05-06 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0307 | Schedule Change | Canceled | 2020-05-21 12:16 | Accelerating material receipt for Rhode Island sites into May as site walks and plans are now completed Funding previously in Q3 and Q4
MTCH NE RHD PAW HFC Receiver Deployment POR20 | NE | RHD | PAW | MTC HE - Hub Signaling | MTCH NE RHD PAW HFC Receiver Deployment POR20 | Chassis | Receiver (1 RU) | 1 | 2020-07-06 | 2020-09-30 |  | Active | EP
MTCH NE RHD PAW HFC Receiver Deployment POR20 | NE | RHD | PAW | MTC HE - Hub Signaling | MTCH NE RHD PAW HFC Receiver Deployment POR20 | Chassis | Receiver (1 RU) | 1 | 2020-08-06 | 2020-09-30 |  | Active | Log | Upd | SN-0021 | New | Approved | 2020-02-06 09:58 | This CR syncs the MTC HE - Hub Signaling 2020 budget and activity plan
MTCH NE RHD PAW HFC Receiver Deployment POR20 | NE | RHD | PAW | MTC HE - Hub Signaling | MTCH NE RHD PAW HFC Receiver Deployment POR20 | Chassis | Receiver (1 RU) | 1 | 2020-05-06 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0307 | Schedule Change | Canceled | 2020-05-21 12:16 | Accelerating material receipt for Rhode Island sites into May as site walks and plans are now completed Funding previously in Q3 and Q4
MTCH NE RHD PAW HFC Receiver Deployment POR20 | NE | RHD | PAW | MTC HE - Hub Signaling | MTCH NE RHD PAW HFC Receiver Deployment POR20 | Chassis | Receiver (1 RU) | 1 | 2020-07-06 | 2020-09-30 |  | Active | Log | Upd | SN-0607 | Schedule Change | Approved | 2020-05-28 11:35 | Innotrans receiver order backordered from ATX now to August Accelerating funding for new req for additional Synamedia licenses in the lab And requesting schedule shift forward one month for RI HFC receiver replacements
MTCH NE RHD PAW RF Passive Splitter Deployment POR20 | NE | RHD | PAW | MTC HE - Hub Signaling | MTCH NE RHD PAW RF Passive Splitter Deployment POR20 | Chassis | 8-way splitter | 1 | 2020-07-06 | 2020-09-30 |  | Active | EP
MTCH NE RHD PAW RF Passive Splitter Deployment POR20 | NE | RHD | PAW | MTC HE - Hub Signaling | MTCH NE RHD PAW RF Passive Splitter Deployment POR20 | Chassis | 8-way splitter | 1 | 2020-08-06 | 2020-09-30 |  | Active | Log | Upd | SN-0021 | New | Approved | 2020-02-06 09:58 | This CR syncs the MTC HE - Hub Signaling 2020 budget and activity plan
MTCH NE RHD PAW RF Passive Splitter Deployment POR20 | NE | RHD | PAW | MTC HE - Hub Signaling | MTCH NE RHD PAW RF Passive Splitter Deployment POR20 | Chassis | 8-way splitter | 1 | 2020-05-06 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0307 | Schedule Change | Canceled | 2020-05-21 12:16 | Accelerating material receipt for Rhode Island sites into May as site walks and plans are now completed Funding previously in Q3 and Q4
MTCH NE RHD PAW RF Passive Splitter Deployment POR20 | NE | RHD | PAW | MTC HE - Hub Signaling | MTCH NE RHD PAW RF Passive Splitter Deployment POR20 | Chassis | 8-way splitter | 1 | 2020-07-06 | 2020-09-30 |  | Active | Log | Upd | SN-0607 | Schedule Change | Approved | 2020-05-28 11:35 | Innotrans receiver order backordered from ATX now to August Accelerating funding for new req for additional Synamedia licenses in the lab And requesting schedule shift forward one month for RI HFC receiver replacements
MTCH NE RHD PTH RF Passive Splitter Deployment POR20 | NE | RHD | PTH | MTC HE - Hub Signaling | MTCH NE RHD PTH RF Passive Splitter Deployment POR20 | Chassis | 8-way splitter | 1 | 2020-09-06 | 2020-10-31 |  | Active | EP
MTCH NE RHD PTH RF Passive Splitter Deployment POR20 | NE | RHD | PTH | MTC HE - Hub Signaling | MTCH NE RHD PTH RF Passive Splitter Deployment POR20 | Chassis | 8-way splitter | 1 | 2020-09-06 | 2020-10-31 |  | Active | Log | Upd | SN-0021 | New | Approved | 2020-02-06 09:58 | This CR syncs the MTC HE - Hub Signaling 2020 budget and activity plan
MTCH NE RHD PTH RF Passive Splitter Deployment POR20 | NE | RHD | PTH | MTC HE - Hub Signaling | MTCH NE RHD PTH RF Passive Splitter Deployment POR20 | Chassis | 8-way splitter | 1 | 2020-05-06 | 2020-05-15 | 2020-06-15 | Active | Log | Upd | SN-0307 | Schedule Change | Canceled | 2020-05-21 12:16 | Accelerating material receipt for Rhode Island sites into May as site walks and plans are now completed Funding previously in Q3 and Q4
MTCH NE RHD WWK HFC Receiver Deployment POR20 | NE | RHD | WWK | MTC HE - Hub Signaling | MTCH NE RHD WWK HFC Receiver Deployment POR20 | Chassis | Receiver (1 RU) |  |  |  |  | Deleted | EP
MTCH NE RHD WWK HFC Receiver Deployment POR20 | NE | RHD | WWK | MTC HE - Hub Signaling | MTCH NE RHD WWK HFC Receiver Deployment POR20 | Chassis | Receiver (1 RU) | 1 | 2020-10-06 | 2020-11-30 |  | Deleted | Log | Upd | SN-0021 | New | Approved | 2020-02-06 09:58 | This CR syncs the MTC HE - Hub Signaling 2020 budget and activity plan
MTCH NE RHD WWK HFC Receiver Deployment POR20 | NE | RHD | WWK | MTC HE - Hub Signaling | MTCH NE RHD WWK HFC Receiver Deployment POR20 | Chassis | Receiver (1 RU) | 1 | 2020-05-06 | 2020-05-15 | 2020-06-15 | Deleted | Log | Upd | SN-0307 | Schedule Change | Canceled | 2020-05-21 12:16 | Accelerating material receipt for Rhode Island sites into May as site walks and plans are now completed Funding previously in Q3 and Q4
MTCH NE RHD WWK HFC Receiver Deployment POR20 | NE | RHD | WWK | MTC HE - Hub Signaling | MTCH NE RHD WWK HFC Receiver Deployment POR20 | Chassis | Receiver (1 RU) |  |  |  |  | Deleted | Log | Del | SN-0607 | Schedule Change | Approved | 2020-05-28 11:35 | Innotrans receiver order backordered from ATX now to August Accelerating funding for new req for additional Synamedia licenses in the lab And requesting schedule shift forward one month for RI HFC receiver replacements
MTCH NE RHD WWK Innotrans Unit Deployment POR20 | NE | RHD | WWK | MTC HE - Hub Signaling | MTCH NE RHD WWK Innotrans Unit Deployment POR20 | Critical Facilities | MTC Hub Signaling | 4 | 2020-07-31 | 2020-09-30 | 2020-10-31 | Active | EP
MTCH NE RHD WWK Innotrans Unit Deployment POR20 | NE | RHD | WWK | MTC HE - Hub Signaling | MTCH NE RHD WWK Innotrans Unit Deployment POR20 | Critical Facilities | MTC Hub Signaling | 4 | 2020-05-15 | 2020-06-30 | 2020-07-30 | Active | Log | Upd | SN-0296 | Schedule Change | Approved | 2020-03-30 14:43 | Bell Get Well Construction and permitting will delay migrations from April Also updating incorrect POR dates Pushing funding in SE by 1 month No open orders against April plan Deferring HFC receiver funding to Q3 and 4 from CT to RI sites Accellerati
MTCH NE RHD WWK Innotrans Unit Deployment POR20 | NE | RHD | WWK | MTC HE - Hub Signaling | MTCH NE RHD WWK Innotrans Unit Deployment POR20 | Critical Facilities | MTC Hub Signaling | 4 | 2020-08-13 | 2020-09-30 | 2020-10-31 | Active | Log | Upd | SN-0607 | Schedule Change | Approved | 2020-05-28 11:35 | Innotrans receiver order backordered from ATX now to August Accelerating funding for new req for additional Synamedia licenses in the lab And requesting schedule shift forward one month for RI HFC receiver replacements
MTCH NE RHD WWK Innotrans Unit Deployment POR20 | NE | RHD | WWK | MTC HE - Hub Signaling | MTCH NE RHD WWK Innotrans Unit Deployment POR20 | Critical Facilities | MTC Hub Signaling | 4 | 2020-07-31 | 2020-09-30 | 2020-10-31 | Active | Log | Upd | SN-0852 | True up | Approved | 2020-08-20 18:04 | Missed receipt for Telestream orders now received in July Movement of labor funding from topside to field PPMs and 3PL to IHL Credit for WIC vDCM licenses pushing to October
MTCH NE RHD WWK Dish Upgrades Deployment POR20 | NE | RHD | WWK | MTC HE - Hub Signaling | MTCH NE RHD WWK Dish Upgrades Deployment POR20 | Labor | TVRO |  |  |  |  | Deleted | EP
MTCH NE RHD WWK Dish Upgrades Deployment POR20 | NE | RHD | WWK | MTC HE - Hub Signaling | MTCH NE RHD WWK Dish Upgrades Deployment POR20 | Labor | TVRO |  |  |  |  | Deleted | Log | Del | SN-0536 | COVID-19 Related | Approved | 2020-05-08 14:24 | POR updates related to the Covid 19 deferrals
MTCH NE RHD WEK NSG 3G 6G Replacement Deployment POR20 | NE | RHD | WWK | MTC HE - Hub Signaling | MTCH NE RHD WWK NSG 3G 6G Replacement Deployment POR20 | Chassis | NSG 40G | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | EP
MTCH NE RHD WWK MPEG4 vDCM Install Deployment POR20 | NE | RHD | WWK | MTC HE - Hub Signaling | MTCH NE RHD WWK MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 4 | 2020-11-15 | 2021-04-15 | 2021-07-15 | Active | EP
MTCH NE RHD WWK MPEG4 vDCM Install Deployment POR20 | NE | RHD | WWK | MTC HE - Hub Signaling | MTCH NE RHD WWK MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-11-06 | 2020-12-15 | 2021-01-15 | Active | Log | Upd | SN-0136 | Schedule Change | Approved | 2020-02-06 11:03 | Updating POR and funding schedule to match the deployment schedule for MPEG4 vDCM installs Pulling funding from topside PPM to self solve new quote for 8VSB installs in CEN region
MTCH NE RHD WWK MPEG4 vDCM Install Deployment POR20 | NE | RHD | WWK | MTC HE - Hub Signaling | MTCH NE RHD WWK MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-09-06 | 2021-04-15 | 2021-07-15 | Active | Log | Upd | SN-0227 | Schedule Change | Approved | 2020-03-30 14:43 | Schedule for vDCM installs is being reprioritized, for purposes of accelerating lower impact market(s) and to allow for CB CMI dependencies to be completed
MTCH NE RHD WWK MPEG4 vDCM Install Deployment POR20 | NE | RHD | WWK | MTC HE - Hub Signaling | MTCH NE RHD WWK MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-11-15 | 2021-04-15 | 2021-07-15 | Active | Log | Upd | SN-0693 | Schedule Change | Approved | 2020-06-30 11:13 | Updates to align with new lead times for equipment from WWT changed to 72 to 80 days
MTCH NE RHD WWK MPEG4 vDCM Install Deployment POR20 | NE | RHD | WWK | MTC HE - Hub Signaling | MTCH NE RHD WWK MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 4 | 2020-11-15 | 2021-04-15 | 2021-07-15 | Active | Log | Upd | SN-0950 | New | Approved | 2020-09-25 14:15 | We received a credit earlier this year for licenses that were invoiced twice against the CHD vDCM project That credit was processed in June but is just now hitting our project code This CR is to align the remaining funding needed to satiate that same orde
MTCH SE GAN GNS Satellite Receiver Deployment POR20 | SE | GAN | GNS | MTC HE - Hub Signaling | MTCH SE GAN GNS Satellite Receiver Deployment POR20 | Chassis | Receiver (1 RU) |  |  |  |  | Deleted | EP
MTCH SE GAN GNS Satellite Receiver Deployment POR20 | SE | GAN | GNS | MTC HE - Hub Signaling | MTCH SE GAN GNS Satellite Receiver Deployment POR20 | Chassis | Receiver (1 RU) |  |  |  |  | Deleted | Log | Del | SN-0536 | COVID-19 Related | Approved | 2020-05-08 14:24 | POR updates related to the Covid 19 deferrals
MTCH SE GLA ALG Uplink Combining Augment POR20 | SE | NOR | ALG | MTC HE - Hub Signaling | MTCH SE NOR ALG Uplink Combining Augment POR20 | Critical Facilities | MTC Hub Signaling |  |  |  |  | Deleted | EP
MTCH SE GLA ALG Uplink Combining Augment POR20 | SE | NOR | ALG | MTC HE - Hub Signaling | MTCH SE NOR ALG Uplink Combining Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-05-06 | 2020-06-15 | 2020-07-15 | Deleted | Log | Upd | SN-0456 | True up | Approved | 2020-04-17 16:27 | Material variance fueled largely due to unexpected charge to 2019 project code in NE and innacurate initial estimates for the MPEG4 vDCM projects Labor variances accumulated across field PPMs related to RPHY Test Rack projects and labor charging ahead o
MTCH SE GLA ALG Uplink Combining Augment POR20 | SE | NOR | ALG | MTC HE - Hub Signaling | MTCH SE NOR ALG Uplink Combining Augment POR20 | Critical Facilities | MTC Hub Signaling |  |  |  |  | Deleted | Log | Del | SN-0536 | COVID-19 Related | Approved | 2020-05-08 14:24 | POR updates related to the Covid 19 deferrals
MTCH SE GLA BTR Satellite Receiver Deployment POR20 | SE | BTR | BTR | MTC HE - Hub Signaling | MTCH SE BTR BTR Satellite Receiver Deployment POR20 | Chassis | Receiver (1 RU) |  |  |  |  | Deleted | EP
MTCH SE GLA BTR Satellite Receiver Deployment POR20 | SE | BTR | BTR | MTC HE - Hub Signaling | MTCH SE BTR BTR Satellite Receiver Deployment POR20 | Chassis | Receiver (1 RU) | 2 | 2020-06-06 | 2020-07-15 | 2020-08-15 | Deleted | Log | Upd | SN-0456 | True up | Approved | 2020-04-17 16:27 | Material variance fueled largely due to unexpected charge to 2019 project code in NE and innacurate initial estimates for the MPEG4 vDCM projects Labor variances accumulated across field PPMs related to RPHY Test Rack projects and labor charging ahead o
MTCH SE GLA BTR Satellite Receiver Deployment POR20 | SE | BTR | BTR | MTC HE - Hub Signaling | MTCH SE BTR BTR Satellite Receiver Deployment POR20 | Chassis | Receiver (1 RU) |  |  |  |  | Deleted | Log | Del | SN-0536 | COVID-19 Related | Approved | 2020-05-08 14:24 | POR updates related to the Covid 19 deferrals
MTCH SE GLA BTR MPEG4 vDCM Install Deployment POR20 | SE | BTR | BTR | MTC HE - Hub Signaling | MTCH SE BTR BTR MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config |  |  |  |  | Deleted | EP
MTCH SE GLA BTR MPEG4 vDCM Install Deployment POR20 | SE | BTR | BTR | MTC HE - Hub Signaling | MTCH SE BTR BTR MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-05-06 | 2020-06-15 | 2020-07-15 | Deleted | Log | Upd | SN-0136 | Schedule Change | Approved | 2020-02-06 11:03 | Updating POR and funding schedule to match the deployment schedule for MPEG4 vDCM installs Pulling funding from topside PPM to self solve new quote for 8VSB installs in CEN region
MTCH SE GLA BTR MPEG4 vDCM Install Deployment POR20 | SE | BTR | BTR | MTC HE - Hub Signaling | MTCH SE BTR BTR MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config |  |  |  |  | Deleted | Log | Del | SN-0227 | Schedule Change | Approved | 2020-03-30 14:43 | Schedule for vDCM installs is being reprioritized, for purposes of accelerating lower impact market(s) and to allow for CB CMI dependencies to be completed
MTCH SE GLA ELM Uplink Combining Augment POR20 | SE | NOR | ELM | MTC HE - Hub Signaling | MTCH SE NOR ELM Uplink Combining Augment POR20 | Critical Facilities | MTC Hub Signaling |  |  |  |  | Deleted | EP
MTCH SE GLA ELM Uplink Combining Augment POR20 | SE | NOR | ELM | MTC HE - Hub Signaling | MTCH SE NOR ELM Uplink Combining Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-05-06 | 2020-06-15 | 2020-07-15 | Deleted | Log | Upd | SN-0456 | True up | Approved | 2020-04-17 16:27 | Material variance fueled largely due to unexpected charge to 2019 project code in NE and innacurate initial estimates for the MPEG4 vDCM projects Labor variances accumulated across field PPMs related to RPHY Test Rack projects and labor charging ahead o
MTCH SE GLA ELM Uplink Combining Augment POR20 | SE | NOR | ELM | MTC HE - Hub Signaling | MTCH SE NOR ELM Uplink Combining Augment POR20 | Critical Facilities | MTC Hub Signaling |  |  |  |  | Deleted | Log | Del | SN-0536 | COVID-19 Related | Approved | 2020-05-08 14:24 | POR updates related to the Covid 19 deferrals
MTCH SE GLA LFY Uplink Combining Augment POR20 | SE | LFY | LFY | MTC HE - Hub Signaling | MTCH SE LFY LFY Uplink Combining Augment POR20 | Critical Facilities | MTC Hub Signaling |  |  |  |  | Deleted | EP
MTCH SE GLA LFY Uplink Combining Augment POR20 | SE | LFY | LFY | MTC HE - Hub Signaling | MTCH SE LFY LFY Uplink Combining Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-05-06 | 2020-06-15 | 2020-07-15 | Deleted | Log | Upd | SN-0456 | True up | Approved | 2020-04-17 16:27 | Material variance fueled largely due to unexpected charge to 2019 project code in NE and innacurate initial estimates for the MPEG4 vDCM projects Labor variances accumulated across field PPMs related to RPHY Test Rack projects and labor charging ahead o
MTCH SE GLA LFY Uplink Combining Augment POR20 | SE | LFY | LFY | MTC HE - Hub Signaling | MTCH SE LFY LFY Uplink Combining Augment POR20 | Critical Facilities | MTC Hub Signaling |  |  |  |  | Deleted | Log | Del | SN-0536 | COVID-19 Related | Approved | 2020-05-08 14:24 | POR updates related to the Covid 19 deferrals
MTCH SE GLA LFY MPEG4 vDCM Install Deployment POR20 | SE | LFY | LFY | MTC HE - Hub Signaling | MTCH SE LFY LFY MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config |  |  |  |  | Deleted | EP
MTCH SE GLA LFY MPEG4 vDCM Install Deployment POR20 | SE | LFY | LFY | MTC HE - Hub Signaling | MTCH SE LFY LFY MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-05-06 | 2020-06-15 | 2020-07-15 | Deleted | Log | Upd | SN-0136 | Schedule Change | Approved | 2020-02-06 11:03 | Updating POR and funding schedule to match the deployment schedule for MPEG4 vDCM installs Pulling funding from topside PPM to self solve new quote for 8VSB installs in CEN region
MTCH SE GLA LFY MPEG4 vDCM Install Deployment POR20 | SE | LFY | LFY | MTC HE - Hub Signaling | MTCH SE LFY LFY MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config |  |  |  |  | Deleted | Log | Del | SN-0227 | Schedule Change | Approved | 2020-03-30 14:43 | Schedule for vDCM installs is being reprioritized, for purposes of accelerating lower impact market(s) and to allow for CB CMI dependencies to be completed
MTCH SE NOR ELM MPEG4 vDCM Install Deployment POR20 | SE | NOR | ELM | MTC HE - Hub Signaling | MTCH SE NOR ELM MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config |  |  |  |  | Deleted | EP
MTCH SE NOR ELM MPEG4 vDCM Install Deployment POR20 | SE | NOR | ELM | MTC HE - Hub Signaling | MTCH SE NOR ELM MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-09-06 | 2020-10-15 | 2021-01-15 | Deleted | Log | New | SN-0136 | Schedule Change | Approved | 2020-02-06 11:03 | Updating POR and funding schedule to match the deployment schedule for MPEG4 vDCM installs Pulling funding from topside PPM to self solve new quote for 8VSB installs in CEN region
MTCH SE NOR ELM MPEG4 vDCM Install Deployment POR20 | SE | NOR | ELM | MTC HE - Hub Signaling | MTCH SE NOR ELM MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config |  |  |  |  | Deleted | Log | Del | SN-0227 | Schedule Change | Approved | 2020-03-30 14:43 | Schedule for vDCM installs is being reprioritized, for purposes of accelerating lower impact market(s) and to allow for CB CMI dependencies to be completed
MTCH SE MGA MCN MPEG4 vDCM Install Deployment POR20 | SE | MGA | MCN | MTC HE - Hub Signaling | MTCH SE MGA MCN MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-03-31 | 2020-09-15 | 2021-01-15 | Active | EP
MTCH SE MGA MCN MPEG4 vDCM Install Deployment POR20 | SE | MGA | MCN | MTC HE - Hub Signaling | MTCH SE MGA MCN MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-11-06 | 2020-12-15 | 2021-01-15 | Active | Log | New | SN-0136 | Schedule Change | Approved | 2020-02-06 11:03 | Updating POR and funding schedule to match the deployment schedule for MPEG4 vDCM installs Pulling funding from topside PPM to self solve new quote for 8VSB installs in CEN region
MTCH SE MGA MCN MPEG4 vDCM Install Deployment POR20 | SE | MGA | MCN | MTC HE - Hub Signaling | MTCH SE MGA MCN MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-03-31 | 2020-09-15 | 2021-01-15 | Active | Log | Upd | SN-0227 | Schedule Change | Approved | 2020-03-30 14:43 | Schedule for vDCM installs is being reprioritized, for purposes of accelerating lower impact market(s) and to allow for CB CMI dependencies to be completed
MTCH CA ORG RSM Rack Consolidation Augment POR19 | CA | ORG | RSM | MTC HE - Hub Signaling | MTCH CA ORG RSM Rack Consolidation Augment POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-02-15 | 2020-03-31 | Active | EP
MTCH CA ORG RSM Rack Consolidation Augment POR19 | CA | ORG | RSM | MTC HE - Hub Signaling | MTCH CA ORG RSM Rack Consolidation Augment POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-02-15 | 2020-03-31 | Active | Log | Undel | SN-0188 | Schedule Change | Approved | 2020-01-21 09:42 | Adding 2019 projects to 2020 POR and aligning funding for material receipt and completion
MTCH CA SAN CHU Grow Fiber Bay Replace Augment POR19 | CA | SAN | CHU | MTC HE - Hub Signaling | MTCH CA SAN CHU Grow Fiber Bay Replace Augment POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-02-15 | 2020-03-31 | Active | EP
MTCH CA SAN CHU Grow Fiber Bay Replace Augment POR19 | CA | SAN | CHU | MTC HE - Hub Signaling | MTCH CA SAN CHU Grow Fiber Bay Replace Augment POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-02-15 | 2020-03-31 | Active | Log | Undel | SN-0188 | Schedule Change | Approved | 2020-01-21 09:42 | Adding 2019 projects to 2020 POR and aligning funding for material receipt and completion
MTCH CA SAN ELC Grow Fiber Management Augment POR19 | CA | SAN | ELC | MTC HE - Hub Signaling | MTCH CA SAN ELC Grow Fiber Management Augment POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-02-15 | 2020-03-31 | Active | EP
MTCH CA SAN ELC Grow Fiber Management Augment POR19 | CA | SAN | ELC | MTC HE - Hub Signaling | MTCH CA SAN ELC Grow Fiber Management Augment POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-02-15 | 2020-03-31 | Active | Log | Undel | SN-0188 | Schedule Change | Approved | 2020-01-21 09:42 | Adding 2019 projects to 2020 POR and aligning funding for material receipt and completion
MTCH CA SAN ESC Grow Fiber Bay Replace Augment POR19 | CA | SAN | ESC | MTC HE - Hub Signaling | MTCH CA SAN ESC Grow Fiber Bay Replace Augment POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-02-15 | 2020-03-31 | Active | EP
MTCH CA SAN ESC Grow Fiber Bay Replace Augment POR19 | CA | SAN | ESC | MTC HE - Hub Signaling | MTCH CA SAN ESC Grow Fiber Bay Replace Augment POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-02-15 | 2020-03-31 | Active | Log | Undel | SN-0188 | Schedule Change | Approved | 2020-01-21 09:42 | Adding 2019 projects to 2020 POR and aligning funding for material receipt and completion
MTCH CA SAN FED Grow Fiber Management Augment POR19 | CA | SAN | FED | MTC HE - Hub Signaling | MTCH CA SAN FED Grow Fiber Management Augment POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-02-15 | 2020-03-31 | Active | EP
MTCH CA SAN FED Grow Fiber Management Augment POR19 | CA | SAN | FED | MTC HE - Hub Signaling | MTCH CA SAN FED Grow Fiber Management Augment POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-02-15 | 2020-03-31 | Active | Log | Undel | SN-0188 | Schedule Change | Approved | 2020-01-21 09:42 | Adding 2019 projects to 2020 POR and aligning funding for material receipt and completion
MTCH CA SAN VST Grow Fiber Bay Replace Augment POR19 | CA | SAN | VST | MTC HE - Hub Signaling | MTCH CA SAN VST Grow Fiber Bay Replace Augment POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-02-15 | 2020-03-31 | Active | EP
MTCH CA SAN VST Grow Fiber Bay Replace Augment POR19 | CA | SAN | VST | MTC HE - Hub Signaling | MTCH CA SAN VST Grow Fiber Bay Replace Augment POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-02-15 | 2020-03-31 | Active | Log | Undel | SN-0188 | Schedule Change | Approved | 2020-01-21 09:42 | Adding 2019 projects to 2020 POR and aligning funding for material receipt and completion
MTCH CE OKC OKC Fiber Management Augment POR19 | CE | OKC | OKC | MTC HE - Hub Signaling | MTCH CE OKC OKC Fiber Management Augment POR19 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-03-15 | Active | EP
MTCH CE OKC OKC Fiber Management Augment POR19 | CE | OKC | OKC | MTC HE - Hub Signaling | MTCH CE OKC OKC Fiber Management Augment POR19 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-15 | 2020-02-15 | 2020-03-15 | Active | Log | Undel | SN-0188 | Schedule Change | Approved | 2020-01-21 09:42 | Adding 2019 projects to 2020 POR and aligning funding for material receipt and completion
MTCH NE CLE CLV Replace Tektronix Upgrade Decom POR19 | NE | CLE | CLV | MTC HE - Hub Signaling | MTCH NE CLE CLV Replace Tektronix Upgrade Decom POR19 | Chassis | Tektronix Sentry | 1 | 2020-11-15 | 2020-12-15 | 2021-01-15 | Active | EP
MTCH NE CLE CLV Replace Tektronix Upgrade Decom POR19 | NE | CLE | CLV | MTC HE - Hub Signaling | MTCH NE CLE CLV Replace Tektronix Upgrade Decom POR19 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-24 | 2020-02-15 | 2020-03-15 | Active | Log | Undel | SN-0188 | Schedule Change | Approved | 2020-01-21 09:42 | Adding 2019 projects to 2020 POR and aligning funding for material receipt and completion
MTCH NE CLE CLV Replace Tektronix Upgrade Decom POR19 | NE | CLE | CLV | MTC HE - Hub Signaling | MTCH NE CLE CLV Replace Tektronix Upgrade Decom POR19 | Chassis | Tektronix Sentry | 1 | 2020-11-15 | 2020-12-15 | 2021-01-15 | Active | Log | Upd | SN-0575 | True up | Approved | 2020-05-14 17:56 | April True Up and Q2F April material variances due to vDCM material delays from WWT now received
MTCH SE GLA MCY Fiber Management Augment POR19 | SE | NOR | MCY | MTC HE - Hub Signaling | MTCH SE GLA MCY Fiber Management Augment POR19 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-30 | 2020-02-15 | 2020-03-31 | Active | EP
MTCH SE GLA MCY Fiber Management Augment POR19 | SE | NOR | MCY | MTC HE - Hub Signaling | MTCH SE GLA MCY Fiber Management Augment POR19 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-30 | 2020-02-15 | 2020-03-31 | Active | Log | Undel | SN-0188 | Schedule Change | Approved | 2020-01-21 09:42 | Adding 2019 projects to 2020 POR and aligning funding for material receipt and completion
MTCH SW LAS BLU Replace HDrx Decom POR19 | SW | LAS | BLU | MTC HE - Hub Signaling | MTCH SW LAS BLU Replace HDrx Decom POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-02-15 | 2020-03-15 | Active | EP
MTCH SW LAS BLU Replace HDrx Decom POR19 | SW | LAS | BLU | MTC HE - Hub Signaling | MTCH SW LAS BLU Replace HDrx Decom POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-02-15 | 2020-03-15 | Active | Log | Undel | SN-0188 | Schedule Change | Approved | 2020-01-21 09:42 | Adding 2019 projects to 2020 POR and aligning funding for material receipt and completion
MTCH SW LAS HEN Replace HDrx Decom POR19 | SW | LAS | HEN | MTC HE - Hub Signaling | MTCH SW LAS HEN Replace HDrx Decom POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-02-15 | 2020-03-15 | Active | EP
MTCH SW LAS HEN Replace HDrx Decom POR19 | SW | LAS | HEN | MTC HE - Hub Signaling | MTCH SW LAS HEN Replace HDrx Decom POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-02-15 | 2020-03-15 | Active | Log | Undel | SN-0188 | Schedule Change | Approved | 2020-01-21 09:42 | Adding 2019 projects to 2020 POR and aligning funding for material receipt and completion
MTCH SW LAS TEN Replace HDrx Decom POR19 | SW | LAS | TEN | MTC HE - Hub Signaling | MTCH SW LAS TEN Replace HDrx Decom POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-02-15 | 2020-03-15 | Active | EP
MTCH SW LAS TEN Replace HDrx Decom POR19 | SW | LAS | TEN | MTC HE - Hub Signaling | MTCH SW LAS TEN Replace HDrx Decom POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-02-15 | 2020-03-15 | Active | Log | Undel | SN-0188 | Schedule Change | Approved | 2020-01-21 09:42 | Adding 2019 projects to 2020 POR and aligning funding for material receipt and completion
MTCH VA NVA DRA Replace RF Rebuild Decom POR19 | VA | NVA | DRA | MTC HE - Hub Signaling | MTCH VA NVA DRA Replace RF Rebuild Decom POR19 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-24 | 2020-02-15 | 2020-03-15 | Active | EP
MTCH VA NVA DRA Replace RF Rebuild Decom POR19 | VA | NVA | DRA | MTC HE - Hub Signaling | MTCH VA NVA DRA Replace RF Rebuild Decom POR19 | Critical Facilities | MTC Hub Signaling | 1 | 2020-01-24 | 2020-02-15 | 2020-03-15 | Active | Log | Undel | SN-0188 | Schedule Change | Approved | 2020-01-21 09:42 | Adding 2019 projects to 2020 POR and aligning funding for material receipt and completion
MTCH VA NVA MFD Replace Tektronix Upgrade Decom POR19 | VA | NVA | MFD | MTC HE - Hub Signaling | MTCH VA NVA MFD Replace Tektronix Upgrade Decom POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-02-15 | 2020-03-31 | Active | EP
MTCH VA NVA MFD Replace Tektronix Upgrade Decom POR19 | VA | NVA | MFD | MTC HE - Hub Signaling | MTCH VA NVA MFD Replace Tektronix Upgrade Decom POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-02-15 | 2020-03-31 | Active | Log | Undel | SN-0188 | Schedule Change | Approved | 2020-01-21 09:42 | Adding 2019 projects to 2020 POR and aligning funding for material receipt and completion
MTCH CE OMA BLV RPHY Test Rack Deployment POR20 | CE | OMA | BLV | MTC HE - Hub Signaling | MTCH CE OMA BLV RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-07-06 | 2020-09-01 |  | Active | EP
MTCH CE OMA BLV RPHY Test Rack Deployment POR20 | CE | OMA | BLV | MTC HE - Hub Signaling | MTCH CE OMA BLV RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-07-06 | 2020-09-01 |  | Active | Log | Undel | SN-0219 | Scope Change | Approved | 2020-04-03 14:06 | Adding the Test Racks for RPHY to the HEHS POR
MTCH VA HRD CHS RPHY Test Rack Deployment POR20 | VA | HRD | CHS | MTC HE - Hub Signaling | MTCH VA HRD CHS RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-02-06 | 2020-05-01 |  | Active | EP
MTCH VA HRD CHS RPHY Test Rack Deployment POR20 | VA | HRD | CHS | MTC HE - Hub Signaling | MTCH VA HRD CHS RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-02-06 | 2020-05-01 |  | Active | Log | Undel | SN-0219 | Scope Change | Approved | 2020-04-03 14:06 | Adding the Test Racks for RPHY to the HEHS POR
MTCH NE CLE CLV RPHY Test Rack Deployment POR20 | NE | CLE | CLV | MTC HE - Hub Signaling | MTCH NE CLE CLV RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-04-06 | 2020-06-01 |  | Active | EP
MTCH NE CLE CLV RPHY Test Rack Deployment POR20 | NE | CLE | CLV | MTC HE - Hub Signaling | MTCH NE CLE CLV RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-04-06 | 2020-06-01 |  | Active | Log | Undel | SN-0219 | Scope Change | Approved | 2020-04-03 14:06 | Adding the Test Racks for RPHY to the HEHS POR
MTCH SE NOR ELM RPHY Test Rack Deployment POR20 | SE | NOR | ELM | MTC HE - Hub Signaling | MTCH SE NOR ELM RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-05-06 | 2020-07-01 |  | Deleted | EP
MTCH CE NWA FTS RPHY Test Rack Deployment POR20 | CE | NWA | FTS | MTC HE - Hub Signaling | MTCH CE NWA FTS RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-09-06 | 2020-11-01 |  | Active | EP
MTCH CE NWA FTS RPHY Test Rack Deployment POR20 | CE | NWA | FTS | MTC HE - Hub Signaling | MTCH CE NWA FTS RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-09-06 | 2020-11-01 |  | Active | Log | Undel | SN-0219 | Scope Change | Approved | 2020-04-03 14:06 | Adding the Test Racks for RPHY to the HEHS POR
MTCH CE TUL GAR RPHY Test Rack Deployment POR20 | CE | TUL | GAR | MTC HE - Hub Signaling | MTCH CE TUL GAR RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-09-06 | 2020-11-01 |  | Active | EP
MTCH CE TUL GAR RPHY Test Rack Deployment POR20 | CE | TUL | GAR | MTC HE - Hub Signaling | MTCH CE TUL GAR RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-09-06 | 2020-11-01 |  | Active | Log | Undel | SN-0219 | Scope Change | Approved | 2020-04-03 14:06 | Adding the Test Racks for RPHY to the HEHS POR
MTCH SE NOR KNN RPHY Test Rack Deployment POR20 | SE | NOR | KNN | MTC HE - Hub Signaling | MTCH SE NOR KNN RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-06-06 | 2020-08-01 |  | Deleted | EP
MTCH SE NOR LPL RPHY Test Rack Deployment POR20 | SE | NOR | LPL | MTC HE - Hub Signaling | MTCH SE NOR LPL RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-09-06 | 2020-11-01 |  | Deleted | EP
MTCH VA HRD LTF RPHY Test Rack Deployment POR20 | VA | HRD | LTF | MTC HE - Hub Signaling | MTCH VA HRD LTF RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-04-06 | 2020-06-01 |  | Active | EP
MTCH VA HRD LTF RPHY Test Rack Deployment POR20 | VA | HRD | LTF | MTC HE - Hub Signaling | MTCH VA HRD LTF RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-04-06 | 2020-06-01 |  | Active | Log | Undel | SN-0219 | Scope Change | Approved | 2020-04-03 14:06 | Adding the Test Racks for RPHY to the HEHS POR
MTCH CE OKC MWC RPHY Test Rack Deployment POR20 | CE | OKC | MWC | MTC HE - Hub Signaling | MTCH CE OKC MWC RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-08-06 | 2020-10-01 |  | Active | EP
MTCH CE OKC MWC RPHY Test Rack Deployment POR20 | CE | OKC | MWC | MTC HE - Hub Signaling | MTCH CE OKC MWC RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-08-06 | 2020-10-01 |  | Active | Log | Undel | SN-0219 | Scope Change | Approved | 2020-04-03 14:06 | Adding the Test Racks for RPHY to the HEHS POR
MTCH CE OKC NEH RPHY Test Rack Deployment POR20 | CE | OKC | NEH | MTC HE - Hub Signaling | MTCH CE OKC NEH RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-09-06 | 2020-11-01 |  | Active | EP
MTCH CE OKC NEH RPHY Test Rack Deployment POR20 | CE | OKC | NEH | MTC HE - Hub Signaling | MTCH CE OKC NEH RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-09-06 | 2020-11-01 |  | Active | Log | Undel | SN-0219 | Scope Change | Approved | 2020-04-03 14:06 | Adding the Test Racks for RPHY to the HEHS POR
MTCH VA HRD NRF RPHY Test Rack Deployment POR20 | VA | HRD | NRF | MTC HE - Hub Signaling | MTCH VA HRD NRF RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-01-06 | 2020-04-01 |  | Active | EP
MTCH VA HRD NRF RPHY Test Rack Deployment POR20 | VA | HRD | NRF | MTC HE - Hub Signaling | MTCH VA HRD NRF RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-01-06 | 2020-04-01 |  | Active | Log | Undel | SN-0219 | Scope Change | Approved | 2020-04-03 14:06 | Adding the Test Racks for RPHY to the HEHS POR
MTCH VA HRD OCN RPHY Test Rack Deployment POR20 | VA | HRD | OCN | MTC HE - Hub Signaling | MTCH VA HRD OCN RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-03-06 | 2020-05-01 |  | Active | EP
MTCH VA HRD OCN RPHY Test Rack Deployment POR20 | VA | HRD | OCN | MTC HE - Hub Signaling | MTCH VA HRD OCN RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-03-06 | 2020-05-01 |  | Active | Log | Undel | SN-0219 | Scope Change | Approved | 2020-04-03 14:06 | Adding the Test Racks for RPHY to the HEHS POR
MTCH CE OMA ONA RPHY Test Rack Deployment POR20 | CE | OMA | ONA | MTC HE - Hub Signaling | MTCH CE OMA ONA RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-09-06 | 2020-11-01 |  | Active | EP
MTCH CE OMA ONA RPHY Test Rack Deployment POR20 | CE | OMA | ONA | MTC HE - Hub Signaling | MTCH CE OMA ONA RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-09-06 | 2020-11-01 |  | Active | Log | Undel | SN-0219 | Scope Change | Approved | 2020-04-03 14:06 | Adding the Test Racks for RPHY to the HEHS POR
MTCH SW LAS OSB RPHY Test Rack Deployment POR20 | SW | LAS | OSB | MTC HE - Hub Signaling | MTCH SW LAS OSB RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-04-06 | 2020-06-01 |  | Active | EP
MTCH SW LAS OSB RPHY Test Rack Deployment POR20 | SW | LAS | OSB | MTC HE - Hub Signaling | MTCH SW LAS OSB RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-04-06 | 2020-06-01 |  | Active | Log | Undel | SN-0219 | Scope Change | Approved | 2020-04-03 14:06 | Adding the Test Racks for RPHY to the HEHS POR
MTCH VA HRD PRA RPHY Test Rack Deployment POR20 | VA | HRD | PRA | MTC HE - Hub Signaling | MTCH VA HRD PRA RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-02-06 | 2020-05-01 |  | Active | EP
MTCH VA HRD PRA RPHY Test Rack Deployment POR20 | VA | HRD | PRA | MTC HE - Hub Signaling | MTCH VA HRD PRA RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-02-06 | 2020-05-01 |  | Active | Log | Undel | SN-0219 | Scope Change | Approved | 2020-04-03 14:06 | Adding the Test Racks for RPHY to the HEHS POR
MTCH VA HRD PTM RPHY Test Rack Deployment POR20 | VA | HRD | PTM | MTC HE - Hub Signaling | MTCH VA HRD PTM RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-02-06 | 2020-05-01 |  | Active | EP
MTCH VA HRD PTM RPHY Test Rack Deployment POR20 | VA | HRD | PTM | MTC HE - Hub Signaling | MTCH VA HRD PTM RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-02-06 | 2020-05-01 |  | Active | Log | Undel | SN-0219 | Scope Change | Approved | 2020-04-03 14:06 | Adding the Test Racks for RPHY to the HEHS POR
MTCH VA ROA RON RPHY Test Rack Deployment POR20 | VA | ROA | RON | MTC HE - Hub Signaling | MTCH VA ROA RON RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-03-06 | 2020-05-01 |  | Active | EP
MTCH VA ROA RON RPHY Test Rack Deployment POR20 | VA | ROA | RON | MTC HE - Hub Signaling | MTCH VA ROA RON RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-03-06 | 2020-05-01 |  | Active | Log | Undel | SN-0219 | Scope Change | Approved | 2020-04-03 14:06 | Adding the Test Racks for RPHY to the HEHS POR
MTCH CA SAB SAB RPHY Test Rack Deployment POR20 | CA | SAB | SAB | MTC HE - Hub Signaling | MTCH CA SAB SAB RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-04-06 | 2020-06-01 |  | Active | EP
MTCH CA SAB SAB RPHY Test Rack Deployment POR20 | CA | SAB | SAB | MTC HE - Hub Signaling | MTCH CA SAB SAB RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-04-06 | 2020-06-01 |  | Active | Log | Undel | SN-0219 | Scope Change | Approved | 2020-04-03 14:06 | Adding the Test Racks for RPHY to the HEHS POR
MTCH CE OKC SRH RPHY Test Rack Deployment POR20 | CE | OKC | SRH | MTC HE - Hub Signaling | MTCH CE OKC SRH RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-09-06 | 2020-11-01 |  | Deleted | EP
MTCH CE OMA WES RPHY Test Rack Deployment POR20 | CE | OMA | WES | MTC HE - Hub Signaling | MTCH CE OMA WES RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-08-06 | 2020-10-01 |  | Active | EP
MTCH CE OMA WES RPHY Test Rack Deployment POR20 | CE | OMA | WES | MTC HE - Hub Signaling | MTCH CE OMA WES RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-08-06 | 2020-10-01 |  | Active | Log | Undel | SN-0219 | Scope Change | Approved | 2020-04-03 14:06 | Adding the Test Racks for RPHY to the HEHS POR
MTCH CE KAN WIC RPHY Test Rack Deployment POR20 | CE | KAN | WIC | MTC HE - Hub Signaling | MTCH CE KAN WIC RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-09-06 | 2020-11-01 |  | Active | EP
MTCH CE KAN WIC RPHY Test Rack Deployment POR20 | CE | KAN | WIC | MTC HE - Hub Signaling | MTCH CE KAN WIC RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-09-06 | 2020-11-01 |  | Active | Log | Undel | SN-0219 | Scope Change | Approved | 2020-04-03 14:06 | Adding the Test Racks for RPHY to the HEHS POR
MTCH SE MGA WRB RPHY Test Rack Deployment POR20 | SE | MGA | WRB | MTC HE - Hub Signaling | MTCH SE MGA WRB RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-06-06 | 2020-08-01 |  | Active | EP
MTCH SE MGA WRB RPHY Test Rack Deployment POR20 | SE | MGA | WRB | MTC HE - Hub Signaling | MTCH SE MGA WRB RPHY Test Rack Deployment POR20 | Standard | RPHY | 1 | 2020-06-06 | 2020-08-01 |  | Active | Log | Undel | SN-0219 | Scope Change | Approved | 2020-04-03 14:06 | Adding the Test Racks for RPHY to the HEHS POR
MTCH CE OKC OKC 8VSB Replacement Deployment POR20 | CE | OKC | OKC | MTC HE - Hub Signaling | MTCH CE OKC OKC 8VSB Replacement Deployment POR20 | Chassis | Inca 4110 (2 RU) | 1 | 2020-02-06 | 2020-04-15 | 2020-05-15 | Active | EP
MTCH CE OKC OKC 8VSB Replacement Deployment POR20 | CE | OKC | OKC | MTC HE - Hub Signaling | MTCH CE OKC OKC 8VSB Replacement Deployment POR20 | Chassis | Inca 4110 (2 RU) | 1 | 2020-02-06 | 2020-04-15 | 2020-05-15 | Active | Log | New | SN-0242 | Schedule Change | Approved | 2020-02-24 12:37 | During audit of 2020 POR, it was noticed that this EPS project was missing for the 8VSB replacement work in CEN Budget available and orders are in flight
MTCH CE NWA NWA PEG Transport Deployment POR20 | CE | NWA | NWA | MTC HE - Hub Signaling | MTCH CE NWA NWA PEG Transport Deployment POR20 | Chassis | Drake encoder (1 RU) | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | EP
MTCH CE NWA NWA PEG Transport Deployment POR20 | CE | NWA | NWA | MTC HE - Hub Signaling | MTCH CE NWA NWA PEG Transport Deployment POR20 | Chassis | Drake encoder (1 RU) | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | Log | New | SN-0292 | Scope Change | Approved | 2020-02-24 12:39 | Adding facilities to POR No financial impact, can self solve under current project funding
MTCH CE OKC OKC PEG Transport Deployment POR20 | CE | OKC | OKC | MTC HE - Hub Signaling | MTCH CE OKC OKC PEG Transport Deployment POR20 | Chassis | Drake encoder (1 RU) | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | EP
MTCH CE OKC OKC PEG Transport Deployment POR20 | CE | OKC | OKC | MTC HE - Hub Signaling | MTCH CE OKC OKC PEG Transport Deployment POR20 | Chassis | Drake encoder (1 RU) | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | Log | New | SN-0292 | Scope Change | Approved | 2020-02-24 12:39 | Adding facilities to POR No financial impact, can self solve under current project funding
MTCH CE TUL TUL PEG Transport Deployment POR20 | CE | TUL | TUL | MTC HE - Hub Signaling | MTCH CE TUL TUL PEG Transport Deployment POR20 | Chassis | Drake encoder (1 RU) | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | EP
MTCH CE TUL TUL PEG Transport Deployment POR20 | CE | TUL | TUL | MTC HE - Hub Signaling | MTCH CE TUL TUL PEG Transport Deployment POR20 | Chassis | Drake encoder (1 RU) | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | Log | New | SN-0292 | Scope Change | Approved | 2020-02-24 12:39 | Adding facilities to POR No financial impact, can self solve under current project funding
MTCH CE OMA OMM PEG Transport Deployment POR20 | CE | OMA | OMM | MTC HE - Hub Signaling | MTCH CE OMA OMM PEG Transport Deployment POR20 | Chassis | Drake encoder (1 RU) | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | EP
MTCH CE OMA OMM PEG Transport Deployment POR20 | CE | OMA | OMM | MTC HE - Hub Signaling | MTCH CE OMA OMM PEG Transport Deployment POR20 | Chassis | Drake encoder (1 RU) | 1 | 2020-04-06 | 2020-05-15 | 2020-06-15 | Active | Log | New | SN-0292 | Scope Change | Approved | 2020-02-24 12:39 | Adding facilities to POR No financial impact, can self solve under current project funding
MTCH SW ARZ BEL Fiber Management Augment POR19 | SW | ARZ | BEL | MTC HE - Hub Signaling | MTCH SW ARZ BEL Fiber Management Augment POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-11-30 | 2020-11-30 | Active | EP
MTCH SW ARZ BEL Fiber Management Augment POR19 | SW | ARZ | BEL | MTC HE - Hub Signaling | MTCH SW ARZ BEL Fiber Management Augment POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-06-15 | 2020-06-15 | Active | Log | New | SN-0287 | Scope Change | Approved | 2020-02-24 12:39 | Requesting funds for the Bell Get Well, given back from FRM in CR 286 Discussions with TPS determine that becasue no major assets are to be purchased, charges should continue against 2019 project and code
MTCH SW ARZ BEL Fiber Management Augment POR19 | SW | ARZ | BEL | MTC HE - Hub Signaling | MTCH SW ARZ BEL Fiber Management Augment POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-12-15 | 2020-12-15 | Active | Log | Upd | SN-0296 | Schedule Change | Approved | 2020-03-30 14:43 | Bell Get Well Construction and permitting will delay migrations from April Also updating incorrect POR dates Pushing funding in SE by 1 month No open orders against April plan Deferring HFC receiver funding to Q3 and 4 from CT to RI sites Accellerati
MTCH SW ARZ BEL Fiber Management Augment POR19 | SW | ARZ | BEL | MTC HE - Hub Signaling | MTCH SW ARZ BEL Fiber Management Augment POR19 | Critical Facilities | MTC Hub Signaling | 1 |  | 2020-11-30 | 2020-11-30 | Active | Log | Upd | SN-0938 | Schedule Change | Approved | 2020-09-25 14:20 | Aligning remaining plan for the Bell Get Well project to install only remaining gear and return excess funding of 15k
MTCH VA HRD LTF RPHY Test Rack Deployment POR20_1 | VA | HRD | LTF | MTC HE - Hub Signaling | MTCH VA HRD LTF RPHY Test Rack Deployment POR20 |  |  | 1 | 2020-03-06 | 2020-04-15 |  | Deleted | EP
MTCH VA HRD NRF RPHY Test Rack Deployment POR20_2 | VA | HRD | NRF | MTC HE - Hub Signaling | MTCH VA HRD NRF RPHY Test Rack Deployment POR20 |  |  | 1 | 2020-03-06 | 2020-05-15 |  | Deleted | EP
MTCH VA HRD OCN RPHY Test Rack Deployment POR20_3 | VA | HRD | OCN | MTC HE - Hub Signaling | MTCH VA HRD OCN RPHY Test Rack Deployment POR20 |  |  | 1 | 2020-03-06 | 2020-06-15 |  | Deleted | EP
MTCH TEST Test | NE | CON | SFD | MTC HE - Hub Signaling | MTCH NE CLE CLV Replace Tektronix Upgrade Decom POR19 | Critical Facilities | MTC Hub Signaling | 1 | 2020-04-06 | 2020-05-06 | 2020-06-06 | Deleted | EP
MTCH NE CON MAN MPEG4 vDCM Install Deployment POR20 | NE | CON | MAN | MTC HE - Hub Signaling | MTCH NE CON MAN MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config |  |  |  |  | Deleted | EP
MTCH NE CON MAN MPEG4 vDCM Install Deployment POR20 | NE | CON | MAN | MTC HE - Hub Signaling | MTCH NE CON MAN MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-10-06 | 2021-03-31 | 2021-05-31 | Deleted | Log | Undel | SN-0368 | Schedule Change | Approved | 2020-04-10 15:22 | POR Updates for solutions team corrections and vDCM site adds related to CR227 for EPS projects that were not created yet No financial impact
MTCH NE CON MAN MPEG4 vDCM Install Deployment POR20 | NE | CON | MAN | MTC HE - Hub Signaling | MTCH NE CON MAN MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config |  |  |  |  | Deleted | Log | Del | SN-0536 | COVID-19 Related | Approved | 2020-05-08 14:24 | POR updates related to the Covid 19 deferrals
MTCH SE GAN GNS MPEG4 vDCM Install Deployment POR20 | SE | GAN | GNS | MTC HE - Hub Signaling | MTCH SE GAN GNS MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config |  |  |  |  | Deleted | EP
MTCH SE GAN GNS MPEG4 vDCM Install Deployment POR20 | SE | GAN | GNS | MTC HE - Hub Signaling | MTCH SE GAN GNS MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-10-06 | 2021-03-31 | 2021-05-31 | Deleted | Log | Undel | SN-0368 | Schedule Change | Approved | 2020-04-10 15:22 | POR Updates for solutions team corrections and vDCM site adds related to CR227 for EPS projects that were not created yet No financial impact
MTCH SE GAN GNS MPEG4 vDCM Install Deployment POR20 | SE | GAN | GNS | MTC HE - Hub Signaling | MTCH SE GAN GNS MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config |  |  |  |  | Deleted | Log | Del | SN-0536 | COVID-19 Related | Approved | 2020-05-08 14:24 | POR updates related to the Covid 19 deferrals
MTCH SE GCT PNS MPEG4 vDCM Install Deployment POR20 | SE | GCT | PNS | MTC HE - Hub Signaling | MTCH SE GCT PNS MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-11-15 | 2021-02-28 | 2021-04-30 | Active | EP
MTCH SE GCT PNS MPEG4 vDCM Install Deployment POR20 | SE | GCT | PNS | MTC HE - Hub Signaling | MTCH SE GCT PNS MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-09-06 | 2021-02-28 | 2021-04-30 | Active | Log | Undel | SN-0368 | Schedule Change | Approved | 2020-04-10 15:22 | POR Updates for solutions team corrections and vDCM site adds related to CR227 for EPS projects that were not created yet No financial impact
MTCH SE GCT PNS MPEG4 vDCM Install Deployment POR20 | SE | GCT | PNS | MTC HE - Hub Signaling | MTCH SE GCT PNS MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-11-15 | 2021-02-28 | 2021-04-30 | Active | Log | Upd | SN-0693 | Schedule Change | Approved | 2020-06-30 11:13 | Updates to align with new lead times for equipment from WWT changed to 72 to 80 days
MTCH VA HRD VBC MPEG4 vDCM Install Deployment POR20 | VA | HRD | VBC | MTC HE - Hub Signaling | MTCH VA HRD VBC MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-11-15 | 2021-02-28 | 2021-04-30 | Active | EP
MTCH VA HRD VBC MPEG4 vDCM Install Deployment POR20 | VA | HRD | VBC | MTC HE - Hub Signaling | MTCH VA HRD VBC MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-08-06 | 2021-02-28 | 2021-04-30 | Active | Log | Undel | SN-0368 | Schedule Change | Approved | 2020-04-10 15:22 | POR Updates for solutions team corrections and vDCM site adds related to CR227 for EPS projects that were not created yet No financial impact
MTCH VA HRD VBC MPEG4 vDCM Install Deployment POR20 | VA | HRD | VBC | MTC HE - Hub Signaling | MTCH VA HRD VBC MPEG4 vDCM Install Deployment POR20 | Chassis | Cisco UCS Chassis and Config | 2 | 2020-11-15 | 2021-02-28 | 2021-04-30 | Active | Log | Upd | SN-0693 | Schedule Change | Approved | 2020-06-30 11:13 | Updates to align with new lead times for equipment from WWT changed to 72 to 80 days
MTCH CE OKC MOO Signal Rewire Augment POR20 | CE | OKC | MOO | MTC HE - Hub Signaling | MTCH CE OKC MOO Signal Rewire Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-05-06 | 2020-07-15 | 2020-08-15 | Active | EP
MTCH CE OKC MOO Signal Rewire Augment POR20 | CE | OKC | MOO | MTC HE - Hub Signaling | MTCH CE OKC MOO Signal Rewire Augment POR20 | Critical Facilities | MTC Hub Signaling | 1 | 2020-05-06 | 2020-07-15 | 2020-08-15 | Active | Log | Undel | SN-0368 | Schedule Change | Approved | 2020-04-10 15:22 | POR Updates for solutions team corrections and vDCM site adds related to CR227 for EPS projects that were not created yet No financial impact
MTCH CE KAN TOP 8VSB Replacement Deployment POR20 | CE | KAN | TOP | MTC HE - Hub Signaling | MTCH CE KAN TOP 8VSB Replacement Deployment POR20 | Chassis | Inca 4110 (2 RU) | 1 | 2020-04-15 | 2020-05-15 | 2020-06-15 | Active | EP
MTCH CE KAN TOP 8VSB Replacement Deployment POR20 | CE | KAN | TOP | MTC HE - Hub Signaling | MTCH CE KAN TOP 8VSB Replacement Deployment POR20 | Chassis | Inca 4110 (2 RU) | 1 | 2020-04-15 | 2020-05-15 | 2020-06-15 | Active | Log | New | SN-0456 | True up | Approved | 2020-04-17 16:27 | Material variance fueled largely due to unexpected charge to 2019 project code in NE and innacurate initial estimates for the MPEG4 vDCM projects Labor variances accumulated across field PPMs related to RPHY Test Rack projects and labor charging ahead o
MTCH CA ORG RSM Tektronix Upgrade Deployment POR20 | CA | ORG | RSM | MTC HE - Hub Signaling | MTCH CA ORG RSM MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | EP
MTCH CA ORG RSM Tektronix Upgrade Deployment POR20 | CA | ORG | RSM | MTC HE - Hub Signaling | MTCH CA ORG RSM MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-11-15 | 2020-12-15 | 2021-01-15 | Active | Log | New | SN-0575 | True up | Approved | 2020-05-14 17:56 | April True Up and Q2F April material variances due to vDCM material delays from WWT now received
MTCH CA ORG RSM Tektronix Upgrade Deployment POR20 | CA | ORG | RSM | MTC HE - Hub Signaling | MTCH CA ORG RSM MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | Log | Upd | SN-0692 | Schedule Change | Approved | 2020-06-30 11:13 | WATTs MOs now created and all material is on hand with SCM at warehouse in ARZ and expectation is for delivery of all material by EOM July with updates to labor to follow
MTCH CA SAB SAB Tektronix Upgrade Deployment POR20 | CA | SAB | SAB | MTC HE - Hub Signaling | MTCH CA SAB SAB MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | EP
MTCH CA SAB SAB Tektronix Upgrade Deployment POR20 | CA | SAB | SAB | MTC HE - Hub Signaling | MTCH CA SAB SAB MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-11-15 | 2020-12-15 | 2021-01-15 | Active | Log | New | SN-0575 | True up | Approved | 2020-05-14 17:56 | April True Up and Q2F April material variances due to vDCM material delays from WWT now received
MTCH CA SAB SAB Tektronix Upgrade Deployment POR20 | CA | SAB | SAB | MTC HE - Hub Signaling | MTCH CA SAB SAB MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | Log | Upd | SN-0692 | Schedule Change | Approved | 2020-06-30 11:13 | WATTs MOs now created and all material is on hand with SCM at warehouse in ARZ and expectation is for delivery of all material by EOM July with updates to labor to follow
MTCH CA SAN CHU Tektronix Upgrade Deployment POR20 | CA | SAN | CHU | MTC HE - Hub Signaling | MTCH CA SAN CHU MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | EP
MTCH CA SAN CHU Tektronix Upgrade Deployment POR20 | CA | SAN | CHU | MTC HE - Hub Signaling | MTCH CA SAN CHU MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-11-15 | 2020-12-15 | 2021-01-15 | Active | Log | New | SN-0575 | True up | Approved | 2020-05-14 17:56 | April True Up and Q2F April material variances due to vDCM material delays from WWT now received
MTCH CA SAN CHU Tektronix Upgrade Deployment POR20 | CA | SAN | CHU | MTC HE - Hub Signaling | MTCH CA SAN CHU MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | Log | Upd | SN-0692 | Schedule Change | Approved | 2020-06-30 11:13 | WATTs MOs now created and all material is on hand with SCM at warehouse in ARZ and expectation is for delivery of all material by EOM July with updates to labor to follow
MTCH CE OKC OKC Tektronix Upgrade Deployment POR20 | CE | OKC | OKC | MTC HE - Hub Signaling | MTCH CE OKC OKC MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 2 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | EP
MTCH CE OKC OKC Tektronix Upgrade Deployment POR20 | CE | OKC | OKC | MTC HE - Hub Signaling | MTCH CE OKC OKC MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 2 | 2020-06-15 | 2020-07-15 | 2020-08-15 | Active | Log | New | SN-0575 | True up | Approved | 2020-05-14 17:56 | April True Up and Q2F April material variances due to vDCM material delays from WWT now received
MTCH CE OKC OKC Tektronix Upgrade Deployment POR20 | CE | OKC | OKC | MTC HE - Hub Signaling | MTCH CE OKC OKC MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 2 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | Log | Upd | SN-0692 | Schedule Change | Approved | 2020-06-30 11:13 | WATTs MOs now created and all material is on hand with SCM at warehouse in ARZ and expectation is for delivery of all material by EOM July with updates to labor to follow
MTCH CE SUN SVI Tektronix Upgrade Deployment POR20 | CE | SUN | SVI | MTC HE - Hub Signaling | MTCH CE SUN SVI MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | EP
MTCH CE SUN SVI Tektronix Upgrade Deployment POR20 | CE | SUN | SVI | MTC HE - Hub Signaling | MTCH CE SUN SVI MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-06-15 | 2020-07-15 | 2020-08-15 | Active | Log | New | SN-0575 | True up | Approved | 2020-05-14 17:56 | April True Up and Q2F April material variances due to vDCM material delays from WWT now received
MTCH CE SUN SVI Tektronix Upgrade Deployment POR20 | CE | SUN | SVI | MTC HE - Hub Signaling | MTCH CE SUN SVI MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | Log | Upd | SN-0692 | Schedule Change | Approved | 2020-06-30 11:13 | WATTs MOs now created and all material is on hand with SCM at warehouse in ARZ and expectation is for delivery of all material by EOM July with updates to labor to follow
MTCH CE TUL TUL Tektronix Upgrade Deployment POR20 | CE | TUL | TUL | MTC HE - Hub Signaling | MTCH CE TUL TUL MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 2 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | EP
MTCH CE TUL TUL Tektronix Upgrade Deployment POR20 | CE | TUL | TUL | MTC HE - Hub Signaling | MTCH CE TUL TUL MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 2 | 2020-06-15 | 2020-07-15 | 2020-08-15 | Active | Log | New | SN-0575 | True up | Approved | 2020-05-14 17:56 | April True Up and Q2F April material variances due to vDCM material delays from WWT now received
MTCH CE TUL TUL Tektronix Upgrade Deployment POR20 | CE | TUL | TUL | MTC HE - Hub Signaling | MTCH CE TUL TUL MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 2 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | Log | Upd | SN-0692 | Schedule Change | Approved | 2020-06-30 11:13 | WATTs MOs now created and all material is on hand with SCM at warehouse in ARZ and expectation is for delivery of all material by EOM July with updates to labor to follow
MTCH NE CLE CLV Tektronix Upgrade Deployment POR20 | NE | CLE | CLV | MTC HE - Hub Signaling | MTCH NE CLE CLV MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | EP
MTCH NE CLE CLV Tektronix Upgrade Deployment POR20 | NE | CLE | CLV | MTC HE - Hub Signaling | MTCH NE CLE CLV MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-11-15 | 2020-12-15 | 2021-01-15 | Active | Log | New | SN-0575 | True up | Approved | 2020-05-14 17:56 | April True Up and Q2F April material variances due to vDCM material delays from WWT now received
MTCH NE CLE CLV Tektronix Upgrade Deployment POR20 | NE | CLE | CLV | MTC HE - Hub Signaling | MTCH NE CLE CLV MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | Log | Upd | SN-0692 | Schedule Change | Approved | 2020-06-30 11:13 | WATTs MOs now created and all material is on hand with SCM at warehouse in ARZ and expectation is for delivery of all material by EOM July with updates to labor to follow
MTCH NE CON MAN Tektronix Upgrade Deployment POR20 | NE | CON | MAN | MTC HE - Hub Signaling | MTCH NE CON MAN MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | EP
MTCH NE CON MAN Tektronix Upgrade Deployment POR20 | NE | CON | MAN | MTC HE - Hub Signaling | MTCH NE CON MAN MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-11-15 | 2020-12-15 | 2021-01-15 | Active | Log | New | SN-0575 | True up | Approved | 2020-05-14 17:56 | April True Up and Q2F April material variances due to vDCM material delays from WWT now received
MTCH NE CON MAN Tektronix Upgrade Deployment POR20 | NE | CON | MAN | MTC HE - Hub Signaling | MTCH NE CON MAN MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | Log | Upd | SN-0692 | Schedule Change | Approved | 2020-06-30 11:13 | WATTs MOs now created and all material is on hand with SCM at warehouse in ARZ and expectation is for delivery of all material by EOM July with updates to labor to follow
MTCH NE RHD WWK Tektronix Upgrade Deployment POR20 | NE | RHD | WWK | MTC HE - Hub Signaling | MTCH NE RHD WWK MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 2 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | EP
MTCH NE RHD WWK Tektronix Upgrade Deployment POR20 | NE | RHD | WWK | MTC HE - Hub Signaling | MTCH NE RHD WWK MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 2 | 2020-06-15 | 2020-07-15 | 2020-08-15 | Active | Log | New | SN-0575 | True up | Approved | 2020-05-14 17:56 | April True Up and Q2F April material variances due to vDCM material delays from WWT now received
MTCH NE RHD WWK Tektronix Upgrade Deployment POR20 | NE | RHD | WWK | MTC HE - Hub Signaling | MTCH NE RHD WWK MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 2 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | Log | Upd | SN-0692 | Schedule Change | Approved | 2020-06-30 11:13 | WATTs MOs now created and all material is on hand with SCM at warehouse in ARZ and expectation is for delivery of all material by EOM July with updates to labor to follow
MTCH SE BTR BTR Tektronix Upgrade Deployment POR20 | SE | BTR | BTR | MTC HE - Hub Signaling | MTCH SE BTR BTR MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Deleted | EP
MTCH SE GAN GNS Tektronix Upgrade Deployment POR20 | SE | GAN | GNS | MTC HE - Hub Signaling | MTCH SE GAN GNS MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-08-07 | 2020-08-30 | 2020-09-30 | Active | EP
MTCH SE GAN GNS Tektronix Upgrade Deployment POR20 | SE | GAN | GNS | MTC HE - Hub Signaling | MTCH SE GAN GNS MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-11-15 | 2020-12-15 | 2021-01-15 | Active | Log | New | SN-0575 | True up | Approved | 2020-05-14 17:56 | April True Up and Q2F April material variances due to vDCM material delays from WWT now received
MTCH SE GAN GNS Tektronix Upgrade Deployment POR20 | SE | GAN | GNS | MTC HE - Hub Signaling | MTCH SE GAN GNS MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | Log | Upd | SN-0692 | Schedule Change | Approved | 2020-06-30 11:13 | WATTs MOs now created and all material is on hand with SCM at warehouse in ARZ and expectation is for delivery of all material by EOM July with updates to labor to follow
MTCH SE GAN GNS Tektronix Upgrade Deployment POR20 | SE | GAN | GNS | MTC HE - Hub Signaling | MTCH SE GAN GNS MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-08-07 | 2020-08-30 | 2020-09-30 | Active | Log | Upd | SN-0800 | Schedule Change | Approved | 2020-07-31 14:24 | Distributing funding from topside to regional PPMs after having resolved support cost issue and pushing funding for material that will not be delivered or available to be picked until next week
MTCH SE GCT PNS Tektronix Upgrade Deployment POR20 | SE | GCT | PNS | MTC HE - Hub Signaling | MTCH SE GCT PNS MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | EP
MTCH SE GCT PNS Tektronix Upgrade Deployment POR20 | SE | GCT | PNS | MTC HE - Hub Signaling | MTCH SE GCT PNS MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-11-15 | 2020-12-15 | 2021-01-15 | Active | Log | New | SN-0575 | True up | Approved | 2020-05-14 17:56 | April True Up and Q2F April material variances due to vDCM material delays from WWT now received
MTCH SE GCT PNS Tektronix Upgrade Deployment POR20 | SE | GCT | PNS | MTC HE - Hub Signaling | MTCH SE GCT PNS MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | Log | Upd | SN-0692 | Schedule Change | Approved | 2020-06-30 11:13 | WATTs MOs now created and all material is on hand with SCM at warehouse in ARZ and expectation is for delivery of all material by EOM July with updates to labor to follow
MTCH SE LFY LFY Tektronix Upgrade Deployment POR20 | SE | LFY | LFY | MTC HE - Hub Signaling | MTCH SE LFY LFY MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | EP
MTCH SE LFY LFY Tektronix Upgrade Deployment POR20 | SE | LFY | LFY | MTC HE - Hub Signaling | MTCH SE LFY LFY MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-11-15 | 2020-12-15 | 2021-01-15 | Active | Log | New | SN-0575 | True up | Approved | 2020-05-14 17:56 | April True Up and Q2F April material variances due to vDCM material delays from WWT now received
MTCH SE LFY LFY Tektronix Upgrade Deployment POR20 | SE | LFY | LFY | MTC HE - Hub Signaling | MTCH SE LFY LFY MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | Log | Upd | SN-0692 | Schedule Change | Approved | 2020-06-30 11:13 | WATTs MOs now created and all material is on hand with SCM at warehouse in ARZ and expectation is for delivery of all material by EOM July with updates to labor to follow
MTCH SE MGA MCN Tektronix Upgrade Deployment POR20 | SE | MGA | MCN | MTC HE - Hub Signaling | MTCH SE MGA MCN MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 2 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | EP
MTCH SE MGA MCN Tektronix Upgrade Deployment POR20 | SE | MGA | MCN | MTC HE - Hub Signaling | MTCH SE MGA MCN MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 2 | 2020-06-15 | 2020-07-15 | 2020-08-15 | Active | Log | New | SN-0575 | True up | Approved | 2020-05-14 17:56 | April True Up and Q2F April material variances due to vDCM material delays from WWT now received
MTCH SE MGA MCN Tektronix Upgrade Deployment POR20 | SE | MGA | MCN | MTC HE - Hub Signaling | MTCH SE MGA MCN MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 2 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | Log | Upd | SN-0692 | Schedule Change | Approved | 2020-06-30 11:13 | WATTs MOs now created and all material is on hand with SCM at warehouse in ARZ and expectation is for delivery of all material by EOM July with updates to labor to follow
MTCH SE NAT AT2 Tektronix Upgrade Deployment POR20 | COR | NAT | AT2 | MTC HE - Hub Signaling | MTCH SE NAT AT2 MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | EP
MTCH SE NAT AT2 Tektronix Upgrade Deployment POR20 | COR | NAT | AT2 | MTC HE - Hub Signaling | MTCH SE NAT AT2 MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-11-15 | 2020-12-15 | 2021-01-15 | Active | Log | New | SN-0575 | True up | Approved | 2020-05-14 17:56 | April True Up and Q2F April material variances due to vDCM material delays from WWT now received
MTCH SE NAT AT2 Tektronix Upgrade Deployment POR20 | COR | NAT | AT2 | MTC HE - Hub Signaling | MTCH SE NAT AT2 MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | Log | Upd | SN-0692 | Schedule Change | Approved | 2020-06-30 11:13 | WATTs MOs now created and all material is on hand with SCM at warehouse in ARZ and expectation is for delivery of all material by EOM July with updates to labor to follow
MTCH SE NOR ELM Tektronix Upgrade Deployment POR20 | SE | NOR | ELM | MTC HE - Hub Signaling | MTCH SE NOR ELM MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-08-07 | 2020-08-30 | 2020-09-30 | Active | EP
MTCH SE NOR ELM Tektronix Upgrade Deployment POR20 | SE | NOR | ELM | MTC HE - Hub Signaling | MTCH SE NOR ELM MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-11-15 | 2020-12-15 | 2021-01-15 | Active | Log | New | SN-0575 | True up | Approved | 2020-05-14 17:56 | April True Up and Q2F April material variances due to vDCM material delays from WWT now received
MTCH SE NOR ELM Tektronix Upgrade Deployment POR20 | SE | NOR | ELM | MTC HE - Hub Signaling | MTCH SE NOR ELM MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | Log | Upd | SN-0692 | Schedule Change | Approved | 2020-06-30 11:13 | WATTs MOs now created and all material is on hand with SCM at warehouse in ARZ and expectation is for delivery of all material by EOM July with updates to labor to follow
MTCH SE NOR ELM Tektronix Upgrade Deployment POR20 | SE | NOR | ELM | MTC HE - Hub Signaling | MTCH SE NOR ELM MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-08-07 | 2020-08-30 | 2020-09-30 | Active | Log | Upd | SN-0800 | Schedule Change | Approved | 2020-07-31 14:24 | Distributing funding from topside to regional PPMs after having resolved support cost issue and pushing funding for material that will not be delivered or available to be picked until next week
MTCH VA HRD VBC Tektronix Upgrade Deployment POR20 | VA | HRD | VBC | MTC HE - Hub Signaling | MTCH VA HRD VBC MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | EP
MTCH VA HRD VBC Tektronix Upgrade Deployment POR20 | VA | HRD | VBC | MTC HE - Hub Signaling | MTCH VA HRD VBC MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-11-15 | 2020-12-15 | 2021-01-15 | Active | Log | New | SN-0575 | True up | Approved | 2020-05-14 17:56 | April True Up and Q2F April material variances due to vDCM material delays from WWT now received
MTCH VA HRD VBC Tektronix Upgrade Deployment POR20 | VA | HRD | VBC | MTC HE - Hub Signaling | MTCH VA HRD VBC MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | Log | Upd | SN-0692 | Schedule Change | Approved | 2020-06-30 11:13 | WATTs MOs now created and all material is on hand with SCM at warehouse in ARZ and expectation is for delivery of all material by EOM July with updates to labor to follow
MTCH VA NVA MFD Tektronix Upgrade Deployment POR20 | VA | NVA | MFD | MTC HE - Hub Signaling | MTCH VA NVA MFD MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-08-07 | 2020-08-30 | 2020-09-30 | Active | EP
MTCH VA NVA MFD Tektronix Upgrade Deployment POR20 | VA | NVA | MFD | MTC HE - Hub Signaling | MTCH VA NVA MFD MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-11-15 | 2020-12-15 | 2021-01-15 | Active | Log | New | SN-0575 | True up | Approved | 2020-05-14 17:56 | April True Up and Q2F April material variances due to vDCM material delays from WWT now received
MTCH VA NVA MFD Tektronix Upgrade Deployment POR20 | VA | NVA | MFD | MTC HE - Hub Signaling | MTCH VA NVA MFD MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | Log | Upd | SN-0692 | Schedule Change | Approved | 2020-06-30 11:13 | WATTs MOs now created and all material is on hand with SCM at warehouse in ARZ and expectation is for delivery of all material by EOM July with updates to labor to follow
MTCH VA NVA MFD Tektronix Upgrade Deployment POR20 | VA | NVA | MFD | MTC HE - Hub Signaling | MTCH VA NVA MFD MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-08-07 | 2020-08-30 | 2020-09-30 | Active | Log | Upd | SN-0800 | Schedule Change | Approved | 2020-07-31 14:24 | Distributing funding from topside to regional PPMs after having resolved support cost issue and pushing funding for material that will not be delivered or available to be picked until next week
MTCH VA ROA RON Tektronix Upgrade Deployment POR20 | VA | ROA | RON | MTC HE - Hub Signaling | MTCH VA ROA RON MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-08-07 | 2020-08-30 | 2020-09-30 | Active | EP
MTCH VA ROA RON Tektronix Upgrade Deployment POR20 | VA | ROA | RON | MTC HE - Hub Signaling | MTCH VA ROA RON MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-11-15 | 2020-12-15 | 2021-01-15 | Active | Log | New | SN-0575 | True up | Approved | 2020-05-14 17:56 | April True Up and Q2F April material variances due to vDCM material delays from WWT now received
MTCH VA ROA RON Tektronix Upgrade Deployment POR20 | VA | ROA | RON | MTC HE - Hub Signaling | MTCH VA ROA RON MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-07-15 | 2020-08-30 | 2020-09-30 | Active | Log | Upd | SN-0692 | Schedule Change | Approved | 2020-06-30 11:13 | WATTs MOs now created and all material is on hand with SCM at warehouse in ARZ and expectation is for delivery of all material by EOM July with updates to labor to follow
MTCH VA ROA RON Tektronix Upgrade Deployment POR20 | VA | ROA | RON | MTC HE - Hub Signaling | MTCH VA ROA RON MPEG4 Telestream Upgrade Deployment POR20 | Chassis | Tektronix Sentry | 1 | 2020-08-07 | 2020-08-30 | 2020-09-30 | Active | Log | Upd | SN-0800 | Schedule Change | Approved | 2020-07-31 14:24 | Distributing funding from topside to regional PPMs after having resolved support cost issue and pushing funding for material that will not be delivered or available to be picked until next week
MTCH VA HRD NKT Inca 8VSB Deployment POR19 | VA | HRD | NKT | MTC HE - Hub Signaling | MTCH VA HRD NKT Inca 8VSB Deployment POR19 | Critical Facilities | MTC Hub Signaling | 1 | 2020-10-07 | 2020-10-30 | 2020-11-30 | Active | EP
MTCH VA HRD NKT Inca 8VSB Deployment POR19 | VA | HRD | NKT | MTC HE - Hub Signaling | MTCH VA HRD NKT Inca 8VSB Deployment POR19 | Critical Facilities | MTC Hub Signaling | 1 | 2020-09-06 | 2020-10-31 | 2020-10-31 | Active | Log | New | SN-0779 | Schedule Change | Approved | 2020-07-27 09:27 | Schedule for 5 sites will push out due to resourcing delays and priorities Adding 2019 projects back to POR
MTCH VA HRD NKT Inca 8VSB Deployment POR19 | VA | HRD | NKT | MTC HE - Hub Signaling | MTCH VA HRD NKT Inca 8VSB Deployment POR19 | Critical Facilities | MTC Hub Signaling | 1 | 2020-10-07 | 2020-10-30 | 2020-11-30 | Active | Log | Upd | SN-0970 | Schedule Change | Approved | 2020-10-02 14:50 | Schedule updates for the VA 8VSB Projects requested to accommodate resourcing constraints for both IHL and 3PL
MTCH VA HRD VBC Inca 8VSB Deployment POR19 | VA | HRD | VBC | MTC HE - Hub Signaling | MTCH VA HRD VBC Inca 8VSB Deployment POR19 | Critical Facilities | MTC Hub Signaling | 1 | 2020-10-07 | 2020-10-16 | 2020-11-30 | Active | EP
MTCH VA HRD VBC Inca 8VSB Deployment POR19 | VA | HRD | VBC | MTC HE - Hub Signaling | MTCH VA HRD VBC Inca 8VSB Deployment POR19 | Critical Facilities | MTC Hub Signaling | 1 | 2020-09-06 | 2020-10-31 | 2020-10-31 | Active | Log | New | SN-0779 | Schedule Change | Approved | 2020-07-27 09:27 | Schedule for 5 sites will push out due to resourcing delays and priorities Adding 2019 projects back to POR
MTCH VA HRD VBC Inca 8VSB Deployment POR19 | VA | HRD | VBC | MTC HE - Hub Signaling | MTCH VA HRD VBC Inca 8VSB Deployment POR19 | Critical Facilities | MTC Hub Signaling | 1 | 2020-10-07 | 2020-10-16 | 2020-11-30 | Active | Log | Upd | SN-0970 | Schedule Change | Approved | 2020-10-02 14:50 | Schedule updates for the VA 8VSB Projects requested to accommodate resourcing constraints for both IHL and 3PL
MTCH VA NVA FBG Inca 8VSB Deployment POR19 | VA | NVA | FBG | MTC HE - Hub Signaling | MTCH VA NVA FBG Inca 8VSB Deployment POR19 | Critical Facilities | MTC Hub Signaling |  |  |  |  | Deleted | EP
MTCH VA NVA FBG Inca 8VSB Deployment POR19 | VA | NVA | FBG | MTC HE - Hub Signaling | MTCH VA NVA FBG Inca 8VSB Deployment POR19 | Critical Facilities | MTC Hub Signaling | 1 | 2020-11-06 | 2020-11-30 | 2020-12-31 | Deleted | Log | New | SN-0779 | Schedule Change | Approved | 2020-07-27 09:27 | Schedule for 5 sites will push out due to resourcing delays and priorities Adding 2019 projects back to POR
MTCH VA NVA FBG Inca 8VSB Deployment POR19 | VA | NVA | FBG | MTC HE - Hub Signaling | MTCH VA NVA FBG Inca 8VSB Deployment POR19 | Critical Facilities | MTC Hub Signaling |  |  |  |  | Deleted | Log | Del | SN-0970 | Schedule Change | Approved | 2020-10-02 14:50 | Schedule updates for the VA 8VSB Projects requested to accommodate resourcing constraints for both IHL and 3PL
MTCH VA NVA FST Inca 8VSB Deployment POR19 | VA | NVA | FST | MTC HE - Hub Signaling | MTCH VA NVA FST Inca 8VSB Deployment POR19 | Critical Facilities | MTC Hub Signaling | 1 | 2020-10-07 | 2020-12-11 | 2020-12-11 | Active | EP
MTCH VA NVA FST Inca 8VSB Deployment POR19 | VA | NVA | FST | MTC HE - Hub Signaling | MTCH VA NVA FST Inca 8VSB Deployment POR19 | Critical Facilities | MTC Hub Signaling | 1 | 2020-11-06 | 2020-11-30 | 2020-11-30 | Active | Log | New | SN-0779 | Schedule Change | Approved | 2020-07-27 09:27 | Schedule for 5 sites will push out due to resourcing delays and priorities Adding 2019 projects back to POR
MTCH VA NVA FST Inca 8VSB Deployment POR19 | VA | NVA | FST | MTC HE - Hub Signaling | MTCH VA NVA FST Inca 8VSB Deployment POR19 | Critical Facilities | MTC Hub Signaling | 1 | 2020-10-07 | 2020-12-11 | 2020-12-11 | Active | Log | Upd | SN-0970 | Schedule Change | Approved | 2020-10-02 14:50 | Schedule updates for the VA 8VSB Projects requested to accommodate resourcing constraints for both IHL and 3PL
MTCH VA ROA RON Inca 8VSB Deployment POR19 | VA | ROA | RON | MTC HE - Hub Signaling | MTCH VA ROA RON Inca 8VSB Deployment POR19 | Critical Facilities | MTC Hub Signaling | 1 | 2020-10-07 | 2020-10-16 | 2020-11-30 | Active | EP
MTCH VA ROA RON Inca 8VSB Deployment POR19 | VA | ROA | RON | MTC HE - Hub Signaling | MTCH VA ROA RON Inca 8VSB Deployment POR19 | Critical Facilities | MTC Hub Signaling | 1 | 2020-09-06 | 2020-10-31 | 2020-11-30 | Active | Log | New | SN-0779 | Schedule Change | Approved | 2020-07-27 09:27 | Schedule for 5 sites will push out due to resourcing delays and priorities Adding 2019 projects back to POR
MTCH VA ROA RON Inca 8VSB Deployment POR19 | VA | ROA | RON | MTC HE - Hub Signaling | MTCH VA ROA RON Inca 8VSB Deployment POR19 | Critical Facilities | MTC Hub Signaling | 1 | 2020-10-07 | 2020-10-16 | 2020-11-30 | Active | Log | Upd | SN-0970 | Schedule Change | Approved | 2020-10-02 14:50 | Schedule updates for the VA 8VSB Projects requested to accommodate resourcing constraints for both IHL and 3PL
Testing | COR | COR | ATL | MTC HE - Hub Signaling | Testing Workflow 1 | Critical Facilities | MTC Hub Signaling | 1 | 2020-09-24 | 2020-10-30 | 2020-11-30 | Deleted | EP
Testing | COR | COR | ATL | MTC HE - Hub Signaling | Testing Workflow 1 | Critical Facilities | MTC Hub Signaling | 1 | 2020-09-24 | 2020-10-30 | 2020-11-30 | Deleted | Log | New | SN-0957 | New | Canceled | 2020-09-28 12:18 | TBD TBD TBD TBD
RPHY MRTR-New-AVJ-CIN-RPA-5110 | CA | ORG | AVJ | R PHY | R PHY CA ORG AVJ RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | EP
RPHY MRTR-New-AVJ-CIN-RPA-5110 | CA | ORG | AVJ | R PHY | MRTR CA ORG AVJ 100G Grow Augment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-AVJ-CIN-RPA-5110 | CA | ORG | AVJ | R PHY | R PHY CA ORG AVJ RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-AVJ-CIN-RPA-5110 | CA | ORG | AVJ | R PHY | R PHY CA ORG AVJ RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-AVJ-CIN-RPA-5110 | CA | ORG | AVJ | R PHY | R PHY CA ORG AVJ RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | Upd | SN-0301 | Schedule Change | Approved | 2020-02-24 12:39 | 1 CR 190 while updating RPHY Metro for CA had some errors especially for 3 sites 2 Palos Verdes and Downtown got deleted and Alsio Viejo count got incorrect 3 This was captured in my audit in the team meeting and correcting it 4 Not a financial or P
RPHY MRTR-New-IRV-CIN-RPA-5110 | CA | ORG | IRV | R PHY | R PHY CA ORG IRV RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 3 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | EP
RPHY MRTR-New-IRV-CIN-RPA-5110 | CA | ORG | IRV | R PHY | MRTR CA ORG IRV NCS Augment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-IRV-CIN-RPA-5110 | CA | ORG | IRV | R PHY | R PHY CA ORG IRV RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 3 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-ORG-CIN-RPA-5110 | CA | ORG | ORG | R PHY | R PHY CA ORG ORG RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-New-ORG-CIN-RPA-5110 | CA | ORG | ORG | R PHY | MRTR CA ORG ORG 100G Grow Augment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-ORG-CIN-RPA-5110 | CA | ORG | ORG | R PHY | R PHY CA ORG PAV RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-ORG-CIN-RPA-5110 | CA | ORG | ORG | R PHY | R PHY CA ORG ORG RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-Growth-RSM-CIN-CBR8 Add - Optics Only | CA | ORG | RSM | R PHY | R PHY CA ORG RSM RPHY Metro Deployment POR20 | Card & Optics | CIN-CBR8 Add - Optics Only | 4 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | EP
RPHY MRTR-Growth-RSM-CIN-CBR8 Add - Optics Only | CA | ORG | RSM | R PHY | R PHY CA ORG RSM RPHY Metro Deployment POR20 | Card & Optics | CIN-CBR8 Add - Optics Only | 4 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-RSM-CIN-RPA-5110 | CA | ORG | RSM | R PHY | R PHY CA ORG RSM RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | EP
RPHY MRTR-New-RSM-CIN-RPA-5110 | CA | ORG | RSM | R PHY | MRTR CA ORG RSM Metro Nexus Augment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-RSM-CIN-RPA-5110 | CA | ORG | RSM | R PHY | R PHY CA ORG RSM RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth-CHU-CIN-RPA-5110 | CA | SAN | CHU | R PHY | R PHY CA SAN CHU RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | EP
RPHY MRTR-Growth-CHU-CIN-RPA-5110 | CA | SAN | CHU | R PHY | MRTR CA SAN CHU 100G Grow Augment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-Growth-CHU-CIN-RPA-5110 | CA | SAN | CHU | R PHY | R PHY CA SAN CHU RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth-ELC-CIN-CBR8 Add - Optics Only | CA | SAN | ELC | R PHY | R PHY CA SAN ELC RPHY Metro Deployment POR20 | Card & Optics | CIN-CBR8 Add - Optics Only | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | EP
RPHY MRTR-Growth-ELC-CIN-CBR8 Add - Optics Only | CA | SAN | ELC | R PHY | R PHY CA SAN ELC RPHY Metro Deployment POR20 | Card & Optics | CIN-CBR8 Add - Optics Only | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-ELC-CIN-RPA-5110 | CA | SAN | ELC | R PHY | R PHY CA SAN ELC RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | EP
RPHY MRTR-New-ELC-CIN-RPA-5110 | CA | SAN | ELC | R PHY | MRTR CA SAN ELC 100G Grow Augment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-ELC-CIN-RPA-5110 | CA | SAN | ELC | R PHY | R PHY CA SAN ELC RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-ELC-CIN-RPA-5110 | CA | SAN | ELC | R PHY | R PHY CA SAN ELC RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-ELC-CIN-RPA-5110 | CA | SAN | ELC | R PHY | R PHY CA SAN ELC RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 6 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | New | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-New-ELC-CIN-RPA-5110 | CA | SAN | ELC | R PHY | R PHY CA SAN ELC RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-05-15 | 2020-07-31 | 2020-08-15 | Active | Log | Upd | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-Growth-VST-CIN-CBR8 Add - Optics Only | CA | SAN | VST | R PHY | R PHY CA SAN VST RPHY Metro Augment POR20 | Card & Optics | CIN-CBR8 Add - Optics Only | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | EP
RPHY MRTR-Growth-VST-CIN-CBR8 Add - Optics Only | CA | SAN | VST | R PHY | R PHY CA SAN VST RPHY Metro Augment POR20 | Card & Optics | CIN-CBR8 Add - Optics Only | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-BVL-CIN MGMT-2K | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-BVL-CIN MGMT-2K | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-BVL-CIN-DPA-5200 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-BVL-CIN-DPA-5200 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-BVL-CIN-RPA-5110 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-BVL-CIN-RPA-5110 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-FAY-CIN MGMT-2K | CE | NWA | FAY | R PHY | R PHY CE NWA FAY RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-FAY-CIN MGMT-2K | CE | NWA | FAY | R PHY | MRTR CE NWA FAY OOB Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-FAY-CIN MGMT-2K | CE | NWA | FAY | R PHY | R PHY CE NWA FAY RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-FAY-CIN-DPA-5200 | CE | NWA | FAY | R PHY | R PHY CE NWA FAY RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-FAY-CIN-DPA-5200 | CE | NWA | FAY | R PHY | MRTR CE NWA FAY OOB Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-FAY-CIN-DPA-5200 | CE | NWA | FAY | R PHY | R PHY CE NWA FAY RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-FAY-CIN-RPA-5110 | CE | NWA | FAY | R PHY | R PHY CE NWA FAY RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-FAY-CIN-RPA-5110 | CE | NWA | FAY | R PHY | MRTR CE NWA FAY OOB Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-FAY-CIN-RPA-5110 | CE | NWA | FAY | R PHY | R PHY CE NWA FAY RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-Growth-IND-CIN-CBR8 Add - Optics Only | CE | TUL | IND | R PHY | R PHY CE OKC WLK RPHY Metro Deployment POR20 | Card & Optics | CIN-CBR8 Add - Optics Only |  |  |  |  | Deleted | EP
RPHY MRTR-Growth-IND-CIN-CBR8 Add - Optics Only | CE | TUL | IND | R PHY | R PHY CE OKC WLK RPHY Metro Deployment POR20 | Card & Optics | CIN-CBR8 Add - Optics Only | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Deleted | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth-IND-CIN-CBR8 Add - Optics Only | CE | TUL | IND | R PHY | R PHY CE OKC WLK RPHY Metro Deployment POR20 | Card & Optics | CIN-CBR8 Add - Optics Only |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-IND-CIN-RPA-5110 | CE | TUL | IND | R PHY | R PHY CE OKC WLK RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | EP
RPHY MRTR-New-IND-CIN-RPA-5110 | CE | TUL | IND | R PHY | MRTR CE TUL IND NCS Augment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-IND-CIN-RPA-5110 | CE | TUL | IND | R PHY | R PHY CE OKC WLK RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 17 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Deleted | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-IND-CIN-RPA-5110 | CE | TUL | IND | R PHY | R PHY CE OKC WLK RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 17 | 2019-11-05 | 2020-01-31 | 2020-04-30 | Deleted | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-IND-CIN-RPA-5110 | CE | TUL | IND | R PHY | R PHY CE OKC WLK RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | Log | Del | SN-0606 | Schedule Change | Approved | 2020-05-22 17:33 | 1 The DPA 17 4 change needs to be retained and added to the 18 15 version of node action plan 2 Adding those 3 Small changes in Site Counts for RPA s 4 Equipment Type changes for 2019 Acceleration Sites
RPHY MRTR-New-OKC-CIN MGMT-2K | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-OKC-CIN MGMT-2K | CE | OKC | OKC | R PHY | MRTR CE OKC OKC OOB Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-OKC-CIN MGMT-2K | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-OKC-CIN-DPA-5200 | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-OKC-CIN-DPA-5200 | CE | OKC | OKC | R PHY | MRTR CE OKC OKC OOB Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-OKC-CIN-DPA-5200 | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-OKC-CIN-RPA-5110 | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-OKC-CIN-RPA-5110 | CE | OKC | OKC | R PHY | MRTR CE OKC OKC OOB Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-OKC-CIN-RPA-5110 | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-OWA-CIN MGMT-2K | CE | TUL | OWA | R PHY | R PHY CE TUL OWA RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-OWA-CIN MGMT-2K | CE | TUL | OWA | R PHY | MRTR CE TUL OWA OOB Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-OWA-CIN MGMT-2K | CE | TUL | OWA | R PHY | R PHY CE TUL OWA RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-OWA-CIN-DPA-5200 | CE | TUL | OWA | R PHY | R PHY CE TUL OWA RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-OWA-CIN-DPA-5200 | CE | TUL | OWA | R PHY | MRTR CE TUL OWA OOB Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-OWA-CIN-DPA-5200 | CE | TUL | OWA | R PHY | R PHY CE TUL OWA RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-OWA-CIN-RPA-5110 | CE | TUL | OWA | R PHY | R PHY CE TUL OWA RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-OWA-CIN-RPA-5110 | CE | TUL | OWA | R PHY | MRTR CE TUL OWA OOB Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-OWA-CIN-RPA-5110 | CE | TUL | OWA | R PHY | R PHY CE TUL OWA RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-QNC-CIN MGMT-2K | CE | TUL | QNC | R PHY | R PHY CE TUL QNC RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-QNC-CIN MGMT-2K | CE | TUL | QNC | R PHY | MRTR CE TUL QNC OOB Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-QNC-CIN MGMT-2K | CE | TUL | QNC | R PHY | R PHY CE TUL QNC RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-QNC-CIN-DPA-5200 | CE | TUL | QNC | R PHY | R PHY CE TUL QNC RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-QNC-CIN-DPA-5200 | CE | TUL | QNC | R PHY | MRTR CE TUL QNC OOB Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-QNC-CIN-DPA-5200 | CE | TUL | QNC | R PHY | R PHY CE TUL QNC RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-QNC-CIN-RPA-5110 | CE | TUL | QNC | R PHY | R PHY CE TUL QNC RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-QNC-CIN-RPA-5110 | CE | TUL | QNC | R PHY | MRTR CE TUL QNC OOB Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-QNC-CIN-RPA-5110 | CE | TUL | QNC | R PHY | R PHY CE TUL QNC RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-Growth-SRH-CIN-RPA-5110 | CE | OKC | SRH | R PHY | R PHY CE OKC SRH RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Deleted | EP
RPHY MRTR-Growth-SRH-CIN-RPA-5110 | CE | OKC | SRH | R PHY | MRTR CE OKC SRH OOB Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-Growth-SRH-CIN-RPA-5110 | CE | OKC | SRH | R PHY | R PHY CE OKC SRH RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Deleted | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth-SRH-CIN-RPA-5110 | CE | OKC | SRH | R PHY | R PHY CE OKC SRH RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | Log | Del | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-TUL-CIN MGMT-2K | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-TUL-CIN MGMT-2K | CE | TUL | TUL | R PHY | MRTR CE TUL TUL OOB Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-TUL-CIN MGMT-2K | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-TUL-CIN-DPA-5200 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-TUL-CIN-DPA-5200 | CE | TUL | TUL | R PHY | MRTR CE TUL TUL OOB Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-TUL-CIN-DPA-5200 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-TUL-CIN-RPA-5110 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-TUL-CIN-RPA-5110 | CE | TUL | TUL | R PHY | MRTR CE TUL TUL OOB Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-TUL-CIN-RPA-5110 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-WLK-CIN MGMT-2K | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-WLK-CIN MGMT-2K | CE | OKC | WLK | R PHY | MRTR CE OKC WLK SLR Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-WLK-CIN MGMT-2K | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-WLK-CIN-DPA-5200 | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-WLK-CIN-DPA-5200 | CE | OKC | WLK | R PHY | MRTR CE OKC WLK SLR Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-WLK-CIN-DPA-5200 | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-WLK-CIN-RPA-5110 | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-WLK-CIN-RPA-5110 | CE | OKC | WLK | R PHY | MRTR CE OKC WLK SLR Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-WLK-CIN-RPA-5110 | CE | OKC | WLK | R PHY | R PHY CE OKC WLK RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-YAL-CIN MGMT-2K | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-YAL-CIN MGMT-2K | CE | TUL | YAL | R PHY | MRTR CE TUL YAL OOB Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-YAL-CIN MGMT-2K | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-YAL-CIN-DPA-5200 | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-YAL-CIN-DPA-5200 | CE | TUL | YAL | R PHY | MRTR CE TUL YAL OOB Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-YAL-CIN-DPA-5200 | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-YAL-CIN-RPA-5110 | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-YAL-CIN-RPA-5110 | CE | TUL | YAL | R PHY | MRTR CE TUL YAL OOB Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-YAL-CIN-RPA-5110 | CE | TUL | YAL | R PHY | R PHY CE TUL YAL RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-ELK-CIN MGMT-2K | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-ELK-CIN MGMT-2K | CE | OMA | ELK | R PHY | MRTR CE OMA ELK 100G Grow Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-ELK-CIN MGMT-2K | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-ELK-CIN-DPA-5200 | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-ELK-CIN-DPA-5200 | CE | OMA | ELK | R PHY | MRTR CE OMA ELK 100G Grow Augment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-ELK-CIN-DPA-5200 | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-ELK-CIN-RPA-5110 | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-ELK-CIN-RPA-5110 | CE | OMA | ELK | R PHY | MRTR CE OMA ELK 100G Grow Augment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-ELK-CIN-RPA-5110 | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-PTM-CIN MGMT-2K | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-05-31 |  | Active | EP
RPHY MRTR-New-PTM-CIN MGMT-2K | NE | RHD | PTH | R PHY | MRTR NE RHD PTH 100G Grow Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-PTM-CIN MGMT-2K | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-05-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-PTM-CIN-DPA-5200 | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-05-31 |  | Active | EP
RPHY MRTR-New-PTM-CIN-DPA-5200 | NE | RHD | PTH | R PHY | MRTR NE RHD PTH 100G Grow Augment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-PTM-CIN-DPA-5200 | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-05-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-PTM-CIN-RPA-5110 | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-05-31 |  | Active | EP
RPHY MRTR-New-PTM-CIN-RPA-5110 | NE | RHD | PTH | R PHY | MRTR NE RHD PTH 100G Grow Augment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-PTM-CIN-RPA-5110 | VA | HRD | PTM | R PHY | R PHY VA HRD PTM RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-05-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-BTR-CIN MGMT-2K | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-09-30 |  | Active | EP
RPHY MRTR-New-BTR-CIN MGMT-2K | SE | BTR | BTR | R PHY | MRTR SE BTR BTR SLR Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-BTR-CIN MGMT-2K | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-08-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-BTR-CIN MGMT-2K | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-09-30 |  | Active | Log | Upd | SN-0881 | Schedule Change | Approved | 2020-08-28 10:07 | 1 Moving Pensacola Activation Date from August to September because of Firewall issues 2 Moving BTR dates from August to September because of Resource constraints in with BTR NF team
RPHY MRTR-New-BTR-CIN-DPA-5200 | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-09-30 |  | Active | EP
RPHY MRTR-New-BTR-CIN-DPA-5200 | SE | BTR | BTR | R PHY | MRTR SE BTR BTR SLR Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-BTR-CIN-DPA-5200 | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-08-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-BTR-CIN-DPA-5200 | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-09-30 |  | Active | Log | Upd | SN-0881 | Schedule Change | Approved | 2020-08-28 10:07 | 1 Moving Pensacola Activation Date from August to September because of Firewall issues 2 Moving BTR dates from August to September because of Resource constraints in with BTR NF team
RPHY MRTR-New-BTR-CIN-RPA-5110 | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-09-30 |  | Active | EP
RPHY MRTR-New-BTR-CIN-RPA-5110 | SE | BTR | BTR | R PHY | MRTR SE BTR BTR SLR Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-BTR-CIN-RPA-5110 | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-08-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-BTR-CIN-RPA-5110 | SE | BTR | BTR | R PHY | R PHY SE BTR BTR RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-09-30 |  | Active | Log | Upd | SN-0881 | Schedule Change | Approved | 2020-08-28 10:07 | 1 Moving Pensacola Activation Date from August to September because of Firewall issues 2 Moving BTR dates from August to September because of Resource constraints in with BTR NF team
RPHY MRTR-New-ABV-CIN MGMT-2K | SE | LFY | ABV | R PHY | R PHY SE LFY ABV RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-10-31 | 2020-09-30 | Active | EP
RPHY MRTR-New-ABV-CIN MGMT-2K | SE | LFY | ABV | R PHY | R PHY SE LFY ABV RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-11-30 |  | Active | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-ABV-CIN MGMT-2K | SE | LFY | ABV | R PHY | R PHY SE LFY ABV RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-ABV-CIN MGMT-2K | SE | LFY | ABV | R PHY | R PHY SE LFY ABV RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-10-31 | 2020-09-30 | Active | Log | Upd | SN-0900 | Schedule Change | Approved | 2020-09-11 09:33 | RPHY Metro: POR Update to activation date for 2 sites Abbeville sue to resource constraints and the site was low priority Adjusting date for Forst SMith as well
RPHY MRTR-New-ABV-CIN-DPA-5200 | SE | LFY | ABV | R PHY | R PHY SE LFY ABV RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-10-31 | 2020-09-30 | Active | EP
RPHY MRTR-New-ABV-CIN-DPA-5200 | SE | LFY | ABV | R PHY | R PHY SE LFY ABV RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-11-30 |  | Active | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-ABV-CIN-DPA-5200 | SE | LFY | ABV | R PHY | R PHY SE LFY ABV RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-ABV-CIN-DPA-5200 | SE | LFY | ABV | R PHY | R PHY SE LFY ABV RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-10-31 | 2020-09-30 | Active | Log | Upd | SN-0900 | Schedule Change | Approved | 2020-09-11 09:33 | RPHY Metro: POR Update to activation date for 2 sites Abbeville sue to resource constraints and the site was low priority Adjusting date for Forst SMith as well
RPHY MRTR-New-ABV-CIN-RPA-5110 | SE | LFY | ABV | R PHY | R PHY SE LFY ABV RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-10-31 | 2020-09-30 | Active | EP
RPHY MRTR-New-ABV-CIN-RPA-5110 | SE | LFY | ABV | R PHY | R PHY SE LFY ABV RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-11-30 |  | Active | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-ABV-CIN-RPA-5110 | SE | LFY | ABV | R PHY | R PHY SE LFY ABV RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-ABV-CIN-RPA-5110 | SE | LFY | ABV | R PHY | R PHY SE LFY ABV RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-10-31 | 2020-09-30 | Active | Log | Upd | SN-0900 | Schedule Change | Approved | 2020-09-11 09:33 | RPHY Metro: POR Update to activation date for 2 sites Abbeville sue to resource constraints and the site was low priority Adjusting date for Forst SMith as well
RPHY MRTR-New-LFY-CIN MGMT-2K | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-05-31 |  | Active | EP
RPHY MRTR-New-LFY-CIN MGMT-2K | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-05-31 |  | Active | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-LFY-CIN-DPA-5200 | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-05-31 |  | Active | EP
RPHY MRTR-New-LFY-CIN-DPA-5200 | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-05-31 |  | Active | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-LFY-CIN-RPA-5110 | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-05-31 |  | Active | EP
RPHY MRTR-New-LFY-CIN-RPA-5110 | SE | LFY | LFY | R PHY | R PHY SE LFY LFY RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-05-31 |  | Active | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-LUL-CIN MGMT-2K | SE | NOR | LUL | R PHY | R PHY SE NOR LUL RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-10-31 | 2020-10-31 | Active | EP
RPHY MRTR-New-LUL-CIN MGMT-2K | SE | NOR | LUL | R PHY | R PHY SE NOR LUL RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-11-30 |  | Active | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-LUL-CIN MGMT-2K | SE | NOR | LUL | R PHY | R PHY SE NOR LUL RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-10-31 | 2020-10-31 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-LUL-CIN-DPA-5200 | SE | NOR | LUL | R PHY | R PHY SE NOR LUL RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-10-31 | 2020-10-31 | Active | EP
RPHY MRTR-New-LUL-CIN-DPA-5200 | SE | NOR | LUL | R PHY | R PHY SE NOR LUL RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-11-30 |  | Active | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-LUL-CIN-DPA-5200 | SE | NOR | LUL | R PHY | R PHY SE NOR LUL RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-10-31 | 2020-10-31 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-LUL-CIN-RPA-5110 | SE | NOR | LUL | R PHY | R PHY SE NOR LUL RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-10-31 | 2020-10-31 | Active | EP
RPHY MRTR-New-LUL-CIN-RPA-5110 | SE | NOR | LUL | R PHY | R PHY SE NOR LUL RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-11-30 |  | Active | Log | New | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-LUL-CIN-RPA-5110 | SE | NOR | LUL | R PHY | R PHY SE NOR LUL RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-10-31 | 2020-10-31 | Active | Log | Upd | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
RPHY MRTR-New-MCY-CIN MGMT-2K | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-MCY-CIN MGMT-2K | SE | NOR | MCY | R PHY | MRTR SE NOR MCY 100G Grow Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-MCY-CIN MGMT-2K | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-MCY-CIN-DPA-5200 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-MCY-CIN-DPA-5200 | SE | NOR | MCY | R PHY | MRTR SE NOR MCY 100G Grow Augment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-MCY-CIN-DPA-5200 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-MCY-CIN-RPA-5110 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-MCY-CIN-RPA-5110 | SE | NOR | MCY | R PHY | MRTR SE NOR MCY 100G Grow Augment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-MCY-CIN-RPA-5110 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-Growth-MCY-CIN-RPA-5110 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
RPHY MRTR-Growth-MCY-CIN-RPA-5110 | SE | NOR | MCY | R PHY | MRTR SE NOR MCY 100G Grow Augment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-Growth-MCY-CIN-RPA-5110 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth-MCY-CIN-RPA-5110 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-Growth-BEL-CIN-CBR8 Add - Optics Only | SW | ARZ | BEL | R PHY | R PHY SW ARZ BEL RPHY Metro Augment POR20 | Card & Optics | CIN-CBR8 Add - Optics Only | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | EP
RPHY MRTR-Growth-BEL-CIN-CBR8 Add - Optics Only | SW | ARZ | BEL | R PHY | R PHY SW ARZ BEL RPHY Metro Augment POR20 | Card & Optics | CIN-CBR8 Add - Optics Only | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-PEO-CIN-RPA-5110 | SW | ARZ | PEO | R PHY | R PHY SW ARZ PEO R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
RPHY MRTR-New-PEO-CIN-RPA-5110 | SW | ARZ | PEO | R PHY | R PHY SW ARZ PEO RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-PEO-CIN-RPA-5110 | SW | ARZ | PEO | R PHY | R PHY SW ARZ PEO RPMA RPSD OCML Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Active | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
RPHY MRTR-New-PEO-CIN-RPA-5110 | SW | ARZ | PEO | R PHY | R PHY SW ARZ PEO RPMA RPSD OCML Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Active | Log | Del | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
RPHY MRTR-New-PEO-CIN-RPA-5110 | SW | ARZ | PEO | R PHY | R PHY SW ARZ PEO R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 4 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | New | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-PEO-CIN-RPA-5110 | SW | ARZ | PEO | R PHY | R PHY SW ARZ PEO R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0487 | COVID-19 Related | Approved | 2020-05-12 17:59 | 1 OSNAP other regions not included in Plan Update as it was deferred 2 OMaha West and North to be partially deferred 3 Updated Plan to reflect 18 14
RPHY MRTR-Growth-MSA-CIN-RPA-5110 | SW | ARZ | MSA | R PHY | R PHY SW ARZ MSA RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
RPHY MRTR-Growth-MSA-CIN-RPA-5110 | SW | ARZ | MSA | R PHY | MRTR SW ARZ MSA 100G Grow Augment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-Growth-MSA-CIN-RPA-5110 | SW | ARZ | MSA | R PHY | R PHY SW ARZ MSA RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth-MSA-CIN-RPA-5110 | SW | ARZ | MSA | R PHY | R PHY SW ARZ MSA RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-Growth-BLU-CIN-CBR8 Add - Optics Only | SW | LAS | BLU | R PHY | R PHY SW LAS BLU RPHY Metro Deployment POR20 | Card & Optics | CIN-CBR8 Add - Optics Only | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | EP
RPHY MRTR-Growth-BLU-CIN-CBR8 Add - Optics Only | SW | LAS | BLU | R PHY | R PHY SW LAS BLU RPHY Metro Deployment POR20 | Card & Optics | CIN-CBR8 Add - Optics Only | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-BLU-CIN-RPA-5110 | SW | LAS | BLU | R PHY | R PHY SW LAS BLU R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 7 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
RPHY MRTR-New-BLU-CIN-RPA-5110 | SW | LAS | BLU | R PHY | MRTR SW LAS BLU NCS Augment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-BLU-CIN-RPA-5110 | SW | LAS | BLU | R PHY |  | Chassis | 1x Juniper QFX5110 Chassis | 7 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-BLU-CIN-RPA-5110 | SW | LAS | BLU | R PHY | R PHY SW LAS BLU R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 7 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | New | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-Growth-HEN-CIN-CBR8 Add - Optics Only | SW | LAS | HEN | R PHY | R PHY SW LAS HEN RPHY Metro Deployment POR20 | Card & Optics | CIN-CBR8 Add - Optics Only | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | EP
RPHY MRTR-Growth-HEN-CIN-CBR8 Add - Optics Only | SW | LAS | HEN | R PHY | R PHY SW LAS HEN RPHY Metro Deployment POR20 | Card & Optics | CIN-CBR8 Add - Optics Only | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-HEN-CIN-RPA-5110 | SW | LAS | HEN | R PHY | R PHY SW LAS HEN R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 13 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
RPHY MRTR-New-HEN-CIN-RPA-5110 | SW | LAS | HEN | R PHY | MRTR SW LAS HEN 100G Grow Augment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-HEN-CIN-RPA-5110 | SW | LAS | HEN | R PHY |  | Chassis | 1x Juniper QFX5110 Chassis | 13 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-HEN-CIN-RPA-5110 | SW | LAS | HEN | R PHY | R PHY SW LAS HEN R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 13 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Undel | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-TEN-CIN-DPA-5200 (100G DPIC) | SW | LAS | TEN | R PHY | R PHY SW LAS TEN R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
RPHY MRTR-New-TEN-CIN-DPA-5200 (100G DPIC) | SW | LAS | TEN | R PHY | MRTR SW LAS TEN 100G Grow Augment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-TEN-CIN-DPA-5200 (100G DPIC) | SW | LAS | TEN | R PHY | R PHY SW LAS TEN R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-TEN-CIN-DPA-5200 (100G DPIC) | SW | LAS | TEN | R PHY | R PHY SW LAS TEN R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-NRF-CIN MGMT-2K | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2021-03-31 | 2021-03-31 | Active | EP
RPHY MRTR-New-NRF-CIN MGMT-2K | VA | HRD | NRF | R PHY | MRTR VA HRD NRF 100G Grow Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-NRF-CIN MGMT-2K | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-NRF-CIN MGMT-2K | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2021-03-31 | 2021-03-31 | Active | Log | Upd | SN-0640 | Schedule Change | Approved | 2020-06-06 12:36 | RPHY Metro : POR CHanges based on Field Inputs
RPHY MRTR-New-NRF-CIN-DPA-5200 | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2021-03-31 | 2021-03-31 | Active | EP
RPHY MRTR-New-NRF-CIN-DPA-5200 | VA | HRD | NRF | R PHY | MRTR VA HRD NRF 100G Grow Augment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-NRF-CIN-DPA-5200 | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-NRF-CIN-DPA-5200 | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2021-03-31 | 2021-03-31 | Active | Log | Upd | SN-0640 | Schedule Change | Approved | 2020-06-06 12:36 | RPHY Metro : POR CHanges based on Field Inputs
RPHY MRTR-New-NRF-CIN-RPA-5110 | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2021-03-31 | 2021-03-31 | Active | EP
RPHY MRTR-New-NRF-CIN-RPA-5110 | VA | HRD | NRF | R PHY | MRTR VA HRD NRF 100G Grow Augment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-NRF-CIN-RPA-5110 | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-NRF-CIN-RPA-5110 | VA | HRD | NRF | R PHY | R PHY VA HRD NRF RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2021-03-31 | 2021-03-31 | Active | Log | Upd | SN-0640 | Schedule Change | Approved | 2020-06-06 12:36 | RPHY Metro : POR CHanges based on Field Inputs
RPHY MRTR-Growth-NRF-CIN-RPA-5110 | VA | HRD | NRF | R PHY | R PHY VA HRD NRF R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | EP
RPHY MRTR-Growth-NRF-CIN-RPA-5110 | VA | HRD | NRF | R PHY | MRTR VA HRD NRF 100G Grow Augment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-Growth-NRF-CIN-RPA-5110 | VA | HRD | NRF | R PHY | R PHY VA HRD NRF R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Active | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth-NRF-CIN-RPA-5110 | VA | HRD | NRF | R PHY | R PHY VA HRD NRF R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-01-01 | 2020-03-31 | 2020-06-30 | Active | Log | Upd | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-OCN-CIN MGMT-2K | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-04-30 |  | Active | EP
RPHY MRTR-New-OCN-CIN MGMT-2K | VA | HRD | OCN | R PHY | MRTR VA HRD OCN 100G Grow Augment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-OCN-CIN MGMT-2K | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-04-30 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-OCN-CIN-DPA-5200 | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-04-30 |  | Active | EP
RPHY MRTR-New-OCN-CIN-DPA-5200 | VA | HRD | OCN | R PHY | MRTR VA HRD OCN 100G Grow Augment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-OCN-CIN-DPA-5200 | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-04-30 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-OCN-CIN-RPA-5110 | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-04-30 |  | Active | EP
RPHY MRTR-New-OCN-CIN-RPA-5110 | VA | HRD | OCN | R PHY | MRTR VA HRD OCN 100G Grow Augment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Active | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-OCN-CIN-RPA-5110 | VA | HRD | OCN | R PHY | R PHY VA HRD OCN RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-04-30 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-VBC-CIN-RPA-5110 | VA | HRD | VBC | R PHY | R PHY VA HRD PRA RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 3 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Deleted | EP
RPHY MRTR-New-VBC-CIN-RPA-5110 | VA | HRD | VBC | R PHY | MRTR VA HRD VBC Metro Nexus Augment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | Log | Del | SN-0047 | Schedule Change | Approved | 2020-02-06 10:20
RPHY MRTR-New-VBC-CIN-RPA-5110 | VA | HRD | VBC | R PHY | R PHY VA HRD PRA RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 3 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Deleted | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-VBC-CIN-RPA-5110 | VA | HRD | VBC | R PHY | R PHY VA HRD PRA RPHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Deleted | Log | Del | SN-0190 | Schedule Change | Approved | 2020-01-23 09:42 | 1 Correcting POR to the current plan 2 No Financial changes required at this point 3 It is aligning to what has been submitted
RPHY MRTR-New-PAV-CIN-RPA-5110 | CA | ORG | PAV | R PHY | R PHY CA ORG PAV R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-01-01 | 2020-03-15 | 2020-06-30 | Active | EP
RPHY MRTR-New-PAV-CIN-RPA-5110 | CA | ORG | PAV | R PHY | R PHY CA ORG PAV R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Active | Log | Del | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-New-PAV-CIN-RPA-5110 | CA | ORG | PAV | R PHY | R PHY CA ORG PAV R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-01-01 | 2020-03-15 | 2020-06-30 | Active | Log | Upd | SN-0301 | Schedule Change | Approved | 2020-02-24 12:39 | 1 CR 190 while updating RPHY Metro for CA had some errors especially for 3 sites 2 Palos Verdes and Downtown got deleted and Alsio Viejo count got incorrect 3 This was captured in my audit in the team meeting and correcting it 4 Not a financial or P
RPHY MRTR-Growth-DWN-CIN-RPA-5110 | CA | SAN | DWN | R PHY | R PHY CA SAN DWN R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-01-01 | 2020-03-15 | 2020-06-30 | Active | EP
RPHY MRTR-Growth-DWN-CIN-RPA-5110 | CA | SAN | DWN | R PHY | R PHY CA SAN DWN R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Active | Log | Del | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth-DWN-CIN-RPA-5110 | CA | SAN | DWN | R PHY | R PHY CA SAN DWN R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis | 1 | 2020-01-01 | 2020-03-15 | 2020-06-30 | Active | Log | Upd | SN-0301 | Schedule Change | Approved | 2020-02-24 12:39 | 1 CR 190 while updating RPHY Metro for CA had some errors especially for 3 sites 2 Palos Verdes and Downtown got deleted and Alsio Viejo count got incorrect 3 This was captured in my audit in the team meeting and correcting it 4 Not a financial or P
R PHY_CCAP_FAY_RPHY Bundled Solution V2_43784 | CE | NWA | FAY | R PHY | R PHY CE NWA BVL R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_FAY_RPHY Bundled Solution V2_43784 | CE | NWA | FAY | R PHY | R PHY CE NWA BVL R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_FAY_RPHY Bundled Solution V2_43784 | CE | NWA | FAY | R PHY | R PHY CE NWA BVL R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_BVL_RPHY Bundled Solution V2_43784 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_BVL_RPHY Bundled Solution V2_43784 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_BVL_RPHY Bundled Solution V2_43784 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_BVL_RPHY Bundled Solution V2_43784 | CE | NWA | BVL | R PHY | R PHY CE NWA BVL R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_CLH_RPHY Bundled Solution V2_43784 | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_CLH_RPHY Bundled Solution V2_43784 | CE | OKC | CLH | R PHY | R PHY CE OKC CLH RPHY CCAP Initial Deployment POR19 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
RPHY MRTR-New-BAR-CIN MGMT-2K | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-BAR-CIN MGMT-2K | CE | TUL | BAR | R PHY | R PHY CE OKC BAR R PHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Active | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
RPHY MRTR-New-BAR-CIN MGMT-2K | CE | TUL | BAR | R PHY | R PHY CE OKC BAR R PHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Active | Log | Del | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
RPHY MRTR-New-BAR-CIN MGMT-2K | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-Growth-BAR-CIN-CBR8 Add - Optics Only | CE | TUL | BAR | R PHY | R PHY CE OKC BAR R PHY Metro Deployment POR20 | Card & Optics | CIN-CBR8 Add - Optics Only |  |  |  |  | Deleted | EP
RPHY MRTR-Growth-BAR-CIN-CBR8 Add - Optics Only | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY Metro Deployment POR20 | Card & Optics | CIN-CBR8 Add - Optics Only | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Deleted | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth-BAR-CIN-CBR8 Add - Optics Only | CE | TUL | BAR | R PHY | R PHY CE OKC BAR R PHY Metro Deployment POR20 | Card & Optics | CIN-CBR8 Add - Optics Only |  |  |  |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
RPHY MRTR-Growth-BAR-CIN-CBR8 Add - Optics Only | CE | TUL | BAR | R PHY | R PHY CE OKC BAR R PHY Metro Deployment POR20 | Card & Optics | CIN-CBR8 Add - Optics Only |  |  |  |  | Deleted | Log | Del | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
RPHY MRTR-New-BAR-CIN-DPA-5200 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-BAR-CIN-DPA-5200 | CE | TUL | BAR | R PHY | R PHY CE OKC BAR R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Active | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
RPHY MRTR-New-BAR-CIN-DPA-5200 | CE | TUL | BAR | R PHY | R PHY CE OKC BAR R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Active | Log | Del | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
RPHY MRTR-New-BAR-CIN-DPA-5200 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-BAR-CIN-RPA-5110 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-BAR-CIN-RPA-5110 | CE | TUL | BAR | R PHY | R PHY CE OKC BAR R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Active | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
RPHY MRTR-New-BAR-CIN-RPA-5110 | CE | TUL | BAR | R PHY | R PHY CE OKC BAR R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Active | Log | Del | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
RPHY MRTR-New-BAR-CIN-RPA-5110 | CE | TUL | BAR | R PHY | R PHY CE TUL BAR RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
R PHY_CCAP_BAR_RPHY Bundled Solution V2_43784 | CE | TUL | BAR | R PHY | R PHY CE OKC BAR R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_BAR_RPHY Bundled Solution V2_43784 | CE | TUL | BAR | R PHY | R PHY CE OKC BAR R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_BAR_RPHY Bundled Solution V2_43784 | CE | TUL | BAR | R PHY | R PHY CE OKC BAR R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_BAR_RPHY Bundled Solution V2_43784 | CE | TUL | BAR | R PHY | R PHY CE OKC BAR R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_PTH_RPHY Bundled Solution V2_43784 | NE | RHD | PTH | R PHY | R PHY CE OKC IND R PHY CCAP R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_PTH_RPHY Bundled Solution V2_43784 | NE | RHD | PTH | R PHY | R PHY CE OKC IND R PHY CCAP R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_PTH_RPHY Bundled Solution V2_43784 | NE | RHD | PTH | R PHY | R PHY CE OKC IND R PHY CCAP R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_OKC_RPHY Bundled Solution V2_43784 | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY CCAP Augment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_OKC_RPHY Bundled Solution V2_43784 | CE | OKC | OKC | R PHY | R PHY CE OKC OKC RPHY CCAP Augment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_WLK_RPHY Bundled Solution V2_43784 | CE | OKC | WLK | R PHY | R PHY CE OKC OKC RPHY CCAP Augment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_WLK_RPHY Bundled Solution V2_43784 | CE | OKC | WLK | R PHY | R PHY CE OKC OKC RPHY CCAP Augment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_OWA_RPHY Bundled Solution V2_43784 | CE | TUL | OWA | R PHY | R PHY CE OKC OKC RPHY CCAP Augment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_OWA_RPHY Bundled Solution V2_43784 | CE | TUL | OWA | R PHY | R PHY CE OKC OKC RPHY CCAP Augment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_QNC_RPHY Bundled Solution V2_43784 | CE | TUL | QNC | R PHY | R PHY CE OKC OKC RPHY CCAP Augment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_QNC_RPHY Bundled Solution V2_43784 | CE | TUL | QNC | R PHY | R PHY CE OKC OKC RPHY CCAP Augment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_TUL_RPHY Bundled Solution V2_43784 | CE | TUL | TUL | R PHY | R PHY CE OKC OKC RPHY CCAP Augment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_TUL_RPHY Bundled Solution V2_43784 | CE | TUL | TUL | R PHY | R PHY CE OKC OKC RPHY CCAP Augment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_TUL_RPHY Unbundled Solution V2_43845 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 4 | 2020-01-15 | 2020-02-15 |  | Active | EP
R PHY_CCAP_TUL_RPHY Unbundled Solution V2_43845 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL R PHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 4 | 2020-01-15 | 2020-02-15 |  | Active | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_TUL_RPHY Unbundled Solution V2_43845 | CE | TUL | TUL | R PHY | R PHY CE TUL TUL RPHY CCAP Deployment POR20 | Card & Optics | Cisco cBR-8 Line Card Addition | 4 | 2020-01-15 | 2020-02-15 |  | Active | Log | Upd | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_YAL_RPHY Bundled Solution V2_43784 | CE | TUL | YAL | R PHY | R PHY CE OKC OKC RPHY CCAP Augment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_YAL_RPHY Bundled Solution V2_43784 | CE | TUL | YAL | R PHY | R PHY CE OKC OKC RPHY CCAP Augment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_ELK_RPHY Bundled Solution V2_43784 | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY CCAP Augment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_ELK_RPHY Bundled Solution V2_43784 | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY CCAP Augment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_ELK_RPHY Bundled Solution V2_43784 | CE | OMA | ELK | R PHY | R PHY CE OMA ELK RPHY CCAP Augment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_SOU_RPHY Bundled Solution V2_43784 | CE | OMA | SOU | R PHY | R PHY CE OMA ELK RPHY CCAP Augment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_SOU_RPHY Bundled Solution V2_43784 | CE | OMA | SOU | R PHY | R PHY CE OMA ELK RPHY CCAP Augment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_MCN_Grand_Master_Clocks_44119 | SE | MGA | MCN | R PHY | R PHY SE MGA MCN RPHY CCAP Deployment POR19_1 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_MCN_Grand_Master_Clocks_44119 | SE | MGA | MCN | R PHY | R PHY SE MGA MCN RPHY CCAP Deployment POR19_1 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis |  |  |  |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_LFY_RPHY Bundled Solution V2_43784 | SE | LFY | LFY | R PHY | R PHY SE NOR MCY R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_LFY_RPHY Bundled Solution V2_43784 | SE | LFY | LFY | R PHY | R PHY SE NOR MCY R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0059 | New | Approved | 2020-02-06 10:24
R PHY_CCAP_LFY_RPHY Bundled Solution V2_43784 | SE | LFY | LFY | R PHY | R PHY SE NOR MCY R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 |  | 2020-05-15 |  | Deleted | Log | Upd | SN-0149 | Schedule Change | Approved | 2020-02-06 11:10 | 1 SE RPHY CCAP Plan Change request per field to meet the node action plan 2 Lapalco CBR8 request date changed from July to Sept 3 PNS, LFY, ABV and Luling migration date changes
R PHY_CCAP_LFY_RPHY Bundled Solution V2_43784 | SE | LFY | LFY | R PHY | R PHY SE NOR MCY R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0609 | New | Approved | 2020-05-26 12:14 | RPHY CCAP duplicate projects for ABV and LFY are mapped into RPHY Metro PPMs This CR is to fix the issue and remove the duplicate entries
R PHY_CCAP_ABV_RPHY Bundled Solution V2_43784 | SE | LFY | ABV | R PHY | R PHY SE NOR MCY R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_ABV_RPHY Bundled Solution V2_43784 | SE | LFY | ABV | R PHY | R PHY SE NOR MCY R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0059 | New | Approved | 2020-02-06 10:24
R PHY_CCAP_ABV_RPHY Bundled Solution V2_43784 | SE | LFY | ABV | R PHY | R PHY SE NOR MCY R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 |  | 2020-11-15 |  | Deleted | Log | Upd | SN-0149 | Schedule Change | Approved | 2020-02-06 11:10 | 1 SE RPHY CCAP Plan Change request per field to meet the node action plan 2 Lapalco CBR8 request date changed from July to Sept 3 PNS, LFY, ABV and Luling migration date changes
R PHY_CCAP_ABV_RPHY Bundled Solution V2_43784 | SE | LFY | ABV | R PHY | R PHY SE NOR MCY R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0609 | New | Approved | 2020-05-26 12:14 | RPHY CCAP duplicate projects for ABV and LFY are mapped into RPHY Metro PPMs This CR is to fix the issue and remove the duplicate entries
R PHY_CCAP_BTR_RPHY Bundled Solution V2_43784 | SE | BTR | BTR | R PHY | R PHY SE NOR MCY R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_BTR_RPHY Bundled Solution V2_43784 | SE | BTR | BTR | R PHY | R PHY SE NOR MCY R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0059 | New | Approved | 2020-02-06 10:24
R PHY_CCAP_LUL_RPHY Bundled Solution V2_43784 | SE | NOR | LUL | R PHY | R PHY SE NOR MCY R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_LUL_RPHY Bundled Solution V2_43784 | SE | NOR | LUL | R PHY | R PHY SE NOR MCY R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0059 | New | Approved | 2020-02-06 10:24
R PHY_CCAP_LUL_RPHY Bundled Solution V2_43784 | SE | NOR | LUL | R PHY | R PHY SE NOR MCY R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 |  | 2020-11-15 |  | Deleted | Log | Upd | SN-0149 | Schedule Change | Approved | 2020-02-06 11:10 | 1 SE RPHY CCAP Plan Change request per field to meet the node action plan 2 Lapalco CBR8 request date changed from July to Sept 3 PNS, LFY, ABV and Luling migration date changes
R PHY_CCAP_LUL_RPHY Bundled Solution V2_43784 | SE | NOR | LUL | R PHY | R PHY SE NOR MCY R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0612 | Schedule Change | Approved | 2020-05-29 16:34 | RPHY Metro: POR Updates based on field review
R PHY_CCAP_MCY_RPHY Bundled Solution V2_43784 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_MCY_RPHY Bundled Solution V2_43784 | SE | NOR | MCY | R PHY | R PHY SE NOR MCY R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth-ALI-CIN-CBR8 Add - Optics Only | SW | LAS | ALI | R PHY | R PHY SW LAS ALI QPSK CIN Enablement Augment POR20 | Card & Optics | CIN-CBR8 Add - Optics Only |  |  |  |  | Deleted | EP
RPHY MRTR-Growth-ALI-CIN-CBR8 Add - Optics Only | SW | LAS | ALI | R PHY | R PHY SW LAS ALI RPHY Metro Augment POR20 | Card & Optics | CIN-CBR8 Add - Optics Only | 2 | 2020-01-01 | 2020-03-15 | 2020-03-15 | Deleted | Log | New | SN-0059 | New | Approved | 2020-02-06 10:24
RPHY MRTR-Growth-ALI-CIN-CBR8 Add - Optics Only | SW | LAS | ALI | R PHY | R PHY SW LAS ALI QPSK CIN Enablement Augment POR20 | Card & Optics | CIN-CBR8 Add - Optics Only |  |  |  |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
RPHY MRTR-Growth-ALI-CIN-CBR8 Add - Optics Only | SW | LAS | ALI | R PHY | R PHY SW LAS ALI QPSK CIN Enablement Augment POR20 | Card & Optics | CIN-CBR8 Add - Optics Only |  |  |  |  | Deleted | Log | Del | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_CHS_RPHY Bundled Solution V2_43784 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_CHS_RPHY Bundled Solution V2_43784 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_CHS_RPHY Bundled Solution V2_43784 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
RPHY MRTR-New-CHS-CIN MGMT-2K | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-CHS-CIN MGMT-2K | VA | HRD | CHS | R PHY | R PHY VA HRD CHS R PHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Active | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
RPHY MRTR-New-CHS-CIN MGMT-2K | VA | HRD | CHS | R PHY | R PHY VA HRD CHS R PHY Metro Deployment POR20 | Chassis | 1x Cisco Nexus 2248 Chassis |  |  |  |  | Active | Log | Del | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
RPHY MRTR-New-CHS-CIN MGMT-2K | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY Metro Initial Deployment POR19 | Chassis | 1x Cisco Nexus 2248 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-CHS-CIN-DPA-5200 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-CHS-CIN-DPA-5200 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Active | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
RPHY MRTR-New-CHS-CIN-DPA-5200 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5200 Chassis |  |  |  |  | Active | Log | Del | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
RPHY MRTR-New-CHS-CIN-DPA-5200 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5200 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
RPHY MRTR-New-CHS-CIN-RPA-5110 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | EP
RPHY MRTR-New-CHS-CIN-RPA-5110 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Active | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
RPHY MRTR-New-CHS-CIN-RPA-5110 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS R PHY Metro Deployment POR20 | Chassis | 1x Juniper QFX5110 Chassis |  |  |  |  | Active | Log | Del | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
RPHY MRTR-New-CHS-CIN-RPA-5110 | VA | HRD | CHS | R PHY | R PHY VA HRD CHS RPHY Metro Initial Deployment POR19 | Chassis | 1x Juniper QFX5110 Chassis | 2 | 2019-11-15 | 2020-03-31 |  | Active | Log | Undel | SN-0211 | Schedule Change | Approved | 2020-01-23 09:55 | 1 Adding 2019 Accelerated sites seperately to 2020 Plan
R PHY_CCAP_NRF_RPHY Bundled Solution V2_43784 | VA | HRD | NRF | R PHY | R PHY VA HRD NRF R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_NRF_RPHY Bundled Solution V2_43784 | VA | HRD | NRF | R PHY | R PHY VA HRD NRF R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0059 | New | Approved | 2020-02-06 10:24
R PHY_CCAP_OCN_RPHY Bundled Solution V2_43784 | VA | HRD | OCN | R PHY | R PHY VA HRD OCN R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_OCN_RPHY Bundled Solution V2_43784 | VA | HRD | OCN | R PHY | R PHY VA HRD OCN R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_OCN_RPHY Bundled Solution V2_43784 | VA | HRD | OCN | R PHY | R PHY VA HRD OCN R PHY Metro Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_BLV_RPHY Bundled Solution V3_44119 | CE | OMA | BLV | R PHY | R PHY CE OMA BLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-04-28 | 2020-10-30 | 2020-10-30 | Active | EP
R PHY_CCAP_BLV_RPHY Bundled Solution V3_44119 | CE | OMA | BLV | R PHY | R PHY CE OMA BLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-08-15 | 2020-09-01 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_BLV_RPHY Bundled Solution V3_44119 | CE | OMA | BLV | R PHY | R PHY CE OMA BLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-04-28 | 2020-07-28 | 2020-07-28 | Active | Log | Upd | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_BLV_RPHY Bundled Solution V3_44119 | CE | OMA | BLV | R PHY | R PHY CE OMA BLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-04-28 | 2020-08-31 | 2020-08-31 | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_BLV_RPHY Bundled Solution V3_44119 | CE | OMA | BLV | R PHY | R PHY CE OMA BLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-04-28 | 2020-10-30 | 2020-10-30 | Active | Log | Upd | SN-0613 | Schedule Change | Approved | 2020-05-29 16:19 | RPHY CCAP POR Update
R PHY_CCAP_FTS_Boundary_Clocks_44119 | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-05-15 | 2020-09-30 | 2020-09-30 | Active | EP
R PHY_CCAP_FTS_Boundary_Clocks_44119 | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-10-15 | 2020-11-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_FTS_Boundary_Clocks_44119 | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-05-15 | 2020-08-31 | 2020-08-31 | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_FTS_Boundary_Clocks_44119 | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-05-15 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0613 | Schedule Change | Approved | 2020-05-29 16:19 | RPHY CCAP POR Update
R PHY_CCAP_FTS_Boundary_Clocks_44119 | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-05-15 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0899 | Schedule Change | Approved | 2020-09-11 09:34 | RPHY CCAP actiation date updates for Fort Smith and Abbeville sites Material delivery date update for CLV FTS RSM BLU and HEN facilites
R PHY_CCAP_CLR_RPHY Bundled Solution V3_44119 | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-01-15 | 2020-08-31 |  | Active | EP
R PHY_CCAP_CLR_RPHY Bundled Solution V3_44119 | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-01-15 | 2020-04-01 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_CLR_RPHY Bundled Solution V3_44119 | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-01-15 | 2020-06-15 |  | Active | Log | Upd | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_CLR_RPHY Bundled Solution V3_44119 | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-01-15 | 2020-07-31 |  | Active | Log | Upd | SN-0742 | Schedule Change | Approved | 2020-07-10 10:13 | RPHY CCAP POR Update for Warner Robins and South Pecue facilites
R PHY_CCAP_CLR_RPHY Bundled Solution V3_44119 | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-01-15 | 2020-08-31 |  | Active | Log | Upd | SN-0811 | Schedule Change | Approved | 2020-08-07 09:40 | This is to update RPHY CCAP POR for CLR WRB SAB and PNS sites
R PHY_CCAP_WIC_Boundary_Clocks_44119 | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-05-15 | 2020-10-30 |  | Active | EP
R PHY_CCAP_WIC_Boundary_Clocks_44119 | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-10-15 | 2020-11-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_WIC_Boundary_Clocks_44119 | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-05-15 | 2020-08-30 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_WIC_Boundary_Clocks_44119 | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-05-15 | 2020-10-30 |  | Active | Log | Upd | SN-0613 | Schedule Change | Approved | 2020-05-29 16:19 | RPHY CCAP POR Update
R PHY_CCAP_WIC_Grand_Master_Clocks_44119 | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2020-05-15 | 2020-10-30 |  | Active | EP
R PHY_CCAP_WIC_Grand_Master_Clocks_44119 | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2020-10-15 | 2020-11-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_WIC_Grand_Master_Clocks_44119 | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2020-05-15 | 2020-08-30 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_WIC_Grand_Master_Clocks_44119 | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2020-05-15 | 2020-10-30 |  | Active | Log | Upd | SN-0613 | Schedule Change | Approved | 2020-05-29 16:19 | RPHY CCAP POR Update
R PHY_CCAP_CLV_RPHY Bundled Solution V3_44119 | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_CLV_RPHY Bundled Solution V3_44119 | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_CLV_RPHY Bundled Solution V3_44119 | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_GAR_Boundary_Clocks_44119 | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-07-05 | 2020-11-30 |  | Active | EP
R PHY_CCAP_GAR_Boundary_Clocks_44119 | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-10-15 | 2020-11-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_GAR_Boundary_Clocks_44119 | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-07-05 | 2020-10-15 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_GAR_Boundary_Clocks_44119 | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-07-05 | 2020-11-30 |  | Active | Log | Upd | SN-0613 | Schedule Change | Approved | 2020-05-29 16:19 | RPHY CCAP POR Update
R PHY_CCAP_ELM_RPHY Bundled Solution V3_44119 | SE | NOR | ELM | R PHY | R PHY SE NOR ELM RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_ELM_RPHY Bundled Solution V3_44119 | SE | NOR | ELM | R PHY | R PHY SE NOR ELM RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-04-15 | 2020-07-01 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_ELM_RPHY Bundled Solution V3_44119 | SE | NOR | ELM | R PHY | R PHY SE NOR ELM RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-10-01 | 2020-12-31 |  | Deleted | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_ELM_RPHY Bundled Solution V3_44119 | SE | NOR | ELM | R PHY | R PHY SE NOR ELM RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_FBG_RPHY Bundled Solution V3_44119 | VA | NVA | FBG | R PHY | R PHY VA NVA FBG RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-05-01 | 2020-08-31 |  | Active | EP
R PHY_CCAP_FBG_RPHY Bundled Solution V3_44119 | VA | NVA | FBG | R PHY | R PHY VA NVA FBG RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-07-15 | 2020-10-01 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_FBG_RPHY Bundled Solution V3_44119 | VA | NVA | FBG | R PHY | R PHY VA NVA FBG RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-07-15 | 2020-10-01 |  | Active | Log | New | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_FBG_RPHY Bundled Solution V3_44119 | VA | NVA | FBG | R PHY | R PHY VA NVA FBG RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-05-01 | 2020-08-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_MWC_Boundary_Clocks_44119 | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-05-10 | 2020-11-30 |  | Active | EP
R PHY_CCAP_MWC_Boundary_Clocks_44119 | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-09-15 | 2020-10-01 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_MWC_Boundary_Clocks_44119 | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-05-10 | 2020-08-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_MWC_Boundary_Clocks_44119 | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-05-10 | 2020-11-30 |  | Active | Log | Upd | SN-0613 | Schedule Change | Approved | 2020-05-29 16:19 | RPHY CCAP POR Update
R PHY_CCAP_MWC_D9485_44119 | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-04-15 | 2020-11-30 |  | Active | EP
R PHY_CCAP_MWC_D9485_44119 | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-09-15 | 2020-11-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_MWC_D9485_44119 | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-04-15 | 2020-07-15 |  | Active | Log | Upd | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_MWC_D9485_44119 | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-04-15 | 2020-08-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_MWC_D9485_44119 | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-04-15 | 2020-11-30 |  | Active | Log | Upd | SN-0613 | Schedule Change | Approved | 2020-05-29 16:19 | RPHY CCAP POR Update
R PHY_CCAP_FTS_RPHY Bundled Solution V3_44119 | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-09-18 | 2020-09-30 | 2020-09-30 | Active | EP
R PHY_CCAP_FTS_RPHY Bundled Solution V3_44119 | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-10-15 | 2020-11-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_FTS_RPHY Bundled Solution V3_44119 | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-06-15 | 2020-09-15 | 2020-09-15 | Active | Log | Upd | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_FTS_RPHY Bundled Solution V3_44119 | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-06-15 | 2020-08-31 | 2020-08-31 | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_FTS_RPHY Bundled Solution V3_44119 | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-06-15 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0613 | Schedule Change | Approved | 2020-05-29 16:19 | RPHY CCAP POR Update
R PHY_CCAP_FTS_RPHY Bundled Solution V3_44119 | CE | NWA | FTS | R PHY | R PHY CE NWA FTS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-09-18 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0899 | Schedule Change | Approved | 2020-09-11 09:34 | RPHY CCAP actiation date updates for Fort Smith and Abbeville sites Material delivery date update for CLV FTS RSM BLU and HEN facilites
R PHY_CCAP_NEH_Boundary_Clocks_44119 | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-10-05 | 2020-12-31 |  | Active | EP
R PHY_CCAP_NEH_Boundary_Clocks_44119 | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-08-15 | 2020-11-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_NEH_Boundary_Clocks_44119 | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-10-05 | 2020-12-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_NEH_D9485_44119 | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_NEH_D9485_44119 | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-08-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_NEH_D9485_44119 | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_GAR_RPHY Bundled Solution V3_44119 | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-07-15 | 2020-11-30 | 2020-11-30 | Active | EP
R PHY_CCAP_GAR_RPHY Bundled Solution V3_44119 | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-10-15 | 2020-11-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_GAR_RPHY Bundled Solution V3_44119 | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-07-15 | 2020-10-15 | 2020-10-15 | Active | Log | Upd | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_GAR_RPHY Bundled Solution V3_44119 | CE | TUL | GAR | R PHY | R PHY CE TUL GAR RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-07-15 | 2020-11-30 | 2020-11-30 | Active | Log | Upd | SN-0613 | Schedule Change | Approved | 2020-05-29 16:19 | RPHY CCAP POR Update
R PHY_CCAP_WEH_Boundary_Clocks_44119 | CE | OKC | WEH | R PHY | R PHY CE OKC WEH RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_WEH_Boundary_Clocks_44119 | CE | OKC | WEH | R PHY | R PHY CE OKC WEH RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis |  |  |  |  | Deleted | Log | Del | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_WEH_D9485_44119 | CE | OKC | WEH | R PHY | R PHY CE OKC WEH RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_WEH_D9485_44119 | CE | OKC | WEH | R PHY | R PHY CE OKC WEH RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | Log | Del | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_BLV_Boundary_Clocks_44119 | CE | OMA | BLV | R PHY | R PHY CE OMA BLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-04-15 | 2020-10-30 |  | Active | EP
R PHY_CCAP_BLV_Boundary_Clocks_44119 | CE | OMA | BLV | R PHY | R PHY CE OMA BLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-08-15 | 2020-09-01 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_BLV_Boundary_Clocks_44119 | CE | OMA | BLV | R PHY | R PHY CE OMA BLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-04-15 | 2020-08-15 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_BLV_Boundary_Clocks_44119 | CE | OMA | BLV | R PHY | R PHY CE OMA BLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-04-15 | 2020-10-30 |  | Active | Log | Upd | SN-0613 | Schedule Change | Approved | 2020-05-29 16:19 | RPHY CCAP POR Update
R PHY_CCAP_ONA_Boundary_Clocks_44119 | CE | OMA | ONA | R PHY | R PHY CE OMA ONA RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_ONA_Boundary_Clocks_44119 | CE | OMA | ONA | R PHY | R PHY CE OMA ONA RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_ONA_Boundary_Clocks_44119 | CE | OMA | ONA | R PHY | R PHY CE OMA ONA RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_KNN_RPHY Bundled Solution V3_44119 | SE | NOR | KNN | R PHY | R PHY SE NOR KNN RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_KNN_RPHY Bundled Solution V3_44119 | SE | NOR | KNN | R PHY | R PHY SE NOR KNN RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-04-15 | 2020-07-01 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_KNN_RPHY Bundled Solution V3_44119 | SE | NOR | KNN | R PHY | R PHY SE NOR KNN RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-04-15 | 2020-08-31 |  | Deleted | Log | Upd | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_KNN_RPHY Bundled Solution V3_44119 | SE | NOR | KNN | R PHY | R PHY SE NOR KNN RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_WES_Boundary_Clocks_44119 | CE | OMA | WES | R PHY | R PHY CE OMA WES RPHY - CCAP Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_WES_Boundary_Clocks_44119 | CE | OMA | WES | R PHY | R PHY CE OMA WES RPHY - CCAP Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-09-15 | 2020-10-01 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_WES_Boundary_Clocks_44119 | CE | OMA | WES | R PHY | R PHY CE OMA WES RPHY - CCAP Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_LPL_RPHY Bundled Solution V3_44119 | SE | NOR | LPL | R PHY | R PHY SE NOR LPL RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_LPL_RPHY Bundled Solution V3_44119 | SE | NOR | LPL | R PHY | R PHY SE NOR LPL RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-07-01 | 2020-11-01 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_LPL_RPHY Bundled Solution V3_44119 | SE | NOR | LPL | R PHY | R PHY SE NOR LPL RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-09-01 | 2020-12-31 |  | Deleted | Log | Upd | SN-0149 | Schedule Change | Approved | 2020-02-06 11:10 | 1 SE RPHY CCAP Plan Change request per field to meet the node action plan 2 Lapalco CBR8 request date changed from July to Sept 3 PNS, LFY, ABV and Luling migration date changes
R PHY_CCAP_LPL_RPHY Bundled Solution V3_44119 | SE | NOR | LPL | R PHY | R PHY SE NOR LPL RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-09-01 | 2020-11-30 |  | Deleted | Log | Upd | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_LPL_RPHY Bundled Solution V3_44119 | SE | NOR | LPL | R PHY | R PHY SE NOR LPL RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_CLV_Boundary_Clocks_44119 | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-07-15 | 2020-12-31 |  | Active | EP
R PHY_CCAP_CLV_Boundary_Clocks_44119 | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-10-15 | 2020-11-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_CLV_Boundary_Clocks_44119 | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-07-15 | 2020-08-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_CLV_Boundary_Clocks_44119 | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-07-15 | 2020-10-15 |  | Active | Log | Upd | SN-0637 | Schedule Change | Approved | 2020-06-05 14:50 | RPHY CCAP POR Update
R PHY_CCAP_CLV_Boundary_Clocks_44119 | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-07-15 | 2020-12-31 |  | Active | Log | Upd | SN-0843 | Schedule Change | Approved | 2020-08-15 10:44 | This is to update Activation date for Cleveland
R PHY_CCAP_CLV_D9485_44119 | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_CLV_D9485_44119 | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_CLV_D9485_44119 | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_CLV_Grand_Master_Clocks_44119 | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2020-07-15 | 2020-12-31 |  | Active | EP
R PHY_CCAP_CLV_Grand_Master_Clocks_44119 | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2020-10-15 | 2020-11-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_CLV_Grand_Master_Clocks_44119 | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2020-07-15 | 2020-08-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_CLV_Grand_Master_Clocks_44119 | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2020-07-15 | 2020-10-15 |  | Active | Log | Upd | SN-0637 | Schedule Change | Approved | 2020-06-05 14:50 | RPHY CCAP POR Update
R PHY_CCAP_CLV_Grand_Master_Clocks_44119 | NE | CLE | CLV | R PHY | R PHY NE CLE CLV RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 1 | 2020-07-15 | 2020-12-31 |  | Active | Log | Upd | SN-0843 | Schedule Change | Approved | 2020-08-15 10:44 | This is to update Activation date for Cleveland
R PHY_CCAP_LTF_RPHY Bundled Solution V3_44119 | VA | HRD | LTF | R PHY | R PHY VA HRD LTF RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-04-28 | 2020-07-31 |  | Active | EP
R PHY_CCAP_LTF_RPHY Bundled Solution V3_44119 | VA | HRD | LTF | R PHY | R PHY VA HRD LTF RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-08-15 | 2020-11-01 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_LTF_RPHY Bundled Solution V3_44119 | VA | HRD | LTF | R PHY | R PHY VA HRD LTF RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-08-15 | 2020-11-01 |  | Active | Log | New | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_LTF_RPHY Bundled Solution V3_44119 | VA | HRD | LTF | R PHY | R PHY VA HRD LTF RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-04-28 | 2020-07-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_CLR_Boundary_Clocks_44119 | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-01-15 | 2020-08-31 |  | Active | EP
R PHY_CCAP_CLR_Boundary_Clocks_44119 | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-01-15 | 2020-04-01 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_CLR_Boundary_Clocks_44119 | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-01-15 | 2020-06-15 |  | Active | Log | Upd | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_CLR_Boundary_Clocks_44119 | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-01-15 | 2020-07-31 |  | Active | Log | Upd | SN-0742 | Schedule Change | Approved | 2020-07-10 10:13 | RPHY CCAP POR Update for Warner Robins and South Pecue facilites
R PHY_CCAP_CLR_Boundary_Clocks_44119 | SE | NOR | CLR | R PHY | R PHY SE NOR CLR RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-01-15 | 2020-08-31 |  | Active | Log | Upd | SN-0811 | Schedule Change | Approved | 2020-08-07 09:40 | This is to update RPHY CCAP POR for CLR WRB SAB and PNS sites
R PHY_CCAP_MWC_RPHY Bundled Solution V3_44119 | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-04-28 | 2020-11-30 | 2020-11-30 | Active | EP
R PHY_CCAP_MWC_RPHY Bundled Solution V3_44119 | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-09-15 | 2020-11-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_MWC_RPHY Bundled Solution V3_44119 | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-04-28 | 2020-07-28 | 2020-07-28 | Active | Log | Upd | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_MWC_RPHY Bundled Solution V3_44119 | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-04-28 | 2020-08-31 | 2020-08-31 | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_MWC_RPHY Bundled Solution V3_44119 | CE | OKC | MWC | R PHY | R PHY CE OKC MWC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-04-28 | 2020-11-30 | 2020-11-30 | Active | Log | Upd | SN-0613 | Schedule Change | Approved | 2020-05-29 16:19 | RPHY CCAP POR Update
R PHY_CCAP_ELM_Boundary_Clocks_44119 | SE | NOR | ELM | R PHY | R PHY SE NOR ELM RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_ELM_Boundary_Clocks_44119 | SE | NOR | ELM | R PHY | R PHY SE NOR ELM RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-04-15 | 2020-07-01 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_ELM_Boundary_Clocks_44119 | SE | NOR | ELM | R PHY | R PHY SE NOR ELM RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-10-01 | 2020-12-31 |  | Deleted | Log | Upd | SN-0217 | Schedule Change | Approved | 2020-02-03 16:50 | RPHY CCAP Q2 POR Correction
R PHY_CCAP_ELM_Boundary_Clocks_44119 | SE | NOR | ELM | R PHY | R PHY SE NOR ELM RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis |  |  |  |  | Deleted | Log | Del | SN-0602 | Schedule Change | Approved | 2020-05-20 16:51 | RPHY CCAP POR Update
R PHY_CCAP_NEH_RPHY Bundled Solution V3_44119 | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_NEH_RPHY Bundled Solution V3_44119 | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-08-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_NEH_RPHY Bundled Solution V3_44119 | CE | OKC | NEH | R PHY | R PHY CE OKC NEH RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_KNN_Boundary_Clocks_44119 | SE | NOR | KNN | R PHY | R PHY SE NOR KNN RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_KNN_Boundary_Clocks_44119 | SE | NOR | KNN | R PHY | R PHY SE NOR KNN RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-04-15 | 2020-07-01 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_KNN_Boundary_Clocks_44119 | SE | NOR | KNN | R PHY | R PHY SE NOR KNN RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-04-15 | 2020-08-31 |  | Deleted | Log | Upd | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_KNN_Boundary_Clocks_44119 | SE | NOR | KNN | R PHY | R PHY SE NOR KNN RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis |  |  |  |  | Deleted | Log | Del | SN-0602 | Schedule Change | Approved | 2020-05-20 16:51 | RPHY CCAP POR Update
R PHY_CCAP_ONA_RPHY Bundled Solution V3_44119 | CE | OMA | ONA | R PHY | R PHY CE OMA ONA RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_ONA_RPHY Bundled Solution V3_44119 | CE | OMA | ONA | R PHY | R PHY CE OMA ONA RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-10-15 | 2020-11-15 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_ONA_RPHY Bundled Solution V3_44119 | CE | OMA | ONA | R PHY | R PHY CE OMA ONA RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_LPL_Boundary_Clocks_44119 | SE | NOR | LPL | R PHY | R PHY SE NOR LPL RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_LPL_Boundary_Clocks_44119 | SE | NOR | LPL | R PHY | R PHY SE NOR LPL RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-07-01 | 2020-11-01 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_LPL_Boundary_Clocks_44119 | SE | NOR | LPL | R PHY | R PHY SE NOR LPL RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-09-01 | 2020-12-31 |  | Deleted | Log | Upd | SN-0149 | Schedule Change | Approved | 2020-02-06 11:10 | 1 SE RPHY CCAP Plan Change request per field to meet the node action plan 2 Lapalco CBR8 request date changed from July to Sept 3 PNS, LFY, ABV and Luling migration date changes
R PHY_CCAP_LPL_Boundary_Clocks_44119 | SE | NOR | LPL | R PHY | R PHY SE NOR LPL RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-09-01 | 2020-11-30 |  | Deleted | Log | Upd | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_LPL_Boundary_Clocks_44119 | SE | NOR | LPL | R PHY | R PHY SE NOR LPL RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis |  |  |  |  | Deleted | Log | Del | SN-0602 | Schedule Change | Approved | 2020-05-20 16:51 | RPHY CCAP POR Update
R PHY_CCAP_SPC_Boundary_Clocks_44119 | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-03-05 | 2020-07-31 | 2020-07-31 | Active | EP
R PHY_CCAP_SPC_Boundary_Clocks_44119 | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-07-01 | 2020-09-01 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_SPC_Boundary_Clocks_44119 | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-03-05 | 2020-04-30 |  | Active | Log | Upd | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_SPC_Boundary_Clocks_44119 | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-03-05 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_SPC_Boundary_Clocks_44119 | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-03-05 | 2020-07-31 | 2020-07-31 | Active | Log | Upd | SN-0742 | Schedule Change | Approved | 2020-07-10 10:13 | RPHY CCAP POR Update for Warner Robins and South Pecue facilites
R PHY_CCAP_PNS_Boundary_Clocks_44119 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-01-16 | 2020-09-30 |  | Active | EP
R PHY_CCAP_PNS_Boundary_Clocks_44119 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-01-15 | 2020-04-01 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_PNS_Boundary_Clocks_44119 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 |  | 2020-05-31 |  | Active | Log | Upd | SN-0149 | Schedule Change | Approved | 2020-02-06 11:10 | 1 SE RPHY CCAP Plan Change request per field to meet the node action plan 2 Lapalco CBR8 request date changed from July to Sept 3 PNS, LFY, ABV and Luling migration date changes
R PHY_CCAP_PNS_Boundary_Clocks_44119 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-01-15 | 2020-05-31 |  | Active | Log | Upd | SN-0191 | Schedule Change | Approved | 2020-01-17 09:24 | Minor POR Update Updating the missing receipt date in POR for one facility
R PHY_CCAP_PNS_Boundary_Clocks_44119 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-01-16 | 2020-07-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_PNS_Boundary_Clocks_44119 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-01-16 | 2020-08-31 |  | Active | Log | Upd | SN-0811 | Schedule Change | Approved | 2020-08-07 09:40 | This is to update RPHY CCAP POR for CLR WRB SAB and PNS sites
R PHY_CCAP_PNS_Boundary_Clocks_44119 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-01-16 | 2020-09-30 |  | Active | Log | Upd | SN-0879 | Schedule Change | Approved | 2020-08-28 10:07 | RPHY CCAP POR Update for Roanoke Baton Rouge and Pensacola
R PHY_CCAP_PNS_D9485_44119 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-03-15 | 2020-09-30 |  | Active | EP
R PHY_CCAP_PNS_D9485_44119 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-01-15 | 2020-04-01 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_PNS_D9485_44119 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 |  | 2020-05-31 |  | Active | Log | Upd | SN-0149 | Schedule Change | Approved | 2020-02-06 11:10 | 1 SE RPHY CCAP Plan Change request per field to meet the node action plan 2 Lapalco CBR8 request date changed from July to Sept 3 PNS, LFY, ABV and Luling migration date changes
R PHY_CCAP_PNS_D9485_44119 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-01-15 | 2020-05-31 |  | Active | Log | Upd | SN-0191 | Schedule Change | Approved | 2020-01-17 09:24 | Minor POR Update Updating the missing receipt date in POR for one facility
R PHY_CCAP_PNS_D9485_44119 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-03-15 | 2020-06-30 |  | Active | Log | Upd | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PNS_D9485_44119 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-03-15 | 2020-07-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_PNS_D9485_44119 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-03-15 | 2020-08-31 |  | Active | Log | Upd | SN-0811 | Schedule Change | Approved | 2020-08-07 09:40 | This is to update RPHY CCAP POR for CLR WRB SAB and PNS sites
R PHY_CCAP_PNS_D9485_44119 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-03-15 | 2020-09-30 |  | Active | Log | Upd | SN-0879 | Schedule Change | Approved | 2020-08-28 10:07 | RPHY CCAP POR Update for Roanoke Baton Rouge and Pensacola
R PHY_CCAP_WRB_Boundary_Clocks_44119 | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-04-15 | 2020-09-30 |  | Active | EP
R PHY_CCAP_WRB_Boundary_Clocks_44119 | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-07-01 | 2020-09-01 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_WRB_Boundary_Clocks_44119 | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-07-01 | 2020-08-31 |  | Active | Log | Upd | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_WRB_Boundary_Clocks_44119 | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-04-15 | 2020-08-31 |  | Active | Log | Upd | SN-0263 | Schedule Change | Approved | 2020-02-21 16:27 | Requesting Santa Barabara and Warner Robins to be accelerated into Q2 due to the following reasons Santa Barbara - To move the nodes from existing 10Ks to RPHY to alleviate the node conjestion Warner Robins - This is to get the site RPHY Ready for the
R PHY_CCAP_WRB_Boundary_Clocks_44119 | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-04-15 | 2020-07-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_WRB_Boundary_Clocks_44119 | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-04-15 | 2020-08-31 |  | Active | Log | Upd | SN-0742 | Schedule Change | Approved | 2020-07-10 10:13 | RPHY CCAP POR Update for Warner Robins and South Pecue facilites
R PHY_CCAP_WRB_Boundary_Clocks_44119 | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-04-15 | 2020-09-30 |  | Active | Log | Upd | SN-0811 | Schedule Change | Approved | 2020-08-07 09:40 | This is to update RPHY CCAP POR for CLR WRB SAB and PNS sites
R PHY_CCAP_PNS_RPHY Bundled Solution V3_44119 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-01-07 | 2020-09-30 | 2020-09-30 | Active | EP
R PHY_CCAP_PNS_RPHY Bundled Solution V3_44119 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-01-15 | 2020-04-01 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_PNS_RPHY Bundled Solution V3_44119 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 |  | 2020-05-31 |  | Active | Log | Upd | SN-0149 | Schedule Change | Approved | 2020-02-06 11:10 | 1 SE RPHY CCAP Plan Change request per field to meet the node action plan 2 Lapalco CBR8 request date changed from July to Sept 3 PNS, LFY, ABV and Luling migration date changes
R PHY_CCAP_PNS_RPHY Bundled Solution V3_44119 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-01-15 | 2020-05-31 |  | Active | Log | Upd | SN-0191 | Schedule Change | Approved | 2020-01-17 09:24 | Minor POR Update Updating the missing receipt date in POR for one facility
R PHY_CCAP_PNS_RPHY Bundled Solution V3_44119 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-01-07 | 2020-05-31 | 2020-05-31 | Active | Log | New | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_PNS_RPHY Bundled Solution V3_44119 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-01-07 | 2020-07-31 | 2020-07-31 | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_PNS_RPHY Bundled Solution V3_44119 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-01-07 | 2020-08-31 | 2020-08-31 | Active | Log | Upd | SN-0811 | Schedule Change | Approved | 2020-08-07 09:40 | This is to update RPHY CCAP POR for CLR WRB SAB and PNS sites
R PHY_CCAP_PNS_RPHY Bundled Solution V3_44119 | SE | GCT | PNS | R PHY | R PHY SE GCT PNS RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-01-07 | 2020-09-30 | 2020-09-30 | Active | Log | Upd | SN-0879 | Schedule Change | Approved | 2020-08-28 10:07 | RPHY CCAP POR Update for Roanoke Baton Rouge and Pensacola
R PHY_CCAP_SPC_RPHY Bundled Solution V3_44119 | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-03-05 | 2020-07-31 | 2020-07-31 | Active | EP
R PHY_CCAP_SPC_RPHY Bundled Solution V3_44119 | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-07-01 | 2020-09-01 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_SPC_RPHY Bundled Solution V3_44119 | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-03-05 | 2020-04-30 |  | Active | Log | Upd | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR
R PHY_CCAP_SPC_RPHY Bundled Solution V3_44119 | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-03-05 | 2020-06-30 | 2020-06-30 | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_SPC_RPHY Bundled Solution V3_44119 | SE | BTR | SPC | R PHY | R PHY SE BTR SPC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-03-05 | 2020-07-31 | 2020-07-31 | Active | Log | Upd | SN-0742 | Schedule Change | Approved | 2020-07-10 10:13 | RPHY CCAP POR Update for Warner Robins and South Pecue facilites
R PHY_CCAP_WEH_RPHY Bundled Solution V3_44119 | CE | OKC | WEH | R PHY | R PHY CE OKC WEH RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_WEH_RPHY Bundled Solution V3_44119 | CE | OKC | WEH | R PHY | R PHY CE OKC WEH RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_WES_RPHY Bundled Solution V3_44119 | CE | OMA | WES | R PHY | R PHY CE OMA WES RPHY - CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | EP
R PHY_CCAP_WES_RPHY Bundled Solution V3_44119 | CE | OMA | WES | R PHY | R PHY CE OMA WES RPHY - CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-09-15 | 2020-10-01 |  | Deleted | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_WES_RPHY Bundled Solution V3_44119 | CE | OMA | WES | R PHY | R PHY CE OMA WES RPHY - CCAP Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis |  |  |  |  | Deleted | Log | Del | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_LTF_Boundary_Clocks_44119 | VA | HRD | LTF | R PHY | R PHY VA HRD LTF RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-05-31 | 2020-07-31 |  | Active | EP
R PHY_CCAP_LTF_Boundary_Clocks_44119 | VA | HRD | LTF | R PHY | R PHY VA HRD LTF RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-08-15 | 2020-11-01 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_LTF_Boundary_Clocks_44119 | VA | HRD | LTF | R PHY | R PHY VA HRD LTF RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-08-15 | 2020-11-01 |  | Active | Log | New | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_LTF_Boundary_Clocks_44119 | VA | HRD | LTF | R PHY | R PHY VA HRD LTF RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-05-31 | 2020-07-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_WIC_RPHY Bundled Solution V3_44119 | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-05-26 | 2020-10-30 | 2020-10-30 | Active | EP
R PHY_CCAP_WIC_RPHY Bundled Solution V3_44119 | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-10-15 | 2020-11-15 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_WIC_RPHY Bundled Solution V3_44119 | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-05-26 | 2020-08-30 | 2020-08-30 | Active | Log | Upd | SN-0550 | COVID-19 Related | Approved | 2020-05-12 17:59 | This is to update RPHY CCAP POR to reflect the latest 18 14 based plan 2020 Deferrals and revised Q3 and Q4 plan This also reflects Cisco QPSK plan changes
R PHY_CCAP_WIC_RPHY Bundled Solution V3_44119 | CE | KAN | WIC | R PHY | R PHY CE KAN WIC RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-05-26 | 2020-10-30 | 2020-10-30 | Active | Log | Upd | SN-0613 | Schedule Change | Approved | 2020-05-29 16:19 | RPHY CCAP POR Update
R PHY_CCAP_FBG_Boundary_Clocks_44119 | VA | NVA | FBG | R PHY | R PHY VA NVA FBG RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-05-15 | 2020-08-31 |  | Active | EP
R PHY_CCAP_FBG_Boundary_Clocks_44119 | VA | NVA | FBG | R PHY | R PHY VA NVA FBG RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-07-15 | 2020-10-01 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_FBG_Boundary_Clocks_44119 | VA | NVA | FBG | R PHY | R PHY VA NVA FBG RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-07-15 | 2020-10-01 |  | Active | Log | New | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_FBG_Boundary_Clocks_44119 | VA | NVA | FBG | R PHY | R PHY VA NVA FBG RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Adva OSA 5420 PTP Clock Chassis | 2 | 2020-05-15 | 2020-08-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_FBG_D9485_44119 | VA | NVA | FBG | R PHY | R PHY VA NVA FBG RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-05-01 | 2020-08-31 |  | Active | EP
R PHY_CCAP_FBG_D9485_44119 | VA | NVA | FBG | R PHY | R PHY VA NVA FBG RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-07-15 | 2020-10-01 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_FBG_D9485_44119 | VA | NVA | FBG | R PHY | R PHY VA NVA FBG RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-07-15 | 2020-10-01 |  | Active | Log | New | SN-0097 | Schedule Change | Approved | 2020-02-06 10:36 | RPHY CCAP POR Correction
R PHY_CCAP_FBG_D9485_44119 | VA | NVA | FBG | R PHY | R PHY VA NVA FBG RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco D9485 QPSK Bridge Chassis | 1 | 2020-05-01 | 2020-08-31 |  | Active | Log | Upd | SN-0605 | Schedule Change | Approved | 2020-05-22 17:33 | RPHY CCAP POR Update
R PHY_CCAP_WRB_RPHY Bundled Solution V3_44119 | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-07-10 | 2020-09-30 | 2020-09-30 | Active | EP
R PHY_CCAP_WRB_RPHY Bundled Solution V3_44119 | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-07-01 | 2020-09-01 |  | Active | Log | New | SN-0060 | New | Approved | 2020-02-06 10:24 | RPHY CCAP POR CORRECTION
R PHY_CCAP_WRB_RPHY Bundled Solution V3_44119 | SE | MGA | WRB | R PHY | R PHY SE MGA WRB RPHY - CCAP Initial Deployment POR20 | Chassis | 1x Cisco cBR-8 Chassis | 1 | 2020-07-01 | 2020-08-31 |  | Active | Log | Upd | SN-0208 | Schedule Change | Approved | 2020-01-24 14:42 | 2019 Accelerated projects are not showing up in POR This CR is to add those projects again to 2020 POR